## Project Structure
Folder Structure |  |  |  | Checklists | #NAME?
Site QA
Inground services
External ducting - Harvey Norman
|  |  | Mains incoming ducts | Inground services
|  |  | Pits | Inground services
|  |  | Ducting from pit to Tx | Inground services
|  |  | Pole light | Inground services
|  |  | Sign | Inground services
|  |  | Telecome incoming sleeve | Inground services
External ducting - Tenancy X
|  |  | Mains incoming ducts | Inground services
|  |  | Pole light | Inground services
|  |  | Telecome incoming sleeve | Inground services
|  |  | Pits | Inground services
|  |  | Ducting from pit to Tx | Inground services
Cable Tray
Harvey Norman
|  |  | Electrical | Cable Tray
|  |  | Furniture | Cable Tray
|  |  | Bedding | Cable Tray
|  |  | BOH | Cable Tray
Switchboard's
Harvey Norman
|  |  | Main Switchboard | Switchboards
|  |  | Electrical DB | Switchboards
|  |  | DB3 | Switchboards
|  |  | DB2 | Switchboards
|  |  | DB4 | Switchboards
Tenancy X
|  |  | MSB | Switchboards
First Fix
Harvey Norman
|  |  | Mains | First Fix Electrical
|  |  | Main Earth | First Fix Electrical
|  |  | sub mains Electrical DB | First Fix Electrical
|  |  | sub mains DB3 | First Fix Electrical
|  |  | sub mains DB2 | First Fix Electrical
|  |  | sub mains DB4 | First Fix Electrical
|  |  | MSB | First Fix Electrical
|  |  | Bedding | First Fix Electrical
|  |  | Furniture | First Fix Electrical
|  |  | Electrical | First Fix Electrical
|  |  | Inwards goods | First Fix Electrical
|  |  | lunch room | First Fix Electrical
|  |  | toilets | First Fix Electrical
|  |  | hallway | First Fix Electrical
|  |  | upstairs offices | First Fix Electrical
|  |  | Exterior lighting | First Fix Electrical
|  |  | Exterior canopy | First Fix Electrical
|  |  | Pole light | First Fix Electrical
Tenancy X
|  |  | showroom | First Fix Electrical
|  |  | BOH | First Fix Electrical
|  |  | toilet | First Fix Electrical
|  |  | Exterior lighting | First Fix Electrical
|  |  | Pole light | First Fix Electrical
Second Fix
Harvey Norman
|  |  | Mains | Second Fix
|  |  | Main Earth | Second Fix
|  |  | sub mains Electrical DB | Second Fix
|  |  | sub mains DB3 | Second Fix
|  |  | sub mains DB2 | Second Fix
|  |  | sub mains DB4 | Second Fix
|  |  | MSB | Second Fix
|  |  | Bedding | Second Fix
|  |  | Furniture | Second Fix
|  |  | Electrical | Second Fix
|  |  | Inwards goods | Second Fix
|  |  | lunch room | Second Fix
|  |  | toilets | Second Fix
|  |  | hallway | Second Fix
|  |  | upstairs offices | Second Fix
|  |  | Exterior lighting | Second Fix
|  |  | Exterior canopy | Second Fix
|  |  | Pole light | Second Fix
Tenancy X
|  |  | showroom | Second Fix
|  |  | BOH | Second Fix
|  |  | toilet | Second Fix
|  |  | Exterior lighting | Second Fix
|  |  | Pole light | Second Fix
FEL SM Weekly Site Checklist
| 2023-04-03 |  |  | FEL SM Weekly Site Checklist
| 2023-04-10 |  |  | FEL SM Weekly Site Checklist
| 2023-04-17 |  |  | FEL SM Weekly Site Checklist
| 2023-04-24 |  |  | FEL SM Weekly Site Checklist
| 2023-05-01 |  |  | FEL SM Weekly Site Checklist
| 2023-05-08 |  |  | FEL SM Weekly Site Checklist
| 2023-05-15 |  |  | FEL SM Weekly Site Checklist
| 2023-05-22 |  |  | FEL SM Weekly Site Checklist
| 2023-05-29 |  |  | FEL SM Weekly Site Checklist
| 2023-06-05 |  |  | FEL SM Weekly Site Checklist
| 2023-06-12 |  |  | FEL SM Weekly Site Checklist
| 2023-06-19 |  |  | FEL SM Weekly Site Checklist
| 2023-06-26 |  |  | FEL SM Weekly Site Checklist
| 2023-07-03 |  |  | FEL SM Weekly Site Checklist
| 2023-07-10 |  |  | FEL SM Weekly Site Checklist
| 2023-07-17 |  |  | FEL SM Weekly Site Checklist
| 2023-07-24 |  |  | FEL SM Weekly Site Checklist
| 2023-07-31 |  |  | FEL SM Weekly Site Checklist
| 2023-08-07 |  |  | FEL SM Weekly Site Checklist
| 2023-08-14 |  |  | FEL SM Weekly Site Checklist
| 2023-08-21 |  |  | FEL SM Weekly Site Checklist
| 2023-08-28 |  |  | FEL SM Weekly Site Checklist
| 2023-09-04 |  |  | FEL SM Weekly Site Checklist
| 2023-09-11 |  |  | FEL SM Weekly Site Checklist
| 2023-09-18 |  |  | FEL SM Weekly Site Checklist
| 2023-09-25 |  |  | FEL SM Weekly Site Checklist
| 2023-10-02 |  |  | FEL SM Weekly Site Checklist
| 2023-10-09 |  |  | FEL SM Weekly Site Checklist
| 2023-10-16 |  |  | FEL SM Weekly Site Checklist
| 2023-10-23 |  |  | FEL SM Weekly Site Checklist
| 2023-10-30 |  |  | FEL SM Weekly Site Checklist
| 2023-11-06 |  |  | FEL SM Weekly Site Checklist
| 2023-11-13 |  |  | FEL SM Weekly Site Checklist
| 2023-11-20 |  |  | FEL SM Weekly Site Checklist
| 2023-11-27 |  |  | FEL SM Weekly Site Checklist
| 2023-12-04 |  |  | FEL SM Weekly Site Checklist
| 2023-12-11 |  |  | FEL SM Weekly Site Checklist

## Inground services
type | name
checklist | Inground Services
section | Ducts and Conduits
checkpoint | Correct size installed
checkpoint | Start and finish locations correct as per plan
checkpoint | separation from other services
checkpoint | Clean inside and in good condition
section | Electrical Pits
checkpoint | Set out correct
checkpoint | Correct size installed
checkpoint | Duct entry holes sealed / water proofed
checkpoint | Pits installed to correct height and level
checkpoint | Clean inside and in good condition
section | Light Pole Foundations
checkpoint | Set out correct
checkpoint | Ducting in correct position - centre of cage
checkpoint | Correct Cage Installed
checkpoint | Cage installed to correct height / level
checkpoint | Ground Plant pole installed to correct height / level
section | Photos

## First Fix Electrical
type | name
checklist | QA - First Fix
section | Flush Boxes
checkpoint | Fire Rated or Acoustic
checkpoint | Height as per plan
checkpoint | Location as per plan
checkpoint | Intumescent Pad In Place
section | Cabling
checkpoint | Power cables installed correctly
checkpoint | Lighting cables installed correctly
checkpoint | Equipment cables installed correctly
checkpoint | Circuits clearly labelled
checkpoint | Separation between Data and Power at 300mm or as specified
checkpoint | All cables secured via cable ties with ends cut
section | Cable Ladder
checkpoint | Minimum 25% spare capacity left on cable tray
section | QA - Lights
checkpoint | Setout Correct
checkpoint | Cabling in correct location
checkpoint | Emergency/ Exit Lighting
checkpoint | Nogging installed for Electrical Services
section | Seismic Bracing
checkpoint | For Lighting
checkpoint | Cable Tray
checkpoint | Switchboard
section | Conduits
checkpoint | Correct size installed
checkpoint | Location as per plan
checkpoint | All conduits glued & watertight
checkpoint | Clean inside and in good condition
checkpoint | Stainless screws used
section | Photos

## Cable Tray
Section | Cable Ladder
Checkpoint | Unistrutt Filed & Painted
Checkpoint | Hangers Spaced as Specified
Checkpoint | Correct Size Ladder Installed
Checkpoint | Ladder Joined Correctly
Checkpoint | Hangers Sceismicly Restrained as per Design
Checkpoint | Ladder Fastened to Hangers
Checkpoint | Correct Anchors used fixing to Ceiling / Walls
Checkpoint | Cable Ladder Bonded
section | Photos

## Switchboards
section | Switchboard
checkpoint | Spatial certificate signed if required
checkpoint | Fixings installed in wall correctly if board is wall mounted
checkpoint | All clearances sighted to ensure location is compliant
checkpoint | All cables correctly installed in protection device and earth and neutral bars and fully secured
checkpoint | Cables neatly dressed
checkpoint | Phase tabs on chassy covered
checkpoint | All earths and neutrals labelled to match phase numbers
checkpoint | Switchboard is clean on the inside and outside
checkpoint | Masking blanks installed
checkpoint | DB legend installed
checkpoint | Feisst label on the door installed
section | Photos

## Second Fix Electrical
type | name | values
checklist | QA - Second fix
section | Power Outlets
checkpoint | Correct type installed
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Outlet Installed level
checkpoint | Circuit Tested and results recorded
checkpoint | Description Labelled on the outlet face with vivid and with dymo labeller on cover plate and ensure label is level
section | Light Switches
checkpoint | Correct type installed
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Light switch Installed level
checkpoint | Circuit Tested and results recorded
checkpoint | Description Labelled on the outlet face with vivid and with dymo labeller on cover plate and ensure label is level
section | Light Fixtures
checkpoint | Correct type installed
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Tested for operation
checkpoint | Correctly installed with stainless screws & 90 / 45 angle
section | Photos

## SM Weekly Checklist
type | name
checklist | FEL SM Weekly Site Checklist
section | Monday
checkpoint | Prestart Meeting with Team
checkpoint | Health Check
checkpoint | Review Tasks for the week
checkpoint | Identify Targets Including Hours
checkpoint | Approve hours by 9AM for previous week
checkpoint | Sign off Subcontractor Hours & Submit
checkpoint | Review SWMS
checkpoint | Site Toolbox Meeting
checkpoint | SSSP in Order
section | Tuesday
checkpoint | Follow up outstanding RFI's with PM
section | Wednesday
checkpoint | Review Roadblocks & Follow Up if still unresolved
checkpoint | QAs up to date
section | Thursday
checkpoint | Weekly planner filled out for week ahead
checkpoint | Roadblocks identified and actioned
checkpoint | Materials organized for week ahead
checkpoint | Plans printed with any relevant notes added
section | Friday
checkpoint | Submit Toolbox minutes to main contractor and FEL office
checkpoint | Job Cards up to date and submitted
checkpoint | Team tasks for week ahead filled out on whiteboard