## struct
resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
| step |  |  | Tier 1: Site QA
| step |  |  | Tier 2: Inground services
| step |  |  | Tier 3: External ducting - Harvey Norman
Inground services | checklist |  |  | Tier 4: Mains incoming ducts
Inground services | checklist |  |  | Tier 4: Pits
Inground services | checklist |  |  | Tier 4: Ducting from pit to Tx
Inground services | checklist |  |  | Tier 4: Pole light
Inground services | checklist |  |  | Tier 4: Sign
Inground services | checklist |  |  | Tier 4: Telecome incoming sleeve
| step |  |  | Tier 3: External ducting - Tenancy X
Inground services | checklist |  |  | Tier 4: Mains incoming ducts
Inground services | checklist |  |  | Tier 4: Pole light
Inground services | checklist |  |  | Tier 4: Telecome incoming sleeve
Inground services | checklist |  |  | Tier 4: Pits
Inground services | checklist |  |  | Tier 4: Ducting from pit to Tx
| step |  |  | Tier 2: Cable Tray
| step |  |  | Tier 3: Harvey Norman
Cable Tray | checklist |  |  | Tier 4: Electrical
Cable Tray | checklist |  |  | Tier 4: Furniture
Cable Tray | checklist |  |  | Tier 4: Bedding
Cable Tray | checklist |  |  | Tier 4: BOH
| step |  |  | Tier 2: Switchboards
| step |  |  | Tier 3: Harvey Norman
Switchboards | checklist |  |  | Tier 4: Main Switchboard
Switchboards | checklist |  |  | Tier 4: Electrical DB
Switchboards | checklist |  |  | Tier 4: DB3
Switchboards | checklist |  |  | Tier 4: DB2
Switchboards | checklist |  |  | Tier 4: DB4
| step |  |  | Tier 3: Tenancy X
Switchboards | checklist |  |  | Tier 4: MSB
| step |  |  | Tier 2: First Fix
| step |  |  | Tier 3: Harvey Norman
QA - First Fix | checklist |  |  | Tier 4: Mains
QA - First Fix | checklist |  |  | Tier 4: Main Earth
QA - First Fix | checklist |  |  | Tier 4: Sub Mains Electrical DB
QA - First Fix | checklist |  |  | Tier 4: Sub Mains DB3
QA - First Fix | checklist |  |  | Tier 4: Sub Mains DB2
QA - First Fix | checklist |  |  | Tier 4: Sub Mains DB4
QA - First Fix | checklist |  |  | Tier 4: MSB
QA - First Fix | checklist |  |  | Tier 4: Bedding
QA - First Fix | checklist |  |  | Tier 4: Furniture
QA - First Fix | checklist |  |  | Tier 4: Electrical
QA - First Fix | checklist |  |  | Tier 4: Inwards goods
QA - First Fix | checklist |  |  | Tier 4: lunch room
QA - First Fix | checklist |  |  | Tier 4: Toilets
QA - First Fix | checklist |  |  | Tier 4: Hallway
QA - First Fix | checklist |  |  | Tier 4: Upstairs Offices
QA - First Fix | checklist |  |  | Tier 4: Exterior lighting
QA - First Fix | checklist |  |  | Tier 4: Exterior canopy
QA - First Fix | checklist |  |  | Tier 4: Pole light
| step |  |  | Tier 3: Tenancy X
QA - First Fix | checklist |  |  | Tier 4: Showroom
QA - First Fix | checklist |  |  | Tier 4: BOH
QA - First Fix | checklist |  |  | Tier 4: Toilet
QA - First Fix | checklist |  |  | Tier 4: Exterior lighting
QA - First Fix | checklist |  |  | Tier 4: Pole light
| step |  |  | Tier 2: Second Fix
| step |  |  | Tier 3: Harvey Norman
QA - Second Fix | checklist |  |  | Tier 4: Mains
QA - Second Fix | checklist |  |  | Tier 4: Main Earth
QA - Second Fix | checklist |  |  | Tier 4: Sub Mains Electrical DB
QA - Second Fix | checklist |  |  | Tier 4: Sub Mains DB3
QA - Second Fix | checklist |  |  | Tier 4: Sub Mains DB2
QA - Second Fix | checklist |  |  | Tier 4: Sub Mains DB4
QA - Second Fix | checklist |  |  | Tier 4: MSB
QA - Second Fix | checklist |  |  | Tier 4: Bedding
QA - Second Fix | checklist |  |  | Tier 4: Furniture
QA - Second Fix | checklist |  |  | Tier 4: Electrical
QA - Second Fix | checklist |  |  | Tier 4: Inwards goods
QA - Second Fix | checklist |  |  | Tier 4: lunch room
QA - Second Fix | checklist |  |  | Tier 4: Toilets
QA - Second Fix | checklist |  |  | Tier 4: Hallway
QA - Second Fix | checklist |  |  | Tier 4: Upstairs Offices
QA - Second Fix | checklist |  |  | Tier 4: Exterior lighting
QA - Second Fix | checklist |  |  | Tier 4: Exterior canopy
QA - Second Fix | checklist |  |  | Tier 4: Pole light
| step |  |  | Tier 3: Tenancy X
QA - Second Fix | checklist |  |  | Tier 4: Showroom
QA - Second Fix | checklist |  |  | Tier 4: BOH
QA - Second Fix | checklist |  |  | Tier 4: Toilet
QA - Second Fix | checklist |  |  | Tier 4: Exterior lighting
QA - Second Fix | checklist |  |  | Tier 4: Pole light
| step |  |  | Tier 1: FEL SM Weekly Site Checklist
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 3-Apr-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 10-Apr-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 17-Apr-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 24-Apr-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 1-May-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 8-May-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 15-May-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 22-May-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 29-May-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 5-Jun-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 12-Jun-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 19-Jun-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 26-Jun-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 3-Jul-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 10-Jul-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 17-Jul-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 24-Jul-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 31-Jul-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 7-Aug-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 14-Aug-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 21-Aug-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 28-Aug-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 4-Sep-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 11-Sep-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 18-Sep-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 25-Sep-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 2-Oct-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 9-Oct-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 16-Oct-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 23-Oct-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 30-Oct-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 6-Nov-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 13-Nov-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 20-Nov-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 27-Nov-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 4-Dec-23
FEL SM Weekly Site Checklist | checklist |  |  | Tier 2: 11-Dec-23