## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
ee1f27ac-a386-46f1-ada0-988b4c8a659b | checklist | Clearing and Grubbing | itp | Clearing and Grubbing
4c6802ba-6f2c-4e3f-9b5b-cedb3650249a | section | Details
cea0d170-f8a2-4a1e-8cfa-35a1d0530d7b | checkpoint | 1 - Areas to Clear and Grub
570ec2ff-fc67-5d4c-a682-15fd7d7d6dff | note | Acceptance Criteria: Clearing and grubbing operations shall be limited to those areas required to construct the Works and/or meet specified visibility requirements. As a minimum, the following clearing and grubbing shall be carried out: a) where earthworks are to be constructed, the minimum width required to construct the Works, plus an additional width of not more than the distance stated in Clause 1.1 of Annexure MRTS04.1 to this Technical Specification or 3 m where not so stated, or the property boundaries, whichever is the lesser, and b )other areas specified in Clause 1.2 of Annexure MRTS04.1 to this Technical Specification.
5ddeff41-0e1e-5788-a916-a7e321b43cc9 | note | Reference - MRTS04 Cl. 7.2.1
8beb50c3-2741-5c47-a996-4d0717f43cbb | note | Item Check - Check and Verify
537a4b23-a952-49bb-9948-1329e942c7d3 | checkpoint | 2 - Limitations
f2fcc416-4126-5d14-9c2a-e61d5f467ea8 | note | Acceptance Criteria: Any trees, shrubs and overhanging branches to be left undisturbed shall be clearly marked by the Contractor. This marking shall be carried out prior to clearing operations reaching the areas concerned. HOLD POINT
b59d225c-1c90-5c20-b8f1-e1e47bd33c8f | note | Clearing operations within streams and waterways shall not include removal of stumps and roots below ground surface. Beyond the areas to be cleared, only those trees, shrubs and overhanging branches which are shown on the drawings shall be removed or pruned, as necessary. Such removal or pruning shall only be carried out after consultation with the Administrator
6c2c1b32-0942-53f1-af25-5154e46c57c7 | note | Reference - MRTS04 Cl. 7.2.2
026ddcc3-dfbc-5cf1-87e5-d71ba6c3ea3e | note | Item Check - HOLDPOINT
4607248b-7ca8-4f10-8a0d-48963b13b491 | signoff | Hold Point
bf8c9b6b-6bad-4327-99e0-b5df946a95b6 | checkpoint | 3 - Trees required by Administrator
86bc7902-1ef4-56ac-965d-cae588acc137 | note | Item Check - HOLDPOINT
2b90815b-c54e-45c8-a9a0-48529b4f1831 | signoff | Hold Point
68f2fa5e-4e11-41f0-b3aa-c6b1bf401cb2 | checkpoint | 4 - Material for Organic Mulch MRTS04 Clause
c45d87be-767f-5e33-8495-5e1b17c875ba | note | Acceptance Criteria: Where site manufactured mulch is required in accordance with MRTS16 Landscape and Revegetation Works or MRTS52 Erosion and Sediment Control, processing of such material shall also be carried out in accordance with the Material and Construction requirements of MRTS16 Landscape and Revegetation Works.
a64c228e-0ff0-538e-8919-4865001d1aa2 | note | Reference - MRTS04 Cl. 7.2.4
45fb18c7-d68f-50d9-84c7-28f1290da0ef | note | Item Check - Check and Verify
157bcdbe-cc12-47c4-9fd5-32506c684894 | checkpoint | 5 - Fauna Habitat Logs
1e66f058-09d0-5c20-86ad-96e1a12581b1 | note | Acceptance Criteria: Hollow timber which is identified as being suitable for fauna habitat logs shall be relocated to areas clear of construction activities as follows:
1515f294-eb71-5fd2-89db-84f82b525616 | note | a) behind batters
7f26777c-2705-5af4-9e05-701e9c6380ba | note | b) behind proposed safety barriers but not within any hazard free zone, and
a0dfcb27-3620-5955-8721-ce0cc85c0c06 | note | c) areas at least 9 m clear of carriageways.
f733615b-d531-5895-88a7-40670c209f26 | note | Fauna habitat log density shall not exceed 20 m length per 100 m² area. Logs shall not be placed in waterways or in any area where they are likely to be struck by errant vehicles.
979ccb52-c959-5776-84fa-0fd111046f1c | note | Reference - MRTS04 Cl. 7.2.5
9efccf4c-6f7f-5613-a07e-aa7fd13c705a | note | Item Check - Check and Verify
09506ffe-cb2b-4aa6-8b1c-4890cb5b0e71 | checkpoint | 6 - Sugar Cane and Banana Plants
96715588-4136-5359-be34-513a45b0acf1 | note | Acceptance Criteria: Particular attention shall be taken to ensure that sugar cane and banana plant root systems are completely removed and disposed of. Any regrowth of sugar cane and/or banana plants occurring during the Contract, including the Defects Liability Period, shall be removed.
f340df70-b9b1-5132-8a23-79f9d3034d17 | note | Reference - MRTS04 Cl. 7.2.6
0f148595-fb69-5a76-8094-e2dbbb07ffdf | note | Item Check - Check and Verify
d5c327c7-71e9-43eb-bde4-b26afabc0af1 | checkpoint | 7- Disposal of Clear and Grub
283f1f23-1842-5232-ad6f-5fb943d2055e | note | Acceptance Criteria: Cleared and grubbed material other than that mulched under Clause 7.2.4 shall be disposed of in any areas stated in Clause 6 of Annexure MRTS04.1. If no such disposal instructions are stated, the cleared and grubbed material shall be removed from the Site and disposed of in accordance with all relevant Statutory Requirements including the requirements in MRTS51 Environmental Management.Any burning of cleared and grubbed materials shall be carried out strictly in accordance with the requirements of the Contract.
bced38b8-4f46-5c4f-895a-be23180d0d15 | note | Reference - MRTS04 Clause 7.2.8
4efd8280-0fbf-59e1-a771-6af772fdae9a | note | Item Check - Check and Verify
d0946237-c90c-4b1c-934b-a402847a9a42 | checkpoint | 8 - Additional Requirements:
e1419ce1-d35e-5ea4-8e4d-148d1b3e9fd5 | note | Acceptance Criteria: Within the limits of the clearing and grubbing, but clear of earthworks operations, any existing local irregularities of the natural surface are trimmed so as not to cause a hazard to errant vehicles. The surface is lightly compacted when necessary to provide a surface consistent with that existing prior to the Works
da166361-4837-57ab-bc8c-9ebced42818c | note | Reference - MRTS04 Clause 7.2.8
e149b3d2-0ced-5507-9188-b860d9e87587 | note | Item Check - Check and Verify
1d808446-ed19-469d-9fd8-29f6cf6b12ae | checkpoint | 9 - Vegetation Management
87c19001-8dc9-5df5-a6fc-8c4fa5a1f217 | note | Acceptance Criteria: The contractor shall identify all vegetation which is at risk of being destroyed or damaged as part of the works. Following the hierarchy, avoid, mitigate, offset, the contractor shall provide a vegetation management plan which provides detailed description of trees within the work zone, providing the details of:
07a44b1c-52cb-5387-b081-ccd10bb68366 | note | -Species
83fbcae5-8ed5-56a7-91d7-71745e1456ea | note | -Size (diameter of trunk at 1.3m above ground level)
f998d47b-a474-5f9f-a7d7-609031a3652a | note | -Proposal for removal or retention based on arborist advice (AQF level 5 or above).
e6c16f10-8d23-5c1d-96b6-9d8a4b2aa793 | note | For native vegetation removal, justification must be provided for Council’s project management deliberation.
29169abc-1f56-5f18-a62b-f709da868023 | note | Reference - Project Specification
39e97b0f-be4e-52b7-8b87-5df2d5c3a571 | note | Item Check - Check and Verify
2a21c8c1-a238-45d2-8bdc-def966569654 | checkpoint | 10 - Fauna Spotter
2c0a861b-ebca-5dd7-b92b-c9b14e2e6a44 | note | Acceptance Criteria: Fauna Spotter to be present when undertaking Tree Removals.
897a199d-bf32-53d2-8d5b-22789c2b0fe5 | note | Reference - Contract Specification
e9e892af-e1c7-55d6-85d4-a5bf90a15d0b | note | Item Check - Check and Verify
df6b3ac8-23a3-4c68-ba69-2c872907b5e4 | checkpoint | Final Verification
3ca333fb-0f5e-5926-9826-82280ae83ce1 | note | Name of Cient's Representative
7cb5bfc5-e41f-5cd2-9b58-c7c0b8db959e | textbox | Print Name:
cc75e62b-45d8-56a4-96cc-ea69f6dde480 | date | Date:
759b4152-9cc5-5f6b-a506-ae41402b37e1 | note | Name of Contractor's Representative
7a596745-c651-5ec0-831b-c2a12e4d3644 | textbox | Print Name:
6d04b1b9-5867-56cb-90f3-70a8e8bb3f39 | date | Date:
fc372490-8c47-4ab5-8697-4d4f871ccad7 | signoff | Signature
a6ab5777-7be4-4d82-a6ab-184392409213 | section | Final Sign Offs (to be completed at closure of Lot)
0333be49-ee06-41f0-92df-fa5f6515d094 | checkpoint | Agreed Quantities
73fa9fe2-478a-4c14-99f7-1da4a2eeb1ac | signoff | Agreed Quantities Sign Off
404953bf-0a3c-4d35-a264-beb26a290831 | checkpoint | Closure of Lot
deca9a3e-30b3-4f5b-a7aa-267b27808561 | signoff | Closure of Lot Sign Off
2fb93f16-2562-4d1b-acd3-0c8cd8989083 | checklist | Concrete (Normal Class) | itp | Concrete (Normal Class)
6b1a6c82-ef5b-4359-b63c-5286ca85cc41 | section | Details
a52f1318-2a07-4e23-9e46-3fd87398267f | checkpoint | 1 - Concrete Class
afa6b8a7-e40a-5d60-a3a0-330808b1384e | note | The strength grade of concrete and maximum nominal aggregate size used shall be as specified on the Drawings.
9ceb3a8b-2abd-53a9-a2f4-00a7c9f3cda3 | note | Reference - MRTS70 Clause 17.1
9fae03c3-c4f0-5f13-9137-a93bc444033a | note | Item Check - Check and Verify
65cb75cf-fcdc-4c5b-bbe4-54aec8105f89 | checkpoint | 2 - Batching, Mixing and Transport
9cc280a9-bacf-5062-b91c-98344b869fd0 | note | Batching, supply and delivery of concrete shall comply with AS 1379.
58759838-0bc9-5820-b9e0-c5787d718645 | note | Reference - MRTS70 Clause 17.6
3df97843-ab79-503d-b95b-6c98383c37fd | note | Item Check - Check and Verify
8332c57e-4db0-406d-92f1-49e3dc543c68 | checkpoint | 3 - Long Distance Travel and Extended Placement Times
48000f1e-140c-5313-b9f7-9e6976deceb4 | note | Where travel times are, by necessity, longer than 90 min as listed in AS 1379, a procedure for long-distance travel or extended placement times shall be submitted to the Administrator for approval six weeks before concreting begins.
4515decf-e50f-5080-8f66-12ba29b68ab8 | note | Reference - MRTS70 Clause 17.6.1
54676591-bd50-5bf6-8bf0-e18cdca2efac | note | Item Check - MILESTONE
2f7cfdf0-9213-4c16-8a8a-63ff8ab30856 | signoff | Milestone
029417c3-be33-432a-a99d-fdd33001d6b0 | checkpoint | 4 - Acceptance and Rejection of Plastic Concrete
60a7ecac-5e74-51a3-849f-68f1c986c41d | note | The consistency and workability of concrete shall be such that it can be handled and transported without segregation and can be placed, worked and compacted into all corners, angles and narrow sections of forms, and around all reinforcement. Consistency testing shall be undertaken in accordance with AS 1379 (which requires a consistence test every time a sample is taken for strength testing).
93ef14cd-2911-5f98-b152-8c9664b6a0b6 | note | Reference - MRTS70 Clause 17.7
de35d888-dc9d-5aeb-a96d-e26d6f81f2b1 | note | Item Check - Check and Verify
fa5f9f18-5501-4cfe-bd7e-0346c242e20a | checkpoint | 5 - Acceptance and Rejection of Hardened Concrete
8564ddd8-9e42-508e-9bd4-6ed717bb78fd | note | Acceptance and rejection of hardened concrete shall be on a production assessment basis in accordance with AS 1379. Concrete for the following applications shall be tested on a project assessment basis if more than 25 m¬≥ is used: a) Signpost footings and plinths with dimensions >150 mm b) Spill through or rock grouting c) Manually placed kerb and channel on or alongside concrete base. Sampling: 1 sample per 50 m¬≥ (as per Clause 6.5 of AS 1379).
0780362f-deb7-5f72-a4f9-d6ad102e400a | note | Reference - MRTS70 Clause 17.8
2155db53-2c48-5073-8393-9877ab479636 | note | Item Check - Check and Verify
0cdb9e89-0c95-400f-9952-32571157078a | checkpoint | 6 - Placing Concrete
04889ee8-2966-58b4-8634-7b0326b8b476 | note | No concrete shall be placed until: a) Formwork and reinforcement are inspected b) All foreign material is removed. This may be downgraded from Hold to Witness Point. The Administrator must be notified 24 hours in advance of placing.
289c96d9-83cc-5033-b9f5-b4b62a1cc0fc | note | Reference - MRTS70 Clause 17.12.1
89e6bbe2-a00a-5182-b9b3-ca9847f4dd1a | note | Item Check - HOLD / WITNESS POINT
d8e32fd1-d5ff-4868-a74e-fc65a26fcd7f | signoff | Hold/ Winess Point
08f24173-ac1d-4049-84c4-123155d605c5 | checkpoint | 7 - Compaction of Concrete
5d5edde1-67ba-5a9f-be07-36449d42cf08 | note | Concrete shall be compacted to achieve dense and durable concrete, to the levels and tolerances specified.
0a37e2c3-c57f-5741-a0f1-83c438e9e815 | note | Reference - MRTS70 Clause 17.12.2
e4d74f3a-6304-555c-a985-c3d39dae8dbe | note | Item Check - Check and Verify
a6244b7f-06a9-438b-82f4-f7801759533f | checkpoint | 8 - Finishing
15f2794c-7870-5192-a300-5cba264eddb5 | note | All unformed surfaces shall be finished true to line and level within the tolerances specified.
04131ee4-811a-516e-88e4-0fd462e6fbf7 | note | Reference - MRTS70 Clause 17.14.1
e300c129-c639-5c90-971f-443c5ee9c685 | note | Item Check - Check and Verify
3814b6d1-b74e-4fdd-915c-40922be3b0a7 | checkpoint | 9 - Early Loading
8cefa877-3282-5fb8-8071-d28feb4d5079 | note | Concrete shall not be loaded until: 3 days have passed since placement, and 70% of specified strength is achieved. Administrator approval is required for any loading.
6225b68f-9f46-5a30-b752-ebc1431d1131 | note | Reference - MRTS70 Clause 15.9
210b4eaa-a249-5c15-b4af-98e6b1e69a2f | note | Item Check - Check and Verify
a6fdef52-fe07-4566-a972-d03678ac7c34 | checkpoint | 10 - Curing
83f72e6d-8449-5105-8382-46615c15769b | note | Curing of unformed surfaces shall begin once hardened and continue for 7 days minimum. If forms are removed early, curing of formed surfaces must begin within 1 hour unless otherwise specified.
51a841f7-5034-5183-9e06-f4689a47e810 | note | Reference - MRTS70 Clause 15.11.1
70a5cc58-905a-5dda-acd2-623690dc43df | note | Item Check - Check and Verify
c219583d-b6d4-4d1b-b00e-1ff4eb11b1df | checkpoint | Final Verification
6d7fea29-00af-5f19-afd9-7b9c071b1038 | note | Name of Cient's Representative
9dae023a-dad7-5c32-b07c-292837e4f6d2 | textbox | Print Name:
bc88d00c-21f2-58cb-bc31-1802aa79f082 | date | Date:
7aa0802d-46f6-56dc-872d-6e26c72d11ef | note | Name of Contractor's Representative
b1224aba-aee4-5de9-9588-759e9fd814af | textbox | Print Name:
bd42db42-c5a4-5208-8374-5d07cf361512 | date | Date:
85940694-4f87-4b86-aa7d-32d3d81c90df | signoff | Signature
5a70af80-0c31-45fc-b02e-a9052f386cfc | section | Final Sign Offs (to be completed at closure of Lot)
0ce8ec96-e0f6-4d1a-8d90-7e88627ba709 | checkpoint | Agreed Quantities
1c9402fd-e047-4ced-aab9-3f6ccc592d10 | signoff | Agreed Quantities Sign Off
0a4cc135-817a-4739-9039-e4bf36758a17 | checkpoint | Closure of Lot
103e8078-b852-4e6d-946a-b2de3f1092cc | signoff | Closure of Lot Sign Off
a6491412-9030-4072-ad58-2fb7db03ff2b | checklist | Concrete (Special Class) | itp | Concrete (Special Class)
cef40270-b921-4fa7-b4ba-69767705a096 | section | Details
b79b86f3-4aa6-4792-9ca0-642d3c0c5577 | checkpoint | 1 - Mix Designs
dfc6fb3e-5caf-5398-94c7-3f814d049889 | note | No concrete shall be placed in the Works until approval of the mix design has been obtained from the Administrator.
bfcfb4f2-226c-5fb9-954a-15f3ef0fecbd | note | Reference - MRTS70 Clause 15.1
cdf3eaba-f1b5-5f9c-af10-0035d35cc011 | note | Item Check - HOLD POINT
f186cd5e-0fa0-4f5c-b894-bf6da927555a | signoff | Hold Point
5f0c869d-4f4e-4265-8dfd-da2bf3b9f9bb | checkpoint | 2 - Trial Mix
d578259b-cb08-5d55-ae0b-3e896dd22ee7 | note | When requested by the Administrator, and where extensive performance data is not available, mix design acceptance will be on the basis of trial mixes.
3091f37c-36d9-505c-9351-1ad5234731c9 | note | Reference - MRTS70 Clause 15.1.1
fb2bc991-a25a-533e-80a6-24d24c78c30a | note | Item Check - WITNESS POINT
62366f86-5df8-477b-917f-0877f445f63d | signoff | Witness Point
d0c63a36-d799-4308-9ab3-df17ba23ca47 | checkpoint | 3 - Transport and Delivery
096ac1c9-4dd6-5915-bc86-385e26ef1895 | note | Concrete shall be placed and compacted within the times from the discharging of the batch plant as per:
38e80228-7a51-5f22-bc83-2f3be2cdd616 | note | <32°C = 60 minutes
c730bc44-f0ee-551a-b834-4a4d86f8fd8e | note | 32–35°C = 45 minutes
e96652aa-414a-4dc0-b6b6-adae2120d6a5 | checkpoint | 35°C = Reject load
a6e7a6f2-c3f7-5fb7-8b82-2b4205c27770 | note | These times may be extended at the Administrator's discretion.
f855e88a-4074-5ee8-8e77-5500e8514a4e | note | Reference - MRTS70 Clause 10.4
b1752d43-4b4e-502a-84df-af45d61639a2 | note | Item Check - Check and Verify
8b7fb0cf-9414-44d7-8148-58a9843e1f59 | checkpoint | 4 - Long Distance Procedure
0a751b1d-2828-535f-999d-6bb14279aef9 | note | Where travel or placement times are, by necessity, longer than those listed in Clause 10.4, a procedure for long-distance travel or extended placement times shall be submitted to the Administrator for approval 6 weeks before concreting begins.
49601e85-7b26-5e48-b1a6-a8f63608d5ee | note | Reference - MRTS70 Clause 10.4
f8673728-74e7-5690-a69f-dc48b9e6c2f2 | note | Item Check - MILESTONE
7c0236f9-e97c-47c2-b491-7480221ac56f | signoff | Milestone
203bb268-2a04-4afc-981b-01e495357270 | checkpoint | 5 - Slump Test
1f568521-5000-5f01-ab83-b06f23d097e0 | note | The plastic material properties (slump) shall lie within the range established using the approved nominated value and the tolerances specified below:
bacf23cd-d76b-5451-a7d1-09fe458de971 | note | ≥60, ≤80 = ±15
b58e57d9-4329-58a4-ba7e-2311dee3b5a3 | note | 80, ≤110 = ±20
69df18ca-af12-53ad-84d6-a22d66927e07 | note | Reference - MRTS70 Clause 11
37a8a0aa-ab7e-5460-811e-52e1c7aace8d | note | Item Check - Check and Verify
a98002f7-bace-452f-b4b0-52c5884bafe3 | checkpoint | 6 - Testing Samples
a6b2f86c-9ccc-5a5a-8f4c-ed8ba32c7b7b | note | Samples for compression strength testing shall be taken from separate batches of concrete during the placing operation.
2df70f94-1c39-5638-a5c4-97933679d957 | note | 1–3 Batches = Every Batch
74587abe-4bd8-5604-bf89-50549a8350be | note | 4–10 Batches = 4 Samples
248ebec1-a380-52f3-9fb5-291f6b6d3890 | note | 11–23 Batches = 5 Samples
72c3b1f4-47d1-59e8-93be-0158661d4193 | note | 23 Batches = n⁄4
230e73b4-fa24-5ef3-8e3e-6e979553742a | note | Reference - MRTS70 Clause 15.2.1
01f2d0ad-925c-5b76-8849-83bd0ffb2a1b | note | Item Check - Check and Verify
905359a7-4755-41de-b508-d0eb8e654f44 | checkpoint | 7 - Temperature
29511d03-d2f3-57b7-98a2-4ba858704b31 | note | No concrete shall be placed in the works if the temperature of the concrete is less than 10 °C or exceeds 35 °C.
e55319f8-98f9-54fa-8892-7b09ea085872 | note | Reference - MRTS70 Clause 13.1
bb95ad8e-bd0a-5f33-ab47-43472652a7d6 | note | Item Check - Check and Verify
f33be6d1-63ab-414a-81ec-8c1cae6d5ced | checkpoint | 8 - Hot Weather Procedure
52329369-100e-5898-859b-737f185ba093 | note | If the ambient air temperature measured at the point of placement is likely to exceed 35 °C, the Contractor shall take practical precautions, approved by the Administrator, to ensure that the temperature of the concrete does not exceed the permitted maximum.
fcffa880-2334-50fe-885a-0d8f486773a8 | note | These precautions shall be submitted as a procedure for hot weather concreting at least two weeks prior to the first concrete pour.
bb8ac9e0-8065-5249-90bf-500fbc7920a3 | note | Reference - MRTS70 Clause 13.1
d23c5db2-63fe-5f47-b791-d2ec26282202 | note | Item Check - MILESTONE
69873b07-fd9a-4845-a3e9-7808b032dca6 | signoff | Milestone
c9ed03fa-bca6-4035-b727-a2261090a8df | checkpoint | 9 - Rain Event
72f1737d-6e6b-51bb-931a-0b27f25d7a65 | note | Concrete shall not be poured in the rain or if rain is imminent unless adequate measures are taken to protect the plastic concrete from the falling rain.
92441cb5-e4bc-56b5-a42c-d3a3f3044988 | note | Reference - MRTS70 Clause 13.3
4aa52564-8373-5198-8770-ec4571dfb308 | note | Item Check - Check and Verify
5cdbebb7-660d-41c3-98ca-b166682fb6f4 | checkpoint | 10 - Early Stripping/Loading
8f2bb53f-d333-5604-98b1-75f75dbabf25 | note | Any proposal by the Contractor for early removal of forms or for early application of significant loads to the structure shall be submitted in writing to the Administrator prior to placing concrete.
3c7b1248-7606-55d9-9e4a-b68c8ddb8da7 | note | Reference - MRTS70 Clause 15.2.3
f7873151-c771-59e2-b282-1c0153f4067e | note | Item Check - Check and Verify
1d0a49c7-3856-43a7-b0d1-79aebf81ba82 | checkpoint | 11 - Formwork
aed35179-6301-5d7e-8a71-ab3d07c0f9f9 | note | All formwork shall be subject to inspection and approval by the Administrator.
e1a9ad3f-c021-5527-8461-11dff513cf16 | note | Reference - MRTS70 Clause 15.4.1
48e75889-4b06-5a22-832c-c192b09b9008 | note | Item Check - HOLD POINT
5b1fb17c-c1e4-4ac8-8ab0-15f3f204591e | signoff | Hold Point
2dd6f7c2-fed2-42b9-b68d-97639a9ef587 | checkpoint | 12 - Construction Joints
c59f9cae-d84a-59e8-b0f3-de71e552e3fb | note | Construction joints shown in the Drawings are mandatory. The use of construction joints elsewhere in the concrete work shall require the prior approval of the Designer.
56a4dcc5-597c-54d7-95ae-16bb2c285054 | note | Reference - MRTS70 Clause 15.13
7b992c9b-76cb-5815-920d-6c9551dbd6d5 | note | Item Check - HOLD POINT
1ca0154f-9b5b-45ef-a03f-f0b258537c22 | signoff | Hold Point
4c359cb4-0413-4910-b608-d23f956ec662 | checkpoint | 13 - Supports
76072ee6-203e-5ac7-a57f-ccc9e5998bfa | note | Bar chairs and/or spacers shall be placed sufficiently close together to ensure that the specified cover is maintained before and during concrete placement and to prevent any potential crushing of the spacers or penetration into the formwork.
ce668280-3297-5fac-b19e-972710d40999 | note | Reference - MRTS70 Clause 15.4.2
d4e07f2c-8d2b-501f-a4a2-57add9ecab7f | note | Item Check - Check and Verify
a46c356d-2e7e-4be3-8d86-4df9f17232f9 | checkpoint | 14 - Foundations
1bb8f04c-3065-576a-96d4-116934f0bb39 | note | Where reinforced concrete is placed on earth, sand or rock foundations, the earth or sand shall be compacted to 95% Relative Compaction as determined by Test Method Q140A and the rock freed of loose material.
0c62f59c-5470-5f1a-ac52-6ee306c27cf0 | note | Reference - MRTS70 Clause 15.6.1
7ac97ef1-b1bf-526c-9108-8c26154e0f6f | note | Item Check - Check and Verify
e8122faf-d425-4775-990f-31cd2a137893 | checkpoint | 15 - Separator
da7127bf-d1de-54cb-b864-15c4e2f2ab37 | note | Where concrete work is constructed on ground surfaces or on a foundation bedding, a polythene sheet separator of thickness not less than 100 μm shall be employed between the ground/bedding and the concrete. The separator shall extend not less than 300 mm beyond the concrete work.
6f55510f-6ed5-56a8-8867-ca8cefda4a0b | note | Reference - MRTS70 Clause 15.6.1
c1495303-bc11-5edb-8973-ae3e681f1e78 | note | Item Check - Check and Verify
5d63fcc9-d506-45b0-b265-cb0a3c3513f4 | checkpoint | 16 - Monitoring Procedure
69c617a6-2330-5189-bbf6-b42651e5551a | note | The Contractor shall submit a procedure and plan for monitoring and procedures for ensuring compliance to the Administrator for approval at least four weeks prior to the concrete pour.
648c7928-d097-5a2d-a5fd-8437c59b07df | note | Reference - eMRTS70 Clause 15.5
7f3b64a0-a963-5c16-bd6a-e16f405967c6 | note | Item Check - MILESTONE
eac22ffe-8fc8-4a36-aa5b-436eed854e1a | signoff | Milestone
d4aefb8b-043a-48d3-af42-b99bc4f19133 | checkpoint | 17 - Curing Procedure
961eb07a-13c2-5e5a-86e1-68e816af3bc1 | note | The Contractor shall submit a procedure for curing, including methods and materials, to the Administrator for approval at least two weeks prior to the first concrete pour.
11ff5df6-7a85-5c22-b272-57145075c210 | note | Reference - MRTS70 Clause 15.11.1
d3300ca2-9665-5e43-a1b5-c5226ae76c99 | note | Item Check - MILESTONE
a29a95e9-8314-49ad-9d47-33887e28e82a | signoff | Milestone
9ba19c56-d13c-4b77-9a9a-c26b3adc5b4b | checkpoint | 18 - Procedures
820e6fbc-3268-5971-a588-48c81ccb269d | note | Concrete operations shall not commence until all relevant procedures have been approved by the Administrator.
bf3c5c3a-671d-5cd4-99a8-bb58590007c9 | note | Reference - MRTS70 Clause 15.6
8430c150-1964-5dbf-a820-e1ee2bc52828 | note | Item Check - HOLD POINT
20827dfe-c254-4529-a253-86cc94445f13 | signoff | Hold Point
4fa84bf7-c1a2-42ae-a4a3-f4ca464dcc17 | checkpoint | 19 - Placing and Compaction
2d664ab8-1e67-548c-a9d0-2b1aaa457df1 | note | No concrete shall be placed in the Works until:
31eae52d-cde2-5410-91d5-f02287598c03 | note | a) The formwork and reinforcement have been inspected
a4020245-e2c7-5229-926d-cc7b9a4c8c44 | note | b) All foreign material has been completely removed from the forms
42f0b62e-b081-5842-be32-4daedf54ef98 | note | c) The mixing, batching, and compaction equipment have been approved by the Administrator.
15f416bf-c4e9-52ef-abf9-c8fec4950561 | note | Reference - MRTS70 Clause 15.6.1
a768f847-426b-5e6c-a5ac-1066a175a6fe | note | Item Check - HOLD POINT
132d593a-e2cd-4498-afe9-2642128de9ec | signoff | Hold Point
adc391f2-248d-49ba-af7f-3c88c171cb5e | checkpoint | 20 - Placing Operation
7b94f215-e2c0-5f7e-8cee-ec26f5f8aaf2 | note | The placing operation shall be conducted in the presence of the Administrator and the Contractor shall give at least 24 hours notice to the Administrator of the time that placing shall start.
7c1c98c3-9aed-5ec4-a739-389368bdf4c8 | note | Reference - MRTS70 Clause 15.6.1
e6bc80cd-180f-53b1-a97d-4d19352a5f9a | note | Item Check - WITNESS POINT
05f0c973-abe5-424d-b6fa-e807a661a088 | signoff | Witness Point
d1641224-5050-41e5-9175-6d8da43adc8d | checkpoint | Final Verification
f5c970df-394e-5c8a-aba8-028998eff3bc | note | Name of Cient's Representative
faa6a850-154a-5aa8-8a4e-c7df14152bf1 | textbox | Print Name:
45f05f19-d90f-513f-adac-e478db68698a | date | Date:
6f9f255d-21c0-5192-9d9c-4cffa0fcf0a1 | note | Name of Contractor's Representative
6815aa6e-0b13-5a31-b9d4-a4f1950c7955 | textbox | Print Name:
ebab9ec6-7b40-5bc5-9295-ca72944321a9 | date | Date:
5a021e62-9117-4e79-b6b2-79b6a8858ac6 | signoff | Signature
5479a18d-6121-4aa1-84e9-5241605761b9 | section | Final Sign Offs (to be completed at closure of Lot)
f409c466-4f2f-489e-a51d-ae9c8980b781 | checkpoint | Agreed Quantities
acf26056-53df-4c46-8674-b30b6cd63d46 | signoff | Agreed Quantities Sign Off
de32b4bb-5034-4efb-8fb0-45f7fe5c9289 | checkpoint | Closure of Lot
7097d882-6c65-4099-b21c-bc42c792eb45 | signoff | Closure of Lot Sign Off
7797c96f-1076-48c6-a1c2-1006dfc434c2 | checklist | Demolition | itp | Demolition
98626ee5-dbbe-4296-903b-73cb0bee9d30 | section | Details
0df183f6-b68d-4c88-bb98-8b107ba0b509 | checkpoint | 1 - Establishing Lot Number / Boundaries
7449c693-4403-53ba-84b3-6df710481242 | note | Acceptance Criteria: Lot Number established with the Lot boundaries of the works clearly defined for traceability within the works.
1f3f1e16-07db-5046-905a-e37e0a547e82 | note | Reference - MRTS50
663a7ba2-f69f-5c75-85af-636335bda141 | note | Item Check - Check and Verify
dfae51a5-46a4-4716-9b2b-9e600b2bc345 | checkpoint | 2 - Safety Check
afb788c2-84db-5c37-8850-27be1309a808 | note | Acceptance Criteria: All site personnel inducted (includes environment and cultural). Required Safe Work Method Statements, Task Hazard Review Cards and Traffic Control Plans completed, signed and implemented. Traffic control devices installed as per the approved traffic control plan and traffic management plan.
41bc56e0-9bfe-5702-9008-651d032c05fc | note | Reference - Induction
17d40395-9b4c-5e33-a6cc-4b5ce49867bc | note | Item Check - Check and Verify
c767a7a4-cfa3-4a44-99a1-7ac301626e28 | checkpoint | 3 - Services
592d1215-5949-5ff6-a316-af6004230397 | note | Acceptance Criteria: All services identified – shall be marked, potholed and/or protected as required. Permit to excavate issued by Project Engineer.
40b868ba-99b1-5605-96f3-a0a17221ddec | note | Reference - DBYD
d8a4d1ab-691e-5746-8f01-f489ff025fef | note | Item Check - Check and Verify
7e930d7a-67f3-4bf6-9829-91d6b8ca3d00 | checkpoint | 4 - Environmental Checks
0609a0af-3611-5a6a-b17c-4dd7cb50f923 | note | Acceptance Criteria: Erosion and sediment controls in place. Vibration and air quality to be monitored as a direct result of construction activities.
c84d104d-d6d0-5b8d-9a96-6e2257108ed1 | note | Reference - CEMP, MRTS51 Cl 10.3, MRTS51.1 Cl 4.1
8d50bfdb-1056-546b-b37d-49e786d60164 | note | Item Check - Check and Verify
dbea9282-8df7-4e31-90dd-6ea1ef92f33d | checkpoint | 5 - Removal/Demolition of Culverts and End Structures
05de5666-cf18-51d1-80c0-6fb75db5be9b | note | Acceptance Criteria: Culverts and culvert end structures shall be removed or demolished where specified in the drawings. Components to be reused shall be removed without damage. Non-reused items removed from site. Resulting voids to be backfilled to safe and free-draining condition.
d46232aa-7d09-576b-b086-b5142fd9816d | note | Reference - MRTS03 Clause 9.2
9a55f382-5021-5914-b4a3-49412f3f10ee | note | Item Check - Check and Verify
01821f9b-cd8a-4244-87c5-5e0917def760 | checkpoint | 6 - Removal/Demolition of Kerbs, Channels and Concrete Slabs
2a0e7676-3338-5e98-a46a-4cdd3ba8e823 | note | Acceptance Criteria: Remove where specified in drawings. No damage to adjacent works. If partial removal, terminate at joints or saw cut. Backfill any excavations and match surrounding level.
437a5fac-94f2-5f7d-bb02-71a0b2765b13 | note | Reference - MRTS03 Clause 9.4
74adb5d3-9c97-5266-a12e-4c01868583b9 | note | Item Check - Check and Verify
ce050063-8e50-4b9b-b419-ae3b816319df | checkpoint | 7 - Removal/Demolition of Gullies and Access Chambers
52edf7fe-4b12-5d11-88c5-49e5956d523a | note | Acceptance Criteria: Remove/demolish as per drawings without damage to adjacent work. Backfill voids and match surrounding surface level.
c1dd582a-d79a-5301-a1ad-5dc37b800b16 | note | Reference - MRTS03 Clause 9.4
c6a09596-3e5e-5dac-93c8-3cfd3892b1a0 | note | Item Check - Check and Verify
8ba9140a-727f-4fc9-8478-1340adc845a4 | checkpoint | 8 - Lot Closure
7aec2f72-f6dc-5ff2-9a0c-dd338e56ffe5 | note | Acceptance Criteria: Lot closure requires all relevant information attached to the Conformance Report including Lot Plan, Survey Report, Hold Points/Approvals & supporting documentation.
dbf87da4-5ef2-5ee6-a9eb-133f3a856c2e | note | Reference - MRTS50
4d01a13e-e600-550a-ac2b-f7f7e57a9853 | note | Item Check - Check and Verify
f7af393e-669d-46bd-bd89-f70ce3ee5aa0 | checkpoint | Final Verification
ca26ac66-d5c5-5971-ac57-5793f4402165 | note | Name of Cient's Representative
1f526fc6-6ffc-5db0-82e2-8fd6ff54aa47 | textbox | Print Name:
7cb03384-aaec-561d-866d-7f01bd94bdc5 | date | Date:
ceb1ca1a-051b-5ec8-8715-da1c70f80643 | note | Name of Contractor's Representative
af55e7ab-0102-5508-85e9-122efcc1807e | textbox | Print Name:
3e6458aa-8104-5f50-b276-5e9f86beeb55 | date | Date:
317a1845-07e3-42c6-8a5e-3c1d5849db1f | signoff | Signature
befd3e00-d56f-4cbd-b454-91ac7579d1d7 | section | Final Sign Offs (to be completed at closure of Lot)
a13afc44-d459-43db-9761-5449a84a6bdd | checkpoint | Agreed Quantities
ac69ba17-cdf0-4788-9199-e74aaf8d4e98 | signoff | Agreed Quantities Sign Off
7742b4a1-d865-4b7e-a771-c9cacb58cd8d | checkpoint | Closure of Lot
8d64b773-7623-4c2d-9fe6-3022721b3d97 | signoff | Closure of Lot Sign Off
d0ad8316-9093-402f-a77e-e31e061cd9d7 | checklist | Drainage Structures | itp | Drainage Structures
a241c473-70cc-4313-a32e-3dd1489bb535 | section | Details
82e82447-8b94-4811-8f60-8c05e5761c40 | checkpoint | 1 - Location
c235d2d5-0d34-5db4-97c8-9062c801860e | note | Acceptance Criteria: Concrete gullies and chambers shall be provided in the locations specified by, and in accordance with, the drawings.
8024a10a-e64e-5126-a6fe-a81cc18fb90e | note | Reference - MRTS03 Clause 21.3
e922dd09-8a16-590d-bba3-82c21495e417 | note | Item Check - Check and Verify
e7fdf303-9586-4e6b-885c-a357527bfaf5 | checkpoint | 2 - Bottom of Excavation
9f6ecf00-1618-5dee-8f65-79dc47a75f5c | note | Acceptance Criteria: Where insitu material on or against which gullies are to be constructed is other than rock, the material shall be compacted as for material at the bottom of excavations in accordance with MRTS04 General Earthworks. Compaction Standard: ≥ 95%
af941c30-aa36-5bcd-9aef-1ceb5f136876 | note | 1 test per 50m2, min 2 test per lot
c29bdc16-8c14-5850-965d-e2b9c30e4943 | note | Structures 06/02, 05/02, 02/05 - Minimum Allowabe Bearing Capacity to be verified prior to construction of base slabs in line with Project Drawings
62940eff-8df3-5f6c-9c38-f5fdeb1c263a | note | Reference - MRTS03 Clause 21.3
432c87d3-11e7-5c8f-8e9c-8ca166913318 | note | Item Check - Check and Verify
8cf8c2a7-76d0-45ee-bfce-3949670ef3ad | checkpoint | 3 - Foundation Bedding
fe565e59-d8c8-53f0-be52-58f9f6db03b4 | note | Acceptance Criteria: Foundation bedding material shall be placed to provide continuous even support for the chambers and gullies.
f62134af-1695-5c59-9f9d-c0ff3317a5ca | note | Reference - MRTS03 Clause 21.3
399f477f-af46-5d7b-98e1-a81f0f8cef34 | note | Item Check - Check and Verify
a78e5852-e72c-4811-adca-8f524e6a8360 | checkpoint | 4 - Backforms
9bc9f5a5-eb3a-5100-a9dd-e54f7fdf3c7e | note | Acceptance Criteria: Where the sides of excavations are in firm ground, the access chamber shafts may be constructed without the use of backforms. Where concrete is placed against the ground without the use of backforms, the specified wall thicknesses shall be increased by 20 mm
1548f068-355c-51d9-a785-523ee21468a0 | note | Reference - MRTS03 Clause 21.3
7ccb6d1c-28a7-599c-bcda-11174ffab3d7 | note | Item Check - Check and Verify
49f7f4cb-85cd-45c2-966e-a892e4bf0335 | checkpoint | 5 - Cast-In-Situ Concrete
6a6fc9f0-4abd-5061-b00f-cbe2aef2dbe5 | note | Acceptance Criteria: Concrete Cast-insitu works shall be completed in accordance with requirements of Concrete (Normal/Special Class) - Refer Lot Register for respective Concrete lot.
f4f3de86-0105-5afc-86fc-55ac7a329d46 | note | Reference - Concrete (Normal Class) – ITP
45bc8770-385f-5dc1-ba6d-af629144af41 | note | Item Check - Check and Verify
253e3c74-ed0a-49ef-8d1b-96aaea20ee7f | checkpoint | 6 - Joints
a64e7b66-2d01-5609-bb4a-27e7daac5262 | note | Acceptance Criteria: The joints between gullies and culverts shall be made watertight using cement mortar. The mortar shall be used within one hour of mixing and shall not be re-tempered. The joints shall be finished to provide smooth surfaces, uniform with the inner surfaces of the gullie
7adf7351-d39c-5f09-b0d4-069655e33fb6 | note | Reference - MRTS03 Clause 21.3
6d419cb9-0970-5f54-85fc-d5d87dde6ced | note | Item Check - Check and Verify
0c2da83d-9639-430e-b24a-83e0debbbf42 | checkpoint | 7 - Concrete Top Slab
d536158c-0725-5c5c-a1ff-5370379e4762 | note | Acceptance Criteria: Concrete top slabs, inlet units or converter slabs as applicable on access chambers and gullies shall not be placed until all the surveying requirements have been met. Hold Point. Concrete top slabs shall be joined to the shafts using cement mortar or epoxy mortar
63d9faa3-c8cb-54f5-aed9-a8b0bf0a069a | note | Gully Units, precast elements have been checked for orientation and installated as per the drawings.
520c05a9-7ad0-5e5a-b741-510c6bb065bc | note | Reference - MRTS03 Clause 21.3
b79daa7d-3510-5151-afa8-8a773fa2e113 | note | Item Check - HOLD POINT
ea63366f-2e59-4969-b550-0947ce5a8192 | signoff | Hold point
1c52c050-5b46-49b4-97e2-d6cd92d5f75f | checkpoint | 8 - Horizontal Tolerances
7383e5cf-7b4c-5ae6-b75f-8a509276b4e0 | note | Acceptance Criteria: The locations of gullies shall not vary from those specified in the drawings by more than ± 100 mm in the direction of the construction centre line and ± 50 mm in the direction at right angles to the construction centre line
e51051ca-807a-53b8-b146-cfc086d48f1a | note | Reference - MRTS03 Clause 21.3
b9656521-7230-5a79-9372-28fc220021c3 | note | Item Check - Survey
5a9a33be-6c65-459b-9656-5e6fd6b92f6d | checkpoint | 9 - Vertical Tolerances
a4c0c406-3f08-5d59-8959-be4aa6c6381c | note | Acceptance Criteria: The invert heights of gullies shall not vary from those specified by the drawings by more than ± 50 mm, provided always that the gullies join neatly to existing drainage structures, do not pond water unnecessarily and are at heights compatible with other adjacent structures. The heights of the tops of back-units, grates and frames shall not vary from those described in the drawings by more than ± 10 mm.
eee24b01-d472-5cf6-a96d-7b2d030fc2b8 | note | Reference - MRTS03 Clause 21.3
a76b4845-025c-5398-8099-c9cf835b268e | note | Item Check - Survey
ece7e190-ba96-4c45-b14b-197acce324ee | checkpoint | 10 - Removal of Formwork
6e1f6f8b-71a5-5072-ac21-26b69fa4f17d | note | Acceptance Criteria: Forms, falsework and centring shall remain in position until the times stated below have elapsed after completion of concreting: Class B1, B2 = 72 Hours
1f2b705c-c9ff-5c4b-9ea5-b548aac2af56 | note | Reference - MRTS70 Clause 15.8 (TMR Structures)
9c363035-5209-59a6-9a4e-c1b46d5a6396 | note | Item Check - HOLD POINT
1d42c3ea-a9d3-4de8-bccd-c1ce0bf64d2a | signoff | Hold point
6d1d837a-2e86-4190-8410-559533071993 | checkpoint | 11 - Backfill
b3baa67e-db05-51a2-9139-de788c06efae | note | Acceptance Criteria: Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met and notice of such works provided to the Administrator
a3ee0c92-d56d-52d4-bcac-cfd4deb1797b | note | 70% of Design Strength has been Achieved. Minimum Compaction 95%. 1 test per 100 m³ with 1 test in each Bedding/Haunch Zone, Side Zone and Overlay Zone - 2 Per lot min
2837e670-0a9b-5861-93e6-003292fc4954 | note | Reference - MRTS03 CL11.3.10 MRTS70 CL15.9
7d8d26b8-554b-5076-8b82-05f9ce1893d2 | note | Item Check - HOLD POINT
2b4b6643-b804-4ad1-a12b-367b56643d56 | signoff | Hold point
198ce62f-0800-4060-9812-878a0caa691a | checkpoint | Final Verification
f4c7bc2a-e46c-571f-8c7b-8a9096488ded | note | Name of Cient's Representative
c9c18bbf-b8e7-5e24-816a-21caeedf4431 | textbox | Print Name:
a503d66b-3313-5820-9cb1-f5c365cab03e | date | Date:
2999e351-2f94-5db1-a0ee-5ba29041f996 | note | Name of Contractor's Representative
250e41c4-6e24-5177-856d-f664ecd13286 | textbox | Print Name:
a8d33b6c-1b3f-5656-af70-6b9f131951c5 | date | Date:
b6920c49-03dc-45a9-81e2-6671105ecc59 | signoff | Signature
5fb9acab-ace0-47be-a0dc-f3154a252b02 | section | Final Sign Offs (to be completed at closure of Lot)
71b133ca-11a6-42cb-acf7-8629236521fa | checkpoint | Agreed Quantities
f2491cd9-9d1d-44e5-9732-bc8ab7e8e199 | signoff | Agreed Quantities Sign Off
971921e9-5b97-4ccd-b989-05d05429a660 | checkpoint | Closure of Lot
bf8991d6-ac74-4e50-b3b6-cc19f5aba3f8 | signoff | Closure of Lot Sign Off
ee7232dc-cdbc-48ae-b383-8e8b9a37a86e | checklist | RCBC Installation | itp | RCBC Installation
8f27cacd-6851-4589-a428-0d4dc6ea511c | section | Details
c95a100c-ce1e-4bf5-9bf9-8a09304e5640 | checkpoint | 1 - Lot Boundaries
9c47b688-46b7-588a-b170-36bf2e8c48cd | note | Acceptance Criteria: Lot Number established with the Lot boundaries of the works clearly defined for traceability within Check and Verify N/A the works
ef80de39-246b-52fa-8a07-e2ff79967641 | note | Item Check - Check and Verify
87e969a9-cefd-41d4-a9b0-4b72ebfd30f2 | checkpoint | 2 - Materials
13251aaa-14be-5b7e-85ba-2b889203aed7 | note | Acceptance Criteria: Below Slab: Concrete Blinder or Gravel Base
4dc344d3-78f5-5b62-8dfe-d8cf0424526f | note | Backfill Material: Approved select fill Refer RFI 013
9b5579db-32f8-59c7-92fe-769c12f61f7b | note | Reference - Note 2 IPEA STD DRW DS-031
9459509e-7f1a-56b6-a22a-5485a6a476db | note | Item Check - Check and Verify
fedcf0d6-7932-41c2-b6b8-b668c82afe6a | checkpoint | 3 - Excavation
add330c7-ffd5-5990-b164-297fe68aa6d5 | note | Acceptance Criteria: Excavations shall be constructed to the shapes, lines, dimensions, and other requirements shown on the drawings
46ead49d-bf07-5f6a-bbb3-76986c98cb7f | note | Reference - MRTS04 Cl13.3.3.1
6191e7d2-8f7f-5884-a8a9-ab8d58a2ef97 | note | Item Check - Check and Verify
c0157ce2-67f5-42b3-b223-2d9e08ae30aa | checkpoint | 4 - Unsuitable Trench Foundation
211d6b25-fa70-5ca7-bbf4-f11ec1ca4bf6 | note | Acceptance Criteria: Where Unsuitable Material or potentially Unsuitable Material is encountered on the Site, the Contractor shall, before proceeding to remove or cover such material, Hold Point notify the Administrator,
1835bab0-197b-5508-b6e5-264bc6e3d189 | note | Reference -MRTS04 Cl13.3.2
8b774533-2f67-5c09-a214-aa0c450552e1 | note | Item Check - Hold Point
9eebd224-885a-40fd-aefd-6004ba4027b6 | signoff | Hold Point
fe94335b-aaaa-428c-a23d-d58c42b0f013 | checkpoint | 5 - Trench Foundation
d34782ef-21a2-55d4-9e07-e53c2af6dcb3 | note | Acceptance Criteria: Testing: Bottom of Excavation. Minimum Compaction 95%. CBR - Min Bearing Capacity 150KPa, 1 test per 20LM / Per Drainage
b99cb199-c64d-5d44-b642-21eb50108458 | note | Reference - MRTS04 CL13.3.7
91037835-028b-5365-95ee-cf59ad63727f | note | Item Check - Check and Verify
13091c74-8214-47ad-934f-f18b635e6e71 | checkpoint | 6 - Drainage of Bedding Materials
3fd083c3-44c3-5471-9e67-f894dd7e0498 | note | Acceptance Criteria: Upstream of each headwall, manhole, or gully (other than an end of line gully), a 3.0 metre length of 100mm diameter sub-soil drainage pipe has been laid in the bedding material
bb8cc1a4-ded6-5f76-b77b-e2ea3751762c | note | Reference - Note 1 IPEA STD DRW DS-031
09a683cc-35c7-5208-8d62-08e985db3626 | note | Item Check - Check and Verify
26324316-f131-4fe1-9a4e-223c5259193c | checkpoint | 7 - RCBC Special Requirements
11971175-6c42-5640-8f46-5e4cbb2495ca | note | Acceptance Criteria: Box Culvert components shall generally be installed in accordance with details shown on Base Slab: TMR Standard Drawing 1318 Culvert Installation: IPEA DS-031 and Project Drawings
4451964a-3188-58b7-87c6-3d1946886f70 | note | Reference - MRTS03 IPEA STD DRW DS-031
f93cc85c-3691-5da1-a229-da6715946dba | note | Item Check - Check and Verify
beb79fab-3750-46ed-a495-ad3239e3c427 | checkpoint | 8 - Material Requirements
87e4acd5-4603-545c-827d-ee226135392d | note | Acceptance Criteria: Precast box culvert components and spanning slabs shall comply with MRTS24 Manufacture of Precast Concrete Culverts.
7d712f53-f878-5238-b1ae-31c4d336961f | note | Reference - MRTS03 CL. 10.2
1c50930d-9974-597a-b220-e2b67aa5a6a8 | note | Item Check - Check and Verify
44e662a0-ceda-440d-b1e6-2ee5a8e2672d | checkpoint | 9 - Bandage Cover Materials
9bc2d203-f537-501e-b8f4-63e656bf00eb | note | Acceptance Criteria: Where Bandage covers are used for culverts, Bandages shall have properties appropriate to the sealing requirements and shall be made available for inspection and acceptance by the Administrator prior to commencement of installation. Denso 600 - Min 75mm Wide - IPEA STD DRW DS-031 Note 4
1d6d29d3-3af4-5df0-9759-972dee247e6c | note | Reference - MRTS03 Cl 11.2
0c3c8024-d735-5295-965a-f4ac5ecfe6e2 | note | Item Check - Hold Point
9c98203a-08aa-4acb-84fc-3b56713699eb | signoff | Hold Point
7e7df6f0-7211-4538-9b0b-6fb253263197 | checkpoint | 10 - Survey
63c5f3dd-175f-552a-829d-e6d3b47fb310 | note | Acceptance Criteria: Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met and notice of such works provided to the Administrator
ff2612db-9cf1-5543-95b8-5c1c536aac99 | note | Reference - MRTS03 CL11.3.10
ed59fa6a-3b5e-57e7-859c-7b53f9701121 | note | Item Check - Hold Point
75dedcb6-55b5-4fd4-b6af-557dac0fe2f6 | signoff | Hold Point
23fd8d95-2412-4346-95af-f51397698761 | checkpoint | 11 - Geometric Tolerances
fbe11483-065b-517e-8129-2e24eeee64ef | note | Acceptance Criteria: Vertical: +- 10mm , Horizontal +- 100mm, Difference in Grade between actual and specified 1% (Absolute)
7f6605e7-cf73-562a-8db6-88ca2290896c | note | Reference - MRTS03 Cl8
acf12f8d-490c-5f0e-b8e7-f5b6ffea56ef | note | Item Check - Survey
2e4edce2-ae64-4852-ab6e-dfc3041e79ef | checkpoint | 12 - Backfill
acd15b3f-99ff-55ce-a59f-f424cc3c2450 | note | Acceptance Criteria: Backfilling of culverts shall not commence until all base slab has reached 100% F'C - Relaxation provided under RFI 003 28/7/25 - Minimum 32MPa required prior to backfilling culverts and Residential traffic Only.
b6d4ac4c-4b35-5e7d-a0cf-03e284bbde36 | note | Minimum Compaction 95%. 1 test per 100 m³ with 1 test in each Bedding/Haunch Zone, Side Zone and Overlay Zone - 2 Per lot min
6e70a051-dfeb-583f-aec2-5ab1619c709a | note | Reference - MRTS03 CL11.3.10
bc694629-83e3-5490-a55a-171b083cb53a | note | Item Check - HOLD POINT
15d9d3be-2f1c-49d4-a3fd-17e88ce05f1b | signoff | Hold point
3fac56b7-28f1-4d9e-a093-1a070ffa0922 | checkpoint | Final Verification
ca9472b4-63e6-5043-b61f-bde2333c325b | note | Name of Cient's Representative
6ba0066d-c2d3-5b7c-8aa0-71de5bb7a80e | textbox | Print Name:
3671037a-cbd0-50f1-be19-4c4c96602126 | date | Date:
6dab9467-f311-594c-969c-19e8e09d4173 | note | Name of Contractor's Representative
d840f978-4b66-5b3d-85b8-5c7619402899 | textbox | Print Name:
50529f09-0354-5be5-ab92-4e090f62825f | date | Date:
06a8bcc2-ccd8-4945-b9ea-0f8b8134218b | signoff | Signature
20ba1e1f-d6d5-49dc-87cf-a61e0d732e9a | section | Final Sign Offs (to be completed at closure of Lot)
e00ca3de-2ff9-42c5-9a8a-703451344178 | checkpoint | Agreed Quantities
7160a8bb-313e-4d0d-8652-e73d56eb2968 | signoff | Agreed Quantities Sign Off
1a9a7dd1-7495-4b14-9984-4859427b7d97 | checkpoint | Closure of Lot
244e1564-8adf-420a-b895-64e0c3bc8d75 | signoff | Closure of Lot Sign Off
40eac258-688e-49fc-8c86-23b00ef676a0 | checklist | RCP Installation | itp | RCP Installation
1fd9de82-d6ec-4822-9d08-6ee1ef613626 | section | Details
ed23d9b8-84d8-4b85-b442-5212d9edab76 | checkpoint | 1 - Lot Boundaries
3bfdc1c6-c607-5cd1-a281-593c2703d312 | note | Acceptance Criteria: Lot Number established with the Lot boundaries of the works clearly defined for traceability
e5254244-25de-54a0-b041-a8ea3347de39 | note | Reference -
0378a9f1-c1a5-5bb8-a9be-78fa03b8d392 | note | Item Check - Check and Verify
5e739909-7ee2-4deb-8485-27b49eb1b4e8 | checkpoint | 2 - Materials
eb45d05c-0433-54df-8048-501ff82a5b49 | note | Acceptance Criteria: Bed Zone Material: Crusher Run Recycled Concrete – 10mm Screenings (Note 5) Embedment Zone Material: Crusher Run Recycled Concrete – 10mm Screenings (Note 5) Backfill Material: Crusher Run Recycled Concrete – 10mm Screenings (Note 5) Refer RFI 013
2ec23440-46de-5df3-bf21-a915bb59f5d8 | note | Reference - Note 2 IPEA STD DRW DS-030
05abf32f-e22e-54fc-a62a-1097858f70e9 | note | Item Check - Check and Verify
626ff3a7-1422-4fe3-9d27-72c74dec2f12 | checkpoint | 3 - Excavation
134181d0-99ae-5c94-8acb-85b2b2747e6c | note | Acceptance Criteria: Excavations shall be constructed to the shapes, lines, dimensions, and other requirements shown on the drawings
48daafd1-33b7-512b-ad71-2ed3a78180d5 | note | Reference - MRTS04 Cl13.3.3.1
40e74f4c-c25e-5176-a0b2-b6a44500d8bb | note | Item Check - Check and Verify
540a01f7-cb4d-4971-9505-e2bec96b5114 | checkpoint | 4 - Unsuitable Trench Foundation
283183f8-e9a2-5757-9ad6-7ab4a2dd0bda | note | Acceptance Criteria: Where Unsuitable Material or potentially Unsuitable Material is encountered on the Site, the Contractor shall, before proceeding to remove or cover such material, Hold Point notify the Administrator,
c737fd36-d7bc-5f73-a7d1-08a796f2df31 | note | Reference - MRTS04 Cl13.3.2
271b64fe-c799-5f77-b34c-4ce1fa4ced65 | note | Item Check - Hold Point
7f773f25-bd3e-48a9-ac0d-a1247c16270b | signoff | Hold Point
3957d052-da05-4218-8b76-07751e554808 | checkpoint | 5 - Trench Foundation
3c522f9e-aac4-5488-b3aa-d67aa92da74e | note | Acceptance Criteria: Testing: Bottom of Excavation. Minimum Compaction 95%. 1 test per 20LM / Per Drainage
ed82d433-52d8-5af3-b5e1-b03464d575b1 | note | Reference - MRTS04 CL13.3.7
080e0276-c8b9-5e62-aa67-6561b9bb9866 | note | Item Check - Check and Verify
e7334cde-e4a2-4246-8fa5-36f86e1c4dfa | checkpoint | 6 - Drainage of Bedding Materials
ed01015a-f3dd-5148-9109-236c135d5113 | note | Acceptance Criteria: Upstream of each headwall, manhole, or gully (other than an end of line gully), a 3.0 metre length of 100mm diameter sub-soil drainage pipe has been laid in the bedding material
72e5560e-ef93-518e-a4ca-7f501fe533b2 | note | Reference - Note 1 IPEA STD DRW DS-030
562ffd83-93c8-58aa-b993-6e94c82746fb | note | Item Check - Check & Verify
2eecfc6a-83b3-4bbb-b835-04d4bd020545 | checkpoint | 7 - Pipe Laying
3955c25f-de82-5a53-b80c-4d0867df4a97 | note | Acceptance Criteria: Where spigot and socket joints are used, the thickness of bedding material under each socket shall not be less than 50 mm. Pipes shall be placed with their external grooved ends or spigot ends facing the culvert outlet. Where the word ‘TOP’ is marked on pipes or where lifting holes are provided, the pipes shall be laid with the word / hole uppermost. Lifting holes shall be plugged or otherwise closed off in accordance with the manufacturer’s instructions after the pipe is installed. Spigot and socket joints shall be made using the appropriate rubber rings
4db3e3c5-f05d-5a39-b21b-5edab35928da | note | Reference - MRTS03 CL11.3.5
422c551c-f62d-5c0e-8bab-21e51808764b | note | Item Check - Check and Verify
ec464628-1209-47f7-8d5c-b8aa16c03c44 | checkpoint | 8 - Survey
65b80dca-689b-5cd7-8aae-9dbbfd11b685 | note | Acceptance Criteria: Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met and notice of such works provided to the Administrator
c8ca8d38-d6a4-536e-b7ad-9f91c8b01c8d | note | Reference - MRTS03 CL11.3.10
11084b9f-9736-50bc-b273-aebde4571a77 | note | Item Check - Hold Point
509b89da-ca71-48a2-be41-2d33429eedac | signoff | Hold Point
b904fc48-e023-4142-a839-3108938bbc26 | checkpoint | 9 - Geometric Tolerances
4d7139de-f14c-58c5-8a17-2bcddd7cf3de | note | Acceptance Criteria: Vertical: +- 10mm. Horizontal +- 100mm, Difference in Grade between actual and specified 1% (Absolute)
d650891f-184c-563e-9b5a-2527f0b14b46 | note | Reference - MRTS03 Cl 8
df5ab839-c31c-5e29-98be-bd42868311ca | note | Item Check - Survey
7241cfcf-8a82-43e1-b04d-d13c946046df | checkpoint | 10 - Pipe Embedment Zone
f1763f72-3667-5399-97ab-d457ae00551c | note | Acceptance Criteria: Where Bandage covers are used for culverts, Bandages shall have properties appropriate to the sealing requirements and shall be made available for inspection and acceptance by the Administrator prior to commencement of installation.
cb4385c0-8a24-5117-89e7-e619c8b97cf9 | note | Reference - IPEA STD DRW DS-030
9a3869fb-53af-5beb-aec4-deffac4bcda4 | note | Item Check - Check and Verify
7a83a6b4-939a-40b8-ba86-233fe7c6dc9b | checkpoint | 11 - Pipe Backfill - Road Reserve
95f01b16-c28f-5717-ad02-8a7a5667ac67 | note | Acceptance Criteria:CMB Road Reserve: Pipe backfill Crusher Run Recycled Concrete – 10mm Screenings (Note 5), FRI 013
4c3ba8a3-f277-555a-badb-f7b7dd6276b6 | note | Reference - Note 5 IPEA STD DRW DS-030
bad2bcab-b7cf-5246-873e-ea3cac731513 | note | Item Check - Testing
f5c1d54e-4e72-44e3-baa3-0ada6ca557d8 | checkpoint | 12 - Pipe Backfill - Outside Road Reserve
850827f6-9a03-5522-87b4-268781964ba0 | note | Acceptance Criteria: Where stormwater pipe is laid in a drainage easement or property other than the road reserve, backfill material backfill material shall be excavated material provided adequate compaction can be provided. Minimum Compaction 95%. Compaction Testing: 1 test per 20LM / Per Drainage adequate compaction can be provided.
a74619e1-ac22-5680-be6b-f7994760c46b | note | Reference - Note 5 IPEA STD DRW DS-030
e9a7e52a-8218-5be4-b15a-86b5993b20a0 | note | Item Check - Testing
7016c78c-7a60-424f-9e2a-160d216ed028 | checkpoint | 13 - CCTV
4c0f198f-6583-55bb-a3fb-fd346a816697 | note | Acceptance Criteria: The contractor shall conduct inspections of the pipe culvert using CCTV in accordance with WSA 05-2013 Conduit inspection Report Code of Australia. Reports shall be submitted to the Administrator, and any rectification works completed, prior to acceptance of the culvert
8a528337-f470-54a0-bf57-0e10ab7c6e35 | note | Reference - MRTS03 CL11.3.5
c9c2982d-5dec-5eab-a5c1-e698548f0871 | note | Item Check - Hold Point
29da1051-943a-40d5-b0f7-8d5aa94e63fb | signoff | Hold Point
b83ced68-6ac2-442d-a67b-b19b0cac4395 | checkpoint | Final Verification
473a6e7c-183d-50e0-bc89-1bbad3bf7231 | note | Name of Cient's Representative
804bbfb9-fe30-5a37-b75d-aa2fd65c425b | textbox | Print Name:
e36fd448-655f-5454-9dca-1945fe66f73a | date | Date:
7cccd34c-557b-505d-bcd5-f5ff42f88978 | note | Name of Contractor's Representative
6edc319b-0ca7-5ffa-a971-88c9b3071d52 | textbox | Print Name:
c7991ebd-5c7a-5e04-84cb-864ca7c464c7 | date | Date:
c28249e2-fc7a-45cc-aeb8-587d039f8eff | signoff | Signature
9525d60a-69c7-491a-980d-cc511a5a6a7f | section | Final Sign Offs (to be completed at closure of Lot)
1089e134-bd4d-41ea-9525-f298734a137c | checkpoint | Agreed Quantities
1a2f523b-adc4-48ca-8171-8a902b03efe3 | signoff | Agreed Quantities Sign Off
cf496aad-6145-4b95-a26a-9072281572ae | checkpoint | Closure of Lot
9f60d041-cbce-4fa4-a08d-941ad540f62d | signoff | Closure of Lot Sign Off
7f2bbbe5-36fe-4a33-9f81-d40bda14fe59 | checklist | Subgrade | itp | Subgrade
f8103139-4cd6-4325-b766-27482542e493 | section | Details
b0c4ba12-c800-4e31-a6b1-4828bb88044e | checkpoint | 1 - Lot Boundaries
d3103db6-f8b9-5235-9f38-2d2254205663 | note | Acceptance Criteria: Lot Number established with the Lot boundaries of the works clearly defined for traceability within the works.
390fc194-1187-50eb-a9b4-96a7373cdadf | note | Reference - MRTS04 Clause 5.6
bbdfcde1-a772-5a91-87b7-1a89d64f1166 | note | Item Check - Check and Verify
45b2ee6d-79df-456b-8517-3436b36a8d7f | checkpoint | 2 - Proof Roll
36649e28-a565-5822-a89a-bcf0d571b4fe | note | Acceptance Criteria: At the completion of earthworks to Subgrade Level, the Contractor shall test for perceptible surface deformation by undertaking proof rolling.
4d15c8f5-6d9c-5748-9a0e-dba9c7f24747 | note | Due to works being completed within defined trench alignments and widths, proof roll of subgrade with a water truck or similar may not be achievable. The Contractor proposes proof roll to be completed at the top of gravel pavements. Refer RFI 012
a66c2b25-e15b-5eae-a542-9f74c79d7e5b | note | Reference - MRTS 04 Cl 18.3.2
0e75c386-ecfb-565c-a506-32af7ca768d5 | note | Item Check - WITNESS POINT 8
f237a297-558f-4d8b-b19a-592285b4b7ac | checkpoint | 3 - Testing - Compaction
f6935f44-c51e-5a28-9c88-80ec2e4eaf40 | note | Acceptance Criteria: Compaction - depth as per Clause 13.5 of Annexure MRTS04.1.
fab0d26c-dea1-50cc-9248-14ea742dbccf | note | Reference - MRTS04 Table A.2 - 2.1
c0d18612-d716-5e7c-83e2-b210ad3099e2 | note | Item Check - Test Reports 1 per 500m2 4 per lot
01252106-6dde-4369-8a25-7cd74357d22b | checkpoint | 4 - Geometrics - Straight Edge
d1628441-f900-5327-9284-b61d640e3dcc | note | Acceptance Criteria: The gap beneath a three metre-long straight-edge placed anywhere on the surface at Subgrade Level shall not exceed 25 mm, due allowance being made for design shape where relevant.
6bfbb533-9dfd-5a0e-9ad3-257f99d0ceeb | note | Due to works being completed within defined trench alignments and widths less than 3m, this will be completed where possible
033f5e83-52f0-56c7-929a-a1b6b87a9fb0 | note | Reference - MRTS04 Table A.2 - 2.1
224a161e-de67-53bc-b26f-d6a8dfc559c9 | note | Item Check - Test Reports 1 test per 20 m.
60ff824a-a0df-4910-9a8d-e16e1ce07a69 | checkpoint | 5 - Geometrics - Survey
8ccf4104-219a-5cf2-9444-20e67f880e69 | note | Acceptance Criteria: The heights of earthworks measured anywhere on a layer surface shall not vary from those shown on the drawings, or calculated in accordance with Clause 6.1, by more than the tolerance stated in Table 6.3.1 unless specified otherwise. Subgrade Level (Individual Results): ± 25mm, Subrade Level (Average): ± 10
eba0845c-949c-5a3d-aa3f-6e3177bcfde1 | note | Reference - MRTS04 Table A.2 - 2.1
c0f09a9e-bda7-5552-8b51-68a72da17500 | note | Item Check - Survey at 20 m intervals.
b939f50b-bd1e-4b7f-bb91-3faaa102c2cd | checkpoint | 6 - Seperation Layer
49284a7a-ca71-54f3-88f4-302a4d73aa65 | note | Acceptance Criteria: Installation of Geofabric seperation layer above Embedment zone at subgrade below pavement layers
46d735da-4a3d-58fe-8c62-43f4728e60c1 | note | Reference - RFI012
f73b9d3b-3f07-5570-a8fa-16c0f2c881fe | note | Item Check - Check and Verify
00af1c95-6c9a-4475-9b6b-9fd8f0082b97 | checkpoint | Final Verification
c40a24c1-7273-5fe8-945c-96206e51572c | note | Name of Cient's Representative
8bcc832a-b6bf-5244-b6e4-d27826cd9dee | textbox | Print Name:
9eacaea8-5d5d-52ea-8a20-d2f9d6074969 | date | Date:
af0934f5-c41e-5d3f-b0cd-6a280eccddd4 | note | Name of Contractor's Representative
0e985589-721c-55fd-a8ab-6478062a7fba | textbox | Print Name:
3474071b-c5e5-54a0-a45e-8a8705bc6ab1 | date | Date:
21509fa9-9f94-4219-bf02-e411520d1bd3 | signoff | Signature
a279a8de-f759-40d7-87d4-21436456ded4 | section | Final Sign Offs (to be completed at closure of Lot)
e3a13f83-ea4b-4d5b-a04a-71987a44ef01 | checkpoint | Agreed Quantities
aa9f9e8a-b954-4e5f-a999-8e02c5813e52 | signoff | Agreed Quantities Sign Off
0b8b07b7-a8ea-4bcf-9560-f1630b315117 | checkpoint | Closure of Lot
59014068-8cc2-49bf-953d-5306302b2150 | signoff | Closure of Lot Sign Off
6693b2b8-f7d8-4f8a-96ad-ed8495ca5dcf | checklist | Unbound Pavements | itp | Unbound Pavements
470bc22d-54dc-4f42-bad5-a76a6b947d57 | section | Details
95547bd7-0eba-40eb-a535-f994205b542f | checkpoint | 1 - Lot Size
b9ab9556-b193-51e1-ab78-c73b166b39eb | note | Acceptance Criteria: Define lot size. Maximum lot size for unbound pavements is 5000 tonnes for supply and the lesser of "A single continuous layer completed in one day's production" and 500m for construction.
99248996-e0ea-5841-815d-a1e27d2a80f2 | note | Reference - MRTS05 App. A Table A1
7cfff779-bb00-5140-a8ac-dc8ca57ad2fe | note | Item Check - MILESTONE
c3c753ab-5199-4370-9540-c645427ae98d | signoff | Milestone
0368317c-3d9f-43c0-b782-ee2d0b020641 | checkpoint | 2 - Submission of Registration Certificate per quarry
6dc93c60-a10b-5fcf-8d29-2133f053a9fd | note | Acceptance Criteria: Copies of current Quarry Registration Certificate (Type 1, 2 or 3) or quarry assessment (Type 4) forwarded to the Administrator at least 7 working days before material deliveries to the stockpile / pavement are to commence.
1b3241b9-e144-5a36-9187-5007f566afdf | note | Reference - MRTS05 Cl.6.2
846934eb-2c15-5f2f-a98b-0ef97cd2709d | note | Item Check - MILESTONE
3148d779-7a96-472b-a9f6-f24b0fb0ceba | signoff | Milestone
7cb7c273-6544-4121-a729-0883118e901a | checkpoint | 3 - Approval of procedure by from the Administrator
ff55305b-baf1-5681-aaa6-a31ae44ceaf4 | note | Acceptance Criteria: No unbound pavement works shall commence until all relevant construction procedure have been accepted by the Administrator.
e12226d8-f1fe-59e2-8685-fd5d3c454e04 | note | Reference - MRTS05 Cl 5.2.1
3f89aaaa-7623-5757-b0a6-5a3014f15dbd | note | Item Check - HOLD POINT
fe65d29e-8ece-472e-a7b1-4fd449d2d45a | signoff | Hold Point
730b7ed8-535f-451b-a75c-d91e6d94eb19 | checkpoint | 4 - Submission of production procedure
823044d0-1bca-580b-a736-835c65864204 | note | Acceptance Criteria: The Material Production Procedures shall be submitted to the Administrator at least seven days prior to the commencement of material production for the Works.
dc9eebe6-7c61-5f71-9c20-c54bc414f504 | note | Reference - MRTS05 Cl 5.2.2
b0464013-02e1-51fa-a754-07144c9b65c1 | note | Item Check - MILESTONE
d8bef157-836e-435c-b4e0-a17204763c3a | signoff | Milestone
ea664499-6c5d-49b3-bec4-698c89cbd051 | checkpoint | 5 - Written Permission from Administrator
e8f7f36b-fa90-5383-9e78-81bfc442e95c | note | Acceptance Criteria: The written permission from the Administrator to use the quarry or source is required prior to material being supplied to or used in the works.
24db5810-30ec-537c-8109-891a578546cc | note | Reference - MRTS05 Cl.6.1
695136ee-4495-5b34-acec-27e95724139f | note | Item Check - HOLD POINT
f27b04a4-4ed9-4ecd-ae02-141dca5e6c7d | signoff | Hold Point
91ba6a0b-76e9-4f52-9c18-350c550aec87 | checkpoint | 6 - Layer Thickness
70ac9845-7101-5580-9a5d-c3f2e9f42e39 | note | Acceptance Criteria: Layer Thickness between 75mm and 250mm in accordance with table 8.3.3.
e3310085-9483-5ba6-a4a6-5090934092d1 | note | Reference - MRTS05 Table 8.3.3
eaddca79-d1d1-5111-87c3-f49846dbb53b | note | Item Check - Check & Verify
185707a1-085b-4ad8-a0e4-48e7e7df6820 | checkpoint | 7 - Relative Dry Density
f095c4df-8a6c-5c13-9b45-8778fe344e63 | note | Acceptance Criteria: Relative Dry Density Requirements: CV of RDD >= 100% MDD for Type 1 Materials | 100% SDD for type 2.3, 2.4 and 2.5.
a3fbe856-f0ea-5452-ad1e-f64aef12f1de | note | Reference - MRTS05 Table 8.4.3
5d269c0b-66eb-5613-9744-fb35c04a5fa7 | note | Item Check - Check & Verify
f9e0e002-15c1-4284-9e7c-3eb4abf79db1 | checkpoint | 8 - Trial Placement
2334d33a-6e9e-534f-93d9-eb36dbeaff93 | note | Acceptance Criteria: Unless agreed otherwise, a trial placement of materials of a minimum size of 1000m2 is required.
7eaac4a2-d261-59ff-a742-d910800e6811 | note | Reference - MRTS05 Cl. 8.2
23266265-c764-5270-ae91-9f6392ef05ee | note | Item Check - HOLD POINT
2175cf8d-2b84-4ee9-932b-318aa995c4ab | signoff | Hold Point
aa77483f-3761-4183-8ae3-076e318ddd30 | checkpoint | 9 - Moisture Content
30873c7e-1ed0-5fdd-a0b3-ba64344707b2 | note | Acceptance Criteria: Moisture content such that the degree of saturation is less than 60%(modified). The administrator may accept a higher level of moisture up to a maximum of 70%. S < 60% (1 test / 500m2, min 4 / lot)
319c5fcb-44c6-517f-83a5-2ac515f3e373 | note | Reference - MRTS05 Table 8.3.4.1
bd700ce3-37c4-5c66-9d09-755dfe956f31 | note | Item Check - HOLD POINT
a02fa294-8477-49c4-87af-bc8031f9b1f0 | signoff | Hold Point
88f78137-f587-493f-91d8-5322576f274c | checkpoint | 10 - Segregation of Material
29bb1cd2-2b25-5d15-91bc-12aeba1cc30d | note | Acceptance Criteria: No visible segregation of material. Particle Size Distribution Q103A. Min 1 per lot | Additional tests as directed by the Administrator.
90061456-5ef3-5506-af12-0e2520fb4de6 | note | Reference - MRTS05 Table A3
3075ac25-2742-5225-b183-c16732ca9e37 | note | Item Check - Check & Verify
b1f467c5-807e-40f6-a711-89179a82cc7e | checkpoint | 11 - Geometric Tolerances
b8a2f498-6916-57bc-a5a9-7ebfee91c17b | note | Acceptance Criteria: ±10mm when covered by AC | ±15 mm in all other cases (1 test / 20m)
a1fcb3ce-efbe-54ff-a0ca-eba095ce0809 | note | Reference - MRTS05 Cl.8.4.4.2 Table A4
25e862f3-f2f7-5e0e-b709-700ea9a8e30c | note | Item Check - Check & Verify
d49193db-0cff-4c66-8f6b-dbd825967b4e | checkpoint | 12 - Straight Edge
a5882f83-84e0-5727-8cf6-62697c50a0df | note | Acceptance Criteria: Deviation from a 3m straight edge shall be less than 5mm. 1 test per 20m.
a174eb6e-85dc-5052-9cf6-3e48b6df8c78 | note | Reference - MRTS05 Cl. 8.4.5
2586ff7a-b4f1-54da-bfa4-4510e9dd238e | note | Item Check - Check & Verify
740b955b-d4f4-4bc7-9036-c2aef78233c0 | checkpoint | 13 - Proof Roll
82b112ea-185f-58e3-b4fc-a55abe4c0e4c | note | Acceptance Criteria: Each unbound pavement layer shall be tested for perceptible surface deformation by 'proof rolling' the pavement, in the presence of the Administrator.
3d3e6560-9c2f-5ea9-8335-c5416c77c486 | note | Reference - MRTS05 Cl.9.4.7
6daffbe0-08b5-5757-8649-4a1415eff554 | note | Item Check - WITNESS POINT
fbef88b1-aed0-443a-9474-f84a5bd13af6 | signoff | Witness Point
78218b73-4aeb-45b6-9977-b49db78c2844 | checkpoint | 14 - Geometrics
9adf9297-7339-5de3-bf74-477aa31370a6 | note | Acceptance Criteria: The crossfall shall not depart from the corresponding crossfall shown in the Contract by more than 0.5% absolute. (1 test / 25m)
120c7a87-373a-5cac-b665-3a3036ba9051 | note | Reference - MRTS05 Cl.8.4.4.4
a9b2f5c6-184e-55f2-bb6f-a96a1e398f38 | note | Item Check - Check & Verify
c3c74d94-2f81-46ec-8174-1e3fc8611c7b | checkpoint | 15 - Visual Inspection
90b3657f-9507-565c-be29-ca52707122f0 | note | Acceptance Criteria: The finished surface of any unbound pavement layer shall: be hard and homogenous in appearance, not have any loose, segregated or contaminated areas, have the coarse particles slightly exposed, not be affected by delamination, and not visibly deflect under load when proof rolled.
8a0c08b9-3d72-596a-bd21-a6704db36ff3 | note | Reference - MRTS05 Cl.8.3.5.1
577a5fd1-4707-52ef-a0b2-1b88399a04c1 | note | Item Check - Check & Verify
5161ac58-b27d-4c20-9989-275391271b9a | checkpoint | 16 - Material Incorporation into Works
c4987301-b6ab-54eb-86a5-a90a1726507f | note | Acceptance Criteria: The Contractor shall not incorporate materials into the work unless it has demonstrated that the material complies fully with the requirements of this Technical Specification before delivery of the material to site.
d07ee4b8-77bc-50d6-b7eb-5a2176a5229f | note | Reference - MRTS05 Cl.9.1
f372fe89-4815-5cfe-a692-6c9c7a4d4d7a | note | Item Check - HOLD POINT
cefe013b-9487-4dd2-b4d4-fefcfbcc70f7 | signoff | Hold Point
893bbab8-0e3b-4d6f-9011-37ed26ca3cec | checkpoint | 17 - Survey
69c991f2-503b-58fe-80a0-65c1091ad6e1 | note | Acceptance Criteria: No layer shall be covered until a) all testing is complete, b) surface finish complies with Clause 8.3.5, c) test results meet spec or corrective actions accepted, d) Administrator inspects the layer, e) As Constructed Survey is completed per MRTS56 and notice is provided.
a54c2c15-0219-5346-b573-fdfef0f3294b | note | Reference - MRTS05 Cl.9.5.1
7cc4df10-06ff-55e3-8fd6-2944edc6e0ce | note | Item Check - HOLD POINT
b2b74f62-7ce3-46bc-bcc5-2801bd2c6388 | signoff | Hold Point
b8fd62a9-a45d-4021-8970-88d5003d0cc9 | checkpoint | Final Verification
91eaa263-c308-5d19-9181-fd0373c38d6c | note | Name of Cient's Representative
ff0375f4-5f85-5a3b-a604-bb4054b67f52 | textbox | Print Name:
c2f265a7-bfe1-51d1-ab8a-780e4a39b69e | date | Date:
2c0ae5fe-4c98-5a04-86af-a0f95d3c29d4 | note | Name of Contractor's Representative
467ec4ec-b6db-5381-91ee-1ff8ef2dabe0 | textbox | Print Name:
6fb4844d-9008-53c8-b3f4-b71c600816b7 | date | Date:
aa52ee96-7242-4f16-8c75-8ab285a5d523 | signoff | Signature
0a90fdca-c323-441f-8e72-81366893356b | section | Final Sign Offs (to be completed at closure of Lot)
f2668931-1762-4984-9645-66e001f1ac0d | checkpoint | Agreed Quantities
2c49d6e0-5592-4c41-9e38-679954f29a17 | signoff | Agreed Quantities Sign Off
35dcd2a3-97be-4f3d-afc6-14e160a59ee5 | checkpoint | Closure of Lot
86348565-2dd4-40f5-bede-c579c878fc98 | signoff | Closure of Lot Sign Off