## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-290-STR-Precast Barriers, Parapets & Kerbs (Supply & Installation)
ITP Description: |  | Precast Barriers, Parapets & Kerbs (Supply & Installation)
Document Number (in Teambinder): |  | 290
Discipline (e.g. CIV/STR/RAIL: |  | STR
Revision Number: |  | 1
Revision Date: |  | 2025-08-05
ITP created by: |  | Manwel KALYANA
ITP approved for use by: |  | Pradeep Talasila
Special Notes to ConQA Team : |  | ITP for Hopkins road only
Inspection & Test Plan - Precast Barriers, Parapets & Kerbs (Supply & Installation)
|  |  | Document No.: | 290 |  |  |  |  | Revision: | 1
[9 empty] | Date: | 2025-08-05
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 610 June 2020 VicRoads Section 620 May 2009 VicRoads Section 630 October 2013 VicRoads Section 671 October 2013 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.2 | IFC Drawings | MRP-AURE-TRANS-004617-MRP-DPK-102-00-CBR-0031 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.3 | IFC Drawings | MRP-AURE-TRANS-004617-MRP-DPK-102-00-CBR-0032 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 | Preliminaries
2.1 | Grout | MRPA Quality Management Plan 610.33 | Details of the grout to be placed between adjacent barriers and lifting lug/anchor recess to be submitted for review to the Nominated Authority. Cementitious grouts shall be as a minimum Type C Class dual shrinkage compensating.and shall have a 28 day characteristic strength of 50MPa UNO. Grout shall acheive a minimun 80% of the 28 days strength prior to loading. Lifting lug/anchor recess to be filled with 40MPa minimum strength grout or approved equivalent Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each product | HP | Nominated Authority | This ITP
2.2 | Epoxy Adhesive | MRPA Quality Management Plan | Details of epoxy adhesive used to install steel bearings to bridge deck/foundation to be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each product | HP | Nominated Authority | This ITP
2 | Preliminaries (Continued)
2.3 | Abelflex | MRPA Quality Management Plan | Details of the Abelflex to be placed between the precast elements to be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each product | HP | Nominated Authority | This ITP
3 | Preliminaries - Documentation
3.1 | IFC Drawings | MRPA Quality Management Plan | Check the revision of the IFC drawings are current as per the drawing register (on Teambinder) | Document Review | Prior to starting Works and at regular intervals | HP* | All | This ITP Signed Off
3.2 | Precast Elements | IFC Drawings 610.47 (a) Table 610.473 (Feb 2020) | Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of: i. Certificate of Compliance / Birth Certificate ii. Compressive strength test results iii. Precast Lifting Design iv. Pre-pour check sheet / ITP v. Post-pour check sheet / ITP vi. Covermeter check record vii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast shown on table 610.473 (Feb 2020). Note: Different revisions of 610 have different clause numbers Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here) | Document Review | Each element | HP | PE/SE/SPE | This ITP
3.3 | Bridge Deck / Foundation Compressive Strength | 671.03 610.32 | "For Precast elements installed on bridge deck, check that the 7 day compressive strength as shown on the IFC Drawings has been achieved. Further to the requirements of clause 610.16 and clause 610.23, bridge decks, deck overlays and approach slabs shall not be loaded or opened to traffic until the concrete is at least 4 days (96 hours) old and not before a minimum compressive strength of 32 MPa after casting has been achieved." | Document Review | Each installation location | IP | SE/PE/SPE | This ITP
4 | Pre-installation Activities
4.1 | Survey Set-out of Precast Elements | IFC Drawings 610.47 (a) Table 610.472 (Feb 2020) | Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.472 as applicable to the element. Where anchor bolts are cast in to the concrete, ensure that these are within tolerance. If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast. Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius. | Measure Visual | Each element | IP | Surveyor SE/PE/SPE | This ITP
4.2 | Hold-down Bracket Levelling Bolt Bearing Plate Placement | IFC Drawings Product TDS | Mix the epoxy adhesive in accordance with the product TDS and apply to the back face of the steel bearing plates. Place the epoxied plates onto the survey marks and ensure that the area level. | Measure Visual | Where applicable, each installation location | IP | Surveyor SE/PE/SPE | This ITP
4 | Pre-installation Activities (Continued)
4.3 | Bearing Shims or Bearing Strip Placement | IFC Drawings | Place the bearing shims, strip or variety of shims to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances. Note: If the precast elements are to be grouted, the minimum and maximum thicknesses of the bearing will determine the product for the grouting activities (usually 10mm min.) | Measure Visual | Where applicable, each installation location | IP | Surveyor SE/PE/SPE | This ITP
4.4 | Sealing Strips, Backing Rod & Bitumen Board | IFC Drawings | Adhere any sealing strips, backing rod or bitumen impregnated fibre-board into the positions shown on the IFC Drawings or where grout or concrete ingress will affect the end use (such as around conduits). Backing rod should be compressed enough to prevent movement during the concrete or grout pouring activities. | Measure Visual | Where applicable, each installation location | IP | Surveyor SE/PE/SPE | This ITP
4.5 | Materials Inspection Checklist | 620.06 620.07 MRPA Quality Management Plan | General inspection of precast elements for defects including cracks, damage, exposed reinforcement and where applicable, damage to coatings. Confirm that the cast in lifters (anchors or loops) are the correct size and orientation as per the Precast Lifting Design (they should be clearly labelled on the end to be connected to). Elements shall have unique identification and orientation marked (if applicable). Complete: Materials Inspection Checklist in ConQA | Measure Visual | Each element | IP | SE/PE/SPE | This ITP
5 | Installation Activities
5.1 | Precast Handling | 620.07 Crane Lift Study | Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times. | Visual | Each element | IP | SE/PE/SPE | This ITP
5.2 | Precast Placement | IFC Drawings 610.27 | Precast elements shall be placed onto the bearing shims and not released from the crane until sufficiently braced or restrained by bolted connection, in accordance with the approved temporary works design and/or IFC drawings. Make any adjustments necessary by lifting the unit and adding/removing shims or adjusting the levelling bolts so that alignment between units, overall height and position remains in tolerance. The nominal gap between elements is as per the IFC Drawings. Departure from plan position 25 mm Departure from alignment 5 mm Irregularities in alignment 3 mm in 3 m Variation in joint gap width 3 mm SD3902, for all TL rated barriers (a) Departure from plan position: ±20 mm (b) Departure from alignment: ±20 mm (c) Seperation between barriers 10mm ±5mm The nominal gap between elements is as per the IFC Drawings. | Measure Visual | Each element | IP | Surveyor SE/PE/SPE | This ITP
5.3 | Draw-string in Service Ducts | IFC Drawings 671.03 | Place a continuous length of 3mm galvanised wire or high-strength nylon draw string so that it can be terminated at any junction boxes. | Visual | Where applicable, each element | IP | SE/PE/SPE | This ITP
5.4 | Hold-down Bracket Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S) | IFC Drawings 630.20 (a) & (c) AS5131 Clause 8.3 | Place washers and nuts onto the embedded thread as detailed on the IFC Drawings. Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater. Tighten with a few impacts of an impact wrench or the full effort of a person using a podger spanner. Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm. | Visual | Where applicable, each bolted connection | IP | SE/PE/SPE | This ITP
5.5 | Precast Traceability | 620.09 | All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number. Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report | Visual | Each element | IP | SE/PE/SPE | This ITP
6 | Post-installation Activities
6.1 | Joint Sealant Application | IFC Drawings | The gap between each precast element or at interfaces with other structures should be sealed with an the approved sealant on top of a backing rod. | Visual | Where applicable | IP | Surveyor SE/PE/SPE | Grout Pedestals & Bearings ITP
6.2 | Flowable Grout Pour | IFC Drawings | Grout shall be poured at connections between elements and/or in the gap between the bottom of the precast element and top of the bridge deck/foundation following full sealant application. Complete: Grout Pedestals & Bearings ITP | Visual | Where applicable | IP | Surveyor SE/PE/SPE | Grout Pedestals & Bearings ITP
6.3 | Barrier Railing | IFC Drawings | Where applicable. Complete: Structural Steel Barrier Rail (Supply & Installation) ITP. | Document Review | Where applicable | IP | Surveyor SE/PE/SPE | Structural Steel Barrier Rail (Supply & Installation) ITP
6.4 | As-built Survey | IFC Drawings 610.47 (a) Table 610.472 (Feb 2020) SD3902 | Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 (November 2018) or 610.472 (March/June 2019) as applicable to the element. Departure from plan position 25 mm Departure from alignment 5 mm Irregularities in alignment 3 mm in 3 m Variation in joint gap width 3 mm SD3902, for all TL rated barriers (a) Departure from plan position: ±20 mm (b) Departure from alignment: ±20 mm (c) Seperation between barriers 10mm ±5m Attach: Survey As-builts / Survey Report | Document Review | Each element | IP | Surveyor SE/PE/SPE | This ITP
6.5 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /

## Sheet2
Precast elements shall be placed onto the hold-down bolt locations and not released from the crane until sufficiently braced or restrained by bolted connection, in accordance with the approved temporary works design and/or IFC drawings.
Adjustments to be made to achieve following tolerances:
VR 670.05, for all medium performance barriers
(a) Departure from plan position: ±25 mm
(b) Departure from alignment: ±5 mm
(c) Irregularities in alignment ±3 mm in 3 m
(d) Variation in joint gap width ±3 mm
(e) Concrete cover 0 to +5mm
SD3902, for all TL rated barriers
(a) Departure from plan position: ±20 mm
(b) Departure from alignment: ±20 mm
(c) Seperation between barriers 10mm ±5mm
The nominal gap between elements is as per the IFC Drawings.