## res_ITP-217-CIV-HOP-Subgrade Pr
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-290-STR Precast Barriers & Kerbs (Supply & Installation) | itp |  |  |  |  | ITP-290-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-290-STR-Precast Barriers, Parapets & Kerbs (Supply & Installation)
label | ITP Description: Precast Barriers, Parapets & Kerbs (Supply & Installation)
label | Discipline (e.g. CIV/STR/RAIL): STR
label | Revision Number: 1
label | Revision Date: 5/08/2025
label | ITP created by: Manwel KALYANA
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - VicRoads Section 610 June 2020
label | ○ VicRoads Section 620 May 2009
label | ○ VicRoads Section 630 October 2013
label | ○ VicRoads Section 671 October 2013
label | 1.2 - IFC Drawings
label | Reference - MRP-AURE-TRANS-004617-MRP-DPK-102-00-CBR-0031
label | 1.3 - IFC Drawings
label | Reference - MRP-AURE-TRANS-004617-MRP-DPK-102-00-CBR-0032
section | 2. Preliminaries
checkpoint | 2.1 - Grout
label | Reference - MRPA Quality Management Plan 610.33
label | Acceptance Criteria - Details of the grout to be placed between adjacent barriers and lifting lug/anchor recess to be submitted for review to the Nominated Authority.
label | ○ Cementitious grouts shall be as a minimum Type C Class dual shrinkage compensating.and shall have a 28 day characteristic strength of 50MPa UNO. Grout shall acheive a minimun 80% of the 28 days strength prior to loading.
label | ○ Lifting lug/anchor recess to be filled with 40MPa minimum strength grout or approved equivalent
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once, for each product
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Epoxy Adhesive
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Details of epoxy adhesive used to install steel bearings to bridge deck/foundation to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once, for each product
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Abelflex
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Details of the Abelflex to be placed between the precast elements to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once, for each product
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries - Documentation
checkpoint | 3.1 - IFC Drawings
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | Method - Document Review
label | Frequency - Prior to starting Works and at regular intervals
label | Category - HP*
label | Responsibility - All
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 3.2 - Precast Elements
label | Reference - IFC Drawings 610.47 (a) Table 610.473 (Feb 2020)
label | Acceptance Criteria - Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | i. Certificate of Compliance / Birth Certificate
label | ii. Compressive strength test results
label | iii. Precast Lifting Design
label | iv. Pre-pour check sheet / ITP
label | v. Post-pour check sheet / ITP
label | vi. Covermeter check record
label | vii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast shown on table 610.473 (Feb 2020).
label | ○ Note: Different revisions of 610 have different clause numbers
label | ○ Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
label | Method - Document Review
label | Frequency - Each element
label | Category - HP
label | Responsibility - PE/SE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Bridge Deck / Foundation Compressive Strength
label | Reference - 671.03, 610.32
label | Acceptance Criteria - For Precast elements installed on bridge deck, check that the 7 day compressive strength as shown on the IFC Drawings has been achieved.
label | ○ Further to the requirements of clause 610.16 and clause 610.23, bridge decks, deck overlays and approach slabs shall not be loaded or opened to traffic until the concrete is at least 4 days (96 hours) old and not before a minimum compressive strength of 32 MPa after casting has been achieved.
label | Method - Document Review
label | Frequency - Each installation location
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
section | 4. Pre-installation Activities
checkpoint | 4.1 - Survey Set-out of Precast Elements
label | Reference - IFC Drawings 610.47 (a) Table 610.472 (Feb 2020)
label | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.472 as applicable to the element.
label | ○ Where anchor bolts are cast in to the concrete, ensure that these are within tolerance.
label | ○ If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast.
label | ○ Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius.
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.2 - Hold-down Bracket Levelling Bolt Bearing Plate Placement
label | Reference - IFC Drawings, Product TDS
label | Acceptance Criteria - Mix the epoxy adhesive in accordance with the product TDS and apply to the back face of the steel bearing plates.
label | ○ Place the epoxied plates onto the survey marks and ensure that the area level.
label | Method - Measure, Visual
label | Frequency - Where applicable, each installation location
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.3 - Bearing Shims or Bearing Strip Placement
label | Reference - IFC Drawings
label | Acceptance Criteria - Place the bearing shims, strip or variety of shims to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances.
label | ○ Note: If the precast elements are to be grouted, the minimum and maximum thicknesses of the bearing will determine the product for the grouting activities (usually 10mm min.)
label | Method - Measure, Visual
label | Frequency - Where applicable, each installation location
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.4 - Sealing Strips, Backing Rod & Bitumen Board
label | Reference - IFC Drawings
label | Acceptance Criteria - Adhere any sealing strips, backing rod or bitumen impregnated fibre-board into the positions shown on the IFC Drawings or where grout or concrete ingress will affect the end use (such as around conduits).
label | ○ Backing rod should be compressed enough to prevent movement during the concrete or grout pouring activities.
label | Method - Measure, Visual
label | Frequency - Where applicable, each installation location
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.5 - Materials Inspection Checklist
label | Reference - 620.06, 620.07 MRPA Quality Management Plan
label | Acceptance Criteria - General inspection of precast elements for defects including cracks, damage, exposed reinforcement and where applicable, damage to coatings.
label | ○ Confirm that the cast in lifters (anchors or loops) are the correct size and orientation as per the Precast Lifting Design (they should be clearly labelled on the end to be connected to).
label | ○ Elements shall have unique identification and orientation marked (if applicable).
label | ○ Complete: Materials Inspection Checklist in ConQA
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
section | 5. Installation Activities
checkpoint | 5.1 - Precast Handling
label | Reference - 620.07 Crane Lift Study
label | Acceptance Criteria - Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.2 - Precast Placement
label | Reference - IFC Drawings 610.27
label | Acceptance Criteria - Precast elements shall be placed onto the bearing shims and not released from the crane until sufficiently braced or restrained by bolted connection, in accordance with the approved temporary works design and/or IFC drawings.
label | ○ Make any adjustments necessary by lifting the unit and adding/removing shims or adjusting the levelling bolts so that alignment between units, overall height and position remains in tolerance.
label | ○ The nominal gap between elements is as per the IFC Drawings.
label | — Departure from plan position: 25 mm
label | — Departure from alignment: 5 mm
label | — Irregularities in alignment: 3 mm in 3 m
label | — Variation in joint gap width: 3 mm
label | ○ SD3902, for all TL rated barriers
label | (a) Departure from plan position: ±20 mm
label | (b) Departure from alignment: ±20 mm
label | (c) Seperation between barriers 10mm ±5mm
label | ○ The nominal gap between elements is as per the IFC Drawings.
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.3 - Draw-string in Service Ducts
label | Reference - IFC Drawings 671.03
label | Acceptance Criteria - Place a continuous length of 3mm galvanised wire or high-strength nylon draw string so that it can be terminated at any junction boxes.
label | Method - Visual
label | Frequency - Where applicable, each element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.4 - Hold-down Bracket Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
label | Reference - IFC Drawings 630.20 (a) & (c) AS5131 Clause 8.3
label | Acceptance Criteria - Place washers and nuts onto the embedded thread as detailed on the IFC Drawings.
label | ○ Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
label | ○ Tighten with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
label | ○ Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
label | Method - Visual
label | Frequency - Where applicable, each bolted connection
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.5 - Precast Traceability
label | Reference - 620.09
label | Acceptance Criteria - All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
label | ○ Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
section | 6. Post-installation Activities
checkpoint | 6.1 - Joint Sealant Application
label | Reference - IFC Drawings
label | Acceptance Criteria - The gap between each precast element or at interfaces with other structures should be sealed with an the approved sealant on top of a backing rod.
label | Method - Visual
label | Frequency - Where applicable
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - Grout Pedestals & Bearings ITP
date | Date Completed:
checkpoint | 6.2 - Flowable Grout Pour
label | Reference - IFC Drawings
label | Acceptance Criteria - Grout shall be poured at connections between elements and/or in the gap between the bottom of the precast element and top of the bridge deck/foundation following full sealant application.
label | ○ Complete: Grout Pedestals & Bearings ITP
label | Method - Visual
label | Frequency - Where applicable
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - Grout Pedestals & Bearings ITP
date | Date Completed:
checkpoint | 6.3 - Barrier Railing
label | Reference - IFC Drawings
label | Acceptance Criteria - Where applicable.
label | ○ Complete: Structural Steel Barrier Rail (Supply & Installation) ITP.
label | Method - Document Review
label | Frequency - Where applicable
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - Structural Steel Barrier Rail (Supply & Installation) ITP
date | Date Completed:
checkpoint | 6.4 - As-built Survey
label | Reference - IFC Drawings 610.47 (a) Table 610.472 (Feb 2020) SD3902
label | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 (November 2018) or 610.472 (March/June 2019) as applicable to the element.
label | — Departure from plan position: 25 mm
label | — Departure from alignment: 5 mm
label | — Irregularities in alignment: 3 mm in 3 m
label | — Variation in joint gap width: 3 mm
label | ○ SD3902, for all TL rated barriers
label | (a) Departure from plan position: ±20 mm
label | (b) Departure from alignment: ±20 mm
label | (c) Seperation between barriers 10mm ±5m
label | ○ Attach: Survey As-builts / Survey Report
label | Method - Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.5 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP