## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
39eaf1a6-ee0d-4100-9bf0-c837b429ac24 | checklist | EVAMP001-THS-QA-ITP-0000 Pre-construction | itp | ITP-0000 Pre-construction
51535b1a-ac26-4769-bc85-1f7ba1beade1 | section | Pre-construction
d5f2de5b-1844-4b8b-9494-00345366394e | checkpoint | PC1.1 - Pre-Construction-PKG-Construction Management Plan
9cb08030-a1b4-58b4-aa30-19759969d214 | note | Responsibility - ENG
d97fd768-106c-5aed-8a49-28134e3d84bd | note | Test Method - Visual
40d7ec2a-577f-590f-8a34-904cf05aeb60 | note | Conformance Criteria - Approved Construction Management Plan saved in Construction Team Sharepoint and detailed in register
b132816d-9c22-58a5-8505-653a25659938 | note | Frequency - Prior to works
8d264537-c84a-59ee-8506-57055b051946 | note | Thiess HP/WP Check - HP
9c63b04d-3123-5f87-a40d-243882371884 | note | Inspector HP/WP Sign Off - WP
24a3466b-fbf5-43de-b7ca-11b4744cff97 | signoff | WITNESS POINT
dccbd29c-6e53-42a4-aa77-56d5a2245e5c | checkpoint | PC1.2 - Lot Register/ WBS
731f8e63-9c21-51d9-8e55-9d9b575b5560 | note | Responsibility - ENG
5067a1db-2194-5c58-9d4a-8e6cb1f8cf52 | note | Test Method - Visual
ea6fa4bd-af40-557b-a1b1-ef2c1fe6b6cf | note | Conformance Criteria - Lot register saved in Construction Team Sharepoint and detailed in register
94588b25-c4ac-5621-ae43-e8a1da908b68 | note | Frequency - Prior to works
a6e495d4-a85e-5c8b-9e94-d0483d48b40e | note | Thiess HP/WP Check - WP
147f889c-d6d7-50b8-b9a2-f8c4d49faaf0 | note | Inspector HP/WP Sign Off - WP
4fcac2b7-4adc-4364-b8a4-7412fb080e6a | signoff | WITNESS POINT
f72a1074-063a-4d47-a7f1-0395bd9eb44b | checkpoint | PC1.3 - Construction procedures
51a8cb8d-2c61-53cb-99e3-e639f64c30c6 | note | Responsibility - ENG
933726ca-6948-5c00-90d7-15d6999cd3de | note | Test Method - Visual
93830690-3c17-57f0-ba13-a8310246c567 | note | Conformance Criteria - Construction procedures saved in Construction Team Sharepoint and detailed in register
6d6147dd-ff23-59a0-90f0-99695566b1f5 | note | Frequency - Prior to works
bbc2999f-f76d-515c-8153-7442c2461dbd | note | Thiess HP/WP Check - HP
7797c642-0f5a-5b06-af1d-9511c315b41f | note | Inspector HP/WP Sign Off - WP
9a028711-23bb-4193-9607-8ddc0bae556b | signoff | WITNESS POINT
9798f2ba-d8c2-48f2-a4f5-d710b962012a | checkpoint | PC1.4 - Excavation permit
95d3c806-8063-5e27-9668-d0b242086300 | note | Responsibility - ENG
8916aac1-51a6-5ce0-8291-cb123c58ade7 | note | Test Method - Visual
f265cb18-d913-5d79-a643-61a578d8f806 | note | Conformance Criteria - Approved Excavation Permit saved in Construction Team Sharepoint and detailed in register
7f93843b-9275-5f5c-8251-435da3789f4b | note | Frequency - Prior to works
8e60b629-9f32-500e-add6-a101551735db | note | Thiess HP/WP Check - HP
0f1e7ca5-4178-5015-bfab-f0176438b559 | note | Inspector HP/WP Sign Off - WP
0793db85-0e32-4baa-a740-27bcc77097e7 | signoff | WITNESS POINT
e25f76c5-b49e-4616-8bf9-5aa7766491c5 | checkpoint | PC1.5 - Dial before you dig check
57a4f0a8-3f8d-5d0e-93ec-6e1a94d3278c | note | Responsibility - ENG
c23a4f48-c772-5fa4-9fcd-b9218b736d35 | note | Test Method - Visual
6363e9c4-d829-5d6c-afdb-b270d7ea490f | note | Conformance Criteria - In date DBYD certificate saved in Construction Team Sharepoint and detailed in register
8c0a1cb2-a6f1-5dd6-901f-16f0e1910bc4 | note | Frequency - Prior to works
81f1fe66-23c8-5d52-9a8f-401f164b4895 | note | Thiess HP/WP Check - HP
62029c75-459c-56b7-9133-1ccc3d7189c2 | note | Inspector HP/WP Sign Off - WP
f89bc0d0-c7d9-4e30-a447-98e5649ba193 | signoff | WITNESS POINT
1afaa620-9ec9-4f52-aefc-23b6fce4cf53 | checkpoint | PC1.6 - Traffic control plan
96b6c5da-dcdf-5ade-bda1-2dd57041593b | note | Responsibility - ENG
756c5fce-de98-5311-8a4b-0df638afd89a | note | Test Method - Visual
3a87cab9-fbc4-5d6a-9ce5-102913bdc911 | note | Conformance Criteria - Traffic control plansaved in Construction Team Sharepoint and detailed in register
10d26ef2-b36a-5071-bd09-c1f8a4c5e39c | note | Frequency - Prior to works
b7f85538-7ac7-5097-8cc0-77faceb9d107 | note | Thiess HP/WP Check - HP
cacb7889-fac6-52a0-bdd7-4b5e86efaec6 | note | Inspector HP/WP Sign Off - WP
c70f264d-517d-40d2-86a2-61ad62419bd1 | signoff | WITNESS POINT
8f7e8f93-0c5e-4834-ba08-0c7b3abcfb02 | checkpoint | PC1.7 - Inspection Test Plan (ITP) submitted and approved
4363e8b0-8dcd-5c88-b25a-db546e0f5a1f | note | Responsibility - ENG
5e97c6ee-75bb-5768-b9e7-ba49656e6d63 | note | Test Method - Visual
4d52017a-5463-5b85-b8a2-3490bd5784db | note | Conformance Criteria - Approved ITPs relevant to the works saved in Construction Team Sharepoint and detailed in register
d2440ea8-6546-56a1-8021-c92d68f9da8d | note | Frequency - Prior to works
7976b1a3-9bf9-5c3a-a4e8-fcf344a5ee9b | note | Thiess HP/WP Check - HP
23bd4684-ca52-5fd9-a24c-746a633febbc | note | Inspector HP/WP Sign Off - WP
89fc55c4-d4a5-4806-9cb7-b5fdd80d1182 | signoff | WITNESS POINT
92b8e7de-0df5-4bd4-84f2-ed1d9583bda8 | checkpoint | PC1.8 - IFC drawings
dc75979a-20a0-5198-8f40-76724f87d807 | note | Responsibility - ENG
5e63740a-41ee-5679-ae88-2d7a1934463a | note | Test Method - Visual
ac97cf8d-b749-5685-bf0b-1e8b850118fb | note | Conformance Criteria - IFC drawings and revisions transmitted from theThiess Technical Services team and detailed in register
4eef36e5-3799-5ded-867a-de41840304f3 | note | Frequency - Prior to works
338676cc-0a7f-5cc4-b981-b7d3d80cc0ee | note | Thiess HP/WP Check - HP
e7452242-72fe-5ea2-b8a8-5a1113f5edf5 | note | Inspector HP/WP Sign Off - WP
d8b918de-ee98-4b11-9e9b-7f7d3f6b19b1 | signoff | WITNESS POINT
d052d567-770d-41f4-afa2-c174d6f29b37 | checkpoint | PC1.9 - Erosion and sediment control plan
0a1d5052-5415-595f-8bed-9139b638007a | note | Responsibility - ENV ENG
9533c9b2-6961-53e0-87af-23d55c41ba75 | note | Test Method - Visual
0f432034-d55b-593b-ac9f-fda7d25cf71a | note | Conformance Criteria - Approved Erosion and Sediment Control Plan saved in Construction Team Sharepoint and detailed in register
0a6a815d-69fe-515d-9c35-c2add07f9b11 | note | Frequency - Prior to works
2559b787-9a4c-5975-a49f-033d91a8272b | note | Thiess HP/WP Check - HP
281a1ef7-5a88-5fc5-ad2c-eae8a63115b1 | note | Inspector HP/WP Sign Off - HP
ad97dae8-4823-426a-ac7e-5254da201e9e | signoff | HOLD POINT
0dddaa81-7464-47f7-90d2-0d5115acd6d1 | checkpoint | PC1.10 - Approved stockpile locations
06dc5854-4fd1-599c-8ef9-94764f959249 | note | Responsibility - ENG
33273c30-deca-50be-93e6-e195869ffbd7 | note | Test Method - Visual
1b9e3f79-a398-5254-9d11-bcfa22c56fbe | note | Conformance Criteria - All stockpile locations to be nominated and approved prior to commencement of activity.
c6d4ccea-a004-51f0-ad47-d7bc6d8aae81 | note | ○ Topsoil register to be maintained with information on topsoil volumes and stockpile locations.
e17e1457-fbe9-54d1-be3f-e7a481ff5179 | note | Frequency - Prior to works
1e774b75-714f-5165-a028-87be80be1650 | note | Thiess HP/WP Check - HP
599e6b3d-22bf-5c13-8c36-8fdf7f17f781 | note | Inspector HP/WP Sign Off - HP
474b6e42-eabe-40f3-bbd3-43605e9adf8a | signoff | HOLD POINT
092a29dc-586c-4af5-8c6c-93f573ee1277 | checkpoint | PC1.11 - Ground Disturbance Permit (GDP)
57deb92a-450c-5c6f-acf0-1b6cc5302f13 | note | Responsibility - ENV ENG
4e8f7e81-676f-5378-b67b-a0c596922c84 | note | Test Method - Visual
3eaad6c4-cc23-589a-b307-c2fc3dc0613e | note | Conformance Criteria - Approved GDP saved in Construction Team Sharepoint and detailed in register
772a83eb-9627-5c9e-ab69-e3dce3724d9f | note | Frequency - Prior to Works
79437ee9-855f-5ca0-8d93-004df1e17c66 | note | Thiess HP/WP Check - HP
063da2da-4fd8-5f0b-9522-51bd6a988cd3 | note | Inspector HP/WP Sign Off - HP
74b6a9dc-373c-48e6-bbc5-8237fdac82c7 | signoff | HOLD POINT
38bea5c9-d2e5-4b3f-bfa9-1046c655f57f | checkpoint | PC1.12 - Cultural Heritage(CH) Clearance Survey
562a1f66-6b93-5287-ac46-06c58d6ba6fa | note | Responsibility - CH
31504bfc-535c-56cc-b732-71f68ee80a00 | note | Test Method - Visual
ed3f2cbe-c482-5b01-9734-53d152e37ad9 | note | Conformance Criteria - Approved CH Clearance Survey saved in Construction Team Sharepoint and detailed in register
b115a458-f82e-5116-a5f1-3bd666a00c93 | note | ○ Areas of CH clearly demarcated
88d3d545-4f08-59ad-b530-c7664f7303c2 | note | Frequency - Prior to Works
1b46bc51-55a7-5e5e-9996-dbce2bb14370 | note | Thiess HP/WP Check - HP
303e84de-712a-50a0-b520-adcb2945d84e | note | Inspector HP/WP Sign Off - HP
1983183e-93dd-4c5c-9708-45146826c2d0 | signoff | HOLD POINT
0d42f951-31ce-433b-a4f9-07634f589721 | checkpoint | PC1.13 - GDP survey set out
9a6024bf-d555-5e25-b971-5fa2e21479e8 | note | Responsibility - SURV
9b4feac1-8b04-53d7-9b75-3751cff6e6b7 | note | Test Method - Field
d11f5616-02df-5515-848f-9d22293a49c1 | note | Conformance Criteria - Area of works pegged and clearly defined to GDP.
20eb98a8-500c-5b75-b847-801f8412de6d | note | ○ Clearing pegs installed at nominal intervals to ensure no over-clearing.
6ba79a40-6aea-54e9-8c14-d8d1f964d289 | note | Frequency - Prior to Works
efad1e71-b8a7-5d38-b11e-6752c2689f4f | note | Thiess HP/WP Check - HP
6cd58d72-91ec-5c56-8451-636e0290a7b0 | note | Inspector HP/WP Sign Off - WP
c7a14af1-9506-496f-af7b-99e8c4e28668 | signoff | WITNESS POINT
fd2bf82c-6252-418e-a706-afb15eedd67d | checkpoint | PC1.14 - Survey of pegs to confirm correct GDP survey set out
a19a3703-8607-58d9-b768-f5140275043c | note | Responsibility - ENV
75316138-d174-572c-a6c3-e268ce59e96e | note | Test Method - Visual
f09acbed-1107-5e56-9a2c-2a4cb62ea91b | note | Conformance Criteria - Pegs to be surveyed and sent back to the engineer. This is then to be confirmed by the environmental team
d294d986-0ecf-5381-b471-376f8b8c8a73 | note | Frequency - Prior to Works
e297e00e-dc5a-585b-942a-6947068053a3 | note | Thiess HP/WP Check - HP
56508615-79a5-598b-9ed6-33ce28b5a2c2 | note | Inspector HP/WP Sign Off - WP
b976c90f-d601-4b63-8b18-99a233eabcd4 | signoff | WITNESS POINT
7ebd9cd1-30e0-4aee-bf10-c8ce9461f849 | checkpoint | PC1.15 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey
daf2ac5d-e08c-5e52-87ac-2f6edc906fae | note | Responsibility - ENG
c552387d-9255-5c0d-8da7-da576f17d86a | note | Test Method - Visual
d6b31c68-1d85-5535-88fc-86ae4c317a47 | note | Conformance Criteria - FSC pre-clearance survey completed within 2 weeks of construction.
b309415d-a068-5fbe-b287-6348bce84c94 | note | ○ Habitat vegetation, threatened species demarcated.
c6a3ede9-b390-5c50-9543-a781f6bc67a0 | note | Frequency - Prior to Works
1a43dad7-0e5d-5d65-aac1-e252f3208028 | note | Thiess HP/WP Check - HP
16b6c643-8f9d-58d7-b654-c9331a6f07b8 | note | Inspector HP/WP Sign Off - HP
dc4f9538-a696-4f5a-86e8-a0e9d9ad80fd | signoff | HOLD POINT
4c813e84-324b-41dd-ac34-f82e23484668 | checkpoint | PC1.16 - Mandatory GDP Pre-Clearing walk
a048fe0b-c15d-5767-9ba3-e4760da924bc | note | Responsibility - SUP OP ENG ENV
5b58f219-b593-5c58-897e-e8658d535401 | note | Test Method - Field
afb8fd38-b72a-5598-af0a-f8e6b1994621 | note | Conformance Criteria - Walkthrough with FSC, Supervisor, Surveyor, PM or Senior Engineer, operations that will be undertaking the clearing
3e58f01b-e39a-5e24-8bee-81346b0fb548 | note | Frequency - Prior to Works
9e67411f-ed37-56f8-b3c5-fe34b6449876 | note | Thiess HP/WP Check - HP
e364c4b0-b2f3-523f-83aa-f6240e7a042a | note | Inspector HP/WP Sign Off - WP
9d9d18e3-fea4-4e4b-91fe-d95674159afd | signoff | WITNESS POINT
95d44b0d-a0ff-4806-8aae-b5928f44fc01 | checkpoint | PC1.17 - Embankment fill materials
fdb76142-99c9-55c7-8098-97b80702bf80 | note | Responsibility - ENG
7ccde0eb-d330-5eb3-b587-f42d4c1dd53c | note | Test Method - Visual
f7c7398e-42e6-5c31-941a-f186e2b66f19 | note | Conformance Criteria - Embankment fill materials have been approved for use and in accordance with the requirements in the specification.
19f448f4-3314-5630-99f5-74a35dde96f6 | note | ○ General fill material as per Table A3-1 Cut/fill material properties in the specification:
40acf6ee-7928-5d79-90bc-c98badb4606c | note | ○ Less than 30% passing 0.075mm sieve
57c7c285-386d-5bc9-8fae-e6450218c790 | note | ○ Liquid limit 20% to 60% Soaked CBR = or >3% (STD compaction @ OMC)
ead91126-8b1c-5b92-aae2-945b752557a7 | note | ○ 1 test per 5,000 m3
9193395c-6e53-549e-b314-3ef8a4544b39 | note | ○ Subgrade replacement material CBR10.
4a1f5779-21c3-55d4-85f7-6eaafb7b52ef | note | ○ Select Fill as per the details in Table A3-2 Select fill material properties & Table A3-3 Select fill grading envelope.
eabb899f-69c7-5124-96f4-33e7fbce683c | note | Frequency - Prior to works
64d2f340-b7fd-5a5a-9b03-ae4d09f98563 | note | Thiess HP/WP Check - HP
89ebe463-c0f5-56bd-a9d4-f58461278a09 | note | Inspector HP/WP Sign Off - WP
e97f3805-6609-4c7a-847e-469d22f8c748 | signoff | WITNESS POINT
07aecab2-8e27-4719-bd19-1c267e693f81 | checkpoint | PC1.18 - QA close out
e1e833cd-7a61-51eb-9747-58e7ce7a1842 | note | Responsibility - ENG
be630aec-8448-550b-9b22-0ad6f23eb76d | note | Test Method - Visual
b1ce9316-1d43-56d0-8f25-dcfa9c5697e2 | note | Conformance Criteria - Works completed and update ITP/Lot register/MDR and close out of GDP
0fda6c46-7778-5ac7-8a3e-e4554528dc37 | note | Frequency - As required
4f7f58c0-5220-5a52-ac2b-a5fcf91bacee | note | Thiess HP/WP Check - HP
8b1a8832-b0d6-5ba8-b862-009772c75ad2 | note | Inspector HP/WP Sign Off - HP
14d0655d-3699-4033-bf1d-d54efd28e116 | signoff | HOLD POINT
6796a4b7-50fd-4c6d-82a5-85be75cf9074 | checklist | EVAMP001-THS-QA-ITP-0001 Clear & Grub | itp | ITP-0001 Clear & Grub
65c63129-50bb-463f-92ee-20d59b94b854 | section | Clear & Grub
489aefec-c9f3-4977-a3a2-44421446c676 | checkpoint | GC1.1 - Underlying lot & ITP signed off and conforming
98434abf-234a-51f2-b704-be1a9de86c51 | note | Responsibility - ENG
a024fe55-4ba9-5fc2-90b0-30f84dcbf2ab | note | Test Method - Visual
c07fbf52-8dec-534f-86e3-08b175a65330 | note | Conformance Criteria - Pre-construction lots closed out
e1d80108-10e4-512a-8cc8-0f00f2bac03b | note | Frequency - As required
f9e55d9e-59ba-5f88-bb29-b5db805daafa | note | Link to ITP - PC1.18
e1684c5e-6d00-4179-ba02-76548e29da42 | checkpoint | GC1.2 - Survey of Natural Surface
6ebbf330-e95d-5e10-8e27-ef6e1c7825e6 | note | Responsibility - Survey
19245fda-d051-5edd-baca-909f624484d2 | note | Conformance Criteria - Check survey pick up of work area and digital file saved in Construction Team Sharepoint and detailed in register. Surface area shape file created and uploaded to Qfield
96356e00-b597-41a7-be38-ca41842ab0df | checkpoint | GC1.3 - Clearing of vegetation
4ad76604-a732-5f00-9202-8b479ba6a09f | note | Responsibility - SUP
160b8fc7-a7f6-5d83-b268-e1aaa26d4321 | note | Test Method - Visual
afd40b38-8546-5d46-b008-32e8c6f6d1f4 | note | Conformance Criteria - FSC individual on site at works during clearing operations.
b0a60139-c641-5810-8191-a3b4d22dfebe | note | ○ Habitat vegetation, threatened species and cultural heritage areas demarcated
b69d176b-96b4-5d45-9aa2-af9173cac2d2 | note | Frequency - As required
b596ec02-f4aa-5645-a935-4d7777f98606 | note | Thiess HP/WP Check - HP
d24f16aa-677d-5eb7-b1c3-48d78cc9f8c4 | note | Inspector HP/WP Sign Off - WP
a7af8165-3a25-45f7-b0f4-c5c6827e3060 | signoff | WITNESS POINT
2ffd8602-4159-4631-b51f-fb50d097b50f | checkpoint | GC1.4 - Stockpile Cleared Vegetation
6ee3953f-8735-54f5-89e5-f208aec95df3 | note | Responsibility - SUP
dd7b1d88-2f7f-5ad0-9131-e4a6399a168c | note | Test Method - Visual
92ca0ab2-2216-5ca8-a440-49b9a542ab8f | note | Conformance Criteria - Cleared vegetation loaded and hauled to approved stockpile location
3387fd36-cd13-5095-87ff-d7937b609226 | note | Frequency - As required
8ad94a31-975a-5c99-8ca0-6636fb57e981 | note | Thiess HP/WP Check - HP
10a24508-4e40-532b-9d55-58c51ec51adc | note | Inspector HP/WP Sign Off - WP
aaf1e0b1-b8f8-426f-bf9f-6bb0df391867 | signoff | WITNESS POINT
668916bf-b68c-4a79-a23e-e790bbe46f1c | checkpoint | GC1.5 - Erosion and sediment control
be16683f-6acc-519f-8e55-b4bc294ff9f9 | note | Responsibility - SUP
46dfae90-06f8-5f4e-857b-bfd837333e53 | note | Test Method - Visual
c6dd806e-baa9-5e10-a07e-51f568dd4282 | note | Conformance Criteria - Erosion and sediment control measures to be implemented whereever possible after clearing has been completed.
27238811-fa23-5cb2-b8af-a292a3025dce | note | Frequency - After clearing
62509e03-b70a-5049-a275-c2aacb3714ae | note | Link to ITP - PC1.10
3c1a6503-66f6-5eb7-be27-47b33e6a9cfb | note | Thiess HP/WP Check - HP
65e4534a-f135-5b93-bd94-cb77a4b83a92 | note | Inspector HP/WP Sign Off - HP
fa877d86-55e1-456c-9e59-c94fd9b13286 | signoff | HOLD POINT
15100512-873e-4694-b8bb-6ae6e682538e | checkpoint | GC1.6 - QA close out
2123b05c-fda5-5cef-ba89-eb0e7e09d771 | note | Responsibility - ENG
7cbe0163-db58-5298-a5ce-55e4205257e2 | note | Test Method - Visual
e3dfd798-8daa-5d94-a78e-aefcba19b2f1 | note | Conformance Criteria - Works completed and update ITP/Lot register/MDR and close out of GDP
c975079d-ffaa-54ef-8b9d-b3003d95f4a0 | note | Frequency - As required
da06f814-8fbd-5785-9bc4-6286327f6abb | note | Thiess HP/WP Check - HP
aac6fe69-eb96-56eb-87d9-32d99c7afd4c | note | Inspector HP/WP Sign Off - HP
12b79af7-f40a-4688-b33d-60e2db049043 | signoff | HOLD POINT
b86ac2fb-a936-4959-bc2c-0b212ce6cb6a | checklist | EVAMP001-THS-QA-ITP-0002 Topsoil Stripping | itp | ITP-0002 Topsoil Stripping
8749f0ea-dcaf-40a1-a9fb-38172bde624a | section | Topsoil Stripping
916380c8-3601-4c5d-aaec-d8f5ce265520 | checkpoint | TS1.1 - Underlying lot & ITP signed off and conforming
ae37fa4e-a8c8-5621-99d3-c3093ffbd813 | note | Responsibility - ENG
eaa1749a-e2ec-5b85-8edd-42ddd734d8a2 | note | Test Method - Visual
dae7b959-a92f-50a9-80f0-f8e4f50ef610 | note | Conformance Criteria - Clear & Grubbing ITP closed out
eeadea39-f306-52fc-83e8-4c96215d2126 | note | Frequency - Prior to works
b23b17a7-7376-533d-9afe-1423f0cb849c | note | Link to ITP - GC1.6
6c621a60-d7a2-4f30-86cf-79266b7cfff1 | checkpoint | TS1.2 - Survey Set out
a04a85f3-030f-5947-93a2-83065c379130 | note | Responsibility - Surv
b0740eeb-b1e8-565d-b6bb-e79334e3c6b7 | note | Test Method - Field
8795b855-e66e-55e4-ae20-2c067a367fa7 | note | Conformance Criteria - Areas of work to be set out by surveyor and/or models in plant
c707d4ab-6d68-5bb7-aa60-78dc74f21831 | note | Frequency - As required
225fa33d-4b6f-5408-b2e1-861b17ce1c7b | note | Thiess HP/WP Check - HP
c0fab7ed-3a57-510c-99ca-1308ec25b414 | note | Inspector HP/WP Sign Off - WP
92c3d114-4ca0-4687-9ab6-1be8c3bbaf48 | signoff | WITNESS POINT
ef0f707e-77c6-47e0-b7b6-f00e62939a07 | checkpoint | TS1.3 - Strip topsoil, load & haul to approved stockpile location
944babb1-ca24-540f-903e-b2314fa26865 | note | Responsibility - ENG
a591edf9-2637-5776-97cf-4ac30f68fd7f | note | Test Method - Visual
93eddc67-b978-54f9-8611-85f084d83259 | note | Conformance Criteria - Provisional depth of topsoil strip shall be 100 mm unless shown otherwise on the drawings.
8e938ca4-1f2e-543e-b9b6-75e0ac18fd76 | note | ○ Stripped topsoil loaded and hauled to approved stockpile location.
e13284e2-f46f-585b-bcd5-00fe9807e382 | note | ○ Stockpile locations located minimum 40m from watercourses and not exceed 2m in height.
48714638-6934-566f-8a20-7f697f7d162d | note | ○ Native seeding of topsoil stockpiles as agreed with Company.
e05858cc-a4bd-5b6a-9caf-8cde8db7aa22 | note | Frequency - As required
9463ad6a-351e-5eee-973e-cc0598eb1f1c | note | Link to ITP - PC1.10
10901a46-aadc-5279-b7e6-6b0eef29320f | note | Thiess HP/WP Check - HP
cabcfed7-1ef9-558c-b8c6-22527fc21bc5 | note | Inspector HP/WP Sign Off - WP
d2bc2732-0651-43bb-8cb4-971bf9e1c4ff | signoff | WITNESS POINT
071da937-196f-4dbf-ac54-4880807d9d2f | checkpoint | TS1.4 - Topsoil location, destination and quantity catalogued.
2f69d885-0944-5510-bc4d-b099d07f8d6e | note | Responsibility - ENG
76b50feb-f81f-5024-9cc6-1a08b9096a8d | note | Test Method - Visual
cfd53ca6-93ea-522e-990b-36f528577392 | note | Conformance Criteria - Topsoil register to be maintained with information on topsoil volumes and stockpile locations
9fef3602-e591-50a2-8b1e-b28b30b00301 | note | Frequency - As required
de9b897a-7bf0-558d-a79a-ab5d0a872b6e | note | Link to ITP - PC1.10
4278a0ee-23c0-5b19-8a90-69a59d37c005 | note | Thiess HP/WP Check - HP
d7122674-faca-594e-887a-749570912de2 | note | Inspector HP/WP Sign Off - HP
05dccf20-f68b-4781-954e-06157df5e77b | signoff | HOLD POINT
c6e48c99-ba54-4abd-bc57-c3bcd1e665fd | checkpoint | TS1.5 - Surface level check and survey pick-up
765c1ef7-26db-5fcb-81b9-462bb14fbba4 | note | Responsibility - SURV
6503a485-f9c8-558d-811b-469336ece816 | note | Test Method - Survey / Field Test
64c8342e-8aae-5f7c-a4e3-df39e8aecf3b | note | Conformance Criteria - Stripped surface level picked up as per Table 10 C15 (DXF file format, volume calculated and filr saved in Construction Team Sharepoint and detailed in register
162e926d-aa9c-5849-b1af-ef6f44f75ea6 | note | Frequency - As required
2ed18220-a06f-52d7-9f65-00887d5aad21 | note | Thiess HP/WP Check - HP
9e188d56-9fad-5d14-b173-8c642a6c6397 | note | Inspector HP/WP Sign Off - HP
af4ae563-b4e9-47a2-a180-1d478211e8ec | signoff | HOLD POINT
ae6c69bd-ecc2-454a-9bff-6080c8c1c94a | checkpoint | TS1.6 - QA close out
8efc1984-16d2-53ba-a057-5431c08fd38b | note | Responsibility - ENG
0e4486bc-38e8-544f-ac30-fb17669c1687 | note | Test Method - Visual
c7e83a05-827a-55ab-a626-c824caa8593d | note | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR.
d228505a-fca4-59be-b984-2e29b12b43a9 | note | Frequency - As required
e910bce3-f30b-59aa-b87d-43474fc1cf31 | note | Thiess HP/WP Check - HP
ef4ec3ef-ada0-5aae-b30f-6405d1fe60ab | note | Inspector HP/WP Sign Off - HP
5e2f8d5f-e7ee-48e0-844a-1e4cf9f054a9 | signoff | HOLD POINT
1e0915ac-c4f2-4889-bc14-8ff55ed38f8d | checklist | EVAMP001-THS-QA-ITP-0003 Subgrade/Foundation Preparation | itp | ITP-0003 Subgrade/Foundation Preparation
3888cb15-c6e9-4774-94f4-ef0136a8d2b8 | section | Subgrade/Foundation Preparation
ac475546-f2ce-4c02-a316-d1bc173edfa8 | checkpoint | SP.1.1 - Underlying lot & ITP signed off and conforming
0ba38702-7e4a-5305-999e-9d0c380b72b1 | note | Responsibility - ENG
cd2dc35a-9502-5741-8b68-f7ea4a27f70c | note | Test Method - Visual
cdae2c66-de7c-5ca1-aaa5-1dcaadf88613 | note | Conformance Criteria - Topsoil ITP closed out
39fb73af-ee7e-5cfb-a384-6dabf3434961 | note | Frequency - Prior to Works
8ee4a552-2995-58d0-9e48-752e910a3518 | note | Link to ITP - TS1.6
2897bed4-d43c-43af-aa95-e7d21d62accd | checkpoint | SP.1.2 - Embankment fill material
6698839b-9391-5658-8be4-54b8641f1d75 | note | Responsibility - ENG
afc74dae-bdf5-5e03-929d-edad53d7c4be | note | Test Method - Visual
e98679c2-b70a-536b-9a9c-bef3a3d5405e | note | Conformance Criteria - Ensure CBR10 subgrade replacement materials have been approved for use and within specification
6171a00d-a560-5761-b6c3-27e3f1536543 | note | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage)
cd5ca6cd-ecd1-5805-9164-3664d4d56063 | note | Link to ITP - PC1.11
8ebc67a8-3f8e-5cfc-aa2c-2ab9989333fa | note | Thiess HP/WP Check - HP
c22e0b29-ee08-5f77-a31c-95c7a96e983a | note | Inspector HP/WP Sign Off - WP
e6f51fb7-6c5b-4f3e-b073-2d76ec83af4c | signoff | WITNESS POINT
f18384a0-36b1-404a-ba16-b643c5ba2214 | checkpoint | SP.1.3 - Survey Set out
4b25c72b-e94d-529d-aa6b-3835cde661fb | note | Responsibility - Surv
6db7605f-6648-5850-b3e9-c41e7f2cfe70 | note | Test Method - Field
d0b3b03b-7fa3-511c-b9b7-9c1db665c392 | note | Conformance Criteria - Areas of work to be set out by surveyor and/or models in plant
662d8646-ee30-5fd1-9ce4-7ccc7f1318a9 | note | Frequency - As required
57f8ebaa-8d19-5e99-8c43-2d16b8aff760 | note | Thiess HP/WP Check - HP
45364d23-92d3-5007-895d-5930c2185259 | note | Inspector HP/WP Sign Off - WP
4d57dd0c-68ce-48ab-bd54-2cee86b3fca9 | signoff | WITNESS POINT
dbba825e-74ac-4f55-a21f-fc1ed370c529 | checkpoint | SP.1.4 - Removal and replacement of unsuitable material
747e0dbf-fcba-5695-b1a3-01b9361dabf7 | note | Responsibility - SUP
30352755-f0c8-5be8-bb2c-b08aec36a9b4 | note | Test Method - Field
21dbc2ce-af3d-5371-a91b-5b924c2fdfbc | note | Conformance Criteria - Determination of unsuitable material by the Level 1 GITA or Inspector (Sedgman) is required prior to the removal of any unsuitable material. Unsuitable material criteria is in the specification.
e4d39c20-3fe5-5de7-bc69-b4f7f854c5fd | note | Frequency - As required
c84d290d-5958-537c-9c8e-48a52d608cc3 | note | Thiess HP/WP Check - HP
47ac2868-dfa4-5963-aa63-9fdf4d28309a | note | Inspector HP/WP Sign Off - HP
abc7c254-a1c2-4d1e-a2cc-9dda06113411 | signoff | HOLD POINT
bf2a450e-c73d-4e58-b6c5-f8d0ad38ec50 | checkpoint | SP.1.5 - Proof rolling and soft spots
6ac50545-6961-5f6e-9358-6a0ee1fb360f | note | Responsibility - SUP
c709b948-1ca6-56d0-9cf6-aefd7aedbedc | note | Test Method - Field
c378f6ef-6f7b-516a-8e9d-004032c7b05c | note | Conformance Criteria - All subgrades and foundations shall be proof-rolled under a standard 8 tonne axle load or 10,000L water cart or heavy self propellled smooth drum roller dynapac 620D or equivalent to confirm that, in the Inspector (Sedgman) s opinion, deflections are negligible
3a550ce8-816b-5397-a561-01745103d955 | note | Frequency - As required
ffbdbde8-4eed-59a2-a503-187d9143d7f6 | note | Thiess HP/WP Check - HP
118fb4dc-b6f4-5712-8aa5-f3abc584a348 | note | Inspector HP/WP Sign Off - HP
6e4cdf2a-ea9e-4e8c-aef7-9e25439a1400 | signoff | HOLD POINT
4fd12e0e-f712-429a-8540-2f342f7bb820 | checkpoint | SP.1.6 - Subgrade/Foundation preparation
53ba4411-a5de-531c-961b-c446ae05e42d | note | Responsibility - SUP
d0ce048c-197d-5912-80e4-60df6073967c | note | Test Method - Field
36fa4a64-d46f-5f5c-ba5f-c800dda0a565 | note | Conformance Criteria - Lightly tyne the subgrade/foundation immediately prior to placing embankment fill.
aa96d8ee-81e4-5cf0-9311-27c35702a144 | note | ○ All material exposed in cuttings at subgrade level minimum CBR 3 or DCP 150kpa. If CBR2: Remove & replace with CBR10 select fill 150mm deep. If CBR1: Remove & replace with CBR10 select fill 250mm deep.
0d516928-6b59-57fe-b7ca-1ee4b1414d64 | note | Frequency - As required
ed5e1566-2280-51c3-be8e-1eb5461ee755 | note | Thiess HP/WP Check - HP
0e74b08d-944f-5d4f-a1a0-598735ce57d8 | note | Inspector HP/WP Sign Off - HP
c760cec8-8ceb-4a0d-a985-5324d40c2be8 | signoff | HOLD POINT
187efc59-29ad-49ed-8390-8b60becf1967 | checkpoint | SP.1.7 - Trim subgrade in cuttings
b3913e7c-bebc-5d12-9a25-bb41ac3c832f | note | Responsibility - SUP / SURV
ae93ba34-1d60-5116-972f-c6a9676fd814 | note | Test Method - Field
a76edf78-b419-5b0e-8f24-353676836a66 | note | Conformance Criteria - Trim all subgrade to the lines and levels shown on the drawings in accordance with the following tolerances: Top of bulk earthworks +/-50mm; Road subgrades & under buildings & structures +0mm to -25mm.
549c5914-07e3-55e7-bad0-0bbf1fce3fab | note | Frequency - As required
ffcc823b-be30-5129-a036-a226605a90d8 | note | Thiess HP/WP Check - HP
f45a1c01-4b58-5b13-93cd-bdb9bab52ee2 | note | Inspector HP/WP Sign Off - HP
f23b4a57-60f2-4a1f-bbca-c06f05da3796 | signoff | HOLD POINT
71594be2-04a9-4642-8c27-46fc02041e66 | checkpoint | SP.1.8 - Surface level check and survey pick-up
ae3e3dc0-bbb7-5161-ab48-8f3e93da7c89 | note | Responsibility - SURV
0233e3da-d7b0-57cb-a28f-791670b10318 | note | Test Method - Survey / Field Test
181a65b6-888f-5718-abc5-1c5ea421f1f5 | note | Conformance Criteria - Surface level picked up as per Table 10 C15 (DXF file format, volume calculated and filr saved in Construction Team Sharepoint and detailed in register
8205adaf-59f9-5e9c-94e0-2407ce8f2386 | note | Frequency - As required
816da858-ab98-54c1-b51c-3cfa04e1791f | note | Thiess HP/WP Check - HP
8fd83ed0-b72c-5af0-9b4a-dc40044dbcee | note | Inspector HP/WP Sign Off - HP
4bcc759d-350a-4250-8f6b-244794b056e2 | signoff | HOLD POINT
cf8c9bf4-266f-4abf-8026-2827cb980a71 | checkpoint | SP.1.9 - QA close out
f480ed2e-dad9-5d6f-bd96-060b4d89131c | note | Responsibility - ENG
1a40051b-4408-5dcb-b87a-220c77689e1a | note | Test Method - Visual
f5308beb-802e-5f5c-af91-fc47fbd956cb | note | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR.
5dd34aff-46bd-5dab-b2af-b6da8a1c725f | note | Frequency - As required
348d3807-5f57-5b32-ba96-d3d360a60099 | note | Thiess HP/WP Check - HP
b9692b12-b245-507c-a77b-b367d15bbc3d | note | Inspector HP/WP Sign Off - HP
fe791962-27f7-473b-bde7-91e7f40b4125 | signoff | HOLD POINT
dce3a70f-9200-4dfb-9e26-88ee054029dd | checklist | EVAMP001-THS-QA-ITP-0004 - RCP installation - RevB |  | ITP-0004 - RCP installation -
56f3d35f-f971-4570-a6cb-a7e2e053164c | section | Construction
43a83497-5fd9-419c-86bb-037369896bba | checkpoint | 7 - Trench Excavation
68b7bc18-4723-554c-9620-02b51a3f322a | note | Responsibility - SV/SC
1e6470b1-a264-52b3-a75c-5facf55b91ec | note | Method - Visual
4eadcc70-fbdc-580a-8923-38941e267486 | note | Conformance Criteria - Trenches should be excavated to the required width and grade indicated on the IFC Drawings, with allowance made for benching for excavations greater than 1.5 meters.
1152136e-5ee8-5625-aec6-e712fe3b8893 | note | ○ Excavations must be kept free from water until work below ground level is adequately set or protected.
c78911a0-c5f8-535b-a451-525848c399e6 | note | Specification Clause - EVAMP001- THS-CV-SPE- 0003
cee4928f-da33-5167-b6bb-06fa4737a3fd | note | Frequency - As required
24f10513-7657-53e6-9190-d3d57af409d4 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
853fb7d6-aa96-5f62-9919-44c0a2eee0b6 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
561d45d4-f536-4b76-b6b0-abcb2ed432d0 | signoff | HOLD POINT
69f40dd9-2323-4125-a6c4-16027c169189 | checkpoint | 8 - Bedding
4239bc90-2604-5eee-89c6-2e482dae7a3d | note | Responsibility - SV
42134d05-d220-53d1-a17b-c9b87c890d00 | note | Method - Visual
c01ad167-a012-5205-9658-537f8d5064e3 | note | Conformance Criteria - Culverts shall be bedded as detailed on the Drawings. proposed
02d5cb2b-1552-55df-991b-c77c37083a89 | note | Specification Clause - EVAMP001-THS-CV-SPE-0003 clause
c3cc6d59-4295-50a2-a460-3887b60d6d4f | note | Frequency - As required
08b14b51-28d3-593c-9e2f-797537a5fb0c | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
c011de9f-89fc-57f6-a607-262811293f31 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
ef1d7cc1-1d5a-543b-8d84-c7f7a90a5c4f | note | Records or Comments - On-site verification sheet and survey
c2dcb488-a998-45a1-9555-f57d1f775ef0 | signoff | HOLD POINT
37e3f4ce-8c23-4ac7-ae40-db511f36d76a | checkpoint | 9 - RCP Installation
ed45f2fa-5bf5-53c4-9582-0d0baed06bcb | note | Responsibility - SV/SC
9f390736-5c83-5e2a-a4db-0f675d5271ea | note | Method - Written/ survey
97da684e-db9b-5e0c-8be2-81bbd59ac16f | note | Conformance Criteria - Culverts are to be installed to the line, level, and grade shown on the IFC Drawings. Inlet and outlet invert levels shall be as shown in the Drawings plus or minus 10mm.
56d8fdfb-15e6-522d-9874-574648b79800 | note | ○ Inverts shall be smooth and of uniform gradient throughout each culvert length.
413e091d-0634-5769-922e-815eb6d55ef1 | note | Tolerances:
a5810a90-5120-5cb0-82a9-06fd5c238ff6 | note | ○ Vertical level: ± 10mm
e1988385-3ee5-5861-9b98-939c44fa0efe | note | ○ Horizontal Alignment: ± 25mm
7718f1eb-2b7f-5d03-9852-9fa62c3ad40c | note | Specification Clause - EVAMP001-THS-CV-SPE-0003 clause 4.17
022b4743-39ff-5bfe-832e-d2ee15b018a1 | note | Frequency - As required
1e3fc071-6371-51d0-b52a-dc432849c086 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
9eea53fe-e2b5-5a9b-96e0-621b9cf431a2 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
5c9691a7-f948-4765-b8b3-1b5e09db9be4 | signoff | HOLD POINT
05163394-849a-4ee5-9526-90a1161cf933 | checkpoint | 10 - Backfilling of culvert
a31cb5a8-a8a2-5ccf-a097-2663f91dbb0e | note | Responsibility - ENG/ SV
df134359-5dc6-5308-9f76-b2a9f1a1674c | note | Method - Visual
c8ffc04e-097b-5afc-98e2-46009a2bb2e3 | note | Conformance Criteria - Backfilling and compaction shall be carried out in horizontal layers of uniform thickness not exceeding 200 mm of uncompacted selected fill material for 300 mm all around the pipe or culvert. Compaction in this zone shall generally be by hand tampers to a minimum density of 95% of the standard maximum dry density at +/- 2% optimum moisture content.
7e941825-8a37-5156-affd-1411e8532ac2 | note | ○ Compaction of backfill in the remainder of the trench to subgrade level shall be to a minimum 98% modified MDD at +/- 2% OMC shall be advised.
77984c67-77a1-5da3-8ac8-11de77c8ada0 | note | Specification Clause - EVAMP001-THS-CV-SPE-0003 clause 2.14
6522d457-7c5f-5a5e-9056-b94a6ca1b608 | note | Frequency - As required
f394ffc6-4cc5-5bd2-961f-50c0beb5bac5 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
cd83e072-f633-504a-9e1f-c63299a17b0f | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
f2e5af3b-4b52-57f2-ae91-b9c0c7559ee0 | note | Records or Comments - On site verification/ NATA Test report
6897bc61-4b65-4218-90dc-8eb3042d74f0 | signoff | HOLD POINT
1159a3cc-7c2c-4c3c-9d96-3e199b49f625 | checkpoint | 11 - End Treatment – Headwall & Wingwalls (Reinforcement)
1f839b98-5b3a-5558-bf19-8b81de80dee7 | note | Responsibility - ENG/ SV
362366e0-290a-568e-8e80-5a1193f105a1 | note | Method - Visual
fe093559-62c5-529b-85e3-426694ba424f | note | Conformance Criteria - Reinforcement installed as per IFC design drawings.
f766d9a7-93b5-5769-9b49-98c8c5aabe64 | note | Specification Clause - EVAMP001- THS-CV-SPE- 0003
1dbdfb8b-8258-5bad-9db4-21316f57a77a | note | Frequency - V
62762074-9d1f-5e8e-90d0-e0ae6cfc8dd3 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
d08ebcfa-f442-55d7-bdb6-052d835388e0 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
e48845db-048a-5b10-a261-4cefc6e06e0e | note | Records or Comments - On-site verification sheet
96016adc-bbd4-4134-bcc1-f724a1ab9824 | signoff | HOLD POINT
7c818fcc-cc64-493d-8034-cf92b606f9ae | checkpoint | 12 - End Treatment – Headwall & Wingwalls (Formwork)
a9032701-cf6f-5eee-84c2-d6357ff70e2f | note | Responsibility - ENG/SV
efbe8cad-9b1d-561d-ba81-8ee22ed5b585 | note | Method - Visual/ Field survey
c66faf42-2a3b-5cfc-8fb7-7ea012e6b781 | note | Conformance Criteria - Formwork installed as per IFC design drawings.
afdc0922-d8d7-5d92-9090-ef5cc7dcfbad | note | ○ Tolerances: Variation in cross- sectional Dimensions: + 5mm Variation in overall dimensions: + 10mm
4dfe8944-544a-5cc6-90f1-459027b8edf7 | note | ○ Variation in surface level: + 5mm
aa234672-3f02-58b0-b36e-25b017b43ec7 | note | Specification Clause - EVAMP001- THS-CV-SPE- 0003
b0f36283-2231-5c55-ac1c-5827af306ec6 | note | Frequency - Each inlet/Outlet
4a7a4587-c369-5b2c-addc-8998424f91fb | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
59fd2fdc-4c0f-59ef-b503-8c724bf40855 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
25e25285-f67a-5ea7-ae93-84513d1c542e | note | Records or Comments - On-site verification sheet
137d8f16-9ee3-4474-8fc1-39d38bbd7fde | signoff | HOLD POINT
b24bc6a2-a678-4de6-b061-dca6e0fcd292 | checkpoint | 13 - End Treatment – Headwall & Wingwalls (Concrete)
0167f7a1-7bba-5c05-9e9e-15167e3e68b0 | note | Responsibility - SC/ SV
0591f5f1-bfd4-5c97-bb0d-e73672a21199 | note | Method - Visual
4ddfda5d-a0a2-59c0-b34b-ee98af2f873a | note | Conformance Criteria - Concrete placed and compacted to specified strength (N40) and slump (max100mm).
80bad0fc-f885-5cc7-9f73-10d29ce83f91 | note | Specification Clause - EVAMP001- THS-CV-SPE- 0003
1cf0043e-b88a-5f8a-9928-b059cab4d704 | note | Frequency - Each inlet/Outlet
857b35fd-f0f6-503f-ab3f-d5d6e0537aa6 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
d2fe7261-8871-5430-adf5-12e042c9a560 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
6e6d6a1e-b88c-425e-94d6-d3663839509d | signoff | HOLD POINT
83e2abd0-bdcf-442c-ab81-a2affc4636ea | checkpoint | 14 - Rock Protection
09d56772-61df-51bb-ae43-e66b558b6368 | note | Responsibility - SC/ SV
73b335aa-4c15-5609-8b6b-1675d49ac423 | note | Method - Visual
51ed2597-3a22-50ef-8036-4943869adcec | note | Conformance Criteria - Dimensions and class of rock protection shall be as specified in the Culvert Schedule and supplied IFC Drawings.
f884cbfc-fe8c-5bb3-a08c-4be6ef921df3 | note | Specification Clause - EVAMP001- THS-CV-SPE- 0003
dc47151a-fdcc-585f-904b-b2e27c251e01 | note | Frequency - Each inlet/Outlet
2db8fee7-f48b-5a2e-b13f-8ce46a619034 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
c434e76d-296f-505e-a677-ea9d29334af0 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
84b95209-acbc-482a-85f5-b36c509aaf2b | signoff | HOLD POINT
0e479983-e29c-4b0b-9eb7-75ef58bf6475 | section | Post Construction
278bde5d-6a3c-4ed0-805d-0d175900ffa3 | checkpoint | 15 - Works completed and update ITP/ Lot Register/ MDR
8d43c8a0-0cfc-51bb-8a2c-9d8b66c01122 | note | Responsibility - ENG
58884201-8c1d-51cd-a5cc-c635bbd4f201 | note | Method - Visual
dda7d387-a34e-5cdd-a4fd-03dc93c691bc | note | Conformance Criteria - ITP closed. Approved MDR
1307e404-dd7f-5a6b-b280-3858988a2a36 | note | Specification Clause - EVAMP001-THS-CV-SPE-0003
22b8d26f-c13a-5b0f-999c-2017754b0fb6 | note | — EVA PMP
e28bf5c7-1451-55c7-b97a-83cf39bed3ac | note | Frequency - As required
bfa86957-b24a-52bb-9baa-cabebc4ed9d6 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
87d689e4-9f82-59b5-8d1c-5a030180de05 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
bd987709-df61-4d12-959b-d025f828d7e7 | signoff | HOLD POINT
e75b191c-dd7a-40a2-a54d-7b0af1535acf | checklist | EVAMP001-THS-QA-ITP-0008 Embankment Construction | itp | ITP-0008 Embankment Construction
e8558513-7ab6-48d1-98de-433944eb476e | section | Embankment Construction
4a614c52-e477-4c8c-b9e8-f9f66f963fae | checkpoint | EC1.1 - Underlying lot & ITP signed off and conforming
635d023a-43cc-507d-b6a4-24cad7028583 | note | Responsibility - ENG
7a8f9240-8a69-5c27-80fb-9d3502e0f1b1 | note | Test Method - Visual
783de080-e185-55a5-b451-0ac7c73b29a8 | note | Conformance Criteria - Subgrade/Foundation Preparation ITP signed off
ba80dbfd-0503-5808-bd81-935e41563a00 | note | Frequency - Prior to works
e20c78d0-1941-5154-ac0b-ffc993dea396 | note | Link to ITP - SP.1.9
3f344af9-d08a-5865-81ef-d9da96d5e264 | note | Thiess HP/WP Check - HP
7db41919-c6e1-5e66-90ec-00c0aa29a5c9 | note | Inspector HP/WP Sign Off - WP
51d9a739-4898-4980-a216-4b966f532089 | signoff | WITNESS POINT
492095ef-bc3f-4c0b-b398-01ff56260bd6 | checkpoint | EC1.2 - Embankment fill material
98a574b1-314a-575b-aca7-fe9482091f7c | note | Responsibility - ENG
627647d6-75a4-5752-8fb3-d2056f51c319 | note | Test Method - Visual
723a775a-1db8-5bf8-8f2a-c909a29ed3c3 | note | Conformance Criteria - Ensure embankment fill materials have been approved for use and within specification
8bd82068-6705-521e-814f-145754eb5f73 | note | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage)
a780ca05-c85c-5f5f-85c1-2b0adbf240d3 | note | Link to ITP - PC1.17
9a67a0a0-915a-56ff-b4f5-9cb31fe49ffc | note | Thiess HP/WP Check - HP
2b09a7b7-e569-5fd1-aea6-8705fa41ac77 | note | Inspector HP/WP Sign Off - WP
a8f80374-068c-4565-8062-7727b7ea763c | signoff | WITNESS POINT
6493e315-0ff4-4f7a-9623-6ef291088e0c | checkpoint | EC1.3 - Survey Set out
2c32f299-db28-5f0d-9219-dad69aa702da | note | Responsibility - Surv
b538f08c-0104-5524-b035-0648db232fbd | note | Test Method - Field
4f98f1fa-6f4a-54b5-9861-396450f47579 | note | Conformance Criteria - Areas of work to be set out by surveyor and/or models in plant
7fd90e11-4239-5ae5-b1f6-d92dd61588ac | note | Frequency - As required
cea1e636-bbb1-5c17-b1d7-a6c6b4e0e266 | note | Thiess HP/WP Check - HP
e6df3954-8c47-523e-9c9a-036c5c7a7d0d | note | Inspector HP/WP Sign Off - WP
78e12c6e-590d-4b8c-8cee-4a2451ccdfef | signoff | WITNESS POINT
ccdc3a9c-ac5e-4033-8c3b-ff3b1cb8c838 | checkpoint | EC1.4 - Place, moisture condition & compact embankment fill
cac8963c-7cf9-5eff-8b81-1bef0d83b70e | note | Responsibility - SUP/GeoTech
3617b082-f963-5109-83e7-e68d12666756 | note | Test Method - Field Test
5503e2c0-6737-5ccf-91b7-cf28d197e969 | note | Conformance Criteria - Lightly tyne the subgrade/foundation immediately prior to placing embankment fill.
45b6b68f-e933-5ad8-83b0-7eb3946a126c | note | ○ Layer thickness minimum 150mm maximum 300mm.
466bda59-dc24-50d2-93ff-8affa9feffb8 | note | ○ Density requirements: < 300mm from finished level under roads & structures minimum RDD 97%, all other areas and depths RDD 95%, moisture content -1% to +2%, normal level of testing 1 test per 500m3, reduced level of testing 1 test per 1,000m3.
dce5ac04-f693-509c-a6b3-2ebebcba7c42 | note | ○ Subject to client approval oversized material up to 500mm can be used in general fill at the following depths: 600mm or greater in depth below subgrade for stockpiles, road surfaces and embankments, or 2m or greater in depth below the footprints of structures.
41c0933b-5d94-550d-8cf7-39b243dc4961 | note | ○ Rock fill may be used >600mm below subgrade level.
7d35401b-3418-5cbd-b393-85111554e194 | note | ○ Material containing a high proportion of large particles may be used in embankments using the Mechanical interlock method of construction.Maximum layer thickness 500mm.
46837dee-32c0-53a6-9d17-ff07221c7e8f | note | Frequency - As required
5f766555-e044-53b1-8d65-3f86e6c06f19 | note | Thiess HP/WP Check - HP
d1404653-b3df-5b6b-a697-a65cbf269dc0 | note | Inspector HP/WP Sign Off - WP
ce87cdd3-a9d0-4757-87ac-a2ea0fef9fb5 | signoff | WITNESS POINT
39df1a89-b400-4f6a-b068-a0ce2d3b0a8b | checkpoint | EC1.5 - Trim embankment
b6161dae-c37e-5e66-afec-102e28e5ccd0 | note | Responsibility - SUP / SURV
db15ec6c-0fb7-5015-97ad-7b1db5e7f266 | note | Test Method - Field
50bbc415-a3fc-5d69-aaf3-55b1d84f8d36 | note | Conformance Criteria - Trim all embankment to the lines and levels shown on the drawings in accordance with the following tolerances: Top of bulk earthworks +/-50mm; Road subgrades & under buildings & structures +0mm to -25mm.
3d9fe111-61b0-5165-ad56-3439aaa484d6 | note | Frequency - As required
080e8708-cbfa-5d10-a02b-897d3d617cab | note | Thiess HP/WP Check - HP
10b4ef1c-dad3-53bc-a762-8fbf3aba37a1 | note | Inspector HP/WP Sign Off - HP
2456b688-6f43-425d-b0ac-2af98045b4fa | signoff | HOLD POINT
836357fc-3e4c-4451-a173-3e657eb706b6 | checkpoint | EC1.6 - Proof rolling
e383c7ba-7517-5fe1-b83c-121bf6ce2c2c | note | Responsibility - ENG/SUP
6ef541cc-2c29-50f9-9bbb-66ae1cbd7327 | note | Test Method - Field Test
8d3648f3-7440-5502-8fe1-08b378df709d | note | Conformance Criteria - Proof-roll embankment finished surface under a standard 8 tonne axle load or 10,000L water cart or heavy self propellled smooth drum roller dynapac 620D or equivalent, to confirm that in the Inspector's opinion, deflections are negligible.
90944651-d678-5c95-a7f1-08f0dbe2c70e | note | Frequency - As required
df90c852-a5c1-5852-b384-1ccc0703ed92 | note | Thiess HP/WP Check - HP
45a06049-4ccc-5fa4-8cea-b75345a03dd9 | note | Inspector HP/WP Sign Off - HP
a46f56dd-fd73-4d13-b3b2-efa98fe73ed2 | signoff | HOLD POINT
2056572e-b705-4f91-981b-da286938b639 | checkpoint | EC1.7 - Surface level check and survey pick-up
6a68517f-e29a-540a-a166-b4ed1f6cc0aa | note | Responsibility - SURV
463ad56d-2dfe-5b12-967d-2e9d9176efe6 | note | Test Method - Survey / Field Test
b987ce65-2b06-5023-91f8-ddcef3797e25 | note | Conformance Criteria - Surface level picked up as per Table 10 C15 (DXF file format, volume calculated and filr saved in Construction Team Sharepoint and detailed in register
5e8239db-904d-5e22-863e-bb8645b2ffd5 | note | Frequency - As required
590d7183-81b5-5457-99b3-3ffac96b3b49 | note | Thiess HP/WP Check - HP
a0a0b0f2-922a-5f5a-83f3-21e33d5bcb84 | note | Inspector HP/WP Sign Off - HP
3315d813-4d2a-4914-9e0a-bbdb04f27890 | signoff | HOLD POINT
cd09000b-518f-46ba-8ae5-98753bd77965 | checkpoint | EC1.8 - QA close out
5f98f2d3-89ee-5c8c-b473-d73e0e57bef0 | note | Responsibility - ENG
e350a75b-9841-500c-96b5-73fd23a695e7 | note | Test Method - Visual
864c182e-1c34-5189-b0fc-5df02f7a0727 | note | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR.
163b2fc0-398b-53e7-9368-7252f7f13d9c | note | Frequency - As required
4de988bf-f463-5ec2-ac20-2b34de1ad1ef | note | Thiess HP/WP Check - HP
324c1887-2a4a-596e-a703-e3e18fd31702 | note | Inspector HP/WP Sign Off - WP
361d46ee-d8e9-4f66-b43f-ad76ae5b1f3d | signoff | WITNESS POINT
55c24be9-c984-4bd7-81d3-89feddd065b1 | checklist | EVAMP001-THS-QA-ITP-0009 - Unbound Granular Pavements - Rev0 |  | ITP-0009 - Unbound Granular Pavements -
46d83e0e-dc12-4a68-9459-5ee3be0534b1 | section | Construction
e90b2496-133f-49c7-ba1d-1ba090063a24 | checkpoint | 8 - Subgrade preparation under pavements
b5efbf58-6f24-51aa-b1cd-8a40a808c5c3 | note | Responsibility - ENG
bd463d03-d36d-5a5f-9fcc-1f3a159a7c5b | note | Method - Visual/ Field Test
afa132fb-a8e2-5f52-8166-363a3262c99b | note | Conformance Criteria - If subgrade material is less than CBR10, subgrade shall be boxed and replaced with 150 mm of CBR10 or greater material.
c0313e55-d4f0-5b52-be4f-9fb1ff37a0f8 | note | ○ Subgrades shall be trimmed and compacted to within 15 mm of the established grade or cross section.
a8178b11-70c0-5c2b-8a04-00dd1c116b0a | note | ○ Compaction requirement: 98% modified maximum dry density at +/- 2% OMC.
57358ae3-c447-52a4-9cdb-5d4fed2a2bd6 | note | Specification Clause - EVAMP001-THS-CV-SPE-0002 clause 4.3
e9c4e6c1-c8a9-513d-9cd5-c07a15a69407 | note | Frequency - As required
b6e15ff0-6098-5812-b90b-5e1ff88b96b5 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
bc08139d-35da-57ab-9fb9-d938de0020df | note | Verification from Thiess / Inspector: Inspector (Initial) - W
ea481d21-1078-5492-80f5-2499193e4dda | note | Records or Comments - On-site verification sheet and survey
6e638e1a-0c65-4171-a48a-36dccaf756f1 | signoff | HOLD POINT
012ca282-bc17-4fec-9b42-0f59b29e5afa | checkpoint | 9 - Surface level check/ and survey pick-up
e261c866-4567-5bb6-a7a4-e36c54336911 | note | Responsibility - SURV
b78e0250-592c-5367-9ae6-cb7619089881 | note | Method - Survey/ Field Test
16ecfa22-1795-5cb3-8de7-7711f212f7a9 | note | Conformance Criteria - Surface level pick-up submitted to company.
89e40833-5aa4-598a-aeac-16fd6c0a2579 | note | Specification Clause - EVAMP001-THS-CV-SPE-0002 clauses 2.4.3 & 4.3
575cc3e2-8f75-5534-9c4a-1372fc9cf720 | note | Frequency - As Required
b8afebd1-45f0-52bb-9a7d-9735a84ac1bd | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
c5d8aa23-2ef4-53e7-a000-dc9907aa36d6 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
9b59d515-ed0d-4cff-b55d-3b57f235b1be | signoff | HOLD POINT
f936770b-0fb7-41e9-bbff-29045acc5cc4 | checkpoint | 10 - Proof roll subgrade prior to placement of pavement materials
cb57e981-e5be-5d0b-ae44-31f82a44fb7d | note | Responsibility - ENG
cae3068d-9561-504d-a99a-af8dbdc3c2d2 | note | Method - Visual
4131e5f5-6d96-5208-a1c0-093b6ce6e051 | note | Conformance Criteria - Subgrades under pavements shall be proofrolled under a 10,000L water cart or heavy, self-propelled, smooth drum vibrating roller capable of operating in variable frequency modes, to confirm that, in the principal’s opinion, deflections are negligible
719d7803-e45f-5434-9154-4f1c38fab648 | note | Specification Clause - EVAMP001-THS-CV-SPE-0002 clause 4.1
e4eb8375-ee1f-54e0-baf4-529a1e5e62e6 | note | Frequency - As required
2e2ac758-8671-54ee-8deb-a12def31fb68 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
ce3581bd-1a67-5101-b67c-7349f9109bb2 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
ea433efd-3c3c-5d9f-a459-bd0eab525b6d | note | Records or Comments - On site verification/ NATA Test report
6de874a5-dfd1-425a-a9a5-ddfca9053e2b | signoff | HOLD POINT
4ff39ad4-cd45-4054-af08-c9082146dae3 | checkpoint | 11 - Placement of pavement material layers
bda7bdcd-8404-56ad-9ccb-c26c625f181a | note | Responsibility - ENG
aa4ad49d-ea89-5d63-8a32-8057473f8d41 | note | Method - Visual/ Field Test
53ea55b3-3d98-5a69-9d5e-d3366dd912fd | note | Conformance Criteria - All materials delivered to site shall be accompanied by test certificates.
307f0d91-a228-5e6c-aa53-dc638d7b67d0 | note | ○ Each layer shall be free from sticks, organic matter, clay lumps and other deleterious material, and be spread and compacted in a uniform thickness minimum 75mm, maximum 250mm as per the details on the drawings.
dbf74966-4609-5f83-81e9-f68dac6b9d0b | note | ○ The deviation from a 3m long straight- edge placed anywhere on the surface of a layer shall not exceed 8mm.
4abf40d2-100f-59b8-bee1-361f69bc707a | note | ○ Pavement layer thickness tolerances: Base -0mm to +30mm; Sub Base - 15mm to +30mm.
93c1b157-a541-56cc-af78-6bb823498b4a | note | ○ Finished pavement surface level tolerance: Base - 15mm to +25mm
7cfd5b84-843e-57ff-886d-01f73a09756b | note | ○ Horizontal tolerances: Base, centreline/crown - 150mm to +50mm, edgeline/changepoint -100mm to +200mm; Sub Base, centreline/crown +/- 200mm, change point -100mm to +400mm
1c31be9a-9db9-545a-b8e1-f61138d6b4b7 | note | ○ Compaction requirements:
304d7098-32a3-51f5-ae4c-243b354d8d76 | note | — Base & Sub Base 100% standard relative dry density (RDD) maximum degree of saturation 70%.
cf30c101-9f36-5c53-9525-ded178f2af9c | note | — Compliance testing frequency as per table in Specification Annexure A clause 5.
4ff76f21-8058-5b6d-b1ae-09dece7324a1 | note | — Road roughness count rate not exceeding 60 counts per kilometre.
a82a95e8-6e86-5bce-a0e9-3bf4908ece1f | note | Specification Clause - EVAMP001-THS- CV-SPE-0002 clauses 2.4.2.3, 3.1, 3.2, 4.2, 4.4, 4.5 & 4.6, Annexure A clauses 3, 4, 5 & 6
2c3875f0-c1c1-5578-9510-09da2a25e00d | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
bda8bfde-41a3-5de9-8c7e-bac658af2ab6 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
f337eb3f-ff96-5e65-b44e-c432ce54a48c | note | Records or Comments - On-site verification sheet
363bfb20-2bf5-4cfe-970a-ef901db1a558 | signoff | HOLD POINT
fa258a49-c5e1-4ecc-add7-5b29dc35a983 | checkpoint | 12 - Surface level check/ and survey pick-up
9bbfee6a-1459-5ff5-96a6-103687da861d | note | Responsibility - SURV
9bca724d-fa3b-531a-ba39-da27feba2410 | note | Method - Survey/ Field Test
3354da69-840d-5222-910b-35bd811ef2f2 | note | Conformance Criteria - Surface level as per the pavement layer details on the drawings, and all layers as per the tolerances listed in item 11 of this ITP.
a9c4dd31-c2c1-5303-8b74-8c29e5ba228c | note | Specification Clause - EVAMP001-THS-CV-SPE-0002 clauses 4.2 & 4.3, Annexure A clause 6
b980ba5c-528c-5187-8d80-20883603a8b6 | note | Frequency - As Required
dbcf31e9-a488-51f5-ba7d-6d1de6db94ca | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
9dcc539e-2b6e-5ec4-9743-22282ed7934e | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
317e3eda-cc36-551f-a27e-67f0912e655a | note | Records or Comments - On-site verification sheet
6db10bbe-e356-4d9b-a520-f1e06263fcc2 | signoff | HOLD POINT
feaffb7e-b0fd-48c5-a063-44285e2c08f5 | section | Post Construction
7176b8cd-0dd5-4d46-bdb5-58e379a8f32c | checkpoint | 13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
0858cb34-def5-5bd3-a85d-59f0a2427b89 | note | Responsibility - ENG
d016dbe0-5d5c-57ab-a181-6aa65df2fe59 | note | Method - Visual
353a2e21-616d-5221-ac50-c442f1e406ef | note | Conformance Criteria - ITP closed. Approved MDR
b67b0f72-e1d5-5827-b53c-f5a98ed1fc24 | note | Specification Clause - EVAMP001-THS-CV-SPE-0002
8eac9977-4d95-520e-bbc8-c7a76b14daf9 | note | — EVA PMP
da9012e1-247f-59ed-ad10-2ea8ab434d52 | note | Frequency - As Required
781d31cf-2259-5597-951b-eacd442be47e | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
157ad191-6e79-5cb4-8c1e-a95575a15543 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
22051a51-b92e-4fc2-88c0-d14ded556b7c | signoff | HOLD POINT
de1a9e86-ba3a-45c4-ae56-863ba7b3664c | checklist | EVAMP001-THS-QA-ITP-0011 - Bechtel - Clear and Grubbing - RevA | itp | ITP-0011 - Bechtel - Clear and Grubbing
2f24d350-63a3-41fd-afaf-7c5af8fb2614 | section | Construction
d811d83d-2890-45f0-9a94-14c7e95d41cb | checkpoint | 11 - Clearing of vegetation and removal to nominated stockpile location
f4cb86ec-3b14-5ba0-9b9b-e9d14df07561 | note | Responsibility - ENG
37721023-f0db-58e0-87e8-a2997c191190 | note | Method - Visual
9cf41248-fca4-501e-9751-401cd4c959d8 | note | Conformance Criteria - Spotter/ catcher in place during clearing operations
894639aa-828d-5b34-94d3-adcdb3aefd42 | note | ○ Habitat vegetation, threatened species and cultural heritage areas demarcated
ac4fb978-0f81-569b-9d8e-5f4d406fd4d5 | note | Specification Clause - EVAMP001- EVA-EN-PLA- 1
5edd7166-777e-5404-a825-82c90477aa71 | note | — EVAMP001- EVA-7340-PE- PRM-1
ecd107db-7d27-5ec3-ab9c-c85b224a2565 | note | — C22 of EVAMP001-QVT- PE-PRM-1
16ef6e93-5d01-535c-b8bc-91867fdaba98 | note | Frequency - As required
c1a2e992-1bc1-5a6e-977a-f9531c28dff7 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
db677aac-25bf-54f4-a41d-6242fcab68a1 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
38b2040a-8592-466f-9602-234750ba945d | signoff | HOLD POINT
3fc4852c-4e0f-47cf-9113-f3ac9f50b3d5 | checkpoint | 12 - All Erosion sediment control measures installed prior to construction
ba985687-e6e7-5096-aee0-092f8c9170f4 | note | Responsibility - ENG
1a30e8a4-8a3f-55e9-be0b-c8fe18a79d2d | note | Method - Visual
d628f1af-6c9a-5a88-8258-b172055404e1 | note | Conformance Criteria - All control measures for erosion sediment control need to be implemented after clearing has been completed.
a1c2b93d-d03b-5c2d-9615-ecc700441f4f | note | Specification Clause - EVAMP001-EVA-7340-PE-PRM-0001, EVAMP001-EVA-EN-PLA-0001
63339f53-d30e-5853-b46f-49b4f7326543 | note | Frequency - After clearing completed
528b32d0-9fef-5130-a593-6fde74646f68 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
b44d941a-8867-5c43-b3da-f2725056b372 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
453c5908-845a-459e-b4fb-372e3304b445 | signoff | HOLD POINT
6d1992dc-aaf0-4c1c-b0e5-4d768959bfcf | checkpoint | 13 - Inspection of foundation prior to next stage of construction
69814b75-904c-5dc5-9ee0-9ca3000ba41c | note | Responsibility - ENG
5e3e056b-3882-5afd-b74f-285639d304c8 | note | Method - Field Test
63a29fba-cfb3-58be-9a79-651fba8bbb7d | note | Conformance Criteria - Proof roll where required
644eb386-d00c-5cbf-b8eb-22b29661eb83 | note | Specification Clause - EVAMP001-EVA- EN-PLA-0001
6625a3ff-379e-58db-8314-f74332599811 | note | Frequency - As required
934f1902-62dc-5fff-a676-5f4d8fd41749 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
d44f2ca2-4b67-55a5-855c-4c2570523051 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
33ee32b5-c894-4448-8535-e40b7bf27f40 | signoff | HOLD POINT
b7523562-898c-4916-83bd-cc22c95203b4 | checkpoint | 14 - Surface level check/ post-strip area survey pick-up
146f00d7-5fb4-5c3e-86fd-20e8254ec4e4 | note | Responsibility - SURV
0aa1c7dd-62d9-5cfd-bda9-bdad7ca35a0a | note | Method - Survey/ Field Test
e5276fdf-6489-5c46-a8b4-bcfeb120580c | note | Conformance Criteria - DXF file submitted to Company
afbf4c1a-95ee-5e79-8ff2-6bdfc95914aa | note | Specification Clause - EVAMP001-EVA-7340-PE-PRM-0001
3695a337-712e-5f33-ac31-fafeb5c0b7d6 | note | Frequency - As required
a408d3db-2050-57e0-9932-ff8777d48855 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
3165b394-7235-5ed1-8b19-98dfb5361ce6 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
08bb96f7-abbd-4a58-92e1-94db2aba5601 | signoff | HOLD POINT
16a4aecd-45f2-4dce-a15b-3759c6c72587 | section | Post Construction
7e9fce8b-4d0f-434c-8439-cd8f03f66538 | checkpoint | 15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
dcb67777-edd9-571a-b768-7b13d07878bd | note | Responsibility - ENG
20382013-bdd0-5a93-a85d-ea91eeae9f52 | note | Method - Visual
6935b9cf-4451-5d31-9c24-e82b83767bab | note | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR
1756ba2b-a6c7-5c6f-8ce3-be1df331d0e8 | note | Specification Clause - EVAMP001-EVA-7340-PE-PRM-0001
01749e0e-c939-543e-b146-b9a9257f2d8b | note | — EVA PMP
23ed15e2-cff7-5925-84e6-ff3943273b26 | note | Frequency - As required
c43babbc-2f13-593d-9a6a-53905e6e30f4 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
60dc22ad-75de-580f-8a77-da5bb39bca84 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
06bc5557-62a0-43bb-aad1-eea66ccd37e8 | signoff | HOLD POINT
25d6a019-b9d4-4013-b535-b74c1c884efa | checklist | EVAMP001-THS-QA-ITP-0012 - Bechtel - Topsoil Stripping - RevA | itp | ITP-0012 - Bechtel - Topsoil Stripping
0a65cfc8-846f-4d49-8237-85977329415d | section | Construction
90579e75-07c0-40db-b677-436b01d9849a | checkpoint | 7 - Stripped topsoil load and hauled to nominated stockpile location
7e422271-4613-596a-9dc0-4364a9fccff5 | note | Responsibility - ENG
4fb12972-881a-5a18-9750-6426df0cc0dd | note | Method - Visual
12105e9e-aeb4-5e1d-a6f0-636a34cdeda9 | note | Conformance Criteria - Stockpile locations located 40m from watercourses and not exceed 2m in height. Native seeding of topsoil stockpiles as agreed with Company. Topsoil stripping shall be to a depth of 200mm or to the bottom of the grass root zone or as shown on the drawings, whichever is the greater
37c07433-6c50-556e-95db-4bb52bada60f | note | Specification Clause - C9 of EVAMP001- QVT-PE-PRM-0001
9a6c68cc-a2ea-56c8-b054-6b70578a86b6 | note | — EVAMP001-EVA-EN-DCR-0002
2abd0ea5-2bbd-5dfe-9067-815bc8df9c16 | note | — EVAMP001-EVA-EN-PLA-0001
1a12c06c-ed04-578e-bdf3-b4824c89f863 | note | — 107501-EB-00000-27280-001 Rev A
dc6be7e3-7bdc-539b-9db9-44796c2be06c | note | — EVAMP001-BEC-3920-CV-SPE-0001 Rev 0
77ba4f7c-5ed2-5769-9c09-2b07f595e5de | note | Frequency - As required
ff0b47e4-001a-51f6-b1c3-6fa449376f40 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
0beaa99a-4767-5732-8d2a-a1547a0b7b4f | note | Verification from Thiess / Inspector: Inspector (Initial) - W
676ba800-130b-45c8-baba-44154397327b | signoff | HOLD POINT
8bc13ab5-87b3-4f98-9ad1-5ab003cbc686 | checkpoint | 8 - Topsoil location, destination and quantity catalogued.
8e545323-c749-58e8-9d20-68056a502169 | note | Responsibility - ENG
7e96687e-0442-5b97-8a12-13ad853e2f8f | note | Method - Field Test
7be9dbc6-05c8-5d9f-ae88-45b36aba056d | note | Conformance Criteria - A topsoil inventory will be maintained with information on topsoil volumes and stockpile locations
26743f42-ce17-5c42-bac7-ef668643d3f3 | note | Specification Clause - EVAMP001-EVA-EN-PLA-0001
0653efb2-685b-51f9-806c-2573035a2bda | note | Frequency - As required
5149dd3b-dcbc-5c9f-b5eb-6e4c2d800dd1 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
84c68a26-a550-5764-bc5d-672e60eb8ac9 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
bbfdd261-f025-4c3e-907f-16cd7feffa48 | signoff | HOLD POINT
401dcbcf-e6fd-4a0d-948a-5d8abbc52cd0 | checkpoint | 9 - Surface level check/post-strip area and volume survey pick-up
7c5ecc4e-6f89-5511-aab9-5baaa777b22f | note | Responsibility - SURV
3bef0e3a-3a7c-5490-9b02-4080824355a2 | note | Method - Survey/Field Test
e9b94fe4-7613-58e9-a603-2e93e685a7e5 | note | Conformance Criteria - DXF file submitted to Company and inventory updated
4c602d0c-5ac1-5f0e-8ef8-1e3acf07179b | note | Specification Clause - EVAMP001-EVA-7340-PE-PRM-0001
203898da-15e3-57ee-b50c-2eae9ec27a42 | note | Frequency - As required
2992b67b-0758-5e28-9a7f-de1dcc6ffddd | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
4437165d-3f81-5598-b12b-ab1988144029 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
d3461d6a-72a7-4686-afb0-a148fa9ad6d5 | signoff | HOLD POINT
250cc13f-93a4-47b1-a374-566f710c73fe | section | Post Construction
c9197ecc-ced5-4056-ac65-12779e809774 | checkpoint | 10 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
eeed2444-7798-5b73-af52-875b5d2db4c9 | note | Responsibility - ENG
78787e50-950d-56bd-a584-cc3ed713d97c | note | Method - Visual
8231646a-cdc3-5813-b5cd-214726360383 | note | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR
fa7e1006-c756-5f28-b02b-c2ab4a5242f9 | note | Specification Clause - - EVAMP001-EVA-7340-PE-PRM-0001
eac0415b-278b-583d-88f1-a648ffa59dd0 | note | — EVA PMP
c9889c3e-2e5f-571a-b92e-69895a5a4396 | note | Frequency - As required
122201a1-46b3-5e8e-a127-983852d5d33a | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
dec22919-7706-5c4d-9043-c358fec671c8 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
d67c2a11-bd1e-489f-9646-f3a5c9cf4f94 | signoff | HOLD POINT
656f4648-5637-4ab5-a76b-575b30a637a3 | checklist | EVAMP001-THS-QA-ITP-0013 - Bechtel - Subgrade - RevA | itp | ITP-0013 - Bechtel - Subgrade
11cd7a4c-8bc9-495a-9140-78a0b3e5a475 | section | Construction
92326171-9b51-4bc9-bb09-c54d705f5139 | checkpoint | 7 - Removal and replacement of unsuitable material
2427d79a-b965-51d1-bd60-b2958848f8d6 | note | Responsibility - SV
6c52769c-2dbe-5497-a783-8e1f2214a9e6 | note | Method - Visual
0d096bb0-074b-50a8-a36e-57d7fd26caee | note | Conformance Criteria - Where directed by the client’s representative remove and replace unsuitable material and dispose to waste at an approved location or as shown on the drawings.
f735ea9d-2490-5529-b7cd-2f0e6a7fcdfe | note | Specification Clause - EVAMP001-BEC- 3920-CV-SPE-0001 rev0 Clauses 3.5.6 Unsuitable Material & 3.5.7 Disposal of Materials
b114f6a5-966b-5ed2-aeac-ccce1f3ee40d | note | Frequency - As required
920b5f3b-9b1d-530a-a5de-179fffe45329 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
9d0fcfd9-500d-5f92-a1ff-3fde9857fec7 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
3c3a07ba-afed-4582-8517-f3bcc2b84b99 | signoff | HOLD POINT
70baa086-6f6d-4192-9482-d444ba1d0f2e | checkpoint | 8 - CBR values of subgrades under pavements, buildings & structures
626b54b0-a61a-50fd-aef7-7833588a20af | note | Responsibility - ENG
468542c3-0fb0-5e2f-a3ee-355085d2bcf8 | note | Method - Test
b30b47d8-9046-5f3a-9579-af162b9d1c09 | note | Conformance Criteria - The materials exposed at subgrade level of cuttings are to have a minimum CBR of 3.
22f26115-120a-5c36-b795-1d06ebe554ef | note | If CBR >3:
002ad5fa-e8f0-599b-aa8b-0fd81f2213d9 | note | ○ CBR 2 excavate 150 mm below subgrade level and replace with compacted selected fill (minimum CBR 10).
a8270f0c-9b23-5a5c-941e-9e6a0e37add8 | note | ○ CBR 1 excavate 250 mm below subgrade level and replace with compacted selected fill (minimum CBR 10)
12d8546c-bad6-56d7-9c81-65414d9308f3 | note | Specification Clause - EVAMP001-BEC- 3920-CV-SPE-0001 rev0 Clause 3.9.4.1 Subgrade Preparation for Structures & Pavement
ab58eda5-378c-5f06-898d-b9ca50e1d8a4 | note | Frequency - Not Specified
60ada166-1cc3-5c4a-97cf-631075a9061a | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
72bd8e06-ff56-5a61-bd49-05a3526fbddf | note | Verification from Thiess / Inspector: Inspector (Initial) - W
68f05dca-4508-4b7f-988b-56017b8b100d | signoff | HOLD POINT
4cecb3fc-bb6d-4cec-9589-e28008e56bdb | checkpoint | 9 - Subgrade preparation under foundations for structures
a7bac71e-433f-5223-8f18-5fc8809a7371 | note | Responsibility - ENG
f8c9d515-d7bc-5f13-a33e-cb4bc0ce3e44 | note | Method - Test
13df9edc-dc6b-5c5c-a4ca-e5c489b2eb7f | note | Conformance Criteria - Area to be ripped to 300mm in depth, moisture conditioned and compacted to not less than 100% of the maximum dry density (standard compaction)
ff0022e5-a848-55fa-88e5-4677b3feceb6 | note | Specification Clause - EVAMP001-BEC- 3920-CV-SPE-0001 rev0 Clauses 3.9.3 Compaction Standards, 3.9.4.1 Subgrade Preparation for Structures & Pavement
813d9584-bd92-5efb-ab32-100d4aaef856 | note | Frequency - Normal Level of Testing: 1/500m2
35da0f79-0de3-57f4-add3-db11300775af | note | ○ 3/visit Reduced Level of Testing: 1/1000m2
20fab213-ab0e-5331-adf9-8398d41db41c | note | ○ 3/visit
c3619d1d-2ba5-5636-a75a-b920e5931483 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
e3311762-0eda-55be-95f7-f5aa47b5008f | note | Verification from Thiess / Inspector: Inspector (Initial) - W
6e4f1ffd-e268-4ed3-bee3-58fe27b1649f | signoff | HOLD POINT
783e7cae-8758-4cc5-af1e-41e701f9f921 | checkpoint | 10 - Subgrade preparation under roadways & earthpads
ef773d26-a435-5b7c-8a8f-76db9322ac36 | note | Responsibility - ENG
e2d476a9-0a64-56ba-a0da-4cca5df7b2f1 | note | Method - Test
0694ccb8-f2d3-5098-b68a-54fc3bd61d29 | note | Conformance Criteria - Area to be ripped to 150mm in depth, moisture conditioned and compacted to not less than 98% of the maximum dry density (standard compaction).
b7ccedde-fd5d-596a-a742-6975deaf558c | note | Specification Clause - EVAMP001-BEC- 3920-CV-SPE-0001 Clauses 3.9.3 Compaction Standards, 3.9.4.1 Subgrade Preparation for Structures & Pavement
a7ba9984-bf99-5b2b-b8d2-a56ae2f55512 | note | Frequency - Normal Level of Testing: 1/500m2
c145e732-7067-5fef-a6b2-04928bd468f0 | note | ○ 3/visit Reduced Level of Testing: 1/1000m2
4bbe7ec8-4e45-5f15-b1c5-dfdfe9e1bb54 | note | ○ 3/visit
e20c7da6-8ea6-54af-8b9a-53044156e885 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
d84b48dc-f810-5909-b88f-dcbd8c11102a | note | Verification from Thiess / Inspector: Inspector (Initial) - W
b865a038-9f54-43b4-82d6-7de32d3c2339 | signoff | HOLD POINT
82942dd8-5869-4203-85ae-b63928d6495e | checkpoint | 11 - Proof-roll subgrade surface
f3dc636e-df8c-5909-9b42-2c8c666b64cb | note | Responsibility - SV
790c33a1-e444-501a-b60b-feb7193805e5 | note | Method - Test
65cd99d7-100d-5ea1-bcf2-2f817374bec4 | note | Conformance Criteria - All subgrades and foundations shall be proof rolled using a 10,000L water truck loaded to 8 tonnes with dual tyres minimum pressure 600kPa driving at 3- 10km/h. Any areas that show signs of visible movement to be rejected and reworked.
1ac20981-fb8a-5706-a955-a0d53f6c5e4e | note | Specification Clause - EVAMP001-BEC- 3920-CV-SPE-0001 rev0 Clause 3.9.4.1 Subgrade Preparation for Structures & Pavement
2dc91b21-d703-5e71-863c-b882f9a99d76 | note | Frequency - As required
9edc5b39-06c1-536f-bf54-7f19c138a54e | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
d9976906-67d0-5e89-9b95-57aed80ad293 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
d3bb97ea-fb0e-4bb4-a44c-f55818d68f4c | signoff | HOLD POINT
100bb891-bf81-4445-ad9d-ea972d1d0938 | checkpoint | 12 - Surface level check/ and survey pick-up
ea8ca583-9929-5460-a5a8-039d91c904f1 | note | Responsibility - Surv
a435ae5d-2347-530d-a408-a1a961eac202 | note | Method - Survey/ Test
299737f5-ddcc-5c96-be05-f8bf0c4a947f | note | Conformance Criteria - Vertical Tolerances: General Earthworks +/-25mm
535aeef5-aec9-5e92-95bd-20c1d03bf801 | note | ○ Road subgrades, buildings/structures pads -25mm to +0mm Horizontal
17e3d75f-0486-50f3-bcba-dbbe9b8895c6 | note | ○ Tolerances: Road width -0mm to +250mm
bd31d2f6-851f-54da-adb7-d24074742c29 | note | ○ Trade Tolerances: Road +/-0.25% Pads +/-0.25%
dbd6a64b-f9ee-5666-af8b-c8abc018dca4 | note | Specification Clause - EVAMP001-BEC- 3920-CV-SPE-0001 rev0 Clause 3.11 Construction Tolerance
2ad07982-25be-5078-9833-2c1795cd9626 | note | Frequency - As required
6e4c790a-c703-5791-ab86-c211569f6b9f | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
df5d36a5-facd-5eaa-a02d-ee9dfd43ebc0 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
b269b6d7-730f-416d-aac3-fb924dec5233 | signoff | HOLD POINT
c15fa9bb-9e18-4678-b244-5b5067bbb7d5 | section | Post Construction
6cdd6b2b-5515-4c73-98e7-f722be38db77 | checkpoint | 13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
9b337e38-ce21-5fd3-bfec-4c5d25315262 | note | Responsibility - ENG
6c3083b4-b2e0-55ac-8e7d-4b836206d302 | note | Method - Visual
4bf31dd0-958a-5745-b660-ad80b11b5546 | note | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR
948efb76-2b53-5f0e-82e5-56bda3da406f | note | Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 rev0
bc58495e-90e4-5b36-a421-3c43cd678939 | note | — EVA PMP
97fcb727-658e-5673-b966-f9d3f7c182e5 | note | Frequency - As required
791b7ba8-f666-5188-81e9-9dc8999bd041 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
fe9f724d-1324-558c-8206-06ada0643994 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
4709d168-7835-48da-9fbd-9db97c4af697 | signoff | HOLD POINT
f7cdde62-7fe5-419b-b18d-3a926be43d98 | checklist | EVAMP001-THS-QA-ITP-0015 - Bechtel - Embankment Construction - RevA | itp | ITP-0015 - Bechtel - Embankment Construction
753cce53-9e64-4b7e-901a-ef9c0cbd2169 | section | Construction
98784bd4-0382-4a0c-a52f-87052e930f67 | checkpoint | 5 - General Fill Embankment Material Properties
f1041bf6-9a45-5463-8a05-b3ee8681f5a4 | note | Responsibility - ENG
7046b142-cf37-5511-a3dc-dddcd116053c | note | Method - Test
6515a4b2-94c6-56d7-ab88-2d12c8f1aeda | note | Conformance Criteria - Class A:
bedcb04c-9f60-5f71-b411-2972c849e45e | note | — WPI < 1200
18aebbe9-7fe2-5df5-a475-f91e89fb8aef | note | — PI > or = 7%
30f44429-eb52-57ee-a327-68a87de23145 | note | — % passing AS 0.075 sieve 15 - 30%
ffd5686c-babc-59dd-858f-9f65d5c40848 | note | Class B:
8a9bb921-90de-54ba-b5a2-94eb2d680ed4 | note | — WPI 1200 to < 2200
936971a3-1f93-5d24-8f67-fd67613c466d | note | Class C:
5cf94440-613e-5d1d-b923-c4a373d20ba8 | note | — WPI 2200 to 32200
3449eb6a-2f2c-5f67-8c89-9f718c4e2c10 | note | Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 Rev0 Clause 3.8.2.1 General Embankment Fill
1f8324d5-24b6-5d58-bffe-924e05cf7189 | note | Frequency - 1 test per 5,000m3
be3b4349-8c91-538c-98b0-c8271d06f981 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
b32cecbe-7bef-5a14-855b-f4e716e90a1a | note | Verification from Thiess / Inspector: Inspector (Initial) - W
c1c54fcc-bbd5-5b6c-89da-558b18b8e6e7 | note | Records or Comments - NATA Test Results
2cd18a11-fd0f-4fd4-aa8b-0c433b481156 | signoff | HOLD POINT
20fb2254-ee87-481a-a627-c15e1414969b | checkpoint | 6 - Select Fill Embankment Material Properties
d7a15999-e99d-57f5-aab6-d2d931d8f4da | note | Responsibility - ENG
a4ac7ee3-e952-5c0d-9a5c-6b2fa69069ea | note | Method - Test
d8b2acc1-e0f1-57ed-ad64-cfd9ec38860a | note | Conformance Criteria - Select Fill Material:
d51404c9-dd00-5577-9e68-c5b712fdcb2a | note | — CBR > OR =15
17a3c0c2-3569-541e-a61e-4da60919d52b | note | — Max. aggregate size: 40mm
54f94931-0d60-5267-8d09-2152244c2e10 | note | — Linear Shrinkage: max. 7.5
73919ddc-738e-50a1-adff-1b8de15d8da2 | note | — Liquid Limit: max. 40
47a7be1e-8ca6-5bfd-97b5-d30895f22c17 | note | — Plasticity Index: 4 to 14
6a7798bc-4add-5f6e-abc6-ea0662530d87 | note | — Weighted Plasticity Index: < 560
da6ffa10-babb-5097-9a78-678cb527bb78 | note | — Swell < OR = 0.5%
2923fe1a-0470-5720-b09c-a287e3772db9 | note | — Particle size distribution as per Bechtel EW Specification Table 3-6: Select Fill Particle Size Distribution Envelopes
d409d0d4-9dab-50ce-9251-12d5906ea7ec | note | Specification Clause - EVAMP001- BEC-3920-CV-SPE-0001 Rev0 Clause 3.8.2.2 Select Embankment Fill
f8fc0cd5-6a38-51a1-a394-94d8b5495401 | note | Frequency - Site Won Material: 1 test per 1,000m3
4e44ece0-2004-5c8a-9269-f340f7811ded | note | ○ Quarry Sourced Material: 1 test per 2,500t
de57b39c-bd59-5c1e-a3c7-f8b2eda663e6 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
01335961-e501-5c2e-909b-383a736c7004 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
3dfdc853-b615-5b1d-b662-6c8b7ed69fd6 | note | Records or Comments - NATA Test Results
52df0f59-55e0-4061-b233-71c5b7f264a9 | signoff | HOLD POINT
c75ec0c4-4b6c-4f9b-a356-90c1aba27cbf | checkpoint | 7 - Structural Fill Embankment Material Properties
8dbdd9f1-d640-5ecc-a973-ddcd5941433c | note | Responsibility - ENG
5425bb56-39de-531b-a2e0-01832d13f4df | note | Method - Test
5b198bea-3855-5435-9898-13946355583e | note | Conformance Criteria - Properties of Coarse components (any component retained on the AS 0.425mm sieve) Type A & B:
c708013e-b110-5521-b007-be2720732ed1 | note | — 10% fines value (wet): min. 85kN
271023d6-b540-589d-8f3e-51e6c9002bfd | note | — Wet/dry strength variation: max. 35%
82efda49-33cb-55a3-922f-904928ffcc48 | note | — Washington degradation: min. 35
de6b66df-854b-57c9-8afa-de0d6744a055 | note | — Flakiness index: max. 40%
cec12b17-6b1e-5d85-8ae4-02b7c408712e | note | Properties of Fine components (any component passing through the AS 0.425mm sieve) Type A:
eecf2c64-578a-5900-95cc-4e1112bf525a | note | — Liquid Limit: max. 25%
99d6eff7-2bf3-56d1-a383-095e7f1fa854 | note | — Plasticity Index: max. 6%
94b5442e-1f3d-5ec4-ac3a-1e5cf8906127 | note | — Plasticity Index x % of whole sample passing the AS 0.425mm sieve: max. 150
56089b95-8e8f-504a-8aeb-00b96309d186 | note | — Linear Shrinkage: max. 8%
9f10c0e5-ec9a-5584-a3b0-1a6775c11504 | note | Properties of Fine components (any component passing through the AS 0.425mm sieve) Type B:
ef6e3b1c-5491-5997-9059-01e3b14e5c03 | note | — Liquid Limit: max. 35%
33ce4acf-a246-5fc2-99d5-ea3d819026a4 | note | — Plasticity Index: max. 12%
a6bdafdb-3d85-5998-a062-6d04eddf5b5b | note | — Plasticity Index x % of whole sample passing the AS 0.425mm sieve: max. 360
7378c11c-f97d-50cb-81ff-bdaa35d09030 | note | — Linear Shrinkage: max. 8%
c2d0ce34-2b21-5f09-9ae3-e24ba64cfd25 | note | Particle size distribution as per Bechtel Specification Table 3-11: Structural Fill Particle Size Distribution Envelopes CBR
2a67822a-b51d-5937-a1ea-9af7ead85055 | note | — Type A: min. 60
8f8a1dfb-29d3-5614-b74d-83a7571272d3 | note | — Type B: min. 35
ff7546b2-d4ef-5100-8ae4-c4f42f375707 | note | Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 Rev0 Clause 3.8.2.5 Structural Fill
2da6f537-7629-5fa2-b784-185a88061665 | note | Frequency - Particle size distribution, Liquid Limit, Plasticity Index. Minimum testing frequency: 1 test per 1,000m3, and 1 per work are and 1 per change of material.
67f956eb-cd03-52ae-9d7b-65be2c702429 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
700e5161-4e9c-5390-9809-002038354598 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
c3791cf7-2529-5d3c-b0d9-ccb370ea8d93 | note | Records or Comments - NATA Test Results
b5c821b1-3a34-47d4-be3d-e356ff4950c8 | signoff | HOLD POINT
68004e7a-5a94-40c0-ae1c-f6df31370430 | checkpoint | 8 - Lined Pond Embankment Material Properties
652e974a-6e82-5a35-bad2-62ac8c434f35 | note | Responsibility - ENG
1a4ba9ba-9e74-5c52-a335-240b1b27306c | note | Method - Test
3128990b-3407-5e55-825c-441146910f46 | note | Conformance Criteria - - % passing 37.5mm sieve > or = 80%
7be52f67-b2ca-5fe4-8217-888f3fd3c35e | note | — % passing 0.075mm sieve > or = 30%
6e7435d7-a505-5f32-bd58-6d070c0d9401 | note | — Maximum particle size 125mm
63d9cc26-3ce6-526d-a3e0-5928559dcbc0 | note | — Plasticity Index > or = 7%
cc7b36be-d1bf-5c3b-b28e-dc4f8bf0db93 | note | — Liquid Limit 20 to 50%
dad3e485-c95a-55ea-ac5d-8503b15daad6 | note | — Emerson Class > 3
206b14ba-2408-51ac-9758-6857b351cfda | note | Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 Rev0 Clause 3.8.2.6 Pond Embankment Fill
f10f179d-3b15-59f8-b93d-fb841e9d8198 | note | Frequency - Not specified
43582e10-dbb1-5df2-8692-f61c36c3d59c | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
1cda9134-a082-53b6-a144-acd63c5fe86d | note | Verification from Thiess / Inspector: Inspector (Initial) - W
22961ca0-82cb-533b-a97a-b11a1f857be4 | note | Records or Comments - NATA Test Results
c5a8952a-fe57-4e62-b523-dd75359192c1 | signoff | HOLD POINT
47a6392b-99f8-43a2-8138-de13a9e3a4ca | checkpoint | 9 - Remove & Replace Unsuitable Material (as directed)
46b08832-f6cd-55c4-85f6-11b66eb45f0c | note | Responsibility - SV ENG SURV
570a1ecc-2d5e-5d0c-b6b9-fb3730952a36 | note | Method - Visual & Survey
6211d747-c519-55a7-a703-89d02a67d857 | note | Conformance Criteria - Where directed by the client’s representative remove and replace unsuitable material and dispose to waste at an approved location or as shown on the drawings prior to placing embankment fill.
63b425aa-89f1-59c6-bbc5-c1befe77ad1c | note | Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 Rev0 Clause 3.5.6 Unsuitable Material
4d74e0ff-5f0a-5692-b6c3-82c82ec1065f | note | Frequency - As required
d85503b3-848a-504e-bc84-cc901e0717ad | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
bd4b7e17-6b72-5b83-8987-f3b7ec0e38c3 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
9c36eba3-0060-5930-8f06-c98dfb5a6554 | note | Records or Comments - Survey Records
693518ad-1743-4f06-8117-6c0044cd6f08 | signoff | HOLD POINT
77c58a38-2570-468a-b15c-c70df79d8359 | checkpoint | 10 - Subgrade Preparation Under Embankment Fill
e7929635-fb10-5c46-a5a0-cb70b83c8489 | note | Responsibility - SV ENG SURV
22a17cb9-6050-569c-b623-43783d0ee679 | note | Method - Test & Survey
9d12ae61-bab5-56aa-af08-fc8ccb64776d | note | Conformance Criteria - Natural surfaces under embankment fill shall be tyned, moisture conditioned and compacted to a dry density ratio of not less than 98% standard compaction.
aebf3c3f-e924-5d4f-b541-f65f9a03905f | note | Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 Rev0 Clauses 3.8.3 Preparation of Natural Ground & 3.10 Testing
5389716f-5972-5bf4-88bc-eb3254f8a2c7 | note | Frequency - Normal level of testing minimum frequency: 1/500m2 & 3/Visit
f957fb3d-80ec-5297-94a2-be9ecfd7559b | note | ○ Reduced level of testing minimum frequency: 1/1,000m2 & 3/visit
4397353f-3944-5b74-a43f-7a087e832f8a | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
892229ea-97d9-5b8d-84e1-6b7073752a00 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
0d89d0b4-8d3a-595e-8261-dd49484f0ee0 | note | Records or Comments - NATA Test Results Survey Records
8b1aeaa9-6749-4f31-8be2-45b8e7062e16 | signoff | HOLD POINT
089529f6-b3e0-40a9-a781-7fc68738e351 | checkpoint | 11 - Embankment Construction, Layer Thickness, Placement & Compaction
36b5afd2-dabb-54c9-a329-53d8ecf12f03 | note | Responsibility - SV ENG SURV
31349fc9-4aa6-5e01-9d76-2187f5852382 | note | Method - Test & Survey
11ced718-c8a2-5212-90ae-1b8b2e4221db | note | Conformance Criteria - Depths of layers shall not exceed the capability of the proposed plant and in any case shall not exceed 300mm uncompacted.
876fa021-73a5-5669-b698-ad392e73a708 | note | ○ Layers in the top 300 mm below subgrade level for foundations, including the foundation of generators in Independent Power Provider, shall be compacted to not less than 100% of the maximum dry density (standard compaction) with moisture content +/- 2% of OMC.
e7f2a4e7-09f7-52b6-8a73-f22c7b458bb9 | note | ○ Layers for Earthpads, the top 150mm of Road Embankments, Foundations in the top 300mm below subgrade level, Pond Embankments, and the Crushed Ore Stockpile to be compacted to 98% of the maximum dry density (standard compaction) with moisture content +/- 2% of OMC.
4b9411b5-924f-5d6d-a5e8-0131a7845d6e | note | ○ Fill material other than that referred to above shall be compacted to a dry density ratio of not less than 95% of the maximum dry density (standard compaction) with moisture content +/- 2% of OMC.
4c52c895-d18c-54b0-8027-865c351366b2 | note | ○ Rockfill or mechanical interlock method shall not be used in areas proposed for buildings and other structural works, nor within a zone 600 mm below subgrade level for road embankments. Minimum thickness of uncompacted layers: Greater of 150mm or 1.5 times the max. rock size. Max. thickness of uncompacted layers shall not exceed those nominated in Table 3-14 of the Bechtel EW Spec.
7c102a44-c806-5dd0-b5d8-29911b404752 | note | Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 Rev0 Clauses 3.9.3
cf840c49-fa25-587a-8b47-514b01433d59 | note | ○ Compaction Standards, 3.9.3.1
312044d2-26d8-5302-a990-5f46e38f547e | note | ○ Compaction for Embankment (Compacted Layer method), 3.9.3.2
852c38bb-2726-5051-9dea-93ce11929c6a | note | ○ Compaction for Rockfill (Mechanical Interlock Method), 3.9.4.3
25646b71-bd21-550a-9846-a66765dce219 | note | ○ Compaction and Moisture Content & 3.10 Testing
d4f8e9d0-6dde-50e1-9ad5-2b049e08711e | note | Frequency - Operations >5,000m3:
a2cfca9d-e1cb-5ab5-bc8c-754da8e92eb5 | note | — Normal level of testing minimum frequency: 1/500m2 & 3/Visit
e7af93cd-22f9-5dbf-84a2-9c9b4d12ec02 | note | — Reduced level of testing minimum frequency: 1/1,000m2 & 3/visit
8d770a56-77ab-5e79-8d6a-b13bc3823291 | note | Operations 500m3 to 5,000m3:
d673a667-e3fc-5946-8d80-f6c89e1df32a | note | — Normal level of testing minimum frequency: 1/500m2 & 3/Visit
a6bcf9ee-b5b9-50ec-9265-8c9c1c4a48ed | note | — Reduced level of testing minimum frequency: 1/1,000m2 & 3/visit
fe7edf22-d408-5743-b44f-0b121c3fa258 | note | Operations <500m3:
8a436bc3-06db-5147-8922-631f5ae2b03d | note | — Normal level of testing minimum frequency: 1/500m2 & 3/Visit
d9fd3706-b860-552b-947e-02b2f713214b | note | — Reduced level of testing minimum frequency: 1/1,000m2 & 3/visit
1ec02359-5853-569b-8470-067dd1619bf7 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
5217ce51-be03-5b8e-a91e-339493ca3667 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
890971ef-9856-55ec-bdd2-54b4fefc5a0e | note | Records or Comments - NATA Test Results Survey Records
6a9981fb-6860-48ed-9e9d-b6f4ed97ab27 | signoff | HOLD POINT
42c52a21-5b3f-4308-bead-86ac132e5d7f | checkpoint | 12 - Subgrade Preparation Under Structural Fill
74f47184-62a0-583d-b938-3d2af03162ad | note | Responsibility - SV ENG SURV
e596d302-3daa-5ee1-9a9e-7deffb1eee72 | note | Method - Visual & Test & Survey
13f3aa9e-88b6-5b48-8d41-6a6ccd1e4f49 | note | Conformance Criteria - The top 300 mm below subgrade level for foundations shall be compacted to not less than 100% maximum dry density (standard compaction).
a2800b3d-881e-5348-a52a-6bcf0af17239 | note | For subgrades under pavements and buildings / structures, the materials exposed at subgrade level of cuttings are to have a minimum CBR of 8. Should the CBR be less than 8, the following subgrade treatments shall be applied:
2b4dfdf2-5efe-5b25-8663-723c8b41df78 | note | ○ CBR 2 to 7 – excavate 150 mm below subgrade level and replace with compacted selected fill (minimum CBR 10).
e14275eb-5106-511d-b026-b2ec46bb32ee | note | ○ CBR 1 – excavate 250 mm below subgrade level and replace with compacted selected fill (minimum CBR 10).
22509fe0-3782-535a-b593-1332f5617ba4 | note | ○ Proof rolling of the formation which is to receive structural fill and pavement structure shall be witnessed by a civil/geotechnical engineer to ensure that no soft spots remain in the compacted subgrade. Any areas that show signs of visible movement under the rear axle of an on-highway type 10,000L water truck will be rejected. The rear axle of the water truck shall be loaded to at least 8.0 tonnes and fitted with dual tyres. The minimum tyre pressure of the water truck shall be 600 kPa and the testing shall be conducted at a speed in the range of 3-10km/h. Both the Company and the Contractor’s representatives shall walk alongside the testing water truck to observe any surface deformation.
e6bb1d88-65e6-5be8-abab-e0a909184c0d | note | Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 Rev0 Clause 3.9.4.1
8397a525-ef3d-588a-827b-c8d41c464262 | note | ○ Subgrade Preparation for Structures and Pavement, 3.9.4.3
f6b51cd7-2a85-5224-9cb3-0e954c961081 | note | ○ Compaction and Moisture Content & 3.10 Testing
8271590e-cd7c-5b11-b17c-82b78aa05ea8 | note | Frequency - Proof roll as required
da194a42-bd43-5c38-9a3d-af1c74c76e83 | note | ○ CBR testing frequency not specified
da76b1aa-e6b6-5861-b943-d93d9c10e111 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
0bdffdee-5b50-5e1d-b32e-8bb8eee2433a | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
0d1ce40e-3c0e-5970-8eb0-4ba520e937c3 | note | Records or Comments - NATA Test Results Survey Records, Visual Inspection Record
2091f869-1121-4a3e-8b2e-acfb7dd83460 | signoff | HOLD POINT
546f679e-a78d-4063-9165-b8fc8e5032af | checkpoint | 13 - Structural Fill Construction, Layer Thickness, Placement & Compaction
5fff39cd-38d8-5a44-b2ec-a222e8a45cb7 | note | Responsibility - SV ENG SURV
bf4dff2f-8c17-558b-8a05-5536998dbb90 | note | Method - Test & Survey
59235499-6521-51c1-bad5-8f9bf60ac2ff | note | Conformance Criteria - Depths of layers shall not exceed the capability of the proposed plant and in any case shall not be less than 75mm or exceed 200mm uncompacted.
58088ca2-e972-5195-aab7-d018dece1704 | note | ○ The top 300 mm below subgrade level for foundations shall be compacted to not less than 100% maximum dry density (standard compaction).
5306934d-0900-57d7-a87b-5d40814113d1 | note | Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 Rev0 Clauses 3.9.4.2 Layer Thickness for Structural Fills, 3.9.4.3 Compaction and Moisture Content
92270603-595b-5784-8485-c75c283ca989 | note | Frequency - In-situ Density, Maximum Dry Density(stan dard compaction) & Density Index Minimum testing frequency: 1 test per 2,500m2 or 1 test per 500m3 distributed evenly through the full depth and area, and 2 per work area, and 1 per change of material
a1cad3ee-1320-5005-8695-33a64d4041f0 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
6819444d-130a-5d64-b5d1-d0f504f1e03e | note | Verification from Thiess / Inspector: Inspector (Initial) - W
10140b64-1f64-5031-af9c-6cf00bf089ce | note | Records or Comments - NATA Test Results Survey Records
6ae0ebb8-d9c9-49b2-8723-f5b762ab4c7f | signoff | HOLD POINT
198ca9e3-bb7f-4121-8f7e-103cb13fabeb | checkpoint | 14 - As-built Survey of completed surface
55e91c5a-caf1-5928-bcba-7b9caced341c | note | Responsibility - ENG SURV
bc4c74f9-43f2-5082-a1e9-734ef47843ea | note | Method - Survey
95d1b725-d472-50ad-9799-53941fa595b8 | note | Conformance Criteria - Survey to be completed of the finished surface to confirm construction as per the lines and levels shown on the drawings in accordance with the following tolerances:
980eedf1-d6db-5e68-a16f-b9d1e80f7ba6 | note | Vertical Tolerances
907ba466-558e-5865-a187-2bc60c748127 | note | — Road subgrade & building/structure pads: -25 to +0mm
e37a8010-9c69-54ec-bace-eb54cf650300 | note | — All other earthworks: +/-25mm
8f5eb17a-3ad8-5b4f-a404-1a5103d8b592 | note | Horizontal Tolerances
88d76030-0f67-5de1-92b4-779ced194cdc | note | — Adjacent Structure: As per the structure
1a3c8af4-c18d-5335-bb68-374eb55a2444 | note | — Not adjacent structure (apart from those listed in Section 3.11.1.1 & Section 3.11.1.2 of the spec): -50 to +150mm
f0b4931f-8c55-5063-90ca-c39ecde12bf0 | note | — Substructure concrete to be placed directly against an excavated vertical surface: -10 to +50mm
b2785589-b2cc-590b-844e-228fdd8076c7 | note | — Road width: -0 to +250mm
a76385df-a037-57ec-ac3e-070ad032f63c | note | — Open channel: -0 to +50mm
dd8994d4-a746-5979-8432-d2ed25874e07 | note | — Any point on earthworks surface except any of the above: +/-50mm
3ae9fae2-e9e3-508e-bf42-664d80f040fd | note | Grade Tolerances
41ad11c6-0ccf-5cfb-bc52-5ddcc4037d72 | note | — Roads & Pad/embankment: +/-0.25%
9a07a693-6e3f-5fc3-851b-3101e9572f1e | note | — Open Channel: +/-0.1%
0cc8a653-7af9-5b0f-af07-54c94b9f9b4e | note | — Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 Rev0 Clause 3.11 Construction Tolerance
6c655b66-2e2d-54a3-8f74-9703372e6a2b | note | Frequency - As required
993ae368-cc0d-5a29-8e02-f40663002c50 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
0491a8fd-361a-53fc-b181-09bdc4c9e4d6 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
4c2c0f07-3e11-5e93-8e0e-173ef1150744 | note | Records or Comments - Survey report
80f7ba23-8373-4c53-bd0a-a5f1832ccaf2 | signoff | HOLD POINT
d7649926-801a-455a-ba0c-aa7da6963cdd | section | Post Construction
709384c9-4edc-44f1-81ab-9e7ffb64e940 | checkpoint | 15 - Works completed and updated ITP/ Lot Register/ MDR and close out of GDP
a5f68433-6b38-5430-bf51-863262cac902 | note | Responsibility - ENG
8ed83eca-58e9-5a85-9391-a036ae784e02 | note | Method - Visual
989cb6f1-366b-5c46-8721-021c06874233 | note | Conformance Criteria - ITP closed. Approved MDR
bd7951c6-ba04-5933-846e-9fa8d6763795 | note | Specification Clause - EVAMP001
8e02b7f4-e135-57a9-9090-a22ceb1c993b | note | — EVA-7340-PE-PRM-1
9d38d435-a540-574f-900d-dd6b8c0664c2 | note | — EVA PMP
8078ed9d-f5d3-5a1b-a215-39029d0a96c1 | note | Frequency - As required
ebab9f8f-0797-5a3e-9b3b-0d9483983526 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
db331757-197d-5f39-b246-5a9280775f6c | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
e292418e-3ff6-428c-9fb6-fb29f59f044a | signoff | HOLD POINT
5e96086d-a65c-4ca9-8418-e3de0c5849ff | checklist | Pre-Construction - EVAMP001-THS-QA-ITP-0004 - RCP installation - RevB |  | ITP-0004 - RCP installation - Pre Construction -
748436ab-a5aa-42fd-a690-09d6b15eb167 | section | Pre-Construction
38aaa94c-61db-497a-b825-2fca8937969d | checkpoint | 1 - Drawings supplied most current IFC and transmitted through In Eight
e599a2d5-7785-5bb1-9589-92bcbe50e551 | note | Responsibility - ENG
38da3d47-4dfb-5751-a6d9-62b0e5c9782a | note | Method - Visual
19afb80b-9213-5b11-a7d4-11cb6651093d | note | Conformance Criteria - Reviewed drawing register
d3b93581-4670-5c39-b4a4-02ccabc33b29 | note | Specification Clause - Reviewed drawing register
aceae988-e31d-5459-87a7-60bd50b128ba | note | Frequency - Prior to works
74af9442-6a44-59cf-a014-62e055e4fa1e | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
8998cffc-7301-5cd2-b5b6-b71c8b153154 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
2fe22ebd-9fad-4b9f-abc4-6cbf0edfed10 | signoff | HOLD POINT
bff70920-ef06-4ffd-b784-de80a3266c67 | checkpoint | 2 - Define RCP ID
c32f62eb-6137-5ddb-afc3-e53af1d425c9 | note | Responsibility - ENG
9a16d2a1-31d3-5bfd-9d8e-98d0ac2bc445 | note | Method - Visual
fca6696c-d736-512a-a893-8ccbb5634bf2 | note | Conformance Criteria - Allocate ID for reinforced concrete pipe, define work area
05c2bb36-bb46-5a81-be20-5dc94d1d5ec7 | note | Specification Clause - Lot register. EVAMP001-THS-CV-SPE-0001, EVAMP001-THS-CV-SPE-0002
8eeadb98-cb82-5f78-b01c-0e60515696ed | note | Frequency - Prior to works
e657181a-d9e8-5e16-ad8f-44075817db35 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
38f7550b-0079-529e-bd1b-0a4bcae8dcda | note | Verification from Thiess / Inspector: Inspector (Initial) - W
2bd08c0b-2c07-4612-bfea-e8841eddccb2 | signoff | HOLD POINT
c11c54a3-bbe9-47eb-afed-1451ef3520b3 | checkpoint | 3 - Lot Register/ WBS submitted and approved
fa668e54-339d-57df-9ee3-7352dbd8ee59 | note | Responsibility - ENG
783cbaf3-0114-5ce8-8fff-a909525e6276 | note | Method - Visual
a3252178-1ebb-5ef9-978e-4949ccfc156d | note | Conformance Criteria - Approved WBS
8a6c9355-e467-53ad-997a-a0f87dc34942 | note | Specification Clause - Approved WBS
99ef8d62-a10d-57ad-adbd-4a479fa3db12 | note | Frequency - Prior to works
fe45bf16-8d2d-5472-9c35-d2433d7d2a1a | note | Verification from Thiess / Inspector: THIESS (Initial) - WP
12777b66-3edd-5d76-9a0b-693caf34a317 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
fa801770-53e4-431b-a2de-ad1a65645188 | signoff | WITNESS POINT
5049a0d1-2131-4008-b555-f9a913d779f6 | checkpoint | 4 - Underlying lot & ITP signed off and conforming
1fe71550-9d67-5b3f-a383-e2efb4af6b56 | note | Responsibility - ENG
36e04c59-7d01-57fc-9261-0561331f1667 | note | Method - Visual
ac8885dc-71f3-555f-96b0-a0dab5e7f2bc | note | Conformance Criteria - Subgrade prep ITP Signed
44e9e7a5-ec87-5441-951f-855c2d438bec | note | Specification Clause - Approved QMP. Approved ITP
2e1b43ef-b8a3-53c8-ad25-2897176ac1da | note | Frequency - Prior to works
fd4683a3-09dc-5d0c-a8cf-4aa5995c1717 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
6f5cfab7-42df-54f5-af8e-ce0fff2cebe6 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
333c93c1-5379-4ca2-b1bc-b614fe2d2ec3 | signoff | HOLD POINT
b5069a29-4c0d-4344-8d21-e92ecd132a76 | checkpoint | 5 - Certificate of compliance for RCP Material
4670de72-07f1-524c-aa16-e51fe860d78b | note | Responsibility - ENG
ea503ed2-a9e0-5c6e-a792-7298d71b9473 | note | Method - Written
e08c570e-678e-5fc0-ab47-5a38a9cc0746 | note | Conformance Criteria - Supplier to provide certificates indicating manufacturing processes, materials, thicknesses, classes, and diameters (Only culverts with materials & dimensions complying with the culvert schedule & specification to be used).
569b086a-ad42-5add-8801-51d00c355b32 | note | Specification Clause - EVAMP001- THS-CV-SPE- 0003
10332621-1a80-5020-8c85-cea325f629c9 | note | Frequency - Per Pipe
16b12dca-ef40-5a74-9f23-2a1da0bdee09 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
ca2e7bb4-28ab-5068-be51-e98b2cb14bad | note | Verification from Thiess / Inspector: Inspector (Initial) - W
5d67c4c5-00d4-4b58-a64c-c2e6e5a38458 | signoff | HOLD POINT
129418db-9484-457b-a462-572e4a6a393b | checkpoint | 6 - Inspect reinforced pipe culverts for damage
d3e8c14b-f81e-5523-998a-d262db1fbeb2 | note | Responsibility - ENG/SV
b66e57a1-1cb0-56f4-a318-dfd45823dd92 | note | Method - Visual
3fe90374-2e49-505b-a859-78021c82f60e | note | Conformance Criteria - Prior to installation, Pipes are checked for damages and accepted/rejected and documented on Incoming Goods Inspection form.
5948a650-6e9d-5e8b-b311-b6275d2aaff6 | note | Specification Clause - EVAMP001- THS-CV-SPE- 0003
470420ef-d4af-5d9f-b662-b85c28781a14 | note | Frequency - Per pipe
184e8c55-9b4a-5540-8336-b08532d803b3 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
68cca66c-d436-5a38-bb35-9df1023e8876 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
f6120744-0675-4ca1-a2ca-34b6267d6292 | signoff | HOLD POINT
bd0bdfd5-70ab-430f-b2e6-094f5eee96a8 | checklist | Pre-Construction - EVAMP001-THS-QA-ITP-0009 - Unbound Granular Pavements - Rev0 | itp | ITP-0009 - Unbound Granular Pavements - Pre-Construction -
e63a7cbf-f01e-4bdb-a1f1-d6ab408dadde | section | Pre-Construction
7c820e86-6a3e-45cf-b50e-d75722ede005 | checkpoint | 1 - Drawings supplied most current IFC Retrieved from InEight
79dec94f-4cca-5639-a31e-7ddab332ce60 | note | Responsibility - ENG
cdb1bddd-0525-5d5c-a9a3-f6658d66c912 | note | Method - Visual
a542f2bb-34c0-5365-8f0c-8b4324c36087 | note | Conformance Criteria - Reviewed drawing register
4f49a0db-5964-548a-88f1-d72422ed83cc | note | Specification Clause - Reviewed drawing register
d4b9ad71-a13f-5d16-b989-5b084c039119 | note | Frequency - Prior to works
2ac48876-18cf-5422-97e8-d75b8c61dcb9 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
f3206f80-42f1-51b7-b12e-33cd261432fd | note | Verification from Thiess / Inspector: Inspector (Initial) - W
7483624e-7c77-438b-9b38-3bbc8bab87d9 | signoff | HOLD POINT
1b1e74df-3df8-48a3-bead-e638a9f8f611 | checkpoint | 2 - Management Plans submitted and approved as per PMP
90aee22b-e54b-53c0-a41d-3ba233d94529 | note | Responsibility - ENG
afcd0b5b-ebad-5e0e-916a-cda784e013bd | note | Method - Visual
f3573a20-1767-5d27-9f23-41bd606e9152 | note | Conformance Criteria - Approved Package MP’s
2a5f3286-6565-519b-a56b-de95ed404990 | note | Specification Clause - Approved Package MP’s
0833a091-a71d-50ba-8c5f-8018f6510ca6 | note | Frequency - Prior to works
a69e636d-a162-508b-a492-40c727e1ae4b | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
59cc8944-e7cc-57ab-8265-41ba2bc8030d | note | Verification from Thiess / Inspector: Inspector (Initial) - W
73abe955-7ce6-451b-927d-bb934c7c3a7b | signoff | HOLD POINT
b5d972e1-3906-4f58-b6b9-b8b68de21b1c | checkpoint | 3 - Inspection Test Plan (ITP) submitted and approved
27111b99-9482-5969-a436-35a077d4a9d5 | note | Responsibility - ENG
50a39c09-452c-5db4-8b57-bb2744d5cb8f | note | Method - Visual
89a0a222-bc11-50a8-8251-dbc70e75fbef | note | Conformance Criteria - Approved ITP revision
1cc0bd99-fa93-5f88-9178-1c0a5329ddc3 | note | Specification Clause - Approved ITP revision
b59a966d-c3af-5440-aad0-fea054b551f2 | note | Frequency - Prior to works
6a43ee69-92ba-5212-94a8-28f6ee158178 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
718b5535-9add-548e-acbf-b255164c0deb | note | Verification from Thiess / Inspector: Inspector (Initial) - W
873ee86a-c379-4f79-810b-088f66377a7f | signoff | HOLD POINT
5960b6f6-b67a-4b94-9431-472c45107dca | checkpoint | 4 - Lot Register/ WBS submitted and approved
2affc047-ffa4-5183-aee8-6f60f7872a8c | note | Responsibility - ENG
5a5e634b-eff3-5afc-bfd4-14c77c6d62c2 | note | Method - Visual
9070104c-ef3a-5897-9424-b3ec0a892e32 | note | Conformance Criteria - Approved WBS
dbf13822-e689-5f15-8bc9-b6dddca957d1 | note | Specification Clause - Approved WBS
a088a685-e22f-594b-93bd-ce3facbc933c | note | Frequency - Prior to works
eb2167c8-5311-5aa4-a821-a2a6c3078289 | note | Verification from Thiess / Inspector: THIESS (Initial) - WP
bdcce601-cd2a-5287-b0e7-64b89460250d | note | Verification from Thiess / Inspector: Inspector (Initial) - W
0cba6f9e-f7b3-4554-91ad-4d3741b78f84 | signoff | WITNESS POINT
de46ab0c-f2c4-471b-97fb-8b1b659921c4 | checkpoint | 5 - Pavement material compliance testing
123ccc45-5e6c-5d04-92a9-469a634eab16 | note | Responsibility - ENG
c9760f42-cf93-500b-bbb0-dd6cc12d5bd1 | note | Method - Visual
6dbf50b9-8c25-54f6-8536-12fe8a0d90b1 | note | Conformance Criteria - Test results comply with the details on the drawings or where not specified the specification
4583863b-7926-5520-8e89-d74dd47a7a23 | note | Specification Clause - EVAMP001-THS-CV-SPE-0002 clauses 2.4.1.1, 3.4
2659f571-15c8-5931-93e9-4daf62b85040 | note | Frequency - Prior to works
ae16cc47-1e04-5675-a5f9-dcb298de85b2 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
df4063f3-a838-56e7-bf46-f4e214fcabff | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
bd568289-b79e-49fa-9b54-6e72fd79fe36 | signoff | HOLD POINT
1d52b0d0-d4a6-4168-a425-7572df36911a | checkpoint | 6 - Stockpile locations
ec5ce24a-7a32-5c4f-8c1c-3d1043e56733 | note | Responsibility - ENG
ca291e88-3ff3-59d5-8b54-ef42dae615b2 | note | Method - Visual
33fd589e-7f97-5a50-ac9d-2b5ae8bb0deb | note | Conformance Criteria - Stockpile locations shown on the drawings or approved by client’s rep
aebc76ea-d301-55f1-8c00-ff7434f13e44 | note | Specification Clause - EVAMP001-THS-CV-SPE-0002 clause 3.6
25f8bd0d-da75-5dd4-bdc0-2f5b3fee7cb9 | note | Frequency - Prior to works
91e8ea99-66f7-5d87-8d3b-4656f6fad1bf | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
e88c4e58-7c0b-5bd6-8885-9e3e83c6d3d0 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
ca60277f-bca8-43f9-b2bf-03b5f39bc6e8 | signoff | HOLD POINT
51d9d0d8-5de7-48dd-b621-784f12774368 | checkpoint | 7 - Underlying lot & ITP signed off and conforming
71a8aed0-44c3-5169-98d9-7b2be70f4914 | note | Responsibility - ENG
e3b1aba0-426f-5461-b691-b1ab90861576 | note | Method - Visual
c433f440-dee1-508a-85b6-9474e691d3d7 | note | Conformance Criteria - Subgrade Preparation ITP signed off
6cfe57cc-ca6b-56a9-afa8-1cec57c58023 | note | Specification Clause - Approved QMP
541edb03-69e5-5341-bfa9-49a163b9f68e | note | Frequency - Prior to works
9448e509-08a8-5cc6-bd70-9c12fe1e5eb7 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
236d741a-dd76-5bd4-8857-6bfa8e567173 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
51f0b2eb-72e0-41f0-8820-22b3fe48def2 | signoff | HOLD POINT
1eeccaa9-0fd8-428e-9aad-e7501ba35cbc | checklist | Pre-Construction - EVAMP001-THS-QA-ITP-0011 - Bechtel - Clear and Grubbing - RevA |  | ITP-0011 - Bechtel - Clear and Grubbing - Pre-Construction -
4fbc9f4b-8408-44db-a4b4-766ff6114cc1 | section | Pre-Construction
69170b47-5149-4fe9-b2d0-cf37d7e77491 | checkpoint | 1 - Drawings supplied most current IFC
11c1fbf4-aa41-557a-b3f7-14c63799bda1 | note | Responsibility - ENG
1eeb7f02-8478-54c7-af1f-ef98b5c302c0 | note | Method - Visual
0bc89fd6-fc6d-57f3-a88a-2364beb3d6a8 | note | Conformance Criteria - Reviewed drawing register
ee3ae01c-d4a0-5580-9f7c-b9c978958ca8 | note | Specification Clause - Reviewed drawing register
c28dbd5e-4170-564a-8b94-06c81aa611b9 | note | Frequency - Prior to works
a260dbc4-1380-5882-98cd-fc74c224264a | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
ef108511-2b2f-500b-a2c6-9ed1ebc878f8 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
f7d85e8e-e004-4744-adec-aa78a95b8dd7 | signoff | HOLD POINT
e49e1d52-f864-4eff-8669-0bc65bc565de | checkpoint | 2 - Management Plans submitted and approved as per PMP
21ee2620-4601-507b-a851-74f77d88466f | note | Responsibility - ENG
928b1145-1667-5a07-b4b1-606c7294f697 | note | Method - Visual
13b03e4c-edf1-548d-85ca-947a0eceda06 | note | Conformance Criteria - Approved Package MP’s
6217aa52-f5f1-556f-9c7d-a77d6cea478d | note | Specification Clause - Approved Package MP’s
9dcafea6-46ae-55e7-9347-a3c0aef38387 | note | Frequency - Prior to works
76e70357-b4c9-5400-b733-9f81782022a8 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
1c712dcf-f897-5229-af02-7e3a820595b5 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
abd60bc4-46b4-4071-9e26-05bae3a3a6b4 | signoff | HOLD POINT
2aed848c-00f5-4544-85f5-0fd9f68ec603 | checkpoint | 3 - Inspection Test Plan (ITP) submitted and approved
944d416d-2167-50c1-81fc-4f505e705592 | note | Responsibility - ENG
7097875e-baf5-524c-b68e-3e31be156427 | note | Method - Visual
b1b455cb-c48f-5e75-b115-5595bcdb51f6 | note | Conformance Criteria - Approved ITP revision
5c7f6219-f4fb-5b3e-a4ff-5a63fb839684 | note | Specification Clause - Approved ITP revision
f06ba0f3-65d9-5742-b971-796a9a1b1578 | note | Frequency - Prior to works
9412b38e-fd62-5ff7-9663-5e053c80a5fe | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
11a41ae0-5e28-56ba-bc16-fcdbb977d2af | note | Verification from Thiess / Inspector: Inspector (Initial) - W
86623a16-c35d-4741-aaf7-1a3158769a06 | signoff | HOLD POINT
b8e73fbb-eb28-41f0-9010-80fe4d344ae5 | checkpoint | 4 - Lot Register/ WBS submitted and approved
8cce20ab-f36f-511e-aad4-0a856c1a4bfd | note | Responsibility - ENG
27f7f453-48db-51bb-933a-971a415a5663 | note | Method - Visual
1a8e164a-f87c-5186-b4a4-f0138473b418 | note | Conformance Criteria - Approved WBS
86fe6478-ce71-5dba-bf9b-6307a1252b95 | note | Specification Clause - Approved WBS
b0cfd592-a659-52e6-8bd4-0b341af9acc1 | note | Frequency - Prior to works
371d5078-4cfd-54ea-b857-82f94c0c4b0f | note | Verification from Thiess / Inspector: THIESS (Initial) - WP
959430be-2651-51f7-8671-ae9af864f4e7 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
859a25a7-02b4-4d87-b4e9-8541a0c9fd75 | signoff | WITNESS POINT
6f436440-3275-4157-a53d-7e7c29f15da8 | checkpoint | 5 - Erosion and sediment control plan approved
aeca647e-ae9d-5389-955a-ee22f0ecc0e0 | note | Responsibility - ENV
b76b841a-c4ad-5a0e-92fa-6367fed30c9b | note | Method - Visual
028599c6-a08f-5199-a87f-e7ee92e384a9 | note | Conformance Criteria - Approved erosion and sediment control plan
be20eabe-ee2b-528f-a8b5-b1f2bd2b6fa8 | note | Specification Clause - EVAMP001-EVA-7340-PE-PRM-0001
74da7be9-d0ea-5c1f-b4b3-2eb624407b11 | note | Frequency - Prior to works
622f2a6b-34ef-505a-b5e4-c3fdb579e8b2 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
d55a02fc-155d-52ed-a78f-c3fc7a837112 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
802e6725-63f6-4d69-a04b-bc1d1efa63ac | signoff | HOLD POINT
dc844812-0c0b-48d6-9535-377ee00fdf86 | checkpoint | 6 - Check existing services and dial before you dig
6fe84171-2a32-5712-8412-7136c3e49b82 | note | Responsibility - ENG
abff9f6a-dea9-54b5-a31f-e935758304c5 | note | Method - Visual
f3fa1919-d494-5af3-bbf9-ca0f89a6b6e8 | note | Conformance Criteria - DBYD certificate and EP
a46924b2-15e3-5c69-9fa9-568b99961dec | textbox | Specification Clause - Excavation Permit (EP) Doc no.
075ce3d8-2fc1-5c9d-ba9d-a1aff0bb373a | note | Frequency - Prior to works
1cb14f31-9a6b-5816-8c8c-30edc4d96f58 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
7fa7acf7-050f-5f0e-a5c3-661e48feea32 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
aaa6af30-a610-4a04-8ff7-2c1c98703cdc | signoff | HOLD POINT
b66c0fda-6b70-4b90-9c7a-81ffe2a38ed8 | checkpoint | 7 - Ground Disturbance Procedure (GDP) obtained
5859d1c8-9451-52f4-8583-e95f12643dba | note | Responsibility - ENG
da17a58c-71b2-5757-ad3d-6cdfe557ba63 | note | Method - Visual
fa8c79ad-b4d2-52a6-a407-ac728040f82e | note | Conformance Criteria - GDP permit with work packs
6e5c2a04-4f5f-5a06-8850-12aaa9529e9e | note | Specification Clause - EVAMP001-EVA-7340-PE-PRM-0001
4849fa8a-76eb-55c4-b6cc-15b6dee55bca | note | Frequency - Prior to works
096eb475-734d-5bfd-a6dd-c7681ce6489b | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
f0392a97-73a9-50a7-9b90-5c5c60ec7b48 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
b8298332-62f1-47fa-b689-9618fd18fb8d | signoff | HOLD POINT
1289223a-a235-471e-8773-eb79ca6a8d53 | checkpoint | 8 - Area of works pegged and clearly defined to GDP. Pre- strip area survey pick-up
b7f2fc75-df31-5193-8adb-89ede6ff7787 | note | Responsibility - SURV
8fd72a58-25dc-5409-8c73-a166dce9fd4f | note | Method - Visual
4caedc21-9dc1-5d43-872b-8124949f04fc | note | Conformance Criteria - Clearing pegs installed at nominal intervals to ensure no over-clearing
42b849c2-93d6-5e12-92a0-0bfced1a3602 | note | Specification Clause - EVAMP001-EVA-7340-PE-PRM-0001 to ensure no over-clearing
1eca5747-75d2-55e0-aaf4-11c4cdf4ad56 | note | Frequency - Prior to works
c5d31586-6b9b-5934-8a94-c20b86e6632c | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
468c6577-6938-541e-a7a7-a2713968d933 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
9ec80b66-bab7-447a-8488-85518cf104b2 | signoff | HOLD POINT
c5cdf66e-7f5e-41ae-9d24-83c59a225fdb | checkpoint | 9 - Area of works been pre-cleared for Fauna/ Flora
6d639e38-2c53-5923-a6e1-4a627c01d9d4 | note | Responsibility - ENV
fe539011-169d-5e46-b0ce-9cf4c4900ec2 | note | Method - Visual
a83a1e32-2ba9-5b74-8fb0-3a6a1c2ff0e6 | note | Conformance Criteria - All areas to be pre-cleared prior to clearing operations.
a7542a38-b49d-54a9-ab10-7f434d22f626 | note | Specification Clause - EVAMP001-EVA- EN-PLA-0001
fee6c5bb-c2b0-52ac-8d0f-0ad876f5c588 | note | Frequency - Prior to works
adf9555f-1876-509a-8832-51afe1abf325 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
769a0438-7212-5367-b3cf-62ffa87651ce | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
73e7566b-edfd-405c-bc15-9691e7cf4b34 | signoff | HOLD POINT
1d2cd06a-05e9-4241-aa1a-4adb9761dd69 | checkpoint | 10 - Survey of pegs to confirm correct setting out
2c2e1c61-3656-5826-9fe5-19df48caa0d1 | note | Responsibility - ENV
f271d5ac-e43b-5b4c-b634-77d1c25f3ceb | note | Method - Visual
1dd371cd-7477-506b-9ec2-5302b5dd8e28 | note | Conformance Criteria - Pegs to be surveyed and sent back to the engineer. This is then to be confirmed by the environmental team
f6224d1d-921c-51f9-947b-ca38ca616364 | note | Specification Clause - EVAMP001-EVA- EN-PLA-0001
e8b3367b-e751-53bd-be13-e9a1cfca8cad | note | Frequency - Prior to clearing
1114a62c-e737-5c83-a113-0bfb2bee758f | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
a86b977f-890a-568d-825b-7adaa1bfcf5a | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
7ac40683-8c47-4c4e-aa13-01c9598179c4 | signoff | HOLD POINT
16298aec-2e3d-43d8-9833-8bb56aff1bd3 | checklist | Pre-Construction - EVAMP001-THS-QA-ITP-0012 - Bechtel - Topsoil Stripping - RevA |  | ITP-0012 - Bechtel - Topsoil Stripping - Pre-Construction -
4d594b1b-cdd6-4ca0-8549-82a0914dfaad | section | Pre-Construction
35655e2e-7cfe-46fb-ad18-479fe9f4dc10 | checkpoint | 1 - Drawings supplied most current IFC
8c1056bd-b391-50ae-824d-fd126880cac0 | note | Responsibility - ENG
59a4d5ba-e0a7-5379-85ef-d422709dd4e2 | note | Method - Visual
668cb47c-7c03-5791-8506-f9081ce8aebc | note | Conformance Criteria - Reviewed drawing register
77613a8a-6749-5c46-80b2-89c86ae5adc2 | note | Specification Clause - Reviewed drawing register
1346c8c4-daef-5e39-a394-9ee998ce6c9a | note | Frequency - Prior to works
a6e9a3f9-0a51-5475-9d15-531848667ceb | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
00999668-32d1-5ec5-81d9-45c893ab4060 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
212088b3-2b07-4741-af8e-4f6aca04070b | signoff | HOLD POINT
91ff7593-bd1b-46d7-af14-605df18ec842 | checkpoint | 2 - Management Plans submitted and approved as per PMP
ae97b1e5-5634-5c25-b4eb-fc670b8f22d5 | note | Responsibility - ENG
3e0ea46d-0f0e-5160-a132-f1c36b6af80f | note | Method - Visual
d70c6f26-8aeb-51ee-9a3f-a9bf0d301df5 | note | Conformance Criteria - Approved Package MP’s
e0fe7195-2db9-5071-a5bf-13ddb8c265c7 | note | Specification Clause - Approved Package MP’s
11f29713-68d8-573a-83bd-d5839f31a2f9 | note | Frequency - Prior to works
4a2e88b7-a6d9-50ca-a8a7-32afccee2741 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
69d9d4be-8789-5618-96dd-f53f531d8f67 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
39fa397f-c9b8-42bc-8cfa-e2cdaa6271a4 | signoff | HOLD POINT
f5923a85-659f-4486-9422-b6792adef757 | checkpoint | 3 - Inspection Test Plan (ITP) submitted and approved
5be58b96-2a08-58ba-bc1b-f659c77183d8 | note | Responsibility - ENG
e11af761-30b8-56b4-a3a5-b46c54a5fbb6 | note | Method - Visual
4be37512-22fb-5440-9625-fa9503788017 | note | Conformance Criteria - Approved ITP revision
4da8cf4b-399b-52f3-9be2-2b42705f86e0 | note | Specification Clause - Approved ITP revision
61907fbc-08ad-5f39-a295-fa48e268c7ad | note | Frequency - Prior to works
60c02263-1116-5447-a76d-8959bef79dc6 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
a63c9a45-32a6-5fff-a53b-276ba649ad73 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
7800bbc4-2b68-41f3-b2d6-cef6e1828dbb | signoff | HOLD POINT
2f9b9c48-e981-4475-b400-b048dd185d44 | checkpoint | 4 - Lot Register/ WBS submitted and approved
07719357-02cd-5784-ac14-83d2bedb4ef6 | note | Responsibility - ENG
9cdd33b0-9aee-5075-9af0-84d5dc8a425c | note | Method - Visual
f7bb7712-cb02-542b-bf8e-52385c9bced7 | note | Conformance Criteria - Approved WBS
aa5c692e-b3e6-53f4-978e-52cc3e047677 | note | Specification Clause - Approved WBS
33833046-471b-5e3a-a9a6-1f58ec6a272d | note | Frequency - Prior to works
276365c8-5d86-57d4-ab04-de4d02cff161 | note | Verification from Thiess / Inspector: THIESS (Initial) - WP
7991706e-9285-5d2a-8240-41c301e341c2 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
2223df32-3149-48cf-9c4b-b47885524908 | signoff | WITNESS POINT
3d006153-d2f3-4292-b3b1-d881897df8e2 | checkpoint | 5 - Check existing services and dial before you dig
b8d1f7c4-5c4f-5b4b-9137-7ae71744ffcb | note | Responsibility - ENG
498c51bf-bfb5-5a03-a52f-0a8950d87ed5 | note | Method - Visual
03ca518d-9bd5-53ad-824f-bf8fa645b4bd | note | Conformance Criteria - DBYD plan
8dd95077-c516-5267-85d9-765ac4e46430 | note | Specification Clause - EVAMP001-EVA- 7340-PE-PRM-0001
b9808a12-9b00-5a84-b99f-7cfc0fcbfcd7 | note | Frequency - Prior to works
3dbe1155-6ca2-53ff-a668-0036f6879a8d | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
cad1debe-a76c-5d2a-a2f5-4ca1acee63a4 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
85aa97f8-2ee1-4b34-bca7-abcf17a913f2 | signoff | HOLD POINT
808a6f11-b91c-4f88-8068-b68603512ab6 | checkpoint | 6 - Area of works pegged and clearly defined to GDP. Pre-strip area survey pick-up
4607e8ed-d257-5820-8d01-10d218ac737c | note | Responsibility - ENG
ce3efa9f-da1d-5a5a-b5cd-a5af173e25f9 | note | Method - Visual
b851bd1b-cd75-59ca-89c3-2a7050a7681c | note | Conformance Criteria - Boundary pegs installed at nominal intervals to ensure no over- stripping
e7a1c3af-50b4-5147-b124-2253ad47f5ca | note | Specification Clause - EVAMP001-EVA- 7340-PE-PRM-0001
00acb9e3-8e83-5cc6-bc5a-e9f869c34060 | note | Frequency - Prior to works
22d3eb45-cdb1-5243-9715-99fa6b56cd3b | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
4efa0b43-eb5a-5960-b97f-b881c2be1f1e | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
a36c9a5d-b932-4ce7-afd5-b8b52331d256 | signoff | HOLD POINT
fb7a2d7f-ada1-44ab-8ff6-f1988c6e7a48 | checklist | Pre-Construction - EVAMP001-THS-QA-ITP-0013 - Bechtel - Subgrade - RevA |  | ITP-0013 - Bechtel - Subgrade - Pre Construction -
7de14ed9-a79a-4cae-b5d7-f8ef676313df | section | Pre-Construction
2f53def5-d0f9-4271-9230-12a1b68d9e7a | checkpoint | 1 - Drawings supplied most current IFC Retrieved from InEight
c9244b41-abf8-5bb7-8abb-87a9e7fd09f6 | note | Responsibility - ENG
72b4459d-6c83-5c20-94a1-bfabae628162 | note | Method - Visual
c41450b0-908b-5ab8-8dc1-0421b2ef5252 | note | Conformance Criteria - Reviewed drawing register
629e643c-fece-5412-808b-2d1201c1244d | note | Specification Clause - Reviewed drawing register
10d99576-fc50-5a10-a095-c0cc2bc53040 | note | Frequency - Prior to works
205144cd-847a-5a78-a9d4-c05eaab4f6a5 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
76336f82-f675-543a-8302-c5eca282d390 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
ed5e681c-ff70-4c55-b5d9-c873ca6729de | signoff | HOLD POINT
61b54a81-a1e4-4162-a22c-7c181f499c09 | checkpoint | 2 - Management Plans submitted and approved as per PMP
e7c2846a-b548-5838-8588-391d7f6fa0a9 | note | Responsibility - ENG
e371932f-28eb-5765-9083-782bcddeb724 | note | Method - Visual
565e1a36-6d7a-5b7a-bb75-cf0e8a56b2bd | note | Conformance Criteria - Approved Package MP’s
ec8e7b9f-2c60-5633-ab3b-2432383e7420 | note | Specification Clause - Approved Package MP’s
0f06c190-37a8-5407-b52e-1a81a5edf6e0 | note | Frequency - Prior to works
08141323-218e-520c-8831-66ff4dcb298a | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
340297cb-237f-5f85-aa40-3cee54950e8a | note | Verification from Thiess / Inspector: Inspector (Initial) - W
a5e0ff98-6305-426b-ac27-4262b150f0b8 | signoff | HOLD POINT
30e80d33-52a6-46f2-930c-22b0bb8e6a19 | checkpoint | 3 - Inspection Test Plan (ITP) submitted and approved
74416919-f498-5586-9228-507588c11e2c | note | Responsibility - ENG
1e3ea4eb-334b-5122-9540-3c444a2cef35 | note | Method - Visual
90f65b7b-3e8b-5c77-be35-9fc2a2e5c027 | note | Conformance Criteria - Approved ITP revision
115d9e06-f5c9-55c7-92a7-b741dfed3890 | note | Specification Clause - Approved ITP revision
b63543b9-f689-51ff-8797-c3b373df1840 | note | Frequency - Prior to works
8db665e3-fced-5b20-8086-6648a189584a | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
cc03abf2-bb73-593f-8614-585505d0d465 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
825ceff8-560b-4d03-bb9e-da2091cb34f4 | signoff | HOLD POINT
9d76f339-80d0-4471-845a-c4edd73fc1fc | checkpoint | 4 - Lot Register/ WBS submitted and approved
85f2bd07-4ff9-5956-a43a-e377f990b29e | note | Responsibility - ENG
c1df7e39-85d3-5fd4-89c6-700def9c1705 | note | Method - Visual
d9f0814c-10d3-5f30-8a9b-456254d8728c | note | Conformance Criteria - Approved WBS
7b7fb3de-56ae-52f3-bf0e-7f897a5c9439 | note | Specification Clause - Approved WBS
139bc34e-037a-58dd-ac0b-c4928740af8d | note | Frequency - Prior to works
48d96817-9d8d-52e4-af3c-813447380f55 | note | Verification from Thiess / Inspector: THIESS (Initial) - W
598dd396-30e7-5114-8cb6-e02f0fd3a8f9 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
79772e40-a184-43e3-8b4e-96bc55b30ecd | signoff | WITNESS POINT
69bcfad9-1982-4856-a4ee-d3e8c0d86f3d | checkpoint | 5 - Check existing services and dial before you dig
485b8fc7-0e6e-5ea1-a613-7618d80bd394 | note | Responsibility - ENV/ENG
0d74e05c-8256-545c-b273-2066ee95d1aa | note | Method - Visual
53dfbce2-0612-5a16-a80c-8bed34fdb2ff | note | Conformance Criteria - Approved erosion and sediment control plan
8ddfb5a0-edf9-5303-b634-b7fd6b590b99 | note | Specification Clause - EVAMP001-EVA- EN-PLA-0001
4c96a71c-735e-55b2-b1ef-847973ea3424 | note | Frequency - Prior to works
0224565a-8bab-5fea-b560-0bc09fa6bbb4 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
aa5204ec-0d3f-5530-ac43-8c261405c554 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
c4832cae-3802-4389-8bad-828c9e679644 | signoff | HOLD POINT
6477c8b8-0d8c-4647-860e-eadf11a4ea4d | checkpoint | 6 - Underlying lot & ITP signed off and conforming
3ea69d99-be2f-5af4-9249-26bbc137ffbb | note | Responsibility - ENG
faf0f9e0-ae3a-563d-8d42-21ec6280d967 | note | Method - Visual
a79294a7-595f-530f-a0c2-c258fabe0726 | note | Conformance Criteria - Topsoil stripping ITP signed off
5681132c-f917-5d77-bf2d-6477c7db9c3c | note | Specification Clause - Approved QMP
f6ce4572-20b8-5b59-b9a3-f4671cd0baa2 | note | Frequency - Prior to works
c0cc3741-a6bb-5f4e-b7f0-841979fae889 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
fe466913-a210-5637-b3bc-4f5baba4b1de | note | Verification from Thiess / Inspector: Inspector (Initial) - W
b740843e-a87b-4742-900b-76c0d8688ab7 | signoff | HOLD POINT
4b8e63c3-0278-4630-b09b-c0b90991c382 | checklist | Pre-Construction - EVAMP001-THS-QA-ITP-0015 - Bechtel - Embankment Construction - RevA |  | ITP-0015 - Bechtel - Embankment Construction - Pre Construction -
3a87fb98-b826-4c8a-9eae-229405aa565f | section | Pre-Construction
a3ee5fa9-b905-4f0c-b605-889c8dc76943 | checkpoint | 1 - Drawings supplied most current IFC
f6b5b4a4-8fa5-52b4-83ff-e5db6dfd034b | note | Responsibility - ENG
e8008609-96e1-5030-8712-82003f104f9e | note | Method - Visual
f28e0dd5-1bf9-5ee6-81ea-c493f7469f26 | note | Conformance Criteria - Reviewed drawing register
28a806c6-46af-507d-a2d6-b0dd3e948bf1 | note | Specification Clause - Reviewed drawing register
83144541-c23b-5081-a019-78c5885cfc3b | note | Frequency - Prior to works
e43e88d6-edf2-53e1-932a-8ce63f9ca810 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
689d84d7-dac4-57d7-b36f-baacfdc4c904 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
af890221-4558-4362-af28-e3a4e7e0b4b1 | signoff | HOLD POINT
e98cdacc-6cda-4ee5-a939-df5c4fef955c | checkpoint | 2 - Define Lot dimensions
b806d77e-d3bb-545d-8c50-02f9ac14899a | note | Responsibility - ENG
1649887c-2ebe-5da5-8294-e3a489d6e847 | note | Method - Visual
1c19f462-96a0-547d-846b-c7fc024b476c | note | Conformance Criteria - Allocate Lot No to ITP and update Lot register
a4e26d47-d6d8-560a-92c5-d9a352a6e488 | note | Specification Clause - Lot register. EVAMP001-THS-CV-SPE-0001, EVAMP001-THS-CV-SPE-0002
e486b966-1b68-5043-81fd-9e5c794850c7 | note | Frequency - Prior to works
e08ba403-3b41-5e75-b5bd-30c261f10691 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
de06ffc0-2d02-535a-bf17-03cdbb4b07f6 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
e1913c48-66df-4256-af9f-5e82bc23dc90 | signoff | HOLD POINT
a3862860-a5b2-4180-9c0f-7a1bda022587 | checkpoint | 3 - Lot Register/ WBS submitted and approved
a558bd68-8110-5a7a-a809-d400e47f29a3 | note | Responsibility - ENG
b26394b2-f0b2-5f9d-b795-4ca560f3acdd | note | Method - Visual
e3b0bd4c-8d34-5cbd-a11e-bf5a8fed1063 | note | Conformance Criteria - Approved WBS
79f39d42-4144-56dd-9876-87906e7fb661 | note | Specification Clause - Approved WBS
a3184db1-747e-52e4-9a80-7de8f30d0594 | note | Frequency - Prior to works
b35b2b50-947e-5a61-8c7f-cee7e4393fb7 | note | Verification from Thiess / Inspector: THIESS (Initial) - WP
0fd4a164-60c7-5516-8c24-a950c99ed53f | note | Verification from Thiess / Inspector: Inspector (Initial) - W
14fbdbc5-04be-47fb-ab36-d5264b9a953d | signoff | WITNESS POINT
9c1fc623-fe6c-42d1-82b4-a216d3dd7ceb | checkpoint | 4 - Underlying lot & ITP signed off and conforming
1094705b-b595-5d1f-bd01-4375719fbdee | note | Responsibility - ENG
06e87dbc-c67f-50c7-821a-2b24caf5a3de | note | Method - Visual
8dca90a1-6596-5922-a5c8-d3ac7eecf89e | note | Conformance Criteria - Topsoil stripping ITP signed off
ca78a685-30d7-5edc-8a5b-97d1341c33d8 | note | Specification Clause - Approved QMP. Approved ITP
c58f47bd-9951-527d-864d-546551c1693d | note | Frequency - Prior to works
283b6b4e-f822-58f0-8409-c9c1fb203ac0 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
0a8b47f9-6493-5390-ab12-8815218ea024 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
0915ce48-e9b2-444f-8cf3-319612b086c9 | signoff | HOLD POINT
3aa92da8-33cf-4aa7-ae9a-445014f17036 | checklist | Ω (ALTERNATE) ITP-0003 Subgrade/Foundation Preparation (v0, different IDs) | itp | DO NOT USE - DEPRECATED
3888cb15-c6e9-4774-94f4-ef0136a8d2b8 | section | Subgrade/Foundation Preparation
ac475546-f2ce-4c02-a316-d1bc173edfa8 | checkpoint | SP.1.1 - Underlying lot & ITP signed off and conforming
0ba38702-7e4a-5305-999e-9d0c380b72b1 | note | Responsibility - ENG
cd2dc35a-9502-5741-8b68-f7ea4a27f70c | note | Test Method - Visual
cdae2c66-de7c-5ca1-aaa5-1dcaadf88613 | note | Conformance Criteria - Topsoil ITP closed out
39fb73af-ee7e-5cfb-a384-6dabf3434961 | note | Frequency - Prior to Works
8ee4a552-2995-58d0-9e48-752e910a3518 | note | Link to ITP - TS1.6
2897bed4-d43c-43af-aa95-e7d21d62accd | checkpoint | SP.1.2 - Embankment fill material
6698839b-9391-5658-8be4-54b8641f1d75 | note | Responsibility - ENG
afc74dae-bdf5-5e03-929d-edad53d7c4be | note | Test Method - Visual
e98679c2-b70a-536b-9a9c-bef3a3d5405e | note | Conformance Criteria - Ensure CBR10 subgrade replacement materials have been approved for use and within specification
6171a00d-a560-5761-b6c3-27e3f1536543 | note | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage)
cd5ca6cd-ecd1-5805-9164-3664d4d56063 | note | Link to ITP - PC1.11
8ebc67a8-3f8e-5cfc-aa2c-2ab9989333fa | note | Thiess HP/WP Check - HP
c22e0b29-ee08-5f77-a31c-95c7a96e983a | note | Inspector HP/WP Sign Off - WP
e6f51fb7-6c5b-4f3e-b073-2d76ec83af4c | signoff | WITNESS POINT
f18384a0-36b1-404a-ba16-b643c5ba2214 | checkpoint | SP.1.3 - Survey Set out
4b25c72b-e94d-529d-aa6b-3835cde661fb | note | Responsibility - Surv
6db7605f-6648-5850-b3e9-c41e7f2cfe70 | note | Test Method - Field
d0b3b03b-7fa3-511c-b9b7-9c1db665c392 | note | Conformance Criteria - Areas of work to be set out by surveyor and/or models in plant
662d8646-ee30-5fd1-9ce4-7ccc7f1318a9 | note | Frequency - As required
57f8ebaa-8d19-5e99-8c43-2d16b8aff760 | note | Thiess HP/WP Check - HP
45364d23-92d3-5007-895d-5930c2185259 | note | Inspector HP/WP Sign Off - WP
4d57dd0c-68ce-48ab-bd54-2cee86b3fca9 | signoff | WITNESS POINT
dbba825e-74ac-4f55-a21f-fc1ed370c529 | checkpoint | SP.1.4 - Removal and replacement of unsuitable material
747e0dbf-fcba-5695-b1a3-01b9361dabf7 | note | Responsibility - SUP
30352755-f0c8-5be8-bb2c-b08aec36a9b4 | note | Test Method - Field
21dbc2ce-af3d-5371-a91b-5b924c2fdfbc | note | Conformance Criteria - Determination of unsuitable material by the Level 1 GITA or Inspector (Sedgman) is required prior to the removal of any unsuitable material. Unsuitable material criteria is in the specification.
e4d39c20-3fe5-5de7-bc69-b4f7f854c5fd | note | Frequency - As required
c84d290d-5958-537c-9c8e-48a52d608cc3 | note | Thiess HP/WP Check - HP
47ac2868-dfa4-5963-aa63-9fdf4d28309a | note | Inspector HP/WP Sign Off - HP
abc7c254-a1c2-4d1e-a2cc-9dda06113411 | signoff | HOLD POINT
bf2a450e-c73d-4e58-b6c5-f8d0ad38ec50 | checkpoint | SP.1.5 - Proof rolling and soft spots
6ac50545-6961-5f6e-9358-6a0ee1fb360f | note | Responsibility - SUP
c709b948-1ca6-56d0-9cf6-aefd7aedbedc | note | Test Method - Field
c378f6ef-6f7b-516a-8e9d-004032c7b05c | note | Conformance Criteria - Proof-roll subgrade/foundation surface prior to placement of embankment fill. Proof roll under a standard 8 tonne axle load or 10,000L water cart or heavy self propellled smooth drum roller dynapac 620D or equivalent to confirm that, in the Inspector (Sedgman) s opinion, deflections are negligible. Any soft spots identified shall be scarified, aerated and recompacted with moisture near optimum.
3a550ce8-816b-5397-a561-01745103d955 | note | Frequency - As required
ffbdbde8-4eed-59a2-a503-187d9143d7f6 | note | Thiess HP/WP Check - HP
118fb4dc-b6f4-5712-8aa5-f3abc584a348 | note | Inspector HP/WP Sign Off - HP
6e4cdf2a-ea9e-4e8c-aef7-9e25439a1400 | signoff | HOLD POINT
4fd12e0e-f712-429a-8540-2f342f7bb820 | checkpoint | SP.1.6 - Subgrade/Foundation preparation
53ba4411-a5de-531c-961b-c446ae05e42d | note | Responsibility - SUP
d0ce048c-197d-5912-80e4-60df6073967c | note | Test Method - Field
36fa4a64-d46f-5f5c-ba5f-c800dda0a565 | note | Conformance Criteria - Lightly tyne the subgrade/foundation immediately prior to placing embankment fill.
aa96d8ee-81e4-5cf0-9311-27c35702a144 | note | ○ All material exposed in cuttings at subgrade level minimum CBR 3 or DCP 150kpa. If CBR2: Remove & replace with CBR10 select fill 150mm deep. If CBR1: Remove & replace with CBR10 select fill 250mm deep.
0d516928-6b59-57fe-b7ca-1ee4b1414d64 | note | Frequency - As required
ed5e1566-2280-51c3-be8e-1eb5461ee755 | note | Thiess HP/WP Check - HP
0e74b08d-944f-5d4f-a1a0-598735ce57d8 | note | Inspector HP/WP Sign Off - HP
c760cec8-8ceb-4a0d-a985-5324d40c2be8 | signoff | HOLD POINT
187efc59-29ad-49ed-8390-8b60becf1967 | checkpoint | SP.1.7 - Trim subgrade in cuttings
b3913e7c-bebc-5d12-9a25-bb41ac3c832f | note | Responsibility - SUP / SURV
ae93ba34-1d60-5116-972f-c6a9676fd814 | note | Test Method - Field
a76edf78-b419-5b0e-8f24-353676836a66 | note | Conformance Criteria - Trim all subgrade to the lines and levels shown on the drawings in accordance with the following tolerances: Top of bulk earthworks +/-50mm; Road subgrades & under buildings & structures +0mm to -25mm.
549c5914-07e3-55e7-bad0-0bbf1fce3fab | note | Frequency - As required
ffcc823b-be30-5129-a036-a226605a90d8 | note | Thiess HP/WP Check - HP
f45a1c01-4b58-5b13-93cd-bdb9bab52ee2 | note | Inspector HP/WP Sign Off - HP
f23b4a57-60f2-4a1f-bbca-c06f05da3796 | signoff | HOLD POINT
71594be2-04a9-4642-8c27-46fc02041e66 | checkpoint | SP.1.8 - Surface level check and survey pick-up
ae3e3dc0-bbb7-5161-ab48-8f3e93da7c89 | note | Responsibility - SURV
0233e3da-d7b0-57cb-a28f-791670b10318 | note | Test Method - Survey / Field Test
181a65b6-888f-5718-abc5-1c5ea421f1f5 | note | Conformance Criteria - Surface level picked up as per Table 10 C15 (DXF file format, volume calculated and filr saved in Construction Team Sharepoint and detailed in register
8205adaf-59f9-5e9c-94e0-2407ce8f2386 | note | Frequency - As required
816da858-ab98-54c1-b51c-3cfa04e1791f | note | Thiess HP/WP Check - HP
8fd83ed0-b72c-5af0-9b4a-dc40044dbcee | note | Inspector HP/WP Sign Off - HP
4bcc759d-350a-4250-8f6b-244794b056e2 | signoff | HOLD POINT
cf8c9bf4-266f-4abf-8026-2827cb980a71 | checkpoint | SP.1.9 - QA close out
f480ed2e-dad9-5d6f-bd96-060b4d89131c | note | Responsibility - ENG
1a40051b-4408-5dcb-b87a-220c77689e1a | note | Test Method - Visual
f5308beb-802e-5f5c-af91-fc47fbd956cb | note | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR.
5dd34aff-46bd-5dab-b2af-b6da8a1c725f | note | Frequency - As required
348d3807-5f57-5b32-ba96-d3d360a60099 | note | Thiess HP/WP Check - HP
b9692b12-b245-507c-a77b-b367d15bbc3d | note | Inspector HP/WP Sign Off - HP
fe791962-27f7-473b-bde7-91e7f40b4125 | signoff | HOLD POINT
625146e1-7fb0-4141-87ad-3630a8a9885d | checklist | Ω (DEPRECATED) ITP-0000 Pre-construction (v0) | itp | DO NOT USE - DEPRECATED
afab5920-763b-41e2-b04f-389f3d863f0f | section | Pre-construction
d5f2de5b-1844-4b8b-9494-00345366394e | checkpoint | PC1.1 - Construction Management Plan
9cb08030-a1b4-58b4-aa30-19759969d214 | note | Responsibility - ENG
d97fd768-106c-5aed-8a49-28134e3d84bd | note | Test Method - Visual
40d7ec2a-577f-590f-8a34-904cf05aeb60 | note | Conformance Criteria - Approved Construction Management Plan saved in Construction Team Sharepoint and detailed in register
b132816d-9c22-58a5-8505-653a25659938 | note | Frequency - Prior to works
8d264537-c84a-59ee-8506-57055b051946 | note | Thiess HP/WP Check - HP
9c63b04d-3123-5f87-a40d-243882371884 | note | Inspector HP/WP Sign Off - WP
24a3466b-fbf5-43de-b7ca-11b4744cff97 | signoff | WITNESS POINT
010e0c6d-951b-4ef9-941a-9ea0f881fde8 | checklist | Ω (DEPRECATED) ITP-0004 RCP Installation (v0) | itp | DO NOT USE - DEPRECATED
bcd810f0-bd1c-493c-a0f7-4aa16e546710 | section | 1.0 Pre-Construction
1b3a1513-b678-4b99-b6d3-43cc70619a41 | checkpoint | RCP1.1 - Drawings supplied most current IFC
a4aacebf-171b-5589-81ef-e7db3359c74e | note | Responsibility - ENG
df665c3b-ed53-581f-a541-00db45ac308e | note | Test Method - Visual
8a2663ba-3a19-5fbd-a510-b4447a77b6af | note | Conformance Criteria - Reviewed drawing register
e1fc5ac9-094e-5c3f-b9b8-6a1cad559c19 | note | Frequency - Prior to works
dc6fe15c-1fb7-58ab-bd9c-70e33c087ca7 | note | HP/WP - HP
78a3b4cb-df5e-4259-bd01-0d06330e8e78 | signoff | HOLD POINT
a3ff5f79-821c-4bbc-8a0d-c574a2deea4b | checkpoint | RCP1.2 - Define RCP ID
bd3ab7df-c91e-50ed-9c41-b6c6b564eeb1 | note | Responsibility - ENG
f2cd55c9-a1ad-5d00-8b04-cfdea5a6ddcc | note | Test Method - Visual
7a92402f-d212-5ba3-932f-a049223bbf1a | note | Conformance Criteria - Inspection Register. Allocate ID for reinforced concrete pipe, define work area
3eabb13e-a5fc-55d1-9e5e-0c2304fa3e88 | note | Frequency - Prior to works
01fa1a7c-777c-5326-96dd-c13febbaac90 | note | HP/WP - HP
9b40fdda-d960-4284-a862-8dfb98171065 | signoff | HOLD POINT
e2eaff84-907c-4e99-a499-7f1652a18357 | checkpoint | RCP1.3 - Lot Register/ WBS submitted and approved
9d4aa403-6f6a-56b3-9372-ec231ffee1e7 | note | Responsibility - ENG
64c2a9f9-6b2b-5b57-8a32-fb3bd9d4174e | note | Test Method - Visual
ba7ba610-14b2-5188-a1e6-92386ddc6c3c | note | Conformance Criteria - Approved WBS
17885f00-406b-5763-9247-ed7adbacc4bf | note | Frequency - Prior to works
5adf77d9-fa43-553f-82e4-d6e8eb9048d2 | note | HP/WP - WP
ca05ac74-ea8b-45d4-83f9-bab5020bb454 | signoff | WITNESS POINT
eee4d041-394d-4bdc-9161-bd3ffe86de15 | checkpoint | RCP1.4 - Underlying lot & ITP signed off and conforming
7e277ac4-11ad-5e40-9244-52e7e58a8071 | note | Responsibility - ENG
0c8f7f10-d540-5ed9-a151-284222351156 | note | Test Method - Visual
f0367775-9636-538b-b3e2-cfee1452cc27 | note | Conformance Criteria - Subgrade prep ITP Signed
4627fa70-eb8e-5276-a9f6-2e41cf56ff42 | note | Frequency - Prior to works
b5bb2635-6b24-5837-88d6-392ed9200951 | note | HP/WP - HP
6ae1236e-00fd-41d0-adcb-7fe315b39cb5 | signoff | HOLD POINT
9fd03587-637a-44af-9e2e-3403e67262d6 | checkpoint | RCP1.5 - Certificate of compliance for RCP Material
8ba8d961-bcba-575b-a70c-8221d691db4a | note | Responsibility - ENG
fb518153-c4c9-599d-9784-df1212063dd3 | note | Test Method - Written
5fa30fd3-a30c-5c0d-b147-18f8f133a4fc | note | Conformance Criteria - Supplier to provide certificates indicating manufacturing processes, materials, thicknesses, classes, and diameters (Only culverts with materials & dimensions complying with the culvert schedule & specification to be used).
8cf8f6f2-49a8-5b2f-8d01-435496f6c210 | note | Frequency - Per pipe
dadf5e5f-dbe9-5839-8f7c-dce6dde67535 | note | HP/WP - HP
b344cfc7-f523-4fa2-80a8-9b815274c179 | signoff | HOLD POINT
21e2741c-a798-4e5a-98ea-a31953dcc9a3 | checkpoint | RCP1.6 - Inspect reinforced pipe culverts for damage
510ea7b2-1f35-5a8c-be2d-a617092ba77b | note | Responsibility - ENG/SV
3307ff91-9395-5339-ae22-fed4c21b27b9 | note | Test Method - Visual
c605fc15-0b95-5237-bf71-4fad6d6f87ef | note | Conformance Criteria - Prior to installation, Pipes are checked for damages and accepted/rejected and documented on Incoming Goods Inspection form
b707dbed-6891-5e5f-996b-f590d76e0587 | note | Frequency - Per pipe
fc05bda0-7cfd-566c-b319-df86a9634428 | note | HP/WP - HP
17ecaae1-e8c3-400e-ae7e-b91084f51cfa | signoff | HOLD POINT
da327277-4581-4fec-9efc-c9ce2dfc1626 | section | 2.0 Construction
5f99f083-bd7a-4240-bb56-a6513b0ad898 | checkpoint | RCP2.7 - Trench Excavation
c62dd798-30d9-55b6-9719-cb98ed9e671c | note | Responsibility - SV/SC
1c623934-6d2d-5d7b-8e83-f6226c870251 | note | Test Method - Visual
192f5475-7e7a-55bf-b802-3502072f98b0 | note | Conformance Criteria - Trenches should be excavated to the required width and grade indicated on the IFC Drawings, with allowance made for benching for excavations greater than 1.5 meters.
4d99e440-ce89-5b56-b3d4-0f2fde0da81f | note | ○ Excavations must be kept free from water until work below ground level us adequately set or protected
26e33e4b-e8e6-54aa-87e7-3c1a0727a43a | note | Frequency - As required
28ba21a3-654e-513b-8455-8a42b0612b39 | note | HP/WP - HP
84dd3f76-d9bd-4de2-aefd-c9b56cc67b8c | signoff | HOLD POINT
9abc2cf3-3ebd-40c3-a008-5c8afe13ab60 | checkpoint | RCP2.8 - Bedding
7a995bcf-015e-5546-9827-de648a94a4d1 | note | Responsibility - SV/SC
76ab9dd0-7895-5420-8f1c-ed2586e46a53 | note | Test Method - Visual
2711b593-0da7-5a67-b619-3ef4e4329c9b | note | Conformance Criteria - Culverts shall be bedded as detailed on the Drawings. Proposed
957c6294-5252-5c6b-ad8f-c46338a51a43 | note | Frequency - As required
40873e2e-581a-55ae-85e2-45f5188c79e7 | note | HP/WP - HP
0094bca9-f5e9-444c-b170-f3eaa36d3310 | signoff | HOLD POINT
980cb612-3b1f-4948-be4f-ea2d97c5ad43 | checkpoint | RCP2.9 - RCP Installation
f986d57c-aa74-5859-b681-d4d43425e32a | note | Responsibility - SV/SC
ec0fb102-ee15-58c8-a28a-cff8bc7e8645 | note | Test Method - Written/survey
0959b8c6-7d24-5417-ab64-96e0a95e728d | note | Conformance Criteria - Culverts are to be installed to the line, level, and grade shown on the IFC Drawings. Inlet and outlet invert levels shall be as shown in the Drawings plus or minus 10mm. Inverts shall be smooth and of uniform gradient throughout each culvert length.
b0760e81-3fb9-5f87-8386-e4352f120eb0 | note | Tolerances:
e0408b1f-90d2-5e4d-8940-1ce733429e5d | note | ○ Vertical level: ± 10mm
f980cab6-dba3-5de1-a198-55d97da85384 | note | ○ Horizontal Alignment: ± 25mm
5c5c42b8-59fa-5640-97ce-c7cf3a315b86 | note | Frequency - As required
9bd65722-6507-5be8-84ba-d465c52382ff | note | HP/WP - HP
f0cf5b45-b952-4de6-b5c3-522098197da4 | signoff | HOLD POINT
6744fe45-cbe1-42fc-9e07-36442691798f | checkpoint | RCP2.10 - Backfilling of culvert
f6a2f34f-0089-5d78-b186-01c03bdb80df | note | Responsibility - ENG/SV
5ac2048e-d459-5ceb-954d-56ca75cfcf62 | note | Test Method - Visual
95968821-c489-5dc4-b025-745a8334401b | note | Conformance Criteria - Backfilling and compaction shall be carried out in horizontal layers of uniform thickness not exceeding 200 mm of uncompacted selected fill material for 300 mm all around the pipe or culvert. Compaction in this zone shall generally be by hand tampers to a minimum density of 95% of the standard maximum dry density at +/- 2% optimum moisture content. Compaction of backfill in the remainder of the trench to subgrade level shall be to a minimum 98% modified MDD at +/-2% OMC shall be advised
92f38c01-2aa7-5ebe-af6c-1d0ded24edd0 | note | Frequency - As required
d884d3c9-653e-56ae-9678-7a54f64f3c21 | note | HP/WP - HP
0e7e983c-c392-42ac-810c-7028e1deca5f | signoff | HOLD POINT
969947be-626a-40d1-bc13-819f2e7cc7b3 | checkpoint | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement)
7d724690-d36d-53cd-a673-65d07ed5cc12 | note | Responsibility - ENG/SV
086fbb4c-5b7a-5a48-9d37-3b7e13829cf4 | note | Test Method - Visual
5114ec53-3c27-58ea-be63-b51987298736 | note | Conformance Criteria - Reinforcement installed as per IFC design drawings
087035a4-ead7-5a9e-817e-c939b19c4ad2 | note | Frequency - V
cfdd3212-9157-50b6-ba02-12ecf47edf45 | note | HP/WP - HP
9d7f81c7-2bd0-44da-8a2e-2a2081fc04ab | signoff | HOLD POINT
d182e6b8-e74b-4565-8218-4bed820fd55c | checkpoint | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork)
7cdb1916-fc65-590d-a4eb-fa79d6946c8c | note | Responsibility - ENG/SV
f85ccf81-f09f-5dff-9f20-137a1b59c880 | note | Test Method - Visual/Field Survey
04c00cb2-0e94-5702-b4b1-b892e31f337f | note | Conformance Criteria - Formwork installed as per IFC design drawings.
6474c17e-0a90-50e2-bac3-18a3ce994be3 | note | Tolerances:
5fe57c4b-dda0-5203-9bd7-63206b00d494 | note | ○ Variation in cross-sectional Dimensions: + 5mm
d6ea1f61-ea27-5460-8ed7-0106e259c934 | note | ○ Variation in overall dimensions: + 10mm
9e8f26a3-2dee-5221-adaf-f9a929d50c7e | note | ○ Variation in surface level: + 5mm
4894c764-4eed-5101-a19c-37e50b168ace | note | Frequency - Each inlet/outlet
7525f319-694c-51ff-ad26-e50f5e7d21f6 | note | HP/WP - HP
51f2810b-9de3-4564-85e9-1784f4711ae2 | signoff | HOLD POINT
dbd762d8-b5af-4b90-bb78-eb60a39c9f5a | checkpoint | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete)
237b4e5c-5984-53e2-90af-25bfa6b49276 | note | Responsibility - SC/SV
6e4694ab-2d41-5ee1-b575-390eb90dc7a7 | note | Test Method - Visual
b794ad17-dbc8-5670-8315-71a072c71eaf | note | Conformance Criteria - Concrete placed and compacted to specified strength (N40) and slump (max100mm).
0fbaa609-c1f4-513e-84c0-9e0c811c0ca9 | note | Frequency - Each inlet/outlet
2239c767-8b55-5af5-a9ed-18f41f9a517f | note | HP/WP - HP
fe6cada3-8994-4551-8fa6-65904ce0e6d7 | signoff | HOLD POINT
7cb7c32d-7d51-439b-bca5-bdba7c65b1eb | checkpoint | RCP2.14 - Rock Protection
1aca3833-d4ee-5f5b-95b6-a3e81fe9907c | note | Responsibility - SC/SV
21d2ef86-da78-5e3f-b1f6-465e6dc1d09c | note | Test Method - Visual
6e7ec58d-8826-5eab-8eb3-008e9894cd23 | note | Conformance Criteria - Dimensions and class of rock protection shall be as specified in the Culvert Schedule and supplied IFC Drawings.
74276163-6b6b-58a5-9c83-d5bfe438ecd8 | note | Frequency - Each inlet/outlet
cb9f8697-2a81-50d5-bad7-6053d541410b | note | HP/WP - HP
299c20d8-e330-4fd8-bd71-87bb5629e5c2 | signoff | HOLD POINT
a3293d54-d437-40ba-832e-fa3f5b592ca3 | section | 3.0 Post Construction
511e13d7-a7ba-4110-af10-f7d0a9723274 | checkpoint | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
cc4c4d61-91aa-5702-bb71-30191f88ba22 | note | Responsibility - ENG
04968476-c886-53ef-8b56-116cf3dcb036 | note | Test Method - Visual
8e2e92e8-66da-5e87-834e-c0f6429d05c6 | note | Conformance Criteria - GDP permits closed.
81bfe09f-ab3a-5f27-a301-6fbe6e38a7cc | note | ○ ITP closed.
5954fb59-df58-5672-81a1-47f1247e9cf9 | note | ○ Approved MDR
f6c3fe36-be45-5f35-b78f-ca66fec32398 | note | Frequency - As required
71bcd464-bfc3-5a88-94ec-5e66074455df | note | HP/WP - HP
0985de39-1d78-45e8-833f-3a49b66440df | signoff | HOLD POINT
16032528-d2b5-4c24-a800-78e1763a1773 | checklist | Ω (DEPRECATED) ITP-0009 Unbound Gravel Pavements (v0) | itp | DO NOT USE - DEPRECATED
2ac16c39-8a1f-4d3c-891c-400476a3c65d | section | 1.0 Pre-Construction
26324e01-52be-4068-8fea-22c36ef22220 | checkpoint | GP1.1 - Drawings supplied most current IFC
ce02b22f-bd6d-5b1f-a166-8a128612ca85 | note | Responsibility - ENG
d9d949bb-0f4a-5392-83f9-a9da5e4b8d65 | note | Test Method - Visual
ea5a6775-7bd4-5396-a748-a150ccd8322f | note | Conformance Criteria - Reviewed drawing register
24180e7b-e081-59ea-8b00-dd6aae2a2fe9 | note | Frequency - Prior to works
f6cec98c-4f58-5269-9e9e-cc57c8ceaf3f | note | HP/WP - HP
2c971e9e-c82a-49d9-a3c5-d4e3b1fb3084 | signoff | HOLD POINT
12c42d3e-2a61-423b-accd-5b7924a373d3 | checkpoint | GP1.2 - Management Plans submitted and approved as per PMP
61634936-80f1-5c18-a1f4-e2fc0bdb8824 | note | Responsibility - ENG
502883bb-0775-5315-a1b5-952d69a6918b | note | Test Method - Visual
73d5a38e-2cd0-5cb9-903a-449e3aaaf099 | note | Conformance Criteria - Approved Package MP’s
7123f834-f4ce-5e36-a2b5-0c2fcdb84cfb | note | Frequency - Prior to works
b046604c-9cd6-5b8c-bd8f-3d420c91d398 | note | HP/WP - HP
83ec0c54-5b43-40bf-9fbb-fcc5ac627825 | signoff | HOLD POINT
209c2651-94d0-4c60-a70a-e367067269f4 | checkpoint | GP1.3 - Inspection Test Plan (ITP) submitted and approved
5a2783e2-7f33-592e-9391-e1e026631214 | note | Responsibility - ENG
a6868bf0-84cc-5fd1-8734-805ddb277708 | note | Test Method - Visual
994b87ac-921c-5312-a2fd-90786d75e492 | note | Conformance Criteria - Approved ITP revision
99921d14-6884-5e36-a20b-2967515c10c6 | note | Frequency - Prior to works
a76a9108-08c4-55f6-b41b-67231acb772a | note | HP/WP - HP
d63a7625-3baf-4def-9bfe-787bfd11af10 | signoff | HOLD POINT
a5d920a2-92e0-4ae4-9a7d-43072889cd49 | checkpoint | GP1.4 - Lot Register/ WBS submitted and approved
bc7038be-d55a-51e0-9376-5d9a70df762b | note | Responsibility - ENG
8c35490e-856d-534e-97f8-bda3697a6d3c | note | Test Method - Visual
68e66969-d275-586e-bc9f-9c38829f8e1b | note | Conformance Criteria - Approved WBS
fe354df8-13a8-567e-9e01-f7e313bd4da1 | note | Frequency - Prior to works
4cc1ba4e-3ea0-5b00-871a-0178fb0d89b9 | note | HP/WP - WP
43392d70-4aef-4e61-b27e-dd683e7de79d | signoff | WITNESS POINT
563f08b5-d8e8-490b-a79e-23c0c5f2269e | checkpoint | GP1.5 - Pavement material compliance testing
593ae87f-da9b-59ae-ae9d-6f58f67f9946 | note | Responsibility - ENG
86d480fc-801a-5af2-b700-357aceef6db7 | note | Test Method - Visual
78a36930-34ea-5c71-af59-c32d8b146a62 | note | Conformance Criteria - Test results comply with the details on the drawings or where not specified the specification
18f6bab0-e4ae-5ef7-805a-9b5c3f97df9a | note | Frequency - Prior to works
aa4e6c65-9d25-5c3b-a871-9af3f2032b36 | note | HP/WP - HP
4eb72e8b-ca63-4d96-884e-50f418adc881 | signoff | HOLD POINT
63bd5c14-6cb7-4109-8991-abe461f60a13 | checkpoint | GP1.6 - Stockpile locations
afe8589b-95ed-549d-8723-f470a09872e4 | note | Responsibility - ENG
d2248fac-bb4d-51bb-adea-9d213bbefec6 | note | Test Method - Visual
2d90b044-8f14-5627-ad5f-a94d40cfbc0a | note | Conformance Criteria - Stockpile locations shown on the drawings or approved by client’s rep
c3ac073e-b195-5b07-95e6-f8f426b79e0f | note | Frequency - Prior to works
9e88f1c9-12bd-5213-a2fb-b750cf73c3d6 | note | HP/WP - HP
0084a942-5284-4325-9493-163a0f456c87 | signoff | HOLD POINT
fa88868d-6bb1-45bb-ac41-e4cb101fbc32 | checkpoint | GP1.7 - Underlying lot & ITP signed off and conforming
495b547f-3d5d-507e-a05b-7b0b42b069db | note | Responsibility - ENG
f793f566-538a-5dc8-8cb2-ac38d08e933f | note | Test Method - Visual
24c395ba-0b40-595e-a5dc-91df7ec24c92 | note | Conformance Criteria - Subgrade prep ITP Signed
8b579c9f-c1e8-5713-bcb1-b494aa313939 | note | Frequency - Prior to works
87b7a7b7-c1a0-5856-8483-378eba4f4b7f | note | HP/WP - HP
55e62c5c-3fa9-4794-8301-d3f671bdff85 | signoff | HOLD POINT
0a53f102-f70c-4fe7-93ec-f75e6288762d | section | 2.0 Construction
329b4b8d-55b7-4ff3-b5e2-da7253cb9846 | checkpoint | GP2.8 - Subgrade preparation under pavements
813a4aa0-0839-5906-879a-21f3c4942019 | note | Responsibility - ENG
b5d820bd-1c01-5b6d-9e21-e68b078dfeb0 | note | Test Method - Visual/Field Test
7f857e7f-47ff-5c39-990f-5b70ce0959a8 | note | Conformance Criteria - If subgrade material is less than CBR10, subgrade shall be boxed and replaced with 150 mm of CBR10 or greater material. Subgrades shall be trimmed and compacted to within 15 mm of the established grade or cross section. Compaction requirement: 98% modified maximum dry density at +/- 2% OMC.
497bbdbb-dbd3-57df-9298-4d8f84db87b3 | note | Frequency - As required
3df73ae8-6903-5847-b8de-67ce8c9ec74b | note | HP/WP - HP
0ff70cca-b90e-4385-a8e3-3a142edc6f63 | signoff | HOLD POINT
4cbd14c8-7eff-4f23-9854-c1c89c0236f8 | checkpoint | EC2.9 - Surface level check/ and survey pick-up
883f4cc6-bc29-56d1-8dfe-01f24bdb2d8a | note | Responsibility - SURV
e51b3cd9-5768-53b9-9b15-f4eaf56fec03 | note | Test Method - Survey/Field Test
952de667-1597-5a53-b992-cc52cf73fd55 | note | Conformance Criteria - Surface level pick-up submitted to company
ac38d1e5-da5a-5444-bf29-5dd5fb516946 | note | Frequency - As required
e8519609-0672-5689-a68c-a721fe80a59b | note | HP/WP - HP
64c35c74-e7a8-4e61-951c-6077599f6746 | signoff | HOLD POINT
c74cb16c-7f6a-45a7-abca-82c1ace91fde | checkpoint | EC2.10 - Proof roll subgrade prior to placement of pavement materials
4dd0e68e-5238-56b7-90b9-48207da80e30 | note | Responsibility - ENG
ad04ce6c-e5e6-51a5-947e-30ee064bab27 | note | Test Method - Visual
d14fa7ef-05d5-5790-a297-a75c9759270b | note | Conformance Criteria - Subgrades under pavements shall be proofrolled under a 10,000L water cart or heavy, self-propelled, smooth drum vibrating roller capable of operating in variable frequency modes, to confirm that, in the principal’s opinion, deflections are negligible
9fc2f4e1-8e59-5022-a52c-0c709409fc8d | note | Frequency - As required
8c05f25c-74a2-5829-9933-2aeed5ddcd49 | note | HP/WP - HP
42dc5316-9d2a-40ea-b02e-6b42f5119a67 | signoff | HOLD POINT
c871f5e0-768f-462e-8f0a-89391baa67fa | checkpoint | EC2.11 - Placement of pavement material layers
75dead7b-9800-5972-8788-71375a3ccb5a | note | Responsibility - ENG
e03186fa-dac3-5291-ae1b-13b6d239b318 | note | Test Method - Visual/Field Test
55210035-c2a4-5e5d-a4cd-95bc1a5acbbe | note | Conformance Criteria - All materials delivered to site shall be accompanied by test certificates.
4dc03d51-94e8-5045-8153-9b0aa6c8add7 | note | ○ Each layer shall be free from sticks, organic matter, clay lumps and other deleterious material, and be spread and compacted in a uniform thickness minimum 75mm, maximum 250mm as per the details on the drawings.
84c4f96e-917f-57ed-bf0f-97cca21c28f7 | note | ○ The deviation from a 3m long straight-edge placed anywhere on the surface of a layer shall not exceed 8mm.
0d94d6ff-9317-5744-b0b9-8af7986febde | note | ○ Pavement layer thickness tolerances: Base -0mm to +30mm; Sub Base -15mm to +30mm.
baf41884-2d3c-575c-b605-063cb9553c30 | note | ○ Finished pavement surface level tolerance: Base -15mm to +25mm
b2ea26ab-d495-51b2-87f3-4b2027094ca0 | note | ○ Horizontal tolerances: Base, centreline/crown -150mm to +50mm, edgeline/changepoint -100mm to +200mm; Sub Base, centreline/crown +/-200mm, change point -100mm to +400mm
7c67790c-4c12-5700-aa18-cedafea91338 | note | Compaction requirements:
5959fa76-0e9d-5ed6-b8be-7ca15b25af3b | note | ○ Base & Sub Base 100% standard relative dry density (RDD) maximum degree of saturation 70%.
4dbce34c-5477-5944-9356-6c0f39a8066e | note | ○ Compliance testing frequency as per table in Specification Annexure A clause 5.
caf13e1b-a77d-580c-8e46-e9c8f951c5bd | note | Frequency - As required
e2e094f8-7189-5554-b44f-cb72006d1903 | note | HP/WP - HP
954eae12-3372-460e-ba45-58cb8b0aeef7 | signoff | HOLD POINT
fe6baa0e-4119-49b3-bf93-46470a42c919 | checkpoint | EC2.12 - Surface level check/ and survey pick-up
242375b7-945d-505a-ad98-29f77818bf0c | note | Responsibility - SURV
db301325-72b3-579b-a48a-7dbe4fe0e789 | note | Test Method - Survey/Field Test
45add8df-cbf6-59b2-9035-9265ae203c65 | note | Conformance Criteria - Surface level as per the pavement layer details on the drawings, and all layers as per the tolerances listed in item 11 of this ITP.
13b8182e-2cb1-5065-81a9-1e3ae533de8c | note | Frequency - As required
6a2c4aeb-7f64-5b52-9ea4-431a16f7d7d4 | note | HP/WP - HP
59daa3e2-cdaf-40f2-b690-3f6d54bd2217 | signoff | HOLD POINT
3cbbed25-f06a-476b-858f-61b9405a30e9 | section | 3.0 Post Construction
62907706-957c-49b3-8c5e-8410f080c594 | checkpoint | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
064f8f32-5c1f-597e-9def-5e082eb9eb59 | note | Responsibility - ENG
06f4f82d-14fa-5206-b688-fb664667c5da | note | Test Method - Visual
e4485279-3a36-5c51-9bb1-4ff1e39e0722 | note | Conformance Criteria - ITP closed.
5c6ab4e5-79dc-5996-8e9f-604b6528f9b7 | note | ○ Approved MDR
2e339af6-9f26-532a-8380-2f27563ada13 | note | Frequency - As required
2dcb3626-803b-59a5-9b33-7ceb37b4b296 | note | HP/WP - HP
f63ab955-f79d-4581-a627-ceb70a5f6c45 | signoff | HOLD POINT