## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
6796a4b7-50fd-4c6d-82a5-85be75cf9074 | checklist | EVAMP001-THS-QA-ITP-0001 Clear & Grub | itp | ITP-0001 Clear & Grub
| section | Lot Map
| checkpoint | Attach Lot Map
65c63129-50bb-463f-92ee-20d59b94b854 | section | Clear & Grub
489aefec-c9f3-4977-a3a2-44421446c676 | checkpoint | GC1.1 - Underlying lot & ITP signed off and conforming
98434abf-234a-51f2-b704-be1a9de86c51 | note | Responsibility - ENG
a024fe55-4ba9-5fc2-90b0-30f84dcbf2ab | note | Test Method - Visual
c07fbf52-8dec-534f-86e3-08b175a65330 | note | Conformance Criteria - Pre-construction lots closed out
e1d80108-10e4-512a-8cc8-0f00f2bac03b | note | Frequency - As required
f9e55d9e-59ba-5f88-bb29-b5db805daafa | note | Link to ITP - PC1.18
e1684c5e-6d00-4179-ba02-76548e29da42 | checkpoint | GC1.2 - Survey of Natural Surface
6ebbf330-e95d-5e10-8e27-ef6e1c7825e6 | note | Responsibility - Survey
19245fda-d051-5edd-baca-909f624484d2 | note | Conformance Criteria - Check survey pick up of work area and digital file saved in Construction Team Sharepoint and detailed in register. Surface area shape file created and uploaded to Qfield
96356e00-b597-41a7-be38-ca41842ab0df | checkpoint | GC1.3 - Clearing of vegetation
4ad76604-a732-5f00-9202-8b479ba6a09f | note | Responsibility - SUP
160b8fc7-a7f6-5d83-b268-e1aaa26d4321 | note | Test Method - Visual
afd40b38-8546-5d46-b008-32e8c6f6d1f4 | note | Conformance Criteria - FSC individual on site at works during clearing operations.
b0a60139-c641-5810-8191-a3b4d22dfebe | note | ○ Habitat vegetation, threatened species and cultural heritage areas demarcated
b69d176b-96b4-5d45-9aa2-af9173cac2d2 | note | Frequency - As required
b596ec02-f4aa-5645-a935-4d7777f98606 | note | Thiess HP/WP Check - HP
d24f16aa-677d-5eb7-b1c3-48d78cc9f8c4 | note | Inspector HP/WP Sign Off - WP
a7af8165-3a25-45f7-b0f4-c5c6827e3060 | signoff | WITNESS POINT
2ffd8602-4159-4631-b51f-fb50d097b50f | checkpoint | GC1.4 - Stockpile Cleared Vegetation
6ee3953f-8735-54f5-89e5-f208aec95df3 | note | Responsibility - SUP
dd7b1d88-2f7f-5ad0-9131-e4a6399a168c | note | Test Method - Visual
92ca0ab2-2216-5ca8-a440-49b9a542ab8f | note | Conformance Criteria - Cleared vegetation loaded and hauled to approved stockpile location
3387fd36-cd13-5095-87ff-d7937b609226 | note | Frequency - As required
8ad94a31-975a-5c99-8ca0-6636fb57e981 | note | Thiess HP/WP Check - HP
10a24508-4e40-532b-9d55-58c51ec51adc | note | Inspector HP/WP Sign Off - WP
aaf1e0b1-b8f8-426f-bf9f-6bb0df391867 | signoff | WITNESS POINT
668916bf-b68c-4a79-a23e-e790bbe46f1c | checkpoint | GC1.5 - Erosion and sediment control
be16683f-6acc-519f-8e55-b4bc294ff9f9 | note | Responsibility - SUP
46dfae90-06f8-5f4e-857b-bfd837333e53 | note | Test Method - Visual
c6dd806e-baa9-5e10-a07e-51f568dd4282 | note | Conformance Criteria - Erosion and sediment control measures to be implemented whereever possible after clearing has been completed.
27238811-fa23-5cb2-b8af-a292a3025dce | note | Frequency - After clearing
62509e03-b70a-5049-a275-c2aacb3714ae | note | Link to ITP - PC1.10
3c1a6503-66f6-5eb7-be27-47b33e6a9cfb | note | Thiess HP/WP Check - HP
65e4534a-f135-5b93-bd94-cb77a4b83a92 | note | Inspector HP/WP Sign Off - HP
fa877d86-55e1-456c-9e59-c94fd9b13286 | signoff | HOLD POINT
15100512-873e-4694-b8bb-6ae6e682538e | checkpoint | GC1.6 - QA close out
2123b05c-fda5-5cef-ba89-eb0e7e09d771 | note | Responsibility - ENG
7cbe0163-db58-5298-a5ce-55e4205257e2 | note | Test Method - Visual
e3dfd798-8daa-5d94-a78e-aefcba19b2f1 | note | Conformance Criteria - Works completed and update ITP/Lot register/MDR and close out of GDP
c975079d-ffaa-54ef-8b9d-b3003d95f4a0 | note | Frequency - As required
da06f814-8fbd-5785-9bc4-6286327f6abb | note | Thiess HP/WP Check - HP
aac6fe69-eb96-56eb-87d9-32d99c7afd4c | note | Inspector HP/WP Sign Off - HP
12b79af7-f40a-4688-b33d-60e2db049043 | signoff | HOLD POINT
b86ac2fb-a936-4959-bc2c-0b212ce6cb6a | checklist | EVAMP001-THS-QA-ITP-0002 Topsoil Stripping | itp | ITP-0002 Topsoil Stripping
| section | Lot Map
| checkpoint | Attach Lot Map
8749f0ea-dcaf-40a1-a9fb-38172bde624a | section | Topsoil Stripping
916380c8-3601-4c5d-aaec-d8f5ce265520 | checkpoint | TS1.1 - Underlying lot & ITP signed off and conforming
ae37fa4e-a8c8-5621-99d3-c3093ffbd813 | note | Responsibility - ENG
eaa1749a-e2ec-5b85-8edd-42ddd734d8a2 | note | Test Method - Visual
dae7b959-a92f-50a9-80f0-f8e4f50ef610 | note | Conformance Criteria - Clear & Grubbing ITP closed out
eeadea39-f306-52fc-83e8-4c96215d2126 | note | Frequency - Prior to works
b23b17a7-7376-533d-9afe-1423f0cb849c | note | Link to ITP - GC1.6
6c621a60-d7a2-4f30-86cf-79266b7cfff1 | checkpoint | TS1.2 - Survey Set out
a04a85f3-030f-5947-93a2-83065c379130 | note | Responsibility - Surv
b0740eeb-b1e8-565d-b6bb-e79334e3c6b7 | note | Test Method - Field
8795b855-e66e-55e4-ae20-2c067a367fa7 | note | Conformance Criteria - Areas of work to be set out by surveyor and/or models in plant
c707d4ab-6d68-5bb7-aa60-78dc74f21831 | note | Frequency - As required
225fa33d-4b6f-5408-b2e1-861b17ce1c7b | note | Thiess HP/WP Check - HP
c0fab7ed-3a57-510c-99ca-1308ec25b414 | note | Inspector HP/WP Sign Off - WP
92c3d114-4ca0-4687-9ab6-1be8c3bbaf48 | signoff | WITNESS POINT
ef0f707e-77c6-47e0-b7b6-f00e62939a07 | checkpoint | TS1.3 - Strip topsoil, load & haul to approved stockpile location
944babb1-ca24-540f-903e-b2314fa26865 | note | Responsibility - ENG
a591edf9-2637-5776-97cf-4ac30f68fd7f | note | Test Method - Visual
93eddc67-b978-54f9-8611-85f084d83259 | note | Conformance Criteria - Provisional depth of topsoil strip shall be 100 mm unless shown otherwise on the drawings.
8e938ca4-1f2e-543e-b9b6-75e0ac18fd76 | note | ○ Stripped topsoil loaded and hauled to approved stockpile location.
e13284e2-f46f-585b-bcd5-00fe9807e382 | note | ○ Stockpile locations located minimum 40m from watercourses and not exceed 2m in height.
48714638-6934-566f-8a20-7f697f7d162d | note | ○ Native seeding of topsoil stockpiles as agreed with Company.
e05858cc-a4bd-5b6a-9caf-8cde8db7aa22 | note | Frequency - As required
9463ad6a-351e-5eee-973e-cc0598eb1f1c | note | Link to ITP - PC1.10
10901a46-aadc-5279-b7e6-6b0eef29320f | note | Thiess HP/WP Check - HP
cabcfed7-1ef9-558c-b8c6-22527fc21bc5 | note | Inspector HP/WP Sign Off - WP
d2bc2732-0651-43bb-8cb4-971bf9e1c4ff | signoff | WITNESS POINT
071da937-196f-4dbf-ac54-4880807d9d2f | checkpoint | TS1.4 - Topsoil location, destination and quantity catalogued.
2f69d885-0944-5510-bc4d-b099d07f8d6e | note | Responsibility - ENG
76b50feb-f81f-5024-9cc6-1a08b9096a8d | note | Test Method - Visual
cfd53ca6-93ea-522e-990b-36f528577392 | note | Conformance Criteria - Topsoil register to be maintained with information on topsoil volumes and stockpile locations
9fef3602-e591-50a2-8b1e-b28b30b00301 | note | Frequency - As required
de9b897a-7bf0-558d-a79a-ab5d0a872b6e | note | Link to ITP - PC1.10
4278a0ee-23c0-5b19-8a90-69a59d37c005 | note | Thiess HP/WP Check - HP
d7122674-faca-594e-887a-749570912de2 | note | Inspector HP/WP Sign Off - HP
05dccf20-f68b-4781-954e-06157df5e77b | signoff | HOLD POINT
c6e48c99-ba54-4abd-bc57-c3bcd1e665fd | checkpoint | TS1.5 - Surface level check and survey pick-up
765c1ef7-26db-5fcb-81b9-462bb14fbba4 | note | Responsibility - SURV
6503a485-f9c8-558d-811b-469336ece816 | note | Test Method - Survey / Field Test
64c8342e-8aae-5f7c-a4e3-df39e8aecf3b | note | Conformance Criteria - Stripped surface level picked up as per Table 10 C15 (DXF file format, volume calculated and filr saved in Construction Team Sharepoint and detailed in register
162e926d-aa9c-5849-b1af-ef6f44f75ea6 | note | Frequency - As required
2ed18220-a06f-52d7-9f65-00887d5aad21 | note | Thiess HP/WP Check - HP
9e188d56-9fad-5d14-b173-8c642a6c6397 | note | Inspector HP/WP Sign Off - HP
af4ae563-b4e9-47a2-a180-1d478211e8ec | signoff | HOLD POINT
ae6c69bd-ecc2-454a-9bff-6080c8c1c94a | checkpoint | TS1.6 - QA close out
8efc1984-16d2-53ba-a057-5431c08fd38b | note | Responsibility - ENG
0e4486bc-38e8-544f-ac30-fb17669c1687 | note | Test Method - Visual
c7e83a05-827a-55ab-a626-c824caa8593d | note | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR.
d228505a-fca4-59be-b984-2e29b12b43a9 | note | Frequency - As required
e910bce3-f30b-59aa-b87d-43474fc1cf31 | note | Thiess HP/WP Check - HP
ef4ec3ef-ada0-5aae-b30f-6405d1fe60ab | note | Inspector HP/WP Sign Off - HP
5e2f8d5f-e7ee-48e0-844a-1e4cf9f054a9 | signoff | HOLD POINT
1e0915ac-c4f2-4889-bc14-8ff55ed38f8d | checklist | EVAMP001-THS-QA-ITP-0003 Subgrade/Foundation Preparation | itp | ITP-0003 Subgrade/Foundation Preparation
| section | Lot Map
| checkpoint | Attach Lot Map
3888cb15-c6e9-4774-94f4-ef0136a8d2b8 | section | Subgrade/Foundation Preparation
ac475546-f2ce-4c02-a316-d1bc173edfa8 | checkpoint | SP.1.1 - Underlying lot & ITP signed off and conforming
0ba38702-7e4a-5305-999e-9d0c380b72b1 | note | Responsibility - ENG
cd2dc35a-9502-5741-8b68-f7ea4a27f70c | note | Test Method - Visual
cdae2c66-de7c-5ca1-aaa5-1dcaadf88613 | note | Conformance Criteria - Topsoil ITP closed out
39fb73af-ee7e-5cfb-a384-6dabf3434961 | note | Frequency - Prior to Works
8ee4a552-2995-58d0-9e48-752e910a3518 | note | Link to ITP - TS1.6
2897bed4-d43c-43af-aa95-e7d21d62accd | checkpoint | SP.1.2 - Embankment fill material
6698839b-9391-5658-8be4-54b8641f1d75 | note | Responsibility - ENG
afc74dae-bdf5-5e03-929d-edad53d7c4be | note | Test Method - Visual
e98679c2-b70a-536b-9a9c-bef3a3d5405e | note | Conformance Criteria - Ensure CBR10 subgrade replacement materials have been approved for use and within specification
6171a00d-a560-5761-b6c3-27e3f1536543 | note | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage)
cd5ca6cd-ecd1-5805-9164-3664d4d56063 | note | Link to ITP - PC1.11
8ebc67a8-3f8e-5cfc-aa2c-2ab9989333fa | note | Thiess HP/WP Check - HP
c22e0b29-ee08-5f77-a31c-95c7a96e983a | note | Inspector HP/WP Sign Off - WP
e6f51fb7-6c5b-4f3e-b073-2d76ec83af4c | signoff | WITNESS POINT
f18384a0-36b1-404a-ba16-b643c5ba2214 | checkpoint | SP.1.3 - Survey Set out
4b25c72b-e94d-529d-aa6b-3835cde661fb | note | Responsibility - Surv
6db7605f-6648-5850-b3e9-c41e7f2cfe70 | note | Test Method - Field
d0b3b03b-7fa3-511c-b9b7-9c1db665c392 | note | Conformance Criteria - Areas of work to be set out by surveyor and/or models in plant
662d8646-ee30-5fd1-9ce4-7ccc7f1318a9 | note | Frequency - As required
57f8ebaa-8d19-5e99-8c43-2d16b8aff760 | note | Thiess HP/WP Check - HP
45364d23-92d3-5007-895d-5930c2185259 | note | Inspector HP/WP Sign Off - WP
4d57dd0c-68ce-48ab-bd54-2cee86b3fca9 | signoff | WITNESS POINT
dbba825e-74ac-4f55-a21f-fc1ed370c529 | checkpoint | SP.1.4 - Removal and replacement of unsuitable material
747e0dbf-fcba-5695-b1a3-01b9361dabf7 | note | Responsibility - SUP
30352755-f0c8-5be8-bb2c-b08aec36a9b4 | note | Test Method - Field
21dbc2ce-af3d-5371-a91b-5b924c2fdfbc | note | Conformance Criteria - Determination of unsuitable material by the Level 1 GITA or Inspector (Sedgman) is required prior to the removal of any unsuitable material. Unsuitable material criteria is in the specification.
e4d39c20-3fe5-5de7-bc69-b4f7f854c5fd | note | Frequency - As required
c84d290d-5958-537c-9c8e-48a52d608cc3 | note | Thiess HP/WP Check - HP
47ac2868-dfa4-5963-aa63-9fdf4d28309a | note | Inspector HP/WP Sign Off - HP
abc7c254-a1c2-4d1e-a2cc-9dda06113411 | signoff | HOLD POINT
bf2a450e-c73d-4e58-b6c5-f8d0ad38ec50 | checkpoint | SP.1.5 - Proof rolling and soft spots
6ac50545-6961-5f6e-9358-6a0ee1fb360f | note | Responsibility - SUP
c709b948-1ca6-56d0-9cf6-aefd7aedbedc | note | Test Method - Field
c378f6ef-6f7b-516a-8e9d-004032c7b05c | note | Conformance Criteria - All subgrades and foundations shall be proof-rolled under a standard 8 tonne axle load or 10,000L water cart or heavy self propellled smooth drum roller dynapac 620D or equivalent to confirm that, in the Inspector (Sedgman) s opinion, deflections are negligible
3a550ce8-816b-5397-a561-01745103d955 | note | Frequency - As required
ffbdbde8-4eed-59a2-a503-187d9143d7f6 | note | Thiess HP/WP Check - HP
118fb4dc-b6f4-5712-8aa5-f3abc584a348 | note | Inspector HP/WP Sign Off - HP
6e4cdf2a-ea9e-4e8c-aef7-9e25439a1400 | signoff | HOLD POINT
4fd12e0e-f712-429a-8540-2f342f7bb820 | checkpoint | SP.1.6 - Subgrade/Foundation preparation
53ba4411-a5de-531c-961b-c446ae05e42d | note | Responsibility - SUP
d0ce048c-197d-5912-80e4-60df6073967c | note | Test Method - Field
36fa4a64-d46f-5f5c-ba5f-c800dda0a565 | note | Conformance Criteria - Lightly tyne the subgrade/foundation immediately prior to placing embankment fill.
aa96d8ee-81e4-5cf0-9311-27c35702a144 | note | ○ All material exposed in cuttings at subgrade level minimum CBR 3 or DCP 150kpa. If CBR2: Remove & replace with CBR10 select fill 150mm deep. If CBR1: Remove & replace with CBR10 select fill 250mm deep.
0d516928-6b59-57fe-b7ca-1ee4b1414d64 | note | Frequency - As required
ed5e1566-2280-51c3-be8e-1eb5461ee755 | note | Thiess HP/WP Check - HP
0e74b08d-944f-5d4f-a1a0-598735ce57d8 | note | Inspector HP/WP Sign Off - HP
c760cec8-8ceb-4a0d-a985-5324d40c2be8 | signoff | HOLD POINT
187efc59-29ad-49ed-8390-8b60becf1967 | checkpoint | SP.1.7 - Trim subgrade in cuttings
b3913e7c-bebc-5d12-9a25-bb41ac3c832f | note | Responsibility - SUP / SURV
ae93ba34-1d60-5116-972f-c6a9676fd814 | note | Test Method - Field
a76edf78-b419-5b0e-8f24-353676836a66 | note | Conformance Criteria - Trim all subgrade to the lines and levels shown on the drawings in accordance with the following tolerances: Top of bulk earthworks +/-50mm; Road subgrades & under buildings & structures +0mm to -25mm.
549c5914-07e3-55e7-bad0-0bbf1fce3fab | note | Frequency - As required
ffcc823b-be30-5129-a036-a226605a90d8 | note | Thiess HP/WP Check - HP
f45a1c01-4b58-5b13-93cd-bdb9bab52ee2 | note | Inspector HP/WP Sign Off - HP
f23b4a57-60f2-4a1f-bbca-c06f05da3796 | signoff | HOLD POINT
71594be2-04a9-4642-8c27-46fc02041e66 | checkpoint | SP.1.8 - Surface level check and survey pick-up
ae3e3dc0-bbb7-5161-ab48-8f3e93da7c89 | note | Responsibility - SURV
0233e3da-d7b0-57cb-a28f-791670b10318 | note | Test Method - Survey / Field Test
181a65b6-888f-5718-abc5-1c5ea421f1f5 | note | Conformance Criteria - Surface level picked up as per Table 10 C15 (DXF file format, volume calculated and filr saved in Construction Team Sharepoint and detailed in register
8205adaf-59f9-5e9c-94e0-2407ce8f2386 | note | Frequency - As required
816da858-ab98-54c1-b51c-3cfa04e1791f | note | Thiess HP/WP Check - HP
8fd83ed0-b72c-5af0-9b4a-dc40044dbcee | note | Inspector HP/WP Sign Off - HP
4bcc759d-350a-4250-8f6b-244794b056e2 | signoff | HOLD POINT
cf8c9bf4-266f-4abf-8026-2827cb980a71 | checkpoint | SP.1.9 - QA close out
f480ed2e-dad9-5d6f-bd96-060b4d89131c | note | Responsibility - ENG
1a40051b-4408-5dcb-b87a-220c77689e1a | note | Test Method - Visual
f5308beb-802e-5f5c-af91-fc47fbd956cb | note | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR.
5dd34aff-46bd-5dab-b2af-b6da8a1c725f | note | Frequency - As required
348d3807-5f57-5b32-ba96-d3d360a60099 | note | Thiess HP/WP Check - HP
b9692b12-b245-507c-a77b-b367d15bbc3d | note | Inspector HP/WP Sign Off - HP
fe791962-27f7-473b-bde7-91e7f40b4125 | signoff | HOLD POINT
dce3a70f-9200-4dfb-9e26-88ee054029dd | checklist | EVAMP001-THS-QA-ITP-0004 - RCP installation - RevB | itp | ITP-0004 - RCP installation -
| section | Lot Map
| checkpoint | Attach Lot Map
56f3d35f-f971-4570-a6cb-a7e2e053164c | section | Construction
43a83497-5fd9-419c-86bb-037369896bba | checkpoint | 7 - Trench Excavation
68b7bc18-4723-554c-9620-02b51a3f322a | note | Responsibility - SV/SC
1e6470b1-a264-52b3-a75c-5facf55b91ec | note | Method - Visual
4eadcc70-fbdc-580a-8923-38941e267486 | note | Conformance Criteria - Trenches should be excavated to the required width and grade indicated on the IFC Drawings, with allowance made for benching for excavations greater than 1.5 meters.
1152136e-5ee8-5625-aec6-e712fe3b8893 | note | ○ Excavations must be kept free from water until work below ground level is adequately set or protected.
c78911a0-c5f8-535b-a451-525848c399e6 | note | Specification Clause - EVAMP001- THS-CV-SPE- 0003
cee4928f-da33-5167-b6bb-06fa4737a3fd | note | Frequency - As required
24f10513-7657-53e6-9190-d3d57af409d4 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
853fb7d6-aa96-5f62-9919-44c0a2eee0b6 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
561d45d4-f536-4b76-b6b0-abcb2ed432d0 | signoff | HOLD POINT
69f40dd9-2323-4125-a6c4-16027c169189 | checkpoint | 8 - Bedding
4239bc90-2604-5eee-89c6-2e482dae7a3d | note | Responsibility - SV
42134d05-d220-53d1-a17b-c9b87c890d00 | note | Method - Visual
c01ad167-a012-5205-9658-537f8d5064e3 | note | Conformance Criteria - Culverts shall be bedded as detailed on the Drawings. proposed
02d5cb2b-1552-55df-991b-c77c37083a89 | note | Specification Clause - EVAMP001-THS-CV-SPE-0003 clause
c3cc6d59-4295-50a2-a460-3887b60d6d4f | note | Frequency - As required
08b14b51-28d3-593c-9e2f-797537a5fb0c | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
c011de9f-89fc-57f6-a607-262811293f31 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
ef1d7cc1-1d5a-543b-8d84-c7f7a90a5c4f | note | Records or Comments - On-site verification sheet and survey
c2dcb488-a998-45a1-9555-f57d1f775ef0 | signoff | HOLD POINT
37e3f4ce-8c23-4ac7-ae40-db511f36d76a | checkpoint | 9 - RCP Installation
ed45f2fa-5bf5-53c4-9582-0d0baed06bcb | note | Responsibility - SV/SC
9f390736-5c83-5e2a-a4db-0f675d5271ea | note | Method - Written/ survey
97da684e-db9b-5e0c-8be2-81bbd59ac16f | note | Conformance Criteria - Culverts are to be installed to the line, level, and grade shown on the IFC Drawings. Inlet and outlet invert levels shall be as shown in the Drawings plus or minus 10mm.
56d8fdfb-15e6-522d-9874-574648b79800 | note | ○ Inverts shall be smooth and of uniform gradient throughout each culvert length.
413e091d-0634-5769-922e-815eb6d55ef1 | note | Tolerances:
a5810a90-5120-5cb0-82a9-06fd5c238ff6 | note | ○ Vertical level: ± 10mm
e1988385-3ee5-5861-9b98-939c44fa0efe | note | ○ Horizontal Alignment: ± 25mm
7718f1eb-2b7f-5d03-9852-9fa62c3ad40c | note | Specification Clause - EVAMP001-THS-CV-SPE-0003 clause 4.17
022b4743-39ff-5bfe-832e-d2ee15b018a1 | note | Frequency - As required
1e3fc071-6371-51d0-b52a-dc432849c086 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
9eea53fe-e2b5-5a9b-96e0-621b9cf431a2 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
5c9691a7-f948-4765-b8b3-1b5e09db9be4 | signoff | HOLD POINT
05163394-849a-4ee5-9526-90a1161cf933 | checkpoint | 10 - Backfilling of culvert
a31cb5a8-a8a2-5ccf-a097-2663f91dbb0e | note | Responsibility - ENG/ SV
df134359-5dc6-5308-9f76-b2a9f1a1674c | note | Method - Visual
c8ffc04e-097b-5afc-98e2-46009a2bb2e3 | note | Conformance Criteria - Backfilling and compaction shall be carried out in horizontal layers of uniform thickness not exceeding 200 mm of uncompacted selected fill material for 300 mm all around the pipe or culvert. Compaction in this zone shall generally be by hand tampers to a minimum density of 95% of the standard maximum dry density at +/- 2% optimum moisture content.
7e941825-8a37-5156-affd-1411e8532ac2 | note | ○ Compaction of backfill in the remainder of the trench to subgrade level shall be to a minimum 98% modified MDD at +/- 2% OMC shall be advised.
77984c67-77a1-5da3-8ac8-11de77c8ada0 | note | Specification Clause - EVAMP001-THS-CV-SPE-0003 clause 2.14
6522d457-7c5f-5a5e-9056-b94a6ca1b608 | note | Frequency - As required
f394ffc6-4cc5-5bd2-961f-50c0beb5bac5 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
cd83e072-f633-504a-9e1f-c63299a17b0f | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
f2e5af3b-4b52-57f2-ae91-b9c0c7559ee0 | note | Records or Comments - On site verification/ NATA Test report
6897bc61-4b65-4218-90dc-8eb3042d74f0 | signoff | HOLD POINT
1159a3cc-7c2c-4c3c-9d96-3e199b49f625 | checkpoint | 11 - End Treatment – Headwall & Wingwalls (Reinforcement)
1f839b98-5b3a-5558-bf19-8b81de80dee7 | note | Responsibility - ENG/ SV
362366e0-290a-568e-8e80-5a1193f105a1 | note | Method - Visual
fe093559-62c5-529b-85e3-426694ba424f | note | Conformance Criteria - Reinforcement installed as per IFC design drawings.
f766d9a7-93b5-5769-9b49-98c8c5aabe64 | note | Specification Clause - EVAMP001- THS-CV-SPE- 0003
1dbdfb8b-8258-5bad-9db4-21316f57a77a | note | Frequency - V
62762074-9d1f-5e8e-90d0-e0ae6cfc8dd3 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
d08ebcfa-f442-55d7-bdb6-052d835388e0 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
e48845db-048a-5b10-a261-4cefc6e06e0e | note | Records or Comments - On-site verification sheet
96016adc-bbd4-4134-bcc1-f724a1ab9824 | signoff | HOLD POINT
7c818fcc-cc64-493d-8034-cf92b606f9ae | checkpoint | 12 - End Treatment – Headwall & Wingwalls (Formwork)
a9032701-cf6f-5eee-84c2-d6357ff70e2f | note | Responsibility - ENG/SV
efbe8cad-9b1d-561d-ba81-8ee22ed5b585 | note | Method - Visual/ Field survey
c66faf42-2a3b-5cfc-8fb7-7ea012e6b781 | note | Conformance Criteria - Formwork installed as per IFC design drawings.
afdc0922-d8d7-5d92-9090-ef5cc7dcfbad | note | ○ Tolerances: Variation in cross- sectional Dimensions: + 5mm Variation in overall dimensions: + 10mm
4dfe8944-544a-5cc6-90f1-459027b8edf7 | note | ○ Variation in surface level: + 5mm
aa234672-3f02-58b0-b36e-25b017b43ec7 | note | Specification Clause - EVAMP001- THS-CV-SPE- 0003
b0f36283-2231-5c55-ac1c-5827af306ec6 | note | Frequency - Each inlet/Outlet
4a7a4587-c369-5b2c-addc-8998424f91fb | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
59fd2fdc-4c0f-59ef-b503-8c724bf40855 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
25e25285-f67a-5ea7-ae93-84513d1c542e | note | Records or Comments - On-site verification sheet
137d8f16-9ee3-4474-8fc1-39d38bbd7fde | signoff | HOLD POINT
b24bc6a2-a678-4de6-b061-dca6e0fcd292 | checkpoint | 13 - End Treatment – Headwall & Wingwalls (Concrete)
0167f7a1-7bba-5c05-9e9e-15167e3e68b0 | note | Responsibility - SC/ SV
0591f5f1-bfd4-5c97-bb0d-e73672a21199 | note | Method - Visual
4ddfda5d-a0a2-59c0-b34b-ee98af2f873a | note | Conformance Criteria - Concrete placed and compacted to specified strength (N40) and slump (max100mm).
80bad0fc-f885-5cc7-9f73-10d29ce83f91 | note | Specification Clause - EVAMP001- THS-CV-SPE- 0003
1cf0043e-b88a-5f8a-9928-b059cab4d704 | note | Frequency - Each inlet/Outlet
857b35fd-f0f6-503f-ab3f-d5d6e0537aa6 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
d2fe7261-8871-5430-adf5-12e042c9a560 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
6e6d6a1e-b88c-425e-94d6-d3663839509d | signoff | HOLD POINT
83e2abd0-bdcf-442c-ab81-a2affc4636ea | checkpoint | 14 - Rock Protection
09d56772-61df-51bb-ae43-e66b558b6368 | note | Responsibility - SC/ SV
73b335aa-4c15-5609-8b6b-1675d49ac423 | note | Method - Visual
51ed2597-3a22-50ef-8036-4943869adcec | note | Conformance Criteria - Dimensions and class of rock protection shall be as specified in the Culvert Schedule and supplied IFC Drawings.
f884cbfc-fe8c-5bb3-a08c-4be6ef921df3 | note | Specification Clause - EVAMP001- THS-CV-SPE- 0003
dc47151a-fdcc-585f-904b-b2e27c251e01 | note | Frequency - Each inlet/Outlet
2db8fee7-f48b-5a2e-b13f-8ce46a619034 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
c434e76d-296f-505e-a677-ea9d29334af0 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
84b95209-acbc-482a-85f5-b36c509aaf2b | signoff | HOLD POINT
0e479983-e29c-4b0b-9eb7-75ef58bf6475 | section | Post Construction
278bde5d-6a3c-4ed0-805d-0d175900ffa3 | checkpoint | 15 - Works completed and update ITP/ Lot Register/ MDR
8d43c8a0-0cfc-51bb-8a2c-9d8b66c01122 | note | Responsibility - ENG
58884201-8c1d-51cd-a5cc-c635bbd4f201 | note | Method - Visual
dda7d387-a34e-5cdd-a4fd-03dc93c691bc | note | Conformance Criteria - ITP closed. Approved MDR
1307e404-dd7f-5a6b-b280-3858988a2a36 | note | Specification Clause - EVAMP001-THS-CV-SPE-0003
22b8d26f-c13a-5b0f-999c-2017754b0fb6 | note | — EVA PMP
e28bf5c7-1451-55c7-b97a-83cf39bed3ac | note | Frequency - As required
bfa86957-b24a-52bb-9baa-cabebc4ed9d6 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
87d689e4-9f82-59b5-8d1c-5a030180de05 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
bd987709-df61-4d12-959b-d025f828d7e7 | signoff | HOLD POINT
e75b191c-dd7a-40a2-a54d-7b0af1535acf | checklist | EVAMP001-THS-QA-ITP-0008 Embankment Construction | itp | ITP-0008 Embankment Construction
| section | Lot Map
| checkpoint | Attach Lot Map
e8558513-7ab6-48d1-98de-433944eb476e | section | Embankment Construction
4a614c52-e477-4c8c-b9e8-f9f66f963fae | checkpoint | EC1.1 - Underlying lot & ITP signed off and conforming
635d023a-43cc-507d-b6a4-24cad7028583 | note | Responsibility - ENG
7a8f9240-8a69-5c27-80fb-9d3502e0f1b1 | note | Test Method - Visual
783de080-e185-55a5-b451-0ac7c73b29a8 | note | Conformance Criteria - Subgrade/Foundation Preparation ITP signed off
ba80dbfd-0503-5808-bd81-935e41563a00 | note | Frequency - Prior to works
e20c78d0-1941-5154-ac0b-ffc993dea396 | note | Link to ITP - SP.1.9
3f344af9-d08a-5865-81ef-d9da96d5e264 | note | Thiess HP/WP Check - HP
7db41919-c6e1-5e66-90ec-00c0aa29a5c9 | note | Inspector HP/WP Sign Off - WP
51d9a739-4898-4980-a216-4b966f532089 | signoff | WITNESS POINT
492095ef-bc3f-4c0b-b398-01ff56260bd6 | checkpoint | EC1.2 - Embankment fill material
98a574b1-314a-575b-aca7-fe9482091f7c | note | Responsibility - ENG
627647d6-75a4-5752-8fb3-d2056f51c319 | note | Test Method - Visual
723a775a-1db8-5bf8-8f2a-c909a29ed3c3 | note | Conformance Criteria - Ensure embankment fill materials have been approved for use and within specification
8bd82068-6705-521e-814f-145754eb5f73 | note | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage)
a780ca05-c85c-5f5f-85c1-2b0adbf240d3 | note | Link to ITP - PC1.17
9a67a0a0-915a-56ff-b4f5-9cb31fe49ffc | note | Thiess HP/WP Check - HP
2b09a7b7-e569-5fd1-aea6-8705fa41ac77 | note | Inspector HP/WP Sign Off - WP
a8f80374-068c-4565-8062-7727b7ea763c | signoff | WITNESS POINT
6493e315-0ff4-4f7a-9623-6ef291088e0c | checkpoint | EC1.3 - Survey Set out
2c32f299-db28-5f0d-9219-dad69aa702da | note | Responsibility - Surv
b538f08c-0104-5524-b035-0648db232fbd | note | Test Method - Field
4f98f1fa-6f4a-54b5-9861-396450f47579 | note | Conformance Criteria - Areas of work to be set out by surveyor and/or models in plant
7fd90e11-4239-5ae5-b1f6-d92dd61588ac | note | Frequency - As required
cea1e636-bbb1-5c17-b1d7-a6c6b4e0e266 | note | Thiess HP/WP Check - HP
e6df3954-8c47-523e-9c9a-036c5c7a7d0d | note | Inspector HP/WP Sign Off - WP
78e12c6e-590d-4b8c-8cee-4a2451ccdfef | signoff | WITNESS POINT
ccdc3a9c-ac5e-4033-8c3b-ff3b1cb8c838 | checkpoint | EC1.4 - Place, moisture condition & compact embankment fill
cac8963c-7cf9-5eff-8b81-1bef0d83b70e | note | Responsibility - SUP/GeoTech
3617b082-f963-5109-83e7-e68d12666756 | note | Test Method - Field Test
5503e2c0-6737-5ccf-91b7-cf28d197e969 | note | Conformance Criteria - Lightly tyne the subgrade/foundation immediately prior to placing embankment fill.
45b6b68f-e933-5ad8-83b0-7eb3946a126c | note | ○ Layer thickness minimum 150mm maximum 300mm.
466bda59-dc24-50d2-93ff-8affa9feffb8 | note | ○ Density requirements: < 300mm from finished level under roads & structures minimum RDD 97%, all other areas and depths RDD 95%, moisture content -1% to +2%, normal level of testing 1 test per 500m3, reduced level of testing 1 test per 1,000m3.
dce5ac04-f693-509c-a6b3-2ebebcba7c42 | note | ○ Subject to client approval oversized material up to 500mm can be used in general fill at the following depths: 600mm or greater in depth below subgrade for stockpiles, road surfaces and embankments, or 2m or greater in depth below the footprints of structures.
41c0933b-5d94-550d-8cf7-39b243dc4961 | note | ○ Rock fill may be used >600mm below subgrade level.
7d35401b-3418-5cbd-b393-85111554e194 | note | ○ Material containing a high proportion of large particles may be used in embankments using the Mechanical interlock method of construction.Maximum layer thickness 500mm.
46837dee-32c0-53a6-9d17-ff07221c7e8f | note | Frequency - As required
5f766555-e044-53b1-8d65-3f86e6c06f19 | note | Thiess HP/WP Check - HP
d1404653-b3df-5b6b-a697-a65cbf269dc0 | note | Inspector HP/WP Sign Off - WP
ce87cdd3-a9d0-4757-87ac-a2ea0fef9fb5 | signoff | WITNESS POINT
39df1a89-b400-4f6a-b068-a0ce2d3b0a8b | checkpoint | EC1.5 - Trim embankment
b6161dae-c37e-5e66-afec-102e28e5ccd0 | note | Responsibility - SUP / SURV
db15ec6c-0fb7-5015-97ad-7b1db5e7f266 | note | Test Method - Field
50bbc415-a3fc-5d69-aaf3-55b1d84f8d36 | note | Conformance Criteria - Trim all embankment to the lines and levels shown on the drawings in accordance with the following tolerances: Top of bulk earthworks +/-50mm; Road subgrades & under buildings & structures +0mm to -25mm.
3d9fe111-61b0-5165-ad56-3439aaa484d6 | note | Frequency - As required
080e8708-cbfa-5d10-a02b-897d3d617cab | note | Thiess HP/WP Check - HP
10b4ef1c-dad3-53bc-a762-8fbf3aba37a1 | note | Inspector HP/WP Sign Off - HP
2456b688-6f43-425d-b0ac-2af98045b4fa | signoff | HOLD POINT
836357fc-3e4c-4451-a173-3e657eb706b6 | checkpoint | EC1.6 - Proof rolling
e383c7ba-7517-5fe1-b83c-121bf6ce2c2c | note | Responsibility - ENG/SUP
6ef541cc-2c29-50f9-9bbb-66ae1cbd7327 | note | Test Method - Field Test
8d3648f3-7440-5502-8fe1-08b378df709d | note | Conformance Criteria - Proof-roll embankment finished surface under a standard 8 tonne axle load or 10,000L water cart or heavy self propellled smooth drum roller dynapac 620D or equivalent, to confirm that in the Inspector's opinion, deflections are negligible.
90944651-d678-5c95-a7f1-08f0dbe2c70e | note | Frequency - As required
df90c852-a5c1-5852-b384-1ccc0703ed92 | note | Thiess HP/WP Check - HP
45a06049-4ccc-5fa4-8cea-b75345a03dd9 | note | Inspector HP/WP Sign Off - HP
a46f56dd-fd73-4d13-b3b2-efa98fe73ed2 | signoff | HOLD POINT
2056572e-b705-4f91-981b-da286938b639 | checkpoint | EC1.7 - Surface level check and survey pick-up
6a68517f-e29a-540a-a166-b4ed1f6cc0aa | note | Responsibility - SURV
463ad56d-2dfe-5b12-967d-2e9d9176efe6 | note | Test Method - Survey / Field Test
b987ce65-2b06-5023-91f8-ddcef3797e25 | note | Conformance Criteria - Surface level picked up as per Table 10 C15 (DXF file format, volume calculated and filr saved in Construction Team Sharepoint and detailed in register
5e8239db-904d-5e22-863e-bb8645b2ffd5 | note | Frequency - As required
590d7183-81b5-5457-99b3-3ffac96b3b49 | note | Thiess HP/WP Check - HP
a0a0b0f2-922a-5f5a-83f3-21e33d5bcb84 | note | Inspector HP/WP Sign Off - HP
3315d813-4d2a-4914-9e0a-bbdb04f27890 | signoff | HOLD POINT
cd09000b-518f-46ba-8ae5-98753bd77965 | checkpoint | EC1.8 - QA close out
5f98f2d3-89ee-5c8c-b473-d73e0e57bef0 | note | Responsibility - ENG
e350a75b-9841-500c-96b5-73fd23a695e7 | note | Test Method - Visual
864c182e-1c34-5189-b0fc-5df02f7a0727 | note | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR.
163b2fc0-398b-53e7-9368-7252f7f13d9c | note | Frequency - As required
4de988bf-f463-5ec2-ac20-2b34de1ad1ef | note | Thiess HP/WP Check - HP
324c1887-2a4a-596e-a703-e3e18fd31702 | note | Inspector HP/WP Sign Off - WP
361d46ee-d8e9-4f66-b43f-ad76ae5b1f3d | signoff | WITNESS POINT
55c24be9-c984-4bd7-81d3-89feddd065b1 | checklist | EVAMP001-THS-QA-ITP-0009 - Unbound Granular Pavements - Rev0 | itp | ITP-0009 - Unbound Granular Pavements -
| section | Lot Map
| checkpoint | Attach Lot Map
46d83e0e-dc12-4a68-9459-5ee3be0534b1 | section | Construction
e90b2496-133f-49c7-ba1d-1ba090063a24 | checkpoint | 8 - Subgrade preparation under pavements
b5efbf58-6f24-51aa-b1cd-8a40a808c5c3 | note | Responsibility - ENG
bd463d03-d36d-5a5f-9fcc-1f3a159a7c5b | note | Method - Visual/ Field Test
afa132fb-a8e2-5f52-8166-363a3262c99b | note | Conformance Criteria - If subgrade material is less than CBR10, subgrade shall be boxed and replaced with 150 mm of CBR10 or greater material.
c0313e55-d4f0-5b52-be4f-9fb1ff37a0f8 | note | ○ Subgrades shall be trimmed and compacted to within 15 mm of the established grade or cross section.
a8178b11-70c0-5c2b-8a04-00dd1c116b0a | note | ○ Compaction requirement: 98% modified maximum dry density at +/- 2% OMC.
57358ae3-c447-52a4-9cdb-5d4fed2a2bd6 | note | Specification Clause - EVAMP001-THS-CV-SPE-0002 clause 4.3
e9c4e6c1-c8a9-513d-9cd5-c07a15a69407 | note | Frequency - As required
b6e15ff0-6098-5812-b90b-5e1ff88b96b5 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
bc08139d-35da-57ab-9fb9-d938de0020df | note | Verification from Thiess / Inspector: Inspector (Initial) - W
ea481d21-1078-5492-80f5-2499193e4dda | note | Records or Comments - On-site verification sheet and survey
6e638e1a-0c65-4171-a48a-36dccaf756f1 | signoff | HOLD POINT
012ca282-bc17-4fec-9b42-0f59b29e5afa | checkpoint | 9 - Surface level check/ and survey pick-up
e261c866-4567-5bb6-a7a4-e36c54336911 | note | Responsibility - SURV
b78e0250-592c-5367-9ae6-cb7619089881 | note | Method - Survey/ Field Test
16ecfa22-1795-5cb3-8de7-7711f212f7a9 | note | Conformance Criteria - Surface level pick-up submitted to company.
89e40833-5aa4-598a-aeac-16fd6c0a2579 | note | Specification Clause - EVAMP001-THS-CV-SPE-0002 clauses 2.4.3 & 4.3
575cc3e2-8f75-5534-9c4a-1372fc9cf720 | note | Frequency - As Required
b8afebd1-45f0-52bb-9a7d-9735a84ac1bd | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
c5d8aa23-2ef4-53e7-a000-dc9907aa36d6 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
9b59d515-ed0d-4cff-b55d-3b57f235b1be | signoff | HOLD POINT
f936770b-0fb7-41e9-bbff-29045acc5cc4 | checkpoint | 10 - Proof roll subgrade prior to placement of pavement materials
cb57e981-e5be-5d0b-ae44-31f82a44fb7d | note | Responsibility - ENG
cae3068d-9561-504d-a99a-af8dbdc3c2d2 | note | Method - Visual
4131e5f5-6d96-5208-a1c0-093b6ce6e051 | note | Conformance Criteria - Subgrades under pavements shall be proofrolled under a 10,000L water cart or heavy, self-propelled, smooth drum vibrating roller capable of operating in variable frequency modes, to confirm that, in the principal’s opinion, deflections are negligible
719d7803-e45f-5434-9154-4f1c38fab648 | note | Specification Clause - EVAMP001-THS-CV-SPE-0002 clause 4.1
e4eb8375-ee1f-54e0-baf4-529a1e5e62e6 | note | Frequency - As required
2e2ac758-8671-54ee-8deb-a12def31fb68 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
ce3581bd-1a67-5101-b67c-7349f9109bb2 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
ea433efd-3c3c-5d9f-a459-bd0eab525b6d | note | Records or Comments - On site verification/ NATA Test report
6de874a5-dfd1-425a-a9a5-ddfca9053e2b | signoff | HOLD POINT
4ff39ad4-cd45-4054-af08-c9082146dae3 | checkpoint | 11 - Placement of pavement material layers
bda7bdcd-8404-56ad-9ccb-c26c625f181a | note | Responsibility - ENG
aa4ad49d-ea89-5d63-8a32-8057473f8d41 | note | Method - Visual/ Field Test
53ea55b3-3d98-5a69-9d5e-d3366dd912fd | note | Conformance Criteria - All materials delivered to site shall be accompanied by test certificates.
307f0d91-a228-5e6c-aa53-dc638d7b67d0 | note | ○ Each layer shall be free from sticks, organic matter, clay lumps and other deleterious material, and be spread and compacted in a uniform thickness minimum 75mm, maximum 250mm as per the details on the drawings.
dbf74966-4609-5f83-81e9-f68dac6b9d0b | note | ○ The deviation from a 3m long straight- edge placed anywhere on the surface of a layer shall not exceed 8mm.
4abf40d2-100f-59b8-bee1-361f69bc707a | note | ○ Pavement layer thickness tolerances: Base -0mm to +30mm; Sub Base - 15mm to +30mm.
93c1b157-a541-56cc-af78-6bb823498b4a | note | ○ Finished pavement surface level tolerance: Base - 15mm to +25mm
7cfd5b84-843e-57ff-886d-01f73a09756b | note | ○ Horizontal tolerances: Base, centreline/crown - 150mm to +50mm, edgeline/changepoint -100mm to +200mm; Sub Base, centreline/crown +/- 200mm, change point -100mm to +400mm
1c31be9a-9db9-545a-b8e1-f61138d6b4b7 | note | ○ Compaction requirements:
304d7098-32a3-51f5-ae4c-243b354d8d76 | note | — Base & Sub Base 100% standard relative dry density (RDD) maximum degree of saturation 70%.
cf30c101-9f36-5c53-9525-ded178f2af9c | note | — Compliance testing frequency as per table in Specification Annexure A clause 5.
4ff76f21-8058-5b6d-b1ae-09dece7324a1 | note | — Road roughness count rate not exceeding 60 counts per kilometre.
a82a95e8-6e86-5bce-a0e9-3bf4908ece1f | note | Specification Clause - EVAMP001-THS- CV-SPE-0002 clauses 2.4.2.3, 3.1, 3.2, 4.2, 4.4, 4.5 & 4.6, Annexure A clauses 3, 4, 5 & 6
2c3875f0-c1c1-5578-9510-09da2a25e00d | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
bda8bfde-41a3-5de9-8c7e-bac658af2ab6 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
f337eb3f-ff96-5e65-b44e-c432ce54a48c | note | Records or Comments - On-site verification sheet
363bfb20-2bf5-4cfe-970a-ef901db1a558 | signoff | HOLD POINT
fa258a49-c5e1-4ecc-add7-5b29dc35a983 | checkpoint | 12 - Surface level check/ and survey pick-up
9bbfee6a-1459-5ff5-96a6-103687da861d | note | Responsibility - SURV
9bca724d-fa3b-531a-ba39-da27feba2410 | note | Method - Survey/ Field Test
3354da69-840d-5222-910b-35bd811ef2f2 | note | Conformance Criteria - Surface level as per the pavement layer details on the drawings, and all layers as per the tolerances listed in item 11 of this ITP.
a9c4dd31-c2c1-5303-8b74-8c29e5ba228c | note | Specification Clause - EVAMP001-THS-CV-SPE-0002 clauses 4.2 & 4.3, Annexure A clause 6
b980ba5c-528c-5187-8d80-20883603a8b6 | note | Frequency - As Required
dbcf31e9-a488-51f5-ba7d-6d1de6db94ca | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
9dcc539e-2b6e-5ec4-9743-22282ed7934e | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
317e3eda-cc36-551f-a27e-67f0912e655a | note | Records or Comments - On-site verification sheet
6db10bbe-e356-4d9b-a520-f1e06263fcc2 | signoff | HOLD POINT
feaffb7e-b0fd-48c5-a063-44285e2c08f5 | section | Post Construction
7176b8cd-0dd5-4d46-bdb5-58e379a8f32c | checkpoint | 13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
0858cb34-def5-5bd3-a85d-59f0a2427b89 | note | Responsibility - ENG
d016dbe0-5d5c-57ab-a181-6aa65df2fe59 | note | Method - Visual
353a2e21-616d-5221-ac50-c442f1e406ef | note | Conformance Criteria - ITP closed. Approved MDR
b67b0f72-e1d5-5827-b53c-f5a98ed1fc24 | note | Specification Clause - EVAMP001-THS-CV-SPE-0002
8eac9977-4d95-520e-bbc8-c7a76b14daf9 | note | — EVA PMP
da9012e1-247f-59ed-ad10-2ea8ab434d52 | note | Frequency - As Required
781d31cf-2259-5597-951b-eacd442be47e | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
157ad191-6e79-5cb4-8c1e-a95575a15543 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
22051a51-b92e-4fc2-88c0-d14ded556b7c | signoff | HOLD POINT
de1a9e86-ba3a-45c4-ae56-863ba7b3664c | checklist | EVAMP001-THS-QA-ITP-0011 - Bechtel - Clear and Grubbing - RevA | itp | ITP-0011 - Bechtel - Clear and Grubbing
| section | Lot Map
| checkpoint | Attach Lot Map
2f24d350-63a3-41fd-afaf-7c5af8fb2614 | section | Construction
d811d83d-2890-45f0-9a94-14c7e95d41cb | checkpoint | 11 - Clearing of vegetation and removal to nominated stockpile location
f4cb86ec-3b14-5ba0-9b9b-e9d14df07561 | note | Responsibility - ENG
37721023-f0db-58e0-87e8-a2997c191190 | note | Method - Visual
9cf41248-fca4-501e-9751-401cd4c959d8 | note | Conformance Criteria - Spotter/ catcher in place during clearing operations
894639aa-828d-5b34-94d3-adcdb3aefd42 | note | ○ Habitat vegetation, threatened species and cultural heritage areas demarcated
ac4fb978-0f81-569b-9d8e-5f4d406fd4d5 | note | Specification Clause - EVAMP001- EVA-EN-PLA- 1
5edd7166-777e-5404-a825-82c90477aa71 | note | — EVAMP001- EVA-7340-PE- PRM-1
ecd107db-7d27-5ec3-ab9c-c85b224a2565 | note | — C22 of EVAMP001-QVT- PE-PRM-1
16ef6e93-5d01-535c-b8bc-91867fdaba98 | note | Frequency - As required
c1a2e992-1bc1-5a6e-977a-f9531c28dff7 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
db677aac-25bf-54f4-a41d-6242fcab68a1 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
38b2040a-8592-466f-9602-234750ba945d | signoff | HOLD POINT
3fc4852c-4e0f-47cf-9113-f3ac9f50b3d5 | checkpoint | 12 - All Erosion sediment control measures installed prior to construction
ba985687-e6e7-5096-aee0-092f8c9170f4 | note | Responsibility - ENG
1a30e8a4-8a3f-55e9-be0b-c8fe18a79d2d | note | Method - Visual
d628f1af-6c9a-5a88-8258-b172055404e1 | note | Conformance Criteria - All control measures for erosion sediment control need to be implemented after clearing has been completed.
a1c2b93d-d03b-5c2d-9615-ecc700441f4f | note | Specification Clause - EVAMP001-EVA-7340-PE-PRM-0001, EVAMP001-EVA-EN-PLA-0001
63339f53-d30e-5853-b46f-49b4f7326543 | note | Frequency - After clearing completed
528b32d0-9fef-5130-a593-6fde74646f68 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
b44d941a-8867-5c43-b3da-f2725056b372 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
453c5908-845a-459e-b4fb-372e3304b445 | signoff | HOLD POINT
6d1992dc-aaf0-4c1c-b0e5-4d768959bfcf | checkpoint | 13 - Inspection of foundation prior to next stage of construction
69814b75-904c-5dc5-9ee0-9ca3000ba41c | note | Responsibility - ENG
5e3e056b-3882-5afd-b74f-285639d304c8 | note | Method - Field Test
63a29fba-cfb3-58be-9a79-651fba8bbb7d | note | Conformance Criteria - Proof roll where required
644eb386-d00c-5cbf-b8eb-22b29661eb83 | note | Specification Clause - EVAMP001-EVA- EN-PLA-0001
6625a3ff-379e-58db-8314-f74332599811 | note | Frequency - As required
934f1902-62dc-5fff-a676-5f4d8fd41749 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
d44f2ca2-4b67-55a5-855c-4c2570523051 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
33ee32b5-c894-4448-8535-e40b7bf27f40 | signoff | HOLD POINT
b7523562-898c-4916-83bd-cc22c95203b4 | checkpoint | 14 - Surface level check/ post-strip area survey pick-up
146f00d7-5fb4-5c3e-86fd-20e8254ec4e4 | note | Responsibility - SURV
0aa1c7dd-62d9-5cfd-bda9-bdad7ca35a0a | note | Method - Survey/ Field Test
e5276fdf-6489-5c46-a8b4-bcfeb120580c | note | Conformance Criteria - DXF file submitted to Company
afbf4c1a-95ee-5e79-8ff2-6bdfc95914aa | note | Specification Clause - EVAMP001-EVA-7340-PE-PRM-0001
3695a337-712e-5f33-ac31-fafeb5c0b7d6 | note | Frequency - As required
a408d3db-2050-57e0-9932-ff8777d48855 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
3165b394-7235-5ed1-8b19-98dfb5361ce6 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
08bb96f7-abbd-4a58-92e1-94db2aba5601 | signoff | HOLD POINT
16a4aecd-45f2-4dce-a15b-3759c6c72587 | section | Post Construction
7e9fce8b-4d0f-434c-8439-cd8f03f66538 | checkpoint | 15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
dcb67777-edd9-571a-b768-7b13d07878bd | note | Responsibility - ENG
20382013-bdd0-5a93-a85d-ea91eeae9f52 | note | Method - Visual
6935b9cf-4451-5d31-9c24-e82b83767bab | note | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR
1756ba2b-a6c7-5c6f-8ce3-be1df331d0e8 | note | Specification Clause - EVAMP001-EVA-7340-PE-PRM-0001
01749e0e-c939-543e-b146-b9a9257f2d8b | note | — EVA PMP
23ed15e2-cff7-5925-84e6-ff3943273b26 | note | Frequency - As required
c43babbc-2f13-593d-9a6a-53905e6e30f4 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
60dc22ad-75de-580f-8a77-da5bb39bca84 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
06bc5557-62a0-43bb-aad1-eea66ccd37e8 | signoff | HOLD POINT
25d6a019-b9d4-4013-b535-b74c1c884efa | checklist | EVAMP001-THS-QA-ITP-0012 - Bechtel - Topsoil Stripping - RevA | itp | ITP-0012 - Bechtel - Topsoil Stripping
| section | Lot Map
| checkpoint | Attach Lot Map
0a65cfc8-846f-4d49-8237-85977329415d | section | Construction
90579e75-07c0-40db-b677-436b01d9849a | checkpoint | 7 - Stripped topsoil load and hauled to nominated stockpile location
7e422271-4613-596a-9dc0-4364a9fccff5 | note | Responsibility - ENG
4fb12972-881a-5a18-9750-6426df0cc0dd | note | Method - Visual
12105e9e-aeb4-5e1d-a6f0-636a34cdeda9 | note | Conformance Criteria - Stockpile locations located 40m from watercourses and not exceed 2m in height. Native seeding of topsoil stockpiles as agreed with Company. Topsoil stripping shall be to a depth of 200mm or to the bottom of the grass root zone or as shown on the drawings, whichever is the greater
37c07433-6c50-556e-95db-4bb52bada60f | note | Specification Clause - C9 of EVAMP001- QVT-PE-PRM-0001
9a6c68cc-a2ea-56c8-b054-6b70578a86b6 | note | — EVAMP001-EVA-EN-DCR-0002
2abd0ea5-2bbd-5dfe-9067-815bc8df9c16 | note | — EVAMP001-EVA-EN-PLA-0001
1a12c06c-ed04-578e-bdf3-b4824c89f863 | note | — 107501-EB-00000-27280-001 Rev A
dc6be7e3-7bdc-539b-9db9-44796c2be06c | note | — EVAMP001-BEC-3920-CV-SPE-0001 Rev 0
77ba4f7c-5ed2-5769-9c09-2b07f595e5de | note | Frequency - As required
ff0b47e4-001a-51f6-b1c3-6fa449376f40 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
0beaa99a-4767-5732-8d2a-a1547a0b7b4f | note | Verification from Thiess / Inspector: Inspector (Initial) - W
676ba800-130b-45c8-baba-44154397327b | signoff | HOLD POINT
8bc13ab5-87b3-4f98-9ad1-5ab003cbc686 | checkpoint | 8 - Topsoil location, destination and quantity catalogued.
8e545323-c749-58e8-9d20-68056a502169 | note | Responsibility - ENG
7e96687e-0442-5b97-8a12-13ad853e2f8f | note | Method - Field Test
7be9dbc6-05c8-5d9f-ae88-45b36aba056d | note | Conformance Criteria - A topsoil inventory will be maintained with information on topsoil volumes and stockpile locations
26743f42-ce17-5c42-bac7-ef668643d3f3 | note | Specification Clause - EVAMP001-EVA-EN-PLA-0001
0653efb2-685b-51f9-806c-2573035a2bda | note | Frequency - As required
5149dd3b-dcbc-5c9f-b5eb-6e4c2d800dd1 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
84c68a26-a550-5764-bc5d-672e60eb8ac9 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
bbfdd261-f025-4c3e-907f-16cd7feffa48 | signoff | HOLD POINT
401dcbcf-e6fd-4a0d-948a-5d8abbc52cd0 | checkpoint | 9 - Surface level check/post-strip area and volume survey pick-up
7c5ecc4e-6f89-5511-aab9-5baaa777b22f | note | Responsibility - SURV
3bef0e3a-3a7c-5490-9b02-4080824355a2 | note | Method - Survey/Field Test
e9b94fe4-7613-58e9-a603-2e93e685a7e5 | note | Conformance Criteria - DXF file submitted to Company and inventory updated
4c602d0c-5ac1-5f0e-8ef8-1e3acf07179b | note | Specification Clause - EVAMP001-EVA-7340-PE-PRM-0001
203898da-15e3-57ee-b50c-2eae9ec27a42 | note | Frequency - As required
2992b67b-0758-5e28-9a7f-de1dcc6ffddd | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
4437165d-3f81-5598-b12b-ab1988144029 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
d3461d6a-72a7-4686-afb0-a148fa9ad6d5 | signoff | HOLD POINT
250cc13f-93a4-47b1-a374-566f710c73fe | section | Post Construction
c9197ecc-ced5-4056-ac65-12779e809774 | checkpoint | 10 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
eeed2444-7798-5b73-af52-875b5d2db4c9 | note | Responsibility - ENG
78787e50-950d-56bd-a584-cc3ed713d97c | note | Method - Visual
8231646a-cdc3-5813-b5cd-214726360383 | note | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR
fa7e1006-c756-5f28-b02b-c2ab4a5242f9 | note | Specification Clause - - EVAMP001-EVA-7340-PE-PRM-0001
eac0415b-278b-583d-88f1-a648ffa59dd0 | note | — EVA PMP
c9889c3e-2e5f-571a-b92e-69895a5a4396 | note | Frequency - As required
122201a1-46b3-5e8e-a127-983852d5d33a | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
dec22919-7706-5c4d-9043-c358fec671c8 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
d67c2a11-bd1e-489f-9646-f3a5c9cf4f94 | signoff | HOLD POINT
656f4648-5637-4ab5-a76b-575b30a637a3 | checklist | EVAMP001-THS-QA-ITP-0013 - Bechtel - Subgrade - RevA | itp | ITP-0013 - Bechtel - Subgrade
| section | Lot Map
| checkpoint | Attach Lot Map
11cd7a4c-8bc9-495a-9140-78a0b3e5a475 | section | Construction
92326171-9b51-4bc9-bb09-c54d705f5139 | checkpoint | 7 - Removal and replacement of unsuitable material
2427d79a-b965-51d1-bd60-b2958848f8d6 | note | Responsibility - SV
6c52769c-2dbe-5497-a783-8e1f2214a9e6 | note | Method - Visual
0d096bb0-074b-50a8-a36e-57d7fd26caee | note | Conformance Criteria - Where directed by the client’s representative remove and replace unsuitable material and dispose to waste at an approved location or as shown on the drawings.
f735ea9d-2490-5529-b7cd-2f0e6a7fcdfe | note | Specification Clause - EVAMP001-BEC- 3920-CV-SPE-0001 rev0 Clauses 3.5.6 Unsuitable Material & 3.5.7 Disposal of Materials
b114f6a5-966b-5ed2-aeac-ccce1f3ee40d | note | Frequency - As required
920b5f3b-9b1d-530a-a5de-179fffe45329 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
9d0fcfd9-500d-5f92-a1ff-3fde9857fec7 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
3c3a07ba-afed-4582-8517-f3bcc2b84b99 | signoff | HOLD POINT
70baa086-6f6d-4192-9482-d444ba1d0f2e | checkpoint | 8 - CBR values of subgrades under pavements, buildings & structures
626b54b0-a61a-50fd-aef7-7833588a20af | note | Responsibility - ENG
468542c3-0fb0-5e2f-a3ee-355085d2bcf8 | note | Method - Test
b30b47d8-9046-5f3a-9579-af162b9d1c09 | note | Conformance Criteria - The materials exposed at subgrade level of cuttings are to have a minimum CBR of 3.
22f26115-120a-5c36-b795-1d06ebe554ef | note | If CBR >3:
002ad5fa-e8f0-599b-aa8b-0fd81f2213d9 | note | ○ CBR 2 excavate 150 mm below subgrade level and replace with compacted selected fill (minimum CBR 10).
a8270f0c-9b23-5a5c-941e-9e6a0e37add8 | note | ○ CBR 1 excavate 250 mm below subgrade level and replace with compacted selected fill (minimum CBR 10)
12d8546c-bad6-56d7-9c81-65414d9308f3 | note | Specification Clause - EVAMP001-BEC- 3920-CV-SPE-0001 rev0 Clause 3.9.4.1 Subgrade Preparation for Structures & Pavement
ab58eda5-378c-5f06-898d-b9ca50e1d8a4 | note | Frequency - Not Specified
60ada166-1cc3-5c4a-97cf-631075a9061a | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
72bd8e06-ff56-5a61-bd49-05a3526fbddf | note | Verification from Thiess / Inspector: Inspector (Initial) - W
68f05dca-4508-4b7f-988b-56017b8b100d | signoff | HOLD POINT
4cecb3fc-bb6d-4cec-9589-e28008e56bdb | checkpoint | 9 - Subgrade preparation under foundations for structures
a7bac71e-433f-5223-8f18-5fc8809a7371 | note | Responsibility - ENG
f8c9d515-d7bc-5f13-a33e-cb4bc0ce3e44 | note | Method - Test
13df9edc-dc6b-5c5c-a4ca-e5c489b2eb7f | note | Conformance Criteria - Area to be ripped to 300mm in depth, moisture conditioned and compacted to not less than 100% of the maximum dry density (standard compaction)
ff0022e5-a848-55fa-88e5-4677b3feceb6 | note | Specification Clause - EVAMP001-BEC- 3920-CV-SPE-0001 rev0 Clauses 3.9.3 Compaction Standards, 3.9.4.1 Subgrade Preparation for Structures & Pavement
813d9584-bd92-5efb-ab32-100d4aaef856 | note | Frequency - Normal Level of Testing: 1/500m2
35da0f79-0de3-57f4-add3-db11300775af | note | ○ 3/visit Reduced Level of Testing: 1/1000m2
20fab213-ab0e-5331-adf9-8398d41db41c | note | ○ 3/visit
c3619d1d-2ba5-5636-a75a-b920e5931483 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
e3311762-0eda-55be-95f7-f5aa47b5008f | note | Verification from Thiess / Inspector: Inspector (Initial) - W
6e4f1ffd-e268-4ed3-bee3-58fe27b1649f | signoff | HOLD POINT
783e7cae-8758-4cc5-af1e-41e701f9f921 | checkpoint | 10 - Subgrade preparation under roadways & earthpads
ef773d26-a435-5b7c-8a8f-76db9322ac36 | note | Responsibility - ENG
e2d476a9-0a64-56ba-a0da-4cca5df7b2f1 | note | Method - Test
0694ccb8-f2d3-5098-b68a-54fc3bd61d29 | note | Conformance Criteria - Area to be ripped to 150mm in depth, moisture conditioned and compacted to not less than 98% of the maximum dry density (standard compaction).
b7ccedde-fd5d-596a-a742-6975deaf558c | note | Specification Clause - EVAMP001-BEC- 3920-CV-SPE-0001 Clauses 3.9.3 Compaction Standards, 3.9.4.1 Subgrade Preparation for Structures & Pavement
a7ba9984-bf99-5b2b-b8d2-a56ae2f55512 | note | Frequency - Normal Level of Testing: 1/500m2
c145e732-7067-5fef-a6b2-04928bd468f0 | note | ○ 3/visit Reduced Level of Testing: 1/1000m2
4bbe7ec8-4e45-5f15-b1c5-dfdfe9e1bb54 | note | ○ 3/visit
e20c7da6-8ea6-54af-8b9a-53044156e885 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
d84b48dc-f810-5909-b88f-dcbd8c11102a | note | Verification from Thiess / Inspector: Inspector (Initial) - W
b865a038-9f54-43b4-82d6-7de32d3c2339 | signoff | HOLD POINT
82942dd8-5869-4203-85ae-b63928d6495e | checkpoint | 11 - Proof-roll subgrade surface
f3dc636e-df8c-5909-9b42-2c8c666b64cb | note | Responsibility - SV
790c33a1-e444-501a-b60b-feb7193805e5 | note | Method - Test
65cd99d7-100d-5ea1-bcf2-2f817374bec4 | note | Conformance Criteria - All subgrades and foundations shall be proof rolled using a 10,000L water truck loaded to 8 tonnes with dual tyres minimum pressure 600kPa driving at 3- 10km/h. Any areas that show signs of visible movement to be rejected and reworked.
1ac20981-fb8a-5706-a955-a0d53f6c5e4e | note | Specification Clause - EVAMP001-BEC- 3920-CV-SPE-0001 rev0 Clause 3.9.4.1 Subgrade Preparation for Structures & Pavement
2dc91b21-d703-5e71-863c-b882f9a99d76 | note | Frequency - As required
9edc5b39-06c1-536f-bf54-7f19c138a54e | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
d9976906-67d0-5e89-9b95-57aed80ad293 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
d3bb97ea-fb0e-4bb4-a44c-f55818d68f4c | signoff | HOLD POINT
100bb891-bf81-4445-ad9d-ea972d1d0938 | checkpoint | 12 - Surface level check/ and survey pick-up
ea8ca583-9929-5460-a5a8-039d91c904f1 | note | Responsibility - Surv
a435ae5d-2347-530d-a408-a1a961eac202 | note | Method - Survey/ Test
299737f5-ddcc-5c96-be05-f8bf0c4a947f | note | Conformance Criteria - Vertical Tolerances: General Earthworks +/-25mm
535aeef5-aec9-5e92-95bd-20c1d03bf801 | note | ○ Road subgrades, buildings/structures pads -25mm to +0mm Horizontal
17e3d75f-0486-50f3-bcba-dbbe9b8895c6 | note | ○ Tolerances: Road width -0mm to +250mm
bd31d2f6-851f-54da-adb7-d24074742c29 | note | ○ Trade Tolerances: Road +/-0.25% Pads +/-0.25%
dbd6a64b-f9ee-5666-af8b-c8abc018dca4 | note | Specification Clause - EVAMP001-BEC- 3920-CV-SPE-0001 rev0 Clause 3.11 Construction Tolerance
2ad07982-25be-5078-9833-2c1795cd9626 | note | Frequency - As required
6e4c790a-c703-5791-ab86-c211569f6b9f | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
df5d36a5-facd-5eaa-a02d-ee9dfd43ebc0 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
b269b6d7-730f-416d-aac3-fb924dec5233 | signoff | HOLD POINT
c15fa9bb-9e18-4678-b244-5b5067bbb7d5 | section | Post Construction
6cdd6b2b-5515-4c73-98e7-f722be38db77 | checkpoint | 13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
9b337e38-ce21-5fd3-bfec-4c5d25315262 | note | Responsibility - ENG
6c3083b4-b2e0-55ac-8e7d-4b836206d302 | note | Method - Visual
4bf31dd0-958a-5745-b660-ad80b11b5546 | note | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR
948efb76-2b53-5f0e-82e5-56bda3da406f | note | Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 rev0
bc58495e-90e4-5b36-a421-3c43cd678939 | note | — EVA PMP
97fcb727-658e-5673-b966-f9d3f7c182e5 | note | Frequency - As required
791b7ba8-f666-5188-81e9-9dc8999bd041 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
fe9f724d-1324-558c-8206-06ada0643994 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
4709d168-7835-48da-9fbd-9db97c4af697 | signoff | HOLD POINT
f7cdde62-7fe5-419b-b18d-3a926be43d98 | checklist | EVAMP001-THS-QA-ITP-0015 - Bechtel - Embankment Construction - RevA | itp | ITP-0015 - Bechtel - Embankment Construction
| section | Lot Map
| checkpoint | Attach Lot Map
753cce53-9e64-4b7e-901a-ef9c0cbd2169 | section | Construction
98784bd4-0382-4a0c-a52f-87052e930f67 | checkpoint | 5 - General Fill Embankment Material Properties
f1041bf6-9a45-5463-8a05-b3ee8681f5a4 | note | Responsibility - ENG
7046b142-cf37-5511-a3dc-dddcd116053c | note | Method - Test
6515a4b2-94c6-56d7-ab88-2d12c8f1aeda | note | Conformance Criteria - Class A:
bedcb04c-9f60-5f71-b411-2972c849e45e | note | — WPI < 1200
18aebbe9-7fe2-5df5-a475-f91e89fb8aef | note | — PI > or = 7%
30f44429-eb52-57ee-a327-68a87de23145 | note | — % passing AS 0.075 sieve 15 - 30%
ffd5686c-babc-59dd-858f-9f65d5c40848 | note | Class B:
8a9bb921-90de-54ba-b5a2-94eb2d680ed4 | note | — WPI 1200 to < 2200
936971a3-1f93-5d24-8f67-fd67613c466d | note | Class C:
5cf94440-613e-5d1d-b923-c4a373d20ba8 | note | — WPI 2200 to 32200
3449eb6a-2f2c-5f67-8c89-9f718c4e2c10 | note | Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 Rev0 Clause 3.8.2.1 General Embankment Fill
1f8324d5-24b6-5d58-bffe-924e05cf7189 | note | Frequency - 1 test per 5,000m3
be3b4349-8c91-538c-98b0-c8271d06f981 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
b32cecbe-7bef-5a14-855b-f4e716e90a1a | note | Verification from Thiess / Inspector: Inspector (Initial) - W
c1c54fcc-bbd5-5b6c-89da-558b18b8e6e7 | note | Records or Comments - NATA Test Results
2cd18a11-fd0f-4fd4-aa8b-0c433b481156 | signoff | HOLD POINT
20fb2254-ee87-481a-a627-c15e1414969b | checkpoint | 6 - Select Fill Embankment Material Properties
d7a15999-e99d-57f5-aab6-d2d931d8f4da | note | Responsibility - ENG
a4ac7ee3-e952-5c0d-9a5c-6b2fa69069ea | note | Method - Test
d8b2acc1-e0f1-57ed-ad64-cfd9ec38860a | note | Conformance Criteria - Select Fill Material:
d51404c9-dd00-5577-9e68-c5b712fdcb2a | note | — CBR > OR =15
17a3c0c2-3569-541e-a61e-4da60919d52b | note | — Max. aggregate size: 40mm
54f94931-0d60-5267-8d09-2152244c2e10 | note | — Linear Shrinkage: max. 7.5
73919ddc-738e-50a1-adff-1b8de15d8da2 | note | — Liquid Limit: max. 40
47a7be1e-8ca6-5bfd-97b5-d30895f22c17 | note | — Plasticity Index: 4 to 14
6a7798bc-4add-5f6e-abc6-ea0662530d87 | note | — Weighted Plasticity Index: < 560
da6ffa10-babb-5097-9a78-678cb527bb78 | note | — Swell < OR = 0.5%
2923fe1a-0470-5720-b09c-a287e3772db9 | note | — Particle size distribution as per Bechtel EW Specification Table 3-6: Select Fill Particle Size Distribution Envelopes
d409d0d4-9dab-50ce-9251-12d5906ea7ec | note | Specification Clause - EVAMP001- BEC-3920-CV-SPE-0001 Rev0 Clause 3.8.2.2 Select Embankment Fill
f8fc0cd5-6a38-51a1-a394-94d8b5495401 | note | Frequency - Site Won Material: 1 test per 1,000m3
4e44ece0-2004-5c8a-9269-f340f7811ded | note | ○ Quarry Sourced Material: 1 test per 2,500t
de57b39c-bd59-5c1e-a3c7-f8b2eda663e6 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
01335961-e501-5c2e-909b-383a736c7004 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
3dfdc853-b615-5b1d-b662-6c8b7ed69fd6 | note | Records or Comments - NATA Test Results
52df0f59-55e0-4061-b233-71c5b7f264a9 | signoff | HOLD POINT
c75ec0c4-4b6c-4f9b-a356-90c1aba27cbf | checkpoint | 7 - Structural Fill Embankment Material Properties
8dbdd9f1-d640-5ecc-a973-ddcd5941433c | note | Responsibility - ENG
5425bb56-39de-531b-a2e0-01832d13f4df | note | Method - Test
5b198bea-3855-5435-9898-13946355583e | note | Conformance Criteria - Properties of Coarse components (any component retained on the AS 0.425mm sieve) Type A & B:
c708013e-b110-5521-b007-be2720732ed1 | note | — 10% fines value (wet): min. 85kN
271023d6-b540-589d-8f3e-51e6c9002bfd | note | — Wet/dry strength variation: max. 35%
82efda49-33cb-55a3-922f-904928ffcc48 | note | — Washington degradation: min. 35
de6b66df-854b-57c9-8afa-de0d6744a055 | note | — Flakiness index: max. 40%
cec12b17-6b1e-5d85-8ae4-02b7c408712e | note | Properties of Fine components (any component passing through the AS 0.425mm sieve) Type A:
eecf2c64-578a-5900-95cc-4e1112bf525a | note | — Liquid Limit: max. 25%
99d6eff7-2bf3-56d1-a383-095e7f1fa854 | note | — Plasticity Index: max. 6%
94b5442e-1f3d-5ec4-ac3a-1e5cf8906127 | note | — Plasticity Index x % of whole sample passing the AS 0.425mm sieve: max. 150
56089b95-8e8f-504a-8aeb-00b96309d186 | note | — Linear Shrinkage: max. 8%
9f10c0e5-ec9a-5584-a3b0-1a6775c11504 | note | Properties of Fine components (any component passing through the AS 0.425mm sieve) Type B:
ef6e3b1c-5491-5997-9059-01e3b14e5c03 | note | — Liquid Limit: max. 35%
33ce4acf-a246-5fc2-99d5-ea3d819026a4 | note | — Plasticity Index: max. 12%
a6bdafdb-3d85-5998-a062-6d04eddf5b5b | note | — Plasticity Index x % of whole sample passing the AS 0.425mm sieve: max. 360
7378c11c-f97d-50cb-81ff-bdaa35d09030 | note | — Linear Shrinkage: max. 8%
c2d0ce34-2b21-5f09-9ae3-e24ba64cfd25 | note | Particle size distribution as per Bechtel Specification Table 3-11: Structural Fill Particle Size Distribution Envelopes CBR
2a67822a-b51d-5937-a1ea-9af7ead85055 | note | — Type A: min. 60
8f8a1dfb-29d3-5614-b74d-83a7571272d3 | note | — Type B: min. 35
ff7546b2-d4ef-5100-8ae4-c4f42f375707 | note | Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 Rev0 Clause 3.8.2.5 Structural Fill
2da6f537-7629-5fa2-b784-185a88061665 | note | Frequency - Particle size distribution, Liquid Limit, Plasticity Index. Minimum testing frequency: 1 test per 1,000m3, and 1 per work are and 1 per change of material.
67f956eb-cd03-52ae-9d7b-65be2c702429 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
700e5161-4e9c-5390-9809-002038354598 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
c3791cf7-2529-5d3c-b0d9-ccb370ea8d93 | note | Records or Comments - NATA Test Results
b5c821b1-3a34-47d4-be3d-e356ff4950c8 | signoff | HOLD POINT
68004e7a-5a94-40c0-ae1c-f6df31370430 | checkpoint | 8 - Lined Pond Embankment Material Properties
652e974a-6e82-5a35-bad2-62ac8c434f35 | note | Responsibility - ENG
1a4ba9ba-9e74-5c52-a335-240b1b27306c | note | Method - Test
3128990b-3407-5e55-825c-441146910f46 | note | Conformance Criteria - - % passing 37.5mm sieve > or = 80%
7be52f67-b2ca-5fe4-8217-888f3fd3c35e | note | — % passing 0.075mm sieve > or = 30%
6e7435d7-a505-5f32-bd58-6d070c0d9401 | note | — Maximum particle size 125mm
63d9cc26-3ce6-526d-a3e0-5928559dcbc0 | note | — Plasticity Index > or = 7%
cc7b36be-d1bf-5c3b-b28e-dc4f8bf0db93 | note | — Liquid Limit 20 to 50%
dad3e485-c95a-55ea-ac5d-8503b15daad6 | note | — Emerson Class > 3
206b14ba-2408-51ac-9758-6857b351cfda | note | Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 Rev0 Clause 3.8.2.6 Pond Embankment Fill
f10f179d-3b15-59f8-b93d-fb841e9d8198 | note | Frequency - Not specified
43582e10-dbb1-5df2-8692-f61c36c3d59c | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
1cda9134-a082-53b6-a144-acd63c5fe86d | note | Verification from Thiess / Inspector: Inspector (Initial) - W
22961ca0-82cb-533b-a97a-b11a1f857be4 | note | Records or Comments - NATA Test Results
c5a8952a-fe57-4e62-b523-dd75359192c1 | signoff | HOLD POINT
47a6392b-99f8-43a2-8138-de13a9e3a4ca | checkpoint | 9 - Remove & Replace Unsuitable Material (as directed)
46b08832-f6cd-55c4-85f6-11b66eb45f0c | note | Responsibility - SV ENG SURV
570a1ecc-2d5e-5d0c-b6b9-fb3730952a36 | note | Method - Visual & Survey
6211d747-c519-55a7-a703-89d02a67d857 | note | Conformance Criteria - Where directed by the client’s representative remove and replace unsuitable material and dispose to waste at an approved location or as shown on the drawings prior to placing embankment fill.
63b425aa-89f1-59c6-bbc5-c1befe77ad1c | note | Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 Rev0 Clause 3.5.6 Unsuitable Material
4d74e0ff-5f0a-5692-b6c3-82c82ec1065f | note | Frequency - As required
d85503b3-848a-504e-bc84-cc901e0717ad | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
bd4b7e17-6b72-5b83-8987-f3b7ec0e38c3 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
9c36eba3-0060-5930-8f06-c98dfb5a6554 | note | Records or Comments - Survey Records
693518ad-1743-4f06-8117-6c0044cd6f08 | signoff | HOLD POINT
77c58a38-2570-468a-b15c-c70df79d8359 | checkpoint | 10 - Subgrade Preparation Under Embankment Fill
e7929635-fb10-5c46-a5a0-cb70b83c8489 | note | Responsibility - SV ENG SURV
22a17cb9-6050-569c-b623-43783d0ee679 | note | Method - Test & Survey
9d12ae61-bab5-56aa-af08-fc8ccb64776d | note | Conformance Criteria - Natural surfaces under embankment fill shall be tyned, moisture conditioned and compacted to a dry density ratio of not less than 98% standard compaction.
aebf3c3f-e924-5d4f-b541-f65f9a03905f | note | Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 Rev0 Clauses 3.8.3 Preparation of Natural Ground & 3.10 Testing
5389716f-5972-5bf4-88bc-eb3254f8a2c7 | note | Frequency - Normal level of testing minimum frequency: 1/500m2 & 3/Visit
f957fb3d-80ec-5297-94a2-be9ecfd7559b | note | ○ Reduced level of testing minimum frequency: 1/1,000m2 & 3/visit
4397353f-3944-5b74-a43f-7a087e832f8a | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
892229ea-97d9-5b8d-84e1-6b7073752a00 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
0d89d0b4-8d3a-595e-8261-dd49484f0ee0 | note | Records or Comments - NATA Test Results Survey Records
8b1aeaa9-6749-4f31-8be2-45b8e7062e16 | signoff | HOLD POINT
089529f6-b3e0-40a9-a781-7fc68738e351 | checkpoint | 11 - Embankment Construction, Layer Thickness, Placement & Compaction
36b5afd2-dabb-54c9-a329-53d8ecf12f03 | note | Responsibility - SV ENG SURV
31349fc9-4aa6-5e01-9d76-2187f5852382 | note | Method - Test & Survey
11ced718-c8a2-5212-90ae-1b8b2e4221db | note | Conformance Criteria - Depths of layers shall not exceed the capability of the proposed plant and in any case shall not exceed 300mm uncompacted.
876fa021-73a5-5669-b698-ad392e73a708 | note | ○ Layers in the top 300 mm below subgrade level for foundations, including the foundation of generators in Independent Power Provider, shall be compacted to not less than 100% of the maximum dry density (standard compaction) with moisture content +/- 2% of OMC.
e7f2a4e7-09f7-52b6-8a73-f22c7b458bb9 | note | ○ Layers for Earthpads, the top 150mm of Road Embankments, Foundations in the top 300mm below subgrade level, Pond Embankments, and the Crushed Ore Stockpile to be compacted to 98% of the maximum dry density (standard compaction) with moisture content +/- 2% of OMC.
4b9411b5-924f-5d6d-a5e8-0131a7845d6e | note | ○ Fill material other than that referred to above shall be compacted to a dry density ratio of not less than 95% of the maximum dry density (standard compaction) with moisture content +/- 2% of OMC.
4c52c895-d18c-54b0-8027-865c351366b2 | note | ○ Rockfill or mechanical interlock method shall not be used in areas proposed for buildings and other structural works, nor within a zone 600 mm below subgrade level for road embankments. Minimum thickness of uncompacted layers: Greater of 150mm or 1.5 times the max. rock size. Max. thickness of uncompacted layers shall not exceed those nominated in Table 3-14 of the Bechtel EW Spec.
7c102a44-c806-5dd0-b5d8-29911b404752 | note | Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 Rev0 Clauses 3.9.3
cf840c49-fa25-587a-8b47-514b01433d59 | note | ○ Compaction Standards, 3.9.3.1
312044d2-26d8-5302-a990-5f46e38f547e | note | ○ Compaction for Embankment (Compacted Layer method), 3.9.3.2
852c38bb-2726-5051-9dea-93ce11929c6a | note | ○ Compaction for Rockfill (Mechanical Interlock Method), 3.9.4.3
25646b71-bd21-550a-9846-a66765dce219 | note | ○ Compaction and Moisture Content & 3.10 Testing
d4f8e9d0-6dde-50e1-9ad5-2b049e08711e | note | Frequency - Operations >5,000m3:
a2cfca9d-e1cb-5ab5-bc8c-754da8e92eb5 | note | — Normal level of testing minimum frequency: 1/500m2 & 3/Visit
e7af93cd-22f9-5dbf-84a2-9c9b4d12ec02 | note | — Reduced level of testing minimum frequency: 1/1,000m2 & 3/visit
8d770a56-77ab-5e79-8d6a-b13bc3823291 | note | Operations 500m3 to 5,000m3:
d673a667-e3fc-5946-8d80-f6c89e1df32a | note | — Normal level of testing minimum frequency: 1/500m2 & 3/Visit
a6bcf9ee-b5b9-50ec-9265-8c9c1c4a48ed | note | — Reduced level of testing minimum frequency: 1/1,000m2 & 3/visit
fe7edf22-d408-5743-b44f-0b121c3fa258 | note | Operations <500m3:
8a436bc3-06db-5147-8922-631f5ae2b03d | note | — Normal level of testing minimum frequency: 1/500m2 & 3/Visit
d9fd3706-b860-552b-947e-02b2f713214b | note | — Reduced level of testing minimum frequency: 1/1,000m2 & 3/visit
1ec02359-5853-569b-8470-067dd1619bf7 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
5217ce51-be03-5b8e-a91e-339493ca3667 | note | Verification from Thiess / Inspector: Inspector (Initial) - W
890971ef-9856-55ec-bdd2-54b4fefc5a0e | note | Records or Comments - NATA Test Results Survey Records
6a9981fb-6860-48ed-9e9d-b6f4ed97ab27 | signoff | HOLD POINT
42c52a21-5b3f-4308-bead-86ac132e5d7f | checkpoint | 12 - Subgrade Preparation Under Structural Fill
74f47184-62a0-583d-b938-3d2af03162ad | note | Responsibility - SV ENG SURV
e596d302-3daa-5ee1-9a9e-7deffb1eee72 | note | Method - Visual & Test & Survey
13f3aa9e-88b6-5b48-8d41-6a6ccd1e4f49 | note | Conformance Criteria - The top 300 mm below subgrade level for foundations shall be compacted to not less than 100% maximum dry density (standard compaction).
a2800b3d-881e-5348-a52a-6bcf0af17239 | note | For subgrades under pavements and buildings / structures, the materials exposed at subgrade level of cuttings are to have a minimum CBR of 8. Should the CBR be less than 8, the following subgrade treatments shall be applied:
2b4dfdf2-5efe-5b25-8663-723c8b41df78 | note | ○ CBR 2 to 7 – excavate 150 mm below subgrade level and replace with compacted selected fill (minimum CBR 10).
e14275eb-5106-511d-b026-b2ec46bb32ee | note | ○ CBR 1 – excavate 250 mm below subgrade level and replace with compacted selected fill (minimum CBR 10).
22509fe0-3782-535a-b593-1332f5617ba4 | note | ○ Proof rolling of the formation which is to receive structural fill and pavement structure shall be witnessed by a civil/geotechnical engineer to ensure that no soft spots remain in the compacted subgrade. Any areas that show signs of visible movement under the rear axle of an on-highway type 10,000L water truck will be rejected. The rear axle of the water truck shall be loaded to at least 8.0 tonnes and fitted with dual tyres. The minimum tyre pressure of the water truck shall be 600 kPa and the testing shall be conducted at a speed in the range of 3-10km/h. Both the Company and the Contractor’s representatives shall walk alongside the testing water truck to observe any surface deformation.
e6bb1d88-65e6-5be8-abab-e0a909184c0d | note | Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 Rev0 Clause 3.9.4.1
8397a525-ef3d-588a-827b-c8d41c464262 | note | ○ Subgrade Preparation for Structures and Pavement, 3.9.4.3
f6b51cd7-2a85-5224-9cb3-0e954c961081 | note | ○ Compaction and Moisture Content & 3.10 Testing
8271590e-cd7c-5b11-b17c-82b78aa05ea8 | note | Frequency - Proof roll as required
da194a42-bd43-5c38-9a3d-af1c74c76e83 | note | ○ CBR testing frequency not specified
da76b1aa-e6b6-5861-b943-d93d9c10e111 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
0bdffdee-5b50-5e1d-b32e-8bb8eee2433a | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
0d1ce40e-3c0e-5970-8eb0-4ba520e937c3 | note | Records or Comments - NATA Test Results Survey Records, Visual Inspection Record
2091f869-1121-4a3e-8b2e-acfb7dd83460 | signoff | HOLD POINT
546f679e-a78d-4063-9165-b8fc8e5032af | checkpoint | 13 - Structural Fill Construction, Layer Thickness, Placement & Compaction
5fff39cd-38d8-5a44-b2ec-a222e8a45cb7 | note | Responsibility - SV ENG SURV
bf4dff2f-8c17-558b-8a05-5536998dbb90 | note | Method - Test & Survey
59235499-6521-51c1-bad5-8f9bf60ac2ff | note | Conformance Criteria - Depths of layers shall not exceed the capability of the proposed plant and in any case shall not be less than 75mm or exceed 200mm uncompacted.
58088ca2-e972-5195-aab7-d018dece1704 | note | ○ The top 300 mm below subgrade level for foundations shall be compacted to not less than 100% maximum dry density (standard compaction).
5306934d-0900-57d7-a87b-5d40814113d1 | note | Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 Rev0 Clauses 3.9.4.2 Layer Thickness for Structural Fills, 3.9.4.3 Compaction and Moisture Content
92270603-595b-5784-8485-c75c283ca989 | note | Frequency - In-situ Density, Maximum Dry Density(stan dard compaction) & Density Index Minimum testing frequency: 1 test per 2,500m2 or 1 test per 500m3 distributed evenly through the full depth and area, and 2 per work area, and 1 per change of material
a1cad3ee-1320-5005-8695-33a64d4041f0 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
6819444d-130a-5d64-b5d1-d0f504f1e03e | note | Verification from Thiess / Inspector: Inspector (Initial) - W
10140b64-1f64-5031-af9c-6cf00bf089ce | note | Records or Comments - NATA Test Results Survey Records
6ae0ebb8-d9c9-49b2-8723-f5b762ab4c7f | signoff | HOLD POINT
198ca9e3-bb7f-4121-8f7e-103cb13fabeb | checkpoint | 14 - As-built Survey of completed surface
55e91c5a-caf1-5928-bcba-7b9caced341c | note | Responsibility - ENG SURV
bc4c74f9-43f2-5082-a1e9-734ef47843ea | note | Method - Survey
95d1b725-d472-50ad-9799-53941fa595b8 | note | Conformance Criteria - Survey to be completed of the finished surface to confirm construction as per the lines and levels shown on the drawings in accordance with the following tolerances:
980eedf1-d6db-5e68-a16f-b9d1e80f7ba6 | note | Vertical Tolerances
907ba466-558e-5865-a187-2bc60c748127 | note | — Road subgrade & building/structure pads: -25 to +0mm
e37a8010-9c69-54ec-bace-eb54cf650300 | note | — All other earthworks: +/-25mm
8f5eb17a-3ad8-5b4f-a404-1a5103d8b592 | note | Horizontal Tolerances
88d76030-0f67-5de1-92b4-779ced194cdc | note | — Adjacent Structure: As per the structure
1a3c8af4-c18d-5335-bb68-374eb55a2444 | note | — Not adjacent structure (apart from those listed in Section 3.11.1.1 & Section 3.11.1.2 of the spec): -50 to +150mm
f0b4931f-8c55-5063-90ca-c39ecde12bf0 | note | — Substructure concrete to be placed directly against an excavated vertical surface: -10 to +50mm
b2785589-b2cc-590b-844e-228fdd8076c7 | note | — Road width: -0 to +250mm
a76385df-a037-57ec-ac3e-070ad032f63c | note | — Open channel: -0 to +50mm
dd8994d4-a746-5979-8432-d2ed25874e07 | note | — Any point on earthworks surface except any of the above: +/-50mm
3ae9fae2-e9e3-508e-bf42-664d80f040fd | note | Grade Tolerances
41ad11c6-0ccf-5cfb-bc52-5ddcc4037d72 | note | — Roads & Pad/embankment: +/-0.25%
9a07a693-6e3f-5fc3-851b-3101e9572f1e | note | — Open Channel: +/-0.1%
0cc8a653-7af9-5b0f-af07-54c94b9f9b4e | note | — Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 Rev0 Clause 3.11 Construction Tolerance
6c655b66-2e2d-54a3-8f74-9703372e6a2b | note | Frequency - As required
993ae368-cc0d-5a29-8e02-f40663002c50 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
0491a8fd-361a-53fc-b181-09bdc4c9e4d6 | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
4c2c0f07-3e11-5e93-8e0e-173ef1150744 | note | Records or Comments - Survey report
80f7ba23-8373-4c53-bd0a-a5f1832ccaf2 | signoff | HOLD POINT
d7649926-801a-455a-ba0c-aa7da6963cdd | section | Post Construction
709384c9-4edc-44f1-81ab-9e7ffb64e940 | checkpoint | 15 - Works completed and updated ITP/ Lot Register/ MDR and close out of GDP
a5f68433-6b38-5430-bf51-863262cac902 | note | Responsibility - ENG
8ed83eca-58e9-5a85-9391-a036ae784e02 | note | Method - Visual
989cb6f1-366b-5c46-8721-021c06874233 | note | Conformance Criteria - ITP closed. Approved MDR
bd7951c6-ba04-5933-846e-9fa8d6763795 | note | Specification Clause - EVAMP001
8e02b7f4-e135-57a9-9090-a22ceb1c993b | note | — EVA-7340-PE-PRM-1
9d38d435-a540-574f-900d-dd6b8c0664c2 | note | — EVA PMP
8078ed9d-f5d3-5a1b-a215-39029d0a96c1 | note | Frequency - As required
ebab9f8f-0797-5a3e-9b3b-0d9483983526 | note | Verification from Thiess / Inspector: THIESS (Initial) - HP
db331757-197d-5f39-b246-5a9280775f6c | note | Verification from Thiess / Inspector: Inspector (Initial) - HP
e292418e-3ff6-428c-9fb6-fb29f59f044a | signoff | HOLD POINT