## Master List Templates
Id | Type | Name | Values | Prompting Name
65334946-7ad1-40ae-94fa-2e6946071ac2 | checklist | Upload Attachments |  | Upload Attachments
6da6f498-e18e-4121-84fe-5cd5ddfb8d03 | section | Details
abd1894c-f4ca-4bd7-adb7-c536eb29dab6 | checkpoint-no-value | Upload Attachments

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
55be814e-699b-401a-ab1f-2e3806f722ed | checklist | ITC Concrete Prepour |  | ITC Concrete Prepour
18ae093f-961a-4b30-ac06-a21765776f50 | section | Preconstruction
07fe3545-88b9-46f4-a9a9-496678e1a7fd | checkpoint | Design Drawings
ad79bc40-20fc-5b82-ae45-f22e762bb3f0 | textbox | Contract Name
7ba732ae-0f0c-5b0a-bb16-48c7d5a62f8e | textbox | Contract Number
5655a817-f105-5320-a5d0-10ef087ff3f2 | textbox | Location
e87beb6e-5e70-505d-a67c-e9702a032ccf | textbox | Lot Number
be2df4b2-3867-54d4-9c76-515426976e7b | textbox | Description of Pour
32a0a760-a5fd-4043-bd22-7343b34c1d4d | checkpoint | Issued for Construction Drawings available
2a35db19-8420-4e17-86a6-451ee28da8fe | section | Construction - Formwork
ffafc235-cc5b-4b4c-b596-77429a985ed1 | checkpoint | Formwork/ Moulds Braced and Secure
6c3e476d-b56f-49ea-bbbb-43876c945d20 | checkpoint | Dimensional Check Completed
6db6f02c-ae4d-4b1f-9e87-c26e8bfcc5e0 | checkpoint | Formwork/ Moulds Within Tolerances
7dcb7661-4775-4d0e-967b-b31f2e642bcd | checkpoint | Formwork/ Mould Surfaces in Good Condition
570eae87-c85f-4d26-bf49-95eccdf1f60a | checkpoint | Chamfers in Place as Per IFC/ Shop Drawings
c918645b-85fc-4b07-9993-cf1a0ccdc836 | checkpoint | Formwork/ Mould Release agent Used
2f493b0f-fd8b-4b24-bee7-641508f0378e | checkpoint | Construction Joints Allowed For
c22768f9-ad06-45e9-b4fb-a5c81acc9a28 | checkpoint | Penetrations Set Out as Per IFC/ Shop Drawings
a8d0a3fd-c6a5-47f5-a662-f6ff0af5dc2e | checkpoint | Cast In Hardware as Per IFC/ Shop Drawings
f1371236-f31e-4375-aeee-0817fb6526e0 | checkpoint | Surface Finish Meets Specification
bc09ac3d-d7d6-4f75-afac-bc34f935fbb2 | section | Steel Reinforcing
83065cb2-0e71-428c-bab6-f02e3ee21924 | checkpoint | Reinforcing Braced and Secure
5235ec19-d65e-4807-a274-55cb3259fc2b | checkpoint | Dimensional Checks Completed
de73dc2c-2e38-4df7-9c32-5d7cfb30a394 | checkpoint | Bar Diameters as Per IFC/ Shop Darwings
5391507f-6367-4926-956a-5a7b853928e4 | checkpoint | No. of Bars as Per IFC/ Shop Drawings
17dbc865-5366-4499-a9bf-8af67ecfee08 | checkpoint | Bar Spacings as Per IFC/ SHop Drawings
6a5b52d4-2e94-4906-91f3-ea9ce7a7035e | checkpoint | Cover as Per IFC/ Shop Drawings
1d28f494-17fd-449a-84f9-5a045ed972bd | checkpoint | Lap Lengths as Per Specifications
b628de2f-0bb7-4669-8984-e2c0a5da8c7e | checkpoint | Lifting Hardware as Per IFC/ Shop Drawings
bda3b6fb-8d7f-4ffd-a7a3-73f1e911a8bb | section | Concrete
eae9b56a-92f1-4e68-afc8-37c82b4a2fd5 | checkpoint | Concrete as Per Approved Mix Design
9008fc51-1e6e-54c6-aed7-0e2cdce716d8 | textbox | Strength Required
1e68906a-8c38-40b7-9994-416f552cd5b3 | checkpoint | Slump Tests Undertaken
b1446900-a82e-4ff6-97fb-92c9b4a4c146 | checkpoint | Test Cylinders Taken
72058e83-45e6-443b-83cf-19cbab4ed647 | checkpoint | Surface Finish as Per Specifications
9f9b02c6-e122-45ec-9f9b-3ec61ff14cb8 | checkpoint | Construction Joints Allowed For
d954484b-84f1-4283-be30-4b52083e5bcb | checkpoint | Additional Curing Measures Required
c997d8cf-d8ca-424c-9406-6df45708e18e | checkpoint | Client / Engineer Inspection Required
a65ba7d2-5c60-4e52-84e0-55dba8fbc220 | section | Pre-Pour Checked and Accepted
7aae1331-dfc1-49ef-af0a-319aa843271b | checkpoint | Prepour Checked and Inspected
2431a6db-b9f9-5ac6-b52f-832b63c5d150 | date | Date of Inspection
64641d9f-8d88-4151-968c-7b60de75e02b | signoff | Holdpoint
bd70e0b5-df06-4d75-8980-088efc9c4c3e | section | Location & Contract Details
b2c8818e-7b7c-411b-be4d-683e6fd33b4e | checkpoint | Contract Details
468c646f-4207-5487-ab89-88941ca51781 | textbox | Contract Name
94039afa-bfa1-5f94-bdf3-61226ee3b1cb | textbox | Contract Number
ec302ea0-2870-46a8-9bf2-41e6566c333f | checkpoint | Location
0c616e01-641c-5864-867c-e4323a850d89 | textbox | Location of Works
0eccac14-f8d2-5f5b-a594-525ed439141a | textbox | Manhole Number/Identifyer
14c7a630-6f8f-4528-b868-737f1ef1326e | checkpoint | Manhole Details
0162a8b3-bac9-5b62-84b3-59a6d2f1e34f | textbox | Manhole size
0235b489-e81e-5602-a64f-4da0f02c483d | textbox | Lid Thickness
5a2a50b4-9332-4ba2-8bd0-b3efa35f9271 | section | Manhole Installation
618b40ae-8da2-468f-ad0f-bb8279d5d2fe | checkpoint | Survey setout completed including RL
10e8428e-a3da-4c41-8450-25192bf1e2c9 | checkpoint | Offsets by drainlayer checked and correct
863933a0-6a48-4f5a-bacd-500ed66b748b | checkpoint | Excavation completed to correct depth
ac549184-5ad9-4a7c-8f36-56acda99b843 | checkpoint | Subgrade meets specification
b94d1dcc-110f-4bcc-9092-69de7d81105c | checkpoint | Hardfill layer installed and meets specification
d14401c2-d0b8-4d06-9fca-1ca27cfead40 | checkpoint | Blinding placed to correct level
859142af-23df-447c-9476-137b9d9113bb | checkpoint | Manhole horizontal position within tolerance
b617435a-7498-40b5-b5b3-229be0831cc5 | checkpoint | Manhole verticle position within tolerance
f873be2c-6033-46a9-882e-d09864ed7092 | checkpoint | Manhole installed plumb and within tolerance
09b5ef78-2f42-5ded-9447-c1e7ce6d3f2e | note | Attachment for sketch of inlets and outlets
ecd94eba-f8ec-41c8-b479-a4a27c8467b7 | checkpoint | Cover and frame opening folds flat in the direction of traffic flow
f06e6387-3b4d-4b6f-ad67-940a452ee525 | checkpoint | Cover and frame opening conforms with surrrounding surfaces
c3e97a6d-343a-4417-9d30-50f874b39c28 | section | Inlet/Outlet Pipes
1a372257-e23d-49e2-bb84-16b3a3752488 | checkpoint | Pipe starters installed as per specification
17ad314f-de30-479f-b4b4-65878607ac06 | checkpoint | Pipe haunching completed as per specification
05b7ea46-d24e-401d-9024-e761daa75229 | checkpoint | Bottom of manhole finished as per specification
d80e8ea9-4e7f-4def-b7fb-edf0e2b2516b | checkpoint | Internal fall as per specification
de9810ea-2ba4-4cdc-b0ab-62e51bfe5551 | checkpoint | Outlet invert level within tolerance
b631df7e-56c6-42b4-b17d-9f58808dd2a0 | checkpoint | Inlet 1 invert level within tolerance
2ae7a49c-a281-4d15-865a-7cb3cbb8ff63 | checkpoint | Inlet 2 invert level within tolerance
06a66255-8029-4721-8bb5-398ea1f7d095 | checkpoint | Inlet 3 invert level within tolerance
e5c2d02f-3acf-460e-98dc-39262d870b6a | checkpoint | Inlet 4 invert level within tolerance
36585646-8461-42b3-89a1-f9d3d80fa5a9 | section | Post Construction
9419acb7-7fc3-473a-a87f-a7dfd6eb171a | checkpoint | Low pressure hydraulic testing of manhole undertaken. The level of water in the manhole shall not drop more than 5mm in 10 minutes
64e12f8d-0d29-40c2-b87b-1d1cfd91807f | checkpoint | As-Builts have been picked up of manhole and laterals
17efbe48-5206-4e27-b02a-0e687c405cfa | signoff | Manhole has been checked and Inspected
5cfb6ded-725f-477a-a17a-b533a308b5c6 | checklist | ITP - Wastewater Reticulation Upgrade | itp | ITP - Wastewater Reticulation Upgrade
80f3cefc-11aa-41ab-907b-0e60110b3e8a | section | Location & Contract Details
09280c10-3899-4bf4-8bb9-2e83afff4ba9 | checkpoint-no-value | Contract Details
e0850e07-d4be-5561-a12f-af8f67fc10b7 | textbox | Contract Name
d80a3c4e-0c54-5de8-a955-ba9c36a25ef1 | textbox | Contract Number
1bb75f14-14d2-495d-a4af-be05bd65c611 | checkpoint-no-value | Location
3570e6cf-f5e5-5a9f-ac29-415b45125421 | textbox | Location of Works
c906d7a3-9984-4585-9d10-0494de31285c | section | Preconstruction
da4f25f2-4742-4bd3-b81a-99c3936d3e33 | checkpoint | Precondition Survey
b967f9c5-8c0b-5569-ab11-6a242c859921 | note | Specification Reference: Wastewater Specification B.2.11.2.2
152aff32-2364-5054-8157-4b764e8efe13 | note | Test/Task Required: Visual inspection.
ce107e84-1fa4-55b8-af22-9a571f9bc4da | note | Inspection By: UCCL
1787067c-1b38-5a1e-8cc1-9d742c217b91 | note | Task Timing or Frequency: Prior to starting on site.
750bffd8-b5c4-5259-a12b-5088180c5f3d | note | ○ Survey conducted of all surfaces, footpaths, kerbs, driveways and the exterior of buldings on or adjacent to the boundaries of the site and of other property that might potentially be affected by the works.
1585a857-c9f8-5481-95fb-cff45f222d51 | note | Acceptance Criteria: Survey documents submitted to Engineer.
1c098442-8c14-4315-95e4-e5ffc005e886 | checkpoint | Materials Quality
70f5debc-fd21-58da-b30b-46686ccbf302 | note | Specification Reference: FNDC Approved Materials List - Wastewater and Stormwater
970d555a-f07c-5fd4-a2cb-b0e50478e765 | note | Test/Task Required: Visual Inspection.
e41e5ce1-e72c-59bc-a180-d5ef8ce11006 | note | Task Timing or Frequency: Visual check for approved materials, quality and condition.
d002de41-1ef1-58d6-9171-e043c69911a0 | note | Acceptance Criteria: Materials meet specifications or otherwise approved by Engineer. - Delivery dockets/Photos.
fe4fc161-a239-430a-b77a-a9c14fa6cb40 | checkpoint | Survey Setout
2874a4ef-3962-5f29-8ea2-90396db900e3 | note | Specification Reference: Wastewater Specification B.2.11.2.4
d2de87e5-4709-5f0d-99ba-963afd9d17c6 | note | Test/Task Required: Survey Setout
2bd76a84-af51-55a6-8603-f5a07084cd46 | note | Inspection By: UCCL
64c15fb2-67fa-5507-a92f-253df728f59b | note | Task Timing or Frequency: Prior to commencing each stage of work
9a911336-d067-52a3-9fe4-14be6af3282b | note | Acceptance Criteria: Survey setout as per IFC drawings.
7a5864ca-2d63-5d39-abc3-02c905958035 | note | ○ Check all MHs for levels, prior to constructing drainage lines, they must verify the inverts and locations of existing manholes as part of the inspection and testing process
d026f1e8-dcd7-49ae-a6dc-3d4748c01f24 | checkpoint | Service Location
4dc56d9d-4089-57ef-a370-c54c35eb3197 | note | Specification Reference: Wastewater Specification B.2.11.4.2
f27a0407-853d-5310-8a5b-76b1bd1a7b75 | note | Test/Task Required: Locate underground services within work area.
62288154-7d42-5d89-81c0-a8c7bdfb1a5f | note | Inspection By: UCCL
4120104b-aa29-534b-a6ce-ba288ef26d19 | note | Task Timing or Frequency: Locate, pothole and protect existing services. Pothole information shall be used to confirm fittings required to connect to the existing services.
fdc18c9d-2d40-4944-b898-0a2525aa7f19 | section | Installation
176b6392-c7c4-4452-940e-3af630dff31d | checkpoint | Material Properties (Bedding)
f4591296-627b-5332-b13c-3d12c64bde59 | note | Specification Reference: Wastewater Specification B.7.5.1.9
8c273a85-5eea-5388-baa3-aee3b83c0bc6 | note | Test/Task Required: AP20 Grading curve to be submitted to Engineer for approval.
6f858ab8-bb07-563e-8cac-25181d429b1a | note | Inspection By: UCCL, Accepted by Haigh Workman
c4636e6e-5ed8-5c05-897a-cac8e36fe341 | note | Task Timing or Task Frequency: Prior to using bedding material on site.
bd1cfbe3-d45a-56cc-864a-41a80cf9da13 | note | ○ PE bedding, pipe surround and haunching shall be AP20 in accordance with AS/NZS 2566.
89676358-b218-545b-accb-cafca6336b21 | note | Acceptance Criteria: Bedding grading curve accepted by Engineer.
e0382034-581f-4386-bc81-ed526bd891c2 | checkpoint | Material Properties (Subbase - AP65)
8ee30c0c-6d2d-5e9b-88f8-9171f2a66af2 | note | Specification Reference: FNDC Engineering Standards 3.3.2
b6651702-fd38-579d-8556-3444fa44dfda | note | Test/Task Required: Subbase material meets FNDC Engineering Standards
7a4740ae-2e24-5e8d-9265-850ee9c42158 | note | Inspection By: UCCL, Accepted by Haigh Workman
7265b6be-2486-5e2f-b78c-cddee8004fdd | note | Task Timing or Task Frequency: Prior to using subbase material on site.
ef1e2f01-323a-582f-96b0-cf5326b61f1a | note | Acceptance Criteria: Subbase material test certificates accepted by Engineer.
68333979-9694-46d2-a8f3-ce17e3e823bc | checkpoint | Material Properties (Basecourse - AP40)
a0af6291-27b7-5ac8-b2d2-8d6b7645c458 | note | Specification Reference:FNDC Engineering Standards 3.3.2
3f2fda1d-8852-5e11-83c1-9594134ef444 | note | Test/Task Required: Bascourse material meets FNDC Engineering Standards
f0d23f56-f0f1-5a20-b56a-fc139c785b38 | note | Inspection By: UCCL
a50bc11d-5517-5fc3-b7b0-b645261931c5 | note | ○ Haigh Workman
f5ec502f-f9c1-5cd5-a0b0-d7ef4650ce28 | note | Task Timing or Task Frequency: Prior to using basecourse material on site.
7d4e2068-bc67-5b27-b6f1-09f0a0c99233 | note | Acceptance Criteria: Basecourse material test certificates accepted by Engineer
8a629f42-8754-4149-af11-8f254493ffc9 | checkpoint | Pipe and Rubber Rings
f99ea8be-740e-5908-802f-5d4bb000489d | note | Specification Reference: Wastewater Specification B.7.8.3
bca39630-11d9-55ba-b13f-c5270d21986b | note | Test/Task Required: Visual inspection
a8c3de06-db63-5eac-b979-36cc83396fb1 | note | Inspection By: UCCL
90811b67-7e6d-5afd-aa85-835a335a8e80 | note | Task Timing or Task Frequency: Visual inspection prior to use (clean and free from defects).
79e63c42-6477-5781-b941-498c1c401081 | note | Acceptance Criteria: Photographs
7026aed7-38dc-4a04-a173-9c958aca228d | checkpoint | Pipeline Installation (PVC)
3e0fdb9b-fb86-5ede-96e4-745a460997ef | note | ○ Wastewater Specification B.7.8 and B.7.9
86501872-688f-55b0-ba80-e15e19186b2e | note | ○ FNDC Engineering Standards Sheet 31
65eb49c6-1612-54c8-a6b6-c8c18065bc2e | note | Specification Reference: Wastewater Specification B.7.8 and B.7.9
8ecfa9b5-100c-5719-a42c-f225f4896a6a | note | ○ FNDC Engineering Standards Sheet 31
72a293b8-95b4-5450-85fb-f219c2b4b9cc | note | Test/Task Required: Visual inspection
75c36d8a-51f2-55fb-ae3f-a9076149184d | note | Pipeline installed to correct alignment, grade and level
a559b65c-439b-5cc1-95ca-90a4d1c8810f | note | Inspection By: UCCL
8fab4b94-cc2f-588b-8b5a-be510de9b819 | note | Task Timing or Task Frequency: On completion of installation of each length of pipe, prior to backfilling.
8463369b-efcb-502d-b3b3-dee145c2d4ab | note | ○ Throughout installation of pipeline.
764605e9-5e04-50cb-8030-8968d44e0c65 | note | ○ Horizontal alignment +100mm.
021a34e1-9dd1-5c01-9137-acc462bc3296 | note | ○ Vertical tolerance +/- 10% of the design grade for each section of pipe.
015bb451-9b0d-505c-9150-f719e8c2d3c5 | note | Acceptance Criteria: As-built drawings.
5e68615d-e353-55a0-81f6-1b3b0b5a5101 | note | Photographs.
d74e0df8-8496-4664-9dbd-48d8a4ceb452 | checkpoint | Stainless Steel Pipe Bridge
f921f2c0-b5f5-5784-9041-21af859a35b8 | note | Specification Reference: Wastewater Specification 'Package 3 - Bisset - Pipe Bridges Specification
a7f70920-1f25-5451-a579-37dcccd895a7 | note | Test/Task Required: Visual inspection
5a3e0ad3-3d32-5506-a4b1-d02e700c6482 | note | ○ Pipe installed as per specification to correct alignment, grade and level
f560bc5e-7347-5635-abd5-ec963a39764c | note | Inspection By: UCCL
8ba7395a-ec30-5147-8444-9a8922fe5e0b | note | Task Timing or Task Frequency: On completion of installation of each pipe bridge.
86c83cbe-1403-509e-955a-93aee01f48e4 | note | ○ Horizontal alignment + 100mm.
314fe0ed-d0f5-505c-8c59-17b054b7bcf1 | note | ○ Vertical tolerance +/- 10% of the design grade for each section of pipe.
cb095f5b-ebfc-5616-89dd-bb2cddad614f | note | Acceptance Criteria: As-built drawings.
5cf72004-77e2-53f7-a1c0-448722c6de73 | note | ○ Photographs.
3841eded-c3f8-49ee-957b-1850bb345bd8 | checkpoint | Manhole Installation and Backfill
d1c4f8a0-79f4-5ec3-b74f-8166f198d9aa | note | Specification Reference: Wastewater specification B.7.9
60b940ba-cfdc-5b01-a9a3-6da92d222f19 | note | Test/Task Required: Visual inspection.
947a4784-5a69-54a3-9cc7-b475f593f272 | note | ○ Manhole checks including position, haunching, steps and sealed joints.
bdd5187b-a49c-590a-9d9d-5ffcb5d4773d | note | Inspection By: UCCL
55642f67-612b-5873-a153-87fa2d5ad98d | note | Task Timing or Task Frequency: On completion of manhole installation.
f4646108-fd24-526d-bcdd-6baae001dfaa | note | Acceptance Criteria: Falls through manholes are to be within +5mm of design levels.
f09f7a31-087b-575d-ab77-3523dcc21213 | note | ○ Maximum deviation from vertical (manholes/chambers) shall be 10mm per metre.
2f2472ad-69de-45a2-98b0-c901c221890a | checkpoint | Pipe Bedding
045b1869-fbdf-5316-9c6b-c63ffa76161a | note | Specification Reference: Wastewater Specification B.3.4.1
b23492dd-1c1b-5a0d-a35b-397863bc3d49 | note | ○ FNDC Engineering Standards Sheet 31
f69a3eac-d3cb-5adc-83d6-5782e56619cf | note | Test/Task Required: Visual inspection.
c39a1f6a-1ec0-5c9d-84e0-6b4773bfaca0 | note | ○ Compaction test on top of bedding.
ee11eb27-c5c2-548b-97ec-8f75fa5a27bf | note | Inspection By: UCCL
1751d63c-a9aa-54bc-9ce5-e78834b51bd0 | note | Task Timing or Task Frequency: Bedding installed as per specifications.
ca1b5d76-e57e-5a7c-ac50-dabe61c536d4 | note | Acceptance Criteria: Photographs/Compaction test results.
f7b2ddd3-de05-4ca1-914c-1eb52265351c | checkpoint | Pipe Backfill (Outside of Carriageway)
a3c66c26-3a9f-570d-a8ce-d530c5a7ef8b | note | Specification Reference: Wastewater Specification B.3.6.3
2d783bb7-c09e-56d6-bb49-f75487b3a91e | note | ○ FNDC Engineering Standards Sheet 31
c9e01304-a7b3-5612-b96c-07df007215a4 | note | Test/Task Required: Visual inspection.
571141f3-d20e-5a57-81cb-3c9c006bc70c | note | ○ Compaction test on top of GAP65.
fcc025ea-6f6e-511a-a2e4-f7a043bbdd44 | note | Inspection By: UCCL
a3b0b28c-1876-501a-8d3e-dafef272533c | note | Task Timing or Task Frequency: On completion of GAP65 layer.
ac9c127e-abbe-5a96-818c-ea6eb34ac19c | note | ○ On completion of ordinary backfill.
f4350bd3-6645-5bb6-bf78-0f4d58050ea2 | note | Acceptance Criteria: Photographs.
633d0ec7-8281-54f3-ad59-231e2b18aa5f | note | ○ Compaction test results.
d41b60ea-1d8d-444a-b7ef-cd1645acb078 | checkpoint | Subbase
d95f94e1-9c57-588f-b029-80fd537a7b6d | note | Specification Reference: Wastewater Specification B.3.6 and B.3.7
924fba71-490d-5577-aa95-22e63cc795cb | note | ○ FNDC Engineering Standards 3.3.3.3 and Sheet 31
8a95030f-bd15-5b6a-90f0-55ab0384d127 | note | Test/Task Required: Visual inspection
93a92e2b-0d73-5c91-8485-a441a325336a | note | ○ NDM testing
a4cae748-49d7-548a-84f7-f61993feb8d7 | note | Inspection By: UCCL
2879ed38-a723-5cf2-809e-ff5a803b2c34 | note | Task Timing or Task Frequency: NDM testing on completion of subbase layer, prior to installing basecourse.
215f98cd-779e-559a-afff-54071b3ea640 | note | ○ Backfill and compaction completed as per specifications.
493f7de4-0fba-5948-b2aa-a687efa657cf | note | Acceptance Criteria: Compaction records.
e8d0b05b-51d8-5941-8100-ac3cda33a9ca | note | ○ Photographs.
c666d7ca-f21f-4b29-b21a-22c61421fee7 | checkpoint | Basecourse
28d8dd82-ff20-5cbe-beee-bdf3d428da48 | note | Specification Reference: Wastewater Specification B.3.6.2
fec6ab6b-d395-5483-85cd-021eaf434551 | note | ○ FNDC Engineering Standards 3.3.3.4 and Sheet 31
4b463fae-699a-5d32-9bc1-cc849906a72d | note | Test/Task Required: Visual inspection
6beb64cf-a55d-58f5-93d3-1237092c741d | note | ○ NDM testing
eb2fd957-2f26-522c-beeb-753027a75633 | note | Inspection By: UCCL, Hold Point Haigh Workman
d383414f-0657-5cde-8d03-0adba4b105f8 | note | Task Timing or Task Frequency: NDM testing on completion of basecourse layer, prior to sealing.
d44e2a43-15bd-5f56-a103-1be71180beef | note | ○ Basecourse installed as per FNDC Engineering Standards, and NZTA B/02.
aafd3d71-d7cf-5870-bbb5-a6078c937341 | note | Acceptance Criteria: Compaction records.
13d2927e-6c1a-56ac-9f03-18f6671ca836 | note | ○ Photographs.
cfc25728-e1d6-4d05-a285-e5b26060adfe | signoff | HOLD POINT
b70dde02-fac1-4890-9a48-d8bfbf41f95f | checkpoint | Detection Tape
cbb920ff-8936-5803-b876-73a1a09c4ad3 | note | Specification Reference: Wastewater Specification B.7.5.1.6
33723dbc-84a9-5613-ac5a-c3588529d16e | note | ○ FNDC Engineering Standards 5.3.3.1.2
6ab72e5f-66db-56df-90f6-51014e1b8013 | note | Test/Task Required: Visual inspection
ef94d333-6ead-555c-a7fe-5097e81b378b | note | Inspection By: UCCL
5c208d88-07a9-5850-bf3b-09665dda4f64 | note | Task Timing or Task Frequency: '"Sewerage" detection tape laid directly above all wastewater pipelines.
e0d993d8-115a-54c0-8f2e-d89876e8ea32 | note | Acceptance Criteria: Photographs.
d5d36a85-474f-48d6-b16d-03bfcdd09ca8 | checkpoint | Pipeline Testing
bc2d8450-987b-524d-a85d-3f4be0805281 | note | Specification Reference: Wastewater Specification B.7.9.1
90b466dd-6b43-50f5-b476-eca2d26101bf | note | Test/Task Required: Air test
d93e9ae6-c45a-524f-a663-11bbec591ffd | note | Inspection By: Hold Point UCCL & Haigh Workman
bcfddf76-061c-5e15-b57a-f4677666d213 | note | Task Timing or Task Frequency: Each section of pipeline is to be tested by 'Air Test', including Lunden junctions.
ccbf70b1-4c10-527a-89a6-5535262fa10b | note | Acceptance Criteria: Drop in pressure shall not exceed 25mm over a period of 5 minutes.
88536c9b-f0e7-41ac-abc2-b33372e1259e | signoff | HOLD POINT
54e8873a-db2e-489b-80aa-4a1ef1db0e5c | checkpoint | Manhole Testing
d6844dcd-a25f-56bb-bd9c-e95d72bdd4a8 | note | ○ Wastewater Specification B.7.9.1
17ced4aa-0743-5964-82f8-28f37df330fb | note | Specification Reference: Visual inspection.
e662eea1-e296-5184-835b-4538de7b851e | note | ○ Water test.
990dc7c5-bf13-5b9a-9bb3-9fc85db7afba | note | Test/Task Required: Visual Inspection & Water Test
739c989f-7a71-52d9-a7b9-05f48cfb8a26 | note | Inspection By: Hold Point UCCL & Haigh Workman
ba084d82-3531-5bfe-9339-a1b165b38231 | note | Task Timing or Task Frequency: Visual inspection of each manhole prior to backfilling.
0360006a-1a9c-5317-a479-510c9e98a382 | note | ○ Water test after backfill.
f68e1cff-bcb3-59a2-90bd-059dbedb2423 | note | Acceptance Criteria: Drop in level shall not exceed 5mm in 10 minutes.
410c4943-76b1-4585-82c2-cc741c330948 | signoff | HOLD POINT
077565d7-7d95-413a-a38d-8bc0e3d5885a | checkpoint | Wastewater House Connections
f80a007e-78c7-53ab-b999-253a6b2b9063 | note | Specification Reference: Wastewater Specification B.7.8.10
0212b3db-97f8-520c-a172-d9595ced5b13 | note | Test/Task Required: Visual inspection.
a3131243-7f10-5387-abaf-fa61f8047ba5 | note | ○ Survey.
510e1fc9-c12c-586e-a849-1ccc8b702052 | note | Inspection By: UCCL
7ac72b5f-c9bd-58c1-9ede-fbdfc198d0c1 | note | Task Timing or Task Frequency: On completion of each connection.
d17cb841-0a96-5128-a27c-37c1ff203771 | note | Acceptance Criteria: Photographs.
6640422e-824a-5afa-9d2b-ad175f2938e1 | note | ○ As-built drawings.
8642ff89-f494-4b02-9cbc-5e425cebe5b5 | checkpoint | Reinstate Driveways
5a07fc01-ebe2-587b-a20a-8982b4c83701 | note | Specification Reference: Wastewater Specification B.3.8.5
971a399c-5e26-5b5d-a481-912ab7a1fccd | note | Test/Task Required: Visual inspection
d2597aba-e01c-59fb-bb13-2e83984b0c3a | note | Inspection By: UCCL
ba00d329-4ecb-5f57-b70c-1c28db7f53c2 | note | Task Timing or Task Frequency: On completion of wastewater installation.
73c20955-7006-5f8d-a93c-a3441ddc762d | note | ○ Driveways reinstated in the same material and to the same standard as existing prior to works.
5fe508fd-df73-5a3c-b635-52f6c583d4bb | note | Acceptance Criteria: Photographs.
cd480720-e298-4506-ba63-ea813446691e | checkpoint | Reinstate Footpaths
c4ce86de-1d12-51c7-b618-8840616331e9 | note | Specification Reference: Wastewater Specification B.3.8.5
e693fde0-1c8b-56c3-977a-2d7f4eca63c3 | note | Test/Task Required: Visual inspection
8b3815a6-3833-536c-b86a-20bc94e5d637 | note | Inspection By: UCCL
7f63987a-a933-53f8-8ca0-858891d842b6 | note | Task Timing or Task Frequency: On completion of wastewater installation.
27db28e1-7dfe-585e-ac19-af3b71dbbffe | note | ○ Footpaths reinstated in the same material and dimensions as existing footpath, and constructed to FNDC Standards.
6ab1b791-6cac-5690-b743-79a0a8b457cd | note | Acceptance Criteria: Photographs.
10e10675-9225-4387-a573-591298f26f52 | checkpoint | Reinstate Kerb and Channel
fc8e055e-7093-5065-91c4-653a87a927b6 | note | Specification Reference: Wastewater Specification B.8.5
3f9fa78a-59cf-5e73-bb0f-fc30cee9e6de | note | Test/Task Required: Visual inspection
8e07c8be-628e-5862-8159-6e4b48bdb3f8 | note | Inspection By: UCCL
eba31cdd-5d05-551b-bc31-f0cd0e63f68b | note | Task Timing or Task Frequency: Kerb and channel profiles match existing.
56709676-a198-50ff-af83-924d3b407cd8 | note | ○ Concrete has minimum 28-day strength of 25MPa.
5fb5b569-430c-5f0e-82f2-aedd66cf8a3a | note | Acceptance Criteria: Photographs.
404cee5c-c5ad-49af-92fa-b3da43868d2a | checkpoint | Concrete Pour
57e26b26-e064-5c59-a0f5-50593c36b79c | note | Specification Reference: Wastewater Specification B.4.4.2
0811801e-ab4c-550f-a0a5-36e45e86e0bf | note | Test/Task Required: Prepour inspection
dc806ddc-ee8c-5605-9fa2-a6adb36cccfb | note | Inspection By: UCCL/Haigh Workman
1dc1e779-c0a7-54ef-ab4e-f864ade6cd47 | note | Task Timing or Task Frequency: Prior to pouring concrete.
dbdf7455-bc83-5011-b6d9-7ba26bcfc3ca | note | Acceptance Criteria: Pre-pour inspection checklist.
eaa81355-412d-51d5-8bba-5666e7aab28e | note | ○ Photographs.
60a2c149-f8b9-4608-8ee2-55d43181b2c4 | checkpoint | Asphaltic Concrete Layer (DG10)
a2d96789-3dda-5386-893a-8aa148f684a0 | note | Specification Reference: NZTA M10 Specification
e5fa5c30-8299-574f-b5f7-fc87ec1271b5 | note | Test/Task Required: As per NZTA M10 Specification
1b85bb2c-44d1-5d9f-8ae1-8298f4faf0c6 | note | Inspection By: UCCL
2795f7a7-9ce4-54a6-9559-ac928196d583 | note | Task Timing or Task Frequency: On completion of the pavement surface.
cf7a238d-6ff2-517a-b45f-ceac3afdbdf3 | note | Acceptance Criteria: Test results submitted to Engineer.
dd3ae88d-7ce7-53d7-8290-b0ec1ea54bac | note | ○ Photographs.
0c7cb718-65cb-41c7-af61-bb4145b5f95f | section | Post Construction
58e98dfb-decd-4459-a6d1-05d79065a435 | checkpoint | As-Built Drawings
6ea44f56-e6da-55a7-bcce-c0148fa9f9fc | note | Specification Reference: Wastewater Specification B.2.18.1
64777011-6ff9-5f6b-8796-f2cf2d344d22 | note | Test/Task Required: As-built records and coordinate data
d8eeb5c6-fa1e-5217-a254-89fbff894e2d | note | Inspection By: UCCL
60571777-eb58-5942-bbbc-e3f749dc7563 | note | Task Timing or Task Frequency: Draft as-builts shall be complete and accepted by Engineer prior to Practical Completion.
1cfe6a6a-b25a-54c6-8ff4-5deea3de12a1 | note | ○ Final as-builts issued prior to Final Completion.
44da4ba1-1784-5b05-8bd8-8165680fe60e | note | Acceptance Criteria: As-builts submitted to the Engineer for approval.
10284d22-d5dc-4418-80ce-8e21ae28cc15 | checkpoint | CCTV
853d048b-4861-5c1f-b433-b3a20c1617f6 | note | Specification Reference: Wastewater Specification B.2.18.2
944ff4a4-3e92-5a82-a105-749e28c0f4a7 | note | Test/Task Required: CCTV video survey to the National Standards
00be29be-5d6f-5c12-84d0-79884e1194e5 | note | Inspection By: UCCL
1d34f4a0-1ac8-5e18-be42-e2fb234a2191 | note | Task Timing or Task Frequency: On completion of the installation of each pipeline with backfill to the top of the pipe.
76550e17-e87e-5618-aec2-941592cae386 | note | Acceptance Criteria: CCTV results submitted to Engineer for approval.
5dff4897-551b-4d27-a931-cdd1617de204 | checkpoint | RAMM Information
82bd25ff-ad96-52b6-b812-8384b38be9eb | note | Specification Reference: Wastewater Specifcation B.2.18.3
fc23a016-bbd0-5221-b8e6-badf1b341319 | note | Test/Task Required: RAMM information
9be74141-d3b0-51f4-bb6f-dd53923f64d6 | note | Inspection By: UCCL
882c49be-a621-5650-a6b4-4da6af494526 | note | Task Timing or Task Frequency: RAMM information submitted to the Engineer on completion of works.
808718bb-ed71-5e09-b57a-f39317adb1ed | note | Acceptance Criteria: RAMM information submitted to the Engineer.
3a531a75-a490-40b3-9d7e-4722adabc115 | checklist | ITP 01 - Bisset Road - Wastewater Reticulation Upgrade | itp | ITP 01 - Bisset Road - Wastewater Reticulation Upgrade
0b7521e7-fd1b-4120-b71e-6060326254b7 | section | Preconstruction
d24f825f-db67-4b15-b1b1-e78c070d9935 | checkpoint | Precondition Survey
79655c9c-a9e1-57b6-8eac-48ae5799bd21 | note | SPECIFICATION REFERENCE: Wastewater Specification B.2.11.2.2
7232b815-2d25-533b-9a8b-c7a7ca5d8f4d | note | TEST/TASK REQUIRED: Visual inspection.
09b1bc56-3230-5a5e-b135-1be451925b1f | note | INSPECTION BY: UCCL
cb713091-457d-5dbf-8a47-924accc92c89 | note | TASK TIMING OR TASK FREQUENCY : Prior to starting on site.
29fc596f-bc82-5dd5-80f0-c0c171849a81 | note | ○ Survey conducted of all surfaces, footpaths, kerbs, driveways and the exterior of buldings on or adjacent to the boundaries of the site and of other property that might potentially be affected by the works.
2603eb30-7d1c-5fa6-8556-fe198f3e3b90 | note | ACCEPTANCE CRITERIA: Survey documents submitted to Engineer.
d68d1ed9-bdfc-5e6f-b10b-f0301e05e14a | note | UCCL: P
ba981add-d198-549e-8f26-9569abf49ca5 | note | Client: S
be286e39-10ea-41c8-9713-015f4f0ae86f | checkpoint | Materials Quality
7ba940d9-f403-5faa-a5ba-ff69e3443d92 | note | SPECIFICATION REFERENCE: FNDC Approved Materials List - Wastewater and Stormwater
7ec43efc-823a-53f7-8f71-bebd0bfc4db6 | note | TEST/TASK REQUIRED: Visual check for approved materials, quality and condition.
2ba3a5e5-4047-5646-a96b-9fd566269bdf | note | INSPECTION BY: UCCL
c0094ef7-d03c-5a30-8cc1-8174c30d11d6 | note | TASK TIMING OR TASK FREQUENCY : On arrival to site, prior to using materials.
88fbda48-db17-5f6f-9847-769afd972e99 | note | ACCEPTANCE CRITERIA: Materials meet specifications or otherwise approved by Engineer.
75d15f4b-338b-5784-97c9-ca82b45381a3 | note | ○ Delivery dockets.
6a4c5bc6-6b8f-59c6-b6c5-402d5a0020d6 | note | ○ Photos.
ee593d67-5b22-5ae6-8012-4ccd8a73424d | note | UCCL: W
842521f7-9310-5ca7-958c-f2e4bc038179 | note | Client: W
e7a180e8-6973-4470-bc94-447d08f15f57 | checkpoint | Survey Setout
97baed9e-7357-5aee-91ef-fe2a7b5ffd58 | note | SPECIFICATION REFERENCE: Wastewater Specification B.2.11.2.4
f611453d-42ad-5654-b314-b765ab6b3831 | note | TEST/TASK REQUIRED: Survey set out.
078cd6d6-ffa0-5834-80ee-1a5466626a67 | note | INSPECTION BY: UCCL
d44d4938-c236-54fc-9ec7-3f06a636c386 | note | TASK TIMING OR TASK FREQUENCY : Prior to commencing each stage of work.
4ab8a7ce-2ba8-5e12-818a-8026dc960a0c | note | ACCEPTANCE CRITERIA: Survey set out as per IFC drawings.
adf4cb40-d8a0-5b82-9052-7e504b75a719 | note | UCCL: P
2d037d6e-7125-5660-b8f7-e28940ab9449 | note | Client: W
364b78c2-5fab-5ecc-964c-bc4c9db1d0a4 | note | COMMENTS: Check all MHs for levels, prior to constructing drainage lines, they must verify the inverts and locations of existing manholes as part of the inspection and testing process
40876d62-31ed-43ba-9db6-7a2c8a19dc3b | checkpoint | Service Location
07290653-a7c9-5fbd-a980-f1a023cbb4a2 | note | SPECIFICATION REFERENCE: Wastewater Specification B.2.11.4.2
bb515529-7252-529d-873c-90dc1418c374 | note | TEST/TASK REQUIRED: Locate underground services within work area.
d91f01e5-cabf-5d23-ab79-45d1528f9910 | note | INSPECTION BY: UCCL
80bb6558-8e3b-5a3b-98e4-7b2ae85f1297 | note | TASK TIMING OR TASK FREQUENCY : Locate, pothole and protect existing services. Pothole information shall be used to confirm fittings required to connect to the existing services.
2faf8b40-1202-59c4-bb4d-4d0e14e45b9d | note | UCCL: P
615eba98-053c-5d9c-ac49-5ec5bf011403 | note | Client: W
4b5965ba-262a-469b-9c45-d715aa0e2756 | checkpoint | Material Properties (Bedding)
44ba095c-20cb-5174-ba04-ac41c05f4b98 | note | SPECIFICATION REFERENCE: Wastewater Specification B.7.5.1.9
c531549f-3a93-56a2-a30e-828c2052b68e | note | TEST/TASK REQUIRED: AP20 Grading curve to be submitted to Engineer for approval.
e5bc2d60-aa84-5cb9-8b1f-fe23801ad1f5 | note | INSPECTION BY: UCCL
158150e8-81fb-52ae-b786-2a1d4e714792 | note | ○ Haigh Workman
b1a5d557-abf8-5f9d-94cd-7609d21927ad | note | TASK TIMING OR TASK FREQUENCY : Prior to using bedding material on site.
42805f92-b5cf-56ea-9fd6-b15f968580fc | note | ○ PE bedding, pipe surround and haunching shall be AP20 in accordance with AS/NZS 2566.
392f8b1c-88ba-54c5-96f4-8426f3a1a28a | note | ACCEPTANCE CRITERIA: Bedding grading curve accepted by Engineer.
36e3f3e3-e55c-5158-ac2b-6057568187ec | note | UCCL: S
e2f7f1e0-73c1-53b2-b0ec-a45dea2f1f31 | note | Client: A
42527be8-6418-4842-9ebe-5223918a2bbe | checkpoint | Material Properties (Subbase - AP65)
fb375739-52b8-5572-8770-5e93a88be3a1 | note | SPECIFICATION REFERENCE: FNDC Engineering Standards 3.3.2
7218d4d5-b00a-5283-8ed4-7dc23c814bf3 | note | TEST/TASK REQUIRED: Subbase material meets FNDC Engineering Standards
e422f46e-3c8f-5060-91b8-c29aef953740 | note | INSPECTION BY: UCCL
f044dc30-392c-5f08-be8c-4d409afb968e | note | ○ Haigh Workman
e5788f88-247e-5d1b-a107-ab41afe34fb8 | note | TASK TIMING OR TASK FREQUENCY : Prior to using subbase material on site.
1b0dd7df-37bc-5d6a-b30d-946dc0e5c0a1 | note | ACCEPTANCE CRITERIA: Subbase material test certificates accepted by Engineer.
1e0a7f96-b5ba-5c1f-875e-c8edff42a896 | note | UCCL: S
cd34472e-e0a2-507a-9a50-e0b27dcabb3f | note | Client: A
b491048c-535b-4f01-92a0-ae2e6e13168c | checkpoint | Material Properties (Basecourse - AP40)
64e04c14-5eee-58f0-9796-f94966e84ccc | note | SPECIFICATION REFERENCE: FNDC Engineering Standards 3.3.2
fa3945ea-3f42-5f6f-af2d-a236809f9915 | note | TEST/TASK REQUIRED: Bascourse material meets FNDC Engineering Standards
6ffc7881-8894-58ca-8050-5e5d38db6220 | note | INSPECTION BY: UCCL
1ef62d2d-7bab-5a1b-b62e-e5195096fcfc | note | ○ Haigh Workman
9bfd54e7-90df-5f99-923c-e9fe963c2fb9 | note | TASK TIMING OR TASK FREQUENCY : Prior to using basecourse material on site.
f38f117a-cf7d-5f39-97ed-20731be174b7 | note | ACCEPTANCE CRITERIA: Basecourse material test certificates accepted by Engineer.
c4b2c819-1b67-5dcb-90cf-ddfd4c3029d3 | note | UCCL: S
27741999-074b-545a-95a1-d1fe22c4a827 | note | Client: A
2696df30-717d-44da-88ae-dd2ad6483d49 | checkpoint | Pipe and Rubber Rings
42566a65-315c-528f-bd04-d6a9ad5d6f03 | note | SPECIFICATION REFERENCE: Wastewater Specification B.7.8.3
56b6364d-38f1-5932-93ec-c32e63965f1b | note | TEST/TASK REQUIRED: Visual inspection
f8f0dc75-fc1d-5a68-98d9-f97b9190b45f | note | INSPECTION BY: UCCL
21098d3d-21ea-582d-97ba-6a78db3e403e | note | TASK TIMING OR TASK FREQUENCY : Visual inspection prior to use (clean and free from defects).
449e37b9-1f1c-5e68-a93e-9551725ad7a7 | note | ACCEPTANCE CRITERIA: Photographs.
fc7f9135-5a69-5a27-a19e-0cfad2a1a4e6 | note | UCCL: W
04871629-67d9-5371-a91e-d89719954bc6 | note | Client: W
cf659304-9428-4a12-9ff4-544941c91514 | checkpoint | Pipeline Installation (PVC)
59a09255-eba5-52e0-8be5-a165fd86ef24 | note | SPECIFICATION REFERENCE: Wastewater Specification B.7.8 and B.7.9
0aa6d163-a6dc-5258-b885-4157952ebdbc | note | ○ FNDC Engineering Standards Sheet 31
23b5dc92-2c15-5d2d-a23a-4953ec91d9a5 | note | TEST/TASK REQUIRED: Visual inspection
ddfd9c77-f6af-5d7a-bfd2-44145e2e6c2c | note | ○ Pipeline installed to correct alignment, grade and level
db14e8c0-9f17-5c64-84a3-fa16b3faaa62 | note | INSPECTION BY: UCCL
478631e2-83df-504b-a0f6-87e026a66f73 | note | TASK TIMING OR TASK FREQUENCY : On completion of installation of each length of pipe, prior to backfilling.
ff143d20-2c11-5337-8c48-35f75d18805e | note | ○ Throughout installation of pipeline.
c9224b5e-091e-5a2d-b11c-abefbd10c082 | note | ○ Horizontal alignment +100mm.
6bbe72eb-47b1-5e00-9b89-e30fbb055648 | note | ○ Vertical tolerance +/- 10% of the design grade for each section of pipe.
c52710c1-d2e0-51c1-af95-5c5cab309c5d | note | ACCEPTANCE CRITERIA: As-built drawings.
0439dc49-460e-572e-80c3-7485f9229961 | note | ○ Photographs.
64537c9a-7960-5b25-a63c-272f2353a16d | note | UCCL: P
addc15ff-b1fb-5709-9b93-dcd535f70f68 | note | Client: W
26bde61c-f357-438b-bd19-333ce3bf5243 | checkpoint | Stainless Steel Pipe Bridge
fa07266e-894e-5b1a-a708-3457917ca7c9 | note | SPECIFICATION REFERENCE: Wastewater Specification 'Package 3 - Bisset - Pipe Bridges Specification
5e3ae0c6-a41f-59f6-aa4d-297c8ff9b683 | note | TEST/TASK REQUIRED: Visual inspection
12f777b6-968c-5631-9402-c3cd25178702 | note | ○ Pipe installed as per specification to correct alignment, grade and level
a26941ee-5f36-5e17-b2a2-3af30d0800aa | note | INSPECTION BY: UCCL
69668273-8701-5f39-b579-d2b5f6f563f8 | note | TASK TIMING OR TASK FREQUENCY : On completion of installation of each pipe bridge.
5f6e011e-88c1-54e7-ac38-7a5a7b9f2645 | note | ○ Horizontal alignment + 100mm.
5afd2900-f966-5b18-8c8b-2dca7ee18131 | note | ○ Vertical tolerance +/- 10% of the design grade for each section of pipe.
31e8624c-9e75-5235-8508-24108cbfd384 | note | ACCEPTANCE CRITERIA: As-built drawings.
ee91c223-1835-553d-947a-98dada61976d | note | ○ Photographs.
8ba26601-2004-5c01-ae96-aa6bc485897e | note | UCCL: P
e4225f4c-4936-5db2-b600-fc437045bc1c | note | Client: W
dbba8084-d500-42ac-980c-14f50b28bd11 | checkpoint | Manhole Installation and Backfill
f2ace7be-e664-537e-b18a-9690c7faf92b | note | SPECIFICATION REFERENCE: Wastewater specification B.7.9
86dac582-3d95-5f6f-a03e-e6b7573033e1 | note | TEST/TASK REQUIRED: Visual inspection.
5289749d-62f3-5cb2-a4a1-b6828d2d8591 | note | ○ Manhole checks including position, haunching, steps and sealed joints.
cb17c7be-a9c3-50bc-8769-11088c10dd6e | note | INSPECTION BY: UCCL
b40ee6c2-e51d-5430-b5dd-8aefefd6063f | note | TASK TIMING OR TASK FREQUENCY : On completion of manhole installation.
25e556cf-b8d9-5cd4-9043-ff93f6e2892a | note | ACCEPTANCE CRITERIA: Falls through manholes are to be within +5mm of design levels.
d87af360-9877-52ec-913d-3bf51324bada | note | ○ Maximum deviation from vertical (manholes/chambers) shall be 10mm per metre.
765dc0a5-dc8e-50e1-b71a-1f2483d8aaaa | note | UCCL: P
6c012b90-a5cb-5101-99f6-f109d9021d1b | note | Client: W
9ce088dc-edd8-4c88-b95d-508f185ba962 | checkpoint | Pipe Bedding
d4a9785d-6728-5c47-b7a6-f6f65b969a3a | note | SPECIFICATION REFERENCE: Wastewater Specification B.3.4.1
212ed0cc-2b6c-5ac0-baf2-b5759fcf8ad9 | note | ○ FNDC Engineering Standards Sheet 31
ca6b70c7-51ad-5cbb-b667-98f3a18f5678 | note | TEST/TASK REQUIRED: Visual inspection.
8c94ce89-4e1a-51aa-ac37-abbadfa83b0b | note | ○ Compaction test on top of bedding.
0104a7b5-be5d-5451-92df-8b359f8912ee | note | INSPECTION BY: UCCL
38960094-3d47-5ab1-822a-432541f62072 | note | TASK TIMING OR TASK FREQUENCY : Bedding installed as per specifications.
cbcdf134-a0b3-55db-b128-2646b3f29f88 | note | ACCEPTANCE CRITERIA: Photographs.
0a1ce8ff-1207-54d6-85a2-be11c2e952fa | note | ○ Compaction test results.
d2e31c57-c6bc-5f5a-aad7-87cb3307d168 | note | UCCL: P
708f65af-f56f-550f-bed5-aef74ee764b7 | note | Client: W
766d8204-7ac8-4ad6-8c5e-d9fe5bfb2547 | checkpoint | Pipe Backfill (Outside of Carriageway)
982f0553-9a8c-5a7e-aa46-c7481327d14b | note | SPECIFICATION REFERENCE: Wastewater Specification B.3.6.3
7d6e29d5-f7f2-50fe-960a-5e273ffbff1e | note | ○ FNDC Engineering Standards Sheet 31
c94ccd3d-9a38-5af7-b76b-017794e69ff5 | note | TEST/TASK REQUIRED: Visual inspection.
82a6562a-c443-5fcf-956f-234d2c7f37cf | note | ○ Compaction test on top of GAP65.
da118dda-4b7d-57cc-8d79-008a7f7a290f | note | INSPECTION BY: UCCL
f2dbca12-ceb6-54a3-b281-16790d3b1e7e | note | TASK TIMING OR TASK FREQUENCY : On completion of GAP65 layer.
dacb66b9-34ac-517e-8568-623b55ca00e9 | note | ○ On completion of ordinary backfill.
244b1ad8-f443-598c-95c0-b54d78a0738d | note | ACCEPTANCE CRITERIA: Photographs.
9c060f60-ba80-5119-a09b-64466844fdaf | note | ○ Compaction test results.
bb85d147-9b1c-55e5-a0b0-c8044f2f58ea | note | UCCL: P
8cc662d4-4cc6-5f53-8f18-6a386997a6cc | note | Client: W
85de378a-b947-4b9b-b0af-1eb4b8fffa99 | checkpoint | Subbase
df0de2a5-212a-559a-bec3-fc64207adf59 | note | SPECIFICATION REFERENCE: Wastewater Specification B.3.6 and B.3.7
fb0fa907-2e98-5112-bec4-1d39bf34418a | note | ○ FNDC Engineering Standards 3.3.3.3 and Sheet 31
c93baa1e-71f3-5973-b7b8-fbe2b2a41958 | note | TEST/TASK REQUIRED: Visual inspection
47b833bd-6f2a-5311-a160-b76c5d78f9e2 | note | ○ NDM testing
4e4bac09-7e77-593b-a4fa-10d0a7f1f517 | note | INSPECTION BY: UCCL
3758438a-aae9-5984-85e4-e9011be8b595 | note | TASK TIMING OR TASK FREQUENCY : NDM testing on completion of subbase layer, prior to installing basecourse.
77c8d287-1ad8-5e61-9a27-c86dc32dae82 | note | ○ Backfill and compaction completed as per specifications.
fbfbc6de-bfae-5f29-a8ac-ff63f17e615b | note | ACCEPTANCE CRITERIA: Compaction records.
44c195f7-de51-5439-bb05-27a1025f95b0 | note | ○ Photographs.
38a977e4-c3ab-5251-b64e-681ada51510b | note | UCCL: P
58bb9e84-25d7-5f17-bfb4-41ca99c12cd2 | note | Client: W
63790035-8ca3-49be-b99d-71ecce64043c | checkpoint | Basecourse
a62d3a90-72bf-5659-ad9d-9409973f9b81 | note | SPECIFICATION REFERENCE: Wastewater Specification B.3.6.2
f7a25469-ca43-5e54-b1cd-5211be328fdf | note | ○ FNDC Engineering Standards 3.3.3.4 and Sheet 31
310c30df-2082-5aee-b314-491d1db437d8 | note | TEST/TASK REQUIRED: Visual inspection
27f3657d-428c-5636-86f9-186f413f9d5a | note | ○ NDM testing
5deaf454-904a-5e6a-ae22-84cf9fa1efc5 | note | INSPECTION BY: UCCL
d8510bd0-7740-5170-95a9-3bc6529d6032 | note | ○ Haigh Workman
227f2906-6e27-57b1-8cd1-58c8dcb43572 | note | TASK TIMING OR TASK FREQUENCY : NDM testing on completion of basecourse layer, prior to sealing.
f8c5a0ef-792b-59de-a5fb-4be023307ee1 | note | ○ Basecourse installed as per FNDC Engineering Standards, and NZTA B/02.
559d5722-2049-50c7-8d0a-0ab9a78ee169 | note | ACCEPTANCE CRITERIA: Compaction records.
131d7528-0501-5fef-8825-dce8ce72c710 | note | ○ Photographs.
99069ac4-e2ff-58bb-9e00-a5c7d78622cb | note | UCCL: H
489e19f2-b57f-58d5-889e-041a8e8205d8 | note | Client: H
db8e6e94-a98a-4a40-85ac-954996c0ee96 | signoff | HOLD POINT
d3be00fb-cb1d-4e49-a0de-cc16534d550f | checkpoint | Detection Tape
6074b34e-1cd0-5200-9868-bfc79aaee14c | note | SPECIFICATION REFERENCE: Wastewater Specification B.7.5.1.6
58c9272e-a81f-5671-92fd-abe63814a96a | note | ○ FNDC Engineering Standards 5.3.3.1.2
062fcefa-e61d-5164-9a8e-721d5af32f58 | note | TEST/TASK REQUIRED: Visual inspection
2c45236c-6422-5cd6-82ac-1c0a5d28d256 | note | INSPECTION BY: UCCL
a8b7bb63-6163-597c-84d3-ce496cdd0d61 | note | TASK TIMING OR TASK FREQUENCY : "Sewerage" detection tape laid directly above all wastewater pipelines.
dceb4e31-609a-5fff-8749-080c3b31f0ea | note | ACCEPTANCE CRITERIA: Photographs.
a6a9afe7-236d-578c-8940-0c216b52b7cc | note | UCCL: P
8078bcd0-69f2-5943-9a4e-0610d36deffa | note | Client: W
4d1ccd9d-9705-4ad9-aa46-3b593914587c | checkpoint | Pipeline Testing
152c9a86-6b18-5b54-85d9-61e6378369a4 | note | SPECIFICATION REFERENCE: Wastewater Specification B.7.9.1
81474bea-e430-5a9c-9116-0d13474fbddd | note | TEST/TASK REQUIRED: Air test
c90fd465-c7d0-5217-8182-6d41185ba58f | note | INSPECTION BY: UCCL
5f781493-dca2-51fb-bb1b-367aeffed561 | note | ○ Haigh Workman
1f06a0e5-22a5-54a5-b1f1-be3d8e7bdd45 | note | TASK TIMING OR TASK FREQUENCY : Each section of pipeline is to be tested by 'Air Test', including Lunden junctions.
bbe8037b-33ed-5a59-bd43-8acb1cb4955f | note | ACCEPTANCE CRITERIA: Drop in pressure shall not exceed 25mm over a period of 5 minutes.
d4716d59-6b13-576c-87fa-2ce8c93823fc | note | UCCL: H
48f3723f-a439-5e68-a4ac-85be724f8a22 | note | Client: H
82ad2b32-926d-461b-b872-6dc7a477aea4 | signoff | HOLD POINT
e544c4fa-fb56-47f8-b55e-9da5b8c76f88 | checkpoint | Manhole Testing
77470a27-b530-5dcb-8bd0-d57d5353ccff | note | SPECIFICATION REFERENCE: Wastewater Specification B.7.9.1
b5e9c17b-9de2-5727-9993-c72a56d0f5ad | note | TEST/TASK REQUIRED: Visual inspection.
fa80e7cb-b2b3-5f03-90bf-7975ecfb2675 | note | ○ Water test.
bc20a9fd-6758-5c2b-8272-061a73d3f363 | note | INSPECTION BY: UCCL
bfcd1956-8621-55b6-a85c-d4fd98e781a6 | note | TASK TIMING OR TASK FREQUENCY : Visual inspection of each manhole prior to backfilling.
515df7d1-9eb7-5131-a6ff-e901e3178131 | note | ○ Water test after backfill.
126c3f05-17f3-5264-8bd6-eec9f5d67cca | note | ACCEPTANCE CRITERIA: Drop in level shall not exceed 5mm in 10 minutes.
d4f5d7bd-3854-5105-bfe8-41489500c99e | note | UCCL: H
2c4caab6-b028-52f3-8c38-c5035f89282e | note | Client: H
313354d3-13a8-45db-bd22-c1f171ec1c1c | signoff | HOLD POINT
dd51a982-c961-4537-a5eb-bf4438c3feec | checkpoint | Wastewater House Connections
cfb7bb9e-d486-557f-ba8b-fb3d8e8e2b23 | note | SPECIFICATION REFERENCE: Wastewater Specification B.7.8.10
9ea481fe-99cc-513c-ab18-ef64297b4efa | note | TEST/TASK REQUIRED: Visual inspection.
47a29ccb-52b5-5e1b-a643-355ea881be78 | note | ○ Survey.
da9a4271-d332-5f6f-892f-9ee0aecf73a8 | note | INSPECTION BY: UCCL
3879ba4d-d949-50ac-8077-092bb211265e | note | TASK TIMING OR TASK FREQUENCY : On completion of each connection.
6b4b176a-b274-5187-bdca-420baaeefc6d | note | ACCEPTANCE CRITERIA: Photographs.
2fc7f255-149d-57df-838e-2f5f573bcc4a | note | ○ As-built drawings.
dc9725ef-c4cc-5bd0-a272-864ee4e5f4c7 | note | UCCL: P
64f1d3c3-981a-575d-9d67-0e22d70756f9 | note | Client: W
cf446c09-6394-49ca-9eec-24b3eec4c7e1 | checkpoint | Reinstate Driveways
f861d9a9-6652-53a4-a0c9-f69145536fe4 | note | SPECIFICATION REFERENCE: Wastewater Specification B.3.8.5
de5c5305-1222-58b3-9037-5cdaeef08a13 | note | TEST/TASK REQUIRED: Visual inspection
adb3cd29-fb56-5289-9272-88bd0c132412 | note | INSPECTION BY: UCCL
56c46658-cd73-5544-adb7-51cf0b4e11b7 | note | TASK TIMING OR TASK FREQUENCY : On completion of wastewater installation.
6c2c023f-1fba-5d99-9655-f4672367dc49 | note | ○ Driveways reinstated in the same material and to the same standard as existing prior to works.
570b1531-70d1-5192-93e3-dec65cd9548e | note | ACCEPTANCE CRITERIA: Photographs.
9028a68b-a575-5028-9766-5937817a9763 | note | UCCL: P
e0248a83-8db0-5cd2-83a0-c8da16bec522 | note | Client: W
23bfd034-4807-4529-af5c-630786bd5f1a | checkpoint | Reinstate Footpaths
af5fb8c8-392f-5c3b-b909-e1ff2c88d5a0 | note | SPECIFICATION REFERENCE: Wastewater Specification B.3.8.5
97032cec-73df-5820-abfc-8b7a6f616bfd | note | TEST/TASK REQUIRED: Visual inspection
0b84253f-9adf-56e0-97e5-422fec6aebd0 | note | INSPECTION BY: UCCL
a990e788-7faa-5467-b2be-46fdffd40062 | note | TASK TIMING OR TASK FREQUENCY : On completion of wastewater installation.
6055e8a9-00fa-5970-92e7-b87f150a4cc1 | note | ○ Footpaths reinstated in the same material and dimensions as existing footpath, and constructed to FNDC Standards.
0f5f9753-b014-5e37-aa7c-41589b9fa97f | note | ACCEPTANCE CRITERIA: Photographs.
963c6873-cd56-5eb6-be7a-c77058ee3df0 | note | UCCL: P
5bce571f-892d-5363-895a-720c037e8174 | note | Client: W
da491965-6dbe-4028-865f-e31d1c00f4e0 | checkpoint | Reinstate Kerb and Channel
30695e14-e71e-59ee-a9fb-50d261cb45d2 | note | SPECIFICATION REFERENCE: Wastewater Specification B.8.5
c178bd43-b2eb-5ed4-9204-3f112cfdc2a4 | note | TEST/TASK REQUIRED: Visual inspection
6c8d79f2-4b25-5c7d-87bc-ae14b196dfd5 | note | INSPECTION BY: UCCL
272fea35-e33d-570b-bd52-2f7b53c07693 | note | TASK TIMING OR TASK FREQUENCY : Kerb and channel profiles match existing.
c88e6b80-1452-58a4-bc0e-3d12208cfd26 | note | ○ Concrete has minimum 28-day strength of 25MPa.
7b600b23-2a94-5b0f-bb38-f564848b3c1b | note | ACCEPTANCE CRITERIA: Photographs.
d3c421aa-f775-5f73-80b8-94427c98bd27 | note | UCCL: P
af08479a-d413-5258-a7b4-7184a1f45565 | note | Client: W
07513700-6c97-4c1f-8936-ccb72bb08bb7 | checkpoint | Concrete Pour
42ff95e5-56ae-5fc0-8387-728d57c5fb75 | note | SPECIFICATION REFERENCE: Wastewater Specification B.4.4.2
5561feba-6523-5ba1-a417-37f594973c58 | note | TEST/TASK REQUIRED: Prepour inspection
a74d751f-29c3-5945-af49-9041e2bcd4e3 | note | INSPECTION BY: UCCL
60c65972-d97a-5310-bb16-6a64c3157ba3 | note | ○ Haigh Workman
aee08c29-ef5b-5489-b4a5-c0b850e3dcc5 | note | TASK TIMING OR TASK FREQUENCY : Prior to pouring concrete.
5631508c-4116-5597-8376-7382eabf4d29 | note | ACCEPTANCE CRITERIA: Pre-pour inspection checklist.
1c044936-6f25-564a-81fb-d70e13c789b5 | note | ○ Photographs.
90543b40-2db4-5ead-93e8-e30ec8ccdfa9 | note | UCCL: P
f95d7485-d54e-5201-82e8-8de5383c980e | note | Client: W
5eecdd94-f55b-43c4-b479-e2a4b74d61c3 | checkpoint | Asphaltic Concrete Layer (DG10)
9fbe465e-9493-546b-863c-19edd2392008 | note | SPECIFICATION REFERENCE: NZTA M10 Specification
e90ac43a-99e1-59c1-97f4-e3ee999cef7c | note | TEST/TASK REQUIRED: As per NZTA M10 Specification
f1e61b54-9be2-58d1-bb3b-d207358df5eb | note | INSPECTION BY: UCCL
792c1f06-8f73-5713-9662-10a4bb5f2a69 | note | TASK TIMING OR TASK FREQUENCY : On completion of the pavement surface.
b7e1c9af-d261-5718-88b4-eb62e659d3bb | note | ACCEPTANCE CRITERIA: Test results submitted to Engineer.
bd0c41be-2605-5e6c-8b20-7da7b8eba822 | note | ○ Photographs.
4ef11574-ddbe-5693-ba9c-1cbe9614e7e7 | note | UCCL: P
aa2049e2-9afc-5659-8ff4-f5aafdc8925b | note | Client: W
abd905e0-b1fd-49c5-8817-018e6823af02 | checkpoint | As-Built Drawings
9730cc14-888f-5240-8502-4061700e3205 | note | SPECIFICATION REFERENCE: Wastewater Specification B.2.18.1
db51f358-101e-5160-be8b-03974ac91eb5 | note | TEST/TASK REQUIRED: As-built records and coordinate data
83e4321f-5ded-5e25-9a63-c26a7d486a90 | note | INSPECTION BY: UCCL
f2960f65-61e2-55de-ae01-9d59eb0b5c22 | note | TASK TIMING OR TASK FREQUENCY : Draft as-builts shall be complete and accepted by Engineer prior to Practical Completion.
d53dd834-715c-5887-9845-1d204af87b1e | note | ○ Final as-builts issued prior to Final Completion.
d2ed49dc-5b46-5321-b227-bb379caca6eb | note | ACCEPTANCE CRITERIA: As-builts submitted to the Engineer for approval.
22a29ec2-cc1d-52ea-8693-a831bcd3de3f | note | UCCL: S
cc19993a-dbc6-5c77-ab7f-e5a3b71bee78 | note | Client: A
e92a689f-cc63-4981-b9c2-b8eefe9e0c0a | checkpoint | CCTV
24f6b1cb-2d25-58e4-ab61-837ad3f9a36c | note | SPECIFICATION REFERENCE: Wastewater Specification B.2.18.2
4d42b745-f222-5a20-8ac4-22f1476efcf8 | note | TEST/TASK REQUIRED: CCTV video survey to the National Standards
e6b8a674-0388-5c98-8c01-7fee6c5f4d51 | note | INSPECTION BY: UCCL
e858e09e-3e1f-580b-9d3e-3aebc6aa2893 | note | TASK TIMING OR TASK FREQUENCY : On completion of the installation of each pipeline with backfill to the top of the pipe.
05138fc5-94f5-5f4b-ac04-6da7c5720e13 | note | ACCEPTANCE CRITERIA: CCTV results submitted to Engineer for approval.
1e0d8456-ff9b-5faf-b1a7-998967670b36 | note | UCCL: S
1dd632ab-d392-5eef-8d32-51507f5281d6 | note | Client: A
a02ede66-e79d-48f7-b375-6e5ded3f751e | checkpoint | RAMM Information
ec5528a0-dae6-59c9-937e-010f94d16b10 | note | SPECIFICATION REFERENCE: Wastewater Specifcation B.2.18.3
ea7695c3-c856-521a-abe3-bb83e096be43 | note | TEST/TASK REQUIRED: RAMM information
d5af3fca-eb8b-5bec-97ad-4703e5507f88 | note | INSPECTION BY: UCCL
c0b0669c-0d8d-5f58-9eca-4499c2e726d3 | note | TASK TIMING OR TASK FREQUENCY : RAMM information submitted to the Engineer on completion of works.
cf898240-d427-507c-85cc-77a4c66efd0d | note | ACCEPTANCE CRITERIA: RAMM information submitted to the Engineer.
6bd40b5f-77b8-5059-a558-36487d678ad5 | note | UCCL: S
9ba3dafe-fa58-53cc-ab08-0387970e8c38 | note | Client: A