## Master List Templates
Id | Type | Name | Values | Prompting Name | Resource Id
7751697f-9e37-598d-b33a-51c2b29cfdf7 | checklist | Add Bespoke Task |  | Bespoke Task | c50d11ae-0e5a-449f-ad82-65c014528368
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
13672680-43c2-5fbf-9b90-beacfc406d47 | textbox | Enter SOW description
13ab94a7-67c1-51f9-a096-4cf077f00eef | button | Warrantable Works | Yes, No
d3294e6f-2eca-5338-a20b-3853ecfd380f | textbox | Notes Relating To Works Performed
2b45df8e-2416-5f86-852b-a719ab6fb7a7 | checkpoint | Area completed - photos attached below
98274fe3-a2f3-58a2-811a-b81adf023a7c | checklist | Bentonite - Anchor Boxouts |  | Bentonite - Anchor Boxouts | b267b441-e833-4b4a-a376-9303d4634422
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
4c7b06d1-d1ea-5c6d-a5d1-27a5c87ce0f3 | textbox | Enter SOW description
4400189c-ba2e-5758-876f-eb664383ffd1 | checkpoint | Substrate suitable for application
5bebbfb0-05d0-5a69-949b-d6834b903d01 | textbox | If inspection failed, please provide reasons and recommended course of action.
633aefe1-b73b-5d0b-8b89-9cc4d79069df | button | Membrane, Bentoseal & waterstop installed? | Yes,No
2b45df8e-2416-5f86-852b-a719ab6fb7a7 | checkpoint | Area completed - photos attached below
cdacfa9c-3605-582f-8a4d-e9c5cf09be11 | textbox | If inspection failed, please provide reasons and recommended course of action.
d9ca658c-1ec6-5f7f-bc81-676b3bb3b8d5 | button | Manufacturer Inspection Requested? | Yes,No,N/A
a6cad3b2-234a-5dfd-9505-ebe73608ce43 | checkpoint | Manufacturer Inspection
f6327ac1-07db-5699-8ffc-5bcc1ca3d4a1 | note | Attach Manufacturer's Signature Below
99fdc77b-061b-5ba9-acd9-bf763e25edc5 | note | Attach Manufacturer's Report Below
03505234-834e-5915-abf1-b8a9460f936d | checklist | Bentonite - Capping Beam Waterstop |  | Bentonite - Capping Beam Waterstop | 3a8fa130-4869-4d44-9abe-087c08e61805
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
e23c3863-5178-5ef0-ad5e-3bf35def1a22 | textbox | Enter SOW description
4400189c-ba2e-5758-876f-eb664383ffd1 | checkpoint | Substrate suitable for application
23250503-46af-5100-995d-48175c071220 | textbox | If inspection failed, please provide reasons and recommended course of action.
9526201f-c069-50b5-b930-8305dfda774f | button | Waterstop installed? | Yes,No
2b45df8e-2416-5f86-852b-a719ab6fb7a7 | checkpoint | Area completed - photos attached below
264e20c9-a1c8-595c-9822-d0e92d9bc7b9 | textbox | If inspection failed, please provide reasons and recommended course of action.
72b8eb06-db21-52b7-a865-f85a23c652c3 | button | Manufacturer Inspection Requested? | Yes,No
a6cad3b2-234a-5dfd-9505-ebe73608ce43 | checkpoint | Manufacturer Inspection
dad277c9-d7e5-5c26-b3e4-2e10203f4d9e | note | Attach Manufacturer's Signature Below
b1b1f226-bb63-5700-a32c-d3e6cc8cc48e | note | Attach Manufacturer's Report Below
88f711e7-a097-5784-b62f-4b4ef7c12a82 | checklist | Bentonite - Dewatering Wells |  | Bentonite - Dewatering Wells | f81fd71b-e80e-42c0-96bb-b0096019f1ac
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
0ab407d1-7b97-54ff-81f8-3b5c463ef208 | textbox | Enter SOW description
4400189c-ba2e-5758-876f-eb664383ffd1 | checkpoint | Substrate suitable for application
6d4507dd-d2e4-5c66-928a-96aaa67453fb | textbox | If inspection failed, please provide reasons and recommended course of action.
cf43e0b8-3d1c-54c9-8aab-512f4b2429ed | button | PureGold Chips Installed | Yes,No
6133f56e-e57f-5f70-a6be-ac93ac5523d2 | button | Builder installed Concrete Grout | Yes,No
af11c48a-9d7a-5d77-931f-f4dd154f6403 | button | Membrane Installed? | Yes,No
8943eb3b-e178-564d-8b8d-cef65d68f9d6 | button | Waterstop installed? | Yes,No
2b45df8e-2416-5f86-852b-a719ab6fb7a7 | checkpoint | Area completed - photos attached below
5e8f4f8f-9a1f-55c9-a683-b9b02ef24e41 | textbox | If inspection failed, please provide reasons and recommended course of action.
a73effa1-314b-588f-9ee1-3e4367fad00b | button | Manufacturer Inspection Requested? | Yes,No
a6cad3b2-234a-5dfd-9505-ebe73608ce43 | checkpoint | Manufacturer Inspection
a0cff7dd-2884-5e76-985c-b8774bc9f2ee | note | Attach Manufacturer's Signature Below
ae57e7b4-63c9-5dfe-b86d-57e577aa690f | note | Attach Manufacturer's Report Below
ca7d27c5-8785-545a-bf9f-38b56c9b68f5 | checklist | Bentonite - PT Slab Wall Junction Termination |  | Bentonite - PT Slab Wall Junction Termination | ea8c1777-27ed-4a1e-b9e6-ae6ace5bfeba
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
6e9b8646-de21-5c24-a017-0e8699a25264 | textbox | Enter SOW description
4400189c-ba2e-5758-876f-eb664383ffd1 | checkpoint | Substrate suitable for application
3b67dcc4-9a39-5907-ac8b-74d2cbda5775 | textbox | If inspection failed, please provide reasons and recommended course of action.
c51b238e-dfd7-5fbc-9adf-d83e8b440214 | button | Waterstop installed? | Yes,No
832a0be4-b411-5c18-9129-8720ecfc9641 | button | Termination bar installed? | Yes,No,N/A
81a30ed1-03b8-50b2-a5e0-722254503313 | button | Bentoseal installed? | Yes,No,N/A
e14c8e6a-0491-5c98-b58b-adaff04ccf20 | button | Cetinject installed? | Yes,No,N/A
2b45df8e-2416-5f86-852b-a719ab6fb7a7 | checkpoint | Area completed - photos attached below
638a3856-62d4-565a-922a-bccd5eb7306d | textbox | If inspection failed, please provide reasons and recommended course of action.
16c4889d-8a80-536e-a26c-f9ec2c68b755 | button | Manufacturer Inspection Requested? | Yes,No
a6cad3b2-234a-5dfd-9505-ebe73608ce43 | checkpoint | Manufacturer Inspection
2e25e2b2-e694-5ea4-ac53-cb1b90e4444c | note | Attach Manufacturer's Signature Below
8b26d37f-d643-5bf4-9a87-249265c641bd | note | Attach Manufacturer's Report Below
c00881bc-bf8d-5999-98c6-3a7f64c999c5 | checklist | Bentonite - Shotcrete Wall Membrane |  | Bentonite - Shotcrete Wall Membrane | 65d2e8c0-4d6c-42b9-a510-c899b16d5314
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
807d2ddf-a8d1-5253-873a-e38c63d2b0cc | textbox | Enter SOW description
4400189c-ba2e-5758-876f-eb664383ffd1 | checkpoint | Substrate suitable for application
78c21440-9a7d-5d84-8045-c3b311d261be | textbox | If inspection failed, please provide reasons and recommended course of action.
24f3f366-f752-53a1-8078-b0ceb637d9dd | dropdown | Join Coverage | 50mm,75mm,100mm,50-100mm
0d786c86-b748-52e6-8c29-ac1f4c1d18e9 | button | Capping Beam Part Of Installation? | Yes,No
83694976-b33f-5b98-add1-f6d1f1aa1f62 | button | Capping Beam Waterstop Installed? | Yes,No
dd3b011a-78e7-5d5a-91fe-216f6c67278c | dropdown | Waterstop Type | RX-102,Akwaswell,Both
51feb509-2db7-58f9-a8b6-b56c072757c3 | button | Waterstop to drop join installed ? | Yes,No,N/A
878f19cd-4085-5ce7-96b3-252333dabe34 | button | Detailing of penetrations | Yes,No,N/A
ecd894a8-f68e-5a9f-9439-f31c9813ee8c | button | Membrane Installed? | Yes,No
035a9248-f827-56a5-a190-8f9eaf316940 | dropdown | Minimum lap required | 150mm,200mm
36ca57ee-58a2-5b4c-ad2e-498db4a33dca | checkpoint | Starter bars detailed
2b45df8e-2416-5f86-852b-a719ab6fb7a7 | checkpoint | Area completed - photos attached below
87910686-9f5b-5520-b8b3-e943aa335846 | textbox | If inspection failed, please provide reasons and recommended course of action.
7401e2a9-8cd3-51b4-910e-2711d8c42e57 | note | Attach Manufacturer's Report Below
d350534a-e35e-58f3-a7ca-0db9f82c6cf4 | checklist | Bentonite - Strip/Pad Footings (Hydrostatic) |  | Bentonite - Strip/Pad Footings (Hydrostatic) | 3ec7a42a-9583-44ec-b25f-1235e42b57c1
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
a72017de-09cc-558c-9848-3090ee7c6b03 | textbox | Enter SOW description
4400189c-ba2e-5758-876f-eb664383ffd1 | checkpoint | Substrate suitable for application
8be87338-cf3c-53c0-8b5e-a8885f5c87f1 | textbox | If inspection failed, please provide reasons and recommended course of action.
0a8d708d-fc95-59c1-9bf6-17aac1fbf72b | checkpoint | Dewatered
bd97c8b7-135a-516b-a629-d099864cc249 | textbox | Notes on dewatering for Project Manager
747122e0-130c-5c21-9236-96e67e9488d6 | button | Granules to perimeter? | Yes,No
baba0ae6-9ad7-5398-aeed-7748abe49194 | button | Membrane Installed? | Yes,No
70e62807-d2b7-5479-82ee-9dd7e5b64d21 | dropdown | Minimum lap required | 150mm,200mm
2b45df8e-2416-5f86-852b-a719ab6fb7a7 | checkpoint | Area completed - photos attached below
bc1fc3d0-b08f-56a6-8ddb-ee52ccdb1121 | textbox | If inspection failed, please provide reasons and recommended course of action.
1e97c4f9-929d-5525-b280-6b243abb1281 | button | Manufacturer Inspection Requested? | Yes,No
a6cad3b2-234a-5dfd-9505-ebe73608ce43 | checkpoint | Manufacturer Inspection
16fdeee3-0e28-56c0-971a-423fd5a8ca12 | note | Attach Manufacturer's Signature Below
1c7cfd90-92b9-5587-8337-5633bfc56b7b | note | Attach Manufacturer's Report Below
55a1b191-c816-5b65-9b83-07e1b0153faa | checklist | Bentonite - Underslab Membrane (Hydrostatic) |  | Bentonite - Underslab Membrane (Hydrostatic) | 5eda08c9-8f42-43d7-9ccb-abb3a480eca6
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
5d5c04d0-14ea-522b-abe0-45f5d383735b | textbox | Enter SOW description
4400189c-ba2e-5758-876f-eb664383ffd1 | checkpoint | Substrate suitable for application
6aba74f9-1db9-566b-b339-506b39844fc1 | textbox | If inspection failed, please provide reasons and recommended course of action.
0a8d708d-fc95-59c1-9bf6-17aac1fbf72b | checkpoint | Dewatered
38afa2f2-5a98-5107-8f44-525b4c96aa5e | textbox | Notes on dewatering for Project Manager
794f576b-e7b3-5d29-b91d-4bf6f7c79c3f | button | Membrane Installed? | Yes,No
83adaa0f-6c64-51fa-b614-080faf889333 | dropdown | Minimum lap required | 150mm,200mm
2a326046-c308-51e1-a8ea-c7f3bf5db829 | button | Waterstop to pile caps | Yes,No,N/A
47d7a6f5-48d7-5bdb-a7d0-661bfb4507c0 | button | Detailing of penetrations | Yes,No,N/A
2b45df8e-2416-5f86-852b-a719ab6fb7a7 | checkpoint | Area completed - photos attached below
3caee4dd-9670-5b01-bb32-d9f387d18ba3 | textbox | If inspection failed, please provide reasons and recommended course of action.
8e025066-9b65-526a-ac21-7da10d4a7a0b | button | Manufacturer Inspection Requested? | Yes,No
a6cad3b2-234a-5dfd-9505-ebe73608ce43 | checkpoint | Manufacturer Inspection
6ca13afd-657b-5c44-8c89-4f681f7d1233 | note | Attach Manufacturer's Signature Below
b3f7b342-3283-58f8-8cb7-e50c838e9369 | note | Attach Manufacturer's Report Below
2f60ca36-ce5d-571a-84ac-40c4e0ed4b7f | checklist | Bentonite - Underslab Membrane (Non-Hydrostatic) |  | Bentonite - Underslab Membrane (Non-Hydrostatic) | aedfb01e-3ea8-4b7e-9c65-e41e1ab56650
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
7823b74b-8933-5ce1-a21a-13ad01b57af3 | textbox | Enter SOW description
4400189c-ba2e-5758-876f-eb664383ffd1 | checkpoint | Substrate suitable for application
b8f966f9-1efe-51f3-abc2-552aba65dd42 | textbox | If inspection failed, please provide reasons and recommended course of action.
0a8d708d-fc95-59c1-9bf6-17aac1fbf72b | checkpoint | Dewatered
8139d3f3-3584-5f66-9e97-83ada1188a62 | textbox | Notes on dewatering for Project Manager
ce95436f-afcc-517b-9c6c-21a7e0b7af0b | button | Membrane Installed? | Yes,No
5217f3c5-0cf4-5496-a86a-f92684865cc7 | dropdown | Minimum lap required | 150mm,200mm
54a3c460-388c-504e-83d0-ed0975adc95e | button | Detailing to pile caps | Yes,No,N/A
c5f11fdf-ebbf-51a2-b449-efc2a70e5347 | button | Detailing of penetrations | Yes,No,N/A
2b45df8e-2416-5f86-852b-a719ab6fb7a7 | checkpoint | Area completed - photos attached below
08aac69c-8776-5f4d-a24b-bdd889b6711d | textbox | If inspection failed, please provide reasons and recommended course of action.
6bc2cf39-7fae-5676-ab4e-7df9adfc7448 | button | Manufacturer Inspection Requested? | Yes,No
a6cad3b2-234a-5dfd-9505-ebe73608ce43 | checkpoint | Manufacturer Inspection
c4f5574f-956c-54cf-9bec-a80d74fd143c | note | Attach Manufacturer's Signature Below
0c24de3e-7588-52a5-97be-34c708663ed9 | note | Attach Manufacturer's Report Below
4a8afb26-a695-57e6-9b9e-e8e23d7aa597 | checklist | Bentonite - Wall / Slab Junction |  | Bentonite - Wall / Slab Junction | 1006e06c-7ddb-4aeb-b28a-6d934b13b919
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
562f5c13-adff-5175-9e62-6f21a6474c7e | textbox | Enter SOW description
4400189c-ba2e-5758-876f-eb664383ffd1 | checkpoint | Substrate suitable for application
1c05c36c-d15d-5824-807b-de561507c110 | textbox | If inspection failed, please provide reasons and recommended course of action.
c8788c95-e324-5600-9fc8-9312d51f8e2c | dropdown | Slab Thickness | <450mm,>=450mm
f087d916-e39a-5776-a62c-45e29d1e2adf | dropdown | No. of waterstops to install | 1,2
335b2842-0c56-5efe-93d1-5306e4c233d2 | button | Waterstop installed? | Yes,No
e8896aac-b439-5954-bbac-f0a42010875d | button | Granules to junction? | Yes,No
2790ebeb-4606-50ac-a01c-5661f74bb770 | button | Akwaswell to lowest 2 laps? | Yes,No
2b45df8e-2416-5f86-852b-a719ab6fb7a7 | checkpoint | Area completed - photos attached below
42e19aeb-2fc1-5b41-8860-cac511e1adab | textbox | If inspection failed, please provide reasons and recommended course of action.
4b8febfa-0d9f-50ae-aecf-3c867808cd69 | button | Manufacturer Inspection Requested? | Yes,No
a6cad3b2-234a-5dfd-9505-ebe73608ce43 | checkpoint | Manufacturer Inspection
9069bf98-9d35-5444-b547-68b747bb4460 | note | Attach Manufacturer's Signature Below
33fa6737-9fdc-5e78-9072-2c635bc8eba7 | note | Attach Manufacturer's Report Below
d64cff1f-e5f8-5616-91c5-586a2e8d8bbb | checklist | Bituthene 6000EIM Installation |  | Bituthene 6000EIM Installation | d4a30be0-a604-4c28-892c-46e2742f1f6b
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
df1ae2d3-4833-5aa9-aca0-57d38b324a9f | textbox | Enter SOW description
f8d85dcb-75e7-5a30-8c80-44d74709972d | checkpoint | Attach TDS for application
c2aa6d82-bfce-5616-acef-6e6e505b0a9d | checkpoint | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below
29f3ee07-43c1-5255-be07-20c921096030 | checkpoint | Substrate temperature is not less then 10*C and no greater then 35*C
9c3e1916-1e20-50b9-8d8b-3d8484e20f84 | checkpoint | Substrate free from pooling or ponding water - Moisture gauge photo attached below
be745d8d-664f-54ff-85b5-652312ae3ab8 | note | If any of these checkpoints fail please provide information and required action by builder
bac745dc-012c-5c2e-9d1a-9059a9f532c4 | textbox | Add Comment
8bbcd2bd-ade2-5024-b024-cb5343e5cbba | checkpoint | Installation of Bituthene Type C primer as required?
11cf6d6b-970f-534d-a67f-12189be0207c | checkpoint | Record (Photo) batch number and date of manufacture of primer
7c757e84-dd74-53cf-8346-fa1420125d79 | checkpoint | Curing time for primer (Minimum 2 hours)
be2c01be-907b-576b-926f-12aa3ee958f3 | checkpoint | Installation of base sheet
d9fb614f-a5fe-5f19-8c70-98ccd17e7ca9 | checkpoint | Record (Photo) batch number and date of manufacture of Bituthene 6000EIM base sheet
c2d03028-52a1-53e9-8aa9-c48cc02b7de2 | checkpoint | Installation of top sheet
79bdf92b-9831-58af-a3af-8ee5e3bb50fe | checkpoint | Record (Photo) batch number and date of manufacture of Bituthene 6000EIM top sheet
98dd3368-71ed-55f0-a342-bb46c30f3239 | checkpoint | Installation of Bituthene LM Mastic to perimeters
88697b6f-8ce1-58cc-85b6-34fb89190399 | checkpoint | Record (Photo) batch number and date of manufacture of top sheet
eeb5ac87-0a3c-57a2-b06d-02d4b9d8c2f4 | checkpoint | Area completed to manufacturer's specification - photos attached below
b4a40a3e-d10e-5760-a347-d26f21a785d3 | checklist | Butynol Installation (External) |  | Butynol Installation (External) | bdc104a5-2b2d-4540-9879-d430dd4cfd27
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
6dc99cdc-faa2-52aa-8cd3-cb0c8627fa46 | textbox | Enter SOW description
0071234a-e6dd-5dec-99fe-3eece8ca0c1e | checkpoint | Attach TDS for application (Download from Simpro)
1e6a7583-4b56-53b4-bdbc-82026d735c79 | checkpoint | Substrate clear of dust, debris and contaminants (Attach photos below)
29f3ee07-43c1-5255-be07-20c921096030 | checkpoint | Substrate temperature is not less then 10*C and no greater then 35*C
56a3f5ba-1bbf-5226-9213-baf248224cc5 | checkpoint | Substrate free from pooling or ponding water? (Attach moisture gauge photo)
3fbdef10-c6bd-523b-8f6a-85d7e4cab951 | button | Adequate fall in substrate? | Yes,No
aa19ec6e-c043-5a97-9554-70401fcd702f | note | If any of these checkpoints fail please provide information and required action by builder
92b06a76-965b-5411-9401-bfde9807db56 | textbox | Add Comment
cb1aac0d-a5f8-5d9d-b84d-2f7a80554648 | button | Installation of primer as required? | Yes,No
f123208e-de12-5762-aa59-78ec8039e93c | checkpoint | Substrate free from surface water? (Attach moisture gauge photo)
6fc854fb-1aa3-5fbf-81ca-e9297e4a1a78 | button | Installation of sheet membrane to manufacturer's specification (min. 50mm overlaps) ? | Yes,No
288bf048-1697-5794-adb2-1e62ed9e7b37 | button | Installation of sheet membrane to perimeters, incl. compatible sealant as required? | Yes,No
ab7fc321-b145-55ec-824c-ab1fa60e3975 | checkpoint | Area completed to manufacturer's specification? - photos attached below
62c5d79a-aa16-565e-8c87-e672785f64c9 | note | Attach Client Signature Below
22e9db65-6654-5071-9986-0869c4cfd716 | checklist | Butynol Installation (Internal) |  | Butynol Installation (Internal) | 99c6c49c-7f20-441c-95fc-a8b44639114f
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
fdba740c-3ad2-5562-850c-784b8e575e13 | textbox | Enter SOW description
0071234a-e6dd-5dec-99fe-3eece8ca0c1e | checkpoint | Attach TDS for application (Download from Simpro)
1e6a7583-4b56-53b4-bdbc-82026d735c79 | checkpoint | Substrate clear of dust, debris and contaminants (Attach photos below)
a517516d-30cb-51b8-a5ef-d63dba2ffd22 | note | If substrate failed please provide information and required action by builder
23b10c1e-05d3-52b0-9d8e-713fdede3c77 | textbox | Add Comment
bc50826f-6f40-5792-ae0c-1757b1e5505e | button | Installation of sheet membrane to manufacturer's specification (min. 50mm overlaps) ? | Yes,No
8a4dd41e-3630-54e0-a416-332b2b7dc709 | button | Installation of sheet membrane to perimeters, incl. compatible sealant as required? | Yes,No
ab7fc321-b145-55ec-824c-ab1fa60e3975 | checkpoint | Area completed to manufacturer's specification? - photos attached below
8820a6f5-5957-58f1-824d-bd9131145a91 | note | Attach Client Signature Below
1d31aba5-53e4-5bcf-b2e5-09234591b727 | checklist | Concrete Injection |  | Concrete Injection | 1c93b074-31f8-487a-a0f8-dc71b397c0ec
445b3149-2a71-5e8f-94aa-4ad9987c6951 | checkpoint | Investigate location and document.
9a197116-df9e-57ab-a7a4-e76e31ee9891 | button | Is injection required? | Yes,No
a9482293-0fa7-5958-9a85-ea10b2533a9f | checkpoint | Record product, batch number and TDS.
110aa801-923e-574b-97ae-cf7de0625723 | textbox | Drill, insert and record packers as required.
69ef3c13-d9c7-5b04-9d4f-3000318dd71a | textbox | Record results of injection including (but not limited to) quantity of material injected per packer and relevant observations. Include sketch/markup if required.
20888a7d-ea3d-50d8-a967-a7a3ddd6328e | button | Injection completed as per manufacturer's specification | Yes,No
1ca07794-a1c6-5076-bf39-0191017fd23a | checklist | Control Joints |  | Control Joints | cffd06c6-c223-4455-8515-b588af1b68a6
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
79301476-5a91-51f2-87a7-f1c5fe195d99 | textbox | Enter SOW description
c69a0501-c329-5440-941b-cb4e3b36c46a | checkpoint | Channel cut to sufficient width
af095250-1167-5223-8e7c-413956204204 | textbox | Enter width
55be28ef-c40c-5387-a988-b502b42c898f | checkpoint | Polyurethane caulk applied to channel
5fa726ce-2c68-5f9e-aac7-45184918f49b | checklist | Dermafil (Concrete Lid) |  | Dermafil (Concrete Lid) | 58e94a7f-a013-44ce-ad52-f08fb15444a8
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
cca6913e-fb5b-55c6-93d6-29493708f733 | textbox | Enter SOW description
0071234a-e6dd-5dec-99fe-3eece8ca0c1e | checkpoint | Attach TDS for application (Download from Simpro)
976681ca-08e8-5579-b68f-29f2996b4432 | checkpoint | Substrate Acceptance (as per manufacturer's technical data sheet and method statement)
a86744d1-63ac-5c78-95e5-67bbc2baf2ad | button | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below | Yes,No
48dc42fc-4175-5212-8dcd-385f9f69f2e4 | button | Substrate temperature is not less then 10*C and no greater then 35*C | Yes,No
8d29f25e-117b-5056-80fd-e6cb2a896c33 | button | Substrate free from pooling or ponding water | Yes,No
7d4e00a7-a4df-55b6-91d2-8f1096746d7e | button | Moisture content is 4% or less (Moisture gauge photo attached below) | Yes,No
b317272a-d287-5054-8966-8b0b8e4990ee | button | Adequate fall in substrate | Yes,No
92a8ae42-a356-56bf-a63a-8428d7e8e051 | checkpoint | Priming
0aec156f-1625-50fa-8e47-81183cc345f7 | note | Record batch numbers
a6339416-d7b0-59ed-8279-06d758703004 | button | Dermaprimer installed to manufacturer's specification - photos attached below | Yes,No
3058dc84-bdd9-58b3-91c5-cd489c662a50 | button | Primer given adequate time to cure as per manufacturers specification | Yes,No
75b90a27-fd14-5418-bf98-42379c758493 | button | Area completed and suitable for membrane application - photos attached below | Yes,No
609e0946-9b0e-595c-b8d6-cf025fa02759 | checkpoint | Dermafil Installation
56cbf7c5-501e-51e6-946f-c16b8956151f | note | Record batch numbers
910b7b5f-e194-5442-8061-3ec7493db1eb | button | Substrate clear of dust, debris and contaminants - photos attached below | Yes,No
b5ad3662-d35d-5e5c-a6d6-6dfd162a35ee | button | Installation of base layer membrane (min. 100mm overlaps) - photos attached below | Yes,No
7fce1b43-16af-57af-b3df-10edbe109ff9 | button | Termination pressure bar installed where required - photos attached below | Yes,No
738df047-2cb8-585b-a150-989f183e7112 | checkpoint | ILD Testing
9b78a4c4-0334-5b26-bdb4-95cb762b598a | button | ILD test requested | Yes,No
acba65c0-0eda-50c7-9874-00414504f247 | button | ILD test performed | Yes,No
b01e44e0-617f-59ac-a998-3bd4c2cbbc35 | textbox | Any rectifications performed
55574ec3-34dc-52de-b15b-134f6c2e5f13 | button | ILD test report issued | Yes,No
baaf9e95-c489-5585-94d7-2784bfa188a8 | checkpoint | Protection
0f632de3-d252-5a89-baec-0a4aaefc45ec | button | Casali Protector installed - photos attached below | Yes,No
eeb5ac87-0a3c-57a2-b06d-02d4b9d8c2f4 | checkpoint | Area completed to manufacturer's specification - photos attached below
55e980be-0b47-5561-ae4e-c5822f9f0160 | note | Attach Client Signature Below
a6ac4c5b-14de-5813-be33-26eb1b4639c9 | checklist | EnduroFlex Insulated Roof PVC Installation |  | EnduroFlex Insulated Roof PVC Installation | 2210723c-99c2-4285-a0c4-075fa721d0cd
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
881d1cae-d465-5f42-99b5-c62de4e35740 | textbox | SOW description entered
0071234a-e6dd-5dec-99fe-3eece8ca0c1e | checkpoint | Attach TDS for application (Download from Simpro)
4ad41a9e-9a48-549a-8119-389c3dda4b78 | checkpoint | Substrate Acceptance
278edb56-039c-5940-979a-cfa10c435f3b | button | Substrate washed / cleaned & assessed for surface uniformity (photos attached below) | Yes,No
f715a8d0-c638-566a-a9b7-7aba7c05d91f | button | Substrate temperature is not less than 10*C and no greater then 35*C | Yes,No
cb9e7e4a-9e3f-58f9-bf7c-baf04c8ca1df | button | Substrate free from pooling or ponding water (Moisture gauge photo attached below) | Yes,No
7215b73f-1b90-508c-a305-3e2ca46533c0 | button | Adequate fall in substrate? | Yes,No
79edbabc-f800-5c0b-8b1c-7a65761baa0c | checkpoint | Vapour barrier installation
d7cd42bc-baaf-570d-bd79-bc3122a4a101 | dropdown | Vapour barrier type | Fully Adhered, Loose Laid
2aed48ab-bca9-5d23-a262-ee19fcd423a8 | button | Primer installed to manufacturer's specification (Record batch and install photos) | Yes,No
eb9c509b-5af2-57df-a6af-a17b75addd3a | button | Vapour barrier installed to manufacturer's specification (Record batch and install photos) | Yes,No
6ddd5a5f-0fd0-5063-9222-d155d29a9220 | checkpoint | Insulation Installation
2fccffb6-fdf2-581e-b14f-21baddeaa725 | button | Vapour barrier free of pooling water? | Yes,No
9f5d89dc-0f29-583b-b8c8-5a1553499613 | dropdown | Insulation installation method | Foam Adhesive,Mechanically Fixed
b08cb857-13c7-55af-a92c-04bf6477f4ac | button | Insulation installed to fall? | Yes,No,N/A
3cf7d56a-455c-5635-884a-1a6523e2190f | checkpoint | Membrane Installation
c35f5365-0ea1-5db7-9ecd-09687a82d044 | button | Installation of fully adhered base sheet membrane to manufacturer's specification (Record batch and install photos) | Yes,No
0abee5f7-a2e4-5210-862a-458efe9fd112 | dropdown | Cap sheet installation method | Fully Adhered,Torched
79e00b46-624f-5fed-817f-5e3a11fa3c38 | dropdown | Cap sheet type | Unexposed,UV-Stable,Anti-Root
8cdeef0f-5fde-50f1-b505-79d1a0671e1e | button | Installation of cap sheet membrane to manufacturer's specification (Record batch and install photos) | Yes,No
34462895-fc66-59a0-8a44-90a3a6fc8009 | button | Termination pressure bar installed to manufacturer's specification (Record batch and install photos) | Yes,No
ab7fc321-b145-55ec-824c-ab1fa60e3975 | checkpoint | Area completed to manufacturer's specification? - photos attached below
42cce3dd-e3a2-5be9-8bc1-100a5235e7fd | checklist | Eradix (Backfilled Downturns) |  | Eradix (Backfilled Downturns) | a8b29387-84b7-46c2-bbbe-8fbd702ba49f
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
262c072e-f20f-5553-9cfb-2832106a2cdb | textbox | Enter SOW description
0071234a-e6dd-5dec-99fe-3eece8ca0c1e | checkpoint | Attach TDS for application (Download from Simpro)
6c59c0c5-8baf-5daf-93c4-b1284f2b8a80 | checkpoint | Diaphragm Wall Preparation
519e7f42-7aff-5d66-bfac-4ee097eb6d59 | button | Transition compound to D-Wall installed as per manufacturer's specification | Yes,No
976681ca-08e8-5579-b68f-29f2996b4432 | checkpoint | Substrate Acceptance (as per manufacturer's technical data sheet and method statement)
d97923e7-6cab-5e9d-9541-1d9c871d0016 | button | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below | Yes,No
bc8b2226-32ce-518f-be88-1e7ec09585b6 | button | Substrate temperature is not less then 10*C and no greater then 35*C | Yes,No
9f33d685-58a1-5224-955e-7b585d71c83b | button | Moisture content is 4% or less (Moisture gauge photo attached below) | Yes,No
92a8ae42-a356-56bf-a63a-8428d7e8e051 | checkpoint | Priming
78b46b01-8cf2-51ab-8dec-13fd61cad1b1 | note | Record batch numbers
32653558-0436-5349-8b1e-2c20587246c3 | button | Dermaprimer installed to manufacturer's specification - photos attached below | Yes,No
9bbdf920-c6c6-57df-89ee-5e21c4ffde90 | button | Primer given adequate time to cure as per manufacturers specification | Yes,No
68497c8a-5ed4-5ddd-ae17-a04269f0cd5f | button | Area completed and suitable for membrane application - photos attached below | Yes,No
695216b1-7063-5527-89b2-722a506db7b6 | checkpoint | Eradix Installation
1ef6aeef-dee7-59c1-af9f-273284ed7e05 | note | Record batch numbers
782f94c7-ea0b-5de6-9f53-572ffbf98a81 | button | Substrate clear of dust, debris and contaminants - photos attached below | Yes,No
cbb5c353-e48c-5701-a2c7-40590c4dd837 | button | Installation of base layer membrane (min. 100mm overlaps) - photos attached below | Yes,No
8e99c39c-cfae-5c88-9dfa-47d024b8963c | button | Termination pressure bar installed where required- photos attached below | Yes,No
738df047-2cb8-585b-a150-989f183e7112 | checkpoint | ILD Testing
87e9195e-2365-5249-9e37-597b36c83d9b | button | ILD test requested | Yes,No
e65c5adc-621e-5390-8ab7-6d4e8af6951e | button | ILD test performed | Yes,No
f7293006-b20d-59ee-ae8f-4c3286f2eec7 | textbox | Any rectifications performed
97a50da0-40f1-5c24-8d28-9e731d18d90c | button | ILD test report issued | Yes,No
baaf9e95-c489-5585-94d7-2784bfa188a8 | checkpoint | Protection
562202d8-9c34-59e8-a26f-0cd03bf785a2 | button | Casali Protector installed - photos attached below | Yes,No
eeb5ac87-0a3c-57a2-b06d-02d4b9d8c2f4 | checkpoint | Area completed to manufacturer's specification - photos attached below
f196104a-7cba-5767-baba-3ed0a421acd5 | note | Attach Client Signature Below
5478188c-722a-5eda-8ba8-9afc13d2dc2f | checklist | External (Exposed) |  | External (Exposed) | 585469a7-a333-48af-b705-fe416932a98b
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
d28a7764-9542-5c8d-8808-0e24012aec8b | textbox | Enter SOW description
0071234a-e6dd-5dec-99fe-3eece8ca0c1e | checkpoint | Attach TDS for application (Download from Simpro)
c2aa6d82-bfce-5616-acef-6e6e505b0a9d | checkpoint | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below
29f3ee07-43c1-5255-be07-20c921096030 | checkpoint | Substrate temperature is not less then 10*C and no greater then 35*C
9c3e1916-1e20-50b9-8d8b-3d8484e20f84 | checkpoint | Substrate free from pooling or ponding water - Moisture gauge photo attached below
7fc11175-5e68-592f-9a08-ddd5f7eeb7b4 | button | Adequate fall in substrate? | Yes,No
f8ed1ef4-afc4-5601-b139-1a2c67988105 | note | If any of these checkpoints fail please provide information and required action by builder
d4446a5c-1929-51f9-8a74-0f234ccca01e | textbox | Add Comment
b462a3d0-8373-5ab9-b9ee-895a55df48a1 | button | Installation of primer as required? | Yes,No
11cf6d6b-970f-534d-a67f-12189be0207c | checkpoint | Record (Photo) batch number and date of manufacture of primer
819686ac-ab1b-5a68-b684-df1d9012436a | dropdown | Curing time for primer (hours) | 6,12,18,24
0854a4b8-9615-5fe3-bad1-1d22e5df8559 | checkpoint | Substrate free from surface water - Moisture gauge photo attached below
b85b128d-cae0-51c9-b535-a234c792ad07 | button | Installation of fillets/bandage to junctions as required? | Yes,No
462de1b6-b119-54de-b736-6f75a46a778e | button | Installation of base coat within rquired maximum curing time of primer? | Yes,No
7111841c-3df3-5950-b15f-a7b4613ed9c0 | checkpoint | Record (Photo) batch number and date of manufacture of base coat
ef7a5954-54f7-5ac7-a69b-dbf5d57377b1 | button | Base coat installed to minimum film thickness? | Yes,No
672970c9-996a-5f5b-b80e-25f723705934 | button | Installation of UV-stable top coat? | Yes,No,N/A
8e552cb8-84e8-5539-b200-d52414c4a4fd | checkpoint | Record (Photo) batch number and date of manufacture of top coat
00c50874-66dd-5c4e-967d-a5f62f45e2f7 | button | Top coat installed to minimum film thickness? | Yes,No,N/A
b5bce0d6-63a2-572c-8c9e-5d0fd89efc84 | button | Broadcast of 30/60 quartz if trafficable? | Yes,No,N/A
eeb5ac87-0a3c-57a2-b06d-02d4b9d8c2f4 | checkpoint | Area completed to manufacturer's specification - photos attached below
3cb527e2-46bc-56ce-ba5d-74958dcf8a22 | checklist | External (Non-Exposed) |  | External (Non-Exposed) | c7b76de3-a0fe-4057-bf94-d02d1c31c42e
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
9cdafd14-ff00-581f-9a62-264cb7467b95 | textbox | Enter SOW description
0071234a-e6dd-5dec-99fe-3eece8ca0c1e | checkpoint | Attach TDS for application (Download from Simpro)
c2aa6d82-bfce-5616-acef-6e6e505b0a9d | checkpoint | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below
29f3ee07-43c1-5255-be07-20c921096030 | checkpoint | Substrate temperature is not less then 10*C and no greater then 35*C
459bf8e5-5686-58a8-8c92-f814dd515fb0 | checkpoint | Substrate free from surface - Moisture gauge photo attached below
f69bc01b-d28c-5cf3-bf2b-d2bfd6e82ea8 | button | Adequate fall in substrate? | Yes,No
ea6f2f7f-cbe2-58a4-adb7-ca59ef80f519 | note | If any of these checkpoints fail please provide information and required action by builder
1d896c19-a0af-57e8-b214-9b996aa22dcd | textbox | Add Comment
52802da8-9083-5d85-ba05-041f077fa2f9 | button | Installation of primer as required? | Yes,No
11cf6d6b-970f-534d-a67f-12189be0207c | checkpoint | Record (Photo) batch number and date of manufacture of primer
12426dab-b28e-59f9-bf76-65ac0bf7a2b8 | checkpoint | Substrate free from surface water - photos attached below
e1c88a62-4a13-50dd-b783-4c96f2098cee | button | Installation of fillets/bandage to junctions as required? | Yes,No
b5951553-87e0-54f4-9f34-73e201e58912 | button | Installation of base coat? | Yes,No
d153b2ad-a9e1-5bc5-b847-1804c9ff3a64 | button | Base coat installed to minimum film thickness? | Yes,No
7111841c-3df3-5950-b15f-a7b4613ed9c0 | checkpoint | Record (Photo) batch number and date of manufacture of base coat
eeb5ac87-0a3c-57a2-b06d-02d4b9d8c2f4 | checkpoint | Area completed to manufacturer's specification - photos attached below
89035656-ffd3-5a98-a77b-32aa6515b923 | note | Attach Client Signature Below
8324dff4-8027-587a-ae5f-7736abbb5051 | checklist | Fatra Insulated Roof PVC Installation |  | Fatra Insulated Roof PVC Installation | e052db65-509a-42f5-96c1-2524a94d0b80
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
26f95d6f-0861-5c39-ac7b-1c74563d2b30 | textbox | SOW description entered
0071234a-e6dd-5dec-99fe-3eece8ca0c1e | checkpoint | Attach TDS for application (Download from Simpro)
4ad41a9e-9a48-549a-8119-389c3dda4b78 | checkpoint | Substrate Acceptance
2daac989-4a0f-58eb-9a1b-e0e016dc8088 | button | Substrate washed / cleaned & assessed for surface uniformity (photos attached below) | Yes,No
52bc80ea-2d0e-5077-b873-b9e71aa6487c | button | Substrate temperature is not less than 10*C and no greater then 35*C | Yes,No
4a8d3bfd-b839-5004-aa31-2d61173a79f3 | button | Substrate free from pooling or ponding water (Moisture gauge photo attached below) | Yes,No
d2ae3e64-ad5e-5893-883d-337ef982c3f6 | button | Adequate fall in substrate? | Yes,No
79edbabc-f800-5c0b-8b1c-7a65761baa0c | checkpoint | Vapour barrier installation
8c5ae038-c04e-5ff3-8d25-102118b809f1 | button | Primer installed to manufacturer's specification (Record batch and install photos) | Yes,No
3cc24bb8-7bac-5028-b2eb-972751ee0b6a | button | Vapour barrier installed to manufacturer's specification (Record batch and install photos) | Yes,No
6ddd5a5f-0fd0-5063-9222-d155d29a9220 | checkpoint | Insulation Installation
478e1ea9-1759-5dc7-a899-1b3f3d45f263 | button | Vapour barrier free of pooling water? | Yes,No
b618520a-1fe2-55ed-a70d-7d00f249c8b6 | button | Foam adhesive applied to manufacturer's specification? | Yes,No
af682ba3-4d7e-5b97-8483-0a3f81de0509 | button | Insulation installed to fall? | Yes,No,N/A
3cf7d56a-455c-5635-884a-1a6523e2190f | checkpoint | Membrane Installation
9aff8715-a3d5-5b5f-85c7-1689cd892eb6 | button | Installation of fleece-backed sheet membrane to floors with minimum 50mm overlaps? (Record batch and install photos) | Yes,No
1ff5fb4b-ef93-5d04-8e10-642cff9f2756 | button | Installation of termination profiles via to perimeter upstands & wall / floor junctions as per manufacturer's specifications as required? | Yes,No
760cd153-0792-56d5-8f92-c84e2fbcaf59 | button | Installation of sheet membrane to perimeters, incl. compatible sealant as required (profiles welded)? | Yes,No
ab7fc321-b145-55ec-824c-ab1fa60e3975 | checkpoint | Area completed to manufacturer's specification? - photos attached below
7c767690-268b-58a2-a5e6-b874d4bbab67 | checklist | Fatra Underslab |  | Fatra Underslab | 59626d8e-e598-4e98-951f-20afc306cf90
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
4fd8b23c-5741-5f5a-8704-f5a91ce4d594 | textbox | Enter SOW description and attach TDS
ea8a7a04-7a80-5979-b3f8-fe2b9a464b5e | checkpoint | Substrate Preparation
4b5b5cd9-0259-52fa-a7b8-c0b1d6f73cd1 | textbox | Substrate assessed for surface uniformity - photos attached below
e6b3c568-a5af-51d3-b875-079311fc92b7 | textbox | Substrate free from pooling, ponding of flowing water
20ae6e8d-5bc6-5ab3-a496-485822fdf9ed | checkpoint | Membrane installation
92849ad1-40bc-59f2-9c9d-5cdc9755ac29 | textbox | Record (Photo) batch number and date of manufacture of all materials
ca3955f1-df65-53a9-b959-1f4408899297 | textbox | Install Fatratex geotextile fabric
590592b9-ffa7-57aa-81b7-5777b400422c | textbox | Install Fatrafol 803V PVC membrane
e488ba1b-661a-52cb-a21a-f76542fb31b3 | textbox | Install Fatrafol 803V reinforcement PVC membrane to slab/wall junction
7bc2f05c-1e96-5b06-a3a3-8944722701c5 | textbox | Install FatraArmour protection board
eeb5ac87-0a3c-57a2-b06d-02d4b9d8c2f4 | checkpoint | Area completed to manufacturer's specification - photos attached below
47fb7ed4-d8b3-53a8-9bbb-0523534fdc80 | checklist | Fatra Walls |  | Fatra Walls | c040c331-bbbc-483e-95ee-2a145cd6d486
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
c3b5fd87-b2f2-5d8b-8fc1-240ef1d37e35 | textbox | Enter SOW description and attach TDS
ea8a7a04-7a80-5979-b3f8-fe2b9a464b5e | checkpoint | Substrate Preparation
8f1ad69f-ba66-51c0-879f-ed5ccafaa855 | textbox | Substrate assessed for surface uniformity - photos attached below
20ae6e8d-5bc6-5ab3-a496-485822fdf9ed | checkpoint | Membrane installation
8082483a-a102-54ae-bafd-dcda9a7d872e | textbox | Record (Photo) batch number and date of manufacture of all materials
1da0891b-7d73-5c3b-a894-cf603f1bf7a9 | textbox | Install Fatrafol 803V PVC membrane
250ffe27-e5ce-56c3-92f8-5a65f09c39be | button | Install FatraArmour protection board | Yes/No
aebc3b83-6170-57ef-af09-3cd8e39854b9 | button | Install Coreflute protection board | Yes/No
0fcd76f5-d7ed-5e13-986e-6f1d7ebcb2f3 | textbox | Install PVC termination profile
eeb5ac87-0a3c-57a2-b06d-02d4b9d8c2f4 | checkpoint | Area completed to manufacturer's specification - photos attached below
3ace243d-a832-51f2-af62-d372052cc2a6 | checklist | Floor Coatings |  | Floor Coatings | 99d711c5-ecff-4d6c-bda1-d3de3a725025
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
3f26cada-e56b-584c-8dcb-1536b6470f73 | textbox | Enter SOW description
0071234a-e6dd-5dec-99fe-3eece8ca0c1e | checkpoint | Attach TDS for application (Download from Simpro)
76a95f56-ca4d-559d-86c0-693a44210e48 | checkpoint | Substrate to be cleaned, mechanically grinded & assessed for surface uniformity - photos attached below
7eb21c5f-38d3-531c-8ebe-a1d632cacb41 | checkpoint | Substrate temperature is not less then 5*C and no greater then 35*C
9c3e1916-1e20-50b9-8d8b-3d8484e20f84 | checkpoint | Substrate free from pooling or ponding water - Moisture gauge photo attached below
ce8a85ac-a492-5a15-b7aa-33aad1d29bc9 | button | Adequate fall in substrate? | Yes,No
fb6c15f0-f9a3-5405-bbf7-2db45d72213d | note | If any of these checkpoints fail please provide information and required action by builder
703ec741-71ab-5a4e-8496-b721de9b1c95 | textbox | Add Comment
39022404-8c57-5cc7-9f41-4c816e758b86 | button | Installation of epoxy primer? | Yes,No
11cf6d6b-970f-534d-a67f-12189be0207c | checkpoint | Record (Photo) batch number and date of manufacture of primer
d9c05da7-bcf0-5921-bd2c-b7148b109654 | checkpoint | Substrate free from surface water?
5e2aad06-60aa-51a4-927d-654f2d161d0e | button | Construction joints marked for mirroring after application? | Yes,No,N/A
4819f37d-f025-5486-8628-cbeb76111e21 | button | Installation of base coat? | Yes,No
7111841c-3df3-5950-b15f-a7b4613ed9c0 | checkpoint | Record (Photo) batch number and date of manufacture of base coat
8bc5e7d6-77f3-5cc2-89cb-1eb88d579c2f | button | Broadcast of non-slip application if required | Yes,No,N/A
f170ef3f-2982-5fbc-80c8-244ca6a4d027 | button | Installation of top coat (UV stable if required)? | Yes,No,N/A
8e552cb8-84e8-5539-b200-d52414c4a4fd | checkpoint | Record (Photo) batch number and date of manufacture of top coat
c6d4c1e6-ac84-5fd8-8604-3c12d9b7d7c4 | button | Chase out onstruction joints and caulk? | Yes,No,N/A
eeb5ac87-0a3c-57a2-b06d-02d4b9d8c2f4 | checkpoint | Area completed to manufacturer's specification - photos attached below
ce4d57fa-7f27-5142-a0f3-3aef7126876e | note | Add Comment
ac965013-4f0e-5fe8-9a78-e6cd4885b163 | note | Attach Client Signature Below
038ecaac-c920-5d2b-832a-ae8493ca43d2 | checklist | Handover |  | Handover | aa9bb1f3-2b04-4200-bd6b-f139e83df835
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
3b38f2ae-4fbf-5eba-a72e-17576cf2ec03 | textbox | SOW description entered
f5e5e7e0-7d19-555d-897d-aa0b47fcdb62 | note | Bravada and Client Representative name/(s) and signature/(s) attached below
7e4d2733-ff69-503f-a0a1-bd6184123a6e | checklist | ILD Testing |  | ILD Testing | 31a98a89-a627-4ebc-a506-40f38981d51e
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
18316e6c-f288-5b53-add2-59f9e7bc75b3 | textbox | SOW description entered
947c8c9c-3d16-53a4-8bc9-171e68c683c5 | button | ILD Test Requested? | Yes,No
32bb3202-947f-5d37-bf1c-7737096492c0 | button | ILD Test Performed | Yes,No
62f52b83-632d-5c8b-86a3-fb3214bfe37f | checkpoint | ILD Test
a7d46359-d914-5d09-9434-ad143437f7b3 | note | ILD technician signature attached below
fb9ff672-0620-5cc0-bcd4-758d7e8b0e77 | note | ILD report attached below
1bc8719c-9ef3-59ef-ba13-7256d7cfd6a9 | checklist | Internal |  | Internal | 11a11c00-8ca7-4ab0-95eb-ce2ccb0ce838
03c1c327-37e4-500e-b066-868bbd08e7ea | checkpoint-no-value | Scope
4d51a533-c9f0-5d5b-966d-16fdf1d86c7c | note | Scope Description (from Bravada SOW) and item numbers
cc61a791-9f38-5a38-8ab5-99d3200b2187 | textbox | Enter SOW description
1e6a7583-4b56-53b4-bdbc-82026d735c79 | checkpoint | Substrate clear of dust, debris and contaminants (Attach photos below)
869b5318-907b-5380-b944-718ac7f08b0d | button | Adequate fall in substrate? | Yes,No
fc96a2dc-836e-5291-ac2d-b1baf2c92e90 | note | If any of these checkpoints fail please provide information and required action by builder
3012f7c6-7b7c-5b5d-9402-e7fb5dfe735f | textbox | Add Comment
fb24a488-9153-5589-a9f1-9368b9cb9cef | button | Installation of tape or caulk to junctions. | Yes,No
2a591944-09dd-5fa6-a55a-6ea10e0f1196 | button | Penetrations correctly detailed? | Yes,No
010a0299-59e6-5c50-b7ad-4cf1ad1f966a | button | Waterstop correctly detailed? | Yes,No,N/A
7e9fae6e-5532-50b1-a341-60ebb4c31574 | button | Installation of liquid membrane to manufacturer's specification? | Yes,No
8076184d-8423-5402-8e43-2a0e396b2c72 | button | Installation of liquid membrane to perimeters, incl. compatible sealant as required? | Yes,No
a0cb26eb-c661-554e-9222-6406fdc9296b | checkpoint | Area completed to manufacturer's specification? - attach photos below
25f92b01-acbf-54ca-a7ee-3a5f0299d87c | checkpoint | Record (Photo) batch number and date of manufacture of membrane
b24b58c1-87d2-56e3-918f-64a45620d7d3 | note | Attach Client Signature Below
94eff8b8-4516-58ef-ad8c-e18996e99f4d | checklist | Leak Remediation |  | Leak Remediation | c8121bcc-88d1-4e3a-99f3-e68035525780
a784da68-cfe9-5270-aa4f-37b5f30b9936 | checkpoint | Locate and identify source of leak
2481d615-6d87-538a-98d8-a8984a3f0ad1 | textbox | Enter description and location of leak
b9b68fd3-0d9c-515c-b2bb-288da4254e7b | button | Can Bravada offer a solution to the leak? | Yes,No
e1a62dd3-9ab7-5c11-921b-ac9daf539c47 | checkpoint | Methodology to resolve leak
204b828a-c3b7-54e5-9a1f-5f3898b920f5 | textbox | Enter methodology
f71cd974-cad2-5ad6-a5a4-11413ef3903f | note | Attach TDS for any products used
a1943af8-37ab-50cc-925a-d03b77793716 | checkpoint | Provide photos of completed remediation
f644056f-7d91-5260-b27f-5744125dcc8f | button | Is ILD testing required? | Yes,No
450135f3-e303-5541-bf94-8f2695e05a18 | button | If ILD testing is required, did it pass? | Yes,No,N/A
38db331b-8adf-5cb1-bed3-1b061e92e7d0 | button | Has the leak been remediated? | Yes,No
0cd24659-fb7a-5fbd-8368-728b62290ac2 | checklist | MataCryl Trafficable |  | MataCryl Trafficable | 4d01149f-08f1-4e83-93c3-e2e59a4694a9
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
38cab569-f797-59d2-a049-f646b6e97043 | textbox | Enter SOW description
0071234a-e6dd-5dec-99fe-3eece8ca0c1e | checkpoint | Attach TDS for application (Download from Simpro)
68fe01f2-4498-5723-b274-cc0f6f465d16 | checkpoint | Preliminary Substrate Assessment for Potential Rectification
f41d6911-96e6-577d-a0a7-3bc6758a5b91 | button | Adequate fall in substrate? | Yes,No,N/A
2fb105ca-3ae1-5199-8670-340d33612898 | textbox | Provide description, photos and plan identifying any areas where the client is required to repair/remediate the substrate
b12a3954-a7fc-580b-9fcb-57ce6ced03f9 | checkpoint | Substrate Assessment for Acceptance, and Adhesion Testing
6f113128-51af-5511-afe9-b111a1405d48 | button | Substrate deemed acceptable for membrane application as per VicRoads specification 691 | Yes,No
ea8a7a04-7a80-5979-b3f8-fe2b9a464b5e | checkpoint | Substrate Preparation
c8000910-8c67-5b7b-8c2a-a032b00cc875 | button | Substrate to be washed/cleaned | Yes,No
9057495b-9b53-5c2c-ba18-2cad305afcf9 | textbox | If any damage has occurred since initial assessment and/or rectification please identify and alert builder.
44d93ac6-2650-5282-858a-ada13a24f8de | button | Substrate ready for membrane application. | Yes,No
59293686-443f-5852-a3cd-a46f69fd1631 | checkpoint | Matacryl Primer H Application
b2e763ad-ba95-5878-9ceb-d191ec72b4d9 | button | Substrate free from surface water | Yes,No
c4407f4d-94f2-5785-90e4-6c9c1fafe4e7 | button | Substrate temperature is not less then 10*C and no greater then 35*C | Yes,No
2e23fcae-2653-52a0-9b3b-b20cf00e106a | button | Moisture content > 7% | Yes,No
dfb596f3-5d9a-5cdc-a8d6-ed6591ff52ae | textbox | Record (Photo) batch number and date of manufacture of primer
09b6bf38-9d29-5890-8c21-128961194399 | textbox | Record date/time, temperature and % catalyst at time of mixing primer
dd1c3c2f-d81d-5557-8f40-c94e88b66aab | button | Substrate free from surface water - record moisture reading | Yes,No
78849dc7-9782-5f12-8217-7915df27cfee | button | Primer installed before pot life expiry? | Yes,No
dafb7bc2-5c48-585f-9c09-6238793b147a | textbox | Record date and time of primer installation
0047e4db-c33f-50cc-a488-27d2d58cd341 | button | Quartz aggregate broadcast into primer | Yes,No
2b996476-a1fd-528d-8c26-d21078ddf33e | textbox | Record date and time of quartz broadcast
7d85d0dc-084a-5514-a666-eea9ae200692 | checkpoint | Matacryl Manual Base Coat Application
368ed5cd-c4a2-5018-bda3-6b671be97c16 | button | Substrate temperature is not less then 10*C and no greater then 35*C | Yes,No
2e758321-1bdd-514b-95d9-202a9e3702f9 | textbox | Record (Photo) batch number and date of manufacture of MataCryl Manual
2f0ba8f8-7f37-58c8-ba58-3e124f427971 | textbox | Record date/time, temperature and % catalyst at time of mixing MataCryl Manual
729a8143-5e4a-5026-a183-f590e573f797 | button | MataCryl Manual installed before pot life expiry? | Yes,No
c47a9f01-191c-5a16-8384-4ca01a01d005 | button | MataCryl Thix installed to upturns before pot life expiry? | Yes,No
9c80f2c8-47e3-58ff-bea7-93c26122775d | textbox | Record date and time of MataCryl Manual installation
c0f4ee7e-97bb-5b7b-8e10-3d045f124fac | checkpoint | Matacryl WL (Wearing Layer) First Top Coat Application
1cf936e9-0f91-590f-bdd9-fc996ce92fe5 | button | Substrate temperature is not less then 10*C and no greater then 35*C | Yes,No
e5b60403-f58a-5aa5-8667-982b9c9f69cc | textbox | Record (Photo) batch number and date of manufacture of MataCryl WL
efbb8808-ae77-5500-a1ba-f93dab1eefc9 | textbox | Record date/time, temperature and % catalyst at time of mixing MataCryl WL
9d2a4f39-2829-5fb2-a71a-9a7dc7e6f4e0 | button | MataCryl WL installed before pot life expiry? | Yes,No
e8b9541a-975f-5a87-ab76-a8fe6fe4eec1 | textbox | Record date and time of MataCryl WL installation
6d5ae0fd-b8c2-5833-be4b-b89312d071dd | button | Quartz aggregate broadcast into primer | Yes,No
d6105bab-218a-515f-849d-db54237fc03b | textbox | Record date and time of quartz broadcast
1deebec1-e60c-54c2-9b64-c7aff46f82c5 | checkpoint | Matacryl WL (Wearing Layer) Second Top Coat Application
dde7f578-1156-5dcc-b3f2-a431c0e4af3e | button | Substrate temperature is not less then 10*C and no greater then 35*C | Yes,No
1fa3c3c4-f5ce-5867-97a6-7b2de1276155 | textbox | Record (Photo) batch number and date of manufacture of MataCryl WL
b1943c27-30de-5334-b646-cb3b2c7a11e0 | textbox | Record date/time, temperature and % catalyst at time of mixing MataCryl WL
80604813-719d-5f55-a9d6-41532438344e | button | MataCryl WL installed before pot life expiry? | Yes,No
961a91c7-443d-5cbb-b2d9-6dbb76882ba8 | textbox | Record date and time of MataCryl WL installation
c0c55c1a-ad57-569d-8d12-725b9f986e1d | note | Attach Client Signature Below
fd848c92-02fa-5776-90df-3bb300821c5b | checklist | Park and Ride - Busway Sarnafil Installation |  | Park and Ride - Busway Sarnafil Installation | 68e4b566-6fb4-4be7-a7a4-e78e41fda697
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
ffb449bb-c4e6-5a2c-9ed3-33b7ebd2a759 | textbox | SOW description entered
f8d85dcb-75e7-5a30-8c80-44d74709972d | checkpoint | Attach TDS for application
ea8c9a49-fb0d-536d-8a52-5725d8f3ce75 | checkpoint | Substrate washed / cleaned & assessed for surface uniformity (photos attached below)
1423fb3d-ff83-5bda-8448-25aa461027f8 | checkpoint | Substrate temperature is not less than 10*C and no greater then 35*C
ff1ea789-9966-57f9-a85b-f3795c598d90 | checkpoint | Substrate free from pooling or ponding water (Moisture gauge photo attached below)
397acaa0-6d26-550e-b34f-454e3ed67c4d | checkpoint | Adequate fall in substrate?
c2216853-72c7-508f-9a28-586c18591746 | note | If any of these checkpoints fail information and required action by builder provided in comments below
9127c44b-7bf4-530d-b9ec-eb173b753077 | checkpoint | Saw cuts (15mm deep x 5 mm wide) at Watertite membrane junctions able to accept Type 5 profile?
2eed36ad-a450-5192-b96e-59374da6953e | checkpoint | Installation of Type 6 profile for junction with Watertite membrane?
9839b1e3-5283-5e13-b1b6-03e8e2fedfd7 | checkpoint | Installation of Type 8 profile on upturn?
a497bd5d-19b0-5157-b7bf-3137bc125a41 | checkpoint | Adhesive installed to manufacturer's specification?
ffe09545-22d3-51ef-832d-7e8725f574f2 | checkpoint | Record (Photo) batch number and date of manufacture of adhesive
b9d5da2e-4396-55e3-af9f-a6d24e814f1c | checkpoint | Installation of sheet membrane to floor areas (min. 50mm overlaps)?
836c1a0c-3dfb-5ec2-92df-058f887b3d52 | checkpoint | Column bases (24) detailed to manufacturers specification?
34fe9424-e263-5086-8a0a-e053e5f5c53d | checkpoint | Installation of Type 5 profile to junction?
182c41fa-c7bc-536e-a9fd-c6b572a04913 | checkpoint | Installation of sheet membrane to perimeters, incl. compatible sealant as required (profiles welded)?
ab7fc321-b145-55ec-824c-ab1fa60e3975 | checkpoint | Area completed to manufacturer's specification? - photos attached below
5c64e867-1817-5675-a03d-d4c1cd3b3bdf | checklist | Park and Ride - Green Roof Sarnafil Installation |  | Park and Ride - Green Roof Sarnafil Installation | 178e36ce-5946-4c49-93dc-0311066813cb
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
409a702c-466b-51c7-a905-7d1741649b69 | textbox | SOW description entered
f8d85dcb-75e7-5a30-8c80-44d74709972d | checkpoint | Attach TDS for application
ea8c9a49-fb0d-536d-8a52-5725d8f3ce75 | checkpoint | Substrate washed / cleaned & assessed for surface uniformity (photos attached below)
1423fb3d-ff83-5bda-8448-25aa461027f8 | checkpoint | Substrate temperature is not less than 10*C and no greater then 35*C
ff1ea789-9966-57f9-a85b-f3795c598d90 | checkpoint | Substrate free from pooling or ponding water (Moisture gauge photo attached below)
397acaa0-6d26-550e-b34f-454e3ed67c4d | checkpoint | Adequate fall in substrate?
93913b53-55f0-5427-8614-f5f3c1a5340c | note | If any of these checkpoints fail information and required action by builder provided in comments below
9127c44b-7bf4-530d-b9ec-eb173b753077 | checkpoint | Saw cuts (15mm deep x 5 mm wide) at Watertite membrane junctions able to accept Type 5 profile?
2eed36ad-a450-5192-b96e-59374da6953e | checkpoint | Installation of Type 6 profile for junction with Watertite membrane?
9839b1e3-5283-5e13-b1b6-03e8e2fedfd7 | checkpoint | Installation of Type 8 profile on upturn?
a497bd5d-19b0-5157-b7bf-3137bc125a41 | checkpoint | Adhesive installed to manufacturer's specification?
ffe09545-22d3-51ef-832d-7e8725f574f2 | checkpoint | Record (Photo) batch number and date of manufacture of adhesive
b9d5da2e-4396-55e3-af9f-a6d24e814f1c | checkpoint | Installation of sheet membrane to floor areas (min. 50mm overlaps)?
35da5b92-f423-5a57-979c-b368c1da2078 | checkpoint | Siphonic drains detailed to manufacturers specification?
34fe9424-e263-5086-8a0a-e053e5f5c53d | checkpoint | Installation of Type 5 profile to junction?
182c41fa-c7bc-536e-a9fd-c6b572a04913 | checkpoint | Installation of sheet membrane to perimeters, incl. compatible sealant as required (profiles welded)?
44113032-0a54-52f9-94d0-3cd09a949b26 | checkpoint | Installation of Dilatec tape detail to existing P-1200 membrane?
ab7fc321-b145-55ec-824c-ab1fa60e3975 | checkpoint | Area completed to manufacturer's specification? - photos attached below
6f245a75-c78d-5174-908c-dbe7824d66d5 | checklist | Park and Ride - Watertite Membrane Junction Installation |  | Park and Ride - Watertite Membrane Junction Installation | 1cb0a33a-55e0-4890-8686-871458d17b32
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
f2edc11d-034a-5740-a0f8-61ce2009ef08 | textbox | SOW description entered
0071234a-e6dd-5dec-99fe-3eece8ca0c1e | checkpoint | Attach TDS for application (Download from Simpro)
ea8c9a49-fb0d-536d-8a52-5725d8f3ce75 | checkpoint | Substrate washed / cleaned & assessed for surface uniformity (photos attached below)
1423fb3d-ff83-5bda-8448-25aa461027f8 | checkpoint | Substrate temperature is not less than 10*C and no greater then 35*C
ff1ea789-9966-57f9-a85b-f3795c598d90 | checkpoint | Substrate free from pooling or ponding water (Moisture gauge photo attached below)
b7aebcc3-5236-541b-a059-1c52768cb25a | note | If any of these checkpoints fail information and required action by builder provided in comments below
43aaa46e-f4f0-52a3-8cc8-207ac0456b90 | checkpoint | Saw cuts (15mm deep x 5 mm wide) at Watertite membrane (Watertite side) junctions able to accept Type 5 profile?
34fe9424-e263-5086-8a0a-e053e5f5c53d | checkpoint | Installation of Type 5 profile to junction?
a497bd5d-19b0-5157-b7bf-3137bc125a41 | checkpoint | Adhesive installed to manufacturer's specification?
ffe09545-22d3-51ef-832d-7e8725f574f2 | checkpoint | Record (Photo) batch number and date of manufacture of adhesive
00e0b25f-15e9-503a-babb-8813c769dc82 | checkpoint | Installation of sheet membrane (min. 50mm overlaps) to ?
ab7fc321-b145-55ec-824c-ab1fa60e3975 | checkpoint | Area completed to manufacturer's specification? - photos attached below
e702049d-513e-50e0-ba0f-b9c3a30a518b | checklist | Planter (Liquid Membrane) |  | Planter (Liquid Membrane) | 9c35b224-d34c-4656-abdf-0fb1c4aec786
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
55f65dfe-760b-5b73-bdb4-8997a2f087bd | textbox | Enter SOW description
0071234a-e6dd-5dec-99fe-3eece8ca0c1e | checkpoint | Attach TDS for application (Download from Simpro)
1329bf5d-f2ef-5dbd-b3f9-5aeb24e7ff37 | checkpoint | Substrate cleaned & assessed for suitability to screed to? (Attach photos below)
21b206d4-00be-5fa8-963e-13977b841c18 | checkpoint | Sufficient fall in planter base?
864ee1dd-6493-5f57-b087-011219daa789 | button | Adequate fall in substrate? | Yes,No
10320f26-c5b1-5eee-9e5f-02ef7f693ba4 | checkpoint | Substrate free from pooling or ponding water?
84d00589-e713-58c8-8bd2-e8d1ce1b36d0 | note | If any of these checkpoints fail please provide information and required action by builder
c146c4e7-73dd-5f93-9540-c41f6f5bb5ab | textbox | Add Comment
18e6ea1f-5fea-579e-9ea6-8a4334a81d2d | checkpoint | Liquid membrane installed to manufacturer's specification?
aa08d75a-892c-5ca8-9e30-9914e7d31cf3 | checkpoint | Anti-root additive applied to manufacturer's specification?
54f01b38-86b9-5d73-8728-075f257e2b62 | checkpoint | Signoff of compliant installation.
dc461f20-5f0c-559d-8d2e-4708a95a4c1f | note | Client Signature
c4229050-0130-589d-9a4f-784760cd9fbe | checklist | Planter (PVC/Butynol Membranes) |  | Planter (PVC/Butynol Membranes) | e8f23b64-39c4-472a-a757-c0ce23821604
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
6385cdfb-584c-5484-8cf0-89b942696a49 | textbox | Enter SOW description
0071234a-e6dd-5dec-99fe-3eece8ca0c1e | checkpoint | Attach TDS for application (Download from Simpro)
1329bf5d-f2ef-5dbd-b3f9-5aeb24e7ff37 | checkpoint | Substrate cleaned & assessed for suitability to screed to? (Attach photos below)
21b206d4-00be-5fa8-963e-13977b841c18 | checkpoint | Sufficient fall in planter base?
e58806ba-3500-59dd-bf9d-a634afd5be14 | button | Adequate fall in substrate? | Yes,No
10320f26-c5b1-5eee-9e5f-02ef7f693ba4 | checkpoint | Substrate free from pooling or ponding water?
9120d6ac-b79f-5638-98bc-27ae54e817ed | note | If any of these checkpoints fail please provide information and required action by builder
a54d7a1f-e2fd-54ad-af98-15b5cd2aebfb | textbox | Add Comment
f0ff68a6-4f4f-5604-85b5-88aa92f6b4dd | checkpoint | Sheet membrane installed to manufacturer's specification?
ebb12dc6-4eba-5d81-bca9-ffd0c9bcb5b0 | checkpoint | Termination pressure bar installed?
54f01b38-86b9-5d73-8728-075f257e2b62 | checkpoint | Signoff of compliant installation.
13a895d8-1016-5913-ba46-12351a90dad5 | note | Attach Client Signature Below
4c32e160-99bc-5891-bf27-731f691ba471 | note | Client Signature
492ef949-70a6-5567-bdb6-be2525f025ae | checklist | Planter (Torch-on Membrane) |  | Planter (Torch-on Membrane) | 03188f17-04db-4616-9c98-3fe37468f3ef
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
d429615e-3614-51fa-9d54-eb8dffd7304f | textbox | Enter SOW description
0071234a-e6dd-5dec-99fe-3eece8ca0c1e | checkpoint | Attach TDS for application (Download from Simpro)
1329bf5d-f2ef-5dbd-b3f9-5aeb24e7ff37 | checkpoint | Substrate cleaned & assessed for suitability to screed to? (Attach photos below)
21b206d4-00be-5fa8-963e-13977b841c18 | checkpoint | Sufficient fall in planter base?
4b660411-e908-56ae-8c2e-8b590368dc37 | button | Adequate fall in substrate? | Yes,No
10320f26-c5b1-5eee-9e5f-02ef7f693ba4 | checkpoint | Substrate free from pooling or ponding water?
98fbdf31-d16e-5252-b2e9-6a0dc04a7687 | note | If any of these checkpoints fail please provide information and required action by builder
1092271e-f779-5b88-8f6f-f6572056249a | textbox | Add Comment
64917915-390c-55a0-b368-4f3b1f1cab9c | checkpoint | Base layer membrane installed to manufacturer's specification?
38325017-8ddc-41aa-87a1-a8be1db3227f | checkpoint | Base layer membrane installed to manufacturer's specification?
cbc3270a-82d0-5757-85dc-e6a7a0f59424 | checkpoint | Anti-root layer membrane applied to manufacturer's specification?
ebb12dc6-4eba-5d81-bca9-ffd0c9bcb5b0 | checkpoint | Termination pressure bar installed?
54f01b38-86b9-5d73-8728-075f257e2b62 | checkpoint | Signoff of compliant installation.
8cc58af8-a282-5d42-9662-38d2a2db4483 | note | Client Signature
a9d17f03-30dc-5405-beb1-897a46793894 | checklist | PVC Installation (Sarnafil and Cosmofin) |  | PVC Installation (Sarnafil and Cosmofin) | 9350c59e-6fdc-485e-8611-85a5f46cf85b
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
a24842c1-6839-5ab3-bc79-de779a7aea9e | textbox | SOW description entered
0071234a-e6dd-5dec-99fe-3eece8ca0c1e | checkpoint | Attach TDS for application (Download from Simpro)
ea8c9a49-fb0d-536d-8a52-5725d8f3ce75 | checkpoint | Substrate washed / cleaned & assessed for surface uniformity (photos attached below)
1423fb3d-ff83-5bda-8448-25aa461027f8 | checkpoint | Substrate temperature is not less than 10*C and no greater then 35*C
ff1ea789-9966-57f9-a85b-f3795c598d90 | checkpoint | Substrate free from pooling or ponding water (Moisture gauge photo attached below)
50c2b7d1-fc5d-519d-8ad6-99e1c413f3f7 | button | Adequate fall in substrate? | Yes,No
cc4e28ab-6952-55e9-8433-8513d8a51e62 | note | If any of these checkpoints fail information and required action by builder provided in comments below
2e3e37f3-0231-5d44-a14a-567d0cd4e841 | button | Adhesive installed to manufacturer's specification? | Yes,No
ffe09545-22d3-51ef-832d-7e8725f574f2 | checkpoint | Record (Photo) batch number and date of manufacture of adhesive
cf871860-27b0-574e-9daf-5691153f7fd5 | note | If any of these checkpoints fail information and required action by builder provided in comments below
9e204e94-ff4b-51c7-b069-68bdfd57e394 | button | Installation of termination profiles via to perimeter upstands & wall / floor junctions as per manufacturer's specifications as required? | Yes,No,N/A
8a873277-9ffd-52c5-9636-96a3afb49e74 | button | Installation of sheet membrane (min. 50mm overlaps)? | Yes,No
1c9a2e48-224b-556b-8338-47bdfdd0c930 | button | Installation of sheet membrane to perimeters, incl. compatible sealant as required (profiles welded)? | Yes,No
ab7fc321-b145-55ec-824c-ab1fa60e3975 | checkpoint | Area completed to manufacturer's specification? - photos attached below
dd0b4400-56c9-503c-b3ee-255dfd494b7b | checklist | PVC Installation (Sikaplan) |  | PVC Installation (Sikaplan) | b6fe8403-1692-45db-9e64-d20ae2975b13
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
f4eb22f9-bcfc-5f3b-b0b9-18ecad7bbe72 | textbox | SOW description and TDS for application (Download from Simpro)
d2fa7b9a-e7e0-5906-9f89-5f9dd4c24f3b | checkpoint | Substrate Assessment
13c1fa84-a225-51ed-956d-656cac7c3da7 | textbox | Substrate washed / cleaned & assessed for surface uniformity (photos attached below)
eee51d2f-2ed0-569b-bf3e-539ecb3d72dd | textbox | Substrate temperature is not less than 10*C and no greater then 35*C
41153742-0ec7-5426-ad9d-e6c01ce4bfe7 | textbox | Substrate free from pooling or ponding water (Moisture gauge photo attached below)
91a203aa-e157-5c64-bb7e-9b373bd34948 | textbox | Adequate fall in substrate
f7e4fbe5-2158-5198-b609-7f7995972164 | note | If any of these checkpoints fail, information and required action by builder provided in comments below
8a29574f-a5d7-555c-8a8c-84b59305f31d | checkpoint | Membrane Installation to Flats
684440cc-fb06-5907-a0a2-536eaeb3f056 | textbox | Record (Photo) batch number and date of manufacture of Sarnacol 2152 adhesive and SikaPlan rolls
e1c7f4c9-35d7-5f9b-a8b7-b3cef087a2e8 | textbox | Sarnacol 2152 Adhesive installed to manufacturer's specification?
f6f29d68-59ea-5e28-b647-d61de2224c8b | textbox | Install and weld Sikaplan membrane over Sarnacol 2152 adhesive (min. 50mm overlaps)
1637cd27-c0d8-51aa-b61a-8fecb7bfd1c7 | button | Sufficient lap of Sikaplan left extended beyond formwork to create upturn? | Yes,No
ebc5e33c-66b1-562d-a42e-0d7154626c40 | checkpoint | Membrane Installation to Upturns
235410f0-442a-5600-928a-df41d41cfb7b | textbox | Record (Photo) batch number and date of manufacture of Sikadur 31 epoxy, WP Tape, Sarnacol 2152 adhesive and Sikaplan rolls
b92dd499-2b53-552a-9ae7-c3942693cd0e | textbox | Sikadur 31 epoxy installed to manufacturer's specification
ccdeb512-cbad-5705-b204-10af80392858 | textbox | WP Tape installed into Sikadur 31 epoxy installed to manufacturer's specification
35c13d7d-cff6-5a9c-877a-1eeadb187fa7 | textbox | Sarnacol 2152 Adhesive installed to manufacturer's specification
dcc2f8f0-34b1-5218-91e3-7ef3ad756b4e | textbox | Install and weld Sikaplan membrane over Sarnacol 2152 adhesive (min. 50mm overlaps)
961bd46f-455d-5297-9862-3c046f17738c | textbox | Installation of backing rod to junction
ff6bfb8f-1c3c-5c43-bafb-899480a639eb | checkpoint | Waterbar Installation to Perimeter
21f7e355-8d32-5ec7-b850-bd07bf0fbd40 | textbox | Record (Photo) batch number and date of manufacture of Sika Waterbar
15af6164-1098-5212-b529-514c25786333 | textbox | Install and weld Sika Waterbar to perimeter of Sikaplan membrane, approximately 200m from formwork.
24ff0f12-a02d-50f7-942a-714bae8c18f9 | checkpoint | Protection Installation
03d2b305-ae2d-596d-ae77-606365457e2f | button | Protection required? | Yes,No
99f4e5f1-6a64-54fb-b854-3a3340d8244b | textbox | If "Yes" to above, install contracted protection board with non-slip rating to membrane.
eeb5ac87-0a3c-57a2-b06d-02d4b9d8c2f4 | checkpoint | Area completed to manufacturer's specification - photos attached below
9b846f2a-0e7c-5464-a603-6adb30c0a54a | checklist | PVC Installation (Wolfin) |  | PVC Installation (Wolfin) | e7863054-93cd-4fd6-b82f-35cd97b0b799
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
5e87aaf3-848d-54dc-aed4-fb299b5d3e1f | textbox | SOW description entered
0071234a-e6dd-5dec-99fe-3eece8ca0c1e | checkpoint | Attach TDS for application (Download from Simpro)
ea8c9a49-fb0d-536d-8a52-5725d8f3ce75 | checkpoint | Substrate washed / cleaned & assessed for surface uniformity (photos attached below)
1423fb3d-ff83-5bda-8448-25aa461027f8 | checkpoint | Substrate temperature is not less than 10*C and no greater then 35*C
54c5fc1a-f7e2-55a8-946e-86012539280f | checkpoint | Substrate free from pooling or ponding water, and adequate fall in substrate (Moisture gauge photo attached below)
ab2e9244-5b07-5e30-9e9c-5a192118bbed | note | If any of these checkpoints fail information and required action by builder provided in comments below
0154b2c6-7140-5524-9aba-64f5bdb912ef | button | Bitunamel primer installed to manufacturer's specification? | Yes,No
b1a1edef-d018-52b0-b69f-5f84a94f4917 | button | Bitunamel primer given adequate time (4 hours) to cure – as per manufacturer's specification? | Yes,No
331af4ff-2c7b-5436-a835-6a5868efab95 | checkpoint | Record (Photo) batch numbers and dates of manufacture of bitunamel primer
a1d118c5-3add-57ed-ba65-10a2baf7cc6f | checkpoint | Area primed and suitable for membrane application. Substrate free of contaminants - photos attached below
71ddeaa2-c7f8-5ae8-a125-df17c8d31eb0 | textbox | If inspection failed, please provide reasons and recommended course of action
43afe1ca-b3d2-5fc3-a48e-f0a2f54c5e0b | button | Installation of termination profiles via to perimeter upstands & wall / floor junctions as per manufacturer's specifications as required? | Yes,No,N/A
4b655e9d-8d96-58e7-a62c-fd139265f701 | button | Installation of sheet membrane (min. 50mm overlaps)? | Yes,No
870274a2-8afd-53fc-a7ea-931fbf24eb93 | button | Installation of sheet membrane to perimeters, incl. compatible sealant as required (profiles welded)? | Yes,No
ab7fc321-b145-55ec-824c-ab1fa60e3975 | checkpoint | Area completed to manufacturer's specification? - photos attached below
a6cad3b2-234a-5dfd-9505-ebe73608ce43 | checkpoint | Manufacturer Inspection
0e2e8602-7fa9-5e2f-bb20-775f7eeac4a9 | note | Manufacturer's Warranty Certificate attached below
466b2095-4a02-5f9c-97a1-34a3b3699d58 | checklist | Retaining Wall (Liquid) |  | Retaining Wall (Liquid) | f2408195-41bb-438c-8136-532454d6a443
03c1c327-37e4-500e-b066-868bbd08e7ea | checkpoint-no-value | Scope
55382fce-7b7f-5401-b909-16afe9dcd713 | note | Scope Description (from Bravada SOW) and item numbers
8583a526-51ba-562e-b2bf-c9edb009eb6a | textbox | Enter SOW description
0071234a-e6dd-5dec-99fe-3eece8ca0c1e | checkpoint | Attach TDS for application (Download from Simpro)
4927163e-dfcf-5298-9939-256c3b2739a7 | checkpoint | Substrate clear of depressions or protrusions that could damage membrane? (Attach photos)
7be925a5-c873-5f84-a1b0-45dffc1a5a72 | button | Installation of liquid membrane as required? | Yes,No
190adbd3-4574-534f-be3c-7584bd1024c5 | checkpoint | Area completed to manufacturer's specification? (Attach photos)
a961f6c2-4aa4-5a8c-95b4-1f44c824478a | button | Cement sheet installed? | Yes,No,N/A
f4813d74-8268-584f-881b-b135314ada18 | button | Corflute installed installed? | Yes,No,N/A
6e1b9b59-c73e-5391-94ab-937968f3479e | button | Drainage cell and geotextile fabric installed? | Yes,No,N/A
bf101524-34df-5bc6-a238-79c40232f4d8 | checkpoint | Backfilled within manufacturer's specified timeframe?
1553c7ea-f385-5090-a18a-2ac00e7ff87a | note | Attach Client Signature Below
d9a357e3-e1fb-5eab-aa54-4de31727756c | checklist | Retaining Wall (Sheet) |  | Retaining Wall (Sheet) | d125bc12-6b81-4452-b54e-8329025e1eb3
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
bd2ecaf4-f6c3-5713-844a-31d581378dc8 | textbox | Enter SOW description
0071234a-e6dd-5dec-99fe-3eece8ca0c1e | checkpoint | Attach TDS for application (Download from Simpro)
4927163e-dfcf-5298-9939-256c3b2739a7 | checkpoint | Substrate clear of depressions or protrusions that could damage membrane? (Attach photos)
ae27e60e-049d-5e9e-bc00-842e9667ab99 | button | Granules installed at cold joint? | Yes,No,N/A
3fc97ba5-af3f-55b1-b989-184b5b3eeedd | button | Installation of sheet membrane as required? | Yes,No
96b13be9-072a-5ae7-bce1-a188e823f842 | button | Termination pressure bar installed as required? | Yes,No
190adbd3-4574-534f-be3c-7584bd1024c5 | checkpoint | Area completed to manufacturer's specification? (Attach photos)
e887b86d-1439-5365-bb45-2c90594ad23c | textbox | If inspection failed, please provide reasons and recommended course of action.
5e3a574c-288d-537a-b40e-efded9fcf5e0 | button | Cement sheet installed? | Yes,No,N/A
bd9ae0c8-0582-5cc0-b246-cf7bef68adc2 | button | Corflute installed installed? | Yes,No,N/A
f32401ee-515d-5cf8-9444-dfdf8efc4006 | button | Drainage cell and geotextile fabric installed? | Yes,No,N/A
bf101524-34df-5bc6-a238-79c40232f4d8 | checkpoint | Backfilled within manufacturer's specified timeframe?
e15e78d2-b48b-5ee2-a15e-90127b1f3c6b | note | Attach Client Signature Below
94d23397-2d4e-5d96-88c0-7cf4ab57fa4d | checklist | Screed |  | Screed | c0ee6532-ea4f-434e-bc70-f1925b85ff81
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
3b65925b-c9f4-538a-a35e-7b32327294d1 | textbox | Enter SOW description
92945f9d-38ce-532b-bc41-6566890782f6 | checkpoint | Substrate cleaned & assessed for suitability to screed to - photos attached below
269b872b-821d-5828-8808-ee422d92a60d | checkpoint | Sufficient setdown depth available to create adequate fall to wastes?
10320f26-c5b1-5eee-9e5f-02ef7f693ba4 | checkpoint | Substrate free from pooling or ponding water?
6700952f-d433-5ef2-83bc-4fb99f31ce9a | checkpoint | Minimum screed thickness of 20mm at waste available to achieve 1:100 fall?
eaf08061-bc1a-5ae4-a1c3-dffd84468e82 | note | If any of these checkpoints fail please provide information and required action by builder
d89c7388-56d8-577c-a91a-472b837ee843 | textbox | Add Comment
a05daf21-0b4a-5c0b-91e6-073db66a4575 | button | Screed mixed to manufacturer's specifications? | Yes,No
6dc157d3-aa0c-5fa7-a4ba-d8cef20e914b | button | Slurry applied for bonding as per manufacturer's specification? | Yes,No
ff832e08-268b-53c7-ae5a-6316d4df57d5 | checkpoint | Screed completed and suitable for membrane application - photos attached below
60712525-fb33-5b1c-bd95-163798d73b72 | note | Attach Client Signature Below
41dc33f9-1918-49cf-93b7-cceff97658c5 | checklist | SikaPlan unbonded PVC with grout control |  | SikaPlan unbonded PVC with grout control | b53334e1-4f9d-4040-97e8-96d0f5740d9e
cdc3a06d-9d0e-4038-aa28-8c020c9e6f07 | section | Details
1a16c554-8693-49ce-bf93-fe2d7404d6ee | checkpoint | Scope Description with slab/wall area identification
60d76200-b93d-5caf-ba0a-73d541defefc | textbox | SOW description
3fb283da-fbad-5ab0-a8b4-1e80145817cb | button | Attach TDS for application | Yes,No,N/A
3a26f3f6-29db-47b8-ada7-c5a9aa534dce | checkpoint | Substrate Acceptance
d0f7daa4-aaa9-5259-933c-17e472a73328 | button | Substrate washed / cleaned & assessed for surface uniformity (photos attached below) | Yes,No
648bf309-dd07-5aed-a644-d0e1f57212d1 | button | Substrate temperature is not less than 10*C and no greater then 35*C as per TDS Service Temperature | Yes,No
6a1735a5-710b-5798-aeeb-e8b044722a45 | button | Substrate free from pooling or ponding water, and adequate fall in substrate | Yes,No
a8843cce-957d-57ce-8cae-d1431a3dc59e | note | If any of these checkpoints fail information and required action by builder provided in comments below
21237081-e9fa-40c9-aee5-38a226a85080 | checkpoint | Geotextile Cushion Layer
d6db30e4-2e35-5f36-9a57-7d9b7ecc23e9 | button | Geotextile laid with 100mm overlap? | Yes,No
6cda073b-0e4b-5ed9-8185-117d96599fb4 | button | Laps taped? | Yes,No
913c56ad-160d-43ee-bb55-55576881ce18 | checkpoint | Membrane Installation
570b2a4b-e6c1-5248-9634-9d0614a6950e | button | Substrate free from pooling or ponding water? | Yes,No
a24b606d-1530-55ca-8221-5cdbcd848b3b | button | Membrane installed with minimum 40mm overlap? | Yes,No
85dee9df-72fa-5a32-9c53-c6696a863d72 | button | Sika Dilatec Tape installed to any terminations where required? | Yes,No
54c91fe5-0bc8-502e-b300-968b63754987 | button | All Dilatec Tape terminations welded as per manufacturer's specification? | Yes,No
b45e6e96-8d7b-4308-8afa-220860879ce1 | checkpoint | PVC Waterstop (Construction Joins and Compartments)
e4f4fed4-4358-5e49-b237-b9e156426136 | button | Waterbar installed along construction joint to match grout control compartment where possible? | Yes,No,N/A
d6d6025b-1ae3-5d36-b50b-8d5bc2cbd470 | button | Waterbar installed to create 150m2 compartments? | Yes,No,N/A
8fe781d0-931d-5f12-b49d-aa8cbd5b91cd | button | Waterbar installed along blinded wall where required? | Yes,No,N/A
bbc6ff1b-6780-53e7-84f2-793bd5ff5bcc | button | Waterbar installed along formwork where insitu wall will be installed where required? | Yes,No,N/A
285ab9f6-ba84-57d4-8cdf-ec2a59af5133 | button | All jig weld joins fully fused? | Yes,No,N/A
5a960668-8fee-4a0c-b3db-cf7bfcd93538 | checkpoint | Grout Control To Compartments
98e63b80-942b-5621-bf0f-acbf5c4dbd7c | button | Grout hose installed as per manufacturer's layout and specification? | Yes,No,N/A
0217980e-6f5a-5847-b748-ca67cf5be55f | button | Grout flanges installed to hose ends? | Yes,No,N/A
959dcdc6-85b1-5a97-8746-66dd801c93b2 | button | Sufficient hose included to reach proposed/agreed injection box location? | Yes,No,N/A
87c8124f-b3d0-49c5-8d22-2e23227c5e71 | checkpoint | Construction Joins - Hydrophilic Waterstop and Grout Hose
cd767a98-2fd7-5aeb-b010-86770d0634d2 | button | Grout hose installed as per manufacturer's layout and specification? | Yes,No,N/A
26bdd70a-bfe4-5144-96f0-762057b25536 | button | Sufficient hose included to reach proposed injection box location? | Yes,No,N/A
5bf0ad61-b350-51b9-be3f-32e3dbe24bc4 | button | Hydrophilic Waterstop installed to manufacturer's specification? | Yes,No,N/A
ab075be8-0e16-4d4e-8011-1bbbd3457ffa | checkpoint | Post Steel Installation
1d0027fd-ac04-5321-9604-ecd98a727312 | button | Injection box for grout control system installed to manufacturer's specification? | Yes,No,N/A
46c9d16e-58f9-5f76-afec-b166543c662b | button | Hose for grout control system connected with 300mm excess beyond injection box? | Yes,No,N/A
1a076878-2227-5373-a378-9178fd83a0ab | button | Injection box for SikaFuko CJ installed to manufacturer's specification? | Yes,No,N/A
cafe422d-26e6-5a5d-a8db-48d8f3ce2216 | button | Hose for for SikaFuko CJ connected with 300mm excess beyond injection box | Yes,No,N/A
060120de-ef34-4c60-8d0a-7650325c2f15 | checkpoint | Manufacturer Inspection
0a448d2c-2126-5d97-9734-1c44deeb65ef | note | Manufacturer's Warranty Certificate attached below
36595dcd-285a-5adf-8ae7-11cb2818d065 | checklist | Torch-On Installation |  | Torch-On Installation | 69424b12-9600-4d79-860a-e028b8243c46
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
d220d04b-c396-5512-a5c7-30991ea9e57d | textbox | Enter SOW description
0071234a-e6dd-5dec-99fe-3eece8ca0c1e | checkpoint | Attach TDS for application (Download from Simpro)
c2aa6d82-bfce-5616-acef-6e6e505b0a9d | checkpoint | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below
29f3ee07-43c1-5255-be07-20c921096030 | checkpoint | Substrate temperature is not less then 10*C and no greater then 35*C
ff1ea789-9966-57f9-a85b-f3795c598d90 | checkpoint | Substrate free from pooling or ponding water (Moisture gauge photo attached below)
121b9edb-af20-5e98-ad90-0202333ac2d6 | button | Adequate fall in substrate? | Yes,No
eee796fc-cb76-54e8-b9d0-3a7362804ccc | button | Bitumen primer installed to manufacturer's specification? | Yes,No
43e05bc0-a958-5eea-92b0-7490f58b8e23 | button | Primer given adequate time to cure – as per manufacturers specification? | Yes,No
07c4e915-c21e-51f0-b8fe-5f1e73bab6ed | checkpoint | Area completed and suitable for membrane application - photos attached below
9ee8a6c3-644d-5cf0-bd6c-2e2dfd817833 | checkpoint | Substrate clear of dust, debris and contaminants - photos attached below
ceb2f537-c732-55a0-b159-9f2c552dfbc2 | checkpoint | Substrate free from surface water? (Moisture gauge photo attached below)
468068ea-86d3-5ba6-a2f1-93241294c350 | button | Installation of base layer membrane (min. 50mm overlaps) ? | Yes,No
da69695a-e9db-5e18-9787-cc0fbd4946a7 | dropdown | Type of second layer | Normal,Mineral,Antiroot
a11ea690-2aa9-5555-bb80-81a36dc94c05 | button | Installation of second layer membrane (min. 50mm overlaps) ? | Yes,No
2f16b0d9-7fcb-5c04-bba6-4badca2e001b | button | Termination pressure bar installed to all upturns where required? | Yes,No
ab7fc321-b145-55ec-824c-ab1fa60e3975 | checkpoint | Area completed to manufacturer's specification? - photos attached below
bf630246-37ce-58b2-904e-699c1b348510 | note | Attach Client Signature Below
8ac4ee3d-bc32-538c-9508-a098b828d7fc | checklist | VerseSeal (Exposed) |  | VerseSeal (Exposed) | 58146530-11d5-4924-bb70-3fc94808e941
6ebcab53-465c-5284-bfe2-0fffc687bdd3 | checkpoint | Scope Description (from Bravada SOW) and item numbers
6f06d353-3dd6-5bf7-96b4-d75dbad1d3b0 | textbox | Enter SOW description
0071234a-e6dd-5dec-99fe-3eece8ca0c1e | checkpoint | Attach TDS for application (Download from Simpro)
c2aa6d82-bfce-5616-acef-6e6e505b0a9d | checkpoint | Substrate to be washed / cleaned & assessed for surface uniformity - photos attached below
29f3ee07-43c1-5255-be07-20c921096030 | checkpoint | Substrate temperature is not less then 10*C and no greater then 35*C
9c3e1916-1e20-50b9-8d8b-3d8484e20f84 | checkpoint | Substrate free from pooling or ponding water - Moisture gauge photo attached below
a3c34d00-a293-5232-8c95-9323634dae25 | note | If any of these checkpoints fail please provide information and required action by builder
de69f744-6ffd-50cc-9821-bd6ee42cdec1 | textbox | Add Comment
11cf6d6b-970f-534d-a67f-12189be0207c | checkpoint | Record (Photo) batch number and date of manufacture of primer
8d35f484-c9a5-5ac5-9ec0-280ec61875d8 | button | Installation of primer as required (90 minute dry time)? | Yes,No
7111841c-3df3-5950-b15f-a7b4613ed9c0 | checkpoint | Record (Photo) batch number and date of manufacture of base coat
9c2b8149-c2f9-50fc-bdbd-d9cb088447ea | button | Installation of base coat within required maximum curing time of primer (2kg per m2 or 7.5m2 per 15kg pail)? | Yes,No
db4fdae4-d6d8-5bf9-8f01-6d801ed461bf | button | Base coat installed to minimum film thickness? | Yes,No
8e552cb8-84e8-5539-b200-d52414c4a4fd | checkpoint | Record (Photo) batch number and date of manufacture of top coat
8f1a8f9f-e0cc-51b5-9104-e848401bb9d7 | button | Installation of top coat (4kg per m2 or 3.75m2 per 15kg pail)? | Yes,No,N/A
ad89507b-1c01-5d23-8473-5fdce70b2618 | button | Top coat installed to minimum film thickness? | Yes,No,N/A
e9429f72-8586-5f99-bd58-a1c83787ab81 | button | Broadcast of 7mm Basalt Scoria into wet / uncured liquid rubber (trowel scoria into liquid rubber 50% depth)? | Yes,No,N/A
eeb5ac87-0a3c-57a2-b06d-02d4b9d8c2f4 | checkpoint | Area completed to manufacturer's specification - photos attached below
a6320739-c28d-5b1c-9cc0-02a64c9b8395 | checkpoint | BARPA inspection & sign off (project completion)

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Colphene Uni NG Capping Beam (ITC) |  | Colphene Uni NG Capping Beam (ITC) | 7e3f578b-2db1-4ed9-ba7d-54e27e5c941d
| section | Details
| checkpoint | Substrate - To Pile Base
2c6c3209-a207-560f-929a-b5a465e7df53 | button | All surfaces dry, clean, smooth and free from sharp objects, laitance, oils, grease or any foreign materials which may inhibit or reduce adhesion. | Yes,No
4fa0d6fd-b333-5913-aaef-5b3d07b4d89c | button | Commencement of installation shall be taken as acceptance of the substrate by the Applicator | Yes,No
| checkpoint | Colphene BSW UNI NG - To Pile Base
5bc2e715-e1c7-58be-98af-0e1d6e59d5d4 | button | Confirm rolls stored upright, with the selvedge side on top. If the product is stored outdoors confirm covered with an protective cover | Yes,No
5c97cce5-b198-55c7-ae35-8626f5862a3e | button | Check COLPHENE BSW UNI NG thickness is 4mm | Yes,No
e543e26f-45b9-560f-82c2-1c3b74c21bd7 | button | Apply COLPHENE BSW UNI NG loose laid on blinding concrete | Yes,No
980ed33a-3f0d-5600-89bc-b618f12a768e | button | Confirm minimum 100 mm side overlap | Yes,No
4080b9db-6db2-5851-ba25-f54dc5003486 | button | Confirm minimum 150 mm end lap between each strip | Yes,No
2ef7e748-da4b-5d6b-81c1-4d0906c5fe17 | button | Confirm end laps are staggered by at least 300 mm | Yes,No
19a489bd-d868-50dc-bd26-733c99393978 | button | Confirm laps avoid excessive layering | Yes,No
b55ba0fa-8013-5c26-92db-8aaacf0c79b9 | button | Visual inspection of joint welds at cross laps | Yes,No
702922f8-0d5b-5a1f-be47-f9a7ffebdb53 | button | Confirm no laps at capping beam construction joint | Yes,No
312c7464-77e2-5d5b-bdec-ce6b1c311c82 | button | Confirm all side laps are sealed and end laps by heat-welding the selvedge with a propane torch and minimum 3-8mm bleed | Yes,No
5991c94e-0690-5ec4-bb56-e56cf4105650 | button | Confirm all angle changes (inside and outside corners) are reinforced by heat-welding on additional 300 mm piece of COLPHENE BSW UNI NG centered on the angle | Yes,No
| checkpoint | Alsan EP M - To Pile Base
eadf1acc-1249-5236-bdd6-c427c9ff84bb | button | MIXING - The mix ratio is 1:1 by volume, 1 parts Part A and 1 part Part B. Care should be taken to ensure that ALSAN EP M is thoroughly mixed. | Yes,No
f3be8a8d-10c8-5227-a92c-33946dfe4194 | button | The entire contents of the hardener (Part B) tin should be poured into the base (Part A) tin and the two materials thoroughly mixed using a suitable slow-speed drill and high shear mixing paddle | Yes,No
10218757-d66e-5e57-8ff2-4fe9ffb81ac8 | button | Mix for 2 minutes until a fully uniform grey colour is obtained; the sides of the tins should be scraped, mixing should continue for a further 2 minutes. DO NOT OVER MIX AS THIS MAY INCORPORATE AIR BUBBLES | Yes,No
a6578c67-a508-5105-bf8b-0fe40340a86f | button | To facilitate mixing and application at temperatures below 10˚C, the separate components should be warmed in hot water bath or conditions to room temperature, up to a maximum temperature of 25˚C before beginning to mix. If heated to 25˚C, the subsequently mixed material will have a pot life that will be reduced to 45 minutes. | Yes,No
51aedf4f-de7c-577a-98c2-a28eb3e14560 | button | Application - brush/trowel 40mm cove, covering joint from horizontal COLPHENE BSW UNI NG to pile | Yes,No
3cbc5865-cb6c-5083-894b-9fd1eb435211 | button | Cure time @ 25˚C - 12 hours | Yes,No
1723d94f-e5d1-5af8-adbc-3b4390404aed | button | Store Aslan EP M in chemical bunds provided by Delta | Yes,No
| checkpoint | Alsan Flashing & Alsan Fleece - To Pile Base
52ade598-a6fb-5949-b5c1-cd5cd38f302c | button | Mix well the product before use | Yes,No
7b250cc2-f3fe-5fc8-8a33-6da2c3b41af2 | button | ALSAN FLASHING is applied with a with a trowel, a brush or a roller in two (2) layers. Each layer must have a minimum wet film thickness of 0.8mm | Yes,No
ba1b8ce9-95e1-5148-8d5d-0c327ca67e2a | button | First layer must be thick enough to completely immerse the reinforcement. POLYFLEECE will be immediately covered with a second layer of ALSAN FLASHING until saturation | Yes,No
32736b6c-b0b5-566a-9b8d-b0e8d7cb52a6 | button | Ready to recoat after 2 hours Dry: 12 hours (remains tacky to touch) | Yes,No
badc142e-4231-5143-9fdd-e4ec6bd9fd45 | button | Store Aslan FLASHING in chemical bunds provided by Delta | Yes,No
| checkpoint | Colphene BSW UNI NG Reiforcement Strip - To Pile Base
55341ea4-8ab9-5ac7-ab8d-31110ececef2 | button | Confirm rolls stored upright, with the selvedge side on top. If the product is stored outdoors confirm covered with an protective cover | Yes,No
1edb0fab-be0b-54a5-a3b8-91a0663d68c3 | button | Check COLPHENE BSW UNI NG thickness is 4mm | Yes,No
7648352c-44b3-5153-bcdc-933ad81beb88 | button | Confirm minimum 100 mm side overlap | Yes,No
347fe3c8-a882-54f2-9761-fe72519733e5 | button | Confirm minimum 150 mm end lap between each strip | Yes,No
99857823-8087-595d-8448-8a83a7183816 | button | Confirm end laps are staggered by at least 300 mm | Yes,No
ebfa6e9d-d9e6-5d60-8a76-4f574047677e | button | Confirm laps avoid excessive layering | Yes,No
cad8c9db-7bef-5c6e-9f9c-4901d448a73d | button | Visual inspection of joint welds at cross laps | Yes,No
8e557981-fb54-5eb9-ac17-7ea0ed86abdc | button | Confirm no laps at capping beam construction joint | Yes,No
8b9b7dee-f278-5987-bd45-cb3912ba39cd | button | Confirm all side laps are sealed and end laps by heat-welding the selvedge with a propane torch and minimum 3-8mm bleed | Yes,No
16324e7a-c689-5a56-a382-9bf14a382094 | button | Confirm all angle changes (inside and outside corners) are reinforced by heat-welding on additional 300 mm piece of COLPHENE BSW UNI NG centered on the angle | Yes,No
| checkpoint | Colphene BSW UNI NG - To External Capping Beam Face (Post Pour)
5809d86e-c6d8-5ffd-9785-fcc029d9e752 | button | ANTIROCK PRIMER can be applied with a brush or roller on clean, dry substrates free of any residue that may hinder adherence. Shake well before using. | Yes,No
f5768857-f1a0-5628-988b-5515355e6e37 | button | It must be thoroughly dry before applying the waterproofing membrane. Drying time will vary depending on air and surface temperature and humidity. | Yes,No
72d4a028-a86a-5c79-aea9-3baa954d7717 | button | Confirm rolls stored upright, with the selvedge side on top. If the product is stored outdoors confirm covered with an protective cover | Yes,No
29f0639b-4eb4-54f3-aa94-d6a2c954c0c6 | button | Check COLPHENE BSW UNI NG thickness is 4mm | Yes,No
ab5c98e7-b3c1-531d-b53f-e57e87f6bc57 | button | Confirm minimum 100 mm side overlap | Yes,No
436352bc-a644-5838-97da-9aa4fe1ad1fd | button | Confirm minimum 150 mm end lap between each strip | Yes,No
6308db2a-46a8-54d9-93b0-b3204a18c421 | button | Confirm end laps are staggered by at least 300 mm | Yes,No
60f2c691-3ec9-5079-b53f-06ad26f8e6c1 | button | Confirm laps avoid excessive layering | Yes,No
d72bcc0d-340c-5c21-8039-e1a946f7f75f | button | Visual inspection of joint welds at cross laps | Yes,No
af9b3627-6be1-5f59-a15a-6882ce3361d3 | button | Confirm no laps at capping beam construction joint | Yes,No
ca38f85a-7cbd-5170-b271-e11d4a6959d5 | button | Confirm all side laps are sealed and end laps by heat-welding the selvedge with a propane torch and minimum 3-8mm bleed | Yes,No
d092deab-f921-5c49-a8b3-7afae1361aa5 | button | Confirm all angle changes (inside and outside corners) are reinforced by heat-welding on additional 300 mm piece of COLPHENE BSW UNI NG centered on the angle | Yes,No
| checkpoint | Sopradrain 20 - To External Capping Beam Face
f8f69e2c-b5cd-58ed-a216-506f74e17d11 | button | The substrate must be firm, even, clean and free from loose materials or any construction debris on the surface. | Yes,No
bc10baf2-7aac-5392-a037-d534929c3a93 | button | Install SOPRADRAIN 20 with the geotextile facing the backfill. | Yes,No
38d5732d-3c7a-5b6a-9cdf-127d61616f6f | button | Join by simply butting edge to edge and overlapping the geotextile overhang and securing with reinforced canvastape | Yes,No
4c3dfbb7-5e82-51fe-8c04-d8e6f5623ebc | button | Terminate SOPRADRAIN 20 by nailing pressure bar at required height | Yes,No
| checkpoint | CHECKLIST COMPLETE AND SIGNED
2f6c8ca7-8383-599f-b3b4-5a60b38a3726 | button | ITC completed | Yes,No
| checklist | Colphene Uni NG Capping Beam ITP |  | Colphene Uni NG Capping Beam ITP | 46df730e-f715-42a3-add3-e499cd4f4e36
| section | Details
| checkpoint | CAPPING BEAM WATERPROOFING ITP
b25d00c5-23bb-571c-b483-ca9d53bc82b8 | button | Sample Submissions Approved | Yes,No
230b1daf-fdd6-51b9-9fa4-f54930f8795b | button | Shop Drawings Approved | Yes,No
f1d28929-0fac-5dd3-a13c-7b38a680d686 | button | Substrate - To Pile Base | Yes,No
da852c75-ab17-543a-a84e-c4a7652d0884 | button | Colphene BSW UNI NG Installed - To Pile Base | Yes,No
bab5081a-e83d-51b6-833d-0247f37ae875 | button | Alsan EP M Installed - To Pile Base | Yes,No
b33b65b6-af48-5404-8468-f6a1e7f06434 | button | Colphene BSW UNI NG Reiforcement Strip Installed - To Pile Base | Yes,No
b2c3ccce-44e0-5e8b-8174-1b3ebb6a0938 | button | Alsan Flashing & Alsan Fleece Installed - To Pile Base | Yes,No
460625f9-e028-591d-a356-5e9a320cb66b | button | Colphene BSW UNI NG - To External Capping Beam Face | Yes,No
87f59e14-6136-51b7-a9e8-3221e7aeb235 | button | Sopradrain 20 - To External Capping Beam Face | Yes,No
28e32940-303f-5fc8-850f-b29d770210cf | button | ITC Pre-Pour Complete & Signed | Yes,No
623b1cbd-a9a2-528d-a844-1b8a6b7b91fb | button | Client Inspections Completed & Report Closed Out | Yes,No
8b0bbb86-cb4d-5a2f-912f-5a8b0f0131d9 | button | Pour Inspection & Sign Off | Yes,No
a4d44b79-bae8-5f5a-a625-36672ef9eab3 | button | Colphene BSW V Installed - To External Capping Beam Face | Yes,No
9a271f24-f064-5d7c-a777-bb6086a3abdd | button | Sopradrain 20 Installed - To External Capping Beam Face | Yes,No
2d1c5667-54f9-50d6-9e3e-64acd9b34ee2 | button | ITC Pre-Pour Complete & Signed | Yes,No
673e8653-d080-5489-bcf6-b13192b1eee0 | button | Client Inspections Completed & Report Closed Out | Yes,No
116bd4c1-0a10-50d2-91ef-907ebe5d01d9 | button | Backfill Inspection & Sign Off | Yes,No
a0ef37d6-7be7-5908-b692-78068a200c2c | button | Soprema & Bravada Quality Documentation issued to Client | Yes,No
2a137d84-cdf9-40ab-be63-48fb0850fd2c | checklist | Colphene Uni NG Riser Pit (ITC) |  | Colphene Uni NG Riser Pit (ITC) | 66483389-e8f8-4a8c-b149-130d03e504e6
226addae-abb4-43a4-a65a-4fa3f1875217 | section | Details
c3d55f82-0daa-4630-99b3-52e79f5ef482 | checkpoint | Substrate - To Pile Base
c2cc497a-8444-5fff-9631-ab9a10d5a42f | button | All surfaces dry, clean, smooth and free from sharp objects, laitance, oils, grease or any foreign materials which may inhibit or reduce adhesion. | Yes,No
3aa758d9-2654-5563-96c0-f2c4bb5deec0 | button | Commencement of installation shall be taken as acceptance of the substrate by the Applicator | Yes,No
c1bb9b38-063c-4d4b-b7ce-b887b115f832 | checkpoint | Colphene BSW UNI NG - To Raft Slab
5f17449b-4f0d-5725-ac86-ce0414158842 | button | Confirm rolls stored upright, with the selvedge side on top. If the product is stored outdoors confirm covered with an protective cover | Yes,No
59906662-7e5a-5ced-b989-3536b6bcec18 | button | Check COLPHENE BSW UNI NG thickness is 4mm | Yes,No
8617d554-d0b8-5f59-a820-4cfcdce80649 | button | Apply COLPHENE BSW UNI NG loose laid on blinding concrete | Yes,No
3385c9b4-c4e5-5f50-8b21-fc58fa5ddf52 | button | Confirm minimum 100 mm side overlap | Yes,No
d62fe843-27d0-5765-936d-61149f5cc37f | button | Confirm minimum 150 mm end lap between each strip | Yes,No
729c4898-a9de-5bde-8b13-68a12b9a3c8a | button | Confirm end laps are staggered by at least 300 mm | Yes,No
b11259a7-01d3-5c18-a221-87a2a3a590d3 | button | Confirm laps avoid excessive layering | Yes,No
95b4427a-4f9f-5fdc-8000-1e5b3ac6a19b | button | Visual inspection of joint welds at cross laps | Yes,No
e1d7c715-43e3-5a75-a23f-7de6e427b6c7 | button | Confirm no laps at capping beam construction joint | Yes,No
0a2ba39d-abf7-533d-ac12-8d101b988ba3 | button | Confirm all side laps are sealed and end laps by heat-welding the selvedge with a propane torch and minimum 3-8mm bleed | Yes,No
e06df59e-1687-5112-bde9-94e98c23ebf9 | button | Confirm all angle changes (inside and outside corners) are reinforced by heat-welding on additional 300 mm piece of COLPHENE BSW UNI NG centered on the angle | Yes,No
b27d5723-a7cc-48d9-9507-3e78376e9534 | checkpoint | Colphene BSW UNI NG Reiforcement Strip - Floor/Wall Junction and Existing Wall Upturn
fa3e56a1-e41f-5082-a0d0-894b1ce8faf6 | button | Confirm rolls stored upright, with the selvedge side on top. If the product is stored outdoors confirm covered with an protective cover | Yes,No
9d63b735-8565-551a-af3b-58af3ffbb405 | button | Check COLPHENE BSW UNI NG thickness is 4mm | Yes,No
149f94ce-ea63-56c8-ab62-163cfaff654f | button | Confirm minimum 100 mm side overlap | Yes,No
2b897576-6890-5038-ae39-45e8ec4fc86c | button | Confirm minimum 150 mm end lap between each strip | Yes,No
8755b459-5512-504d-8fc6-7e648357a72e | button | Confirm end laps are staggered by at least 300 mm | Yes,No
1b104f4d-2edf-53ac-91df-c769acbc84af | button | Confirm laps avoid excessive layering | Yes,No
b4661318-27ad-5524-8ea1-b8ec1625271d | button | Visual inspection of joint welds at cross laps | Yes,No
5adc1450-ff9f-513b-86d4-69760a587566 | button | Confirm no laps at capping beam construction joint | Yes,No
d3e5f15c-9194-5b8b-bb91-5fec6a2213f6 | button | Confirm all side laps are sealed and end laps by heat-welding the selvedge with a propane torch and minimum 3-8mm bleed | Yes,No
0e9631d7-0983-4a09-80b0-441df56aef2d | checkpoint | WPA Injection System - To Insitu Wall Junctions with Slab, Existing Wall and Itself
86f84565-68ab-5905-8dee-c7fb9e620f2c | button | Verify all components for installation are in the kit | Yes,No
de7c57e6-54aa-5f18-9f1b-f7c54fe2c72f | button | Verify kit is not damaged | Yes,No
90e99e80-d80d-594f-8ce2-2b85bfcd1203 | button | Install and fix hose to construction joins | Yes,No
3c7c03a5-e5a1-5636-85d6-e5066295f9bf | button | Install Injection box(es) in agreed locations | Yes,No
75117e39-090a-5723-b24d-bef08c7154bc | button | Feed hoses into injection boxes | Yes,No
25d52ec4-a775-54f6-9207-192035691ed6 | button | Clip and cap hoses | Yes,No
64abc0a8-160a-4a7e-9695-01dcc903b38b | checkpoint | Colphene BSW UNI NG - To Insitu Walls
923d9141-a17b-5573-912a-b99a969b23b6 | button | ANTIROCK PRIMER can be applied with a brush or roller on clean, dry substrates free of any residue that may hinder adherence. Shake well before using. | Yes,No
d30ca1d2-3b5b-5743-b193-d1df2b949de9 | button | It must be thoroughly dry before applying the waterproofing membrane. Drying time will vary depending on air and surface temperature and humidity. | Yes,No
ae4f42b5-c97f-56b4-97dc-0a6d41581ec2 | button | Confirm rolls stored upright, with the selvedge side on top. If the product is stored outdoors confirm covered with an protective cover | Yes,No
46bd92b8-0e71-5340-9975-08abe6176032 | button | Check COLPHENE BSW UNI NG thickness is 4mm | Yes,No
1383b571-c866-5732-9bf1-35351fcda3ad | button | Confirm minimum 100 mm side overlap | Yes,No
98824be5-5a24-5b5f-bbf5-663d5d074f20 | button | Confirm minimum 150 mm end lap between each strip | Yes,No
855b649e-56a2-5ef7-aa42-fd2413e4c3aa | button | Confirm end laps are staggered by at least 300 mm | Yes,No
7bb7df6e-abcb-55b2-828a-dee19e6cd971 | button | Confirm laps avoid excessive layering | Yes,No
09c6f8c4-6a74-5ed0-b1a4-bfbc58fca817 | button | Visual inspection of joint welds at cross laps | Yes,No
7731c698-2789-5363-9163-de5730e4e3a5 | button | Confirm no laps at capping beam construction joint | Yes,No
b71ad2fa-013e-5afd-8627-4e8c8095ef5c | button | Confirm all side laps are sealed and end laps by heat-welding the selvedge with a propane torch and minimum 3-8mm bleed | Yes,No
d97e509b-1869-50b3-b597-981c0360de4a | button | Confirm all angle changes (inside and outside corners) are reinforced by heat-welding on additional 300 mm piece of COLPHENE BSW UNI NG centered on the angle | Yes,No
a27c9721-d31d-4281-9406-b51889c30a73 | checkpoint | Sopradrain 20 - To Insitu Walls
cb8f3c7d-8968-5a1a-9772-5f8bcf0c4857 | button | The substrate must be firm, even, clean and free from loose materials or any construction debris on the surface. | Yes,No
da99fd49-a1a6-5994-a157-d568bdadc285 | button | Install SOPRADRAIN 20 with the geotextile facing the backfill. | Yes,No
11da3e25-e295-581c-95ef-f72e37efbef8 | button | Join by simply butting edge to edge and overlapping the geotextile overhang and securing with reinforced canvastape | Yes,No
05c41cd1-6b02-5b9f-91bd-40022c666ccc | button | Terminate SOPRADRAIN 20 by nailing pressure bar at required height | Yes,No
377e2abe-f669-4beb-8217-1eac19eca92f | checkpoint | WPA 100 - To Top of Raft Slab
221a042f-6321-5ad6-b122-49980ff58248 | button | Mix well the product before use | Yes,No
131e5c2e-ed61-5691-94ef-9480d1f5b512 | button | WPA100 is applied with a with a brush or a roller in two (2) layers. Application must be a minimum of 2 coats @ >= 1.2kg/m2 per coat to achieve a dry film thickness not less than 2mm as per the technical data sheet. | Yes,No
bfabd62e-5172-5898-822b-5876f9207f9b | button | Ready to recoat after 2 hours. Dry: 24 hours (remains tacky to touch). | Yes,No
77ac3a22-025c-5442-9c00-92e168a4fa11 | button | Store WPA 100 in chemical bunds provided by Delta | Yes,No
e4e48e04-8d80-44b4-8770-0d8d68343ec8 | checkpoint | CHECKLIST COMPLETE AND SIGNED
11ae3588-27af-505f-8e30-66ccd8ea55aa | button | ITC completed | Yes,No
db16214c-1f6a-4174-bb4d-856eca1d6eb1 | checklist | Colphene Uni NG Riser Pit ITP |  | Colphene Uni NG Riser Pit ITP | 113bc979-5bd5-4d90-a78c-ff542630b875
8b313fe3-12db-4bdc-9071-3d925df9113c | section | Details
7b23096b-5a01-4b22-9202-d17cf007c4ab | checkpoint | RISER PIT WATERPROOFING ITP
b5b77e20-27be-5670-9098-420e8e7a2758 | button | Sample Submissions Approved | Yes,No
bf0b603e-2f3c-5449-98dd-af4de99f2a2f | button | Shop Drawings Approved | Yes,No
dd84061d-0a9b-5865-a652-398862fcff85 | button | Colphene BSW UNI NG Installed - To Raft Slab Blinding | Yes,No
337ed77f-b8f3-5887-b46e-19a4b5da10b4 | button | Colphene BSW UNI NG Upturn to Installed - Existing Wall | Yes,No
9adc7d3e-fa7e-5d62-8250-9a3d21503587 | button | Colphene BSW UNI NG Reiforcement Strip Installed - Floor/Wall Junction | Yes,No
7fb3e28c-8b84-5b1b-b148-ea3e7c2305a3 | button | Injection System Installed - To Insitu Walls | Yes,No
7ddbbb32-c503-5b00-a4d6-6b7f1ad98efb | button | Primer Installed - To Insitu Walls | Yes,No
4097dbab-2d82-553c-ace4-e55b81530a93 | button | Colphene BSW UNI NG Installed - To Insitu Walls | Yes,No
c9ccffb5-fc7c-5ee7-8915-54c75441fa1a | button | Sopradrain Installed - To Insitu Walls | Yes,No
9841948e-416f-5dce-8ce9-e444ae6793b4 | button | WPA 100 Installed - To Top of Raft Slab | Yes,No
2814c845-9e22-49db-abd7-3261e3ec622f | checklist | Colphene Uni NG Tieback Slab L4 (ITC) |  | Colphene Uni NG Tieback Slab L4 (ITC) | 238bc180-6c8c-4102-8afc-e4e13fac13e2
b58a621d-5db5-4f77-a24a-300c27cbfd0e | section | Details
8dbab9cf-29d3-4fb3-a5d9-a5a7548fd32e | checkpoint | Substrate - To Pile Base
f1d42105-2767-52bf-8b61-5f7bae24e5f9 | button | All surfaces dry, clean, smooth and free from sharp objects, laitance, oils, grease or any foreign materials which may inhibit or reduce adhesion. | Yes,No
b6c9df10-7c6d-5536-9119-06969c056823 | button | Commencement of installation shall be taken as acceptance of the substrate by the Applicator | Yes,No
d69759c9-b71d-456f-9b03-3e02e943ea96 | checkpoint | Colphene BSW UNI NG - To Pile Base
6f5a2249-2986-5085-8948-c37403d1e819 | button | Confirm rolls stored upright, with the selvedge side on top. If the product is stored outdoors confirm covered with an protective cover | Yes,No
7beb751a-d781-5bfb-ad48-253e006105e9 | button | Check COLPHENE BSW UNI NG thickness is 4mm | Yes,No
349e355b-dce9-574f-99be-967c9db635ca | button | Apply COLPHENE BSW UNI NG loose laid on blinding concrete | Yes,No
89ec20a1-bb27-576a-b108-a24bb71761d4 | button | Confirm minimum 100 mm side overlap | Yes,No
a6f3bed9-1dbd-586d-9011-e0e3d994e8fb | button | Confirm minimum 150 mm end lap between each strip | Yes,No
31b70339-aff6-5292-a8b2-e27233add93e | button | Confirm end laps are staggered by at least 300 mm | Yes,No
ae4e6ef3-5379-5bd2-9f95-2bd98205fe1f | button | Confirm laps avoid excessive layering | Yes,No
479fde3e-ad25-5e5e-b295-6ada8d8ee62b | button | Visual inspection of joint welds at cross laps | Yes,No
dab3ff50-4088-5136-805c-6f18b3a1e20d | button | Confirm no laps at capping beam construction joint | Yes,No
cf59ea30-bdaf-5364-8a88-b41c6a3ee241 | button | Confirm all side laps are sealed and end laps by heat-welding the selvedge with a propane torch and minimum 3-8mm bleed | Yes,No
c4a13d58-86b9-5e65-9983-9389b9e30998 | button | Confirm all angle changes (inside and outside corners) are reinforced by heat-welding on additional 300 mm piece of COLPHENE BSW UNI NG centered on the angle | Yes,No
33eab5f2-6577-488c-80e2-0bbc8e7d75d1 | checkpoint | Alsan EP M - To Pile Base
7138e326-1163-54be-b77a-fe7b4651a15a | button | MIXING - The mix ratio is 1:1 by volume, 1 parts Part A and 1 part Part B. Care should be taken to ensure that ALSAN EP M is thoroughly mixed. | Yes,No
74078c59-e9a2-5b7c-aeda-e6fc60e6c386 | button | The entire contents of the hardener (Part B) tin should be poured into the base (Part A) tin and the two materials thoroughly mixed using a suitable slow-speed drill and high shear mixing paddle | Yes,No
befc6310-fca0-5e92-b778-48f422f368cd | button | Mix for 2 minutes until a fully uniform grey colour is obtained; the sides of the tins should be scraped, mixing should continue for a further 2 minutes. DO NOT OVER MIX AS THIS MAY INCORPORATE AIR BUBBLES | Yes,No
d0d42081-c89e-57b8-82b5-97470a726134 | button | To facilitate mixing and application at temperatures below 10˚C, the separate components should be warmed in hot water bath or conditions to room temperature, up to a maximum temperature of 25˚C before beginning to mix. If heated to 25˚C, the subsequently mixed material will have a pot life that will be reduced to 45 minutes. | Yes,No
0accc04f-5fef-59dd-ad1b-536eaa63de55 | button | Application - brush/trowel 40mm cove, covering joint from horizontal COLPHENE BSW UNI NG to pile | Yes,No
79321c62-0f36-5e07-8d52-f548b4a2c4e6 | button | Cure time @ 25˚C - 12 hours | Yes,No
be29e568-ed3e-57f9-8692-85791918cb49 | button | Store Aslan EP M in chemical bunds provided by Delta | Yes,No
d424774e-3a56-478a-b3b4-ea44dc7092e1 | checkpoint | Alsan Flashing & Alsan Fleece - To Pile Base
282d8d76-ba04-5e86-902d-2db66af83387 | button | Mix well the product before use | Yes,No
53079818-abbf-50c8-a408-1b9c0783798a | button | ALSAN FLASHING is applied with a with a trowel, a brush or a roller in two (2) layers. Each layer must have a minimum wet film thickness of 0.8mm | Yes,No
ff778eb0-57e9-5dbd-90f6-111882f34d81 | button | First layer must be thick enough to completely immerse the reinforcement. POLYFLEECE will be immediately covered with a second layer of ALSAN FLASHING until saturation | Yes,No
8385e3bc-4f51-5ddb-94c9-4ce8c4bda7fd | button | Ready to recoat after 2 hours Dry: 12 hours (remains tacky to touch) | Yes,No
3ffb4dc4-9c61-529c-8df9-20eb95455673 | button | Store Aslan FLASHING in chemical bunds provided by Delta | Yes,No
9cd0fc16-2953-468a-b009-1577d06d650b | checkpoint | Colphene BSW UNI NG Reiforcement Strip - To Pile Base
231aa07e-08ce-5729-9335-2123366ca92b | button | Confirm rolls stored upright, with the selvedge side on top. If the product is stored outdoors confirm covered with an protective cover | Yes,No
cb63094b-1653-554a-a746-1b6d4d551889 | button | Check COLPHENE BSW UNI NG thickness is 4mm | Yes,No
ef4eaaab-acf2-5af4-8ea5-f282ea3c3b12 | button | Confirm minimum 100 mm side overlap | Yes,No
92221d1a-0f93-543e-97b3-e45c9779522b | button | Confirm minimum 150 mm end lap between each strip | Yes,No
d5cd054e-87f7-5f6a-8b77-66add5cf2169 | button | Confirm end laps are staggered by at least 300 mm | Yes,No
f776f164-61fd-5008-911f-5eae27e748ff | button | Confirm laps avoid excessive layering | Yes,No
ac80b737-abc8-56f1-b0e4-a147fb0131dd | button | Visual inspection of joint welds at cross laps | Yes,No
8157ac12-9aa3-523a-b6a1-ab9dd13d0843 | button | Confirm no laps at capping beam construction joint | Yes,No
4c5debae-a129-51be-a11f-ea02c912b30e | button | Confirm all side laps are sealed and end laps by heat-welding the selvedge with a propane torch and minimum 3-8mm bleed | Yes,No
2c27fae9-6d36-5de7-8034-5793051c792e | button | Confirm all angle changes (inside and outside corners) are reinforced by heat-welding on additional 300 mm piece of COLPHENE BSW UNI NG centered on the angle | Yes,No
bb95b3d7-93fe-4890-9ac5-552e1992ad71 | checkpoint | Colphene BSW UNI NG - To External Capping Beam Face (Post Pour)
1d203d1d-1182-5b75-a345-ad8802d42130 | button | ANTIROCK PRIMER can be applied with a brush or roller on clean, dry substrates free of any residue that may hinder adherence. Shake well before using. | Yes,No
d01e4d4c-8aa0-500f-b363-7de700d1075e | button | It must be thoroughly dry before applying the waterproofing membrane. Drying time will vary depending on air and surface temperature and humidity. | Yes,No
dbd93d6d-aabf-5069-818a-94f6c4cf0f2b | button | Confirm rolls stored upright, with the selvedge side on top. If the product is stored outdoors confirm covered with an protective cover | Yes,No
71c5cbd8-9cee-5107-8cb7-f830cff766b9 | button | Check COLPHENE BSW UNI NG thickness is 4mm | Yes,No
dc64f16e-3dc5-5de8-ac3a-eff65bd10312 | button | Confirm minimum 100 mm side overlap | Yes,No
89c875e3-55cf-5e10-95d5-96ab36db7e16 | button | Confirm minimum 150 mm end lap between each strip | Yes,No
1b974c0d-c73d-54ad-b863-6ef26af651f2 | button | Confirm end laps are staggered by at least 300 mm | Yes,No
07061a0f-2d3c-53bc-b965-0b1baa48e0e6 | button | Confirm laps avoid excessive layering | Yes,No
61b44c4d-cfe3-58b8-a37c-25077d864bff | button | Visual inspection of joint welds at cross laps | Yes,No
6085e9c4-57e5-5689-b2ce-451f861054d5 | button | Confirm no laps at capping beam construction joint | Yes,No
5aaaa996-0eec-5765-81ea-f3d2d996aa56 | button | Confirm all side laps are sealed and end laps by heat-welding the selvedge with a propane torch and minimum 3-8mm bleed | Yes,No
d621b5f0-79f8-581a-b8bb-34f58ae3dab7 | button | Confirm all angle changes (inside and outside corners) are reinforced by heat-welding on additional 300 mm piece of COLPHENE BSW UNI NG centered on the angle | Yes,No
6dbec900-599d-4d9a-9cfd-0c0f2001f09a | checkpoint | Sopradrain 20 - To External Capping Beam Face
627924af-3a4a-544b-8ca8-7ffba14845b3 | button | The substrate must be firm, even, clean and free from loose materials or any construction debris on the surface. | Yes,No
a6676975-578b-5ebe-bfa3-225c5e5e5b4a | button | Install SOPRADRAIN 20 with the geotextile facing the backfill. | Yes,No
dee23728-b764-5658-a3ff-509a94ace2ef | button | Join by simply butting edge to edge and overlapping the geotextile overhang and securing with reinforced canvastape | Yes,No
106e426a-b43e-5727-8745-83e470e2da15 | button | Terminate SOPRADRAIN 20 by nailing pressure bar at required height | Yes,No
34b011f8-74db-454e-80db-6d9d5168becf | checkpoint | Substrate - Slab
096ddb61-b7ed-5ce0-b69c-1c7d4447f01b | button | All surfaces dry, clean, smooth and free from sharp objects, laitance, oils, grease or any foreign materials which may inhibit or reduce adhesion. | Yes,No
557fd296-dd1f-5ca8-a5cb-f23b8e4aee4a | button | Commencement of installation shall be taken as acceptance of the substrate by the Applicator | Yes,No
2c1b43f8-ee60-46ff-a579-151562c9ec59 | checkpoint | Colphene BSW UNI NG - Slab
85e1ad03-2635-531b-ab53-7002d5ea4f54 | button | Confirm rolls stored upright, with the selvedge side on top. If the product is stored outdoors confirm covered with an protective cover | Yes,No
1a782cf9-e55a-55f4-a7c3-2723be72c96e | button | Check COLPHENE BSW UNI NG thickness is 4mm | Yes,No
d1ea3ba5-1871-5bdb-9695-e3474c54ddf9 | button | Apply COLPHENE BSW UNI NG loose laid on blinding concrete | Yes,No
c5cc3c80-c969-5330-bd26-e398b612cbc7 | button | Confirm minimum 100 mm side overlap | Yes,No
79979b57-81ac-59aa-810c-79a42a676b9f | button | Confirm minimum 150 mm end lap between each strip | Yes,No
18449fd8-e4d3-5168-85f2-5c4c9e130135 | button | Confirm end laps are staggered by at least 300 mm | Yes,No
3093e38e-7444-5a2f-ae97-dfe67c891f90 | button | Confirm laps avoid excessive layering | Yes,No
01910126-9419-5042-8cec-d5482026e769 | button | Visual inspection of joint welds at cross laps | Yes,No
d6a69c8a-2c8b-5634-b33e-eb7ba11855d9 | button | Confirm no laps at capping beam construction joint | Yes,No
ea00c614-92f0-5212-8d67-3fb51ceb8718 | button | Confirm all side laps are sealed and end laps by heat-welding the selvedge with a propane torch and minimum 3-8mm bleed | Yes,No
d1efa40a-2f4f-563c-8182-8391b2416a36 | button | Confirm all angle changes (inside and outside corners) are reinforced by heat-welding on additional 300 mm piece of COLPHENE BSW UNI NG centered on the angle | Yes,No
f776aa85-6593-40c1-9a38-3b00ae58759b | checkpoint | CHECKLIST COMPLETE AND SIGNED
f44a1ab7-11fd-534c-bf70-ff22846001c3 | button | ITC completed | Yes,No
9ad4e03c-81d9-45b8-b483-593fe5243d2f | checklist | Colphene Uni NG Tieback Slab L4 ITP |  | Colphene Uni NG Tieback Slab L4 ITP | fc08aa31-3883-40e2-8c84-eb9016619fe2
e901acc3-4703-4fb9-bb41-c36d01ea793c | section | Details
be42ba96-7f82-4d83-8909-4114ad65f10d | checkpoint | TIEBACK SLAB WATERPROOFING ITP
44a1d633-4978-5df6-8b83-912ff3f53ac4 | button | Sample Submissions Approved | Yes,No
bad07c0a-4611-500c-9b5a-89e657a5f5f7 | button | Shop Drawings Approved | Yes,No
8ed62de9-e021-549e-8241-01d4782a38e8 | button | Substrate - To Pile Base | Yes,No
b1b8ac96-f629-5d4c-86a7-d333d53c6d82 | button | Colphene BSW UNI NG Installed - To Pile Base | Yes,No
5e78e783-f14a-546a-959c-3b452b46d47b | button | Alsan EP M Installed - To Pile Base | Yes,No
657fbcb7-743e-5729-ac43-d07facdc5a62 | button | Colphene BSW UNI NG Reiforcement Strip Installed - To Pile Base | Yes,No
227b0cd6-f636-54bc-aec3-23a19a35c4d0 | button | Alsan Flashing & Alsan Fleece Installed - To Pile Base | Yes,No
4ba54c67-28d2-59e6-921f-527b569970e6 | button | Colphene BSW UNI NG - To External Capping Beam Face | Yes,No
877b5447-bc80-56bb-a437-7ed18318cd5b | button | Sopradrain 20 - To External Capping Beam Face | Yes,No
5d1de687-b73c-5c50-9c84-5f6cb9a0813c | button | ITC Pre-Pour Complete & Signed | Yes,No
d9868169-4561-5dfa-b30a-8f65a8e8a2f1 | button | Client Inspections Completed & Report Closed Out | Yes,No
5cb949c2-c074-5d55-9944-2f4fa0c0b11b | button | Pour Inspection & Sign Off | Yes,No
0ed923dd-d6d2-54e6-8e42-c1cac276e549 | button | Colphene BSW V Installed - To External Capping Beam Face | Yes,No
97ac537e-c288-5c1c-bade-529491a9df68 | button | Sopradrain 20 Installed - To External Capping Beam Face | Yes,No
368167ac-f920-538a-bdce-044adb798e2f | button | ITC Pre-Pour Complete & Signed | Yes,No
5fdac3ab-bdc9-50cf-85cb-bc31255073eb | button | Client Inspections Completed & Report Closed Out | Yes,No
7d508406-2249-5624-9c60-5122298e4b8e | button | Backfill Inspection & Sign Off | Yes,No
42661ced-1f4a-53e6-9e04-598bb8bf3b10 | button | Substrate - Slab | Yes,No
01a67981-b153-57d4-8e69-c9597d706a55 | button | Colphene BSW UNI NG Installed - Slab | Yes,No
c225e4d2-9172-57ca-8c34-5d37c99eeeb1 | button | Soprema & Bravada Quality Documentation issued to Client | Yes,No