## General
SECTION 1 – GENERAL DETAILS
Project Name: | DCC11014 Water Pump Station Renewals - SILVERSTREAM | [5 empty] | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | 561482 | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Dunedin City Council | [5 empty] | B | Report by Breach | CM | Construction Manager | Stephen Vorgers
Contract Number: | DCC11014-WPS002 | [5 empty] | C | Check | CR | Cust. Representative | Joff Riley / Mark Todd
Area/ Sub-System: | Wet Wall Penetration Preparation - SILVERSTREAM |  |  | Lot ID Number: | N/A |  | D | Dimension Inspection | IP | Inspection Personnel | Jason Bell
[7 empty] | E | Examine | MC | Material Controller
ITP Number: | 561482-ITP-008 |  |  | Version: | DRAFT |  | H | Hold Point | OP | Operations Manager
ITP Description: | Wet Well Wall final inspection/pre-fill - Inspection Test Plan | [5 empty] | I | Inspection | PM | Project Manager | Matt Paterson
Discipline: | Wet Well Wall pre-fill inspection | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor
Specification: | C11014 Water Pump Station Renewals Specification 12581908 | [5 empty] | O | Operation | QE | Quality Engineer
[7 empty] | R | Review | QM | QA Manager
Drawings: | Construction Issue Drawings as issued by GHD - Silverstream Pump Station Project Ref: 12581908-GHD-PS-SS-DRG-GN Drawings: G0001, M0001 through M0004 & P0001 | [5 empty] | S | Subcontractor | SP | Supervisor | Bruce Allan
[7 empty] | V | Visual Verification | ST | Superintendent
Prepared By: (Name) | Matt Paterson |  |  | Date: | 2024-12-10 |  | W | Witness Point | SV | Surveyor
Quality Specified: | None - As per Specification | [7 empty] | WS | Welding Supervisor
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: | Matt Paterson/Jason Bell |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: | Matt Paterson/Stephen Vorgers |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: | Joff Riley / Mark Todd |  |  | Signature: |  |  |  |  | Date:

## Receiving Inspection
SECTION 3 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
3.1 | Grout Castings (Penetrations 1 through 3) | Inspection of castings. Inspection for air pockets, cracks, fissures oa any other imperfections | Completion of ITP's 561482-ITP-007.1. 561482-ITP-007.2 561482-ITP-007.3 Elapsed time of 7 days post pour | None | Once | Visual + Photographs | A | IP

## In Process Inspections
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
4.1 | Removal of Formwork - Penetration 1 | Check and verify quality of casting both wet well side and Dry side | Approval from Engineer | Drawing M0003 and annotations | once | Document + Visual + Photograph + Engineer site Inspection | H | CR
4.2 | Removal of Formwork - Penetration 2 | Check and verify quality of casting both wet well side and Dry side | Approval from Engineer | Drawing M0003 and annotations | once | Document + Visual + Photograph + Engineer site Inspection | H | CR
4.3 | Removal of Formwork - Penetration 3 | Check and verify quality of casting both wet well side and Dry side | Approval from Engineer | Drawing M0003 and annotations | once | Document + Visual + Photograph + Engineer site Inspection | H | CR

## Final Inspection and Handover
SECTION 5 – FINAL INSPECTION AND HANDOVER Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
5.1 | Clean tank of any Downer construction debris | Upon removal of boxing and any remedial activities | Client Representative acceptance | NTC and or other written conformation | once | Visual Inspection + Photograph | H | CR
5.2 | Approval to fill Wet well | All activities and pre-checks required by client | Client Representative acceptance | NTC and or other written conformation | once | Visual Inspection + Photograph | C | CR
SECTION 6 – COMMENTS
|  |  | Customer Release Granted: | ☐ Yes | ☐ No | Date:
Certificate Number: