## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Picton Street and Ridge Road - Stormwater Drainage | itp |  |  |  |  | ITP - Picton Street and Ridge Road - Stormwater Drainage
section | Stormwater Drainage
checkpoint | 1 - Permits & Services (1)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
label | FREQUENCY: Prior to any construction commencing
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Relevant Fulton Hogan Permits to Work.
label | ○ AT Access Authority approved and signed by RCA Authority
label | RECORDS: Permit attached or permit number noted.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1 - Permits & Services (2)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Locate and mark out all existing services
label | FREQUENCY: Prior to any construction commencing
label | CONFORMANCE CRITERIA: B4u dig procedure - follow utility protocols
label | RECORDS: B4u dig plans & GPR report attached
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Pre-Construction Sign Offs
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Sub-Contract and Supplier Agreements
label | FREQUENCY: Prior to commencement.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Sub-Contract and Supplier Agreements to be agreed and signed
label | RECORDS: Subcontract and Supplier Agreements
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Design
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Design is approved and Drawings are of the latest revision.
label | FREQUENCY: Prior to commencement.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Ensure that Design is approved and Drawings are of the latest revision.
label | ○ Drawings to be 'ISSUED FOR CONSTRUCTION' status.
label | ○ HOLD POINT of not issued to IFC.
label | RECORDS: Drawing Register.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Survey Set out
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Set out Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
label | FREQUENCY: Prior to commencement.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
label | CONFORMANCE CRITERIA: As per GHD Engineering Drawings: 12549626-CS07 & Set out files
label | RECORDS: Survey Receipt.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Pipe and Manhole Material Compliance
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
label | FREQUENCY: Prior to commencement.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review, Visual Inspection
label | CONFORMANCE CRITERIA: Pipe shall be:
label | ○ Check for freshly formed pipes and return if required
label | 1) DN300 Class 4 RCRRJ pipes AS/NZS 4058
label | 2) All Concrete RCRRJ pipes to be fitted with Rubber rings
label | 3) Pipes shall have product certification (ISO Type 5) to AS/NZS 4058
label | ○ Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
label | RECORDS: Manufacturers Data Sheets, Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure all services conflicting with the line of trench have been exposed by hand digging.
label | FREQUENCY: Prior to commencement.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing / Survey
label | CONFORMANCE CRITERIA: All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
label | RECORDS: As-built Drawings. Doc. Review
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Trenching & Excavation (1)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Excavation methodology
label | FREQUENCY: Daily
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Prestart review
label | CONFORMANCE CRITERIA: The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
label | RECORDS: Prestart RCP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Trenching & Excavation (2)
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Trench Profile - Width
label | FREQUENCY: Daily / as trenching takes place. Different depth methodology
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Excavation methodology
label | CONFORMANCE CRITERIA: Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
label | RECORDS: Construction Photos
checkpoint | 7 - Trenching & Excavation (3)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Trench Profile - Depth
label | FREQUENCY: Daily / as trenching takes place.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Measurement
label | CONFORMANCE CRITERIA: Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
label | RECORDS: FH Drainage Line Record / Construction Photos
checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Placing and compaction of Bedding Material.
label | FREQUENCY: Inspected continuously during placing and compaction of Bedding Material.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
label | RECORDS: FH Drainage Line Record / Construction Photos
checkpoint | 9 - Pipe Position Tolerance
label | ACTION (Hold, Monitor, Witness): M
label | FREQUENCY: At any point of pipe
label | CONFORMANCE CRITERIA: Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
label | RECORDS: FH Drainage Line Record, Survey Data.
checkpoint | 10 - Trench Backfill - Placing & Compacting
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Placing and compacting of Trench Backfill Material
label | FREQUENCY: Throughout Trench Backfilling operation.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
label | RECORDS: Construction Photos
checkpoint | 11 - As-Built Drawings
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Red pen marked-up As-Built of every 'Issued for Construction' AT drawings
label | FREQUENCY: Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings / Visual Inspection
label | CONFORMANCE CRITERIA: As Built and GIS Data
label | RECORDS: Redline As-Built Drawings, scanned as .pdf files.
section | ITP APPROVAL
checkpoint | ITP Approval
textbox | QA checked By Quality Manager:
textbox | Accepted By Engineers Rep:
checklist | ITP - Picton Street and Ridge Road - Enabling Works - Footpath, Kerb and channel | itp |  |  |  |  | ITP - Picton Street and Ridge Road - Enabling Works - Footpath, Kerb and channel
section | Site Set Out
checkpoint | 1 - Site Set out
label | VERIFICATION ACTIVITY: Surveyor
label | METHODS OR REFERENCE: Surveyor
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: Onsite records/photos
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Materials
checkpoint | 2 - Kerb & Channel
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5
label | HOLD POINT: In process Inspection
label | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Channel Level
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | HOLD POINT: In process Inspection
label | RECORDS: FH concrete QA sheet
label | ONSITE RESPONSIBILITY: Site Engineer
section | CIVIL WORKS
checkpoint | 4 - Concrete Footpaths
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - FP0001
label | FREQUENCY: 10m Intervals
label | ACCEPTANCE CRITERIA: Basecourse - 100mm min. thickness GAP40
label | ○ Clegg CIV > 12
label | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 5 - Tactiles
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: TDM Technical Standards - FP0010
label | FREQUENCY: Each PX
label | ACCEPTANCE CRITERIA: Warning TGSI tiles should have 100mm concrete slab underneath
label | HOLD POINT: Inprocess Inspection, Measurement
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 5.1 - Tactiles
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 5.2 - Tactiles
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 5.3 - Tactiles
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | RAMM DATA
checkpoint | 6 - As built information
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
label | HOLD POINT: In Process Inspection
label | RECORDS: As built records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | ITP APPROVAL
checkpoint | ITP Approval
label | Prepared By: Divnish Chand
label | Approving Delegate: Sumesh Sharma
checklist | ITP - Picton Street and Ridge Road - Traffic Islands | itp |  |  |  |  | ITP - Picton Street and Ridge Road - Traffic Islands
section | Site Set Out
checkpoint | 1 - Mountable Kerb
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet, photos.
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 2 - Survey Setout
label | VERIFICATION ACTIVITY: Survey
label | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
label | FREQUENCY: Prior to commencement.
label | ACCEPTANCE CRITERIA: Survey
label | HOLD POINT: As per Construction Drawings
label | RECORDS: Survey Receipt.
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Concrete Island (1)
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: Kerbs to be haunced with 20MPa Concrete
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Concrete Island (2)
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0003
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: Basecourse to be 150mm min thickness of GAP65
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 4 - Concrete Infil
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish unreinforced Concrete with 4kg/m3 red oxide
label | ○ Cross Fall of 2% or max rise in centre of 180mm
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 5 - As built information
label | VERIFICATION ACTIVITY: Drawings
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
checkpoint | 6 - RAMM DATA
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: RAMM SHEET
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | ITP APPROVAL
checkpoint | ITP Approval
label | Prepared By: Divnish Chand
label | Approving Delegate: Sumesh Sharma