## Sheet1
checklist | Façade - Membrane Gutter
section | Prestart
checkpoint | Steel QA received
checkpoint | Safe Access
checkpoint | GL and datum provided
checkpoint | Work face mark-up
checkpoint | Upload drawings and CAN's
section | Framing
checkpoint | Packing to steel/precast panels
tickbox | Correct bolts/fixings
tickbox | Correct timber size/grade
checkpoint | Studs, plates, joists and runners/nogs
tickbox | Correct fixings and hardware (Hangers, multigrips etc)
tickbox | Correct spacing
tickbox | Built to falls
tickbox | Sump locations OK
checkpoint | Carpenters QA received
checkpoint | IFG - AC Inspection received and closed out
section | Substrate
checkpoint | Plywood install
tickbox | Correct grade and thickness
tickbox | Sheet configuration OK
tickbox | Correct fixngs (Screw type and centres etc)
tickbox | Outlet recess complete
checkpoint | Carpenters QA received
checkpoint | IFG - AC Inspection received and closed out
section | Membrane
checkpoint | Drain outlet installed
checkpoint | Prep and primer to substrate
checkpoint | Membrane install
tickbox | Correct laps
tickbox | Detail at corners correct
tickbox | Detail to drain outlet correct
tickbox | termination bar installed
checkpoint | Waterproofers QA received
tickbox | ILD Testing report included
checkpoint | ITK - AC Inspection received and closed out
checklist | Structure - Timber Framing
section | Prestart
checkpoint | Steel/slab QA received
checkpoint | Safe Access
checkpoint | GL and datum provided
checkpoint | Work face mark-up
checkpoint | Upload drawings and CAN's
section | Framing
checkpoint | Packing to steel/precast panels
tickbox | Correct bolts/fixings
tickbox | Correct timber size/grade
checkpoint | Framing install
tickbox | Correct timber size/grade
tickbox | Stud spacing correct
tickbox | Ribbon, top and bottom plates correct
tickbox | Nog spacing correct
checkpoint | Openings: RL's and dimensions correct
checkpoint | Carpenters QA received
checkpoint | Structural engineer inspection report received and closed out
checkpoint | IFG - AC Inspection received and closed out