## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Facade - Membrane Gutter
section | Prestart
checkpoint | Steel QA received
checkpoint | Safe Access
checkpoint | GL and datum provided
checkpoint | Work face mark-up
checkpoint | Upload drawings and CAN's
section | Framing
checkpoint | Packing to steel/precast panels
bool | Correct bolts/fixings
bool | Correct timber size/grade
checkpoint | Studs, plates, joists and runners/nogs
bool | Correct fixings and hardware (Hangers, multigrips etc)
bool | Correct spacing
bool | Built to falls
bool | Sump locations OK
checkpoint | Carpenters QA received
checkpoint | IFG - AC Inspection received and closed out
section | Substrate
checkpoint | Plywood install
bool | Correct grade and thickness
bool | Sheet configuration OK
bool | Correct fixngs (Screw type and centres etc)
bool | Outlet recess complete
checkpoint | Carpenters QA received
checkpoint | IFG - AC Inspection received and closed out
section | Membrane
checkpoint | Drain outlet installed
checkpoint | Prep and primer to substrate
checkpoint | Membrane install
bool | Correct laps
bool | Detail at corners correct
bool | Detail to drain outlet correct
bool | termination bar installed
checkpoint | Waterproofers QA received
bool | ILD Testing report included
checkpoint | ITK - AC Inspection received and closed out
checklist | Structure - Timber Framing
section | Prestart
checkpoint | Steel/slab QA received
checkpoint | Safe Access
checkpoint | GL and datum provided
checkpoint | Work face mark-up
checkpoint | Upload drawings and CAN's
section | Framing
checkpoint | Packing to steel/precast panels
bool | Correct bolts/fixings
bool | Correct timber size/grade
checkpoint | Framing install
bool | Correct timber size/grade
bool | Stud spacing correct
bool | Ribbon, top and bottom plates correct
bool | Nog spacing correct
checkpoint | Openings: RL's and dimensions correct
checkpoint | Carpenters QA received
checkpoint | Structural engineer inspection report received and closed out
checkpoint | IFG - AC Inspection received and closed out