## ITPs
ConQA Team Notes:
Document Title: |  | ITP-243-CIV-FRMS-Stormwater Drainage-Pit & Covers Supply & Installation
ITP Description: |  | Stormwater Drainage Pit & Cover Installation
Discipline (e.g. CIV/STR/RAIL): |  | Ferris -CIV
Revision Number: |  | 0
Revision Date: |  | 27/02/2025
ITP created by: |  | Kamel ALSHOBAKI
ITP approved for use by: |  | Sandy Escalona
Special Notes to ConQA Team : |  | ITP for Ferris only
Inspection & Test Plan - Stormwater Drainage Pit & Cover Only
|  |  | Document No.: ITP-243-CIV-FRMS-Stormwater Drainage-Pit & Covers Supply & Installation | [5 empty] | Revision: | 0
[9 empty] | Date: | 27/02/2025
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 701 (May 2020) VicRoads Section 705 (June 2023) IFC Drawings CHK-001-CIV-Stormwater Drainage Pipes Installation Rev 0 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries-Materials
2.2 | Precast Drainage Pit | VR Cl 705.04 VR Cl 705.07 VR Cl 705.09 | Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with VR Section 705, BTN 033, Section 610 and 611. All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of VR Section 705.04 610. Concrete grades shall comply with Table 705.041 Enter: Teambinder Material Approval number [free text box] Attach: precast drainage pit delivery docket | Document Review | Prior to Commencement | HP* | PE/SE | Teambinder Material Approval Precast drainage pit delivery docket
2.5 | Drainage Pit - Step Irons | VR Cl 705.04 VR Cl 705.12 | Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04 Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with VR Section 705 and AS 1657. Enter: Teambinder Material Approval number [free text box] Attach: step irons delivery docket | Document Review | Prior to Commencement | HP* | PE/SE | Teambinder Material Approval Number Step irons delivery docket
2.6 | Drainage Bedding Material | VR Cl 701.09 | Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092. Enter: Teambinder Material Approval number [free text box] Attach: bedding material delivery docket | Document Review | Prior to Commencement | HP* | PE/SE | Teambinder Material Approval - Bedding Material delivery docket
2.7 | Drainage Backfill Material | VR Cl 701.09 VR Cl 701.19 | Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092. Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with VR Section 701.19 Enter: Teambinder Material Approval number [free text box] Attach: backfill material delivery docket | Document Review | Prior to Commencement | HP* | PE/SE | Teambinder Material Approval - Backfill Material delivery docket
3 | Pre-Construction Activities
3.1 | Survey Set Out - Pits | IFC Drawings VR Cl 701.10 | Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent. Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10 | Survey | Each Lot | IP | PE | This ITP
4 | Construction / Installation Activities
4.1 | Pits - Excavation | IFC Drawings VR Cl 705.05 | Excavation shall be to the depth indicated on the IFC drawings or as necessary to secure a satisfactory foundation. Precast pits shall have min of 400mm clearance from all external faces of the pit to each face of the excavation. | Visual inspection Measure | Each Lot | IP | SE | This ITP
4.2 | Pits - Placement of Bedding Material | IFC Drawings VR Cl 705.05 | Bedding conforming to to 701.09 shall be supplied, placed and compacted to a thickness: > 80mm for clay foundations > 150mm for rock foundations | Visual inspection Measure | Each Lot | IP | SE | This ITP
4.3 | Pits - Bedding Testing | IFC Drawings VR Cl 701.20 | Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three. Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material (Swell ≥ 2.5%) shall be mantained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer | Compaction Test | Each Lot | IP | SE | This ITP
4.4 | Pits - Placement of Precast Drainage Pit | IFC Drawings VR Cl 701.10 | Survey pick-up to verify: - Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm - Offset of entry pits required to match lines of kerbs or barriers ±20 mm | Visual inspection Measure | Each Lot | IP | SE | This ITP
4.5 | Pits - Jointing & Drainage Connections | VR Cl 705.11 VR Cl 705.15 | All connections to drainage pits shall be neatly made in accordance with VR Section 705.11. Openings into drainage pit walls to facilitate drainage connections shall be neatly saw cut to the required size not more than 50mm greater than pipe diameter. Breaking out of holes is not permitted. Drainage pits shall be replaced if circumferential or longitudinal cracking occurs as a result of installing holes or if the hole exceeds the pipe diameter by more than 50 mm. Exposed reinforcement shall be coated with an approved epoxy treatment to prevent corrosion prior to rendering around the pipes. | Visual inspection Measure | Each Lot | IP | SE | This ITP
4.6 | Pits - Shaping of Floor | VR Cl 705.13 | Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one‑third of the diameter of the outlet pipe with cementitious mortar in accordance with VR Clause 610.33 | Visual inspection Measure | Each Lot | IP | SE | This ITP
4.7 | Pits - Step Irons | IFC Drawings VR Cl 705.12 | Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with VR Section 705 and AS 1657. Ladder rungs shall be located directly below the opening in the cover and set into a wall which has no openings, or beside an opening, or accross a corner of a pit. Step rungs do not come within 50mm of the top of the riser. Ladder rungs shall have circular or rounded edges. Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions. | Visual inspection Measure | Each Lot | IP | SE | This ITP
4.8 | Pits - Fitting of Covers | IFC Drawings VR Cl 705.17 | Frames for drainage pit covers shall be cast into the top of the drainage pit or bedded on fresh mortar, 5 mm thick, consisting of two parts of sand, one part of cement and sufficient water to produce a mix of suitable consistency. Height shall be within 10mm of the design level and the line of the cover shall be within 10mm of the design kerb line. | Visual inspection Measure | Each Lot | IP | SE | This ITP
4.9 | Pits - Backfilling Around Drainage Pits | VR Cl 705.18 | Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment. | Visual inspection Measure | Each Lot | IP | SE | This ITP
5 | Post-construction / Post-installation Activities
5.1 | As Built Survey | VR Section 701.10 | Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in VR Section 701.10 Attach: As-Built Survey Conformance | Document Review | Each lot | IP | SE | As-Built Survey Report
5.2 | Compaction and Moisture content tests | VR Cl 701.20 | Bedding and backfill shall be placed and compacted in layers not exceeding 150mm loose thickness. Bedding and backfill shall be assessed for compaction and or moisture in lots (3 tests per lot). A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls. Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested. ATTACH: Compaction and Moisture content test results: | Document Review | Each Lot | IP | SE/PE | Test Results
5.3 | Repairs to Damaged pits | VR Section 705.16 | The method of repair of minor surface imperfections including porous spots, shallow honeycombing, rough areas and blow holes not conforming to the class of surface finish as specified in clause 705.14. The cementitious patch repair of other concrete defects shall be in accordance with Section 689. Epoxy materials shall not be used for the patch repair of concrete. The exposed surface of the repaired area shall be similar in texture and colour to the surrounding concrete. | Document Review for Repair Procedure Visual Inspection | Each lot | HP* | SE/PE | ConQA HP Release Approved Repair Procedure
5.4 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder. Enter: TeamBinder NCR number (if applicable) | Document Review | Once, prior to closure of this lot / element / Work area | HP* | PE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: