## Table 1
,
| Client: AIAL | [7 empty] | Subcontractor: V&B | [8 empty] | Work Area: Sub Structure
| Project Name: Domestic Jet Terminal | [7 empty] | Job No: HA0423 | [8 empty] | Subcontractor Representative: Ross Ferraby
1. ITP Element : Pile Cap and Beam Backfilling
2. Revision Records
| Rev No. |  | Revision Description | [11 empty] | Name of Author |  |  |  |  | Authorised by: |  |  | Date
| 0 |  | For Approval | [11 empty] | Ross Ferraby |  |  |  |  | Joe Burke |  |  | 2024-09-10
| A |  | For Approval Mott Mac-CAN-000129 | [11 empty] | Ross Ferraby |  |  |  |  | Joe Burke |  |  | 2024-10-29
B
4
5
3. Relevant Documents
| Doc No. |  |  | Specification/ Drwgs/ Standards |  |  |  | Additional Info |  |  |  | Document No. |  | Specification/ Drwgs/ Standards | [8 empty] | Additional Info
| 1 |  |  | DP001-MMD-SPC-ST-Z-Z-0001 Rev 01 Structural Specifications (8 Aug 24) |  |  |  | Section 2 |  |  |  | 5 |  | Winstone MTR to follow if used
| 2 |  |  | Stevenson MTR ATAP65 Portage Rd Quarry |  |  |  | Material Cert 25/09/24 |  |  |  | 6
| 3 |  |  | WWLW_Domestic Processor_Airfield and Headhouse_EMP_Rev 1 | [7 empty] | 7
| 4 | [10 empty] | 8
4. Document Deliverables (The documents listed below shall be completed and compiled during the course of the construction)
[17 empty] | Inspected by* |  |  |  |  | Hold Points
|  | Description Inspection / test | [7 empty] | Acceptance Criteria |  |  | Devices |  |  | Reporting Format | HCL |  | SC |  | Consult | Sign off Remarks
No. | [5 empty] | Frequency | Spec/standard
1 |  | Representative |  |  |  | once | Strut 2.3 |  |  | Accept/Reject |  |  | N/A |  |  | CV |  |  | SUB |  | R |  | Hawkins-GCOR-1784
2 |  | Silt Control |  |  |  | Daily | Strut 2.11 |  |  | Resource Council Requirements |  |  | N/A Observation |  |  | N/A included in pre start | M |  | M
3 |  | Dewatering |  |  |  | Daily | Strut 2.12.4 |  |  | AIAL requirements no standing water |  |  | N/A Observation |  |  | N/A included in pre start | M |  | M
4 |  | Approved Backfill |  |  |  | Every new material |  |  |  | Accepted |  |  | Off Site |  |  | Certificate |  |  | SUB |  |  | Hold Point | With rev A Submission
5 |  | Removing all timber/rubbish/ loose material |  |  |  | Prior to backfill | Strut 2.16 |  |  | Observation |  |  | N/A |  |  | N/A | M |  | M |  | M
6 |  | Inspection notifications |  |  |  | TBA | Strut 2.13 Strut 1.3.2 |  |  | 2 days notice |  |  | N/A |  |  | N/A |  |  |  |  | S | Hold Point | Actions to be issued on Field
7 |  | Backfilling layers |  |  |  | Max 150mm layers or as per drwgs | Strut 2.16, |  |  | Material agreed |  |  | Tape / level |  |  | N/A | M |  | M |  | M |  | Or as instructed by Engineer
8 |  | Compaction – vibrating roller/ plate compactor etc. |  |  |  | Every layer | Strut 2.16, 2.14 |  |  | CIV equivalent to 95% of max dry density NZ4432:2022 |  |  | Clegg Impact Hammer Test |  |  | Results |  |  | SUB |  | R |  | As per test report
Measuring
9 |  | Compaction – vibrating roller/ plate compactor etc. |  |  |  | Every 3 months | Strut 2.16, 2.14 |  |  | 95% of max dry density NZ4432:2022 |  |  | NDM |  |  | Results |  |  | SUB |  | R
10 |  | Closing out Reports |  |  |  | when works is available to be closed | Civil 1.3.3 |  |  | Accept/ reject |  |  | N/A |  |  | Aconex Field | M |  |  |  | R |  | Inspection closed on Aconex Field
5. Documents
Results of Compactions
Material Certificates
6. Distribution Records
| Name |  |  |  | Position | [5 empty] | Company | [12 empty] | Date
| TBA | [9 empty] | Mott McDonalds
| TBA | [9 empty] | BECA
| TBA | [9 empty] | AIAL
 Inspect (I) – To visually examine or measure an item or contracted work operation to verify its conformance to predetermined quality requirements  Review (R) – To examine any form of documentation to establish its acceptability against specified requirements  Surveillance (S) – To observe in-process activities to the degree necessary to be assured that they comply with the established criteria  Test (T) – To subject a component, structure, or system to a controlled set of physical, chemical, environmental or operational conditions to determine or verify its capability to meet specified requirements  Witness (W) – To watch over, observe or visually examine a specific work operation or test performed by others under Contractor supervision  Monitor (M) – General oversight of work in progress with no need to document formally.  SUB (SUB) Submission