## Table 1
Client: AIAL | [8 empty] | Subcontractor: V&B | [8 empty] | Work Area: Sub Structure
Project Name: Domestic Jet Terminal | [8 empty] | Job No: HA0423 | [8 empty] | Subcontractor Representative: Ross Ferraby
1. ITP Element : Pile Cap and Beam Excavation
2. Revision Records
Rev No. |  |  | Revision Description | [11 empty] | Name of Author |  |  |  |  | Authorised by: |  |  | Date
0 |  |  | For Approval | [11 empty] | Ross Ferraby |  |  |  |  | Joe Burke |  |  | 26 August
1 |  |  | For Approval updated with comments Mott Mac- GCOR-001150 | [11 empty] | Ross Ferraby |  |  |  |  | Joe Burke |  |  | 9 September
A |  |  | For Construction | [11 empty] | Ross Ferraby |  |  |  |  | Joe Burke |  |  | 11 September
3. Relevant Documents
Doc No. |  |  |  | Specification/ Drwgs/ Standards |  |  |  | Additional Info |  |  |  | Document No. |  | Specification/ Drwgs/ Standards | [8 empty] | Additional Info
1 |  |  |  | DP001-MMD-SPC-ST-Z-Z-0001 Rev 01 Strucutral Specifications (8 Aug 24) |  |  |  | Section 2 |  |  |  | 9
2 |  |  |  | WWLW_Domestic Processor_Airfield and Headhouse_EMP_Rev 1 | [7 empty] | 10
3 | [11 empty] | 11
4 | [11 empty] | 12
5 | [11 empty] | 13
No. |  | Description Inspection / test |  |  |  | Frequency | Spec/standard |  |  | Acceptance Criteria |  |  | Measuring Devices |  |  | Reporting Format | Inspected by* |  |  |  |  | Hold Points Sign off |  | Remarks
[17 empty] | HCL |  | SC |  | Consult
1 |  | Representative |  |  |  | once | Strut 2.3 |  |  | Accept/Reject |  |  | N/A |  |  | CV |  |  | SUB |  | R |  |  | HAWKINS-GCOR- 001784
2 |  | Checklist |  |  |  | Once | Strut 2.3 |  |  | Accept/Amend |  |  | N/A |  |  | Checklist | R |  | SUB |  | R | Hold Point |  | Agreed prior to excavation commencing HAWKINS-GCOR- 001784
3 |  | Silt Control |  |  |  | Daily | Strut 2.11 |  |  | Resource Council Requirements |  |  | N/A Observation |  |  | N/A included in pre start | M |  | M |  |  |  |  | Auckland Council Guidelines 2016/005
4 |  | Dewatering |  |  |  | Daily | Strut 2.12.4 |  |  | AIAL requirements no standing water |  |  | N/A Observation |  |  | N/A included in pre start | M |  | M |  |  |  |  | Auckland Council Guidelines 2016/005
5 |  | Excavation |  |  |  | Zone | Strut 2.2.12 Strut 2.12.6 |  |  | +50mm for line and level |  |  | Total Station/ Dumpy level/ Measuring Tape |  |  | Checklist/ Marked Up Drwgs | M |  | T |  | M |  |  | Over excavation engineer to instruct
6 |  | Soft sports |  |  |  | Inspections required daily (every pile) until further arrangement | Strut 2.12.5 |  |  | <40kPA | [5 empty] | Directed by Geo Engineer - CAN | M |  | M |  | T | Hold point |  | Tested by Geotechnical engineer CAN to advise how to proceed works
7 |  | Hazardous Materials |  |  |  | As and when | [6 empty] | N/A Observation |  |  | Directed by Designer - CAN | M |  | M |  | I | Hold point |  | WWLA to advise
8 |  | Maintain Excavation |  |  |  | As and when | Strut 2.12.7 |  |  | Maintained and safe excavations |  |  | N/A Observation |  |  | N/A included in checklist | M |  | M |  |  |  |  | Temporary Works Engineer
9 |  | Inspection notifications |  |  |  | As agreed in the pre start meeting – daily | Strut 2.13 Strut 1.3.2 |  |  | 2 days notice |  |  | N/A |  |  | QA checklist | M |  |  |  | S | Hold Point |  | Actions to be closed on Field
10 |  | Closing out Reports |  |  |  | when works is available to be closed | Strut & Civ 1.3.3 |  |  | Accept/ reject |  |  | N/A |  |  | Aconex Field | M |  |  |  | R |  |  | Inspection to be issued and closed on Aconex Field
4. Document Deliverables (The documents listed below shall be completed and compiled during the course of the construction) 5. Documents
QC Checklist
6. Distribution Records
| Name |  |  |  | Position | [5 empty] | Company | [13 empty] | Date
| TBA | [9 empty] | Mott McDonalds
| TBA | [9 empty] | BECA
| TBA | [9 empty] | AIAL
 Inspect (I) – To visually examine or measure an item or contracted work operation to verify its conformance to predetermined quality requirements
 Review (R) – To examine any form of documentation to establish its acceptability against specified requirements  Surveillance (S) – To observe in-process activities to the degree necessary to be assured that they comply with the established criteria  Test (T) – To subject a component, structure, or system to a controlled set of physical, chemical, environmental or operational conditions to determine or verify its capability to meet specified requirements  Witness (W) – To watch over, observe or visually examine a specific work operation or test performed by others under Contractor supervision  Monitor (M) – General oversight of work in progress with no need to document formally.  SUB - Submission (SUB) – Document to be submitted