## Sheet1
1 | Representative | once | Strut 2.3 | Accept/Reject | N/A | CV |  | SUB | R |  | Hawkins-GCOR-1784 | 1 - Representative | Frequency - once | Spec/standard - Strut 2.3 | Acceptance Criteria - Accept/Reject | Devices - N/A | Reporting Format - CV | Inspected by: HCL - | Inspected by: SC - SUB | Inspected by: Consult - R | Hold Points: Sign off - | Remarks - Hawkins-GCOR-1784 | 1 - Representative
2 | Silt Control | Daily | Strut 2.11 | Resource Council Requirements | N/A Observation | N/A included in pre start | M | M | [14 empty] | Frequency - once
3 | Dewatering | Daily | Strut 2.12.4 | AIAL requirements no standing water | N/A Observation | N/A included in pre start | M | M | [14 empty] | Spec/standard - Strut 2.3
4 | Approved Backfill | Every new material |  | Accepted | Off Site | Certificate |  | SUB |  | Hold Point | With rev A Submission | [11 empty] | Acceptance Criteria - Accept/Reject
5 | Removing all timber/rubbish/ loose material | Prior to backfill | Strut 2.16 | Observation | N/A | N/A | M | M | M | [13 empty] | Devices - N/A
6 | Inspection notifications | TBA | Strut 2.13 Strut 1.3.2 | 2 days notice | N/A | N/A |  |  | S | Hold Point | Actions to be issued on Field | [11 empty] | Reporting Format - CV
7 | Backfilling layers | Max 150mm layers or as per drwgs | Strut 2.16, | Material agreed | Tape / level | N/A | M | M | M |  | Or as instructed by Engineer | [11 empty] | Inspected by: HCL -
8 | Compaction – vibrating roller/ plate compactor etc. | Every layer | Strut 2.16, 2.14 | CIV equivalent to 95% of max dry density NZ4432:2022 | Clegg Impact Hammer Test | Results |  | SUB | R |  | As per test report | [11 empty] | Inspected by: SC - SUB
9 | Compaction – vibrating roller/ plate compactor etc. | Every 3 months | Strut 2.16, 2.14 | 95% of max dry density NZ4432:2022 | NDM | Results |  | SUB | R | [13 empty] | Inspected by: Consult - R
10 | Closing out Reports | when works is available to be closed | Civil 1.3.3 | Accept/ reject | N/A | Aconex Field | M |  | R |  | Inspection closed on Aconex Field | [11 empty] | Hold Points: Sign off -
Remarks - Hawkins-GCOR-1784