## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ST004 A - Backfilling PC and GB | itp |  |  |  |  | ST004 A - Backfilling PC and GB REV A
section | Document Deliverables
checkpoint | 1 - Representative
label | Frequency - once
label | Spec/standard - Strut 2.3
label | Acceptance Criteria - Accept/Reject
label | Devices - N/A
label | Reporting Format - CV
label | Inspected by: SC - SUB
label | Inspected by: Consult - R
label | Remarks - Hawkins-GCOR-1784
checkpoint | 2 - Silt Control
label | Frequency - Daily
label | Spec/standard - Strut 2.11
label | Acceptance Criteria - Resource Council Requirements
label | Devices - N/A Observation
label | Reporting Format - N/A included in pre start
label | Inspected by: HCL - M
label | Inspected by: SC - M
checkpoint | 3 - Dewatering
label | Frequency - Daily
label | Spec/standard - Strut 2.12.4
label | Acceptance Criteria - AIAL requirements no standing water
label | Devices - N/A Observation
label | Reporting Format - N/A, included in pre start
label | Inspected by: HCL - M
label | Inspected by: SC - M
checkpoint | 4 - Approved Backfill
label | Frequency - Every new material
label | Acceptance Criteria - Accepted
label | Devices - Off Site
label | Reporting Format - Certificate
label | Inspected by: SC - SUB
label | Hold Points: Sign off - Hold Point
label | Remarks - With rev A Submission
holdpoint | HOLD POINT
checkpoint | 5 - Removing all timber/rubbish/ loose material
label | Frequency - Prior to backfill
label | Spec/standard - Strut 2.16
label | Acceptance Criteria - Observation
label | Devices - N/A
label | Reporting Format - N/A
label | Inspected by: HCL - M
label | Inspected by: SC - M
label | Inspected by: Consult - M
checkpoint | 6 - Inspection notifications
label | Frequency - TBA
label | Spec/standard - Strut 2.13, Strut 1.3.2
label | Acceptance Criteria - 2 days notice
label | Devices - N/A
label | Reporting Format - N/A
label | Inspected by: Consult - S
label | Hold Points: Sign off - Hold Point
label | Remarks - Actions to be issued on Field
holdpoint | HOLD POINT
checkpoint | 7 - Backfilling layers
label | Frequency - Max 150mm layers or as per drwgs
label | Spec/standard - Strut 2.16,
label | Acceptance Criteria - Material agreed
label | Devices - Tape / level
label | Reporting Format - N/A
label | Inspected by: HCL - M
label | Inspected by: SC - M
label | Inspected by: Consult - M
label | Remarks - Or as instructed by Engineer
checkpoint | 8 - Compaction – vibrating roller/ plate compactor etc.
label | Frequency - Every layer
label | Spec/standard - Strut 2.16, 2.14
label | Acceptance Criteria - CIV equivalent to 95% of max dry density NZ4432:2022
label | Devices - Clegg Impact Hammer Test
label | Reporting Format - Results
label | Inspected by: SC - SUB
label | Inspected by: Consult - R
label | Remarks - As per test report
section | Measuring
checkpoint | 9 - Compaction – vibrating roller/ plate compactor etc.
label | Frequency - Every 3 months
label | Spec/standard - Strut 2.16, 2.14
label | Acceptance Criteria - 95% of max dry density NZ4432:2022
label | Devices - NDM
label | Reporting Format - Results
label | Inspected by: SC - SUB
label | Inspected by: Consult - R
checkpoint | 10 - Closing out Reports
label | Frequency - when works is available to be closed
label | Spec/standard - Civil 1.3.3
label | Acceptance Criteria - Accept/ reject
label | Devices - N/A
label | Reporting Format - Aconex Field
label | Inspected by: HCL - M
label | Inspected by: Consult - R
label | Remarks - Inspection closed on Aconex Field
checklist | ST004 - Backing Pile Caps and Beams | itp |  |  |  |  | ST004 - Backing Pile Caps and Beams REV 0
section | Document Deliverables
checkpoint | 1 - Representative
label | Frequency - once
label | Spec/standard - Strut 2.3
label | Acceptance Criteria - Accept/Reject
label | Devices - N/A
label | Reporting Format - CV
label | Inspected by: SC - SUB
label | Inspected by: Consult - R
label | Remarks - Hawkins-GCOR-1784
checkpoint | 2 - Silt Control
label | Frequency - Daily
label | Spec/standard - Strut 2.11
label | Acceptance Criteria - Resource Council Requirements
label | Devices - N/A Observation
label | Reporting Format - N/A included in pre start
label | Inspected by: HCL - M
label | Inspected by: SC - M
checkpoint | 3 - Dewatering
label | Frequency - Daily
label | Spec/standard - Strut 2.12.4
label | Acceptance Criteria - AIAL requirements no standing water
label | Devices - N/A Observation
label | Reporting Format - N/A, included in pre start
label | Inspected by: HCL - M
label | Inspected by: SC - M
checkpoint | 4 - Approved Backfill
label | Frequency - Every new material
label | Spec/standard - Mott Mac-GCOR- 000999
label | Acceptance Criteria - Accepted
label | Devices - Off Site
label | Reporting Format - Certificate
label | Inspected by: SC - SUB
label | Hold Points: Sign off - Hold Point
label | Remarks - Accepted Mott Mac- GCOR-000999
holdpoint | HOLD POINT
checkpoint | 5 - Removing all timber/rubbish/ loose material
label | Frequency - Prior to backfill
label | Spec/standard - Strut 2.16
label | Acceptance Criteria - Observation
label | Devices - N/A
label | Reporting Format - N/A
label | Inspected by: HCL - M
label | Inspected by: SC - M
label | Inspected by: Consult - M
checkpoint | 6 - Inspection notifications
label | Frequency - TBA
label | Spec/standard - Strut 2.13, Strut 1.3.2
label | Acceptance Criteria - 2 days notice
label | Devices - N/A
label | Reporting Format - N/A
label | Inspected by: Consult - S
label | Hold Points: Sign off - Hold Point
label | Remarks - Actions to be issued on Field
holdpoint | HOLD POINT
checkpoint | 7 - Backfilling layers
label | Frequency - Max 150mm layers or as per drwgs
label | Spec/standard - Strut 2.16,
label | Acceptance Criteria - Material agreed
label | Devices - Tape / level
label | Reporting Format - N/A
label | Inspected by: HCL - M
label | Inspected by: SC - M
label | Inspected by: Consult - M
label | Remarks - Or as instructed by Engineer
checkpoint | 8 - Compaction – vibrating roller/ plate compactor etc.
label | Frequency - Over layer
label | Spec/standard - Strut 2.16, 2.14
label | Acceptance Criteria - 95% of max dry density NZ4402
label | Devices - Clegg Impact Hammer Test, NDM
label | Reporting Format - Results
label | Inspected by: SC - SUB
label | Inspected by: Consult - R
section | Measuring
checkpoint | 9 - Closing out Reports
label | Frequency - when works is available to be closed
label | Spec/standard - Civil 1.3.3
label | Acceptance Criteria - Accept/ reject
label | Devices - N/A
label | Reporting Format - Aconex Field
label | Inspected by: HCL - M
label | Inspected by: Consult - R
label | Remarks - Inspection closed on Aconex Field
checklist | STR-002-A Excavation PC and GB | itp |  |  |  |  | STR-002-A Excavation PC and GB REV A
section | Document Deliverables
checkpoint | 1 - Representative
label | Frequency - once
label | Spec/standard - Strut 2.3
label | Acceptance Criteria - Accept/Reject
label | Measuring Devices - N/A
label | Reporting Format - CV
label | Inspected by: SC - SUB
label | Inspected by: Consult - R
label | Remarks - HAWKINS-GCOR- 001784
checkpoint | 2 - Checklist
label | Frequency - Once
label | Spec/standard - Strut 2.3
label | Acceptance Criteria - Accept/Amend
label | Measuring Devices - N/A
label | Reporting Format - Checklist
label | Inspected by: HCL - R
label | Inspected by: SC - SUB
label | Inspected by: Consult - R
label | Hold Points: Sign off - Hold Point
label | Remarks - Agreed prior to excavation commencing HAWKINS-GCOR- 001784
holdpoint | HOLD POINT
checkpoint | 3 - Silt Control
label | Frequency - Daily
label | Spec/standard - Strut 2.11
label | Acceptance Criteria - Resource Council Requirements
label | Measuring Devices - N/A Observation
label | Reporting Format - N/A included in pre start
label | Inspected by: HCL - M
label | Inspected by: SC - M
label | Remarks - Auckland Council Guidelines 2016/005
checkpoint | 4 - Dewatering
label | Frequency - Daily
label | Spec/standard - Strut 2.12.4
label | Acceptance Criteria - AIAL requirements no standing water
label | Measuring Devices - N/A Observation
label | Reporting Format - N/A, included in pre start
label | Inspected by: HCL - M
label | Inspected by: SC - M
label | Remarks - Auckland Council Guidelines 2016/005
checkpoint | 5 - Excavation
label | Frequency - Zone
label | Spec/standard - Strut 2.2.12, Strut 2.12.6
label | Acceptance Criteria - +50mm for line and level
label | Measuring Devices - Total Station/ Dumpy level/ Measuring Tape
label | Reporting Format - Checklist/ Marked Up Drwgs
label | Inspected by: HCL - M
label | Inspected by: SC - T
label | Inspected by: Consult - M
label | Remarks - Over excavation engineer to instruct
checkpoint | 6 - Soft sports
label | Frequency - Inspections required daily (every pile) until further arrangement
label | Spec/standard - Strut 2.12.5
label | Acceptance Criteria - <40kPA
label | Reporting Format - Directed by Geo Engineer - CAN
label | Inspected by: HCL - M
label | Inspected by: SC - M
label | Inspected by: Consult - T
label | Hold Points: Sign off - Hold point
label | Remarks - Tested by Geotechnical engineer CAN to advise how to proceed works
holdpoint | HOLD POINT
checkpoint | 7 - Hazardous Materials
label | Frequency - As and when
label | Measuring Devices - N/A Observation
label | Reporting Format - Directed by Designer - CAN
label | Inspected by: HCL - M
label | Inspected by: SC - M
label | Inspected by: Consult - I
label | Hold Points: Sign off - Hold point
label | Remarks - WWLA to advise
holdpoint | HOLD POINT
checkpoint | 8 - Maintain Excavation
label | Frequency - As and when
label | Spec/standard - Strut 2.12.7
label | Acceptance Criteria - Maintained and safe excavations
label | Measuring Devices - N/A Observation
label | Reporting Format - N/A included in checklist
label | Inspected by: HCL - M
label | Inspected by: SC - M
label | Remarks - Temporary Works Engineer
checkpoint | 9 - Inspection notifications
label | Frequency - As agreed in the pre start meeting – daily
label | Spec/standard - Strut 2.13, Strut 1.3.2
label | Acceptance Criteria - 2 days notice
label | Measuring Devices - N/A
label | Reporting Format - QA checklist
label | Inspected by: HCL - M
label | Inspected by: Consult - S
label | Hold Points: Sign off - Hold Point
label | Remarks - Actions to be closed on Field
holdpoint | HOLD POINT
checkpoint | 10 - Closing out Reports
label | Frequency - when works is available to be closed
label | Spec/standard - Strut & Civ 1.3.3
label | Acceptance Criteria - Accept/ reject
label | Measuring Devices - N/A
label | Reporting Format - Aconex Field
label | Inspected by: HCL - M
label | Inspected by: Consult - R
label | Remarks - Inspection to be issued and closed on Aconex Field