## Greys Schedule
Greys Ave
Tower A
Unit # | Kitchen Type
A801 | A STUDIO
A804 | D
A806 | C UNI
A807 | E UNI
A901 | A STUDIO
A904 | D
A906 | C UNI
A907 | E UNI
A1001 | A STUDIO
A1002 | B ACC 2
A1003 | B ACC 2
A1004 | D
A1006 | C UNI
A1007 | E UNI
A1101 | A STUDIO
A1102 | B ACC 2
A1103 | B ACC 2
A1104 | D
A1106 | C UNI
A1107 | E UNI
A1201 | A STUDIO
A1202 | B ACC 2
A1203 | B ACC 2
A1204 | D
A1206 | C UNI
A1207 | E UNI
Tower A Laundry Unit and Shelf
Unit # | Type
201 | Type A
205 | Type F
301 | Type A
305 | Type F
401 | Type A
405 | Type F
501 | Type A
505 | Type F
601 | Type A
605 | Type F
701 | Type A
705 | Type F
801 | Type A
805 | Type F
901 | Type A
905 | Type F
1001 | Type A
1005 | Type F
1101 | Type A
1105 | Type F
1201 | Type A
1205 | Type F
Tower B Storage Cupboard and Robe Shelving
Unit # | Type
601 | Type H
602 | Type J
603 | Type K
604 | Type K
605 | Type H
606 | Type J
701 | Type H
702 | Type J
703 | Type K
704 | Type K
705 | Type H
706 | Type J
801 | Type H
802 | Type J
803 | Type K
804 | Type K
805 | Type H
806 | Type J
901 | Type H
902 | Type J
903 | Type K
904 | Type K
905 | Type H
906 | Type J

## Layout
Type | Name
Checklist | Kitchen Joinery QA
section | Joinery install
checkpoint | Area ready for joinery install
checkpoint | Joinery on site and free from damage
checkpoint | Kitchen install - Area left tidy - Photos
bool | All units installed
bool | No delivery or install damage
checkpoint | Kicks installed and Silicone complete
Section | Handover
checkpoint | Final Handover
holdpoint | Final Handover - Request Signoff
Type | Name
Checklist | Laundry Joinery QA
section | Joinery install
checkpoint | Area ready for joinery install
checkpoint | Joinery on site and free from damage
checkpoint | Laundry install - Area left tidy - Photos
bool | Unit installed
bool | Shelf installed
bool | No delivery or install damage
checkpoint | Kick installed and Silicone complete
Section | Handover
checkpoint | Final Handover
holdpoint | Final Handover - Request Signoff
Type | Name
Checklist | Laundry Joinery QA
section | Joinery install
checkpoint | Area ready for joinery install
checkpoint | Joinery on site and free from damage
checkpoint | Laundry install - Area left tidy - Photos
bool | Unit installed
bool | Shelf installed
bool | No delivery or install damage
checkpoint | Kick installed and Silicone complete
Section | Handover
checkpoint | Final Handover
holdpoint | Final Handover - Request Signoff
Type | Name
Checklist | Storage and Robe Shelving QA
section | Joinery install
checkpoint | Area ready for joinery install
checkpoint | Joinery on site and free from damage
checkpoint | Storage Shelving install - Area left tidy - Photos
bool | Storage Shelves installed
bool | Robe Shelves installed
bool | No delivery or install damage
checkpoint | Silicone complete
Section | Handover
checkpoint | Final Handover
holdpoint | Final Handover - Request Signoff