## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | SVR: |  |  |  |  | Yes | Engineer Site Visit Report | 02963c06-15b7-4667-a33c-9941bd9ea40e
checkpoint-group |  |  | section | Site Visit Report
checkpoint-status |  |  | checkpoint | SVR Attached
text | 2bf6224d-212d-4c05-8d20-702627eeda57 |  | textbox | SVR No.
folder-normal |  | Not allowed as a child of checklist-sectioned. | folder-normal | Follow-Up Action(s)
checkpoint-group |  |  | section | Close-Out
checkpoint-status |  |  | checkpoint | SVR Closed-Out
checklist-sectioned |  |  | checklist | Ceiling Preline incl High Level Services |  |  |  |  | Yes | Ceiling Preline incl High Level Services | 1397430a-c250-4975-b408-6d3672401e83
checkpoint-group |  |  | section | QA - Plumbing First Fix
checkpoint-status |  |  | checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Consultants Inspection sign off
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Council inspection and testing complete and signed off
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Witness testing of pipework by Hawkins
checkpoint-group |  |  | section | Fire Protection (Sprinklers & Alarms) First Fix
checkpoint-status |  |  | checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Consultant inspection sign off
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Witness testing of pipework by Hawkins
checkpoint-group |  |  | section | Mechanical Services First Fix
checkpoint-status |  |  | checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | All required testing complete
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Consultant sign off
checkpoint-status |  |  | checkpoint | All ends covered/protected to reduce debris
checkpoint-status |  |  | checkpoint | Witness testing of compliance check by Hawkins
checkpoint-group |  |  | section | Electrical First Fix
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | All required testing complete
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Consultant sign off
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Witness testing of compliance check by Hawkins
checkpoint-group |  |  | section | Data First Fix
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | All required testing complete
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Consultant sign off
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Witness testing of compliance check by Hawkins
checkpoint-group |  |  | section | Security First Fix
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | All required testing complete
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Consultant sign off
checkpoint-status |  |  | checkpoint | Engineer has signed off Seismic restraints
checkpoint-status |  |  | checkpoint | Witness testing of compliance check by Hawkins
checkpoint-group |  |  | section | Rondo Ceiling Grid Installation
checkpoint-status |  |  | checkpoint | Service penetrations mark out completed, checked and acceptable (clashes considered)
checkpoint-status |  |  | checkpoint | Ceiling Grid ( pass when all below ticked)
boolean | 68e7cef0-de8a-5c29-8460-fc52fad1daa9 |  | tickbox | Ceiling height correct
boolean | 74b9a255-4e27-5a78-8ecd-f370ccb73e3a |  | tickbox | Appropriate fixings used and installed as per required specification
boolean | 98f383af-0990-5f7b-8a95-6e5e275ead5c |  | tickbox | Appropriate spacings for respective grid elements
boolean | 70642190-88ae-5cef-aa35-b8f91b909586 |  | tickbox | Perimeter channel/angle installed correctly
boolean | ba858e08-ae3b-51aa-9d03-c4d16db0180e |  | tickbox | All strong backs installed where required to meet specification
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | Insulation Prior to Lining
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Insulation pre lining works completed, checked & approved
boolean | 0e8a6528-73d9-5e03-87e2-32322c4873f4 |  | tickbox | Correct product & R value as per specification
boolean | 34066410-3f3f-5290-b2ec-9cf9ed662c9d |  | tickbox | Fitting Snug
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | Council Sign Off
checkpoint-status |  |  | checkpoint | Council preline inspection passed
checklist-flat |  |  | checklist | Base Isolator |  |  |  |  | Yes | Base Isolator | 161037e5-9cdf-4639-a81f-373b64ced9cf
checkpoint-status |  |  | checkpoint | Base Isolator
text | 567df56e-5eb8-598a-9772-d8f4ecf553a7 |  | textbox | Zone / Level / Grid(s) recorded
checkpoint-status |  |  | checkpoint | RL base isolator checked
button | c940c22f-ea8a-5aca-b7db-1ea3416a4105 |  | button | Isolator type | LRB,NRB,PS-A,PS-B,PS-C
checklist-sectioned |  |  | checklist | ISN Report: |  |  |  |  | Yes | ISN Report | 368f0a2d-e9ae-46ac-b6a5-d673601baf08
checkpoint-group |  |  | section | Site Visit Report
checkpoint-status |  |  | checkpoint | SVR Attached
text | 2bf6224d-212d-4c05-8d20-702627eeda57 |  | textbox | SVR No.
folder-normal |  | Not allowed as a child of checklist-sectioned. | folder-normal | Follow-Up Action(s)
checkpoint-group |  |  | section | Close-Out
checkpoint-status |  |  | checkpoint | SVR Closed-Out
checklist-flat |  |  | checklist | Site Concrete Checklist |  |  |  |  | Yes | Site Concrete Checklist | 3e65946a-d9f9-4b20-bb2b-6e917280ca60
checkpoint-status |  |  | checkpoint | Excavation depth and location checked and correct
checkpoint-status |  |  | checkpoint | Ground conditions acceptable
checkpoint-status |  |  | checkpoint | Concrete specifications checked, correct and delivery docket photographed
checkpoint-status |  |  | checkpoint | Site concrete placed
text | 4d63a2e5-37bf-5496-b4fa-b5b68f82dc43 |  | textbox | Placed by:
checkpoint-status |  |  | checkpoint | Concrete placed to the correct height
checkpoint-status |  |  | checkpoint | Site concrete pour completed and finish acceptable
checklist-flat |  |  | checklist | Civil - Sanitary Sewer |  |  |  |  | Yes | Civil - Sanitary Sewer | 4db08abb-c08b-4125-baed-699b2c45e719
checkpoint-status |  |  | checkpoint | Location details and relevant mark ups attached
checkpoint-status |  |  | checkpoint | Consultant inspection completed as required
checkpoint-status |  |  | checkpoint | Council Inspection completed as required
checkpoint-status |  |  | checkpoint | Invert levels recorded
checkpoint-status |  |  | checkpoint | Invert levels as per design
checkpoint-status |  |  | checkpoint | Received QA from Subcontractor?
checkpoint-status |  |  | checkpoint | As Built drawings received
checkpoint-status |  |  | checkpoint | CCTV Survey
checkpoint-status |  |  | checkpoint | Certificates provided
checkpoint-status |  |  | checkpoint | Installation record photos
checkpoint-status |  |  | checkpoint | Foul Installation completed
checkpoint-status |  |  | checkpoint | Any onsite changes documented (Attach marked up drawings, etc)
checklist-flat |  |  | checklist | Description/Number: |  |  |  |  | Yes | ISN Follow Up Action | 4ecac9a3-994c-4f28-b83b-5ae35da7bced
checkpoint-status |  |  | checkpoint | Follow-Up Action completed
text | ddf14301-8239-5b3b-951b-d5fa379a59cd |  | textbox | Specific Location:
text | 91c806c7-c985-559e-94d6-00a2b29bd0fd |  | textbox | Detail:
text | f17daeb2-6b36-59f2-add1-159d86b7a239 |  | textbox | Action Required:
holdpoint |  |  | signoff | Request Review
checklist-flat |  |  | checklist | Ceiling Postline |  |  |  |  | Yes | Ceiling Postline | 5231d811-39b5-4a95-b5b8-91f3f6ab9b91
checkpoint-status |  |  | checkpoint | Correct linings installed as per linings plan
checkpoint-status |  |  | checkpoint | Fixings as per specification including if glue required
checkpoint-status |  |  | checkpoint | Service penetrations cut out as per architecture RCP
checkpoint-status |  |  | checkpoint | Any ceiling hatches installed & fixed correctly
checkpoint-status |  |  | checkpoint | Ceiling approved for stopping
checkpoint-status |  |  | checkpoint | Stopping light check complete ready for paint
checklist-flat |  |  | checklist | Backfill Checklist |  |  |  |  | Yes | Backfill Checklist | 5b9f438f-c1de-4e63-a188-742908209859
checkpoint-status |  |  | checkpoint | Backfill methodology and material confirmed
checkpoint-status |  |  | checkpoint | Any formwork/ debris removed from area
checkpoint-status |  |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint-status |  |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closed out
checkpoint-status |  |  | checkpoint | General photos and observations during backfill
checkpoint-status |  |  | checkpoint | Backfill completed correctly and heights checked/ correct
checklist-sectioned |  |  | checklist | Concrete Pour Checklist (Self Perform) |  |  |  |  | Yes | Concrete Pour Checklist (Self Perform) | 612e926c-bce9-4f0f-8faa-fb3e43064a34
checkpoint-group |  |  | section | Pour Details
checkpoint-no-status |  |  | checkpoint | Pour Details:
text | 56535b3e-d0a7-5921-adfc-f8c02e5c2a96 |  | textbox | Area to be poured:
text | a13f129e-ab15-58c3-b2ea-f102f4655927 |  | textbox | Date of pour:
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group |  |  | section | Formwork and Embedded Items
checkpoint-status |  |  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint-status |  |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork etc)
checkpoint-status |  |  | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
checkpoint-group |  |  | section | Reinforcing
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise Remedial / Request trades QA / Sign Off
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Splice laps checked/correct
checkpoint-status |  |  | checkpoint | All couplers installed correctly
checkpoint-status |  |  | checkpoint | Any starter bars are installed correctly (location, size and spacing )
checkpoint-status |  |  | checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Welding certificates sited and attached
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Any waterproofing elements have been correctly installed and checked
checkpoint-status |  |  | checkpoint | Any relevant service requirements completed (locations checked and accurate)
checkpoint-status |  |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint-status |  |  | checkpoint | All relevant inspections completed and attached
checkpoint-status |  |  | checkpoint | Main contractor inspection completed - Approval given to pour concrete
checkpoint-group |  |  | section | Concrete Supplier Specifics
checkpoint-no-status |  |  | checkpoint | Concrete Supplier Specifics:
text | 4f39b43a-f59b-591f-a22e-def2e43c795f |  | textbox | Supplier Name:
text | 74ff00be-21af-5944-858e-8b549bbcb90c |  | textbox | Specified concrete strength:
text | e99293c8-715e-5ecb-ab91-81453b575302 |  | textbox | Concrete strength ordered:
text | 0d971149-5263-5e2a-b3ee-90464604b481 |  | textbox | Concrete quantity ordered:
checkpoint-status |  |  | checkpoint | Test blocks booked
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-group |  |  | section | Concrete Distribution
checkpoint-status |  |  | checkpoint | General distribution photos, documents and observations attached
checkpoint-status |  |  | checkpoint | All concrete distributed correctly (area left clean and tidy)
checkpoint-group |  |  | section | Placement Method
checkpoint-status |  |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint-status |  |  | checkpoint | Heights and falls checked/confirmed before placement
button | 1cf85b65-9ecb-5aec-863e-753b0f2266f5 |  | button | Is the cover correct to specification | Yes, No
checkpoint-status |  |  | checkpoint | Heights and falls checked/ confirmed after placement
checkpoint-status |  |  | checkpoint | Any curing compound applied correctly
checkpoint-status |  |  | checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checklist-flat |  |  | checklist | Description/Number: |  |  |  |  | Yes | Engineer Follow Up Action | 66bf98fc-2aca-4032-a7f9-6f5ab8a7f23c
checkpoint-status |  |  | checkpoint | Follow-Up Action completed
text | ddf14301-8239-5b3b-951b-d5fa379a59cd |  | textbox | Specific Location:
text | 91c806c7-c985-559e-94d6-00a2b29bd0fd |  | textbox | Detail:
text | f17daeb2-6b36-59f2-add1-159d86b7a239 |  | textbox | Action Required:
holdpoint |  |  | signoff | Request Review
checklist-flat |  |  | checklist | Bulk Excavation Checklist |  |  |  |  | Yes | Bulk Excavation Checklist | 78c10b4e-549c-419f-a24c-2baece743a91
checkpoint-status |  |  | checkpoint | Excavation depth determined using appropriate RL's
checkpoint-status |  |  | checkpoint | Confirm location and isolation of relevant services
checkpoint-status |  |  | checkpoint | General excavation documentation and photos attached
checkpoint-status |  |  | checkpoint | Any batters formed correctly
checkpoint-status |  |  | checkpoint | Any trenches/ pits / hazardous areas appropriately isolated
checkpoint-status |  |  | checkpoint | Any soft spots identified and appropriate remedial completed
checkpoint-status |  |  | checkpoint | Any hardfill/ blinding installed correctly to required specification
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Excavation completed - Correct locations and RL's achieved
checklist-flat |  |  | checklist | Flooring |  |  |  |  | Yes | Flooring | 88d090ae-0b7c-4c6c-ac5b-e46cb473bff6
checkpoint-status |  |  | checkpoint | Floor substrate clean, dry, ready for finishes
checkpoint-status |  |  | checkpoint | Finishes as per architectural plans
checkpoint-status |  |  | checkpoint | Trim thresholds junction as per detail
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checklist-flat |  |  | checklist | Shotcrete Fill Works Checklist |  |  |  |  | Yes | Shotcrete Fill Works Checklist | 9a209efb-31eb-4d67-864d-38849fd15c70
checkpoint-status |  |  | checkpoint | Specified the cut upper or lower cut and position (grid lines)
checkpoint-status |  |  | checkpoint | Imported fill material checked either GAP65 hardfill-HOROKIWI or RM65 hardfill-Winstones belmont
checkpoint-status |  |  | checkpoint | Every 500mm layer plateform checked
checkpoint-status |  |  | checkpoint | Compaction test with Mats check and passed
checkpoint-status |  |  | checkpoint | As built location of the cut confirmed
checkpoint-status |  |  | checkpoint | As built the slope either 40deg or 60deg
checkpoint-status |  |  | checkpoint | Progress photos
checklist-flat |  |  | checklist | Bore Drain Checklist |  |  |  |  | Yes | Bore Drain Checklist | 9baf8235-8c5a-48a6-8670-3b7e4a48268d
checkpoint-status |  |  | checkpoint | Set out confirmed
checkpoint-status |  |  | checkpoint | Coordinate with pile locations
checkpoint-status |  |  | checkpoint | General photos, comments and observations during drilling
checklist-flat |  |  | checklist | Ground Anchor Checklist |  |  |  |  | Yes | Ground Anchor Checklist | 9ecbef25-39ec-42d9-8101-eda57339d4ac
checkpoint-status |  |  | checkpoint | Set out confirmed
checkpoint-status |  |  | checkpoint | Drilling angle confirmed
checkpoint-status |  |  | checkpoint | Coordinate with pile locations
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Load testing complete
checkpoint-status |  |  | checkpoint | General photos, comments and observations during drilling
checklist-flat |  |  | checklist | Grouting Checklist |  |  |  |  | Yes | Grouting Checklist | b0179418-bc04-4424-bfff-68d97253f7ea
checkpoint-status |  |  | checkpoint | Dry pack completed?
checkpoint-status |  |  | checkpoint | Pumped used?
checkpoint-status |  |  | checkpoint | Grout Used: Mapei SP (If different add in comments)
text | 93cdd564-7873-50ad-a6ea-b748040d5270 |  | textbox | Number of bags of grout used
checkpoint-status |  |  | checkpoint | Is the grout mixed properly? (3.0 to 3.4 Litres of Water per bag)
text | ecd64d6e-531d-5263-9781-a4b1eb8c8644 |  | textbox | Number of grout tubes in panel
text | 399d2858-213f-5223-92f5-3e5aff18d5db |  | textbox | Duration of pumping the whole panel
checkpoint-status |  |  | checkpoint | Did grout came out of top of dross tube?
checkpoint-status |  |  | checkpoint | No blow outs
checklist-flat |  |  | checklist | Final Sign Off |  |  |  |  | Yes | Final Sign Off | b4ac42ea-5913-401c-8068-7ef79c4b6af7
checkpoint-status |  |  | checkpoint | Doors Installed including drop down seals if applicable
checkpoint-status |  |  | checkpoint | Hardware as per approved schedule
checkpoint-status |  |  | checkpoint | Architraves and skirtings installed
checkpoint-status |  |  | checkpoint | Electrical Power/Lighting second fix installed
checkpoint-status |  |  | checkpoint | Sprinkler/Alarm second fix installed
checkpoint-status |  |  | checkpoint | Security second fix installed
checkpoint-status |  |  | checkpoint | Data second fix installed
checkpoint-status |  |  | checkpoint | HVAC second fix installed
checkpoint-status |  |  | checkpoint | Floor finishes installed as per architectural plan
checkpoint-status |  |  | checkpoint | Paint correct colour
checkpoint-status |  |  | checkpoint | Door signage installed
checkpoint-status |  |  | checkpoint | Manifestations on glazing
checkpoint-status |  |  | checkpoint | Joinery installed correctly
checklist-sectioned |  |  | checklist | Wall Preline |  |  |  |  | Yes | Wall Preline | c562b382-c53a-47b1-93fd-b0eea059984f
checkpoint-group |  |  | section | Interior Framing
checkpoint-status |  |  | checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | All framing setout correctly & surveyed in respective area
boolean | c5461e37-9dd3-5471-9ca6-290d56001b84 |  | tickbox | Spot checks on frames for square
boolean | 77546d39-aa58-5b0d-bd28-c7ff65566f29 |  | tickbox | Spot checks on frame level
boolean | aabbc6a5-b4ba-5559-87e0-08bb26e4882e |  | tickbox | Fixings are correct including seismic requirements
boolean | dffceefc-1ab2-5a28-89ac-70d17825a1e7 |  | tickbox | Service Nogs installed
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | Plumbing Walls First Fix
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Plumbing install First fix complete - checks done based on elevations of current drawings
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Council inspection and testing complete and signed off
checkpoint-group |  |  | section | Fire Protection Walls (Alarms) First Fix
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First Fix checks with Subcontractor (alarms)
checkpoint-status |  |  | checkpoint | All required 1st fix testing complete
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | Mechanical Services Wall First Fix
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First Fix checks with subcontractor
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | Electrical Wall First Fix
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | First Fix checks with Subcontractor
checkpoint-status |  |  | checkpoint | All required first fix testing complete
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | Data Wall First Fix
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | All required first fix completed
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | Security Wall First Fix
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | All required first fix completed
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | AV Wall First Fix
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | All required first fix completed
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | Insulation/Acoustic
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Spot checks on correct product
checkpoint-status |  |  | checkpoint | Spot checks on correct R value
checkpoint-status |  |  | checkpoint | Fitting Snug
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-group |  |  | section | Council Sign Off
checkpoint-status |  |  | checkpoint | Council preline inspection passed
checklist-sectioned |  |  | checklist | Blockwork Checklist |  |  |  |  | Yes | Blockwork Checklist | d0ad75e6-94a7-4aa1-9a1a-2cc41c1c7e41
checkpoint-group |  |  | section | Blockwork Setout/Pre Start QA
checkpoint-status |  |  | checkpoint | Grids available for reference and base of wall marked accurately
checkpoint-status |  |  | checkpoint | RL reference/TOW confirmed
checkpoint-status |  |  | checkpoint | Starter bars correct (location, length and strength)
checkpoint-status |  |  | checkpoint | Concrete/footing clean, tidy and level (ready for first course)
checkpoint-status |  |  | checkpoint | Blockwork reinforcing steel delivered correct and accessible (Attach photos of respective reinforcing docket)
checkpoint-status |  |  | checkpoint | Any additional pre start observations
checkpoint-status |  |  | checkpoint | Correct blocks delivered, checked & accessible
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
text | 9aedf9df-f3d9-565a-8c91-170ce02767bf |  | textbox | Relevant drawings & revisions for reference:
checkpoint-status |  |  | checkpoint | Approval given to start laying blockwork
checkpoint-group |  |  | section | Blockwall Prepour
checkpoint-status |  |  | checkpoint | Base of wall in correct location
checkpoint-status |  |  | checkpoint | Horizontal reinforcing installed correctly (centres/ size / splicing etc)
checkpoint-status |  |  | checkpoint | Ties / Control joints installed as required
checkpoint-status |  |  | checkpoint | Vertical reinforcing installed as required with appropriate splice laps & secure
checkpoint-status |  |  | checkpoint | Openings checked and correct - location, height and width
checkpoint-status |  |  | checkpoint | Washouts correct/openings covered correctly and wall braced adequately (if required)
checkpoint-status |  |  | checkpoint | Any additional observations/ inspections attached
checkpoint-status |  |  | checkpoint | Wall built within tolerance - straight, level and to the correct height (Approval to pour)
checkpoint-group |  |  | section | Blockwall Pour
checkpoint-status |  |  | checkpoint | Any remedial work completed/observations closed out and approval given to pour
checkpoint-status |  |  | checkpoint | Concrete specifications checked and correct - delivery docket(s) photographed
checkpoint-status |  |  | checkpoint | General photos and any additional observations
checkpoint-status |  |  | checkpoint | All blocks filled to correct height
checkpoint-status |  |  | checkpoint | Starter bars in centre of block if applicable
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Any concrete spillage/splatter cleaned up
checkpoint-status |  |  | checkpoint | Blockwork wall(s) complete to required specification
checklist-flat |  |  | checklist | Civil - Storm Checklist |  |  |  |  | Yes | Civil - Storm Checklist | d210e3cd-e249-46d1-9239-5f19665a62a9
checkpoint-status |  |  | checkpoint | Location details and relevant mark ups attached
text | a9663646-22e9-5ab0-9117-3cae71fd1015 |  | textbox | Location
checkpoint-status |  |  | checkpoint | Consultant inspection completed as required
checkpoint-status |  |  | checkpoint | Council Inspection completed as required
checkpoint-status |  |  | checkpoint | Invert levels recorded
checkpoint-status |  |  | checkpoint | Invert levels as per design
text | 8e93c404-a12c-589c-be44-16a75a010538 |  | textbox | Invert Levels
checkpoint-status |  |  | checkpoint | Received QA from Subcontractor?
checkpoint-status |  |  | checkpoint | As Built drawings received
checkpoint-status |  |  | checkpoint | CCTV Survey
checkpoint-status |  |  | checkpoint | Certificates provided
checkpoint-status |  |  | checkpoint | Installation record photos
checkpoint-status |  |  | checkpoint | Storm Installation completed
checklist-flat |  |  | checklist | Screw Piling Checklist |  |  |  |  | Yes | Screw Piling Checklist | d718ba31-adcc-4c6c-86e5-6ef77e629807
checkpoint-status |  |  | checkpoint | As-Built location confirmed (allowable tolerance 75mm)
checkpoint-status |  |  | checkpoint | Verticality checked
checkpoint-status |  |  | checkpoint | Concrete specification checked (concrete docket supplied)
checkpoint-status |  |  | checkpoint | Rebar installed (if required)
checkpoint-status |  |  | checkpoint | Lattey QA Received (As per requirements of Section 1.23 Piling Specification)
checkpoint-status |  |  | checkpoint | Cut off RL checked
checkpoint-status |  |  | checkpoint | Excess pile removed and disposed off
checkpoint-status |  |  | checkpoint | Progress photos
checklist-flat |  |  | checklist | Walls Postline |  |  |  |  | Yes | Walls Postline | f21a05d6-e610-459e-b5c9-903642eeeb38
checkpoint-status |  |  | checkpoint | Correct linings installed as per linings plan
checkpoint-status |  |  | checkpoint | Bracing fixings installed correctly as per requirements
checkpoint-status |  |  | checkpoint | Linings cut out for flush boxes neat and tidy
checkpoint-status |  |  | checkpoint | All screws installed flush
checkpoint-status |  |  | checkpoint | Wall approved for stopping
checkpoint-status |  |  | checkpoint | Stopping light check complete ready for paint
checklist-flat |  |  | checklist | Retaining Wall Checklist |  |  |  |  | Yes | Retaining Wall Checklist | f4a8dded-3356-4ea2-aa22-c8841ed67b2c
checkpoint-status |  |  | checkpoint | Retaining wall(s) setout/heights confirmed
checkpoint-status |  |  | checkpoint | Area prepared - Excavation depths and location of wall checked and correct
checkpoint-status |  |  | checkpoint | General install photos and observations attached
checkpoint-status |  |  | checkpoint | Correct materials used and installed using appropriate methodology
checkpoint-status |  |  | checkpoint | All relevant services / waterproofing elements completed, checked and approved prior to backfill
checkpoint-status |  |  | checkpoint | Backfill completed - correct materials and compaction methodology used - specified compaction achieved
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Additional observations/ inspections attached and all remedial items closed out
checkpoint-status |  |  | checkpoint | Retaining wall completed to required specifications