## Project Detail
Date | 2025-01-06
Project | Exit 49
Job No | QLD 23-007
Client | Seymour Whyte
Client Contact | Mohammed Rashidy
Site Address | Exit 49
Inspected by

## post height
|  |  | Inspection & Test Heights & Steel Numbers Qty's |  | A1 Highways 16/53-57 Link Drive, Yatala QLD PH: 07 3462 2747 ABN : 76 122 395 135
Reference - Location :
Project Name |  |  | Exit 49
Client |  |  | Seymour Whyte
A1 Job No |  |  | QLD 23-007
Job Address |  |  | Exit 49
Del | Height | Marking on the rail |  | Marking on the post | Quantity Installed | Total
1 | 830 | 3042024 |  | 18112023 | W-Beam (m) | 112
2 | 830 | 3042024 |  | 18112023 | Thrie Beam (m)
3 | 830 | 2042024 |  | 18112023 | Long Posts ea
4 | 830 | 2042024 |  | 18112023 | Posts through Rock ea
5 | 830 | 2042024 |  | 18112023 | Bolt-Down Posts ea
6 | 830 | 2042024 |  | 18112023 | Trailing Terminal
7 | 900 | 13122023 |  | 31012024 | Mash TL2 Terminal (<70km/h)
8 |  |  |  |  | Mash TL3 Terminal (>70km/h) | 1
9
10 |  |  |  |  | 8m Thrie Beam Transition Type 1
11 |  |  |  |  | 6m Thrie Beam Transition Type 2 | 1
12 |  |  |  |  | 8m W-Beam Transition Type 3
13 |  |  |  |  | Transition rail (2m)
14 |  |  |  |  | Delineators | 7
15 |  |  |  |  | Motorcycle Protection rail
16 |  |  |  |  | Motorcycle rail bullnoes ends
17 |  |  |  |  | Delineators
18 |  |  |  |  | Foundation Type ( __________)
19 |  |  |  |  | reinstall w beam
20 |  |  |  |  | Removal w beam m
21 |  |  |  |  | Terminal removal ea
Comments :
Inspected by: ( Name ) Signature: Date:

## Ramshield
|  |  |  | Inspection & Test Plan Guardrails |  | A1 Highways 16/53-57 Link Drive, Yatala QLD PH: 07 3462 2747 ABN : 76 122 395 135
Reference - Location :
Material Type List Installation
Type 2 6m Transition |  |  |  |  | Ramshield W-Beam
Motorcycle protection rail |  |  |  |  | Max Tention X350
Project Name |  |  |  | Exit 49
Client |  |  |  | Seymour Whyte
A1 Job No |  |  |  | QLD 23-007
Job Address |  |  |  | Exit 49
Prelims ( Hold Points )
Yes | No | NCR | Have all the Local services been marked up and located ( picture ) DBYD plans / permit to dig been supplied.
Yes | No | NCR | The site conditions for the installation is suitable. Clearance to the obstruction - Batter hinge point proximity-set back sufficient ( picture )
Yes | No | NCR | Is the finished road level surface in place. If no, what is the overlay requirements - enter the uplift difference in mm ( _50_______ ) as instructed by the customer.
Yes | No | NCR | Has the setting out for the alignment and setback been marked up and as per the drawings ( picture ) By customer or A1 ( cycle 1 )
Installation ( Witness Points )
Yes | No | NCR | The posts are spaced at maximum 2.0m centres.
Yes | No | NCR | The posts are correctly orientated with the release tab on the traffic side.
Yes | No | NCR | The rail is secured to each post with a M16 x 32mm (or 50mm) mushroom head bolt & standard nut.
Yes | No | NCR | The rails are spliced with eight (8) M16 x 32mm mushroom head bolt & oversized nuts.
Yes | No | NCR | The rail lap is orientated so that the leading edge of the splice is shielded from approaching traffic.
Yes | No | NCR | All bolts are tightened.
Yes | No | NCR | Any minor damage to the galvanised finish is repaired using two coats of an organic zinc rich paint.
Yes | No | NCR | The barrier is appropriately delineated (Placement between delineators in meters _20____ )
Yes | No | NCR | End terminal installed to specifications
Yes | No | NCR | Motorcycle protection rail installed to specifications
Yes | No | NCR | The area around the barrier is free of debris. ( Picture Required of completed works )
Comments NCR reference No :
Inspected by: ( Name ) Signature: Date: