## Master List Templates
Id | Type | Name | Values | Prompting Name
f44b8f97-2690-4f95-a346-eb44201c1701 | checklist | Inspection Test Plan – Steel Beam Guard Fence |  | Inspection Test Plan – Steel Beam Guard Fence
de345826-e13f-4f40-aced-81b79f68f2c1 | section | 1.0 Preliminary
143a4f73-7b9b-4696-9911-3c48eaac7e86 | checkpoint | 1.1 - Authorised documentation for commencement of Work is in place
4da4a1dc-1bac-5dba-aebe-4546d54bfcf1 | note | SPECIFICATION / REFERENCE DOCUMENT - Construction Work pack
82e046e3-1760-52b0-a62f-020ba32b2bef | note | ACCEPTANCE CRITERIA - Construction Work pack approved
77a06bab-9e18-5532-ac17-ca1579317cd8 | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
53987e3f-45e7-5a50-a3c5-0930a397bfd4 | note | RESPONSIBLE PERSON / METHOD - SE Review Document
076f593f-ee12-5b9f-8909-2c5a725a1759 | textbox | RECORDS - Construction Work pack No
d15e006d-8cd3-4987-83da-322bc5094e87 | checkpoint | 1.2 - Occupational Health & Safety, Environmental Control
6cd43f00-30ad-575f-9d91-da51e9f073de | note | SPECIFICATION / REFERENCE DOCUMENT - Site Induction Record, Environmental Management Plan, Quality Management Plan, SWMS, JSA
2a4144f5-5660-54a1-aa1c-bf3f59a544f8 | note | ACCEPTANCE CRITERIA - All personal working on the lot are site inducted as per the induction requirements in the Construction Health & Safety Management Plan &/or construction procedure. All environmental controls in place & operational & all work methods are approved.
4593de4a-b617-5b50-ab0a-71d2b0f96114 | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
5284608f-4bca-5a6a-8624-00c7d05bdf1f | note | RESPONSIBLE PERSON / METHOD - SE Review Document
9d084aff-6c9c-4bd2-bd04-a9c875e9c715 | checkpoint | 1.3 - Define Work Lot
17af63ed-f184-5428-833b-3e579c3d6d29 | note | SPECIFICATION / REFERENCE DOCUMENT - Construction Quality Management Plan
da2a1f80-3f3d-5e74-871b-38ea9c16390f | note | ACCEPTANCE CRITERIA - Survey boundaries clearly define the Steel Beam Guard Fence Construction works. Work Lot open
37697e90-055d-5557-b884-73bb17511265 | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
61a92e5c-e3a0-5435-8676-835e78977080 | note | RESPONSIBLE PERSON / METHOD - SE Review
85050492-7c5e-5d71-bafb-40bbc5b32b74 | note | RECORDS - Lot Diagram
37d98f5e-4adf-5146-82f5-1bccf98f4fa4 | note | Lot Number
fa701358-1123-440e-a6aa-e897a37a677d | checkpoint | 1.4 - Permit to Excavate
53322c92-4f13-5803-9c6b-332a5fa19bad | note | SPECIFICATION / REFERENCE DOCUMENT - SWMS /R132D Planning 4.1
bf26a1be-abfd-5c17-bec2-49967d60cacb | note | ACCEPTANCE CRITERIA - Excavation Permit issued prior to commencement of any excavation
c0217358-1c66-5b0f-b51a-771049046a1e | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
57ed3199-da41-532c-82f7-60f93883e91f | note | RESPONSIBLE PERSON / METHOD - SE Review
4b44382c-34b6-52ae-bd27-60cf05de1f29 | textbox | RECORDS - Excavation Permit No.:
ced36065-1317-484a-b412-8fb9426e1c54 | checkpoint | 1.5 - Material Compliance – Steel
8e48b418-dc68-5e4d-8899-55a9df8cc16b | note | SPECIFICATION / REFERENCE DOCUMENT - RMS132 2.3 compliance
41feaaca-f4d7-5775-a252-10244dd7cf53 | note | ACCEPTANCE CRITERIA - Submit to the Nominated Authority all test certificates related to the supply of steel for the Works at least 14 days prior to commencement of installation. All testing shall be endorsed in accordance
7e369189-8b65-58c5-9f2d-c1c93ea63f22 | note | TEST REQUIREMENT & FREQUENCY - HOLD POINT WITNESS POINT REVIEW POINT
c404e866-6e70-503f-aaf9-d53c519c175c | note | RESPONSIBLE PERSON / METHOD - NA IR SE
786f0fa7-a9f9-5ad6-b7cf-819e7c5972e7 | textbox | RECORDS - HOLD POINT NO.:
3ed672e2-ffee-5e2f-958f-71ecd61c153a | note | Compliance test certificates including compliance for galvanised
ca4d7f5d-476e-4f5d-8289-6b676a6f8f7e | signoff | AUTHORITY HOLDPOINT
b6f5918d-2386-4507-8112-4a3c333d488d | checkpoint | 1.6 - Material Compliance – W-beam Base Metal Mechanical Properties
e942693b-1b34-5ff8-b4a0-a41e3906d89d | note | SPECIFICATION / REFERENCE DOCUMENT - R132 2.4 Steel
c1ad7488-4317-5921-9082-edab785a2e17 | note | ACCEPTANCE CRITERIA - W-beams to meets requirements of AS/NZS 1594 Grade HA350. Mechanical Properties of Base Metal: • Min. Yield Strength 350MPa • Min. Tensile Strength 430MPa • Min. Elongation in 80mm 16%
8c1a510a-840e-543c-ba89-ab128e4ae70e | note | TEST REQUIREMENT & FREQUENCY - HOLD POINT WITNESS POINT REVIEW POINT Each Lot
808204ba-ea61-560e-9e77-debdc1b370e5 | note | RESPONSIBLE PERSON / METHOD - NA IR SE Review Document Notification
134913a4-dec8-5dd9-a4b4-31e54768a376 | textbox | RECORDS - HOLD POINT NO.:
f5dfdbe3-1434-50e5-a1b4-8ac2c90cc5e9 | note | Compliance test certificates including compliance for galvanised
dcef21e2-1975-422c-9d56-3bfde28a5096 | signoff | AUTHORITY HOLDPOINT
effa3da6-7b67-47a0-86e1-f7b997d5c8fb | checkpoint | 1.7 - Material Compliance – W-beam Base Metal Dimensional Tolerances
1ca9bb3a-d5dc-5c4e-ac66-f9bb47b6bdf0 | note | SPECIFICATION / REFERENCE DOCUMENT - RMS132 2.4 Steel
725afea0-5125-551b-af00-1906a8297d8d | note | ACCEPTANCE CRITERIA - The base metal shall comply with the following tolerances when measured in accordance with the methods of AS/NZS 1365 • Base metal thickness 2.7mm +0.21mm or -0.10mm • Mill tolerance on strip width +2.5mm, -0.0 • Mill camber tolerance on 2500mm length 10mm max
70bb6c1d-6893-5dbf-87cf-69762ecc1f3e | note | TEST REQUIREMENT & FREQUENCY - HOLD POINT WITNESS POINT REVIEW POINT Each Lot
a36886e7-c835-59e0-a9df-af331ebb1260 | note | RESPONSIBLE PERSON / METHOD - NA IR SE Review Document Notification
0569d31c-ec38-5e97-8bde-818735618eec | textbox | RECORDS - HOLD POINT NO.:
53e4ebb3-ff65-5581-86df-c9a0addcd28c | note | Compliance test certificates including compliance for galvanised
47bfb6e1-8634-4ee0-825c-25544ca35dc3 | signoff | AUTHORITY HOLDPOINT
ef889427-0195-48c5-9f7d-5c9ac4269ca2 | checkpoint | 1.8 - Material Compliance – Steel Posts & Blocks
b200a2b7-b837-5c34-8d2a-7638e4a983aa | note | SPECIFICATION / REFERENCE DOCUMENT - RMS123 2.4 steel
b757be2b-db9b-59f4-a7cf-7e06abcb4846 | note | ACCEPTANCE CRITERIA - Manufactured from steel which meets AS/NZS 1594 Grade HA250 • Base material thickness shall be 6.0mm +/-0.27mm
8dd2bc1b-eb4c-5ec8-8836-cd7e49489212 | note | TEST REQUIREMENT & FREQUENCY - HOLD POINT WITNESS POINT REVIEW POINT Each Lot
86d77a1e-03da-5ba8-ab87-c48f6aae7e9f | note | RESPONSIBLE PERSON / METHOD - NA IR SE Review Document Notification
1d25634e-4971-5c23-aa0d-5601b99680eb | textbox | RECORDS - HOLD POINT NO.:
4aeb6140-32cb-5fd2-bd26-52bec9010be6 | note | Compliance test certificates including compliance for galvanised
28dab9a5-8486-4bb6-bd85-301678a855d5 | signoff | AUTHORITY HOLDPOINT
92accab0-c23f-42a1-af70-2381e42be2eb | checkpoint | 1.9 - Material Compliance – Terminal Sections
45e9d078-67b4-53df-8df1-e163f7c89661 | note | SPECIFICATION / REFERENCE DOCUMENT - RMS132 2.4 steel
fdb04405-b1d8-5f90-badd-caf32ce7c1f3 | note | ACCEPTANCE CRITERIA - Manufactured from steel which meets AS/NZS 1594 Grade HA350
cd793cc2-834d-5aa5-ab64-6f1fe203cc03 | note | TEST REQUIREMENT & FREQUENCY - HOLD POINT WITNESS POINT REVIEW POINT Each Lot
f23e5896-53a4-51c7-817f-6448419c14ab | note | RESPONSIBLE PERSON / METHOD - NA IR SE Review Document Notification
148c2cc3-19d5-5b6a-9807-8626d5614015 | textbox | RECORDS - HOLD POINT NO.:
f02a8f08-f3f9-5653-aac0-5453eb5f5b80 | note | Compliance test certificates including compliance for galvanised
b0529224-8894-401a-9197-de557414fcb2 | signoff | AUTHORITY HOLDPOINT
c733faec-b419-40cf-b898-b26d20a44cea | checkpoint | 1.1 - Protective Treatment -
7d6efae8-d21b-53f7-a2b4-ceee1caf4e55 | note | SPECIFICATION / REFERENCE DOCUMENT - RMS 2.4.3 protective coating
89b59886-36f4-5e87-864a-a337fc72a3cf | note | ACCEPTANCE CRITERIA - • AS 1627 - Parts 1 & 4 & finished by hot-dipped galvanising in accordance with AS/NZS 4680.• Hot-dipped galvanised coating on Bolts, Nuts & Washers shall comply with AS 1214 • Repairs to a damaged galvanised coating to be done with Zinc Rich Inorganic Paint with a minimum of 2 coats in accordance with AS 3750.9 & one coat of aluminium paint. • All galvanised coatings shall be smooth, adherent & free from stains, gross surface imperfections, markings, brand names &/or inclusions. Appearance is of prime importance & colour shall be uniform. • Where curved W-beam of less than 45 m curve radius is specified, the curving operation shall be carried out off site in a manner that will not result in damage to the galvanising.
f4d2f22f-9fda-5381-95b2-dbb4dd531be8 | note | TEST REQUIREMENT & FREQUENCY - HOLD POINT WITNESS POINT REVIEW POINT Each Lot
92f30ede-534a-5934-b50b-ba5faec1ce42 | note | RESPONSIBLE PERSON / METHOD - NA IR SE Review Document Notification
6a026a2d-9e34-56d7-8757-b9698c1531b8 | textbox | RECORDS - HOLD POINT NO.:
2306591a-e540-5032-a2c4-94638770f703 | note | Compliance test certificates including compliance for galvanised
bc3a3b40-4b60-5394-8faa-68cbb7b62644 | note | 58519-QUA-LIS-00-00021 Incoming Material Inspection Checklist
74933c6f-6360-459d-b06a-b7ae4780cc69 | signoff | AUTHORITY HOLDPOINT
dc93d46f-1358-404d-834c-0aefd1db3979 | checkpoint | 1.11 - Timber - Compliance
e19b74bd-e91c-5e71-acfe-b65f92224f4e | note | SPECIFICATION / REFERENCE DOCUMENT - RMS 132 2.10 AS1604.1
3661fbd2-d74d-584c-bce2-4839733c03fc | note | ACCEPTANCE CRITERIA - • All timber shall be straight & sound • Timber posts & blocks shall be seasoned timber dried to equilibrium moisture content & sawn from species complying with Class 1 or 2 durability & stress grading • Free from shakes, pipes, cores, flaws & other imperfections • The timber shall be sawn parallel to the grain, & exposed knots shall be sound, tight, well-spaced & shall not exceed 25 mm in size in any face
09f55783-8ff0-5c03-b48e-11543a0aea2b | note | TEST REQUIREMENT & FREQUENCY - HOLD POINT WITNESS POINT REVIEW POINT Each Lot
733b8407-0031-5595-8eb8-4b7267b28a2d | note | RESPONSIBLE PERSON / METHOD - NA IR SE Review Document Notification
dcde8950-ca5a-5592-9a9d-00a0c04d81d4 | textbox | RECORDS - HOLD POINT NO.:
9fceb43f-e773-5b5b-9ccd-fd0ec24f7413 | note | Compliance test certificates including compliance for galvanised
8f2c27c7-0134-522c-b2c6-6d7cb339b4e9 | note | 58519-QUA-LIS-00-00021 Incoming Material Inspection Checklist
366de0ee-be48-4713-a1d4-08c4c6966020 | signoff | AUTHORITY HOLDPOINT
2ed099be-8c16-4e31-86b0-70eacc1754b0 | checkpoint | 1.12 - Material Compliance – Breakaway Cable Terminal
5fd7be2f-d62d-56c3-a6b2-1b07d7351d07 | note | SPECIFICATION / REFERENCE DOCUMENT - RMS132 2.4.5 wire rope
aef5c7cd-e1b9-5e50-9891-68d7b10317d7 | note | ACCEPTANCE CRITERIA - The wire rope shall comply with the requirements of AS3569 & the details shown on IFC Drawings. Wire ropes used in proprietary devices must comply with the manufacturer’s recommendations.
424293fa-f41c-51c8-af3f-fb666ea3466d | note | TEST REQUIREMENT & FREQUENCY - HOLD POINT WITNESS POINT REVIEW POINT Each Lot
f53b9f00-4f37-5ec4-93e4-7b6582b95b3d | note | RESPONSIBLE PERSON / METHOD - NA IR SE Review Document Notification
1cd4303e-5cdf-58b4-b1f0-3455aa97647f | textbox | RECORDS - HOLD POINT NO.:
5f365184-b4c2-5fbb-9071-d876ed21d638 | note | Compliance test certificates including compliance for galvanised
89d10de7-5327-49bb-ac04-8476c8e6cf54 | signoff | AUTHORITY HOLDPOINT
6bd9e545-903a-40d2-bc79-dcd5334825b0 | checkpoint | 1.13 - Handling & Storage
c8e27d0e-dfb3-53c2-b244-183d5d491a1b | note | SPECIFICATION / REFERENCE DOCUMENT - QMP 13.1.3
a2f80b7e-a612-5e96-a4e3-db8476a5fc39 | note | ACCEPTANCE CRITERIA - • Items are loaded, transported, unloaded, stacked & handled in such a way to protect items from distortion & that galvanised surfaces are protected from damage.• All materials stored to prevent damage & corrosion at least 200 mm above the ground on platforms, slabs or other supports. • Rusted, bent or damaged steel shall be rejected. • If stacks located behind a serviceable road safety barrier system, the clear space must allow for dynamic deflection & proper functioning of the end treatments.
a17a7dbb-ae3d-5190-83c0-02e1222d86e0 | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
820a6eff-76eb-54b2-909b-e7830a35242a | note | RESPONSIBLE PERSON / METHOD - SE Inspection
f9e33374-fee6-4111-9086-43694ada629e | checkpoint | 1.14 - Pre-Construction Planning
1bb45062-c43b-5e89-a25c-1e45a34c78c7 | note | SPECIFICATION / REFERENCE DOCUMENT - R132/D planning QMP 13.2
b4c37518-4cdb-5835-8994-ea2fbb4e990c | note | ACCEPTANCE CRITERIA - • Plan & execute the work in a manner that prevents damage to underground & above ground facilities. Construct a guard fence to form a smooth line vertically & horizontally, when viewed along the line of the installation, free of humps, sags, or other irregularities, within tolerances (Activity 4.1). • Any component of a guard fence must not be welded, or flame cut in the field under any circumstances. Welding & flame cutting may only be conducted when shown on drawings in accordance with the manufacturer’s recommendations. • End treatments & transitions commissioned at the earliest practicable time where the guard fence is being constructed on a road open to traffic. Temporary end treatments to the satisfaction of the Nominated Authority until the permanent treatments are complete. • Removal of an existing installed safety barrier system includes: o Dismantling or demolition of safety barriers, transitions & end treatments o Extracting all posts, anchors & other in-ground components & materials o Removing all components & waste materials from the site o Cleaning, backfilling & mechanically compacting all excavations & holes in 150mm layers to not less than the density of the surrounding layers o Stacking or disposing of components & waste materials
04f46398-b573-5ceb-a212-29a1d40c8bef | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
82882c6d-fe64-5b55-affb-0e399bfd9374 | note | RESPONSIBLE PERSON / METHOD - SE Inspection
5698cf05-8672-4e60-bc63-9a2f71081b73 | checkpoint | 1.15 - Delineators
33ca9791-afc6-5dd4-8da4-0871204c0f34 | note | SPECIFICATION / REFERENCE DOCUMENT - R132/A 1.21 4.1 R0710-18
8ba1a296-1e6f-5154-a59c-bb44c26e073c | note | ACCEPTANCE CRITERIA - • Delineators to be as per RMS Roads Supplement to AS 1742.2 Clause 4.2.5.4(b). • Flexible plastic mounting brackets fitted with 100 cm2 of Class 1A retro- reflective material, as defined in AS/NZS 1906.2.
99fb502a-b70c-5c20-82d5-aab70fec687a | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
75da4f28-1285-5908-b14d-611b67a0cc2d | note | RESPONSIBLE PERSON / METHOD - SE Review Document
cfcfaabd-a668-56a8-a8d0-f87f08bf0d6d | note | RECORDS - Compliance test certificates
d5f5feaf-b356-4b7e-9518-75d905b4a828 | checkpoint | 1.16 - Material Inspection
4947450a-5029-5496-abab-d5c673922eb0 | note | SPECIFICATION / REFERENCE DOCUMENT - QMP 13.6
efabfb10-b2fc-52d3-a21c-49f61ce09ed7 | note | ACCEPTANCE CRITERIA - Ensure that materials are in compliance with RMS Roads specifications & IFC Drawings
35fe0bd2-916b-5d88-bd52-b176a08d8216 | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
6f36db33-a5ae-5cd3-8634-1bac2b6c5153 | note | RESPONSIBLE PERSON / METHOD - SE Review Document Inspection
b6c4fa38-63ae-523b-954c-f1841f67ba51 | note | RECORDS - 58519-QUA-LIS-00-00021 Incoming Materials Inspect
4da0a1f8-8e17-404b-a3e3-a96ea48a3f11 | section | 2.0 Guard Fence Post Installation
1d665bfa-44b4-4c42-9343-b2fddf962daa | checkpoint | 2.1. - Set Out
bba6f16d-0035-5a25-ae98-0771fba33b15 | note | SPECIFICATION / REFERENCE DOCUMENT - RMS132 4.1.2
a2de02f0-fb23-57c9-9966-8a9ca2e19161 | note | ACCEPTANCE CRITERIA - Prior to installation, the required location & length of all guard fence to be confirmed with the Nominated Authority.
f5c7726b-924f-54fe-88c3-7fb08814e31c | note | TEST REQUIREMENT & FREQUENCY - HOLD POINT WITNESS POINT REVIEW POINT Each Lot
6b447ffe-e017-5fcf-b912-8d1aa78f5f6f | note | RESPONSIBLE PERSON / METHOD - NA IR SE Inspection Notification
f57ff76c-1e0c-5b54-bc0c-6d85ae99c1cd | textbox | RECORDS - HOLD POINT NO.:
c678a8c9-377f-4765-a3b3-a5632ea458e4 | signoff | AUTHORITY HOLDPOINT
c7491e0d-324c-4c12-96ef-6ea444c14889 | checkpoint | 2.2. - Posts – Installation
667d8275-9a89-5935-86b2-64532a061a20 | note | SPECIFICATION / REFERENCE DOCUMENT - R132 4.2.1
51833f1f-de0c-5d5c-9ba6-edfa5223b7cd | note | ACCEPTANCE CRITERIA - • Installed to a depth not less than shown on IFC drawings • Posts orientated to the direction of traffic as shown on drawings • Posts shall not be damaged during driving • Posts in rock - 75mm clearance from back of post to face of the hole • Posts shall be installed such that the back of post is not less than 500 mm from hinge point.
b8c6605c-cb0a-570a-b4fa-2c76eae5e8f6 | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
39b0ee69-ce14-5c06-9de9-6e1b74c297e5 | note | RESPONSIBLE PERSON / METHOD - SE SUR Inspection
42a72cf4-07c9-54c6-8c6a-9bfe1b9aa9eb | note | RECORDS - Survey Set-Out
220ce703-dd5c-5fb4-a378-e75451545c4a | note | SUR Signature
27e8e4df-2b19-4a1a-b4e5-7fe71dbc36b7 | checkpoint | 2.3. - Posts – Backfilling
d04bd27b-243e-50cc-9abb-498adcc03723 | note | SPECIFICATION / REFERENCE DOCUMENT - R132 3.3
5a792e70-f461-53ff-a27f-26a917650869 | note | ACCEPTANCE CRITERIA - • Posts in rock – Except for anchorage posts, post holes backfilled with a granular material • Other post holes backfilled with selected earth, free of rock • Backfill shall be firmly compacted not exceeding 100mm compacted layers • Posts in paved areas shall be backfilled 50mm below underside of such paving & remaining depth filled with paving material
dabe978c-6eb1-51d6-8471-750775d74757 | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
1d7f74ac-d684-54d1-b921-8f6c84cbe4bc | note | RESPONSIBLE PERSON / METHOD - SE Inspection
7d6e0429-2b97-4f81-bb15-c0c105d65435 | checkpoint | 2.4. - Post – Foundation
751eb123-5d72-59db-8bce-237ba54fbfb4 | note | SPECIFICATION / REFERENCE DOCUMENT - R132 3.3
541ef5df-366f-5d65-9886-def7bc2eb455 | note | ACCEPTANCE CRITERIA - • Foundation displacement at ground level not to exceed 3 mm when a 1 kN force is applied 200 mm below the top of the post in any direction • Any failing post shall be rectified & retested plus one similar post within 5m.
ba9046ba-37ac-5b7a-a58b-4c41809032f6 | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
266c5551-510f-580f-851b-d699edcd4677 | note | RESPONSIBLE PERSON / METHOD - SE Inspection
b6604d90-7fb8-50cb-ad67-482843b084dc | note | RECORDS - Foundation Test results
5c7271d7-b4c4-44da-aa79-8453f1f372b8 | checkpoint | 2.5. - Non-Standard Post Lengths
c9c41340-6c24-55d1-b4c3-4762a1e5e72e | note | SPECIFICATION / REFERENCE DOCUMENT - RMS132/ C2 4.1
4b49e1c0-7cfe-545b-b8ad-bf132c7e2312 | note | ACCEPTANCE CRITERIA - • Where non-standard post lengths or other special measures are required (e.g. Shallow Concrete Foundations), details to be provided to the Nominated Authority. • Where shallow foundations that require a concrete ground beam are proposed to be constructed, the design shall be proof engineered by a RMS Roads pre- qualified consultant.
9a6dc7b3-0861-57e9-bb2c-e3746b36e3c1 | note | TEST REQUIREMENT & FREQUENCY - HOLD POINT WITNESS POINT REVIEW POINT Each Lot
836c5874-89ea-5028-8fab-a87eec683f6f | note | RESPONSIBLE PERSON / METHOD - NA IR SE Inspection Notification
f94f6ff5-dad8-5f38-8eb2-ef8d6c96d4da | textbox | RECORDS - HOLD POINT NO.:
950dddbc-e094-4819-927f-509b1f1ea2e2 | signoff | AUTHORITY HOLDPOINT
f3c6f63f-3c98-48e0-b57a-9931f0b5ef5b | section | 3.0 Guard Fence Installation
e5de8fff-375f-4329-9627-ab93003fbcd2 | checkpoint | 3.1 - Guard Fence/Rail - Installation
17c2d361-fefc-5690-8e4b-29fd15017797 | note | SPECIFICATION / REFERENCE DOCUMENT - RMS132 4.0
df5f4f51-7d39-5a6e-a3b6-b6c0bbe28330 | note | ACCEPTANCE CRITERIA - • Guard fence shall be installed at the offsets shown on Standard Drawing SD 3502 • Guard Fence/Rail sections lapped so that the exposed ends face away from near sided approaching traffic • Edges of guardrail fixed in contact with post or post blocks • All bolts fully tightened • Posts attached to bridges or culverts shall be bolted to supporting members as shown on drawings • Where radius of curvature is 45m or less, guardrail sections shall be curved to shape prior to delivery to site. • End treatments constructed in accordance with the drawings
7eae1730-3d2d-5443-ac9e-e1e320776374 | note | TEST REQUIREMENT & FREQUENCY - HOLD POINT WITNESS POINT REVIEW POINT Each Lot
a06644e2-f849-55ca-b5b0-20b91466ad4e | note | RESPONSIBLE PERSON / METHOD - NA IR SE Inspection Notification
54e3ce85-fd91-5d08-ab52-0213fe610beb | textbox | RECORDS - HOLD POINT NO.:
d08f72de-678c-5671-9671-a9a59eb0bfff | note | Bolt Tensioning Records
6f63ed92-4263-49d7-b317-05a58829afe1 | signoff | AUTHORITY HOLDPOINT
13afa17a-72ca-48e4-81de-f2333b3ec138 | checkpoint | 3.2 - End Treatments
98130ae2-dfcc-50f6-8110-d48984bb625a | note | SPECIFICATION / REFERENCE DOCUMENT - RMS132 4.0
0cfd2ef7-0814-53d7-bf40-3d7084299bd6 | note | ACCEPTANCE CRITERIA - • During installation of wire ropes in the end treatments of W-beam, ensure that no twisting of the rope occurs. • The anchorage cable shall be tightened sufficiently to remove slack. • When rope assemblies are used, the nuts at each end of the rope shall be tightened to a minimum torque of 50 Nm on the assemblies or as per the manufacturer’s
e0a373bc-4c60-528d-9b55-c119df5bd70c | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
5114de39-40d8-56a3-ba40-2c24b8908131 | note | RESPONSIBLE PERSON / METHOD - SE Inspection
23db45c8-8d13-4790-8cf3-3afea2ae36e0 | checkpoint | 3.3 - Height of guard fence/Rail
d68a7396-72f0-52ea-b3a5-3485d298315b | note | SPECIFICATION / REFERENCE DOCUMENT - RMS132.4.5
c6833e7b-2756-57e2-862d-17a51e5aff73 | note | ACCEPTANCE CRITERIA - • Top of Rail shall be within 25mm of the specified level • Rail shall be within 50mm of the specified line • Variations in line & level shall not occur at a rate exceeding 15mm in any 5m length Notwithstanding the above, the line & level shall be adjusted to provide a smooth & even vertical & horizontal alignment.
f637f186-9743-5df5-8b21-cfb1bb88d20b | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
49e54b01-bf0e-5bde-ab22-2c1632ee8403 | note | RESPONSIBLE PERSON / METHOD - SE Inspection
b4f633a6-b954-5493-8dd6-408f889f4e66 | note | RECORDS - As-built survey & tabulations verifying compliance
d855c1fd-6903-4dc5-873f-1f8356cdd9f6 | checkpoint | 3.4 - Motorcyclist Safety
b57b4da8-f79d-5f8a-8a2c-eb2fe2e23b7d | note | SPECIFICATION / REFERENCE DOCUMENT - Where specified, steel rub rail or other proprietary under-run systems, as listed in RDN 06-04 to be at attached to Guard Fence on nominated sections of barrier as shown on the drawings only.
f32201a5-b072-5b88-9561-ea1c20147cf1 | note | ACCEPTANCE CRITERIA - REVIEW POINT Each Lot
954523a8-1b11-56cf-947c-654d9fdcbdff | note | TEST REQUIREMENT & FREQUENCY - SE Inspection
e93f7506-0a80-4a49-9592-bf56d3b981c3 | checkpoint | 3.5 - Installation of Delineators
54932634-ac08-5492-9483-c03db7e30c3c | note | SPECIFICATION / REFERENCE DOCUMENT - R132/A 1.21 4.1 R0710-18
4af41f8b-74fa-5330-8834-077a9f76d80a | note | ACCEPTANCE CRITERIA - • Red delineators on the left side of one- way & two-way roadways; • White delineators on the right side of two-way roadways; and • Yellow delineators on the right side of one-way roadways • Delineators not required where Guard Fence offset is greater than 4 m from the traffic lane. • White guide posts with delineators shall be installed in accordance with RMS Roads Supplement to AS 1742.2 Clause 4.2.4 – Guide Posts.
cd4ce3b0-0654-5099-b618-6f495161b811 | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
2f52a4cf-a4d4-508c-aa05-bd45f130f9cc | note | RESPONSIBLE PERSON / METHOD - SE Inspection
ee20498d-51f0-4f77-8bff-24dcdd9fd885 | checkpoint | 3.6 - Concrete maintenance strips
ff57a2f4-e946-5704-8c02-4172668d4995 | note | SPECIFICATION / REFERENCE DOCUMENT - Tfnsw3204
92ddad6b-7483-570f-9874-b2175e097bbd | note | ACCEPTANCE CRITERIA - Concrete maintenance strips beneath all steel beam guard fence railing shall meet the following requirements: • 300 mm clear of the rear of the post & 300 mm clear from the face of w-beam • Bedding to be 75mm thick of class 3 crushed rock • Concrete shall be 75mm thick & 20MPa Strength • Edges of infill boarded up prior to pour • Edge board shall be parallel with steel beam guard rail fencing• Surface finished with a wooden float to produce a lightly textured finish • Shall be constructed with a minimum 2% cross fall away from the road & shall be flush with the adjacent ground level so the finished level does not impede road runoff • Where maintenance strip is adjacent to kerb or pavement, cork expansion joint or approved alternative shall be placed in between kerb / pavement & infill area
aef629ae-ec6c-50a5-8cda-cfea7b4b5009 | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
b6d31523-7a3f-5e4a-b26e-4f859045d528 | note | RESPONSIBLE PERSON / METHOD - SE Inspection
48095f4f-4d64-588d-939e-5dc96d1c1ab8 | note | RECORDS - Material compliance records – concrete strength
1b6c7b90-518d-41dd-abd1-fdb30c8dbc62 | checkpoint | 3.7 - Concrete Infill adjacent to kerb or pavement
e02321c6-e4a9-511e-ac67-1834efed5537 | note | SPECIFICATION / REFERENCE DOCUMENT - Tfnsw3204
601bb679-d74c-5082-aa49-cf12b004999b | note | ACCEPTANCE CRITERIA - • Edges of infill area to be boarded up prior to placing concrete to ensure smooth edges are produced. • Concrete infill can use low strength concrete (<0.85 MPa).
a5a57b6e-3b67-56a4-b918-095743380462 | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
0e4eb081-38d8-5685-b9b9-2fe1b3cd4496 | note | RESPONSIBLE PERSON / METHOD - SE Inspection
6f35f7ed-3de9-4ebe-a05c-9b07518cafed | checkpoint | 3.8 - Expansion Joints perpendicular to the line of Guard Fence
7e6ffa4a-076b-5b4a-a1e5-ca4228cb11c5 | note | SPECIFICATION / REFERENCE DOCUMENT - TfNSW3204
e1dcfdbe-e5d4-52f4-af9d-b8ebecf1c8bb | note | ACCEPTANCE CRITERIA - An expansion joint shall be provided perpendicular to the line of the steel beam guard rail fence 200mm each side of every post using cork expansion joint or an approved alternative.
e33849f8-3826-52e7-8223-cfba6b50d5fa | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
d949992d-320b-5c6e-b6f5-6cdb27e78257 | note | RESPONSIBLE PERSON / METHOD - SE Inspection
7d20b947-8cd4-414f-815f-ad27f36c1318 | section | 4.0 Completion
e37d69dd-2b5c-479b-a306-50cfcc7cc7e9 | checkpoint | 4.1 - Guard Fence Tolerances
a0df616a-504a-5e69-a895-579549d3b606 | note | SPECIFICATION / REFERENCE DOCUMENT - RMS132 4.5
6c1dca95-3674-5242-aa52-4606f05ee4c2 | note | ACCEPTANCE CRITERIA - The guard fence shall be installed at the positions so confirmed & shall be constructed true to line & level & to the following tolerances: i. Variation from true plan position of posts ±20 mm ii. Variation of line of w-beams from specified vertical profile ±10 mm iii. Variation of w-beams from specified horizontal alignment ±20 mm iv. Variation of posts from vertical (measured at top of the post) ±15 mm v. Orientation of block &/or post to w- beam+0 mm, -15 mm measured at the point of greatest offset between the block or post to the w-beam) vi. Dimension of holes -0 mm, +50 mm vii. Top of bolt head relative to w-beam -0 mm, +5 mm
88086c3a-4960-5aa9-a872-ba059d241914 | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
7c22434b-8651-5ec1-a7f5-e378eda99aa1 | note | RESPONSIBLE PERSON / METHOD - SUR Inspection Review Document
7bdc82fd-75ca-514a-b950-441e94f9749a | note | RECORDS - Survey Conformance Report
fbd37230-67ef-580f-9327-9922c673387b | note | SUR Signature
52bc8899-9d6e-41db-9649-441b62031703 | checkpoint | 4.2 - Safety Barrier Compliance Audit
286125f8-42d0-5c27-8c32-ffc3f8657375 | note | SPECIFICATION / REFERENCE DOCUMENT - QMP14.
e8e79fa8-0010-52b0-8fd1-f0d6f5ccb727 | note | ACCEPTANCE CRITERIA - After Completion, arrange for a safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract. The audit shall be undertaken, & a report prepared by the Australian Licensed Supplier of the safety barrier system. In addition, complete & submit to the Nominated Authority compliance certificates for review.
b50a1c68-6347-5fdd-b970-d2c8e0645cfe | note | TEST REQUIREMENT & FREQUENCY - HOLD POINT WITNESS POINT REVIEW POINT Each Lot
b86de8bd-c249-5955-967e-9461f80a335c | note | RESPONSIBLE PERSON / METHOD - NA IR SE Inspection Review Document Notification
961a4bb1-c900-57d5-9875-8eb61c580d6e | textbox | RECORDS - HOLD POINT NO.:
30f63dda-464c-5c85-9ae5-07255c8e4c22 | note | Compliance Audit & Certificate of Compliance
107b7e15-6632-49d0-a575-cb4a2e3e1d01 | signoff | AUTHORITY HOLDPOINT
d3d1c10d-efb1-4195-acac-4d7e08e5bd47 | checkpoint | 4.3 - Reinstated Works
5e10b454-5dc8-5ec9-a528-e55d430a424c | note | SPECIFICATION / REFERENCE DOCUMENT - RMS specification
9f390f2f-7a5a-5816-b5f6-048c422a09fd | note | ACCEPTANCE CRITERIA - All existing signs & markings, median crossings & existing vegetation removed due to Guard Fence installation shall be reinstated.
7658526a-e217-5043-b350-a76e4f0f1c9f | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
2b00aa30-c03d-568b-823b-8c1e93e72510 | note | RESPONSIBLE PERSON / METHOD - SE Inspection
29521ca8-1bd3-4c74-a5bd-9758c707b68a | section | 5.0 Work Lot Close out
c33aa6c5-ac3d-4a45-9758-2dab73d11300 | checkpoint | 5.1 - Test Reports
a606b4db-7e26-5925-bf88-5034accd56c3 | note | SPECIFICATION / REFERENCE DOCUMENT - RMS132 / C2 2.3
c95e6d3b-33a7-5f7e-aaf0-499ef332712f | note | ACCEPTANCE CRITERIA - All Test reports received & Reviewed
7e477ca4-698a-5e40-8a62-d4134395b908 | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
27bc54db-812d-53d8-becf-6a67a841fef2 | note | RESPONSIBLE PERSON / METHOD - PE Review Document
23c206f3-c2be-54c8-ba2e-f3ac4e5069ad | note | RECORDS - NATA Endorsed Test Reports
a7d11a34-8f10-4c45-b8e0-8404c13186be | checkpoint | 5.2 - Product Non- Conformance
9d9cb58a-6bd2-50c1-93f4-d6c76bc614b8 | note | SPECIFICATION / REFERENCE DOCUMENT - QMP
02a33f18-92f5-548e-a86a-beb121b49ceb | note | ACCEPTANCE CRITERIA - All Product Non-Conformance(s) recorded & closed (if applicable)
07a85581-8252-5938-96e7-68c7ca7b7b5e | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
13cc1af5-f582-5c4d-9c31-fa7490b472b2 | note | RESPONSIBLE PERSON / METHOD - PE Review Document
716e4086-0b29-5870-8365-f09065363988 | textbox | RECORDS - NCR No:
66198d8b-b0d8-5e46-bf16-c96a81f51834 | note | NCR reports
25736c9f-cb38-48af-b3c6-2f41db2df8a5 | checkpoint | 5.3 - Quality Representative to check the above criteria and records to confirm
eee2aa77-bd93-5294-9a7a-42212f1ca5cb | note | SPECIFICATION / REFERENCE DOCUMENT - QMP Lot Records
8f9d78d0-2b92-53a5-8ebd-0b2faaf06cd4 | note | ACCEPTANCE CRITERIA - All above criteria met & records identified attached.
a9c1037e-0008-50b5-8a69-41b86e7e0a25 | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
e1f2c749-34a8-55c3-af46-28b57133a191 | note | RESPONSIBLE PERSON / METHOD - QR Review Document
559c7302-c1e5-5b6e-bf5e-e792fa72115f | note | RECORDS - Completed Checklist (if applicable) & reports & other compliance records attached.
6ce4fd2d-a333-4187-86a1-6702299dff3e | section | ITP COMPLETION
d11da74d-68e3-4d21-8421-a1618553b8e8 | checkpoint | ITP COMPLETION - Project Representative:
ef9ab20f-90e5-45dc-b763-958227699e09 | signoff | Add / Request Signature
f7242ce5-a7ad-45f1-b055-a6bc36c1fc5d | checkpoint | ITP COMPLETION - Quality Representative:
3871d5f1-e1c4-4ff8-a67c-c5ba518ad613 | signoff | Add / Request Signature
0b0ddd01-822b-4752-97a9-8802c6df4e7c | checklist | Inspection Test Plan – Wire Rope Safety Barrier |  | Inspection Test Plan – Wire Rope Safety Barrier
d3840127-a344-4583-b6f0-30f6c0c661c2 | section | 1.0 Preliminary
6c559b72-f1fa-4f3a-acf8-dc571febe89e | checkpoint | 1.1 - Authorised documentation for commencement of Work is in place
c352475f-0e7f-539a-916f-c770d849e13f | note | SPECIFICATION / REFERENCE DOCUMENT - Construction Work pack
8a0da98f-b3b7-598b-aba2-fa07059de0f5 | note | ACCEPTANCE CRITERIA - Construction Work pack approved
7ff77f18-2c85-54ea-ae12-a1030b31a182 | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
9a064dc4-a4ba-5541-ab8a-e6a1a539392b | note | RESPONSIBLE PERSON / METHOD - SE Document Review
f2cec25a-4aa0-50c0-8f9e-d742fefc44bd | textbox | RECORDS - Construction Work pack No.:
1029e972-0dce-49e9-b56d-95da179a91ff | checkpoint | 1.2 - Occupational Health & Safety, Environmental Control
89fcc290-7125-511a-9321-2899c4efb627 | note | SPECIFICATION / REFERENCE DOCUMENT - Site Induction Record, Environmental Management Plan, Quality Management Plan, SWMS, JSA
d4a7a5e8-5089-5afc-9789-d49bd9aa8c61 | note | ACCEPTANCE CRITERIA - All personal working on the lot are site inducted as per the induction requirements in the Construction Health & Safety Management Plan &/or construction procedure. All environmental controls in place & operational & all work methods are approved.
44e2f427-eb46-52fa-85e4-98d577a4ee68 | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
38501a2f-8f5d-52fa-9d89-8bc698609434 | note | RESPONSIBLE PERSON / METHOD - SE Document Review
6571e779-3cbf-4fce-a583-2ab9693abd2e | checkpoint | 1.3 - Define Work Lot
376223cc-d222-5d07-9d17-0183ed11dd4b | note | SPECIFICATION / REFERENCE DOCUMENT - Construction Quality Management Plan
295376d3-f030-54b8-9d22-16d86ba8c5e8 | note | ACCEPTANCE CRITERIA - Survey boundaries clearly define the Wire Rope Safety Barrier Construction works. Work Lot open in QAntrol
820ccf96-c065-5124-8d13-6504867f8c3f | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
775a8f2d-8c14-5b3c-b8b8-d0eca07e1494 | note | RESPONSIBLE PERSON / METHOD - SE Review
3335669a-4c0f-503d-a864-a8b3265dc74f | note | RECORDS - Lot Diagram
478b6120-c31b-5635-9961-381c5b7aeb38 | note | Lot Number
8e8c0b11-a864-4fd7-994e-5bbd2cf9a1b9 | checkpoint | 1.4 - WRU Excavation & Penetration Permit
4458b5c1-0df7-5a30-b622-fa9d2cd9aee4 | note | SPECIFICATION / REFERENCE DOCUMENT - SWMS /R132D Planning 4.1
c8666b0d-5aa1-5af4-a2ed-2e6c86898071 | note | ACCEPTANCE CRITERIA - Excavation & Penetration Permit issued prior to commencement of any excavation
d2947212-2af1-5bdc-b828-41879ae46659 | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
3da1c451-8c8b-5f6f-be8e-9976b0297d2a | note | RESPONSIBLE PERSON / METHOD - SE Review
ce963a66-bdf0-503d-b7b4-ecd3db4db620 | textbox | RECORDS - WRU Excavation & Penetration Permit No:
6e1814fd-5cab-4f53-8692-9cee05b406bd | checkpoint | 1.5 - Material Compliance
de9bedc2-ba8b-547a-b9ff-1183a096ed67 | note | SPECIFICATION / REFERENCE DOCUMENT - RMS132 4.4
eab1f23d-4d45-5c62-a7f4-a71de18ab7ca | note | ACCEPTANCE CRITERIA - The installation of the WRSB shall not proceed until the signed statement & certificates of compliance have been accepted by the Nominated Authority. WRSB details, certificates & test reports to be Submitted to the Nominated Authority at least 14 days prior to installation • WRSB manufactured in accordance with Specification for a minimum 20- year design life, • Posts hot dipped galvanized in accordance with AS/NZS 4680 or AS 1397 • Green Posts Powder coated as per (Dulux Anotec Heritage Green or approved equivalent) • White Post to provide a grainy, low gloss appearance • Hot-dipped galvanised coating on bolts, nuts & washers as per AS 1214
8c179f29-a580-5032-a3d6-387461201a2f | note | TEST REQUIREMENT & FREQUENCY - HOLD POINT WITNESS POINT REVIEW POINT Each Lot
05538eb1-0ab3-5b88-8b35-ea31f1829a81 | note | RESPONSIBLE PERSON / METHOD - NA IR SE Review Notification
8b17bf06-4bf8-5d36-9e9f-fa2cd6c08ac9 | textbox | RECORDS - HOLD POINT NO.:
954c9f2d-dcaa-50ac-b52b-1bd510be093e | note | Certificates of Compliance including: Test Reports
e5ca8331-66c3-589f-870d-ade0180a3c6f | note | 58519-QUA-LIS-00-00021 Incoming Materials Inspection Checklist
df93c99a-9f51-4db8-b341-b7ebbda652ea | signoff | AUTHORITY HOLDPOINT
f900c238-5dc9-411e-8f39-9da151eed240 | checkpoint | 1.6 - Material Handling & Storage
ed4d9ba7-33e6-575a-b5a0-f767161c9520 | note | SPECIFICATION / REFERENCE DOCUMENT - QMP 13.1.3
f3f373e0-4d3b-5db9-ae69-ce674eb81784 | note | ACCEPTANCE CRITERIA - WRSB to be handled & stored to avoid damage, particularly to threaded components. Care in avoiding damage to galvanised & powder coating systems.
9a97fa67-dc77-55e1-b1ad-fbefb0ecd940 | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
a4c8cef5-1ac1-5f41-a488-72b327c36438 | note | RESPONSIBLE PERSON / METHOD - SE Inspection
4d8a9ac1-6f24-4db1-bd11-33678c452c39 | checkpoint | 1.7 - Post Foundations & Anchor Blocks
8e4734cd-02d1-5c40-9408-0e413089c07d | note | SPECIFICATION / REFERENCE DOCUMENT - Manufactures specification
e526f84e-5e1d-50c9-8978-3e2c9a39b98e | note | ACCEPTANCE CRITERIA - Where no geotechnical investigation is undertaken the proprietary WRSB supplier’s nominated default anchor & post footing shall be used in accordance with manufacturers specifications
be1f172e-bbcd-51f2-9355-b871a06512a9 | note | TEST REQUIREMENT & FREQUENCY - HOLD POINT WITNESS POINT REVIEW POINT Each Lot
594ec844-7638-59f3-bbfb-73db115917a6 | note | RESPONSIBLE PERSON / METHOD - NA IR SE Review Notification
9d96a65d-4767-5207-9198-3adc2b05cacb | textbox | RECORDS - HOLD POINT NO.:
296c25b0-317d-589f-bfac-081e0b6cfdaa | note | Compliance test certificates
601f71cf-1471-4fce-b406-735ac6464c16 | signoff | AUTHORITY HOLDPOINT
f687ebf9-b530-4f9e-8592-a84b7f881863 | checkpoint | 1.8 - Alternative Anchor or Post foundation
a173b779-299a-5eed-8f1d-611f233c86c4 | note | SPECIFICATION / REFERENCE DOCUMENT - Manufactures specification
4d40924e-2517-5b10-89a7-fa2b59c7dedc | note | ACCEPTANCE CRITERIA - • Confirm with the supplier the geotechnical information required, but shall include as a minimum soil bearing pressure, soil type & average allowable soil stress. Submit the results of the geotechnical investigation to the supplier • A written statement from the supplier that the anchor block size & post foundation size are appropriate for the existing natural or constructed ground conditions. • Anchor blocks & post foundations shall not be constructed until the design & manufacturer’s acceptance has been reviewed by the Nominated Authority.
1edb9ac3-0984-5789-ba45-5c6a11276768 | note | TEST REQUIREMENT & FREQUENCY - HOLD POINT WITNESS POINT REVIEW POINT Each Lot
21540534-296d-5062-9766-c411b1b52303 | note | RESPONSIBLE PERSON / METHOD - NA IR SE Review Notification Document
2aa123dd-9658-512d-95d6-74e9e849fd3b | textbox | RECORDS - HOLD POINT NO.:
c27b9e9c-13ae-5a94-b56d-6b529152088f | note | Geotechnical Information
c4a22870-8a5e-5f67-822b-bb44ce316704 | note | Written Statement from the Supplier for Anchor Blocks & Post Foundation suitability
f0c7324e-34d7-46dc-b64b-c17ff1741482 | signoff | AUTHORITY HOLDPOINT
726c0a3f-c28b-48fc-8dc1-8c1c510e9498 | checkpoint | 1.9 - Delineators
b6df7cf3-b328-5624-a91e-eafbb2dd19c9 | note | SPECIFICATION / REFERENCE DOCUMENT - R132/A 1.21 4.1 R0710-18
ef6afc0e-528d-5518-a3b3-deefdb0b6f4a | note | ACCEPTANCE CRITERIA - The delineators that are to be attached to the WRSB posts (either using 50mm x 100mm post caps or fastening directly to the front top of the posts above the wire ropes shall consist of Class 1A retro- reflective material as defined in AS/NZS 1906.2.
9604a9b0-082b-58a6-8fa2-153069aba71a | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
8c9ecea3-f2dc-5269-9b6d-fa4f61584779 | note | RESPONSIBLE PERSON / METHOD - SE Document Review
5f028919-ad76-5865-92e3-e1b9685ba40c | note | RECORDS - Compliance Certificates
d8329791-4426-43bb-98e0-18b382f540a0 | section | 2.0 Anchor Blocks & Post Installation
625d66f9-bcf3-4dcb-9398-202ac5a64c46 | checkpoint | 2.1. - Safety Barrier Inspection
093aa9a4-01c4-52c2-b084-d52216c817c0 | note | SPECIFICATION / REFERENCE DOCUMENT - QMP 13.6
49c5ddc4-f85f-5ee8-9653-c9c54a060bbc | note | ACCEPTANCE CRITERIA - Inspect material to ensure specification compliance
518abd14-c987-5f39-9140-478fb8e054b1 | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
f1138aaf-25a7-55e1-8b84-9cc25b07077e | note | RESPONSIBLE PERSON / METHOD - SE Inspection
2508bbc8-4d87-5d48-91ae-c9160b58fa89 | note | RECORDS - 58519-QUA-LIS-00-00021 Incoming Materials Inspection Checklist
481bb799-c86c-42dd-be2e-75183188af7b | checkpoint | 2.2. - Set Out
c82deea0-b37d-5ea3-b2eb-edbd36bdebc8 | note | SPECIFICATION / REFERENCE DOCUMENT - RMS132 4.1.2
b4000b8b-9a5f-5c41-8144-cae7a7ffff8c | note | ACCEPTANCE CRITERIA - The WRSB shall not be installed until the set-out alignment of the posts has been reviewed & accepted by the Nominated Authority. Allow the Nominated Authority a minimum of one working day to inspect the pegged alignment & a further minimum period of five working days to provide its acceptance including details of any required changes in alignment, length or number of installations or terminals.
2d20f73d-92ea-5007-9b20-018da422ee95 | note | TEST REQUIREMENT & FREQUENCY - HOLD POINT WITNESS POINT REVIEW POINT Each Lot
481f4752-a1d6-599f-bd29-5fe20665ac67 | note | RESPONSIBLE PERSON / METHOD - NA IR SE Inspection Notification
8fc671eb-20d3-5b15-a6cb-8062b0f15dce | textbox | RECORDS - HOLD POINT NO.:
88e4bcf8-1ae6-5a18-995a-2abaf022b44c | note | SUR Signature
0b7ade79-bbdc-49ba-9d08-018ea4149930 | signoff | AUTHORITY HOLDPOINT
280c9c6e-2774-4f2b-9f00-6c271526e842 | checkpoint | 2.3. - Anchor Block Foundation Excavation
e3d5120a-642b-5dc4-a5a2-f5676a27a18b | note | SPECIFICATION / REFERENCE DOCUMENT - Manufacturers specifications
5fa330b4-3fb0-5f5e-8032-6cf91bfb93d6 | note | ACCEPTANCE CRITERIA - Anchor blocks & post foundation shall not be cast until inspected by the Nominated Authority. • Anchor block holes to be of correct dimension, shape, level & alignment • Over-excavation of the anchor block excavation shall not be reformed with form work or soil, but shall be cleaned out & filled with concrete forming the concrete anchor block • To be free of loose material, debris & water prior to the placement of concrete.
d91b11ff-003b-5276-ac04-179658421f06 | note | TEST REQUIREMENT & FREQUENCY - HOLD POINT WITNESS POINT REVIEW POINT Each Lot
ea03b8e6-0fc8-5624-b080-4429c2f0c239 | note | RESPONSIBLE PERSON / METHOD - NA IR SE Inspection Notification
73257db8-d671-5ce6-bcf2-4c63bbcb218a | textbox | RECORDS - HOLD POINT NO.:
b7cbe11e-8e8d-4d95-b19f-c75ae37f140d | signoff | AUTHORITY HOLDPOINT
d9c15928-48fe-48d4-8ec1-1ca915fb132d | checkpoint | 2.4. - Post Holes Excavation
a970502d-93ff-5ec3-acb5-c851b751d36a | note | SPECIFICATION / REFERENCE DOCUMENT - Manufacturers specification
96088556-b8c6-5d23-b683-dd0aec601d4e | note | ACCEPTANCE CRITERIA - • Holes to be free of loose material, debris & water prior to the placement of concrete. • Excavation of the hole to the correct dimension, shape, level & alignment specified by the proprietary system. • Posts shall be spaced in accordance with the manufacturer’s specification unless otherwise required by the design requirements of the manufacture
35b029e4-097a-5e86-a3e0-e79cab4dead5 | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
7d82dbcb-943f-5d1d-a407-cf1aef3ecff8 | note | RESPONSIBLE PERSON / METHOD - SE Inspection
bbc5042f-598b-49cd-81ab-59a5b686c7ca | checkpoint | 2.5. - Anchor Block Pour
bc4479eb-e92c-5619-b5b7-b6034f9287de | note | SPECIFICATION / REFERENCE DOCUMENT - Tfnsw3204
33f1dada-021e-5a87-8dc3-0318d2953779 | note | ACCEPTANCE CRITERIA - • N32 Strength Grade Concrete to be used. • All anchor frames, posts, sockets & reinforcing rings shall be positioned to the line & levels as specified in the drawings & shall be secured against displacement during placing of the concrete • No construction joints shall be provided within the anchor block.
344f3d6c-baa4-5a36-8ae3-1818690339e5 | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
11a01ac2-a309-5ff5-8f84-7044d40615c8 | note | RESPONSIBLE PERSON / METHOD - SE Inspection
66d520af-5afe-5a02-9b1e-c99aacc08a80 | note | RECORDS - 58519-QUA-LIS-00-0009 Concrete Checklist 58519-QUA-LIS-00-0010 Concrete Pour Record
cbe19b7b-2383-440f-985a-7684e86ce5d5 | checkpoint | 2.6. - Post Foundation Pour
84adb05e-f373-5cd0-84c9-71073a0971c9 | note | SPECIFICATION / REFERENCE DOCUMENT - Tfnsw3204
24f48262-c784-5ac9-b81b-a6937a52b8e0 | note | ACCEPTANCE CRITERIA - • N25 Strength Grade Concrete to be used. • The finished surface of all anchor blocks & footings shall be shaped such that water cannot pool on the surface.
a7d93c20-4b9a-5e22-ade8-009bceb57936 | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
5cbbd70f-e241-5022-b055-5428ff88685b | note | RESPONSIBLE PERSON / METHOD - SE Inspection
336b054a-328c-533a-898b-109589608653 | note | RECORDS - 58519-QUA-LIS-00-0009 Concrete Checklist 58519-QUA-LIS-00-0010 Concrete Pour Record
838f8fdf-dab6-4b7f-a8fd-2de2256dc03a | checkpoint | 2.7. - Location of Posts Adjacent to Batter Hinge Points ≥ 1m
6677ce38-7dfe-574a-aba9-952f1b13d903 | note | SPECIFICATION / REFERENCE DOCUMENT - Manufacturers specification
85dd6b56-5849-52e2-b3c7-3de98241b5e4 | note | ACCEPTANCE CRITERIA - • WRSB posts constructed with the manufacturer’s default post footing design shall be located at the greater of a minimum 1 m offset from the batter hinge point & the manufacturer’s specification, subject to dynamic deflection requirements being met • The batter hinge points as
c712905b-78b9-554a-8791-448a19ef5aaf | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
1fcd3f94-3f07-5964-bb90-5f4ee0aceda9 | note | RESPONSIBLE PERSON / METHOD - SE Inspection
2a764661-2687-53be-bc80-1a31b40781c8 | note | RECORDS - Survey Certificate
ba27cbe2-49c1-4e13-9890-5508d5e3872a | checkpoint | 2.8. - Location of Posts Adjacent to Batter Hinge Points < 1m
4100aba7-2093-5157-b6fd-c370d5a17f22 | note | SPECIFICATION / REFERENCE DOCUMENT - Manufacturers specification
753ccce7-fd8c-5b48-847e-956a71546d5c | note | ACCEPTANCE CRITERIA - If minimum offset to the Batter Hinge Point is reduced, the depth of the footing to be adjusted shall be in accordance with the manufacturer's specification. Side Load Testing at 45 degrees to the WRSB in all directions at locations nominated by the Nominated Authority.
30999fda-c212-5cb7-8418-e82bf3366b4d | note | TEST REQUIREMENT & FREQUENCY - HOLD POINT WITNESS POINT REVIEW POINT Each Lot
ffd93e48-2a8a-519a-8750-1a3a90d63101 | note | RESPONSIBLE PERSON / METHOD - NA IR SE Review Notification
b5f8f407-c4ae-5516-a791-38b047ba002a | textbox | RECORDS - HOLD POINT NO.:
978ffa95-8679-5233-94e2-cf5c17244a65 | note | Written statement from Manufacturer
46f1fa9a-1041-4861-b46f-95a65bf24bdc | signoff | AUTHORITY HOLDPOINT
a96b9217-cdc2-420e-8c1e-08deca3efc47 | checkpoint | 2.9. - Concrete maintenance strips
8d919865-c068-5605-a3cf-34f8b2ebcefb | note | SPECIFICATION / REFERENCE DOCUMENT - Tfnsw3204
655557e2-6209-54b7-9ddd-c81871dc7c81 | note | ACCEPTANCE CRITERIA - Concrete maintenance strips parallel to the WRSB shall meet the following requirements: • Where the maintenance strip is adjacent to kerb or pavement, separation from the kerb or pavement by the use of a cork expansion joint (or approved alternative) shall be used • Extends a minimum of 300 mm clear on both sides with min 2% cross fall • Bedding to be 75mm thick of class 3 crushed rock • Concrete shall be 75mm thick & 20MPa Strength • Edges of infill boarded up prior to pour • Dummy joints at least 20 mm deep & 5 mm wide shall be formed at 2 m intervals across the full width of the concrete maintenance strip Surface • Expansion joints shall be placed at intervals not exceeding 12 m. • finished with a wooden float to produce a lightly textured finish
05283f6c-02c5-50cb-8e4f-cdc2db2e435e | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
fd19d6f2-3788-5d2d-89d8-d6f7844625dc | note | RESPONSIBLE PERSON / METHOD - SE Inspection
b7421526-0067-44c5-bcbe-c24f248c62df | checkpoint | 2.10. - Concrete Testing – 28day Compressive Strength.
5e040f1c-076c-532b-b076-455f122a5dc2 | note | SPECIFICATION / REFERENCE DOCUMENT - Tfnsw3204 QMP
75874ab6-e85b-5bf9-b9c6-0c0800c4844c | note | ACCEPTANCE CRITERIA - Supplied concrete to comply with AS 1379, including sampling & testing in accordance with Clause 6.2 of AS1379, & VR Specification. Frequency: One per 6cu.m (or part thereof), per day, per concrete grade.
4d697391-5d30-5d3e-ba89-c5e97eb40618 | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
3426332e-4c6a-56f9-b89c-f3c06310f003 | note | RESPONSIBLE PERSON / METHOD - SE Document Review
c760c36f-3b83-5f65-ae91-70c47fe702bb | note | RECORDS - NATA Test Report: Concrete Compressive Strength Test
79fcbcd2-f74c-46d1-bc8a-fdabc09abb51 | section | 3.0 Wire Rope Installation
68833676-9347-461d-8316-a8e4cfef7b59 | checkpoint | 3.1 - Loading Test of Post Foundation
ae1e50d8-c417-5702-8fa6-fcab72e57b95 | note | SPECIFICATION / REFERENCE DOCUMENT - Manufacturers specification
7fbb5497-1d47-5c9c-ae43-e25de338e2e0 | note | ACCEPTANCE CRITERIA - • Side Lode testing at locations nominated by Nominated Authority prior to the installation of Wire Rope. • Side load testing of posts shall be carried out by applying a force of 10 kN (approximately 1 tonne) to the post 600 mm above ground level at an angle of 45 degrees to the WRSB. • The top of the footing shall not move more than 3 mm • Foundations satisfy the specification requirements & will not crack, lift or displace during impact.
612d2721-6ac7-5750-8687-587a26613847 | note | TEST REQUIREMENT & FREQUENCY - HOLD POINT WITNESS POINT REVIEW POINT Each Lot
591c15dc-41b1-51d8-bdec-f3fa3857d514 | note | RESPONSIBLE PERSON / METHOD - NA IR SE Inspection Notification
70079f1a-4153-57c5-8721-d911fbd647e7 | textbox | RECORDS - HOLD POINT NO.:
8ce09bb3-cddd-5cba-85fa-c1ffea8a5c0d | note | Diagram
77c0d0a3-8d82-43fe-8c1b-e971e1b1ab59 | signoff | AUTHORITY HOLDPOINT
f195659c-720f-420f-801b-3e7a3b13ac51 | checkpoint | 3.2 - Install Wire Rope
8dafe8e5-4dc0-5bfb-9a8a-e2340fa2f81f | note | SPECIFICATION / REFERENCE DOCUMENT - Manufactures specification
319ef1d5-4090-52f0-ae6e-df703abd93db | note | ACCEPTANCE CRITERIA - Vertical alignment of the wire rope shall be smooth, uniform & generally consistent with the vertical alignment of the edge of the traffic lanes. Wire Rope installed to the correct line, level & height.
586f1bd8-bf53-5fb2-88de-a03f716f0eb2 | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
8957d0b4-d0ac-5907-bc41-df3ddf73e1f2 | note | RESPONSIBLE PERSON / METHOD - SE Inspection
4f2e8c1d-57e5-4cae-bc86-d2ab305b146f | checkpoint | 3.3 - Tensioning of the Wire Rope.
f6ebf4cc-330d-5ca9-986e-8e178e3e910d | note | SPECIFICATION / REFERENCE DOCUMENT - Manufactures specification
907ed964-0d2c-543b-9c20-a7fbda66ddf4 | note | ACCEPTANCE CRITERIA - Each wire rope shall be tensioned in accordance with the relationship between rope tension & ambient temperature, applicable to the proprietary WRSB system as per the manufacturer’s specification The tension shall be measured using a tension meter supported with a current calibration certificate. Prior to commissioning the WRSB system, the tension in each wire rope shall be checked, & re-tensioned if required, to ensure compliance with the ambient temperature/rope tension relationship. Prepare & submit a tensioning report for review by the Nominated Authority within seven days of the tensioning works being carried out.
b5ee5271-fdf3-542b-af61-ae52881aa81d | note | TEST REQUIREMENT & FREQUENCY - HOLD POINT WITNESS POINT REVIEW POINT Each Lot
2875d6ee-f792-5a9c-b554-f0a50b8cce04 | note | RESPONSIBLE PERSON / METHOD - NA IR SE Document Review Notification
b66247e8-0e00-5dc6-b2fd-4b547447dc7c | textbox | RECORDS - HOLD POINT NO.:
d69a108f-4bdc-5448-9d68-26d74cd6fb70 | note | Current calibration certificate of tension meter. Tensioning report
e2806a97-a2c1-497f-8c12-062829dac7ae | signoff | AUTHORITY HOLDPOINT
7d40e746-042a-401e-83e4-c00d7f8f9c34 | checkpoint | 3.4 - Installation of Delineators
8a2f5fab-b980-56b2-b47a-698b1978494d | note | SPECIFICATION / REFERENCE DOCUMENT - R132/A 1.21 4.1 R0710-18
2606e403-dbf2-54c1-8661-da976b194c3c | note | ACCEPTANCE CRITERIA - • Attach delineators to the WRSB posts by either using 50mm x 100mm post caps with delineators attached, or fastening delineators directly to the front top of the posts above the wire ropes • Install delineators at approximately 12.5 to 15m spacing. • Delineators are not to be installed on flared sections of WRSB • Red delineators on the left side of one- way & two-way roadways; • White delineators on the right side of two-way roadways; and • Yellow delineators on the right side of one-way roadways • Delineators not required where WRSB offset is greater than 4 m from the traffic lane.
84cfe536-a9cf-5b23-a6fe-4b206b864202 | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
76e46614-6339-5f50-af1d-04c7c54cb14a | note | RESPONSIBLE PERSON / METHOD - SE Inspection
d2430ad0-9876-4984-90b1-99f9a8f781a0 | section | 4.0 Completion
72084df6-acfb-47b8-a6a1-7afb2bba1aa4 | checkpoint | 4.1 - Construction Tolerances –
2a5a3745-c329-5652-af7a-86055252944e | note | SPECIFICATION / REFERENCE DOCUMENT - Manufactures specification
502268c6-5580-5be5-a185-721ef3a52ef9 | note | ACCEPTANCE CRITERIA - a) vertical tolerance on the height of the WRSB shall be ± 20 mm from the design line b) longitudinal line tolerance for the WRSB system shall be ± 20 mm in plan view c) tolerance on post spacing shall be ± 25 mm. WRSB height shall be measured from the road pavement when it is located within 1.5 m of the edge of pavement. For distances beyond 1.5 m, the WRSB height shall be measured from the ground surface at its location.
fcb24dfc-3749-5c01-968a-980723489ad6 | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
77dcf42a-5dc5-5724-9bc5-e4a089e9d440 | note | RESPONSIBLE PERSON / METHOD - SUR Inspection
c8262802-8bf4-52b8-8133-7bd0793fbb96 | note | RECORDS - SUR Signature
176d7dc9-aa9a-56ce-abd8-7aa49858dacf | note | Survey Conformance Report
38f37bdc-9b76-4dbf-b33b-c44393da20a7 | checkpoint | 4.2 - Safety Barrier Compliance Audit
4eb44d32-c79d-54a7-ba9c-743a81bdc047 | note | SPECIFICATION / REFERENCE DOCUMENT - QMP
c58bb9a8-cfd0-5d19-b034-2acc1445166c | note | ACCEPTANCE CRITERIA - After Completion, arrange for a safety barrier compliance audit on all WRSB installations. The audit shall be undertaken, & a report prepared by the Australian Licensed Supplier of the safety barrier system. Certificate of Compliance for each length of WRSB, signed by the Contractor’s Representative & the Licensed Supplier, to be provided certifying that the product systems (including terminals) have been installed in accordance with the manufacturer’s Installation Manual & Specification Section 711. Complete & submit to the Nominated Authority a signed copy of the manufacturer’s Installation Checklist/ Inspection & Test Plan as per the manufacturer’s Product & Installation Manual.
a7ad6247-0b41-53d0-a9ab-aa5a4fb47b0c | note | TEST REQUIREMENT & FREQUENCY - HOLD POINT WITNESS POINT REVIEW POINT Each Lot
b7ea808f-d847-54d4-86d5-63537f83097c | note | RESPONSIBLE PERSON / METHOD - NA IR SE Inspection Document Review Notification
4ee6b7ac-bbf8-51ef-89ea-03b4de020bfb | textbox | RECORDS - HOLD POINT NO.:
9b8c2388-3f92-55ac-a9ee-4e586170cd46 | note | Compliance Audit & Certificate of Compliance
4b7d7f17-de9b-4f93-a86b-34f8a3eb9aa5 | signoff | AUTHORITY HOLDPOINT
29d1a8a2-11ed-403e-8ccf-48cccb7119b7 | checkpoint | 4.3 - Reinstated Works
abda4742-876c-519c-96a0-2b476b26d058 | note | SPECIFICATION / REFERENCE DOCUMENT - Integrate the WRSB with existing roadside barriers & remove redundant assets (e.g. guide posts, sections of conflicting existing roadside barriers. All existing signs & markings, median crossings & existing vegetation removed due to WRSB installation shall be reinstated.
85c8bc82-fb71-5b2c-8677-6f0d835b932f | note | ACCEPTANCE CRITERIA - REVIEW POINT Each Lot
38106f16-1cd4-513f-b2a7-bdd54bc3a0d5 | note | TEST REQUIREMENT & FREQUENCY - SE Inspection
b3086e1b-1f32-5ef0-992d-857e0f6eb72d | note | Manufacturer’s Installation Checklist/ Inspection & Test Plan
7bdfe886-9f2a-4072-9871-b70859655530 | section | 5.0 Work Lot Close out
528f85f5-86c6-424a-8a0f-db3faf28ebea | checkpoint | 5.1 - Test Reports
a4b23ca1-baff-5a30-90bf-54103f7354f7 | note | SPECIFICATION / REFERENCE DOCUMENT - RMS Roads Specifications
bf81bb8f-66d4-51a9-b3f9-1bfbfc3834d9 | note | ACCEPTANCE CRITERIA - All Test reports received & Reviewed
33019671-3699-5545-b86f-223309ea1b0b | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
b8cf1a8a-b0b5-5432-8051-e19fbc8326b9 | note | RESPONSIBLE PERSON / METHOD - PE Document Review
0a237665-c3c4-5fac-918f-9e45c4f7a00a | note | RECORDS - NATA Endorsed Test Reports
cb2871bc-62fb-4140-839e-49bf2ec431ae | checkpoint | 5.2 - Product Non- Conformance
143d2e0e-044f-5dfb-abfa-713e4b827703 | note | SPECIFICATION / REFERENCE DOCUMENT - QMP
996e4b59-8107-505d-8b94-e19b44620465 | note | ACCEPTANCE CRITERIA - All Product Non-Conformance(s) recorded & closed (if applicable)
464f32a2-ccf2-5850-a92b-0922afc3fe31 | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
af75787c-1508-536e-b9c7-7ba4a9df4478 | note | RESPONSIBLE PERSON / METHOD - PE Document Review
f65d3d9f-ca2a-5322-a1af-b6d2c11913b4 | textbox | RECORDS - NCR No:
e92ef22a-401f-55b2-b462-5244aa65f44f | note | NCR reports
adca4dbf-b67b-4fed-9bb6-4d472dd6fe17 | checkpoint | 5.3 - Quality Representative to check the above criteria & records to confirm
e72a9946-b6a8-57b8-ab16-bccb73a51613 | note | SPECIFICATION / REFERENCE DOCUMENT - QMP Lot Records
7d3fc423-f254-5242-97a5-fd1e747f8b78 | note | ACCEPTANCE CRITERIA - All above criteria met & records identified attached.
2b71ddd4-efff-56fc-ade2-7e032e818ff7 | note | TEST REQUIREMENT & FREQUENCY - REVIEW POINT Each Lot
40bd1e6b-2cd1-58a9-bf70-daf2c528b020 | note | RESPONSIBLE PERSON / METHOD - QR Document Review
bfacfc9d-db9a-5fed-829e-c9205984937e | note | RECORDS - Completed Checklist (if applicable) & reports & other compliance records attached.
999cc9c6-bddc-4d80-8bb5-0c74ba07a7d7 | section | ITP COMPLETION
88c04ae3-7e5a-48d5-8ea6-de65ccbad085 | checkpoint | ITP COMPLETION - Project Representative:
3bea0bb0-6b38-4987-8141-bb4f7b62143d | signoff | Add / Request Signature
630ae2e6-b869-474a-88e5-bc5c46f1e5dc | checkpoint | ITP COMPLETION - Quality Representative:
fd257b7f-9460-4804-9c92-acef5ae53c93 | signoff | Add / Request Signature
d5b66c64-aa88-4773-b04b-31b8456cfcf0 | checklist | ITP - Guardrails |  | ITP - Guardrails
48c34ada-fd40-4289-8f22-9db997dafb65 | section | Prelims (Hold Points)
ace76b77-ae05-44bf-9d9f-90ca6d41afa4 | checkpoint | Have all the Local services been marked up and located ( picture ) DBYD plans / permit to dig been supplied.
3e750593-5313-4304-a61c-50c9f4daf65d | checkpoint | The site conditions for the installation is suitable. Clearance to the obstruction - Batter hinge point proximity-set back sufficient ( picture )
326531af-b1e5-4f0f-b1fe-66c28eeb9e76 | checkpoint | Is the finished road level surface in place. If no, what is the overlay requirements -
d58b7d89-0fc5-5812-9a66-53e4805df5c6 | textbox | Enter the uplift difference in mm as instructed by the customer.
03418394-197f-492c-b1b2-e6205adfc825 | checkpoint | Has the setting out for the alignment and setback been marked up and as per the drawings ( picture ) By customer or A1 ( cycle 1 )
037e08f2-4b00-4a94-8c17-5d99d1be0955 | section | Installation (Witness Points)
8040d659-0f8c-4c85-a853-0754fcf74fd1 | checkpoint | The posts are spaced at maximum 2.0m centres.
40652620-d8af-468a-af5e-95c4d9f90bc5 | checkpoint | The posts are correctly orientated with the release tab on the traffic side.
d032c571-a284-4c50-8ddd-2573622e9755 | checkpoint | The rail is secured to each post with a M16 x 32mm (or 50mm) mushroom head bolt & standard nut.
e794f55c-0007-4a8e-957c-fec770a6e0d0 | checkpoint | The rails are spliced with eight (8) M16 x 32mm mushroom head bolt & oversized nuts.
848dbd75-a21e-47ec-97ce-173870e1b192 | checkpoint | The rail lap is orientated so that the leading edge of the splice is shielded from approaching traffic.
35fe229e-53e4-4d71-9b82-387a71ef75d3 | checkpoint | All bolts are tightened.
6d7c4abe-a731-4674-8bf1-5b8d8de8a864 | checkpoint | Any minor damage to the galvanised finish is repaired using two coats of an organic zinc rich paint.
9667a9ef-5016-4c01-a430-4c5d57885897 | checkpoint | The barrier is appropriately delineated
f6a3afd7-8a7f-579e-8369-32aaf6ad0f35 | textbox | Placement between delineators in meters
0af8d908-aefd-4069-8a18-cceca3b80549 | checkpoint | End terminal installed to specifications
749b62e9-c738-4a19-b04d-6ad022660184 | checkpoint | Motorcycle protection rail installed to specifications
94492e15-063d-4a02-be95-00d67c4ca3f3 | checkpoint | The area around the barrier is free of debris. ( Picture Required of completed works )
949c1cfa-a486-4bb4-8f95-8e7a86d40567 | checklist | ITP - Wire Rope |  | ITP - Wire Rope
2d533b69-e9f2-4c46-b5a0-f1b7698acf1c | section | Details
5ea99c3f-82f5-420e-962c-1b0fed0537ce | checkpoint | Type of Wire Rope Safety Fence Installed:
a48eee2e-9ddf-5e6b-a7b3-a808ea30d417 | textbox | Type of Wire Rope Safety Fence Installed:
d145b32d-10b0-49fa-8ca6-6f26796f9bf7 | section | Quantity Installed
0869eebe-2a41-4230-aba7-0d033251e1d3 | checkpoint | Posts at 2 m Centres
0ba04201-785b-5805-90cb-31b674deed7a | textbox | Quantity:
bb63f19e-0ae3-4aa8-bb53-69593db713aa | checkpoint | Posts at 3 m Centres
c4e351a8-902e-519f-a953-d5e0ea1fb0ac | textbox | Quantity:
a5b7f416-23ff-441c-921d-6774cea1f11a | checkpoint | Posts as m Centres
66a5e468-0c86-5262-877e-b97ce50edf0e | textbox | Quantity:
4534b091-a60f-4bc6-8b73-c9ad053a1040 | checkpoint | Wire Rope Installed
a17d928d-73f3-5bd8-97be-553d63d4bcda | textbox | Quantity:
81da1d7c-9c10-46ae-8cf7-eca8fdeb81c9 | checkpoint | End Terminals
b3738e87-2723-5938-93dc-859934d1eec9 | textbox | Quantity:
07bb7e84-c061-4439-9cc8-a3248128fb6a | checkpoint | Tension Bays
10dc671e-b0c2-500d-b5c6-313f66c7f210 | textbox | Quantity:
f335f0f8-fdcc-4427-8fa9-19ea370119ad | checkpoint | Maintenance / Repairs to Terminals
2159ebbe-f26f-5ca0-b383-ea363eb42cb7 | textbox | Quantity:
aea5e6ad-f8c8-42e3-aaee-1e5b0f9ec6a1 | checkpoint | Maintenance / Repairs to Posts
bd91b1bd-df25-5202-886d-2d52eddf7e87 | textbox | Quantity:
bf86d62f-ac8d-4a54-9795-00ab017c6af6 | checkpoint | Maintenance / Repairs to Wire Rope
f04b5caa-0c01-5810-8039-28ada90634c6 | textbox | Quantity:
239a6b14-9877-443a-94df-c98c584f8a8a | checkpoint | Anchor Concrete Doc No
5e2ec928-a4aa-5f2c-8627-36babb30bf01 | textbox | Quantity:
28b3ed79-917c-4564-b717-7c1fdd5c85ac | checkpoint | Date Anchor Installed
87f2c07e-e1ae-5f42-8e18-70f5ac50c9d8 | textbox | Quantity:
15b72704-e0b6-4e7e-b8e1-b9a46b878124 | checkpoint | Post ID
6fe2837d-2ada-5abd-851a-52151e925237 | textbox | Quantity:
db110015-57fa-44fc-9830-8a93fc07ef27 | section | Inspection and Tes
62ca0fc3-2356-4fdf-b6d9-bff45d47a1fb | checkpoint | Set Out of system - Visual Inspection
e8df99b9-8bd3-45d5-a4f7-d3649ce12975 | checkpoint | Post Holes to Correct Depth - Checked with Tape
7658160e-a8fe-4a35-b9c8-302f5b45fc96 | checkpoint | Post Heights and Levels Correct - Checked with Tape and Level
fadd2542-0155-4136-a064-24a4451d0a82 | checkpoint | Material Compliance Certified - Check Compliance Certificate
f9efdc41-1d27-41c4-893c-4ff68269bfdd | checkpoint | Post Reflectors Installed - Visual Check
54dddcf7-3766-4c51-a5a4-077e0b918940 | checkpoint | Wire Rope Installed - Visual Check
9d48b068-5720-4380-8534-64047dda1f23 | checkpoint | Terminal Block Excavated to Size - Checked with Measuring Tape
aaba49e9-8cf3-4788-b0ae-4fc298c46d98 | checkpoint | Concrete Foundation Reinforcement Installed - Installed With Concrete
0c934ac8-73ff-4be9-b456-1bd1aee370c6 | checkpoint | Concrete Test - See Test Docket
09b74049-5eea-4d26-8e83-15645e3b2249 | checkpoint | Post Caps Installed - Visual Check
9ab4a1bf-7091-4894-bfdb-cfd038a08de6 | checkpoint | Installed to manufacturers Specification -
52868eb1-b5f0-4634-979e-d1aeb0157bd1 | checkpoint | Area Cleaned Up - Visual Inspection
f033a3e0-5c06-589a-83e4-e214393c2a48 | textbox | Coil ID No
eff775ac-0c4e-405e-a052-6f1f8930f5ab | section | Tensioning of Wire Rope
464c6aec-4a13-48e7-8f70-cf28c018fed2 | checkpoint | Tensioning of Wire Rope
96e8e11d-3d3f-5cf6-9122-1cd199480c04 | textbox | Date/ Time/Temp of Tensioning (°C)
e29d4152-7254-5dd6-8924-c87fd937a3f7 | textbox | Maximum Allowable Tension at Temperature (kN)
a4778aa5-00dd-58fe-9625-c1bd5fd12f19 | textbox | Minimum Allowable Tension at Temperature (kN)
c0fe32e0-fbab-42d8-bf98-13d635a6a538 | section | Gauge Reading
b67ef88a-c369-4f30-a46f-0825e7826a58 | checkpoint | Gauge Reading
a6d7e117-4073-5640-9417-41d9f83cfbc6 | textbox | Top Rope (kN)
f61008cf-fa6c-598a-a5dd-cc7bfe1323fc | textbox | 2nd Rope (kN)
b100f718-d0f8-591a-b6d5-183a9baa9159 | textbox | 3rd Rope (kN)
860c14d7-7cd2-5b2e-9f58-736b7df1b1ba | textbox | 4th Rope (kN)
47329573-8cb4-4272-9882-d6eb555c94a0 | section | ITP Completion
7f6f2155-ba28-4e62-83f0-7d90c92356d7 | checkpoint | I confirm that the above works have been installed in accordance with the Specification Requirements. Any minor alterations to the standards are stated on the attached NCR Report. - Signed by A1 Highways Rep:
bdbcccaf-847d-4bc1-ad93-ceb3dff5d66d | signoff | Add Signature / Request Sign Off
00e40395-1212-43ea-828b-11b92f42018d | checkpoint | I confirm that the above works have been installed in accordance with the Specification Requirements. Any minor alterations to the standards are stated on the attached NCR Report. - Signed by Client:
1f1176be-d1e1-4467-a714-44cc4eb2d504 | signoff | Add Signature / Request Sign Off
3aa02cb8-732d-414f-94e2-bbd7f905b7f7 | checklist | RFI / COI / NCR Form |  | RFI / COI / NCR Form
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
4cc9c88f-d0de-43c6-a54c-3a86590f4917 | checkpoint | RFI / COI / NCR
6206fdf0-6eda-5a90-bc0d-f4a0bb10690a | button | RFI / COI / NCR | RFI, COI, NCR
5db270f5-eebd-5eb1-873e-60281908aa26 | textbox | Request for information / Confirmation of Instruction / Non-Conformity Report
7bc510ca-c5d5-574f-8fa2-7742a8464a50 | textbox | Reply / Additional Comments / Corrective Action
0d37bb2e-ff51-55ab-afa0-93596a7bbefd | textbox | Reasons Why it Happened
c0a1a965-b59f-5fa8-9ee0-5c3e14c44494 | textbox | Corrective Action Taken / Preventative Action Taken
6bb6dd44-9920-41ae-bedd-0497c267338b | checkpoint | Signed A1 Highways Rep:
02bb6d81-7307-4264-a92a-62f1fe303b54 | signoff | Add / Request Signature