## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Precast Components ITP
section | Documentations
checkpoint-no-status | Special Instructions
checkpoint-no-status | Approved Shop Drawings
bool | 3.9m Wide Deck Type A Panels
bool | 3.9m Wide Deck Type B Panels
bool | Abutment AA
bool | 582mm Upper Wall to suit Abutment AA
bool | Abutment BB
bool | 776mm Upper Wall to suit Abutment BB
checkpoint-no-status | Other
section | Job Approval Documents/Construction Documents
checkpoint | Shop drawings repaired, reviewed and updated. Issued "As For Construction"
label | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
section | Pre-Pour Check Approvals
checkpoint-no-status | Formwork
checkpoint-no-status | Reinforcement(Reo)
checkpoint-no-status | Embedded Items and their placement
checkpoint-no-status | Lift Procedure
checkpoint-no-status | Concreting (mix design
section | Test on Concrete (requests and approvals)
checkpoint-no-status | Request From Client
checkpoint-no-status | Test schedule and Test Results
checklist | Checkers Checklist - Type A - Bridge Plank | [5 empty] | Checkers Checklist - Type A - Bridge Plank
section | Checkers Checklist
checkpoint | Site Safety / Workers Safety
checkpoint | Availability of updated shop drawing
checkpoint | Double Check the Ferrule placement - Type A (300F1450F400F1450F300)
dropdown | Ferrule: | 300F1450F,250F1450F
checkpoint | Overall Measurements of construction Element
checkpoint | Embedded Item - Ferrules - Position,Size,Orientation -M20 (96mm) - 10Nos
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal
checkpoint | Double check ferrules are firmly positioned & Fixed with M12 on shutter
checkpoint | Concrete cover check minimum 30mm
checkpoint | Panel Thickness check,allignment check -150mm
checkpoint | Panel length check, alignment check -3900mm
checkpoint | Diagonal length check, alignment check (4025 mm or close to this)
checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Curing Procedure arranged
checkpoint | Photo Taken
checklist | Installers Checklist - Type A - Bridge Plank | [5 empty] | Installers Checklist - Type A - Bridge Plank
section | Job Approval Documents/Construction Documents
checkpoint | Complete Material "Bucket List"
checkpoint | Eye Anchor - 2.5T - 04
checkpoint | Ferrules - M20 x 96mm - 10
checkpoint | ID Plate
textbox | ID:
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Double Check the Ferrule placement -Type A
checkpoint | Reinforcement Check - Reo as-per Shop Drawing
checkpoint | Lifters, Ferrules Fixed Firm & aligned -Check
bool | Embedded Item - Ferrules - Position,Size,Orientation -M20 (96mm) - 10Nos
bool | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal
checkpoint | Concrete cover Check - minimum 30mm
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
checkpoint | QA - Concrete mixdesign ,variations%, adjustments%, mix time
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
date | Pour Date
checkpoint | CONCRETE TEST Procedure
checkpoint | APPROVAL FROM ENGINEER
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged
dropdown | Finish: | Fine finish,Broom finish
checkpoint | Curing Procedure arranged
checklist | Checkers Checklist - Type B - Bridge Plank | [5 empty] | Checkers Checklist - Type B - Bridge Plank
section | Checkers Checklist
checkpoint | Site Safety / Workers Safety
checkpoint | Availability of updated shop drawing
checkpoint | Double Check the Ferrule placment -Type A (250F1450F500F1450F250)
dropdown | Ferrule: | 300F1450F,250F1450F
checkpoint | Overall Measurements of construction Eliment
checkpoint | Embeded Item - Ferrules - Position,Size,Orientation -M20 (96mm) - 10Nos
checkpoint | Embeded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal
checkpoint | Double check ferrules are firmly positioned & Fixed with M12 on shutter
checkpoint | Concrete cover check minimum 30mm
checkpoint | Panel Thickness check,allignment check -150mm
checkpoint | Panel length check, allignment check -3900mm
checkpoint | Diaganal length check, allignment check (4025 mm or close to this)
checkpoint | Formwork Check - Magnets are 100% Secure,All supports,Ties,Bracing
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
checkpoint | Reinforcement (Reo) placed, cleaned, tightned
checkpoint | Curing Procedure arranged
checkpoint | Photo Taken
checklist | Installers Checklist - Type B - Bridge Plank | [5 empty] | Installers Checklist - Type B - Bridge Plank
section | Job Approval Documents/Constrction Documents
checkpoint | Complete Material "Bucket List"
checkpoint | Eye Anchor - 2.5T - 04
checkpoint | Ferrules - M20 x 96mm - 10
checkpoint | ID Plate
textbox | ID:
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Double Check the Ferrule placment -Type B
checkpoint | Reinforcment Check - Reo as-per Shop Drawing
checkpoint | Lifters, Ferrules Fixed Firm & alligned -Check
bool | Embeded Item - Ferrules - Position,Size,Orientation -M20 (96mm) - 10Nos
bool | Embeded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal
checkpoint | Concrete cover Check - minimum 30mm
section | Quality Assuarance
checkpoint | QA - Final Check of ALL measurerments
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
checkpoint | QA - Concrete mixdesign ,veriations%, adjustments%,mix time
checkpoint | QA - All main & other requirment to do Concreting -DOUBLE CHECK
date | Pour Date
checkpoint | CONCRETE TEST Procedure
checkpoint | APPROVAL FROM ENGINEER
section | Other Arangments
checkpoint | Concrete surface Finish Requirment arranged
dropdown | Finish | Fine finish,Broom finish
checkpoint | Curing Procedure arranged
checkpoint | Curing Procedure arranged
checklist | Checkers Checklist - Abutment Base - AA | [5 empty] | Checkers Checklist - Abutment Base - AA
section | Checkers Checklist
checkpoint | Site Safety / Workers Safety
checkpoint | Availability of updated shop drawing
checkpoint | Double Check the Ferrule placement -Type AA (550F400F1050F400F1050F400F550)
dropdown |  | 550F400F1050
dropdown |  | 500F500F950
checkpoint | Overall Measurements of construction Element
checkpoint | Embedded Item - Ferrules - Position,Size,Orientation -M24 (96mm) - 06Nos
checkpoint | Embedded Item - Ferrules for Dowels - Position, Size -M24 (96mm) - 07Nos
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
checkpoint | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement
checkpoint | Double check ferrules are firmly positioned & Fixed with M12 bars on shutter
checkpoint | Concrete cover check minimum 30mm
checkpoint | Panel length check, alignment check -4400x800mm
checkpoint | Diagonal length check, alignment check (4472 mm or close to this)
checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Curing Procedure arranged
checkpoint | Photo Taken
checklist | Installers Checklist - Abutment Base - AA | [5 empty] | Installers Checklist - Abutment Base - AA
section | Job Approval Documents/Construction Documents
checkpoint | Complete Material "Bucket List"
checkpoint | Eye Anchor - 2.5T(170mm) - 04
checkpoint | Ferrules - M24 x 96mm
checkpoint | ID Plate
textbox | ID:
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Double Check the Ferrule placement -Type AA
checkpoint | Reinforcement Check - Reo as-per Shop Drawing
checkpoint | Lifters, Ferrules Fixed Firm & aligned -Check
bool | Embedded Item - Ferrules - Position,Size,Orientation -M24 (96mm) - 06Nos
bool | Embedded Item - Ferrules for Dowels - Position,Size -M24 (96mm) - 07Nos
bool | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
checkpoint | Concrete cover Check - minimum 30mm
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
date | Pour Date
checkpoint | CONCRETE TEST Procedure
checkpoint | APPROVAL FROM ENGINEER
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged
dropdown | Finish: | Fine finish,Broom finish
checkpoint | Curing Procedure arranged
checklist | Checkers Checklist - Abutment Base - BB | [5 empty] | Checkers Checklist - Abutment Base - BB
section | Checkers Checklist
checkpoint | Site Safety / Workers Safety
checkpoint | Availability of updated shop drawing
checkpoint | Double Check the Ferrule placement -Type BB (500F500F950F500F950F500F500)
dropdown | Ferrule: | 550F400F1050,500F500F950
checkpoint | Overall Measurements of construction Element
checkpoint | Embedded Item - Ferrules - Position,Size,Orientation -M24 (96mm) - 06Nos
checkpoint | Embedded Item - Ferrules for Dowels - Position, Size -M24 (96mm) - 07Nos
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
checkpoint | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement
checkpoint | Double check ferrules are firmly positioned & Fixed with M12 bars on shutter
checkpoint | Concrete cover check minimum 30mm
checkpoint | Panel length check, alignment check -4400x800mm
checkpoint | Diagonal length check, alignment check (4472 mm or close to this)
checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Curing Procedure arranged
checkpoint | Photo Taken
checklist | Installers Checklist - Abutment Base - BB | [5 empty] | Installers Checklist - Abutment Base - BB
section | Job Approval Documents/Construction Documents
checkpoint | Complete Material "Bucket List"
checkpoint | Eye Anchor - 2.5T(170mm) - 04
checkpoint | Ferrules - M24 x 96mm
checkpoint | ID Plate
textbox | ID:
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Double Check the Ferrule placement -Type BB
checkpoint | Reinforcement Check - Reo as-per Shop Drawing
checkpoint | Lifters, Ferrules Fixed Firm & aligned -Check
bool | Embedded Item - Ferrules - Position,Size,Orientation -M24 (96mm) - 06Nos
bool | Embedded Item - Ferrules for Dowels - Position, Size -M24 (96mm) - 07Nos
bool | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
checkpoint | Concrete cover Check - minimum 30mm
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
date | Pour Date
checkpoint | CONCRETE TEST Procedure
checkpoint | APPROVAL FROM ENGINEER
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged
dropdown | Finish: | Fine finish,Broom finish
checkpoint | Curing Procedure arranged
checklist | Checkers Checklist - Upper Wall - AA | [5 empty] | Checkers Checklist - Upper Wall - AA
section | Checkers Checklist
checkpoint | Site Safety / Workers Safety
checkpoint | Availability of updated shop drawing
checkpoint | Double Check the Ferrule placement -Type AA Wall Height - 582mm
dropdown | Ferrule: | 582mm,776mm
checkpoint | Overall Measurements of construction Element
checkpoint | Embedded Item -75x75x8EA galvanized Edge strip - Position,Size,Orientation-4000mm
checkpoint | Embedded Item - Grout Tube - Position, Size -50mmDia ,290mm
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
checkpoint | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement
checkpoint | Double check ferrules are firmly positioned & Fixed with M12 bars on shutter
checkpoint | Concrete cover check minimum 30mm
checkpoint | Panel Thickness check,allignment check -150mm
checkpoint | Panel length check, alignment check -4400x800mm
checkpoint | Diagonal length check, alignment check (4472 mm or close to this)
checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Curing Procedure arranged
checkpoint | Photo Taken
checklist | Installers Checklist - Upper Wall - AA | [5 empty] | Installers Checklist - Upper Wall - AA
section | Job Approval Documents/Construction Documents
checkpoint | Complete Material "Bucket List"
checkpoint | Eye Anchor - 2.5T(170mm) - 04
checkpoint | ID Plate
textbox | ID:
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Double Check the Ferrule placement -Type AA
checkpoint | Reinforcement Check - Reo as-per Shop Drawing
checkpoint | Lifters, Ferrules Fixed Firm & aligned -Check
bool | Embedded Item -75x75x8EA galvanized Edge strip - Position,Size,Orientation-4000mm
bool | Embedded Item - Grout Tube - Position, Size -50mmDia ,290mm
bool | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
bool | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement
checkpoint | Concrete cover Check - minimum 30mm
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
date | Pour Date
checkpoint | CONCRETE TEST Procedure
checkpoint | APPROVAL FROM ENGINEER
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged
dropdown | Finish: | Fine finish,Broom finish
checkpoint | Curing Procedure arranged
checklist | Checkers Checklist - Upper Wall - BB | [5 empty] | Checkers Checklist - Upper Wall - BB
section | Checkers Checklist
checkpoint | Site Safety / Workers Safety
checkpoint | Availability of updated shop drawing
checkpoint | Double Check the Ferrule placement -Type BB Wall Height - 776mm
dropdown | Ferrule: | 582mm,776mm
checkpoint | Overall Measurements of construction Element
checkpoint | Embedded Item -75x75x8EA galvanized Edge strip - Position,Size,Orientation-4000mm
checkpoint | Embedded Item - Grout Tube - Position, Size -50mmDia ,290mm
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
checkpoint | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement
checkpoint | Double check ferrules are firmly positioned & Fixed with M12 bars on shutter
checkpoint | Concrete cover check minimum 30mm
checkpoint | Panel Thickness check,allignment check -150mm
checkpoint | Panel length check, alignment check -4400x800mm
checkpoint | Diagonal length check, alignment check (4472 mm or close to this)
checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Curing Procedure arranged
checkpoint | Photo Taken
checklist | Installers Checklist - Upper Wall - BB | [5 empty] | Installers Checklist - Upper Wall - BB
section | Job Approval Documents/Construction Documents
checkpoint | Complete Material "Bucket List"
checkpoint | Eye Anchor - 2.5T(170mm) - 04
checkpoint | ID Plate
textbox | ID:
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Double Check the Ferrule placement -Type BB
checkpoint | Reinforcement Check - Reo as-per Shop Drawing
checkpoint | Lifters, Ferrules Fixed Firm & aligned -Check
bool | Embedded Item -75x75x8EA galvanized Edge strip - Position,Size,Orientation-4000mm
bool | Embedded Item - Grout Tube - Position, Size -50mmDia ,290mm
bool | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
bool | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement
checkpoint | Concrete cover Check - minimum 30mm
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
date | Pour Date
checkpoint | CONCRETE TEST Procedure
checkpoint | APPROVAL FROM ENGINEER
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged
dropdown | Finish: | Fine finish,Broom finish
checkpoint | Curing Procedure arranged