## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
2cc5882c-84cb-415b-b69e-b0fe91690b2c | checklist | 02.01 - Traffic Management | itp | 02.01 - Traffic Management
0aaa63a2-f47b-4b46-93f5-4f99c151466c | section | Details
f73782f1-95c0-4519-a701-7ab31bf4a2af | checkpoint | The Contractor's Nominated Traffic Officer submitted to the Administrator and meets the requirements as specified
d2e1762e-d5e3-5155-adc3-1b709f6a58d4 | note | Acceptance Criteria and Frequency (Project Specific) - Accreditation Supplied to Administrator
840fc706-86cf-5662-9ed4-07a220c921c4 | note | Check Item - Check Item
49a83c19-a6b0-5028-84ff-90d511a3bf4b | note | Reference - MRTS02 Cl. 5.2
db43b244-e01b-4a50-893c-4e4c79981afa | checkpoint | No traffic rearrangements shall be carried out until after the Administrator has advised the Contractor that the submitted, and amended as directed, TMP is approved and suitable for use.
7a8990e5-d46d-564d-87e1-10fe87cfceab | note | Acceptance Criteria and Frequency (Project Specific) - Approval via Contract Notice - Per NTO
311590c8-6ea1-5fc6-88b8-b293d8950ea5 | note | Check Item - Hold Point 1
e714963d-7a67-5272-9fc5-359d6cf7c5d1 | note | Reference - MRTS02 Cl. 5.3
aa4f13ae-8cb4-430d-b2e6-8b8a98b9000e | signoff | Hold Point
d6db6649-df82-4943-880b-2d64ea5eeb53 | checkpoint | All traffic control devices inspected and records kept in accordance with the specification
7194b092-d7d7-5b3b-8195-0e77fa81d0b3 | note | Acceptance Criteria and Frequency (Project Specific) - Site Records - Daily
ca834e78-79a7-5e5f-b2cf-ba464a88d2ac | note | Check Item - Check Item
fd305a1b-c53c-52a7-8ba5-7a940ea924cc | note | Reference - MRTS02 Cl. 5.6.4
ccf513cd-a3e8-41ac-9411-a9e7161cf12d | checkpoint | In the event of a traffic crash/incident within the site, the Contractor shall record the date and take time and date stamped photographs of the signs/devices in the vicinity of the crash.
11a23fd7-8f5b-5102-86b4-b078460d6e6e | note | Acceptance Criteria and Frequency (Project Specific) - Incident Report - Per incident
6289d6b0-0d66-5019-8db9-f65bf2b0c976 | note | Check Item - Check Item
0b07e35a-77ee-5ec4-8f77-1eb34c63c362 | note | Reference - MRTS02 Cl. 5.6.5
7ad4d3f4-ed19-4f66-b960-fdd032622ac1 | checkpoint | All TGS's prepared by a suitably qualified person and submitted to the Administrator for review and shall be accompanied with a specific risk assessment, as required. Innovations, alternatives and departures from standards shall be certified by a RPEQ.
60c60f2c-dd25-59b6-a305-b0587e8f1c39 | note | Acceptance Criteria and Frequency (Project Specific) - TMD sign off of TGS and, RPEQ Risk Assessment as required
a08a0d7a-0897-5e6c-a50f-92f08e07f0c7 | note | Check Item - Hold Point 2
befdf6a8-b58d-5d90-aed9-3df67791003a | note | Reference - MRTS02 Cl. 6.2
8e0366fc-cc65-44a2-9fd5-4c5851f375a6 | signoff | Hold Point
e4514f04-2165-4195-877c-b4ae3522bf30 | checkpoint | The Traffic Management Inspection report to the Contractor for action, together with documentation of any actions taken in regard to findings.
67a63be3-e016-5294-b4c2-b26f619a151b | note | Acceptance Criteria and Frequency (Project Specific) - Submission of report to Administrator - Per inspection
e7a2d621-1fb7-5ef6-85ca-f5db1e473652 | note | Check Item - Milestone
c03d96f5-def4-53d0-9b60-e84b630339cf | note | Reference - MRTS02 Cl. 7.5
e76580a1-476a-41f3-9816-063a8fe1356c | checkpoint | Final Verification
1ffc6dad-80aa-5df0-ad9a-1276820db32c | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
0f225e7f-e4ae-5fe9-8593-db35fbb0e938 | textbox | Print Name:
a7fb97f4-689f-533c-94d7-a45d48549f5c | date | Date:
93138be1-a604-597c-93fb-e8302a9ecc3f | note | Project Manager Verify that the Above has been Constructed according to Specification
17272619-1361-50df-9b3d-cfab75cdbe32 | textbox | Print Name:
5b3a0bc8-0455-58c9-80d1-692c0d83e906 | date | Date:
29821b5e-8def-4aea-9824-1e4c152dabc9 | signoff | Signature
3a3eda14-af0e-4ed7-80e2-027201fcfbe8 | section | Final Sign Offs (to be completed at closure of Lot)
66908d1a-5af4-40c0-9428-b78b79f3320a | checkpoint | Agreed Quantities
fa50f812-6868-4fb8-9bdf-63a321e1a84d | signoff | Agreed Quantities Sign Off
6184102a-2d98-42ff-beb6-d7bbe137170d | checkpoint | Closure of Lot
c364635e-2c40-4a03-96f8-45aad2d1c5da | signoff | Closure of Lot Sign Off
b28e5f88-15c5-4166-b3d8-cb1da573baf3 | checklist | 03.09 - Removal of Existing Drainage Structures and Concrete Slabs | itp | 03.09 - Removal of Existing Drainage Structures and Concrete Slabs
41048ca1-6002-4c72-84fd-62d944da87c2 | section | Details
457038a6-3c54-4880-a74f-4e0cfdb17229 | checkpoint | Culverts and culvert end structures shall be removed or demolished where specified in the drawings.
b353b56e-c600-5341-ae28-b817d75d721e | note | Acceptance Criteria and Frequency (Project Specific) - Culvert Removal - Per Culvert
d0f8d0ab-d1fb-512b-b7c8-c0ee210bc22f | note | Check Item - Check Item
8a44955f-ebc1-522e-af47-9767177efb88 | note | Reference - MRTS03 Cl 9.2
e86d1b9e-866c-4b58-867a-47f07c5ead21 | checkpoint | If existing culvert components are to be removed and re-used, they shall be removed and stacked in a manner which avoids damaging the components.
7efaa550-2f1c-5a3e-8fea-8a187a50053d | note | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Culvert
27c2ce4b-193b-5a4a-92df-cc211222a424 | note | Check Item - Check Item
1abc9e71-c37b-5590-8557-a19c4693cb2f | note | Reference - MRTS03 Cl 9.2
8c569a81-6b54-4d0d-a1b3-03435e7ca566 | checkpoint | Removed components which are not to be salvaged, nor reused, shall be removed from the Site and disposed.
616c3e48-1e12-5fa5-a36b-15fc443add9a | note | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Culvert
cabc993e-59e3-55d0-8d72-e731eb2cdc36 | note | Check Item - Check Item
8b0158ac-f1e4-5712-b386-68b1171b54da | note | Reference - MRTS03 Cl 9.2
2e77bf03-1cdd-4b11-a0d4-a48e093f457b | checkpoint | Excavations carried out and the void left by the removed culvert or end structure shall be backfilled to reinstate the area to a safe and free draining state.
5e902134-d917-5f45-9f48-4dc847da4d4a | note | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Culvert
b3ee1cf4-1084-5649-9c2c-e6259c03658b | note | Check Item - Check Item
684adb27-c9f1-52d4-8526-124cf6fbccf6 | note | Reference - MRTS03 Cl 9.2
5f30b46a-2877-440e-b03c-1ba3b478efae | checkpoint | Existing kerbs, channels, kerbs and channels, kerb crossings and concrete slabs shall be removed or demolished where specified in the drawings.
21c22537-31c3-5787-ba11-6272c52efd98 | note | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Kerb
1640c5f5-053d-5f74-b596-b7244414440b | note | Check Item - Check Item
3f8efe6b-fd76-5a5a-8698-cdf3219b7cc7 | note | Reference - MRTS03 Cl 9.4
f0d307a8-8836-4bb5-8c34-7931e4061a25 | checkpoint | Any Kerb and Channel or concrete slab to be removed is saw cut at removal extents or removed to existing joint (or removed in its entirety) where specified in the drawings and no damage shall occur to adjacent work
c72493a9-ee62-50d4-b13d-69632d874f6d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
96bde0d0-873d-5149-a604-35fbcbef9a04 | note | Check Item - Check Item
9f586a4a-2dd3-5907-8f9d-15326bb7a949 | note | Reference - MRTS03 Cl. 9.4
7095a94b-585e-4bf7-bd00-9bfc3fcf6033 | checkpoint | Kerb excavations shall be backfilled to flush with the surrounding area.
6a23b262-f610-5d50-9f9c-eea02875fb4b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
36a5fec5-9502-5153-9fdc-d54a45aff0ed | note | Check Item - Check Item
e8c24fce-6b45-58d7-ac5c-7498ffb97981 | note | Reference - MRTS03 Cl. 9.4
e214dfdc-59f0-49c6-afac-5abe1d43205e | checkpoint | Final Verification
0dffd488-a5f5-5de2-8552-802d78f1669f | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
89447a10-f99c-5942-a82d-1e13ea029bf1 | textbox | Print Name:
10d8bbc4-81a7-5faa-b4fa-033e488e0256 | date | Date:
edebca7b-69aa-5725-85e1-e347cb4a9c40 | textbox | Print Name:
6d67667f-2f5f-5e8a-8854-9850dbcbded5 | date | Date:
6c52e4c2-4a60-4e00-96a3-8f240f542ec8 | signoff | Signature
a9f8c4bc-53e4-4e1c-b346-fc921868a4ad | section | Final Sign Offs (to be completed at closure of Lot)
3df473a1-55f1-449a-9c02-7a1b9595bde5 | checkpoint | Agreed Quantities
756f5190-6d24-4e3b-a76e-82f283569f9b | signoff | Agreed Quantities Sign Off
379fdd5f-be3c-4276-a856-4083537deca6 | checkpoint | Closure of Lot
22132607-2de0-4ebe-8b66-a69b61fb7f71 | signoff | Closure of Lot Sign Off
d60018e4-af20-43c6-b24e-f4d4058b9b1a | checklist | 03.10 - Supply and Installation of Precast Concrete Culverts | itp | 03.10 - Supply and Installation of Precast Concrete Culverts
edc695db-749c-4814-87b2-5d9b84de850c | section | Details
543d1a05-5245-4869-8e54-fad8f2dab7be | checkpoint | Once the initial set out is complete the Administrator will determine the design appropriateness of the set out with regard to the actual site conditions
8f1e8bfc-3c3f-5289-825f-483efe103fbe | note | Acceptance Criteria and Frequency (Project Specific) - Visual
bd5ac214-dbec-555c-980f-c27881986d06 | note | Check Item - Hold Point 1
6813f608-1860-5afc-9a33-72282429ef38 | note | Reference - MRTS01 Cl8
7d321e35-a614-4be8-bf2e-c89790ac54f9 | signoff | Administrator Sign Off
96aff8ea-fa50-4625-b509-43c5cce42aea | checkpoint | Maximum Lot Size - 1 Culvert
053cc937-5aab-53dc-a66a-826eb613b1b8 | note | Acceptance Criteria and Frequency (Project Specific) - Lot size </= 1 Culvert - Per lot
96d4b683-80b3-50c8-bf7a-5efd6bc5f3e9 | note | Check Item - Check Item
28a457d5-fafb-540a-a2ae-6ece450485a3 | note | Reference - MRTS04 Table A.2
e55e2639-f3d4-4c7a-8776-b6c1fa360b2c | checkpoint | Concrete Pipe culvert components comply with MRTS25/26, FRCP with Slotted Drain Insert Complies with MRTS26
fe0450e1-e941-5868-b2b0-34994b514541 | note | Acceptance Criteria and Frequency (Project Specific) - Manufacture and Test Certificates
a0dc30f8-b23b-5364-967f-729a7c27f4c4 | note | Check Item - Check Item
9f3cef73-ffb9-5136-89ba-9488833d86d0 | note | Reference - MRTS03 Cl10.2
1fe3b1e1-02ca-42eb-aafe-f261f43ff6fc | checkpoint | All pipes of diameter 800 mm or less shall have spigot and socket joints with rubber sealing rings. Joints for other sizes shall be as specified on the drawings.
5ca18472-060a-5ee3-8a61-68b7e4dab24c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
067a4a8e-1423-501c-96a8-4430ac0da7c9 | note | Check Item - Check Item
3f7e9209-6863-520c-86e2-d13c711cee99 | note | Reference - MRTS03 Cl10.2
0e9c6f89-70e0-4464-a6c1-a362792223ff | checkpoint | Component size, wall thickness and class is as specified in the drawings
116e8d00-3b39-5373-abbc-547f40d24b6c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9a6e8210-7687-5062-9ea0-49909fb4b406 | note | Check Item - Check Item
458f601d-b3f8-58cd-be78-9de2facd4f76 | note | Reference - MRTS03 Cl10.2
4b685b01-9c8b-43ea-8545-ea8bcd6f7189 | checkpoint | Bandage Covers are a Proprietary Product, either: Synthetic or Rubber Band, samples inspected by administrator
f3d8536f-e77b-55d8-ba94-251e92f10ee6 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1f808034-428a-5162-b44a-6a3316743474 | note | Check Item - Hold Point 1
0949d835-ce49-52d6-8fe0-4e8cddba2630 | note | Reference - MRTS03 Cl11.2
b66fc274-8a5c-463d-8f9a-48a162cb161e | signoff | Hold Point
9d20a8a9-fcb7-4086-a11d-74cb34a2c2ad | checkpoint | Culvert Construction Procedures to be accepted prior to commencement of Installation
379961d8-8510-534a-9c1a-77d49b0150ae | note | Acceptance Criteria and Frequency (Project Specific) - Visual
01251c35-e310-53b0-804d-cad75e0551aa | note | Check Item - Hold Point 2
29ed85fc-aec6-5480-84e0-1f8702beac39 | note | Reference - MRTS03 Cl11.3.1
99e3c298-e149-4cec-a3f6-eaebd052a914 | signoff | Hold Point
3c3b7294-2cf6-4bf9-baa2-b3cd8d757fab | checkpoint | Load testing of non standard pipes ordered for specific projects shall be a witness point
647079b8-0618-5e5f-9870-c6a05a781539 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
7d059952-8f49-5708-b6d6-52558b55725b | note | Check Item - Witness Point
e756cda0-3528-502e-a468-52c4ba4f4037 | note | Reference - Annexure MRTS26.1 Cl 2
59a8b3ca-9c5d-47b5-a40c-ec7b2969a24f | section | Excavation
81647aff-24f0-4caf-a182-ab23b1c7d0ca | checkpoint | Excavations shall be carried out in accordance with Clause 13 of MRTS04 General Earth works
6b47eee6-4c0b-5a99-8e9d-909524749f22 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
eb14f505-c315-59fe-a01b-0b05074586ec | note | Check Item - Check Item
10500a94-dd00-5d64-9311-61294998664c | note | Reference - MRTS03 Cl.11.3.1
6c68891e-8f2a-4f83-890e-9f843f86d0b1 | checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or potentially unsuitable Material is encountered on site the contactor shall, before proceding with removal, shall notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl. 9.3 and CL.11.3
21d16031-d018-5844-94e3-f797ba274e8b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
05e81834-446a-5918-8c91-c691a05c411b | note | Check Item - Hold Point 4
141a281c-83a1-5cee-a699-078e81656b1a | note | Reference - MRTS04 Cl. 9.4
269872d0-3742-460a-91f4-ae37bcdd3f6c | signoff | Hold Point
758d7a09-cea3-41ec-ad0f-47d2b85e5072 | checkpoint | Bottom of excavation compaction tested. 0 - 150mm below foundation -RDD Q140A
83be6440-2b50-5a96-bc6d-79fd4245bb6d | note | Acceptance Criteria and Frequency (Project Specific) - Cl 15, Table 15.3(b), CV 95% minimum (1 tests / 50m2 - min 2 / lot)
0f6689c1-52bf-5d0f-82eb-b579c897a15f | note | Check Item - Test results
491ffe82-042c-5994-b5fb-ab2cba1dc22a | note | Reference - MRTS04 Table A.2
a5b90fe6-9840-4c8f-9de0-152ef55f1fc1 | section | Culvert Installation
aedf7136-6029-4e84-b729-214067b8b0d4 | checkpoint | Components are assembled as per manufaturers specifications, and if possible, contruction commenced at outlet
45ba52e7-d629-5760-90b5-db93037ef789 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
dd424ac5-c2e4-58c5-974a-f8578bee2a3d | note | Check Item - Check Item
13e06544-40a5-5117-ad77-87bef08dc553 | note | Reference - MRTS03 Cl11.3.3, Cl11.3.4
18eee509-f557-4d73-be42-4939a2a44220 | checkpoint | Pipes shall be placed with their external grooved ends or spigot ends facing the culvert outlet
60d76056-8381-5a17-9fad-daf58ef602de | note | Acceptance Criteria and Frequency (Project Specific) - Visual
624118b7-e266-5331-87ee-0816bfd13e03 | note | Check Item - Check Item
c50abe98-fec0-5d91-9e6b-a4da6e0497d9 | note | Reference - MRTS03 Cl11.3.5
eb56dcfc-2a50-45f3-b9ac-431aaac326b5 | checkpoint | The pipes shall be laid with the lifting hole or "TOP" marking uppermost. Lifting holes shall be plugged or otherwise closed off in accordance with the manufacturer’s instructions after the pipe is installed.
ebda2607-9e4d-5065-8da4-a8f90f4ddde0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6057080b-ccdb-54c9-8444-99abe7f8c3ee | note | Check Item - Check Item
31a6ca2b-130a-5489-9083-716b8012f22f | note | Reference - MRTS03 Cl11.3.5
ccdef04c-0c71-46df-9625-121b8c8264ba | checkpoint | Placed with external groove or spigot end facing outlet with minimum of 50mm bedding material
117c1a4d-2d64-5242-85cd-eb9d5a02d8a7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
651b00f4-217f-5fc4-891c-78f9599d826a | note | Check Item - Check Item
594de0f3-fde7-5b47-a7ea-e2f9484ea73d | note | Reference - MRTS03 Cl11.3.5
de5a6704-7ef9-4f38-a55a-54d632290e80 | checkpoint | The horizontal alignment of culverts shall not vary from the location specified in the Drawings by more than ± 100 mm
df64d91a-6cd5-599d-acd3-43892a606ad6 | note | Acceptance Criteria and Frequency (Project Specific) - ± 100mm (All points shown on drawings - min 1 per 20m or 2 points)
e807a2b9-5e66-537d-b153-9d5f9220e63f | note | Check Item - Survey Results
617c1d14-315f-5833-8c6f-b75eb7447e62 | note | Reference - MRTS03 Cl.8.2
ab6f9865-aecf-4da6-8f7d-5aaa545b4ae9 | checkpoint | The invert heights of culverts shall not vary from those specified by more than ± 10 mm and nowhere shall the grades of culverts depart from those specified by more than 1%
77e18532-9f50-536b-8de2-ed42aa7706d3 | note | Acceptance Criteria and Frequency (Project Specific) - ± 10mm, ± 1% grade (All points shown on drawings - min 1 per 20m or 2 points)
838206f6-1922-5db1-be82-ae6a72416f00 | note | Check Item - Survey Results
0062b748-b89a-5bc2-a054-909eafb66111 | note | Reference - MRTS03 Cl.8.3
96bb1269-1ca7-4450-b10e-49e6be645be1 | section | FRCP with Slotted Drain Installation
cc0239cb-2034-4afb-8f4e-9ae3918fde79 | checkpoint | Fibre-reinforced concrete pipes shall be designed for installation in accordance with AS/NZS 3725. Construction load cases shall be considered in accordance with Clause 5.5.1. Designs already completed to AS 5100.2 shall be deemed to comply with these requirements.
909c8a4a-2526-5113-b1d4-e9e55286b570 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
64c1752f-eaeb-5b94-b9c7-42afc4962bed | note | Check Item - Check Item
2228e213-c338-56c1-99a9-92f8525f440d | note | Reference - MRTS26.1 Cl 2, MRTS26 5.5
e6ce583d-fce8-4bec-8dfa-e5011e582b16 | checkpoint | FRCP: The maximum angle of deflection of joints for pipes is two degrees
bea31d96-bb58-5310-8327-81105175904d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
056c7066-c5c3-50c3-8791-b5e9b1ba08ab | note | Check Item - Check Item
d20ac042-d620-52fd-8dac-cd41ab30ea27 | note | Reference - MRTS26.1 Cl 2, MRTS26 11
bdfe0085-77d4-40c8-aea4-1f7cd424cb79 | checkpoint | For the specified pipe class and size, the contractor shall progressively backfill the pipe using the fill depth and construction equipment permissible in Table B1 of AS/NZS 3725.
71105c02-17c7-518f-9987-6646bf69acb5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
270e5fbc-7e08-5b8b-a17f-fb907bc1fdbd | note | Check Item - Check Item
95c59b9b-77dd-5ec5-a49d-bd3135cf1d55 | note | Reference - MRTS26.1 Cl 2, MRTS26 11
9a5d7f65-f0d2-4515-8c60-d2cd3cfade0a | section | Backfill
de73223f-32cb-4782-b25e-c34874825b08 | checkpoint | Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met and notice of such works provided to the Administrator
aeae6fd3-1aa3-5ad4-a70c-e28e2feacb66 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9c016308-684a-50f1-bb95-674268ca39db | note | Check Item - Hold Point 4
3a847cca-da5d-5eee-bbde-2721aafb54bb | note | Reference - MRTS03 11.3.10
a506673e-6da8-4e4c-a2e9-5cacacf16b63 | signoff | Hold Point
7eee1930-c427-4bde-88f0-108f5f8fe577 | checkpoint | Backfill material shall not be placed until culverts, structures, pipes, conduits, pits, etc have been completed and inspected, and any specified curing periods have elapsed.
dedd4023-d31b-56a2-94bb-0ffe911b75a2 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
97d4ea01-ddab-5f49-b118-58b55cff4cd9 | note | Check Item - Hold Point 14
b8f6f3e9-1a6a-50b2-8113-690a7d4fc936 | note | Reference - MRTS04 Cl.19.3.3
19401ab5-27b8-4ce4-9f73-7a0ea15c9368 | signoff | Hold Point
5774b013-26bd-409b-9fb6-64b1539333db | checkpoint | Overlay material within 300 mm of the structure, culvert, pipe, etc shall be general back fill Class A1, A2 or B material conforming to MRTS04 Cl.19.2.2 excep 100% material shall pass 25.0mm test sieve.
bfe64fb3-32c2-5937-bebf-d3aa3679ad81 | note | Acceptance Criteria and Frequency (Project Specific) - Class A1:
3ff4fac3-2e6b-50ff-9d71-eed1681ae62b | note | ○ Class A2:
598ef8c7-474f-5223-8a52-fb85ddedbc33 | note | ○ Class B:
657884b1-20c2-57ee-b1d7-3fe3d1e9a724 | note | ○ Except: 100% passing 25mm
f3cf1de7-5088-5bb6-8bfe-7cc67cedb53f | note | Check Item - Witness Point
942c58c2-25e5-55b9-9804-5f2d9fc41a42 | note | Reference - MRTS04 19.3.1, 19.2.2 Table 14.2.2
8e4d6446-9142-44e1-966d-53d21172eca1 | checkpoint | Compaction - Q142A, Q141B
19c77b35-2c66-5a9a-9642-b3e91768e8c3 | note | Acceptance Criteria and Frequency (Project Specific) - Top 300mm below Subgrade Level ≥97%
82ac86f2-3059-50e9-aa6a-c62892709be2 | note | ○ Greater than 300mm below Subgrade Level ≥95% (1 test / 50m3, min 1 per lot)
28ad9cb1-1e76-56a1-ae69-b7ced8f377ec | note | Check Item - Test results
59df0482-e6aa-5fff-ae39-5591f69bebeb | note | Reference - MRTS04 Table 15.3(b)
78447d2d-fc6e-4375-8108-0defd403dfff | checkpoint | Moisture content within ranges specified Rainfall Zone: HIGH
eeaabf81-476e-56d6-8020-82704ddf96b1 | note | Acceptance Criteria and Frequency (Project Specific) - Class A1/A2: 70-100%
5a8bcfcf-2200-5509-adc1-f81babb7b61d | note | ○ Class B: 80-110%
58fb7c42-7175-55de-b1be-91c3dd0713ad | note | Check Item - Test results
1090c314-996d-55ed-9f07-7c53a12cc80e | note | Reference - MRTS04 Table 15.3(c)
be6c29d3-98ce-4685-b386-c7760d25ce01 | section | Completion
78bb4f4f-67d7-4459-8659-17b6edfdcc71 | checkpoint | CCTV inspection undertaken, report submitted and accepted by administrator. Visual inspection may be approved by the Administrator in lieu of CCTV inspection.
6a2b01d6-4250-564c-bfa7-a396afa1aa21 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f036143d-4c29-5c2f-af8d-24ec01e316c3 | note | Check Item - Hold Point 3
2e69dae5-a52b-5df6-9441-2785b72fd854 | note | Reference - MRTS03 Cl11.3.5
1eeffe8d-1f3e-42b0-befb-6b1ed53c6ee2 | signoff | Hold Point
5749de53-0d49-403f-878a-0810e772089d | checkpoint | Final Verification
eb3dbced-924b-565d-9165-861bbc8c6ecf | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
f952e1f4-2c90-5645-8233-e6f544c32d6a | textbox | Print Name:
70bff043-75a2-5e32-bf82-098770f7fafc | date | Date:
90d28b00-19c1-5433-98c9-7e1772f5fb79 | note | Project Manager Verify that the Above has been Constructed according to Specification
f9ce1477-9a43-5e27-bf3c-3f5580e3d442 | textbox | Print Name:
3f53bcbf-a008-5dc6-9ec7-c5bc60c83528 | date | Date:
1c53b000-4aa9-4068-aa40-f4fb2bedf1ac | signoff | Signature
e7b28b8d-56e1-46e3-9594-c6441b73e1dd | section | Final Sign Offs (to be completed at closure of Lot)
f7746652-e49b-4056-a294-2c5550b3a502 | checkpoint | Agreed Quantities
055e0678-a7c2-4451-a0f9-65393c1fa47c | signoff | Agreed Quantities Sign Off
634d3918-1371-43a5-85e5-8a1b2f155990 | checkpoint | Closure of Lot
b8b6f77b-83ee-4a62-a95a-09da159bff1d | signoff | Closure of Lot Sign Off
2223e847-6c61-4feb-8be1-1693f7a97ad0 | checklist | 03.11 - Installation of Culvert Components and Structures - Precast or In-Situ | itp | 03.11 - Installation of Culvert Components and Structures - Precast or In-Situ
b69c460b-73a7-424b-bdb4-0b4deadbae15 | section | Details
95a2425d-5d2f-448d-8ca4-b8051c23947f | checkpoint | Once the initial set out is complete the Administrator will determine the design appropriateness of the set out with regard to the actual site conditions
ab7bd622-f514-5d9c-90c2-b03767287be3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f48a7de0-8bb3-5b5a-bfb6-bdd2bdbb484b | note | Check Item - Hold Point 1
1246932d-63b2-5aba-a12b-c05171542f34 | note | Reference - MRTS01 Cl8
7523aaec-d7cd-45cc-a780-778f176da79c | signoff | Administrator Sign Off
293c3191-5b74-4587-b7cd-8da022cd719d | checkpoint | Maximum Lot Size - 1 Culvert
d2bef293-d61c-50be-ad49-f4679a6064b3 | note | Acceptance Criteria and Frequency (Project Specific) - Lot size </= 1 Culvert - Per lot
38b62273-d7f9-543f-8f6d-5e877d927f40 | note | Check Item - Check Item
33f20396-a47d-54f3-bf5d-c47b386459b9 | note | Reference - MRTS04 Table A.2
91a0479f-cf2f-418f-8335-7ae9b2787cdb | checkpoint | Culvert Construction Procedures accept prior to commencement of Installation
ca121c07-a963-5583-b7f5-e218066d2a0b | note | Acceptance Criteria and Frequency (Project Specific) - Administrator Approval - Per Project
c3038458-88a9-5db5-b42a-f7a1499891d9 | note | Check Item - Hold Point 2
f8bf377f-efa9-5b4c-9cba-71b85b6b12fc | note | Reference - MRTS03 Cl 11.3.1
43f345e5-766e-4d10-83f1-c1835c443ebc | signoff | Hold Point
96d8da73-2bc2-46d5-874b-865a883268ac | section | Excavation
4efb6554-969c-436e-aecc-7ee97a6d05c6 | checkpoint | Excavations shall be carried out in accordance with Clause 13 of MRTS04 General Earthworks.
a493ec26-0d4c-53e7-be6c-0f9b607bfbb0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual - Per lot
89d358c5-3920-5645-a564-e94638c3b56a | note | Check Item - Check Item
922b95a6-62a7-523d-86d2-a733614ed741 | note | Reference - MRTS03 Cl 12.3.1
fa3852f0-2f29-459e-8ec1-ec1d215683e4 | checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or potentially unsuitable Material is encountered on site the contactor shall, before proceding with removal, shall notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl. 9.2 and CL.11
47ed0c94-1f5c-5f71-bb23-f3901f8d6d48 | textbox | Reference Unsuitable Lot No. :
d644e436-f0f1-5d74-9e54-df5cdbf86334 | note | Acceptance Criteria and Frequency (Project Specific) - Visual - Per lot
b7cade95-54f0-5283-9830-4a479f52d44b | note | Check Item - Hold Point 4
822efda0-1279-534a-a409-166de5b3c9d1 | note | Reference - MRTS04 Cl 9.4
bdb0ac6f-921b-47d1-929c-c24c4a4efee9 | signoff | Hold Point
f5e34e3f-a662-44a3-8315-d1da72ea5607 | checkpoint | Bottom of excavation compaction tested. 0 - 150mm below foundation - AS 1289.5.4.1 or AS1289.5.7.1
98fe33f6-55b5-5f00-9016-79d9e226d3b8 | note | Acceptance Criteria and Frequency (Project Specific) - Cl 15, Table 15.3(b)
a7d7100b-0fb6-5320-b304-2eaf746c45d5 | note | ○ CV 95% minimum (1 tests / 50m2 - min 2 / lot)
3aca3eca-12a0-5f14-8557-f6f6e63dad12 | note | Check Item - Test results
c892eb99-8509-5312-b92a-30b3abf461e4 | note | Reference - MRTS04 Table A.2
e226b779-8c58-47fb-b4e3-943985c18cb0 | section | Installation
3c622348-aff6-4788-80cc-9a86cd4c92d5 | checkpoint | Cast In Situ material: In accordance with MRTS03 Cl.6.1, MRTS 70 & MRTS71
a478407c-3fb0-54b8-aacc-4cff309ba6e6 | note | Acceptance Criteria and Frequency (Project Specific) - MRTS03
c493e606-6d66-551d-9b8f-be4dfb9965f5 | note | ○ Cl.15: End Structures
7f9fd1f3-e5ca-5fea-90a6-e3aa64e89cda | note | ○ Cl.21: Gullies
35a88e25-babb-5d11-8aad-c80d4809a770 | note | ○ Cl.21: Access Chambers
884900f0-bac2-50c2-8d06-0810ae782d5c | note | Check Item - Check Item
eb9e1f91-903f-5406-b380-c8e677e25856 | note | Reference - MRTS03 Cl.6.1
65be6c1b-ef3e-44cc-a98c-547778026b13 | checkpoint | Precast: Installed in accordance with MRTS03 - Components shall be laid on a foundation bedding which provides continuous even support to the structures.
cca5c89b-71e7-51f7-a1d9-67b6daf4d521 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3b393fa4-983f-5de2-a3e6-1f2d898ecc16 | note | ○ Cl.19: Precast End Structures
f90a2d33-525f-57e5-96cf-9fff5ff5a36d | note | ○ Cl.21: Precast Gullies
cdc6ae48-8d15-502a-be99-16e8d72f93cf | note | ○ Cl.21.5.1 Precast Access Chamber
61c89b62-043c-58e2-8492-2ada9ca96c8c | note | Check Item - Check Item
89edf5a1-a0ab-5e45-b560-e41f7b2e06c5 | note | Reference - MRTS03
cf50c872-288f-5c31-bb9f-0ea4e001f864 | note | ○ Cl. 16
1b23088b-6c47-5d67-8393-7172671f3407 | note | ○ Cl. 21
80979e20-4f38-51a4-b5d8-a872f3b403e7 | note | ○ Cl. 21.5.1
b567fb59-f323-448c-badf-511f1f75627c | checkpoint | Precast: Culverts shall be joined to shafts/pits to form watertight joints using cement mortar. Cement mortar shall be used within one hour of mixing and shall not be re-tempered. The joints shall be finished to given smooth surfaces which are uniform with the surfaces of the shafts.
3430cb37-83ef-5afc-a8a5-8cc076bc9977 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
800cac85-4224-5ce8-a66d-aaf8bc3181f4 | note | Check Item - Check Item
6e9eef64-8289-5a89-aa20-1049b28eb3f6 | note | Reference - MRTS03 Cl. 21.3
dfaa4058-eef2-4cad-9aa6-219d62764428 | section | Tolerances
7d3c0253-be18-4095-85d8-d5adbb323067 | checkpoint | Gullies/Chambers: Vertical Tolerances: Invert heights shall not vary from those specified by the Drawings by more than ± 50 mm
8a850430-d178-5dc8-b1d2-34f61f26aefd | note | Acceptance Criteria and Frequency (Project Specific) - ±50mm (All points specified on drawings)
c940c91f-7bdb-58f6-aca8-e529eef468aa | note | Check Item - Survey Results
04b13825-791e-549f-a170-c1ad4c3d3a70 | note | Reference - MRTS03 Cl.21.4.2
fb4854d8-5c50-4a8c-90b7-ed8e112e216e | checkpoint | Gullies/Chambers: Vertical Tolerances: The heights of the tops of back-units, grates and frames shall not vary from those described in the Drawings by more than ± 10 mm
5673cc54-89f1-58d0-832d-1c1dbfbd0d54 | note | Acceptance Criteria and Frequency (Project Specific) - ±10mm (All points specified on drawings)
ef81275d-babf-51fa-bc40-87b3d7c56478 | note | Check Item - Survey Results
1aee99e6-2f32-5107-853d-ad44122a3d0a | note | Reference - MRTS03 Cl.21.4.2
9115132c-3b4f-4f41-afec-19902eaa5051 | checkpoint | Horizontal tolerances: Gullies: shall not vary from those specified in the Drawings by more than ± 100 mm in the direction of the construction centre line and ± 50 mm in the direction at right angles to the construction centre line. Access Chambers: shall not vary from those specified in the Drawings by more than ±100mm
2db82d9d-dde8-5096-8f59-b33775849d3e | note | Acceptance Criteria and Frequency (Project Specific) - Gullies:
7ae75b0d-7505-5b7e-9723-9063b4b2b25f | note | ○ ±100mm in road direction
c9e6fd66-4687-5a46-97cb-bc4e6252c9bd | note | ○ ±50mm perpendicular to road
88a8f2f1-f02d-5d85-a726-4dc76c79a67f | note | Access Chambers:
390c1a0f-273e-5c31-aca0-492a632de92a | note | ○ ±100mm (All points specified on drawings)
1bdc3cd0-1021-5a1e-9102-ef548406d75c | note | Check Item - Survey Results
72f6fadb-2318-52c0-aea4-0f98cceecdb5 | note | Reference - MRTS03 Cl.21.4.1
9d693f3f-d3c4-4fd1-a6bb-737ed667b88c | checkpoint | Gullies/Chambers: join neatly to existing drainage structures, do not pond water unnecessarily and are at heights compatible with other adjacent structures.
dc6788a0-ea2a-56bd-96f3-544c6054c45c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f25cdfff-adf4-54ee-87f0-5d194d4ae2ab | note | Check Item - Check Item
4331d280-bfbf-5112-90d3-bcb1c6b2bf6c | note | Reference - MRTS03 Cl.21.4.2
290096fa-3e1b-4ab3-86c4-96049e7f73c5 | checkpoint | Gullies/Chambers: Grates on gullies or Concrete top slabs on precast concrete access chambers shall not be installed until all the surveying requirements have been met and notice of such works provided to the Administrator
75aa627b-f4b8-5699-b5c0-4fca1393344f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c7f26026-aad1-5168-ad65-c39cf9e408a6 | note | Check Item - Hold Point 5, Hold Point 6
c0bc4a07-0017-5766-8b99-0d37b5fd6d7d | note | Reference - MRTS03 Cl.21.3
348b4aaa-c002-4271-afbd-c6c7a53918ab | signoff | Hold Point
69b077da-cec1-4694-b801-2d50154c4278 | section | Backfill
bfe0fdcf-84c6-49a9-8063-44d766789912 | checkpoint | Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met and notice of such works provided to the Administrator
49eed5f1-7da9-50f7-adeb-e9bfe9dd9ad3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
94c43eb6-139a-5585-8bb1-a4e86c829833 | note | Check Item - Hold Point 4
1763df09-c45c-582d-a468-cdb8081259a7 | note | Reference - MRTS03 11.3.10
ded6a73a-69f8-4847-aa78-02c52d717758 | signoff | Hold Point
2f04afa9-7d07-4af9-8ab1-084f4702c399 | checkpoint | Prior to incorporating any Backfill material into the Works, the Contractor shall submit stockpile or source tests results as specified in Appendix A which demonstrate the source meets the specified material requirements
b53f375e-0a39-5ebb-ae2a-2e53eb3658df | note | Acceptance Criteria and Frequency (Project Specific) - Quarry Material Test Results
96ca09a7-7967-50f9-8056-ce30e5c9247f | note | Check Item - Hold Point 8
d2e4cd7c-15a6-5c98-a5c2-2382ac83d3a7 | note | Reference - MRTS04 Cl. 14.2.1
164953e1-9ccb-4583-b3b8-49f80a14bb0d | signoff | Hold Point
e7c0e0e2-470d-42e2-8d21-929bc2a19dc1 | checkpoint | Material for backfill shall be as shown on the drawings or as specified elsewhere in the ContractEarth Backfill Material shall comply with the requirements of Earth Fill Material Class A1, Class A2 or Class B specified in Clause 14.2.2 except that 100% of the material shall pass 25.0 mm test sieve.
d48953a5-91f4-577f-a7eb-40a680de2f60 | note | Acceptance Criteria and Frequency (Project Specific) - Test Results
d96d4662-f470-596c-bb76-22fbd58d8d0d | note | Check Item - Witness Point 5
4f8f5256-d4a3-5f45-9fea-a47011b265be | note | Reference - MRTS04 Cl. 19.3.1
7a735ad0-c8ad-4eb2-85be-3570de831167 | checkpoint | Backfill material shall not be placed until culverts, structures, pipes, conduits, pits, and so on have been completed and inspected, and any specified curing periods have elapsed.
1b4f136e-9b2c-5b63-a010-4120a0e55e33 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5f02f401-aeb9-5f83-a1f6-0e82eda2b7c6 | note | Check Item - Hold Point 14
6bd1bb4c-1d9f-5734-a033-033b8770df51 | note | Reference - MRTS04 Cl.19.3.3
0c58fc12-37ee-4530-ba08-df0c718b67c6 | signoff | Hold Point
a0fcdd7c-e045-410c-98ad-fbe22f99e1fd | checkpoint | Overlay material within 300 mm of the structure, culvert, pipe, etc shall be general back fill Class A1, A2 or B material conforming to MRTS04 Cl.19.2.2 except 100% material shall pass 25.0mm test sieve. Else where material may contain stone sized up to 150mm maximum dimension
de31f19f-5085-51d3-bee4-6154bb49c1f4 | note | Acceptance Criteria and Frequency (Project Specific) - Class A: WPI < 1200, PI > 7,
1455db66-97c0-5110-a3e5-fbb3c72b259e | note | ○ % passing 0.075mm: 15 - 30
8d1fe649-8075-5952-bc30-196838771572 | note | ○ Class B: 1200 < WPI < 2200
c69cccb6-03bb-5f24-a0ac-9ef484de5f6f | note | ○ Class A/B: 100% passing 25mm
91ccad1b-5219-56bd-af8f-7e56fecfacc7 | note | Check Item - Witness Point
f9d581ac-77df-57a6-97fa-6d23e31828f5 | note | Reference - MRTS04 19.3.1, 19.2.2
13bbc4b3-3ec7-484d-8d46-2eff75dc81b8 | checkpoint | Compaction - Q142A, Q141B
6a489e98-a59e-54dd-a581-79c7316e24da | note | Acceptance Criteria and Frequency (Project Specific) - Top 300mm below Subgrade Level ≥97%
28bd9d0e-cbe8-5317-a1ac-a1c8fe522a55 | note | ○ Greater than 300mm below Subgrade Level ≥95% (1 test / 50m3, min 1 per lot)
190e1975-86b3-54ab-a9ad-0e2b2950d5fc | note | Check Item - Test results
3663444b-b184-5d64-9fa0-c64d9d1446d3 | note | Reference - MRTS04 Table 15.3(b), MRTS03.1 Cl.1
3c50dfa6-906e-48d6-a9b4-41106e5a4541 | checkpoint | Moisture content within ranges specified Rainfall Zone: HIGH
ce7fef80-1fce-51f7-bfff-4ce790f67a5f | note | Acceptance Criteria and Frequency (Project Specific) - Class A: 70-100%
c1824456-4340-56a9-86c3-235d545c1df4 | note | ○ Class B: 80-110%
f6a2a2dd-fe82-5bf3-9191-ba846def8e33 | note | Check Item - Test results
ea4f1610-1c96-5464-8ce1-4b4923fb210b | note | Reference - MRTS04 Table 15.3(c)
d121b8f7-538d-4f24-a8c1-c31e95b44a60 | section | Completion
f3d98613-d6ca-4a01-9467-f04f51aadebf | checkpoint | A water test on a side inlet gully shall be carried out where the longitudinal grade is less than 1%. Water shall be discharged into the side inlet gully to check uniformity of flow. After the flow has ceased, water shall not pond to a depth of more than 5 mm in any section of the channel.
ed054509-1eb8-5046-bfe8-e95715185799 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3e03187a-ce38-5110-9742-3060c21e9751 | note | Check Item - Witness Point
58ea9517-912a-5653-8eea-1b4adde567c1 | note | Reference - MRTS03 Cl. 21.6.2
c269161c-7971-4d7b-94df-14405d96cde5 | checkpoint | CCTV inspection undertaken, report submitted and accepted by administrator.
d842c967-9805-5ab0-903e-6dab97121806 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0230c03c-d4ec-574c-9758-097910f3e93b | note | Check Item - Hold Point 3
b8973046-7cec-5d65-ac95-16e28f599fec | note | Reference - MRTS03 Cl11.3.5
f30be7b9-9278-4568-b3d0-8e1fa7d96e8b | signoff | Hold Point
481afc67-4987-4dc2-8b3d-77b4d7e3a1bf | checkpoint | Final Verification
83e1286a-be19-55ea-bc08-f74795c7d55d | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
9fd0b727-b765-529d-9b83-02ad6b05d2fa | textbox | Print Name:
8a3fd2d4-2399-57c4-9cf9-e1fa66720640 | date | Date:
68b74ba5-e1de-57dc-b456-ad42a0271a63 | note | Project Manager Verify that the Above has been Constructed according to Specification
2fb4d60a-aea4-5248-aa83-a9af7a4d691b | textbox | Print Name:
ec9e5a53-e7e8-5110-8c33-a0e47b833ab3 | date | Date:
0a3379cf-587c-4f6e-b30f-6de25eb362d2 | signoff | Signature
c7ed0b22-a887-46d1-a4c4-f0195248c8d0 | section | Final Sign Offs (to be completed at closure of Lot)
8196b64b-863a-450c-8942-a8e679bf12be | checkpoint | Agreed Quantities
b73ab12d-b0ef-404c-bc21-8953863418d2 | signoff | Agreed Quantities Sign Off
b930208a-7075-4dae-b084-eecf932376de | checkpoint | Closure of Lot
21c230a8-9074-41e5-9358-e2261ad1eb57 | signoff | Closure of Lot Sign Off
2c21a788-6a70-437e-8fc8-266859d18735 | checklist | 03.18 - Kerb and Channel | itp | 03.18 - Kerb and Channel
aa6c9999-8fd5-44ed-95b7-17d4124e68c1 | section | Details
1ba00b4a-05eb-464d-91c9-da81068d3292 | checkpoint | Concrete shall be in accordance with the requirements of MRTS70 Concrete.
f32ca22c-7d26-5d3a-867b-b9702cc01e79 | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
372e0ad6-546f-5eec-ac5d-118894f0040a | note | Check Item - Check Item
6463980a-2497-5e7d-93fb-4de4ee93451e | note | Reference - MRTS03 Clause 5.4
7679329d-4bc1-4c96-8aeb-45b6300c1470 | checkpoint | Cast-in-place concrete kerb, channel, and kerb and channel, including kerb crossings, shall be provided in the locations specified in the drawings and in accordance with SD1033
959dafa8-cd3b-5c0e-bee5-151799482023 | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
26961047-ee57-5428-9edb-3903c58fa9e4 | note | Check Item - Check Item
e7b7e28f-d4fd-57ab-911a-f0891f2e9498 | note | Reference - SD1033
f3dcbb8f-c7f6-4569-9bfa-240d05a5ca2c | checkpoint | Where insitu material on or against which kerbs or channels are to be constructed is other than rock, the material shall be compacted as for material at the bottom of excavations in accordance with MRTS04 General Earthworks.
d5506d05-9b5e-5a19-86d8-52908bbbab5d | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
c10cd387-e0f6-539b-9df6-5b9ee8bf5051 | note | Check Item - Check Item
905f41d4-387d-515e-a8fd-edd9eaa4838b | note | Reference - MRTS03 Clause 18.3
d473090a-63e4-4cc7-a373-5cc601de4b01 | checkpoint | Manually-placed concrete shall be in accordance with Clause 6.1. Exposed surfaces shall have a steel-trowelled finish.
e53c9d1a-55c8-557e-a55c-9e89d8e03088 | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
37540aa1-8a70-52c7-9917-3ece2b509a03 | note | Check Item - Check Item
c97be776-dc79-539a-96ea-366b384821e0 | note | Reference - MRTS03 Clause 18.3
0deb44fa-893a-49e9-8ee1-54019aff03f3 | checkpoint | Where kerb, channel and/or kerb and channel is constructed by an extrusion process, concrete shall comply with a maximum aggregate size not exceeding 20 mm and a minimum of 320 kg of cement per cubic metre of concrete. The extrusion machine shall be fitted with a tamper and an automatic control which allows adjustment of the position of the forming mould while the machine is in operation.
d399777e-37db-5e78-a9dc-7b1d847d4bc4 | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
a471baf1-c248-58cf-8e3d-307682710df4 | note | Check Item - Check Item
ffcf8353-14d0-5a21-87a2-10dbc90ec483 | note | Reference - MRTS03 Clause 18.3
f1472087-d0d9-444a-bb19-4501d71ac1cc | checkpoint | The finished kerb, channel and/or kerb and channel shall be well compacted and shall have exposed surfaces free from voids and honeycombing
571554c7-2149-5708-9e65-f74272f9cb8e | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
82ef0853-d786-55b2-8130-f09d1ba2b075 | note | Check Item - Check Item
3e476e4f-8870-5631-93c4-89910bead7dd | note | Reference - MRTS03 Clause 18.3
4251ac2b-6d01-4303-bcca-5eb734c475e4 | checkpoint | Expansion joints shall be installed at regular intervals not exceeding 20 m. The joints shall be constructed by installing 6 mm maximum thickness compressible packing in the full cross-section of the kerb, channel and/or kerb and channel. Where relevant, joints shall be located to line up with expansion joints in adjacent structures.
27c97ce1-c503-5966-92ba-afdf184e4a1a | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
3c5f0b8f-11b7-5a28-8afc-5a45d45239c8 | note | Check Item - Check Item
8b396928-0c25-57a4-bd41-05ac1979426e | note | Reference - MRTS03 Clause 18.3
c6932179-4497-4be5-ab63-7b95a3522e64 | checkpoint | Contraction joints between expansion joints shall be installed at regular intervals not exceeding 5 m. The joints shall be constructed by forming grooves 40 mm deep and not more than 6 mm wide in all exposed surfaces of the kerb, channel and/or kerb and channel.
271be4ad-9461-5649-a32e-c1b8a547b989 | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
57e98ca2-af55-530a-a740-a7fa4a3f03f8 | note | Check Item - Check Item
2876ba32-169e-5ab6-ba72-961c7b2cf41a | note | Reference - MRTS03 Clause 18.3
c5b2b0b7-9786-4b91-94bb-c8f08f3e665e | checkpoint | Concrete shall be cured for a period not less than seven days before any other roadworks operations are carried out adjacent to the kerb, channel or kerb and channel.
a179da00-08ae-5e4e-b025-d6ea8a62f674 | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
6d41e8bd-fb58-5de9-8497-916ec74fffe9 | note | Check Item - Survey Results
59caaea6-7e79-5f7a-9ddf-a07fcc05636c | note | Reference - MRTS03 Clause 18.3
94356f4a-147f-478a-adf0-cc02756096d3 | checkpoint | The horizontal and vertical alignments of kerb, channel and/or kerb and channel shall not vary from those specified by more than ± 10 mm.
01a86243-7cc5-5a9a-aa3c-60d4d0810420 | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
a3536ff9-ffaf-5c69-995c-b20b091b6b79 | note | Check Item - Check Item
3c806d76-a7c2-580e-af2e-2f773d28061e | note | Reference - MRTS03 Clause 18.4
54daca65-393b-41db-a063-473852f9b4cf | checkpoint | Where the longitudinal grade of channels is less than 1%, a test shall be carried out by discharging water into the channel to check uniformity of flow along the channel. After the flow has ceased, water shall not pond to a depth of more than 5 mm in any section of the channel. The test shall be carried out as soon as possible after the concrete in the channel has hardened.
207a7abf-998f-5be1-9d8e-6181a04259c4 | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
ce171c6e-c2f4-5a09-bee8-ac750248a5c8 | note | Check Item - Witness Point
b065c8d4-d496-5206-af02-3a45d4fe4c4a | note | Reference - MRTS03 Clause 18.5
756ca979-0323-48f2-afd8-5fa22866a115 | checkpoint | Final Verification
1a8bc494-d468-58ba-8d69-5dd0b3bcefad | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
4e14cb4e-d6fd-5918-82ee-c976628b1623 | textbox | Print Name:
12f67fa7-c4b6-58be-bb02-9c263a49ee74 | date | Date:
c4b9db76-1487-5768-a67a-2c0bfb5a5b8b | note | Project Manager Verify that the Above has been Constructed according to Specification
f4637739-0992-5360-8643-b29447f2ff9a | textbox | Print Name:
8131e5eb-b19b-565d-825d-d7b96ebae29d | date | Date:
8de39065-457c-4e8f-8364-1cd4da614cd8 | signoff | Signature
d9dd1098-2edf-4fc5-98cf-5e469e1664d0 | section | Final Sign Offs (to be completed at closure of Lot)
ec054068-6983-47a4-9fbf-f5f669dffe5e | checkpoint | Agreed Quantities
f3026bda-f7ba-455b-9424-f85872b90761 | signoff | Agreed Quantities Sign Off
3f5b0e3e-dd41-4f3b-a955-e4d3fa861196 | checkpoint | Closure of Lot
72587be0-d11c-45fc-be0a-f0e5f30a482a | signoff | Closure of Lot Sign Off
44a58f07-47a7-473d-a3c1-53e1d35c870b | checklist | 03.22 - Subsoil Drainage | itp | 03.22 - Subsoil Drainage
4f56bcfb-c7e3-4e67-ba1d-20be95fd09fd | section | Details
d6bb4bf9-cd10-491a-8f53-57cc7dca4d80 | checkpoint | Once the initial set out is complete the Administrator will determine the design appropriateness of the set out with regard to the actual site conditions
5079f201-0013-552b-8700-c3e203f38bc0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5f27d702-a54d-5bba-a1ae-3c088e896723 | note | Check Item - Hold Point 1
fd58c545-3fd4-5bcf-a4e8-c0aa52af39a6 | note | Reference - MRTS01 Cl8
480fa446-24da-4916-9a6a-e9a2af7fb391 | signoff | Administrator Sign Off
7c84288e-7178-42b5-84ec-362cfa568c2a | checkpoint | Subsoil Drains constructed to appropriate dimensions, inspect trench prior to backfill
6fb67174-e585-5603-8980-be8e0fc985d9 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3b272c2c-bf7b-51da-a770-dd01d93c1c54 | note | Check Item - Check Item
df47e23a-aeb1-421a-a20d-fe52bd590c19 | checkpoint | Backfill materialshall be damp when placed in trench. Material shall be carefully placed in layers not exceeding 200mm loose thickness. Shall be compacted to achieve effective mechanical interlock between particles.
6f332fe4-1553-5eea-8cdb-90a1ec5865d5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f850f03a-fb57-52b9-9102-b8bd28d9157e | note | Check Item - Check Item
61334697-44be-546e-9904-84b8b6208242 | note | Reference - MRTS03 Cl 22.3
15227d65-4af9-4b0a-a4af-6d0f88e0f47b | checkpoint | Subsoil Drains shall be constructed in the locations and in accordance to the drawings. Subsoil Drains shall be installed to the grades specified in the drawings. Where the grades are not specified, the bottom of trenches shall be trimmed to provide not less that 0.5% longitudinal fall towards outlets for pipe type drains and not less that 1% longitudinal fall towards outlets for strip filter type drains.
8991f4b6-9686-5675-afc6-5e24a5bda13f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
126d570b-089a-5bee-9c1d-678d8fa4b811 | note | Check Item - Check Item
5777bd12-9a00-5a86-b6af-3d51424b1631 | note | Reference - MRTS03 Cl 22.3
c76b4b66-7316-43e6-a5a6-953c5369b56b | checkpoint | Cleanout and outlet pipes, Geotextiles, trench backfill, concrete for headwalls and surrounds, marker posts shall be as per specification
72f6a6f2-1f25-5e31-ac4a-0b36f5ff2731 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6e132a7a-1a7e-5ca3-b22e-ed07bfac8a78 | note | Check Item - Check Item
154c23b4-2c3e-546e-8b3f-90636a43f8f0 | note | Reference - MRTS03 Cl22.2
e109dabd-102d-462c-8b0f-170f11b24a4e | checkpoint | Clean-outs shall be located at the heads of all subsoil drains and at subsequent spacings not exceeding 60m for Type B subsoil drains and 50m for Type D subsoil drains. Cleanouts shall be constructed in accordance with the details shown on Standard Drawings 1116.
8699cd97-311f-5392-a3c1-426ce83e5128 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
fbabfd3a-4804-5158-aee2-9e38d88e8105 | note | Check Item - Check Item
e27a58cd-6db6-574b-93eb-b5ba57c85d5b | note | Reference - MRTS03 Cl22.3 TMR SD 1116
cb9477f8-47c3-4540-8337-e6a8ed0ac7bd | checkpoint | Marker posts installed where and when required as shown in the project drawings or standard drawings.
ab143219-d904-53a6-95db-e809ec6bf6fa | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f5a8c0ab-4d02-5af5-92ff-de90aa170a35 | note | Check Item - Check Item
e180d967-472e-5aae-9aec-987a4f221332 | note | Reference - MRTS03 Cl22.2.7 TMR SD 1116
8d7d1227-2d26-4bfb-98e0-1479c082296b | checkpoint | Where directed by Administrator, drains shall be flushed until outlet water is clean and flows consistently
fa4075e0-ffcb-5819-aaa2-b4ecf55cab8f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f05ed798-bb31-5bc8-a8d9-1c12048e2074 | note | Check Item - Witness Point
0b6b4107-7354-5c0d-9221-a64c14a48344 | note | Reference - MRTS03 Cl22.3
68d750af-5274-4586-ab4f-66b581452554 | checkpoint | As Constructed drawings prepared
08bb419a-ebc3-50b3-9782-545d925fa392 | note | Acceptance Criteria and Frequency (Project Specific) - As constructed drawings submitted to administrator
96d1898e-242b-5508-8000-107fc3d6f7c5 | note | Check Item - Witness Point
de4dc569-89b0-4f63-8d52-e54b3f2d2c73 | checkpoint | All geometric tolerance requirements met
3d0b71b9-5b6c-54fd-a252-a7f2b900ab9d | note | Acceptance Criteria and Frequency (Project Specific) - Survey
9f297059-7ee3-562d-81ac-4e6e5c2ea82e | note | Check Item - Check Item
e033f933-5c32-4bb9-9e1c-779a8f3fa6d0 | checkpoint | Final Verification
35357d4a-ab67-5597-8284-a5ab6ee4a231 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
874eb93e-428a-5022-ad46-584261743b31 | textbox | Print Name:
a7720170-3612-509e-a885-2be00994bbf8 | date | Date:
dc6c7656-be8f-5868-9417-260e651c2f75 | note | Project Manager Verify that the Above has been Constructed according to Specification
85733598-cc8c-5417-9750-4ff0f4e7c8a3 | textbox | Print Name:
e7dce7bf-b617-5645-98d9-5a76f258bdcc | date | Date:
aa7d37f2-6393-45e1-a5ff-636eddffdaee | signoff | Signature
ab027d0e-dbc9-41a1-a1f8-13fec0733e14 | section | Final Sign Offs (to be completed at closure of Lot)
51adbf7b-2fe6-4efd-9948-6d8ec46f094b | checkpoint | Agreed Quantities
cb201608-9dd2-4d60-97f7-2539addda41c | signoff | Agreed Quantities Sign Off
9ebc5217-206d-47ef-ae2e-a8c3df038e2b | checkpoint | Closure of Lot
056d7f88-ea05-4021-896c-fa899aaeebb8 | signoff | Closure of Lot Sign Off
39ee5f33-dae0-45c5-a3ff-daccb7c80856 | checklist | 03.35 - Rock Protection | itp | 03.35 - Rock Protection
fe4752d9-5713-438a-adda-1ce67f237a59 | section | Details
b156f1d7-fa40-4631-91e4-0d8c33f13fdf | checkpoint | Rock employed as per drawings. If not specified, between 150 - 500mm, with at least 50% larger than twice the minimum size
ff93b5f1-3019-5769-ad81-1e4ca86c46a2 | note | Acceptance Criteria and Frequency (Project Specific) - Visual Inspection
134600f0-583d-5bd1-9080-7f2bc133b43c | note | Check Item - Check Item
55323631-ab5c-5171-b6c6-cb81df478f5a | note | Reference - MRTS03 Cl 35.2
b2e0f089-c499-4f13-b85b-00ae5fb76119 | checkpoint | Uniform appearance overall, and shall not have noticeable overall irregularities in horizontal and vertical alignments. The layers of placed rock shall be of even thickness and of even grading
a5fa8575-8653-56c9-a20c-eb980e28a2e0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual Inspection
bbb90430-dc79-5845-9569-5b305911bbcd | note | Check Item - Check Item
8f98be84-7e26-5889-965d-9804286262c8 | note | Reference - MRTS03 Cl 35.3
a4b58f20-13e8-480c-9bd0-d1f556a5e9fc | checkpoint | Ordering Geotextile - Documentation which demonstrates that the design of the geotextile is in accordance with MRTS27 Cl. 6 submitted to the administrator and accepted prior to ordering.
57f8f51e-e010-5bf2-a860-359a6c893e19 | note | Acceptance Criteria and Frequency (Project Specific) - Written Approval
f8e4687f-c7ab-5c37-98dd-2198ae4f6f32 | note | Check Item - Hold Point 1
f9e15331-e7f7-5e6c-9dce-7f2727faa819 | note | Reference - MRTS27 Cl 8.1
6d20b31d-a0c6-469c-9ea9-05ff49a2778d | signoff | Hold Point
8644dd9f-17c2-4f1d-876a-5d0647102725 | checkpoint | Geotextile - Inspection of product to be incorporated into works. Where Lot sites are greater than 5000m2, a representative sample covering approximately 15 m² of geotextile shall be cut from each sampled roll but not within two metres of the start or end of the roll. Where directed by the Administrator, samples shall also be cut and supplied to the Administrator.
119307dd-2de3-579d-8599-99dbeebb9218 | note | Acceptance Criteria and Frequency (Project Specific) - Visual Inspection
10a3cd0a-fabb-521b-a613-eea7a2f89026 | note | Check Item - Witness Point 1
4edc8167-a11d-5846-b271-267bc7dedc4b | note | Reference - MRTS27 Cl 10.2
2e65ab35-68b2-4b10-9022-b9d33899d8b9 | checkpoint | Compliance of delivered Geotextile - Geotextile shall not be placed prior to acceptance of the test results by the Administrator
ffc8aa52-bc16-52c2-88a0-f1fd5ac95d99 | note | Acceptance Criteria and Frequency (Project Specific) - Visual Inspection
be3adefd-a014-55ed-8505-5f332d8cdb9a | note | Check Item - Hold Point 2
4baf7e71-b60f-58aa-bad0-69fc19667511 | note | Reference - MRTS27 Cl 10.4
f2d3b055-e66c-4ed8-8a7f-5633bd683bbc | signoff | Hold Point
1105bb05-9a30-4c9a-8c0d-b8ad0b8e2391 | checkpoint | Final Verification
461e730d-99f9-588b-b921-063ba7de31a2 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
8990be32-9787-5641-a030-308c8c36288a | textbox | Print Name:
fdb828e7-7430-5598-bd0b-036d955cf062 | date | Date:
a08bd7a4-0f0a-5a85-9503-a670e4ece26b | note | Project Manager Verify that the Above has been Constructed according to Specification
2d9a2d6d-89b7-54e5-820e-31131a20b113 | textbox | Print Name:
835534c5-50c2-5d99-bda9-e2f5097b5b34 | date | Date:
13d080c2-5829-487a-bc45-3a0b8340c94b | signoff | Signature
3685e105-03b3-4882-b330-2d5fec84c80b | section | Final Sign Offs (to be completed at closure of Lot)
56c431d5-6772-471a-a10e-e82e4f8f0b77 | checkpoint | Agreed Quantities
cdb26271-db73-4055-93a7-88d1da3262bc | signoff | Agreed Quantities Sign Off
c36d0fc7-1e1f-4b2b-9b2e-8b137cbc03f3 | checkpoint | Closure of Lot
c2bcac13-ce43-4aba-b59a-2be398711c62 | signoff | Closure of Lot Sign Off
187d9287-7de2-4391-94c4-1a444f2df76b | checklist | 04.07 - Clear and Grub | itp | 04.07 - Clear and Grub
a246fc7b-9e17-44bd-a40b-b4e5b24418a4 | section | Details
95945558-0e92-4f80-8688-20a49af92daa | checkpoint | Any trees, shrubs and overhanging branches to be left undisturbed shall be clearly marked prior to clearing operations reaching the areas concerned.
e2b8ad48-b4a0-5913-a2d2-f2fd8002decc | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6b867981-fe59-5154-a600-77a6c4e5e6b2 | note | Check Item - Hold Point 2
0041f025-7197-5b36-a0a6-09a6f3e5b138 | note | Reference - MRTS04 Cl. 7.2.2
d472251e-8323-4ac9-814e-4eb32c83d2fd | signoff | Hold Point
95972e41-c45b-4344-a33b-9d8fbacba6be | checkpoint | Any trees required by the Administrator for use as marketable timber shall be as nominated in Clause 1.3 of Annexure MRTS04.1. Such trees shall be clearly marked by the Contractor prior to clearing operations reaching the areas concerned
c201f3c2-aa24-5d3f-9f9a-029d0fa08aff | note | Acceptance Criteria and Frequency (Project Specific) - Visual
df0a81da-b50b-51c9-9fb9-c4a8711af3b3 | note | Check Item - Hold Point 3
2da42a3f-44e8-550f-b88a-854890442a60 | note | Reference - MRTS04 Cl. 7.2.3
38f43012-5613-4567-adf2-15381f7840ec | signoff | Hold Point
49aa2d0d-2930-4fa1-ab21-e0ca7cbf2e4d | checkpoint | As soon as practicable and prior to initial earthworks operations (clearing and grubbing) for any stage or section of the Works, erosion and sediment controls associated with drainage paths flowing through the Works area shall be installed.
2a0f0ca2-e55d-5521-9802-47ba59310e3c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
06d98ee7-9a8a-5b14-b577-342926a67a98 | note | Check Item - Hold Point 2
1b34b7c9-f4d6-562b-b765-2d885cdec7cf | note | Reference - MRTS52 Cl. 7.1
9163ff82-43b3-443b-bdd8-fc7f405ffeef | signoff | Hold Point
dc13b043-6e41-4b2f-a7f4-a5c49d0ab7cc | checkpoint | Hollow timber which is identified as being suitable for fauna habitat logs relocated to areas clear of construction activities
6e2262da-e4c6-5ac6-a673-daf720c83edf | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9f8a9b50-f070-5944-99c9-f45bb0b65ee7 | note | Check Item - Check Item
f97e8b5b-6b54-587c-9f81-7d737d5e0368 | note | Reference - MRTS04 Cl. 7.2.5
1004dc78-18fd-4bff-8b2e-796ecae61ca6 | checkpoint | Surplus topsoil material and material considered not suitable for use as planting media in accordance with Cl. 8.3 shall be assessed for suitability for use as fill or deemed as unsuitable and disposed in accordance with Cl. 11
3299e649-118b-54a2-9cfe-96dff4ae5061 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
32d6e808-10b7-5656-a9d2-c54341a3d456 | note | Check Item - Check Item
39ca70db-c7ea-5fda-b077-88f9747b56b8 | note | Reference - MRTS04 Cl. 8.4.2
8897fe1f-74ed-4fd9-9266-73d777d6fd11 | checkpoint | The scope of clearing and grubbing shall include the items as per Annexure MRTS04.1 Cl. 1.2 & Cl. 1.4
98f891df-3322-5a3e-8956-67776c0328cf | note | Acceptance Criteria and Frequency (Project Specific) - Visual
42848d5b-92ec-55e3-8d8b-dfbe0600c996 | note | Check Item - Check Item
ece207ec-4468-5f4b-a882-cbb68ae0d6e2 | note | Reference - MRTS04 Cl. 7.2.8, MRTS04.1 Cl 1.2, Cl 1.4
bcca27c9-d5dc-44ea-b141-a59a92826e87 | checkpoint | The additional width for clearing (no grubbing) is 3.0m as per Annexure MRTS04.1
31343b84-6070-5133-a736-cadf433962dc | note | Acceptance Criteria and Frequency (Project Specific) - Visual
cdca65e4-bac8-5a83-bbe3-4d104276c1bc | note | Check Item - Check Item
1d21ad90-7a14-591b-9bdb-db0b1ecddbfd | note | Reference - Annexure MRTS04.1
03bbcf7e-3cd0-4e14-8f1e-8f50ac3d878c | checkpoint | Material not to be removed from within drip lines of existing plants to be retained except where this would result in unsuitable material being left beneath embankments. Root systems of existing plants to be retained are preserved where practical.
c4f3eeb9-49e6-5d3e-9806-1565887e31b8 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
24bb6a66-64c4-508a-bfb1-9127c226e8a4 | note | Check Item - Check Item
e1b978c7-ae17-5960-b1dd-a2d2dcf84982 | note | Reference - MRTS04 Cl. 8.4.3
9c38a916-ab7f-467a-ab31-37895e06810c | checkpoint | Final Verification
23f276b7-5521-5d3d-97a7-036f1eacdfa1 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
44041a8f-517f-5941-b66c-e722968880b2 | textbox | Print Name:
12901fb5-2249-53db-b508-9d12c15f0337 | date | Date:
cc2d3922-6feb-576a-b80b-39ba1d647b85 | note | Project Manager Verify that the Above has been Constructed according to Specification
4c6c0f05-7801-54d5-9afc-355076de09ff | textbox | Print Name:
28bf6c8e-12f0-57ae-b853-9d604f2be59c | date | Date:
7f4f1641-cb3d-45cd-bf03-25157f26bd60 | signoff | Signature
4a312968-67ec-47f3-83af-756a67f7d971 | section | Final Sign Offs (to be completed at closure of Lot)
073a31fb-a7fc-449b-ae44-109267f87ad9 | checkpoint | Agreed Quantities
8ef1e698-0cfd-4999-9b7c-ab306a35e2fa | signoff | Agreed Quantities Sign Off
ddda68e7-90d7-408f-8248-f131197dde33 | checkpoint | Closure of Lot
9912f5ed-aeb0-4cd1-8e52-a2399f9fb6a0 | signoff | Closure of Lot Sign Off
2119a884-1469-4e8a-ac29-7fffe78e6dc5 | checklist | 04.09 - Unsuitable Material | itp | 04.09 - Unsuitable Material
b84bee9f-421d-403c-8faf-643f7372dd7c | section | Details
d3511891-bf32-4bb1-bd0c-03e8168e7667 | checkpoint | The identification of unsuitable material shall include items listed in MRTS04 Cl. 9.2
4fba6413-ba81-5fda-b098-5af3bb658b4e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
85c96ad9-0893-507a-9e5f-b15a59676f6e | note | Check Item - Check Item
fe2835f2-478d-5903-9726-a97373db5351 | note | Reference - MRTS04 Cl. 9.2
29aeb71a-783d-486b-9f4c-31082984044e | checkpoint | Where Unsuitable Material or potentially Unsuitable Material is encountered on the Site, the Contractor shall, before proceeding to remove or cover such material, notify the Administrator and provide any test results required to justify such a claim.
59c29430-56b5-589c-9997-12db19e6fba9 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
fefd62e6-7d86-549f-8af4-7e57593d7026 | note | Check Item - Hold Point 4
4c21a81d-d7a0-543f-a90b-9752d2da63df | note | Reference - MRTS04 Cl. 9.4
70cb443d-ad47-4601-b133-6f32a56b7f08 | signoff | Hold Point
552807df-af70-4f4c-8ae1-5b7447894f39 | checkpoint | Excavated as per MRTS04
c8644d39-9301-592d-913e-18d75529acc4 | note | Acceptance Criteria and Frequency (Project Specific) - MRTS04 (General Excavation ITP)
dc61f41f-b453-5856-acc0-ef0db4879bf9 | note | Check Item - Check Item
87bf1361-fc9c-56c1-9f4b-daf14cc95551 | note | Reference - MRTS04 Cl. 13
934b7b69-9353-4d5f-a7d8-36853554b049 | checkpoint | Backfilling of the excavation shall not commence until an As Constructed Survey of the excavation have been met as specified in MRTS56 and notice of such Works provided to the Administrator
608d4aee-c230-585c-b150-3e91615e1048 | note | Acceptance Criteria and Frequency (Project Specific) - Survey Report
980fea0f-a7da-5e3e-85a6-e2e913b9c561 | note | Check Item - Check Item
8e239b1d-c13a-5ac1-85d8-804e9967cf86 | note | Reference - MRTS04 Cl. 13.3.2.2
aa04669b-3ad4-4982-91c0-4158ef08edef | checkpoint | Backfill as per MRTS04. Replacement fill material shall be placed uniformly in layers and compacted using compacted layer method.
51d337f2-8000-57d3-962e-f59fcbb3567f | note | Acceptance Criteria and Frequency (Project Specific) - MRTS04 (Backfill ITP)
add3ca5c-f478-5843-bb0d-6e1371e83bfb | note | Check Item - Check Item
40a6b840-b66e-53f2-bae9-67f748d6684a | note | Reference - MRTS04 Cl. 13.3, MRTS04 Cl 15.3
3dd6be07-55e7-4a31-b082-24ca2bafee42 | checkpoint | After backfilling of the excavated area has been completed, an As Constructed Survey shall be undertaken.
9fa5c7c9-2dd1-58cf-8a70-d42d8612b42d | note | Acceptance Criteria and Frequency (Project Specific) - Survey Report
1bbcc608-461d-54e0-9e17-cb49a6bde8ea | note | Check Item - Check Item
41ce1f5c-6d45-567c-a54b-4ff59110e98a | note | Reference - MRTS04 Cl. 13.3.2.2
7783473a-8412-4c6e-9df3-4db9d43d268b | checkpoint | All surplus material and/or Unsuitable Material shall be disposed of off the Site
86632494-9f63-59b3-a67a-bf85d80473e7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a325c462-6099-56f5-abde-b62fdc913b63 | note | Check Item - Check Item
b5ca6bee-5e70-5f20-9d0c-6ac243607e02 | note | Reference - MRTS04 Cl. 11.3
98893702-0d07-4174-837c-02151d575741 | checkpoint | Final Verification
be27ce6f-7460-52fa-8314-c1daa5607723 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
50311681-b9e4-5a5d-b119-c784923882c6 | textbox | Print Name:
92b79a81-2f8e-588d-975b-e035992cf2d0 | date | Date:
1deed7ec-0af8-572f-a3f1-b1e765786ade | note | Project Manager Verify that the Above has been Constructed according to Specification
f61706cc-9d7a-5b8a-92a7-94a71678dad7 | textbox | Print Name:
ddc6bf99-72d2-592f-bacf-a31c146f873a | date | Date:
01f7da49-1ae7-4855-8ae2-2f93e5f4dfbe | signoff | Signature
076495b3-01de-4bea-a084-036c592e6924 | section | Final Sign Offs (to be completed at closure of Lot)
131a0134-a5d8-4772-9e5e-c57defe6eba6 | checkpoint | Agreed Quantities
2d47d7fe-5a04-4dfb-9b8b-881af24cf120 | signoff | Agreed Quantities Sign Off
16a28120-f58d-461b-803c-9fea6d32753d | checkpoint | Closure of Lot
5899c21e-7e64-4556-9e7e-452792bde4d8 | signoff | Closure of Lot Sign Off
4c221b9d-28f8-46e5-bcb9-06e8d0c02991 | checklist | 04.12 - Ground Surface Treatment | itp | 04.12 - Ground Surface Treatment
4115c75c-1b65-422e-ba13-2472fc2902be | section | Details
4454e1da-69eb-413b-9bd7-687837cd15c7 | checkpoint | Testing for acid sulfate potential and reporting of test results shall be carried out on all excavated material and exposed cuttings on the Site which could reasonably be expected to have a possible acid sulfate potential.
a6fce155-12e7-51ef-918b-9e7a8ebe13fe | note | Acceptance Criteria and Frequency (Project Specific) - Field pH testing As per National Acid Sulfate Soils Guidance
ef858d7a-5c87-50fd-8c1e-b9ca169a70bf | note | Check Item - Hold Point 5
1010805c-3103-58ad-876a-3c65d607ab0d | note | Reference - MRTS04 Cl. 10.1.4 Table A2
faa5d57f-c596-4485-aeca-59019501c9f9 | signoff | Hold Point
6361ed4a-b5f7-4a5b-a4ad-75c7ef6996cc | checkpoint | Ground Surface Treatment carried out on all areas beneath road embankment/pavement (except where special treatment or subgrade preparation is required)
504a0d96-4cc8-590d-a194-b65f4a29ed84 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5b918509-61ab-516f-abcb-d5b636c8ae6d | note | Check Item - Check Item
3ebcbbf0-6c88-576a-bdba-9b1aa790c6ab | note | Reference - MRTS04 Cl. 12.2.1.1
7311086b-d88f-4aa3-beae-8ece40bdf3b8 | checkpoint | Holes and localised depressions filled with similar material to the surrounding ground surface or material specified and compacted in accordance with Cl. 15
a732884d-ea0f-58bb-932f-82bbf9a917bc | note | Acceptance Criteria and Frequency (Project Specific) - Visual
fb1f67db-f4a3-585a-98c4-57e98b104601 | note | Check Item - Check Item
6eacbfec-c311-5644-8690-e14b0944bdd2 | note | Reference - MRTS04 Cl. 12.2.1.2
e52305b5-af28-4751-84f9-bd7caf661215 | checkpoint | Where Unsuitable Material or potentially Unsuitable Material is encountered on the Site, the Contractor shall, before proceeding to remove or cover such material, notify the Administrator and provide any test results required to justify such a claim
91395a01-04fb-5e21-ba1c-d4b1bc34d107 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1d47a657-f7c4-50f7-bce2-1fa93b472f98 | note | Check Item - Hold Point 4
57fd62f3-9025-5f0c-ae2e-8812b8a863e2 | note | Reference - MRTS04 Cl. 9.4
d3a3c0f8-cb60-4858-ba18-d339a254526f | signoff | Hold Point
cee85d80-1bf4-4159-85a9-2a7713e1c0da | checkpoint | Existing surface scarified >150mm deep and compacted in accordance with Cl. 15. If material is too wet or too dry to compact and does not classify as unsuitable, moisture content adjusted to a maximum depth of 300mm using appropriate methods. Material below this depth shall be assesed under Clause 9.2.
eca9bb41-b154-52e3-b6cf-7aa4d171822e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c4a24374-6754-571e-beb2-16bacb97ca3a | note | Check Item - Check Item
47ea1f52-a7d6-50f1-95d3-557b1b725022 | note | Reference - MRTS04 Cl. 12.2.1.3
7b3be541-de88-479e-8247-2c10e6f4e6ee | checkpoint | Relative Compaction - AS 1289.5.4.1 or AS 1289.5.7.1. After any clearing and grubbing, stripping of Topsoil and replacement of Unsuitable Material, the exposed ground surface on which an Embankment is to be placed shall, as a minimum, be scarified and re-compacted to a depth of at least 150 mm
de0a16a4-8c5c-58b9-98b2-6a88ae56dfe0 | note | Acceptance Criteria and Frequency (Project Specific) - CV 95% minimum - 1 tests per 500 m2 (min 1 per lot)
425a22a4-2844-5912-bdfa-64e4dd20a839 | note | Check Item - Test
aa4834c5-4b85-5921-9962-1d18747fb7f9 | note | Reference - MRTS04 Table 15.3(b) App. A
99da54a7-cb90-415b-90a5-ce397065d362 | checkpoint | Final Verification
f64c4e34-a806-5736-8128-5d2329895bcf | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
3752c9d2-7088-53ae-bb79-543fae850cfe | textbox | Print Name:
a733e720-ed86-5b04-a3f1-ec2f39307d2e | date | Date:
7ff64d55-d0d3-5bbe-a29d-f6d13e924bd4 | note | Project Manager Verify that the Above has been Constructed according to Specification
be7b42f1-1afd-5c4d-b41a-814d6e1c57ab | textbox | Print Name:
dfddee0d-997d-5c85-91a5-b10933c134c7 | date | Date:
c381ba72-b3b1-48cf-9e31-6c9d66220014 | signoff | Signature
8ffe0c7b-ee80-4c14-889d-59672017f84b | section | Final Sign Offs (to be completed at closure of Lot)
6408dbb5-bfeb-4a20-b1b1-99c17dc57b77 | checkpoint | Agreed Quantities
83b5ff69-e862-4c3a-8ebc-f35e3d8ab546 | signoff | Agreed Quantities Sign Off
12d85e75-fea4-423f-9a2e-089b0da2c33e | checkpoint | Closure of Lot
f195e049-795f-45dd-a611-1ed0aed726d3 | signoff | Closure of Lot Sign Off
4e0531c3-a827-4d35-9331-787d003b0fa1 | checklist | 04.13 - General Excavation | itp | 04.13 - General Excavation
d73e8369-713e-49ce-bc8c-d9d522125a02 | section | Details
3a3e8bb7-734b-41da-aecc-fb26942f42f7 | checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or potentially Unsuitable Material is encountered on site, the Contactor shall, before proceeding to remove or cover such material, notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl.11
4e24ca75-26bd-5d3c-ab28-b48a06c1c5b9 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ec420384-7e5f-5e81-8bcd-d0c4184718fe | note | Check Item - Hold Point 4
237a91a2-82d9-5a12-8bfb-057b35f3abb5 | note | Reference - MRTS04 Cl. 9.4
c2a27a42-6698-4727-90c5-1fb2cd6d96f5 | signoff | Hold Point
771d3ea3-7090-49c8-9162-b3427d7d7507 | checkpoint | When the level of excavation has reached subgrade level, the Contractor shall carry out the requirements of the relevant provisions of Clause 18.3.3 and cease excavation until the subgrade treatment type has been determined in accordance with Clause 18.3.3.
9cb6f676-2408-5d71-951c-f83c806bb2e6 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a35dc73d-daca-5079-96bd-44a4b80e699b | note | Check Item - Hold Point 8
6dc00e43-8d87-59f5-97b0-644b572f6d7f | note | Reference - MRTS04 Cl. 13.3.2.1
22576b0c-a7a9-4b5a-afe7-9fef703242ae | signoff | Hold Point
9e05d252-e440-4154-a6d3-0ea74a6db4c4 | checkpoint | Excavation completed to the shapes, lines and dimensions and other requirements shown on the drawings and tolerances specified
345fbbaa-f9c2-5ef7-bcb5-3f88da19a191 | note | Acceptance Criteria and Frequency (Project Specific) - Survey
d76aff92-e320-5823-9832-e0a547736cd5 | note | Check Item - Check Item
44677455-ea4a-5c31-9630-295fea6c6afe | note | Reference - MRTS04 Cl.13.3.1, Cl. 6
26b31c11-b999-4635-80bd-34f79acc9ef0 | checkpoint | Protection of excavations in accordance with MRTS04 Cl.13.3.3.3
8861e979-c671-5d11-a398-c98afef24655 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
877a3de0-94fa-5d2d-b23f-f96bb641af52 | note | Check Item - Check Item
6eceaf99-35f9-5c91-995c-1333f94d5abf | note | Reference - MRTS04 Cl. 13.3.3.3
8843ec1d-28de-4058-b897-5921e8db070c | checkpoint | Dewatering of excavations shall comply with requirements of EMP
ffed5923-d062-5441-9916-17ca98e72cd1 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a5f7d69a-24d2-52e7-97a2-fd25528362c2 | note | Check Item - Check Item
94ace330-1c54-5ac1-95b5-23b695d8c7e5 | note | Reference - MRTS04 Cl. 13.3.8
c88b5fa5-ff92-4461-b5a0-2235c00cdb9b | checkpoint | Batters in cuttings shall be free of loose material and shall be trimmed neatly to the shapes specified.
1cb837a6-646a-5bb0-8a8c-7f0a0f4e9062 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6b3c1d57-c200-5e36-8015-78a7a11b0e55 | note | Check Item - Check Item
865e2b59-acfe-5b4b-b924-bd063af4ae48 | note | Reference - MRTS04 Cl. 16.1
e1d639d9-fa2e-4b50-b3ac-5c1773950861 | checkpoint | If any section of a batter has been over-excavated beyond the tolerance limit specified, the Contractor shall re-form the batter to the average batter slope shown on the drawings, using an approved rectification method
4baed528-962f-5886-bb6a-ca643f50e7ec | note | Acceptance Criteria and Frequency (Project Specific) - Visual
409153d2-f7ea-5871-8bfb-75c5d1f4b137 | note | Check Item - Check Item
133a134e-173d-5f21-96f3-5e766ba13595 | note | Reference - MRTS04 Cl. 13.3.2.4
0804a0ca-131f-47f1-95b1-07ba1a24cfff | checkpoint | Final Verification
7e599365-2f47-56c0-8b41-d41777c24b1d | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
8adb4071-6920-5b97-a6b5-73247a88efdc | textbox | Print Name:
93490e77-b811-5fe0-9036-36931b1fbc47 | date | Date:
b7abfcc8-ddb7-54d5-a19a-e0704fa948d6 | note | Project Manager Verify that the Above has been Constructed according to Specification
bb6c819a-3cac-5af4-967e-81843ee795ef | textbox | Print Name:
f7ef99a3-cc85-52f6-8de1-1ee616cd25a1 | date | Date:
89123b5f-cf92-44b1-9fc8-57e784ee78c7 | signoff | Signature
a3aae7f2-f57c-4f38-bc5c-495d2a8b9869 | section | Final Sign Offs (to be completed at closure of Lot)
c4e4dadf-a016-40cb-b39c-40d74513c494 | checkpoint | Agreed Quantities
be0906f7-2c49-4540-ab8f-d0b595488fcd | signoff | Agreed Quantities Sign Off
b4568089-5e82-4403-bd5a-5d4a8619d234 | checkpoint | Closure of Lot
f7776458-b266-46e0-a0cc-1a6a5782f860 | signoff | Closure of Lot Sign Off
9e780b74-f03f-4dba-870e-03c97dc0cef2 | checklist | 04.14 - Embankment | itp | 04.14 - Embankment
09ac64dc-b3f7-48a7-a025-00541f792df9 | section | Details
cbd0d1db-02c1-4f7b-ac88-b0f27a42c5d6 | checkpoint | Earthworks construction procedure shall be sumbitted to the Administrator at least seven days prior to commencing the Works.
f3728430-6df3-581c-9a26-3047e77ba689 | note | Acceptance Criteria and Frequency (Project Specific) - Construction Procedure Acceptance
b07f9138-d7b8-5f87-b321-63c11e93023e | note | Check Item - Hold Point 1
c8c0083a-af09-55f8-bb90-c4a9badf3c93 | note | Reference - MRTS04 Cl. 5.2
cf64a61e-b5a7-49bb-b469-30eafee57a3f | signoff | Hold Point
7216b3a5-849b-4229-a9d2-905d0ebf1d2e | checkpoint | Define lot size.
e6d6efce-9236-5cc1-b77a-09a33eb8f201 | note | Acceptance Criteria and Frequency (Project Specific) - Normal : Max 2000m2
bcd18bb8-2347-5d0c-9334-f3bf6fe4a49c | note | ○ Reduced Level : Max 4000m2
0cc8d39a-eb43-5494-9851-07f2436a4b1f | note | Check Item - Check Item
8980cec3-afdd-5400-8bd8-0bab3d25d621 | note | Reference - MRTS04 App. A Table A.2
87fcdaba-d6e4-4b82-831e-732c4af62f8b | checkpoint | Earth Fill Material stockpile or source material results submitted to Administarator
bdb96e58-311f-5f4b-9354-f9a5bd6d943e | textbox | Reference Stockpile Lot No. :
44f0ead8-09c5-5358-8913-73c59b4e14c4 | note | Acceptance Criteria and Frequency (Project Specific) - Stockpile Lot Acceptance
76fe3760-a7ae-501b-ae6c-40b604616c3d | note | Check Item - Hold Point 10
4c074e5a-9da1-5f59-8198-2f2a3205afa9 | note | Reference - MRTS04 Cl. 14.2.1
d3117adc-f160-4a19-a4a3-7c58b6f789fe | signoff | Hold Point
83c84ed1-4185-4d2f-96ea-67f4b7b00d34 | checkpoint | General fill material used for the construction of road embankments sourced from general excavations on site or imported, complies with General fill Class A1, A2 or B and is homogeneous.
ac327b53-2b77-5613-abd9-6146b26dd305 | note | Acceptance Criteria and Frequency (Project Specific) - Stockpile Lot MRTS04 Table 14.2.2
59d40cf3-d644-5da4-893a-dad480b814c8 | note | Check Item - Test reports
7361a70b-f57c-5f59-a298-6ddb34235543 | note | Reference - MRTS04 Cl. 14.3.1
ab157ce9-e590-4fd0-ba92-bfa6c7fb7dca | checkpoint | Compacted Layer Method:
2e27a42e-c4e5-5a66-8331-cd835b14cc2b | note | Fill material placed uniformly in layers. Uncompacted layer thicknesses;
21cb0773-98b5-5254-9b36-0047abc036b2 | note | – General Fill 150-300m
8fbd64ad-6a0c-5f0d-b111-fecd6a6c5cf9 | note | – Fill material in water-retaining embankments 150- 200mm
2d20b352-a5f6-52e6-8b11-426ef20229de | note | – Backfill except Sand 100-150mm
a98976b0-eb47-5644-b68d-645613767ed6 | note | – Sand 150-300mm
c17c0350-aa76-5776-a4e1-6d718e397a9f | note | Fill compacted to required density (by Characteristic Value)
5bb7f391-d6e7-5939-8f42-26e821502433 | note | Acceptance Criteria and Frequency (Project Specific) - AS1289.5.4.1 or AS1289.5.7.1
a46aa85e-4314-5318-81f3-d351cddd46c7 | note | ○ Top 300mm below Subgrade Level ≥97%
a573c092-adc9-5eb3-9d16-eb5aaba982d9 | note | ○ Greater than 300mm below Subgrade Level≥95%
b6664287-e21c-5308-a7c0-c5f60db405fb | note | ○ Normal: 1 per 500m2 (per layer), 4 per lot
85fd53a2-f4c6-5f73-88e4-480a52fdd9c2 | note | ○ Reduced Level: 1 per 1000m2 (per layer) or 4 per lot
6f0ed723-eb15-5a14-80fc-e036b298b340 | note | Check Item - Test reports
3f9d0e29-1c24-5604-9980-074a3d12d3ba | note | Reference - MRTS04 Cl. 15.3 Table 15.3(b)
b7c18e1f-e81e-4cca-bc2b-57421153e664 | checkpoint | Compacted Layer Method: Embankment moisture ratio within ranges specified Rainfall Zone: HIGH
386798f0-bf91-5303-970d-4e32b479218e | note | Acceptance Criteria and Frequency (Project Specific) - AS1289.5.4.1 or AS1289.5.7.1
6ac75048-711c-56a0-b46b-201f46b1d8d5 | note | ○ Class A1/A2: 70 - 100
d9bd7a0e-7791-5273-8569-45085b49ab18 | note | ○ Class B: 80 - 110
d7f33c96-976b-57c8-aadb-3d2d76afff8f | note | ○ Normal : 1 per 500m2/layer or 4 per lot
58cdf132-9bac-520c-822b-4d1d8f94eb2c | note | ○ Reduced Level : 1 per 1000m2/layer or 4 per lot
d6e48861-0106-5e3a-be6f-13928810bc6e | note | Check Item - Test results
513b393a-1936-5270-a380-5b0329c2afd2 | note | Reference - MRTS04 Cl. 15.3 Table 15.3(c)
07bcc50f-bf1c-45b8-9f44-b0fa0f8428ff | checkpoint | Testing of Each Layer - Each layer shall be tested to conform the requirements as per Clause 5.6 before placing the subsequent layers.
df84608d-3263-5038-b5cf-9e60b944bd2a | note | Acceptance Criteria and Frequency (Project Specific) - Testing after compaction on site
b0a78db5-dc36-5abb-a181-ae57b5d3cfc7 | note | ○ Gradings: AS1289.3.6.1
9c4c8a13-9951-5f38-894b-9ec24f2d4279 | note | ○ PI: AS1289.3.3.1 or AS1289.3.3.2
e866a27c-5a4d-53e3-9327-59d717c694d1 | note | ○ WPI: Test Method Q252
c5a45cf7-1120-54ab-9c07-7da43ec9f1b1 | note | ○ 1 per 1000m2(per Layer), 2 per Lot
c9069cc7-7b84-5dc9-bccf-81400cfd00b7 | note | Check Item - Witness Point 5
8594a201-341b-571a-9dee-5b494e0396f1 | note | Reference - MRTS04 Cl. 15.3
663ce35e-824e-4661-a3ee-cae1316c9de8 | checkpoint | Mechanical Interlock Method: Each layer rolled until no further permanent visible lowering of the surface occurs and layer thickness no greater than specified in Table 15.4
0090da87-acb0-5c5c-98a0-bc4dcb75c59e | note | Acceptance Criteria and Frequency (Project Specific) - Table 15.4
f77c7fd9-8d13-5ffb-a658-a16d8948d847 | note | Check Item - Witness Point 6
e5478dc1-c94a-5156-9578-0b18b43c7249 | note | Reference - MRTS04 Cl15.4
83743cb3-b34b-4c9b-a01a-b7620dc1ad2c | checkpoint | Geotextile placed at interchange between compaction methods
ff843700-ac97-537a-893b-acdfcc3f1e1f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5804c506-81ab-566f-ab95-045a43d68028 | note | Check Item - Check Item
10fb5b42-5104-5e96-9175-88ee4ea10ce7 | note | Reference - MRTS04 14.3.2
b3d4b68a-baf2-4e0d-a40d-bbb68c4cc656 | checkpoint | Within Vertical Geometric Tolerance
11c63a2d-0198-5927-94ce-fa7de0ef6f4d | note | Acceptance Criteria and Frequency (Project Specific) - Subgrade level ± 25
789a7acd-0bf6-5c4e-a0e0-11d8321d0a65 | note | ○ average ± 10
57c91163-f220-5be8-bc71-b862dd26ec34 | note | ○ 1 test /20m
881cc7a3-cba7-5192-97d6-44b91a36ef1c | note | Check Item - Dip Sheet Records
1a7c9c72-87c8-5104-a596-5e3a9332b739 | note | Reference - MRTS04 Cl. 6, Cl.13.3.1 Table 6.3.1
bb6f5852-0e0f-491d-9991-1f1b41ae25b1 | checkpoint | Final Verification
a4d2ae52-fc2b-5dbf-9c78-6763853716af | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
88f4dc4e-0a8a-5066-877a-87834b06e29c | textbox | Print Name:
650b44fe-192b-5c43-8aa1-70c2422e2163 | date | Date:
2ed9ea64-4893-5718-9e51-65112aa4c943 | note | Project Manager Verify that the Above has been Constructed according to Specification
9ffe153a-359b-508a-bf0b-f2645d7495f1 | textbox | Print Name:
d6e1e37d-eeaf-51b6-8354-6e90eb5ff2f0 | date | Date:
6990e2ef-23da-4d6e-a390-f41c0a2613bb | signoff | Signature
33ca4d0f-a3f7-4452-b7a9-5d2bf30bce50 | section | Final Sign Offs (to be completed at closure of Lot)
926ccec3-dd75-41a7-abac-a9dcb882799c | checkpoint | Agreed Quantities
c1cb6d86-4843-48e5-901a-e3bcd30e0093 | signoff | Agreed Quantities Sign Off
9e42c293-d9f2-436c-8eee-210f7cf4f6aa | checkpoint | Closure of Lot
52dc1eeb-941c-4d17-add6-f9d6e9b839b8 | signoff | Closure of Lot Sign Off
58fc5fd3-3132-40e7-ae05-8aff54b7b3a9 | checklist | 04.181 - Subgrade Level | itp | 04.181 - Subgrade Level
92a15911-1974-4476-a45f-0438c0c333dd | section | Details
cd093876-5ffc-4e3c-8138-c028da67586d | checkpoint | Define Lot
08c5b367-6103-516a-ae96-0ac12bbd078f | note | Acceptance Criteria and Frequency (Project Specific) - Normal: Max Lot Size : 2000m2
8d1545d2-ec35-5a60-a7e0-154aa1c16256 | note | ○ Reduced: Max Lot Size : 4000m2
bb640a40-c47d-53ee-9462-cf0132929783 | note | Check Item - Lot Records
0426183d-a29d-51f8-a994-14d6a74370ab | note | Reference - MRTS04 App A
35a4d681-5801-477d-9ce7-8c3c0225d158 | checkpoint | Reporting Pavement Design Requirements
24001170-d490-555f-a0c6-4b8b8c3088a7 | note | For Contracts where the Principal has supplied the pavement design (that is, Construct Only or similar Contracts), the Contractor shall submit the following information to the Administrator for each existing Subgrade Lot:
545ce065-ab5f-52f2-ae78-39f5927d62ca | note | a) test pit logs
7e1c299a-eb67-529f-b7cc-4d308816038c | note | b) all test results for each layer encountered within the test pit, including certified test certificates, and
dd9e39c1-9f48-5644-b96e-3cc007e8d6a4 | note | c) marked-up drawings accurately showing all test locations within the Lot.
5a03ca72-80b5-5df6-a90c-db9a99227e94 | note | The Contractor shall allow a minimum period of 14 days for the Administrator to review the information prior to any Subgrade treatment and the placement of any overlying materials.
ff24ac34-89a4-58fa-9e65-f47941ad9001 | note | Acceptance Criteria and Frequency (Project Specific) - Submission to Administrator
f7c1a0bd-3a5d-5e18-b87b-87436bf22713 | note | Check Item - Hold Point 16
1e660a3e-01af-51b8-9343-62cf60b269e5 | note | Reference - MRTS04 App B.6.1
7f6bd7cc-4cac-4f5c-9b0a-0ee69f37ed72 | signoff | Hold Point
fab4e205-e0fb-40be-9a69-0adcb28f521e | checkpoint | Bottom of Excavation for Cuttings - Where subgrade is reached in cutting works shall cease until subgrade treatment type has been directed by the Administrator in accordance with Clause 13.3.2.1
7ff96d8d-d931-59a5-b4c5-5081e5835fa9 | textbox | Subgrade Treatment Type Directed:
a5b6b5a3-dcfc-574a-b3ea-dcafe84ff915 | note | Acceptance Criteria and Frequency (Project Specific) - As directed by Administrator
9e080623-99bd-5723-87d5-239ca1b17246 | note | Check Item - Hold Point 8
438730fc-643d-585e-9125-86f25170e52e | note | Reference - MRTS04 Cl13.3.2.1, Cl 18.3.3
f7c01421-a391-4ecd-81fc-214a0726970a | signoff | Hold Point
3adc1fd6-527a-476f-9b95-1e5967f72410 | checkpoint | Subgrade Treatment Type A - As ordered by the Administrator at subgrade level on all section. The material below Subgrade Level shall be to compacted a density of not less than that stated in Table 15.3(b) and to a depth of 150 mm.
00ee9687-6f1f-5210-8905-021aae349fb7 | note | Acceptance Criteria and Frequency (Project Specific) - Treatment Depth - 150mm
0579b609-48c1-51db-b668-d7121884455d | note | ○ Compaction Standard: min 97%
eb1278ad-3fbe-5740-99e4-8212c82336a3 | note | ○ Normal: 1 per 500m2, 4 per lot
fad71e23-2e21-5851-8e64-b71996fa04fd | note | ○ Reduced: 1 per 1000m2, 1 per lot
d5ce2c55-94ea-57ac-ab54-39516c8b3173 | note | Check Item - Test Reports
fc13a61b-b957-5b1d-ad5b-628fefdc3007 | note | Reference - MRTS04.1 Cl 12.3, MRTS04 Cl 18.3.3.1 Table 15.3(b)
cbb4890b-cf8b-46b3-81ba-fd765a2f2fd2 | checkpoint | Subgrade Treatment Type C - Replace with unbound granular material. As ordered by the Administrator at subgrade in cuttings and embankment. The material below subgrade level shall be compacted to a density of not less than that stated in Table 15.3(b) and a depth of 200mm (or as directed by Administrator).
249e3a6a-6453-52d8-9b2f-96b4e9cb86c7 | note | Acceptance Criteria and Frequency (Project Specific) - Treatment Depth - 200mm
ce8c7435-d6b2-57cd-bd03-3378d912f281 | note | ○ Compaction Standard: min 100%
5ad2341c-c43b-5297-b15d-0656547ec4be | note | ○ Normal: 1 per 500m2, 4 per lot
1227e394-f9f1-5228-9efa-f76f442b3227 | note | ○ Reduced: 1 per 1000m2, 1 per lot
7aa1d885-cc81-5d8e-a0a2-721e64c2d8be | note | Check Item - Test Reports
b4db07f0-a343-5089-9ccc-f2e64424b043 | note | Reference - MRTS04.1 Cl 12.3, MRTS04 Cl 18.3.3.1 Table 15.3(b)
cb4c7f46-8f2e-4a3b-a086-555e794007c3 | checkpoint | Subgrade Treatment Type E - Replace with plant-mixed stabilised material. As ordered by the Administrator at subgrade in cuttings and embankment. The material below subgrade level shall be compacted to a density of not less than that stated in Table 15.3(b) and a depth of 200mm (or as directed by Administrator).
e7dcda74-6764-50b3-b136-76c961d9564e | note | Acceptance Criteria and Frequency (Project Specific) - Treatment Depth - 200mm
f3900a80-bf75-5c09-8ac0-d7b35e2cf734 | note | ○ 102% standard upper most layer
01f1cc03-897a-5481-8469-339581427757 | note | ○ 100% standard lower layers
e93733b9-d624-5ee8-bd4e-54ea34b9f5f7 | note | ○ (1/500m2, min 4/lot)
c278afc7-9b24-55ac-9bd9-f8f0a8c91e99 | note | ○ (1/1000m2, min 4/lot)
54f6f506-f987-5d55-a107-420e92371009 | note | Check Item - Test Reports
a94519e6-b92e-598b-93f0-ef04f8060b35 | note | Reference - MRTS04.1 Cl 12.3, MRTS04 Cl 18.3.3.1 Table 15.3(b)
4f754e7f-4c9d-4abf-8162-d75e96462753 | checkpoint | Subgrade Treatment Type I - High-permiability drainage layer. Drainage Layer Required. As ordered by the Administrator at subgrade in cuttings and embankment. The material below subgrade level shall be to a depth of 200mm (or as directed by Administrator). The drainage layer shall be wrapped in a non-woven geotextile in accordance with MRTS27.
82c50f29-3c6a-52fd-8612-b2118733afe2 | note | Acceptance Criteria and Frequency (Project Specific) - Treatment Depth - 300mm
e68258c6-25b5-50b8-820a-e59c06396291 | note | ○ 70% (Density Index)
ccae59d4-1628-5e40-adef-ab375f9b5fa9 | note | ○ Normal: 1 per 2500t, 1000m3
54be2ff7-e69a-57e8-b675-b5a163837a33 | note | ○ Reduced: 1 per 5000tn, 2000m3
aea676c0-227a-5ad7-bd08-da9030861262 | note | Check Item - Test Reports
baeaba03-f244-5cb3-ae72-1880e4375a35 | note | Reference - MRTS04.1 Cl 12.3, MRTS04 Cl 18.3.3.1 Table 15.3(b)
a60e92f9-80b5-4082-8e34-f362957c5aab | checkpoint | Subgrade Emabankment - Material to be compacted to requirements not less than that specified in Table 15.3(b). Subgrade relative density tested to Q140A.
21c4c428-e3b6-5239-bea6-5e8924cdff28 | textbox | Material Source Stockpile Lot Ref:
9fcade3c-63ae-5221-bb7f-c64be6643d5c | note | Acceptance Criteria and Frequency (Project Specific) - Top 300mm below subgrade level -
89f2f7df-8c09-5709-902c-04a8ac3e71e2 | note | ○ Embankment Fill at subgrade: Class A1, B, Unbound Granular or stabilised material : min 97%
d1cfb345-587e-531e-a0b0-5f60bbb4d0f6 | note | ○ Normal: 1 per 500m2, 4 per lot
5601690d-05df-5de7-b68b-17a7374ea1a4 | note | ○ Reduced: 1 per 1000m2, 4 per lot
e14d385a-4266-5c14-af88-8ec651c9148d | note | Check Item - Test Reports
c3882f8e-24c5-50ea-a3c8-3d219bb94a1d | note | Reference - MRTS04 Cl15.3(b) App A
0de41138-654d-40bd-ad33-99b256a6ecc1 | checkpoint | Proof Roll: Subgrade material provides a stable dense surface displaying no vertical movement under proof roll by:
d4293a74-1edd-502c-837e-62bb4eba9cab | note | – pneumatic-tyred roller > 4.5T/tyre and 600kPa pressure, or
7f041b9f-80a1-5192-bf50-2a04f4f75c91 | note | – 10,000L water tanker with 600kPa tyre pressure.
2409a44e-26b7-5187-acb2-3645f523c58a | note | Acceptance Criteria and Frequency (Project Specific) - Visual. No Deflection. Continuous
2da85866-d9af-52df-8bc4-f422aee9cd6a | note | Check Item - Witness Point 8
8c9e077d-ed8c-5ab7-96ac-8ff1341beec3 | note | Reference - MRTS04 Cl18.3.2 Q723
98797821-b5a1-4f66-809a-e7513f21cd48 | signoff | Witness Point
c20be1f3-8607-45bd-83a2-3b3318bd239e | checkpoint | Subgrade constructed to tolerance as stated in Table 6.3.1 Primary Vertical Tolerances unless it cannot be trimmed by a grader
90dbf8c7-ecc2-55f5-851b-5779b4c92f11 | note | Acceptance Criteria and Frequency (Project Specific) - Subgrade level ± 25
89a528bb-2404-559f-86fa-040bd75822f3 | note | ○ average ± 10
0228c360-a2a7-5445-9760-77efd42c6d43 | note | ○ 1 test /20m
d31fd30d-22eb-5d72-aa71-36ab162f8dec | note | Check Item - Dip Sheet Records
700b2cb8-696a-5823-8251-ebbce53066c1 | note | Reference - MRTS04 Cl. 6, Cl.13.3.1 Table 6.3.1
4667bb43-6ad2-4da3-a2d0-c3e69905ba1b | checkpoint | Straight Edge Testing: The gap beneath a three metre-long straight-edge placed anywhere on the surface at Subgrade Level shall not exceed 25 mm, due allowance being made for design shape where relevant.
430c1064-9176-5d21-963a-1d982c2d081f | note | Acceptance Criteria and Frequency (Project Specific) - 1 test per 20m (Left and rigt)
69cef597-d6bf-510d-b611-0b0cd88df429 | note | Check Item - Dip Sheet Records
aea4cb93-5d94-55bd-8eb6-cee2ae58753a | note | Reference - MRTS04 Cl. 6.3.2
22c7696f-b5f7-4604-bac5-078b7f706c72 | checkpoint | Subgrade shall not pond water and be free draining.
ee3f0de5-1289-5d21-9832-54fc089df202 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
27d35cc5-2f2a-57cd-9915-f501d5cc6db4 | note | Check Item - Check Item
2735dbc5-bc10-590c-8d52-e9d131cf694b | note | Reference - MRTS04 Clause 6.3.2
d29bec99-ce81-478e-9914-09546372b663 | checkpoint | The subgrade shall be constructed and tested to subgrade level in accordance with the requirements, prior to construction of the pavement.
fd99c80a-e4d5-5e6d-820d-3341301911b9 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9689f3c8-6f8f-582e-86cc-3749ff76faa9 | note | Check Item - Hold Point 12
588b8fee-feba-5660-b3e8-65ef5e9ec406 | note | Reference - MRTS04 Cl. 18.3.1
8961b269-d42a-4aca-9c72-c9a85e2e60ec | signoff | Hold Point
f404e6f4-6862-4458-8bb9-9ff60aa5d627 | checkpoint | Final Verification
6a0e25ec-5ac3-54c6-bb3d-81c48c96face | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
e6991ddf-3319-5a99-ab31-1dc142870fd9 | textbox | Print Name:
0a56d422-f69e-5b33-a54e-39ab302ceb6f | date | Date:
a927e1e1-8817-5f07-b08b-952208097ac0 | note | Project Manager Verify that the Above has been Constructed according to Specification
9add145d-4750-5c64-b91a-c3c24cfc3baf | textbox | Print Name:
73ce43db-0274-52d5-ae73-7bf9484fa9b9 | date | Date:
94ade3f6-76d9-4328-bb98-d1a62691cd02 | signoff | Signature
dec6fe1f-28c5-485b-855c-90259b5d17f3 | section | Final Sign Offs (to be completed at closure of Lot)
48f3996c-3cc5-4f37-8d3a-a3c0916bf891 | checkpoint | Agreed Quantities
bd2df042-5a48-4ba0-a510-e1afc3ab6a78 | signoff | Agreed Quantities Sign Off
7dc70632-3867-4dda-9cc5-03670935d239 | checkpoint | Closure of Lot
0675f4f6-8971-4298-b312-14e2fd6a2d2e | signoff | Closure of Lot Sign Off
180b7bef-1743-42d3-a2e3-af427945f2e6 | checklist | 05.01 - Unbound Pavement | itp | 05.01 - Unbound Pavement
b2d0195f-1de0-4c17-8fdb-77865b6c0db0 | section | Details
2cfd1d63-4b2c-4406-8a82-cfa348469c48 | checkpoint | Define lot size. Maximum lot size for unbound pavements is 5000 tonnes for supply and the lesser of "A single continuous layer completed in one day's production" and 500m for construction
134dd6df-6696-5115-afba-574aaf78a9c5 | note | Acceptance Criteria and Frequency (Project Specific) - Supply of unbound pavement materials - 5000tn
765e81c4-f7c1-503b-980f-ad902cca9082 | note | ○ Maximum lot size - A continuous single layer constructed in 1 day's production
e1a966cb-c694-530d-bc13-e8d11ebce501 | note | ○ Road roughness testing: maximum lot size 100m
61176531-688f-5e3b-a79f-cdc605c840a7 | note | Check Item - Check Item
98d1ce5f-9122-576c-9d66-c88c8aed8fe8 | note | Reference - MRTS05 App. A Table A1
37c95ea4-84b5-46fe-b458-883a0d75ba5d | checkpoint | Copies of current Quarry Registration Certificate (Type 1, 2 or 3) or quarry assessment (Type 4) forwarded to the Administrator at least 7 working days before material deliveries to the stockpile / pavement are to commence.
40ef9295-ad54-55e5-a5d2-89bea012bce1 | note | Acceptance Criteria and Frequency (Project Specific) - Submission of Registration Certificate per quarry
9192bef0-afb9-5766-8933-2ac4891852a8 | note | Check Item - Milestone
42bbe6b7-db7e-5660-ad42-647ffa0828d1 | note | Reference - MRTS05 Cl.6.2
302d9cb7-065e-442d-9d8e-5c27f8c821e5 | checkpoint | No unbound pavement works shall commence until all relevant construction procedure have been accepted by the Administrator.
cb8e078c-f302-5446-944f-49252707a4c1 | note | Acceptance Criteria and Frequency (Project Specific) - Approval of procedure by from the Administrator
5cd35a9e-f9ad-5c81-9b40-54e914ee1176 | note | Check Item - Hold Point 1
abd1f8f6-da57-5add-96e0-61cbd7081642 | note | Reference - MRTS05 Cl 5.2.1
4c5baa98-827a-4d23-a608-ba0b23472e6d | signoff | Hold Point
40d1eaa4-3fff-49eb-a40d-63371f2299df | checkpoint | The Material Production Procedures shall be submitted to the Administrator at least seven days prior to the commencement of material production for the works.
474d944d-2463-5345-a1a7-adb0ddcb0d0a | note | Acceptance Criteria and Frequency (Project Specific) - Submission of production procedure
6c3e24a6-1433-5bf6-850d-9411d4b2a35a | note | Check Item - Milestone
a7e74c4f-1d6f-5012-960f-55d80009c7a8 | note | Reference - MRTS05 CL 5.2.2
3c7819b4-56f1-47f1-88f2-355de96b0778 | checkpoint | Submission of Construction Procedure for unbound pavement construction at least 14 days prior to commencement of works.
b48e2b5f-50f5-5f0f-a8f0-65d1fbec0abd | note | Acceptance Criteria and Frequency (Project Specific) - Approval of procedure by from the Administrator
e9f8b3c1-0b65-55cb-8ac4-ec4bba697686 | note | Check Item - Milestone
ec0f7584-25b1-54d4-b0d3-f7539e5bcf56 | note | Reference - MRTS05 Cl 5.2.3
b0fa6185-3e04-4a8b-8c3b-6e2011a38b30 | checkpoint | The written permission from the Administrator to use the quarry or source is required prior to material being supplied to or used in the works.
021c9bb5-5244-5774-8bb6-19fb6bc6b119 | note | Acceptance Criteria and Frequency (Project Specific) - Written Permission from Administrator
e9ea309a-887c-51d4-9901-7d6796dd3e25 | note | Check Item - Hold Point 2
05c120ee-9e7d-5fbc-a3af-d36c34e1d52b | note | Reference - MRTS05 Cl.6.1
9ac56f01-c81c-4c19-aedc-7ad1ed3fca78 | signoff | Hold Point
516eb31a-7076-454a-951c-26ca441d7a68 | checkpoint | Layer Thickness between 75mm and 250mm for all subtypes excluding Type 1 (HSG).
c0f94b1e-9cb6-5ddf-baf3-281618bc4a70 | note | Acceptance Criteria and Frequency (Project Specific) - Visual, Layer Thickness 75mm - 250mm
87663821-fc67-53a8-9c48-8781db79b7d3 | note | Check Item - Check Item
a3913c65-d2b7-5090-8698-ccdd07c9e9a5 | note | Reference - MRTS05 Table 8.3.3
73f62f54-180e-4bd2-9c2e-acd3e97d582b | checkpoint | Minimum value of Relative Dry Density Requirements - C.V of RDD = 100% MDD for Base course 2.1, 2.2, = 100% SDD for other than base course 2.1, 2.2 and 100% SSD for all layers of 2.3, 2.4 and 2.5.
1fa3de43-7b99-51d6-8506-5dde399af6ed | note | Acceptance Criteria and Frequency (Project Specific) - C.V of RDD >= 100% MDD
94189fc4-3a72-5695-80df-679ef5852aa4 | note | ○ Normal: 1 test / 500m2, 4 per lot,
d3be5d6a-6886-554e-9458-e889056f63ba | note | ○ Reduced: 1 test / 1000m2, 4 per lot
7cde7dd3-de81-55f5-81c0-0987cbb260a7 | note | Check Item - Check Item
9d6ed987-7797-56bf-a9a2-d960a5b328f6 | note | Reference - MRTS05 Table 8.4.3
86af32c9-578b-47cd-938d-c435b66a3123 | checkpoint | Unless agreed otherwise, a trial placement of materials of a minimum size of 1000m2 is required.
fa92f568-be88-502e-a95b-2a979172609e | note | Acceptance Criteria and Frequency (Project Specific) - All tests as described by this ITP and MRTS05
f5f6c37e-bd58-5665-88ab-8d14819c9c0a | note | Check Item - Hold Point 3
aae3b82d-a99d-517c-a740-ed0d63ffd6a9 | note | Reference - MRTS05 Cl. 8.2
282f84f6-305a-4319-a1d2-3a75129dcf2e | signoff | Hold Point
a6bee067-f10a-45fe-9724-7e17f957454e | checkpoint | Moisture content such that the degree of saturation is less than 70%(modified).
b5628d31-f5d1-593f-9530-7f5bb78d3986 | note | Acceptance Criteria and Frequency (Project Specific) - S < 70%
336f1d1b-11d9-5687-883f-82b588d7047c | note | ○ Normal: 1 test / 500m2, 4 per lot,
9fa57cf8-6b87-5ccc-bca3-3132caa5b067 | note | ○ Reduced: 1 test / 1000m2, 4 per lot
ca6a6b0e-1e33-500e-9317-fd0566c220fd | note | Check Item - Hold Point 4
a9d21410-f35f-51d2-9109-a8f8e0a9ad7f | note | Reference - MRTS05 Table 8.3.4.1
82173304-ea61-4204-832c-8b7ec7c408a4 | signoff | Hold Point
5a9f8369-f757-4a56-b076-8e2d8948c64d | checkpoint | No visible segregation of material. Partical Size Distribution Q103A.
0a86cab4-115e-5782-81e5-4d97d792c97d | note | Acceptance Criteria and Frequency (Project Specific) - Min 1 per lot
2c51926e-58fd-5927-b8c8-efd010734c0f | note | ○ Additional tests as directed by the Administrator
fc226cef-6903-5d7c-b0c6-0ed9bd791f6c | note | Check Item - Check Item
99bf8804-c087-5719-9342-192a60fd1da4 | note | Reference - MRTS05 Table A3
45d55ab5-eb2e-4b74-9f71-fb2c7585e0e9 | checkpoint | Geometric Tolerances in accordance with MRTS05 Cl.8.4.4.3
796255ea-dda1-56eb-957f-68ea766083e0 | note | Acceptance Criteria and Frequency (Project Specific) - ±10mm when covered by AC
05c97cf2-cb0f-515d-bb66-0f269cac554c | note | ○ ±15 mm in all other cases (1 test / 20m)
afe21e29-a4e3-5c1a-b26b-dd4b85ab17ab | note | Check Item - Check Item
1ecb244c-e810-59b2-b352-050079061176 | note | Reference - MRTS05.1 Cl.8.4.4.3
721788b4-d6eb-47c1-bdcf-ee222a08c818 | checkpoint | Geometric Tolerances: Horizontal tolerance of ±50mm, or -50 / +250mm for pavement edges not adjacent to any other section of pavement and not adjacent to any structure or adjoining road
291bb234-9d27-55be-b153-90740e6b1d50 | note | Acceptance Criteria and Frequency (Project Specific) - ±50mm, or -50 / +250mm if not adjacent to adjoining pavement (1 test / 25m)
5360e074-8361-5702-91dd-b5b3f9dbb359 | note | Check Item - Check Item
014d1ccb-40b1-524a-8a62-c4fc4222df17 | note | Reference - MRTS05 Cl.8.4.4.2 Table A4
9fbed9de-fe58-41e9-ba23-cd98bbde1f11 | checkpoint | Deviation from a 3m straight edge shall be less than 5mm for material types 1,2,3 and 4
cb4f1327-b1d0-5bce-8850-612c3f3293a3 | note | Acceptance Criteria and Frequency (Project Specific) - Straight Edge Test
70f08582-71cc-52e6-afc0-78bf3733ab88 | note | ○ Less than 5mm
474533d6-d08b-572d-9c9d-8e71d7f28302 | note | ○ 1 test per 20m
7c171239-5647-5b0e-ae21-d482c124c696 | note | Check Item - Check Item
88e595cd-01d2-582f-9e63-d2bbd6974351 | note | Reference - MRTS05 Cl. 8.4.5
05125ef6-8954-45bd-a3d1-7f24ad06ab33 | checkpoint | Each unbound pavement layer shall be tested for perceptable surface deformation by 'proof rolling' the pavement, in the presence of the Administrator.
f8cb9431-12ad-5b52-9c7d-4fcbc73bfee7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual, Continuous testing
564c931e-6f8b-5ecf-8578-5359b3545cda | note | Check Item - Witness Point 2
7cf7089e-ef1d-58cb-a6e3-a6df0b7d0191 | note | Reference - MRTS05 Cl.9.4.7
9f569a36-0671-47ab-88be-238b0723a5b2 | checkpoint | Additional Geometrics (final layer only) - The crossfall shall not depart from the corresponding crossfall shown in the Contract by more than 0.5% absolute.
a7159c69-9ca7-5bde-b742-b74ef1e3a494 | note | Acceptance Criteria and Frequency (Project Specific) - 0.5% deviation from crossfall (1 test / 25m)
6eabdcb1-ae4f-57e0-b6ca-f8901f6dd292 | note | Check Item - Check Item
e09385cf-fc94-5e37-83c3-2f2b38057bcd | note | Reference - MRTS05 Cl.8.4.4.4
e3059779-d389-4ee9-8be8-788404be26c9 | checkpoint | The contractor shall provide a methodology and calculations to determine the road roughness to the administrator for acceptance. Roughness shall be less than 2.31m/km.
ebf09872-d7e1-54d5-8c6b-f76d46301362 | note | Acceptance Criteria and Frequency (Project Specific) - Less than 2.31m/km
e18e657f-1bfc-5e36-bfbf-8dd3ad199ff7 | note | ○ 1 test per 500m
35bb7aec-0be7-590e-8326-3bd2de25c5bd | note | Check Item - Check Item
8f880509-f1ac-583d-b19b-15e33b6e7bed | note | Reference - MRTS05 Cl.8.4.6
ffd2d066-d724-4e17-9907-1f7c23f2f6b8 | checkpoint | The finished surface of any unbound pavement layer shall:
56d89795-3a99-50b0-86f7-92d70800bced | note | – be hard and homogenous in apperance
dbca24b7-da71-5a64-bbca-481607d7b59a | note | – not have any loose, segregated or contaminated areas
4508d740-2450-53e4-9324-aa0d9b658f5a | note | – have the coarse particles slightly exposed
1c78e483-1ef6-52bf-b80b-bb7e4525cd70 | note | – not be affected by delamination
029b8c5b-e508-5314-a6b3-a5d1836e0fc7 | note | – not show signs of water pumping, and
8989a973-05a2-56b9-be92-3fa7fc4ca1b8 | note | – not visibly deflect under load when proof rolled in accordance with Cl 9.4.7
6cd251e7-89eb-54e1-8dfd-6cbec378f8fe | note | Acceptance Criteria and Frequency (Project Specific) - Visual
06d669ae-bc03-5c18-8211-0654b67a5df2 | note | Check Item - Check Item
fb5ef54c-f7f2-5522-a794-5d0ae5894ec4 | note | Reference - MRTS05 Cl.8.3.5.1
921af861-62b9-48d6-8a7d-f015d59da87c | checkpoint | The Contractor shall not incorporate materials into the work unless it has demonstrated that the material complies fully with the requirements of this Technical Specification before delivery of the material to site
68efa7a0-5588-56b1-ba0e-8ec9398579d5 | note | Acceptance Criteria and Frequency (Project Specific) - Test Results per lot
01837d6e-8df9-543b-826d-d51a6e244b07 | note | Check Item - Hold Point 5
df803ddd-2ce3-52c3-999f-56675f044799 | note | Reference - MRTS05 Cl.9.1
e929f285-8196-41bc-801d-05f42986dbb3 | signoff | Hold Point
7d755840-b2d5-44a1-a2a8-31c474c8f68d | checkpoint | Unless otherwise approved by the Administrator, no unbound pavement layer shall be covered by a subsequent layer of pavement or by a surfacing until Hold Point 6:
806f057d-ab3a-5add-82a6-b1444161daad | note | a) all testing has been completed
5da26345-a470-5c36-89f3-9b0e7b965697 | note | b) the surface finish of the layer complies with the requirements of Clause 8.3.5
d26c079f-683a-573a-a31c-c564e2b177a7 | note | c) all test results comply with the requirements of this Technical Specification, or any nonconformances have been submitted, with corrective actions proposed by the Contractor, and accepted by the Administrator
448d57ec-71aa-54d0-a220-1ab416ba346d | note | d) the layer has been presented to the Administrator for inspection, and
44d1fbfa-ca7d-56fb-b512-9ee194069898 | note | e) the As Constructed Survey requirements of the lot have been met as specified in MRTS56 Construction Surveying and notice of such works has been provided to the Administrator.
77fa3dbd-b403-5cbd-814a-24a3bc768062 | note | Acceptance Criteria and Frequency (Project Specific) - Adminstrator Acceptance
b2f1c2d4-6151-5dd7-af67-4e4061a76a16 | note | Check Item - Hold Point 6
fa13500c-67aa-5b7c-9a4b-868108c34b62 | note | Reference - MRTS05 Cl.9.5.1
1bf01aa7-b1c3-49ea-919b-4acd0f9f0b10 | signoff | Hold Point
5a6a699e-34c0-46bb-aaf2-c48cce59940e | checkpoint | Final Verification
41ff0546-2cb0-5875-a3e8-a3536836ce47 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
12e686b7-313a-5287-86df-8faaa26bac7a | textbox | Print Name:
90c2ca44-e82f-5a68-a3a1-4573f9f1d0d0 | date | Date:
50324302-4e08-507c-b944-9c95adc53793 | note | Project Manager Verify that the Above has been Constructed according to Specification
988a4ad5-9ce6-5d11-a635-dae887f8ecce | textbox | Print Name:
a9126210-1870-548d-b746-8c9a5ba85657 | date | Date:
9e543e0e-1886-449f-b8d7-08be63dfb0e8 | signoff | Signature
f0fa23f1-abbd-4434-bd4e-29b896d48789 | section | Final Sign Offs (to be completed at closure of Lot)
15483250-314e-457e-9b2a-5d93c6ad6f9b | checkpoint | Agreed Quantities
072af264-d8b6-4b34-b7a1-a37011321619 | signoff | Agreed Quantities Sign Off
27270277-cd15-4ffc-925a-4725b8ef3be3 | checkpoint | Closure of Lot
6fb9135f-ad64-4c0e-9161-dd562f7e0bbd | signoff | Closure of Lot Sign Off
1ee53336-9c11-4df2-ba64-21c1b7d173b3 | checklist | 10.01 - Plant Mixed Lightly Bound Pavements | itp | 10.01 - Plant Mixed Lightly Bound Pavements
67c85e21-faf3-45ac-977f-d6209541bd05 | section | Details
be39606e-cd4f-45c8-8606-4e7c1f72eabd | checkpoint | Construction Procedure: Documented procedure shall be prepared for all construction processes as defined in Clause 6 of MRTS50 and shall be submitted for approval at least 14 days prior to commencement of lightly bound pavement works (No work shall commence until accepted by the Administrator)
1e603f8f-0a40-5f96-9c6e-dedfe0a3cbf0 | note | Acceptance Criteria and Frequency (Project Specific) - Acceptance
f9381cb6-29d0-55ed-98c2-09659f9b9b10 | note | Check Item - Hold Point 1, Milestone
0781c97b-b485-5c25-8579-a218a970c41d | note | Reference - Clause 5.2 MRTS10
cf0d74d9-e76c-49a8-a01d-c8f0da0b8c45 | signoff | Hold Point
a80485bd-ebc2-4e6a-866b-6424e749d73c | checkpoint | Material Requirements - Unbound Pavement Material: The Contractor shall not incorporate unbound pavement material into the works unless it has been demonstrated that the unbound pavement material lot conforms fully to the requirements of MRTS10. All conformance results shall be no more than six months old.
6299d2c1-b745-5c3e-bcfb-783859eda651 | note | Acceptance Criteria and Frequency (Project Specific) - Acceptance
f44ee2f9-3868-510d-bb08-fc47e392bbb2 | note | Check Item - Hold Point 2
8a1f5d46-c58a-5658-982c-3306b58eda3b | note | Reference - MRTS10 Clause 6.1.1
8b488501-06fd-4160-8aba-c15fff0de91e | signoff | Hold Point
4dcbabf8-6c13-47d1-b735-f87c055a5992 | checkpoint | Mix Design Report: A mix design must be submitted at least 14days before mixing operations commence. Construction of the lightly bound pavement layer shall not proceed until a conforming mix design (refer to Clause 7.2) has been deemed suitable and accepted by the Administrator.
9c8b73e6-39da-543f-a52a-51c360a6af6e | note | Acceptance Criteria and Frequency (Project Specific) - Acceptance
7ae5e9bb-e6f3-53fc-932d-2d02b0ac1024 | note | Check Item - Hold Point 3
2532c70c-04a0-565c-8389-de6f5d60d28b | note | Reference - MRTS10 Clause 7.1
907ec115-8522-4596-bec4-b92baf82b250 | signoff | Hold Point
df8746ea-218c-472c-8860-c7b66ff4d70b | checkpoint | Moisture Content - The Contractor shall nominate upper and lower moisture content limits as part of their Mix Design that will ensure:
9eb9f0c5-90d6-5ba9-b45b-0bc40e7e162a | note | a) there is adequate moisture to achieve the specified compaction standard
587e524c-4ee2-5a8a-a9aa-8b2f23e3e473 | note | b) the constructed lightly bound pavement layer is trafficked in accordance with requirements of Clause 8.2.11, and
bbd5f0c2-1b58-545e-9bbc-5e0811d719a6 | note | c) the lightly bound pavement material does not exceed the optimum moisture content (OMC), determined in accordance with Test Method Q142A.
345a855e-431f-5f3a-90da-8e7b0d0b4bae | note | Acceptance Criteria and Frequency (Project Specific) - Testing - AS1289.2.1.1
d0b949c0-5eb3-5eda-903c-f5dc9968f3c9 | note | ○ 1 per 500m2
6bbb638a-18d3-575a-b73f-347c3a3a3368 | note | ○ 4 per lot
b3e6716b-c13f-5647-8094-049507c8a6ce | note | Check Item - Test Report
e78f9de8-ff40-50dc-8dbe-d23d69289a5e | note | Reference - MRTS10 Clause 8.2.5, Clause 9.4.8 Table A3
5fd9e42e-e361-43cf-b7af-916b89015b68 | checkpoint | Construction - Trial Pavement
0ed59cf1-7b82-5eb6-b8f7-f17a8bab8bfc | note | ○ Unless otherwise agreed by the Administator, a trial of the manufacturing and laying operations shall be caried out prior to commencement of the work.
d3291cad-a391-594b-a486-b734370e1983 | note | ○ The trial pavement shall be located within the site and be not less than 1000m2. It shall determine the characteristics highlighted in Clause 8.1 MRTS10. The trial may be incorporated into the permanent works at the Administrators discression.
da77cad6-963c-51fb-ab6f-64e4effe2eb8 | note | ○ The Contractor is to undertake the material and construction compliance testing nominated in Clause 8.1 and the finished pavement complies with the technical specification of MRTS10. If deemed not conforming, further trialing shall be undertaken.
75cd7869-0bfb-5d96-92df-9e844a8f79ba | note | Acceptance Criteria and Frequency (Project Specific) - Visual & Check
ff72f1ba-3afd-5dbf-8761-adb0579383db | note | Check Item - Witness Point 1 /Hold Point 4
d6211123-9982-5e5f-8c2a-75494a322491 | note | Reference - MRTS10 Clause 8.1
8ae1d205-5518-4422-8f1c-f7d039911883 | signoff | Hold Point
7a9b5425-fcd2-4c6a-a527-d8cf2891b311 | checkpoint | Material Compliance Testing - Each supply lots shall be sampled and tested for compliance in accordance with the testing frequencies specify in MRTS05. No material shall be incorporated into the work unless it has demonstrated compliance fully with the requirements of MRTS05 and MRTS10
b41af4e8-3984-56e8-ade4-52a4c7fe4c06 | textbox | Material Type:
40df86b5-1248-5f0c-a959-2f73f69eef60 | textbox | Material Stockpile Lot Ref:
baa1c4cd-e5aa-5d3e-8744-5899d04b677a | note | Acceptance Criteria and Frequency (Project Specific) - MRTS05 Cl. 7, Table A1, MRTS10 Cl.6, Table A2
ae4a3d53-e141-5bae-b4f4-00be2e2eb5e1 | note | Check Item - Check Item
0579a827-35e9-558c-b5c3-c64044b01c81 | note | Reference - MRTS05 Clause 7
d1814e6f-3b2e-47d1-8bd3-9dcb6138f88a | checkpoint | Equipment - Equipment as specified in approved construction procedure
6f57094a-68d3-5613-b4b7-777ab8cdfd58 | note | Acceptance Criteria and Frequency (Project Specific) - Construction Procedure Approval
1d9e799b-28e7-519d-a7df-25568c02e6d4 | note | Check Item - Contract Notice
a3b6d9d5-509b-524e-8c2a-4195bf7a460c | note | Reference - MRTS10 Cl.8.2.1.4
898916a0-da99-4c8e-8ef5-0f97ccbde5a7 | checkpoint | Weather Conditions - CMB material shall not proceed when:
2401e60f-a473-5428-915b-8bc624a73416 | note | a) air temperature is less than 10°C or greater than 40°C
e6857ae6-2b68-5a17-abf3-3d59ba609603 | note | b) during rain or when rain is likely to fall during placement
5cf19a6c-7fbd-5eec-be53-8ad5b2f933cb | note | c) evaporation rate due to the combined effect of air temperature, wind and relative humidity may result in excessive drying of the CMB
6cff8605-97f6-5171-8b1e-3c048f5af8db | note | Acceptance Criteria and Frequency (Project Specific) - Check & Verify
f5cf0c98-f684-532d-91e1-6e3fa1f2605a | note | Check Item - Check Item
84681a9f-2352-5267-a724-be9dadc07676 | note | Reference - MRTS10 Clause 8.2.4
f8544904-20a5-4743-b6ab-8f35869983ec | checkpoint | Allowable Working Time - Define as the maximum period between mixing the modifying binder into the unbound granular material and the completion of compaction. The allowable working time for the plant-mixed lightly bound pavement is to be the lesser of the following:
920584b7-4838-58f1-899d-d45b7368f667 | note | a) Working time determined in accordance with Test Method Q136A
53c42bb1-e817-57f5-9e94-df4a3ebc2936 | note | b) Four hours
6fb531f0-2a37-596b-95a2-a3083f1c9d6e | note | Acceptance Criteria and Frequency (Project Specific) - Monitor
3cbd147e-9578-58bd-9265-346a2aa6f0e0 | note | Check Item - Check Item
77284100-1616-5acd-be29-7bf00f36a218 | note | Reference - MRTS10 Clause 8.2.3
707878cd-b81a-4dc8-84dc-2ee980b3318d | checkpoint | Construction Joints - Deemed to be fresh when the material compacted on each side of the joint has been modified, placed and compacted within the allowable working time. In multi layer of lightly bound pavement, longitudinal joints of each layer shall be offset from the underlying layer by a minimum of 150mm
7e0882bc-b925-501e-b60c-0cbb12ec4164 | note | Acceptance Criteria and Frequency (Project Specific) - Check & Verify
41dde831-2f0d-5ae3-beff-ccafb6fe4050 | note | Check Item - Check Item
d751f2de-cc36-514b-9038-479584f64e42 | note | Reference - MRTS10 Clause 8.2.10
0b839170-8a86-4767-8e94-5c2592f359c8 | checkpoint | Fresh Joints - Where fresh joint between adjoining or adjacent run is to be compacted, the outside 300mm of material from the first run shall be left uncompacted until the adjacent run is ready for compaction.
7f4e8c65-9454-5d36-a96e-b0c485b02fed | note | Acceptance Criteria and Frequency (Project Specific) - Check & Verify
dc27c377-e866-5f3c-b6ef-e649901b8d3f | note | Check Item - Check Item
d9bcc7d1-590e-5429-a7bf-9b45fa709c52 | note | Reference - MRTS10 Cl. 8.2.10.1
d9b313ef-22d3-49ac-aa0e-ac6ee82fcfb6 | checkpoint | Other (Cold) Joints - Joints that are not fresh shall be cut back to form a neat, clean vertical face. Cutback distance shall be a minimum of 150mm and before placing the adjoining layer or adjacent layer, the cut back edge of the existing layer shall have a cement/water slurry at a rate of 2kg/m2. The slurry cement/water ratio to be 0.6 and 0.7.
632baaaa-03cd-533c-8efd-b866f3feef8b | note | Acceptance Criteria and Frequency (Project Specific) - Check & Verify
6cc113b5-5bf7-5228-9fe0-f75935199eea | note | Check Item - Check Item
7fc3cb24-c57a-55b9-b2b9-978f8654bebc | note | Reference - MRTS10 Cl. 8.2.10.2 Cl.6.4
89a369f1-a4b7-4094-97b5-0d94cbb414bf | checkpoint | Curing of CMB Layers - The surface of an existing layer of lightly bound pavement shall be water cured until placement of the next layer and/or bituminous surfacing is applied. Unless approved, within 7 days of placement the lightly bound pavement shall be covered by a subsequent layer and/or bituminous treatment. Water curing shall be completed in accordance with Cl. 8.2.1.5
5f9dbd8f-2b0b-55f2-a04e-9df53287b9fd | note | Acceptance Criteria and Frequency (Project Specific) - Check & Verify
4ab178df-e80e-52a7-a37c-7c83c0963ba1 | note | Check Item - Check Item
ecab715e-1ff8-5d78-89da-79f83db9d5ff | note | Reference - MRTS10 Clause 8.2.9
3f273112-1cba-47a0-aa6e-a59f64a01ca0 | checkpoint | Trafficking of CMB Layers during Construction - Unless approved by the Administrator, lightly bound pavement layers shall not be opened to either construction traffic or general traffic until the lot has been tested for, and passes proof rolling (Cl 9.4.10)
b05330f6-d1d3-5820-a6f4-77fe14bfd2c5 | note | Acceptance Criteria and Frequency (Project Specific) - Check
2fb1b30a-2aff-5ff0-9e2f-9a1251fcce2c | note | Check Item - Check Item
e9935c03-0b5c-50fc-8995-60be72075452 | note | Reference - MRTS10 Clause 8.2.11
88a6c33f-7bed-457e-8e45-d759ae2fe7c3 | checkpoint | Compaction Standard - The characteristic value of relative compaction shall not be less than 100% standard, except for the upper most layer of lightly bound base which shall not be less than 102% standard
7930a3f4-e16f-52a8-920b-1ef97b3c180e | note | Acceptance Criteria and Frequency (Project Specific) - 102% standard upper most layer
0b239e6e-cde0-539f-a1be-bd130eec635e | note | ○ 100% standard lower layers
efa2a642-081d-5dfd-a300-85828c3dec48 | note | ○ (1/500m2, min 4/lot)
1a545784-8ae9-5db6-ab13-72dc62bafc17 | note | ○ (1/1000m2, min 4/lot)
85814890-5927-52b3-8a50-6e8e78a2a011 | note | Check Item - Test Report
e06d90c0-0383-591c-80c0-bc479d5f96da | note | Reference - MRTS10 Clause 8.3.4
6928350a-e8be-467d-88c2-20aae5db7c39 | checkpoint | UCS - Unconfined compressive strength between 1 - 2MPa
03f7cf30-ccfd-575e-b05e-4c36924461fb | note | Acceptance Criteria and Frequency (Project Specific) - UCS 1-2MPa (1 per lot)
af1a573a-f56e-5b8c-95a9-7b37f839ef2b | note | Check Item - Check Item
f55d7e5f-4012-5d54-944f-f4e3b1d2fa38 | note | Reference - MRTS10 Clause 9.4.9
d87ac9f4-682c-4577-baee-6086926d98a2 | checkpoint | Stabilising Agent Content - The actual content of stabilising agent for each lot shall be represented by both the:
ca37b72e-04e4-56b1-acad-953d8aca65c2 | note | a) minimum characteristic value of the actual content of stabilising agent, and
930d8b43-6eb0-5e15-baac-7386b7e4e1c2 | note | b) maximum characteristic value of the actual content of stabilising agent.
ceb33d30-9c0f-52a8-a2eb-c9149bf34404 | note | When UCS tests are being undertaken, the sample being used must also be tested for stabilising agent content.
1d8a5e7c-f243-5856-9234-83568192110a | note | Acceptance Criteria and Frequency (Project Specific) - Target content minus MPV
9422ec2d-8f2e-56f9-9d4e-b46a6b2654ef | note | ○ Min. test 1 per lot
6fd50913-981d-5379-82e4-f6eca07ce0f3 | note | Check Item - Check Item
ba7fce6d-6cc0-5a14-974c-13e6f1ec0632 | note | Reference - MRTS10 Clause 9.4.6
88f262db-cd5f-48bc-a9df-10eee83c5296 | checkpoint | Geometrics - Horizontal Tolerances
0633fc48-642e-5716-b225-3b4ef62bc758 | note | Shall not be more than ± 50mm except for the following:
6135eebe-4075-5931-b689-44d932b74303 | note | a) Pavement edges not adjacent to any other part of the pavement and not adjacent to any structure or adjoining road, transverse tolerance shall be -50mm + 250mm
210ec9cc-e367-55c3-a64b-128f6c4724f7 | note | b) Where alignment of the pavement with an existing structure is necessary, the new work shall be joined neatly to the existing in a smooth manner
5fb0a9e0-b53b-5a63-9c17-36813b7b2439 | note | Acceptance Criteria and Frequency (Project Specific) - -50mm/+250mm (1 per 20m)
b0a8f2ac-2dbc-5d63-89c8-38cc37864cd6 | note | Check Item - Survey Report
63f1c00e-4c42-5b88-8754-bd36369380b7 | note | Reference - MRTS10 Clause 8.3.5.2
ac4ef22d-86c3-4cb7-9539-c9c680c806d1 | checkpoint | Geometrics - Primary Vertical Tolerances
afe55e1c-1708-54ab-8122-438d8f85a973 | note | The vertical tolerances specified in Table 8.3.5.3 shall apply or:
e0bb5ddc-40ff-5eb7-8272-dacbf38befc3 | note | – the surface level measured at any point on the surface of any layer.
38d89715-a66f-5787-af94-85ef57c64be4 | note | – The average total thickness of the constructed course compared to the specified total thickness.
180289d7-8b6b-5a2b-9588-835d284b52f7 | note | Acceptance Criteria and Frequency (Project Specific) - ±15mm for layers that have been hard cut
df4c38c9-39f1-5fe9-8c8e-9141716b12cf | note | ○ ±10mm for all other layers
35a8136a-7404-5de0-ab78-5df67cc04b76 | note | ○ Layer thickness -20mm, +unspecified
3202671c-6b00-59e2-a4da-47da7318705a | note | ○ (1 per 20m at shoulders, lane lines & grade changes)
5faf46dd-303f-597f-89b7-64db5c842283 | note | Check Item - Survey Report
ada5b336-b05d-5a9a-b687-a1c141d1dafb | note | Reference - MRTS10 Clause 8.3.5.3
d161bf3d-ad82-4fbf-b456-6e4e7fd880cb | checkpoint | Geometrics - Deviation from a Straight - Edge: Deviation of a straight edge place anywhere on the surface shall not exceed 5mm over 3m
416298ef-8283-591e-8be4-7155012147a6 | note | Acceptance Criteria and Frequency (Project Specific) - 5mm over 3m (1 per 20m and at joints)
9d27c8d5-6b65-5aea-bd1a-c176b71ad75e | note | Check Item - Check Sheet
dbb221f6-6648-5f1c-92ff-4782071f8f1c | note | Reference - MRTS10 Clause 8.3.6
73fcd42c-8b03-4d11-9a9b-610c46af9c33 | checkpoint | Geometrics - Crossfall: Shall not differ from the designed crossfall by more than 0.5% absolute.
9b7aa3df-35b4-5a30-bfba-526484f5765a | note | Acceptance Criteria and Frequency (Project Specific) - Check
ca80a8d3-057d-54c4-b283-02f4f8665b84 | note | Check Item - Survey Report
bfbe7703-e037-52d1-be01-3d2a102b576f | note | Reference - MRTS10 Clause 8.3.5.4
98bec551-d7bf-4bd7-853b-cab8f1ab311d | checkpoint | Proof Rolling - The perceptible surface deformation test (Q723) shall be undertaken in the presence of the Administrator
6424e404-31cc-5d71-b114-8ce4c96d578e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
de4f33ac-aac4-5060-9174-fc200718fbec | note | Check Item - Witnesss Point 2
9f9f112e-e9e2-5c3d-8418-6a5e250290f3 | note | Reference - MRTS10 Clause 9.4.10
f18032fc-c090-40d9-a6c8-4d17eaee3d66 | signoff | Hold Point
d2c06052-3395-4f48-bd4f-c159273216be | checkpoint | Acceptance - No CMB layer shall be covered by a subsequent layer of pavement or surfacing untill all testing has been completed (other than UCS), the surface finish comlies with Clause 8.2.8 and the layer presented to the Administrator.
c0223ade-f8cc-563c-baf5-9f97cdba57c8 | note | Acceptance Criteria and Frequency (Project Specific) - Acceptance
8d525ac5-d081-58d9-8ed0-30590258d35a | note | Check Item - Hold Point 5
f7927ee2-e8a2-5f13-99ed-24b69d04c533 | note | Reference - MRTS10 Clause 9.5.1
46d87793-d0e9-4e64-9364-b34e55f55690 | signoff | Hold Point
72d16dea-4fae-46e4-a49c-60dcee5141bc | checkpoint | Final Verification
b8cf46f9-3697-572b-84dc-588bba611c30 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
9f44ac9b-1bb6-5670-8f95-3b3f61cfcfa2 | textbox | Print Name:
23f58246-afa9-5e5b-9bf2-1f31e4353622 | date | Date:
c58c3949-9a5b-5e4a-9785-e89819fc0773 | note | Project Manager Verify that the Above has been Constructed according to Specification
b925d856-f154-5f2d-9642-cd94b77233db | textbox | Print Name:
7d2fcb78-b6de-5182-b3b2-6443e946c6c8 | date | Date:
1ee9ef25-8574-4594-9c59-706b3f0c9838 | signoff | Signature
0f371af2-e30b-4472-9a61-554eee1126a9 | section | Final Sign Offs (to be completed at closure of Lot)
75db6f8f-1b11-4222-bb8c-90b98c2a1268 | checkpoint | Agreed Quantities
963ad937-cb08-4129-9609-3cff4c84299b | signoff | Agreed Quantities Sign Off
cbb4f2df-508d-419c-b328-493ef8058b2a | checkpoint | Closure of Lot
b5123b71-6a73-46ac-9546-8c329a5dcfbb | signoff | Closure of Lot Sign Off
e6fd1d9d-c59b-486a-8c23-2dce86b344ee | checklist | 11.01 - Spray Seal | itp | Spray Seal
c6c82c3e-100b-465f-be09-79afbd71d45a | section | Subcontractor ITP
70526267-1856-4745-a5fd-b72a5d3f047d | checkpoint-no-value | Attachments
eef6c8a6-6e19-41c6-882e-25cb7c4760e2 | section | Final Sign Offs (to be completed at closure of Lot)
07a03581-89e5-4ab9-8f3a-f3b5ef8b27e2 | checkpoint | Agreed Quantities
71a4b3b2-1b40-46b7-86b1-233178764997 | signoff | Agreed Quantities Sign Off
e632fc34-6772-4e47-8f56-aa3e8fa81c30 | checkpoint | Closure of Lot
0248f845-227b-43e3-a4af-5f54dd13ccd6 | signoff | Closure of Lot Sign Off
7f3293d1-d1ec-4ca2-9a6a-0550f9887f03 | checklist | 14.07 - Demolition of Road Furniture | itp | 14.07 - Demolition of Road Furniture
f2705f94-4ca9-4b5c-96a9-e820127d1388 | section | Details
23ab13ed-7c12-42fa-adf1-c283daebb1eb | checkpoint | Road furniture to be removed are as listed in MRTS14.1.
504cb487-307a-5523-ad36-ef71e699376f | note | Acceptance Criteria and Frequency (Project Specific) - Signange/REGP's and Lighting to be removed
62578065-8cb1-5651-80fd-9c9fa424fb44 | note | Check Item - Check Item
be397293-5c3a-5c9a-bded-d7482d31f2f5 | note | Reference - MRTS14.1
8762f019-2f13-4f74-94df-090274506195 | checkpoint | Existing road furniture demolished and removed in a manner which avoids damaging any adjacent work.
d20bd410-acc4-54c3-a170-fc4dd28adaca | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d6c54744-c512-54a2-959b-83a5f4887ab3 | note | Check Item - Check Item
d691c478-2b2d-558f-8dbb-d047ec96dd92 | note | Reference - MRTS14 Cl.7.3
2f61292f-c189-4957-b8de-7af558ac7728 | checkpoint | Resulting excavations are backfilled and finished so the area is in a safe and free-draining state.
6cada7db-2f67-59cf-8b43-9a1edcc9a006 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f7b563a0-ce65-57a5-946f-7c819d15615f | note | Check Item - Check Item
ddd54910-04e2-50b1-9a90-f392044db4dd | note | Reference - MRTS14 Cl.7.3
462f6ff0-a188-4e54-aa47-ad932a8d4a16 | checkpoint | The Constractor shall submit (7 days prior to work) a schedule of items of existing road furniture to be salvaged in accordance with the provisions of the design documentation
a78dfb3a-be49-5b18-8e6e-dedb71508842 | note | Acceptance Criteria and Frequency (Project Specific) - Submission of Schedule
a7d1c588-4601-57dc-9dae-45c353e85ea4 | note | Check Item - Milestone
3c83817b-7cb5-587f-93bf-8821c5e9087d | note | Reference - MRTS14 Cl8.2
f1e7a7d7-e9f9-414a-ae62-f565bbcd7c12 | checkpoint | Dismantling and removal shall not commence until expiration of the seven day period
807b8d73-e63b-579c-ac67-8248ac2afdcd | note | Acceptance Criteria and Frequency (Project Specific) - Expiry of 7 days since submission of Schedule
e4a50f45-8211-52a2-9de4-133a06ee481b | note | Check Item - Hold Point 1
d9c23519-56ba-5676-a150-22ac38c0cc11 | note | Reference - MRTS14 Cl8.2
4bbe09b3-5169-45f1-95e6-328154752c92 | signoff | Hold Point
06d2adb4-5779-422b-9b54-3cebffe653a1 | checkpoint | The Constractor shall submit (7 days prior to work) a schedule of items of existing road furniture to be dismantled for re-erection in accordance with the provisions of the design documentation
43108e1e-7c1c-5283-a957-2db1723b2507 | note | Acceptance Criteria and Frequency (Project Specific) - Submission of Schedule
d83e24d6-8d8f-5e78-bc1b-46abb0ad939b | note | Check Item - Milestone
cce35e27-f355-5d64-9be6-4cf348e3bc2d | note | Reference - MRTS14 Cl9.2
cf142815-6901-49c2-81da-9d97590f5dae | checkpoint | Dismantling and removal shall not commence until epiration of the seven day period
a7cbc7da-06c5-5dc8-890d-6587646b7056 | note | Acceptance Criteria and Frequency (Project Specific) - Expiry of 7 days since submission of Schedule
b5864e24-28ee-53c8-a0b1-0bedaef2499a | note | Check Item - Hold Point 2
81acf582-238a-5de4-b0ed-cb50f37858f5 | note | Reference - MRTS14 Cl9.2
5ace69dc-2fef-4b72-9690-60b71ddb1ebb | signoff | Hold Point
4b93530a-2373-498a-bd27-4ef10bda9b51 | checkpoint | Final Verification
d5964ec8-6106-5954-b377-560e16e07a92 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
d1e5b178-bc14-57f1-b07f-1169370d1bb1 | textbox | Print Name:
7112d1f8-8a1f-539d-90da-f62d89c5c8ce | date | Date:
37e44e86-ade2-5676-8480-12ff37fcdf40 | note | Project Manager Verify that the Above has been Constructed according to Specification
f009d986-fdbc-5dd7-9fa5-6cf1584e0fce | textbox | Print Name:
a8c082e9-4399-5f5d-b0b9-334ad479e0c6 | date | Date:
34f5fcfa-d6b6-4ce1-b8a3-4ecb41fc645a | signoff | Signature
77e172a5-cec9-492c-8a9e-8603bc3911c7 | section | Final Sign Offs (to be completed at closure of Lot)
ab98f455-881b-43a0-9774-6f16d41a4251 | checkpoint | Agreed Quantities
fbee09d2-e1c8-41a7-a850-2760c937578f | signoff | Agreed Quantities Sign Off
c5b13ec0-2766-42c1-94d6-b40b3f6b7f9c | checkpoint | Closure of Lot
57e480bc-7086-4255-b846-47eb81574a1a | signoff | Closure of Lot Sign Off
04c2938c-220f-4262-b64c-d604f1e2a250 | checklist | 14.13 - Supply and Installation of Road Signs | itp | 14.13 - Supply and Installation of Road Signs
8d7461d8-f730-4e92-b338-526ed52be738 | section | Details
2453fec2-3afc-458a-b3b0-ec384c0472b5 | checkpoint | Not less than seven days prior to commencement of dismantling and removal of existing road furniture, the Contractor shall submit a schedule of items of existing road furniture to be disamantled or re-erection in accordance with the provisions of the design documentation.
89770391-f918-5f7a-97c8-41fa630be8ad | note | Acceptance Criteria and Frequency (Project Specific) - Submission of Schedule
d7188a45-633a-55c8-abd8-80289bb8e459 | note | Check Item - Milestone
05b2b092-213b-54bd-ac08-9774867615f3 | note | Reference - MRTS14 Cl 9.2
60f346a5-c4a5-4ad7-9ca6-f54bfb926d3a | checkpoint | Dismantling and removal shall not commence until the experation of the seven day period.
1e844e07-391b-5428-9080-136f182fd00e | note | Acceptance Criteria and Frequency (Project Specific) - Expiry of 7 days since submission of Schedule
748306df-d796-57ab-9b93-2211856748ab | note | Check Item - Hold Point 2
3ca17df1-8d84-585a-accb-bf595a032816 | note | Reference - MRTS14 Cl 9.2
309ee22a-6bd3-4752-885e-5d72adfe078f | signoff | Hold Point
1e002a18-9634-48ad-b1a8-7c8a405413a5 | checkpoint | All legend elements, including letters, numerals, symbols, colours and borders in all sign faces conform to the MUTCD and project drawings.
947840b2-c594-593a-a4bc-644f55556074 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ff37b9f5-fa1b-53de-b334-4bad5c95de83 | note | Check Item - Check Item
8f0153c4-8351-5df4-b625-bbaae6b8e15d | note | Reference - MRTS14 CL 13.2
9ab0d35f-196d-4c5d-afa2-40ec89c4fe7d | checkpoint | Dimensional Tolerances conform to the requirements detailed in AS1743 and legends and lettering conforms to AS1744.
e065b52f-de45-58ce-ab30-9ef0aadf3753 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c0d48d43-b44e-5b28-a8c8-0b2c3f969c86 | note | Check Item - Check Item
4ae89b79-b166-5543-a99e-b49e7007e063 | note | Reference - MRTS14 CL 13.2
2db2d13f-ac17-46da-9b60-031dfe16a339 | checkpoint | Sign Material conforms with the requirements as set out in Cl 13.3.
c6f582c6-07cb-5960-ab28-9427d7d84cd8 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ac3e1ba4-aa11-534e-9564-5649473c9b8d | note | Check Item - Check Item
bca38804-b197-5873-b266-36fd40b72566 | note | Reference - MRTS14 Cl 13.3
e070eb17-9af5-48d9-9238-52daae5de5a7 | checkpoint | The sign substrate shall be manufactured from aluminium. Other materials may be considered but evidence of the full approval of the department will be provided to the administrator prior to their use.
a247d5b8-78e8-5489-9af1-d6ecf6a6de8d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ab244341-27cf-5ecc-9485-6da060a386bc | note | Check Item - Hold Point 3
488a9e3b-c6dc-58b0-874d-aeb0590734ea | note | Reference - MRTS14 CL 13.3.1.1
ec13a980-027f-4d2b-8e3b-9de4b9f09e1d | signoff | Hold Point
c5f779e9-435c-4b02-8996-6a0dcc6ac6bd | checkpoint | Sign faces are fabricated in accordance with the requirements of Traffic and Road Use Management Manual (TRUM) Volume 3, Part 5.
dd6e4f72-9163-5065-ba44-9b1e01af27c0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
49d1aa01-2efa-587b-a76f-9b789eb943fe | note | Check Item - Check Item
9c6a0834-0e58-5bab-b946-7bbfd0c59a42 | note | Reference - MRTS14 Cl 13.4
1791ba3a-0482-4b87-b049-d4db3ebb039d | checkpoint | Sign posts shall be circular or rectangular hollow sections unless specifically shown otherwise in the design documentation.
689d0cc1-4503-5b38-b218-19048a2b1f92 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
cb8a0df5-1413-5742-a92a-23e307475dfb | note | Check Item - Check Item
0d7acbe3-0f83-54dd-80a0-89fbebbdd06c | note | Reference - MRTS14 Cl 14.2.3
371aaf09-3aea-49b0-aa03-a3c95582c9ea | checkpoint | Post sizes and spacings shall conform to the design documentation with slip bases and fuse plates as required.
ae344e14-5cca-5c96-bd42-2fd6b13029ec | note | Acceptance Criteria and Frequency (Project Specific) - Visual
cc8fc72d-5593-596a-9e9f-176fabc2c7c1 | note | Check Item - Check Item
72e02225-a709-56a9-9db7-2093bd0ab4a8 | note | Reference - MRTS14 Cl 14.2.3
a8a1de2f-0d49-4713-8077-88f36fa89fb5 | checkpoint | Concrete footings shall conform to MRTS70 and to the dimenesions shown in the design documentation.
6434bc7c-b5c1-595c-bf64-ce5f0b8bfaf7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ca03ce04-c60c-56a6-80c4-0429932021c5 | note | Check Item - Check Item
3dd19b77-74c3-5c55-a265-e84868dedc5e | note | Reference - MRTS14 Cl 14.3
f2a0bf56-637c-4065-93bc-dea640f12c19 | checkpoint | Erection of Road Signs.
5a84eea0-1825-56af-a80b-3729492ac206 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
11f48402-39eb-5db6-8558-8fa20540f898 | note | Check Item - Witness Point 1
a824fab8-69bd-5cc9-a650-28aea35ca5cb | note | Reference - MRTS14 Cl 14.4
e37d8a83-c031-4783-b5ab-4106503c011d | checkpoint | Signs erected at the locations shown in the design documentation and the orientation shall be in accrodance with the MUTCD.
b235527d-4279-581a-8bc9-c3d7d3c95f64 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9122c582-bd2d-590f-89e7-ed133192362e | note | Check Item - Check Item
a32ede57-d961-5ed1-a266-0215f5ab0c5d | note | Reference - MRTS14 Cl 14.4.2
f145a16b-cc36-47e7-9331-f4f51af7acb0 | checkpoint | Sign faces installed on the posts and/or frame once all other erection is complete.
c295c1a5-a78b-5e5d-b138-b10a1bc9f233 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
df2a7936-9ee7-5e13-8d25-7939dde88af3 | note | Check Item - Check Item
20fc0060-512b-5468-9b34-34772bcc308e | note | Reference - MRTS14 Cl14.4.5
21ff214b-5626-479c-bd45-8f5bf2f9979b | checkpoint | Welded Mesh Fence shall comply with the details shown in the design documentation & Std Dwg. 1604
b4f5f140-c768-5f9b-a85f-27da3bc69934 | note | Acceptance Criteria and Frequency (Project Specific) - Check
da00a84c-7c30-5a25-8531-192390927ab9 | note | Check Item - Check Item
9493dfa4-9cdf-5118-9ea1-e5ed8a307b78 | note | Reference - MRTS14 Cl 11, MRTS14.1 Cl 6.1, Std Dwg. 1604
7ae39d14-3632-4e2b-b6fd-583e7543d67f | checkpoint | Install Fencing as per Manufacturer's Guidelines - Fencing shall be constructed in the locations and to the details shown in the design documentation.
a00ec114-c54c-5b38-8939-dc204d282cdb | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d0c1e31f-d871-5d7c-beaf-909bf4bf5cb0 | note | Check Item - Check Item
6ab94b70-48ea-5969-bb5f-7a77cf4ce82a | note | Reference - MRTS14 Cl 11 MRTS14 Cl 11.4
a0630b5a-558e-40ad-9b45-fd17ff572682 | checkpoint | Warrenty Statement from sign panel manufacturer shall be provided.
ea7cfd61-692b-597a-ae0c-20cc2c7ca956 | note | Acceptance Criteria and Frequency (Project Specific) - Submission
9539c0a2-36f1-5e6d-b3fc-e1ee93b12f15 | note | Check Item - Check Item
2701c9a8-650b-5492-a2ae-67d290f7bf0b | note | Reference - Annexure MRTS14.1 Cl 7.1
66f944f3-ffc5-4369-b3e1-4409d88dcaeb | checkpoint | Final Verification
fb93263f-4d89-576b-87b3-3535539c3a4d | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
baf2188f-b116-5007-9dae-e46c893b8a90 | textbox | Print Name:
5e557e87-eb57-5c89-b703-57bc4e8c4666 | date | Date:
b8295e3e-3051-5eba-8778-a874b24000bc | note | Project Manager Verify that the Above has been Constructed according to Specification
8bdbca8e-f9fd-544d-ad50-e1979d6130a8 | textbox | Print Name:
2f1751d0-d559-5744-8ab7-9f45629dfe64 | date | Date:
53f21fa8-afc0-4800-b34b-f1043c068576 | signoff | Signature
eb662afa-c219-4564-a940-a234abbcd26b | section | Final Sign Offs (to be completed at closure of Lot)
e6c78038-3816-4037-8709-3634b1557cf3 | checkpoint | Agreed Quantities
702b6223-a46d-4802-9e9a-d54ed7b2163d | signoff | Agreed Quantities Sign Off
97083129-3371-4bd9-a179-3fa0c07397d7 | checkpoint | Closure of Lot
482e20a1-05ef-4aee-ab6a-573792ca9d52 | signoff | Closure of Lot Sign Off
c21bb1ee-20f9-4982-8ab6-ee50288ee026 | checklist | 14.20 - Installation of Steel beam Guardrail and End Treatments | itp | 14.20 - Installation of Steel beam Guardrail and End Treatments
0ca4dc29-adbc-416d-8bf3-61f6cd3fb7eb | section | Details
043a606a-9cbb-4254-ae56-d102dcf03c72 | checkpoint | Manufacture of steel beam guardrail post, panel components and end treats are maufactured by an approved manufacturer.
36b6b694-6a61-5a29-8521-3757baf1b338 | note | Acceptance Criteria and Frequency (Project Specific) - Approved Manufacturer
dd97c9b7-661b-512e-ac65-58058e19399a | note | Check Item - Check Item
b3562f6d-27aa-567b-8ea7-a149c797caa8 | note | Reference - MRTS14 Cl. 20.2
9bcc6d5d-d88b-4b1c-a93f-b1b09f7a9719 | checkpoint | Steel beam guardrail components and end treatments shall only be supplied by an approved supplier.
c57a0592-9c7b-5b76-b07d-4a013f3e1c32 | note | Acceptance Criteria and Frequency (Project Specific) - Approved Supplier
98112f13-f24a-54a2-88ea-da453fd96536 | note | Check Item - Check Item
b2c84b3c-62c5-5656-b8e6-999a12b68f6b | note | Reference - MRTS14 Cl 20.3
63cb3404-f4ea-4b9e-af59-ff2c87636ba3 | checkpoint | Hexagonal head bolts and nuts shall be manufactured to the dimensions shown on Standard Drawings, and tested in accordance with MRTS78. Mushroom head (C) bolts shall be manufactured to the details shown on Standard Drawing 1479 Circular washers shall conform to the requirements of AS 1237.
62860b8d-a585-503a-b8f6-1cdf60fdc2ae | note | Acceptance Criteria and Frequency (Project Specific) - Test Certificates
7bc767c8-faf4-50ae-999b-f26791583c43 | note | Check Item - Check Item
d37fc9a4-4881-58c9-b4ae-44a62754c7f8 | note | Reference - MRTS14 Cl 20.4.7
64aaadf8-6dd3-44d2-bc85-de746400dcec | checkpoint | All panels, steel posts and blockouts shall be batch stamped during the manufacturing process with manufacturer's ID, Metal grade and thickness, and batch number. Single batch <2000 items.
5ac2bd64-24ba-527f-a1a4-d0ff7c20b56d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8e448858-346b-5b2b-8cdb-4c6fac132c64 | note | Check Item - Check Item
d9ec2d0b-f889-5a7e-aa88-059010a48ccf | note | Reference - MRTS14 Cl20.4.2.2, Cl. 20.4.3.2
75a1ace3-9202-4a98-9d55-890438a82f9f | checkpoint | All steel components shall be hot-dipped galvanised after manufacture in accordance with the requirements of AS/NZS 4680.
212b3466-f575-5af3-9889-1135939b340b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8947fb18-6d3c-5d4e-abaf-42b61218e423 | note | Check Item - Check Item
ec3fdc90-ff7a-5359-a35d-f9adc2aabe4b | note | Reference - MRTS14 Cl20.4.1
847afba0-3eee-416a-afa9-2a848be6abbd | checkpoint | All the steel manufacturer material test certificates shall be supplied to the Administrator. The test certificates shall show the full chemical composition including the carbon equivalence, and mechanical test results for yield, tensile and elongation
5818cbd4-c7be-57ea-ab35-4cc2a0f0bc81 | note | Acceptance Criteria and Frequency (Project Specific) - Test Certificates
73e8ecfb-fb04-55b2-b056-645db5e640cb | note | Check Item - Hold Point 7
3c62b573-1ea3-57c4-bdb9-b6db933618a2 | note | Reference - MRTS14 Cl20.4.5
2825c76c-f4ef-4fe7-8d5b-2376673d6dc4 | signoff | Hold Point
ef67ff1d-96a8-47dc-81c1-89a06521d7c1 | checkpoint | If required, the Administrator shall randomly select two post and two panels from each batch number for audit testing.
e76b6d5a-9bca-53b4-b782-22fdfcf6d565 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
281e12f8-dade-548c-be68-5f215b731bd0 | note | Check Item - Witness Point 3
2cda1a05-3511-5392-94b0-02b89fd599a3 | note | Reference - MRTS14 Cl20.4.6.1
af02021c-046f-448b-8461-d662d41bb5c5 | checkpoint | Installation shall not commence until the Administrator has confirmed the materials tested match the material test certificates supplied for the batch of guardrail components.
f9da8cdd-cd73-5a10-9d79-b8848c493709 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
bcac6a6a-e793-553f-88bd-b4679bee95bd | note | Check Item - Hold Point 8
7986fb3c-ecb0-5631-b4d5-f801d9744a37 | note | Reference - MRTS12 Cl20.4.6.3
2ab180ea-0252-4590-9563-b04c7f8a7285 | signoff | Hold Point
035df3ce-0488-4d0b-88ba-d0e45f436324 | checkpoint | A list of component parts and fabrication drawings defining the dimensions and weld sizes of the various components and the grade of materials and relevant standards with which the component materials are required to comply shall be provided to the Administrator prior to commencement of installation of the device or system.
f6bf77fc-8177-5a74-96b7-cbbfc9d009be | note | Acceptance Criteria and Frequency (Project Specific) - Visual
248fc7f4-83fb-50a8-af16-d4e8ec34a67e | note | Check Item - Hold Point 11
40a7aa59-5a90-5ec3-a566-ac7c279d7978 | note | Reference - MRTS14 Cl21.2
62fbcdcd-5c1a-4e49-8f37-8cf1da215e5a | signoff | Hold Point
a10e47ea-a3b7-411d-8eff-1c8beca49b44 | checkpoint | Once the initial set out is complete the Administrator will determine the design appropriateness of the set out with regard to the actual site conditions
bffb4af3-03bf-52e7-ba68-6fb1afcf7fe5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ced08838-3abb-56ef-ae0b-9dd3abb6a0ff | note | Check Item - Hold Point 1
778e3d4c-108d-535a-a485-eea2f0f09c6c | note | Reference - MRTS01 Cl.8
e251b665-effb-45e6-a9a9-fdb6ff624ca2 | signoff | Hold Point
c42ee677-f6d4-4772-bf41-e160da6f02b5 | checkpoint | Dial before you dig consulted and services located where required prior to excacation or driving of posts
b3406608-6b33-5f83-9f07-913d53e1bfbf | note | Acceptance Criteria and Frequency (Project Specific) - Visual
22ed7b4a-893e-5e5b-baa3-1275246797d2 | note | Check Item - Check Item
1096b164-4b55-566e-b437-1eab92687f0a | note | Reference -
38c52723-0db4-4ea9-9f41-ecab45614f23 | checkpoint | Steel Beam guardrail installed in the locations shown in the design documentation and in accordance with the Standard Drawings.
92a3683c-99f1-511f-b817-5b6f72551332 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1b145a17-7d20-5f27-83d8-cf672d474c79 | note | Check Item - Check Item
7fcb508e-f643-5cb2-a025-e5f8fcd49128 | note | Reference - MRTS14 Cl20.6.1
7c670a1f-f73d-4b0d-80a8-13876f72f92c | checkpoint | A proprietary road safety barrier system and/or end treatment shall be installed as shown in and required by the design documentation, and in accordance with the requirements of the installation manual
05f33e69-0cf4-537c-b34e-2ac5b5b01cc8 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ca691447-f2ed-579e-8436-61bd8c3ddd1f | note | Check Item - Check Item
3bfdfef1-12a9-50e7-8181-4d1e8aa90458 | note | Reference - MRTS14 Cl.21.4.1
9024724c-bd73-480e-bd5a-530aaab7e493 | checkpoint | Public Domain (Departure Terminal): Soil plate on type 2 departure terminal shall not be ommitted
d62f927d-dba9-57f7-af4b-5d2e4592e2dc | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5819ea3e-e1d3-554d-ab3d-71c6f04cf881 | note | Check Item - Check Item
21178ae6-881f-504e-88ff-ad714e2a4b63 | note | Reference - MRTS14 Cl20.6.3
30d1b1a1-6900-4056-89f3-6e0d037c62a6 | checkpoint | Delinerators installed on steel beam guardrail in accordance with the MUTCD Part 2
327048a0-e65f-5c00-b401-f7c0c932516d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
fb2b2578-61ff-5f45-85c2-38668454d543 | note | Check Item - Check Item
6707e3ab-2068-5162-b8f3-6e4a6c9698bb | note | Reference - MRTS14 Cl20.6.5, Cl21.4.5
ccb96e90-9044-4c79-a306-7697cef5881e | checkpoint | Installed within Geometric Tolerances
8119f31c-204c-5579-a140-1dd1997cb36e | note | Acceptance Criteria and Frequency (Project Specific) - Post Verticality: ± 15mm
8a311db6-6571-543c-9529-3a8214cea379 | note | ○ Post Height: ± 10mm
772185f7-0a9d-5424-94b1-457cf31cc137 | note | ○ Rail Height: ± 10mm
498b7e66-662e-5102-ad63-54cdf34d2d83 | note | Check Item - Check Item
75702769-9f29-547f-9a37-a2320395d113 | note | Reference - MRTS14 Cl21.4.6.2
4df77fb6-7357-440d-9f45-a12efd53d32b | checkpoint | Adminstrator accepts guardrail installation as per the design documentation
31d82dbc-8663-50a5-b49a-a7dd477cfa0c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b9d8c9eb-3c92-5d07-a0b0-b94072a9b65e | note | Check Item - Hold Point 10
e4748028-3e63-5e0c-b880-0eec0f7a8825 | note | Reference - MRTS14 Cl 20.6.7
fcf3cb5d-d301-4222-b1c3-927d9fc0cb79 | signoff | Hold Point
f66db2d7-3c88-4435-8162-2112671e674d | checkpoint | Final Verification
4f49eedc-ced7-5d4f-a243-128adea58641 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
25fb27f2-d416-5a95-91e9-158fcc518465 | textbox | Print Name:
25f81c89-2921-5b30-aaaf-09cb57f9cbcc | date | Date:
eac6c34a-2251-5eba-bfe9-53162f97494c | note | Project Manager Verify that the Above has been Constructed according to Specification
cfaaecaf-3d0a-53a4-b03c-220e0ad39bf3 | textbox | Print Name:
4f70a1af-424b-5e73-9799-ce39ced2c435 | date | Date:
956bcdff-8cb1-470e-991d-c58c81234b56 | signoff | Signature
6bd2ca0b-d5b9-4c8b-bbf5-e7268b897e0a | section | Final Sign Offs (to be completed at closure of Lot)
71b4b5cc-abfb-41b0-9217-0868ff6ba95c | checkpoint | Agreed Quantities
95433bd1-4e2e-4e88-a2ff-17c7d5e727f1 | signoff | Agreed Quantities Sign Off
a921a253-9ddd-4410-b68d-bce8e4ee7847 | checkpoint | Closure of Lot
79dd4ff1-8ff1-4cf3-a005-1ff8965eb46c | signoff | Closure of Lot Sign Off
0ff598a0-1dd6-483d-94fe-4828146452c4 | checklist | 16.01 - Landscape and Revegetation Works | itp | 16.01 - Landscape and Revegetation Works
2c11b5e5-2210-49f8-8cd3-84eae60c60b9 | section | Details
620fee86-58a2-4de5-98a6-a5a1471f01e2 | checkpoint | Soil Management Plan prepared in accordance with Form A of Appendix MRTS16. Construction and regular Updates submitted to the Administrator for approval
2fe25942-2fd6-5fea-b5d6-1553940b2d67 | note | Acceptance Criteria and Frequency (Project Specific) - Written Acceptance
b4e64caf-78f7-5c4c-80a3-96e212e31052 | note | Check Item - Hold Point 1
d1333ac5-c694-529f-82ec-854d39a92fc5 | note | Reference - MRTS16 Cl 5.2.1
425d15c4-4d15-49dd-8053-661d9b6dec16 | signoff | Hold Point
cc28abbc-b0b1-4c86-aff6-1a707c93a0e9 | checkpoint | Non-Potable Water Plan and permits submitted to the Administrator
4bb5fe9b-6ff1-51b7-b680-ac876b4ecac3 | note | Acceptance Criteria and Frequency (Project Specific) - Plan
7e434a59-2d1b-52c7-991b-3d3d84d72c19 | note | Check Item - Hold Point 2
4bd33efa-1940-5a77-9a09-537b10afa3bf | note | Reference - MRTS16 Cl 5.2.2
9ec6bb3d-b2b2-4ad4-b40a-3727f932c81d | signoff | Hold Point
79b7e96a-2b25-43b8-894c-5aa626010624 | checkpoint | Seed Supply Proposal submitted to the Administrator within 30 days of Possession of Site
abfbd7b4-8e34-518b-abdf-221cd3f6082d | note | Acceptance Criteria and Frequency (Project Specific) - Plan
94f6f872-81c0-52ec-bbc3-0c7bf5bc4734 | note | Check Item - Hold Point 3
38c8dbe5-fcf0-58c5-ab9a-0bdd157961ab | note | Reference - MRTS16 Cl 5.3.1
40bccc25-5f45-4859-a529-c9b088927844 | signoff | Hold Point
996df832-75f6-4c9f-8d73-95285171b075 | checkpoint | Plant Supply Proposal submitted to the Administrator within 30 days of Possession of Site
e562c6bd-ce12-52c0-b359-7ad99e328ae2 | note | Acceptance Criteria and Frequency (Project Specific) - Plan
8b14c09f-dbf5-55bd-bcf4-d66f9289bb41 | note | Check Item - Hold Point 5
0220c3f4-3cd9-5e99-ae73-5c639fdd481c | note | Reference - MRTS16 Cl 5.3.3
ecf48aab-4f43-4d38-be56-d3f54b3f6d50 | signoff | Hold Point
61d62476-a0de-4c70-9285-e66a987d66bd | checkpoint | Plant Harvesting Proposal submitted to the Administrator prior to harvesting plants
38bcfcf3-4e6f-52e2-bf14-1deb06af2f0d | note | Acceptance Criteria and Frequency (Project Specific) - Plan
10bfc4a9-c000-5b66-b95a-a8d925deb70c | note | Check Item - Hold Point 6
c871aeda-9a5b-5db4-aa8c-1bc14da3b15a | note | Reference - MRTS16 Cl 5.3.4
3965e934-85a9-45b1-93ca-c74ada911a9b | signoff | Hold Point
385137e0-ccda-490d-a963-857f74c7170e | section | Materials
78c04179-11b9-4172-aa05-adf957aaf813 | checkpoint | Materials imported to Site shall be free of prohibited or restricted biosecurity matter
766841e9-3ade-559b-8713-cb2b63bedee3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
50d04974-7348-5110-b8d7-eb7691fedd49 | note | Check Item - Check Item
11cd2596-35df-5211-98d8-4f0e3f6f20bf | note | Reference - MRTS16 Cl 7
801e5571-59b5-4b1e-b952-20ebf0834954 | checkpoint | Materials are stored to ensure no deterioration or contamination occurs, including the potential for environmental harm
30e1ba48-522b-5cdc-ad7f-add8dac80098 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d19d79bf-9de0-588c-8db1-b2ba2ab5dcfe | note | Check Item - Check Item
bfacf9d1-f7d0-5bf3-ba83-d5f4a6209fe2 | note | Reference - MRTS16 Cl 7
a1d4b331-61e9-4924-a289-7c724f808bbe | checkpoint | Materials; including pesticides, soil amelioration agents, soil, seeding, turf, mulch, matting, plants water, plant bed edging and irrigation systems, comply with requirements and specifications set out in MRTS16 Clause 7 where applicable
53b9eb10-8456-550d-b339-030f21a59aab | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1c68f167-1388-57ce-8c0d-933f8531a1ba | note | Check Item - Check Item
d3bee589-4aab-5d81-ac38-90c4459f7072 | note | Reference - MRTS16 Cl 7
66dc4621-fc81-4f09-906a-e9e27bb6f3ac | checkpoint | Containerised plants and ex ground stock in accordance with MRTS16 Cl. 7.6.2
41a23f75-9156-58ae-aa82-42af68accf58 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
37675e21-d1e4-53b4-9076-686dd756e1bc | note | Check Item - Check Item
3c25e11c-b26c-5f69-8488-00b0d67300f0 | note | Reference - MRTS16 Cl 7.6.2
eeb78a78-70ca-4c8d-9080-22d0a037a125 | checkpoint | The extent and types of vegetation treatments are installed as specified in the contract and/or shown on the drawings
41b0b9ab-bb45-52f2-8f72-1f235f5eb091 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6eb0dca1-e571-5ff3-a797-6d07b404f903 | note | Check Item - Check Item
f79bef2a-8f2d-5072-80a6-da3454e50010 | note | Reference - MRTS16 Cl 8
386e590a-4e6c-4ac9-a99a-d2c9b73679cf | section | Subsoil and Topsoil Amelioration
4c402795-0eda-4fab-adf4-bc3089c38a9d | checkpoint | Site is weed free prior to ground preparation operations
26e69e52-9e22-546a-918b-f2ccdec424b9 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b83f63d8-8b75-5368-8c2d-55648f5d42b8 | note | Check Item - Witness Point 2
b81f977c-758c-5564-b6f0-a73a03c654b7 | note | Reference - MRTS16 Cl 8.3
bbcbe2b1-32b3-4eb0-8345-843602e076fb | checkpoint | Administrator notified at least 3 days before each of the following: application and incorporation of amelioration agents ripping cultivation roughening
8a5d4c9a-7a59-5f60-9fa7-26d11309928b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a7f83e4f-3317-5dc6-9f0a-2f1c4a6bb17a | note | Check Item - Witness Point 3, 4, 5
ab48613b-6e22-5d3f-8011-7d3de67cedec | note | Reference - MRTS16 Cl 8.1.1, Cl 8.4.1.1, Cl 8.4.1.2, Cl 8.4.1.3, Cl 8.4.1.4
3c5535a9-939e-4fad-8df7-5b691789a3ae | checkpoint | Amelioration agents, where specified in the Soil Management Plan – Construction, shall be spread over the subsoil surface at the specified rates prior to subsoil operations
666a4d16-0d45-517a-b547-e02c7801d875 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
dea87e09-4ac2-5018-8762-604e59679195 | note | Check Item - Hold Point 8
28e5a37b-aa1b-5dc7-b908-5fbab57c397a | note | Reference - Cl 8.4.1.1
60e369b5-c0d5-4f6e-ab01-f6b4c65d4600 | signoff | Hold Point
ff689a73-8114-4383-9481-1cf00c5f62de | checkpoint | Manufactured site topsoil shall be in accordance with Form D of MRTS 16 Appendix prior to being used.
eb50d4ed-f8ea-54c5-a59c-f249f888cd72 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d4aacab3-5733-5c8d-b35f-9eec8a9b8fed | note | Check Item - Hold Point 7
56e3f30e-f4c7-586d-a00e-f59b4805e450 | note | Reference - MRTS16 Cl 8.2.1
1fcb4991-6a32-4e13-b403-d93bc2739d44 | signoff | Hold Point
139f6fd9-3943-4919-9a22-8490a60e6d89 | checkpoint | The Contractor shall give at least three days notice before installation of topsoil. Topsoil installed evenly over the surface, within 3 days of subsoil preparation and Topsoil shall be spread to the depths described in the relevant vegetation works operation, and allow for settlement after installation.
34d95b92-1226-5b35-b795-17286521d847 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e86913c3-2ebd-5de1-978e-19bb83d5e1e4 | note | Check Item - Witness Point 6
a6dd4c2d-4e43-5aaa-b2ed-8400625e39f1 | note | Reference - MRTS16 Cl 8.4.2.1
edb76d66-b784-41b5-9bdf-0c9dbfa6d885 | section | Grass seeding, Hydromulching and Turfing
52187cc4-d4f4-4b8e-b99c-f0b600c1eba4 | checkpoint | Turf shall be installed within two days from the completion of the topsoil operations, Turf shall be installed by:
ddad084c-6864-5f14-ba25-e496082d3be9 | note | a) spreading fertiliser over the topsoil and raking the surface smooth
4ff9707e-445a-51fd-a992-d7ccdf51bd66 | note | b) to the prepared surface that has been moistened with a solution of water and wetting agent
21687a94-1d0e-5561-a5a3-2049159e3334 | note | c) on the day turf is delivered to site
e61842f7-3798-534e-8d4e-5626fa70316e | note | d) by laying rolls parallel to the contour, in a staggered brick pattern, and
0628a226-ecc4-5f3a-9577-5da055aaac1b | note | e) by watering, within 2 hours of installation, with a solution of water and wetting agent until the topsoil layer is moist. Watering shall be applied in multiple applications to ensure surface erosion does not occur.
af99c8c9-4887-5895-b0fe-3ee16c54646e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
97f9e724-9b4b-54ee-84c6-0587dabebe3d | note | Check Item - Check Item
f07a7fae-8efc-5836-b11c-5ed102c865fb | note | Reference - MRTS16 Cl 8.5.2
cc35cb0d-dccd-4c45-8b47-4b7587bcde6f | checkpoint | Turf installed within 2 days of topsoil, within 24 hours of delivery and in accordance to Table 8.5.2 with initial watering on the day of installation and at least 25L/m2
f5882ea3-c522-5d45-8679-20f5f2a84a97 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0c56f604-1cd0-530f-8e85-d84e8fefa729 | note | Check Item - Check Item
41bba46a-5dd2-5d0c-96c2-82ef006d96db | note | Reference - MRTS16 Cl 8.5.2
fd1df74d-d637-4103-8f15-ef231f38cb87 | checkpoint | For seeding operations, the Contractor shall prepare a sample instillation to provide an agreed quality control for further instillations. The sample instillation shall be established as per Cl 8.5.1
fc05c670-ec14-54a9-957e-4e308812cd45 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
77c61d74-53bd-5d53-81ee-09dfbeea3724 | note | Check Item - Hold Point 9
9637296d-2b88-5b0e-a051-3aa35876ef5f | note | Reference - Cl 8.5.1
5eba805a-cf78-4a06-bc19-d675bb5b4791 | signoff | Hold Point
967c9b63-a300-453c-9960-8945bb3c8418 | checkpoint | All seed, wetting agents and fertilisers shall be brought on site in seperately labelled containers and mixed on-site to allow verification of materials and quanitities
917ebdb9-4f91-5553-9159-e5e4ea1fc1a5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
108990b1-d029-56f1-bdaa-d6a3430ea488 | note | Check Item - Hold Point 7
02a361a8-f694-5b60-92ba-e174811ae520 | note | Reference - Cl 8.5.1
25776535-e92d-4a0e-a23e-7e1937571ef8 | signoff | Hold Point
12bbe723-55a1-46c8-b623-add987d521c1 | checkpoint | Broadcast seeding installed as per Cl 8.5.1.2
85fc1535-24f8-5aca-a7ca-e40f00915c36 | note | Acceptance Criteria and Frequency (Project Specific) -
b20ca56d-514f-50db-a2e5-7dff9196f046 | note | Check Item - Check Item
4802447e-8e28-5c60-bff2-800b2aba6e7c | note | Reference - Cl 8.5.1.2
0bfbbf45-dd81-425e-a98c-b85e9cdfbc4a | checkpoint | Hydrumulch bonded fibre matrix installed as per Cl 8.5.1.4
9b1ab71c-ccf9-5e4e-bbf7-9feccf157a09 | note | Acceptance Criteria and Frequency (Project Specific) -
eb8fbb0e-6873-5485-a54e-20d1349d9640 | note | Check Item - Check Item
d481828d-70f4-5056-9d90-1b877d789ee7 | note | Reference - Cl 8.5.1.4
21b19096-f2b3-42db-bf34-1f65e2904b3b | section | Establishment, Monitoring and Finalisation
ef0b351d-8e89-4fa1-864c-53438892272b | checkpoint | Commencement of the Establishment Period
a3e4357d-31cb-5638-90c2-60bf729532ea | note | Acceptance Criteria and Frequency (Project Specific) - Issue of Certificate of Commencement of the Establishment Period by the Administrator
6af2245e-2f50-5162-bc69-c85677328691 | note | Check Item - Milestone
cce85eba-cc72-5e11-b2ae-952e33801f22 | note | Reference - MRTS16 Cl 9.1
93261179-917e-46de-824f-cb2c60815e00 | checkpoint | The Contractor shall care for the installed vegetation treatments to ensure their long term sustainability and to meet the completion criteria of Clause 9.1.2
9c57bbde-78d7-5f6d-a4d8-d0c1813b777e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2264f332-6aeb-5133-8ba9-35c9f129160f | note | Check Item - Check Item
88e549c5-1402-5ee3-9e91-c6bbe176e35f | note | Reference - MRTS16 Cl 9.1.1
6af467d5-8e2a-46ae-a21c-b41170e362de | checkpoint | Commencement of the Monitoring Period
df141946-b2b4-5889-a96e-e6a8c09b1396 | note | Acceptance Criteria and Frequency (Project Specific) - Issue of Certificate of Commencement of the Moitoring Period by the Administrator
48a240e1-dee0-5b04-8912-8be1c18c8b78 | note | Check Item - Milestone
e7ceec52-bc3e-587b-9445-6367d1bdeeb2 | note | Reference - MRTS16 Cl 9.2
2be88d7d-5954-4d8f-b5f3-1a5a04d56b24 | checkpoint | All Monitoring operations; including, watering, fertilising, weed, pest and disease control, mowing, slashing and brush cutting, pruning, and repair and reinstallation of failed plants, comply with Clause 9.2.1
faa018d6-5e98-5df9-a32c-e2c6adaa21bc | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f026417e-2a2e-5262-98ea-65de83e149b4 | note | Check Item - Check Item
20e917e0-3213-50cc-b729-c124d9531e47 | note | Reference - MRTS16 Cl 9.2.1
7f66e6d6-bf65-4319-80d0-ce5c8e7fe5ca | checkpoint | Certificate of finalisation of landscape and revegetation works monitoring period issued
a07d51e5-4498-5ac5-9d30-4b1334d91e5f | note | Acceptance Criteria and Frequency (Project Specific) - Issue of Certificate of Completion of the Moitoring Period by the Administrator
ac10b029-25b2-523e-aa0f-d97a383918bd | note | Check Item - Milestone
29e09937-fbd3-5fba-bfaa-cbaa090840f3 | note | Reference - MRTS16 Cl 9.2.2
7bbae4cd-aa78-4330-810e-f1e4982a2931 | checkpoint | Final Verification
6d1cf251-a4f1-5bb1-b2c2-1570bc13a5f7 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
2d0e41cf-0cba-59c1-8e5c-2dd25c35706b | textbox | Print Name:
00aa751a-0f0c-5f73-8ee3-fcbd42997448 | date | Date:
da92b00b-375c-5d68-afe4-3501b4960952 | note | Project Manager Verify that the Above has been Constructed according to Specification
055f8967-63b6-5639-872d-fc41fdcb18db | textbox | Print Name:
4ed9b416-2fb1-5365-be79-ced79667fe88 | date | Date:
19ad3d3e-92d4-4893-a022-0c9acf67d049 | signoff | Signature
9dc3d8e6-14c1-40e8-a23a-b8b1ff8cedbc | section | Final Sign Offs (to be completed at closure of Lot)
23da34d9-dc8a-4bae-b4f3-26e9da924966 | checkpoint | Agreed Quantities
629179c4-5cc2-41a4-8c60-392a92038444 | signoff | Agreed Quantities Sign Off
4d651bf6-01ec-4d24-9026-253647ebd787 | checkpoint | Closure of Lot
8ce197c0-e950-47d6-a766-f6e84708bbde | signoff | Closure of Lot Sign Off
58048cb8-f881-4552-98d0-8954bc897002 | checklist | 28.01 - Contractor's Camp and Site Facilities | itp | 28.01 - Contractor's Camp and Site Facilities
b5c2faa2-9d0a-4a7d-b3ba-71df8cec0fef | section | Details
cc97c2bd-a689-42ec-8ade-f47c834923b9 | checkpoint | Location of facilities within areas given in MRTS 28.1 Cl. 1 or through private arrangements.
9e9a45f2-4748-558b-ab66-cebe194a8946 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a29865d6-508e-5ac0-aa1c-b82a47fb195a | note | Check Item - Check Item
a41add24-b4ee-5c65-9ecf-2280d077ea85 | note | Reference - MRTS28 Cl. 4.2
f4fad6d4-8821-4f5b-8625-c98bc6648c17 | checkpoint | Properly constructed toilets, rubbish receptacles and wash facilities provided.
25dbaca8-b827-5f56-9466-66919070c8ad | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b3e87ba3-15bf-5478-89bd-89733a4dffaf | note | Check Item - Check Item
085737bd-ccd3-5f4f-b15d-11a8a938c6f7 | note | Reference - MRTS28 Cl. 4.3
a84c49d3-c9ad-4e45-8979-b974213af182 | checkpoint | Camp and facilities provide safe egress and ingress and do not impact on existing through traffic.
a186d5bb-e9db-588c-83dd-b2dd000581b3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
90cc4374-5ddd-5e11-b87e-6944113ed670 | note | Check Item - Check Item
627c97cb-f30b-5886-bef8-081c504c04d4 | note | Reference - MRTS28 Cl. 4.5.6
069d30f3-2864-4d55-ae63-8812333f8cff | checkpoint | Contractors camp complies with all requirements of MRTS52 and included in the E&SC plan.
f015b7c3-2a17-5a9e-846a-145ebe500181 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
28606408-b984-51ad-a276-18609687e2c1 | note | Check Item - Check Item
8680f8a5-9c9a-5131-8697-64fa3b73d36b | note | Reference - MRTS52 Cl. 6
4e867700-b491-4502-82b4-412d0b2e28ad | checkpoint | Contractors camp complies with all requirements of MRTS28 annexure with a proposed site facility layout submitted to the administrator.
be7de33a-bc32-5308-abd7-33c0fa469081 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
99276423-4ab2-5c84-a94e-19f5b2b3edd0 | note | Check Item - Check Item
cf09e5b9-86f8-5fb7-9dfc-42970ed27bfc | note | Reference - MRTS28.1
f9348be9-5c95-4ddb-beb3-5e7b63a00f4e | checkpoint | Final Verification
f7d9af72-39f7-593f-a21c-eafa66b62931 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
b7f42a5b-408f-5a02-97fa-d580eb8b0081 | textbox | Print Name:
c8c99aa9-a13b-5506-8bd7-4999345788dd | date | Date:
a186018e-5bce-56e2-9c49-3eaf22f09291 | textbox | Print Name:
46fd1d11-1018-529a-968d-7f0adf74ed14 | date | Date:
b6231c73-3782-4d08-a262-388e6c947bb2 | signoff | Signature
08666aa3-edfe-4ed5-bf26-22fe068fc48c | section | Final Sign Offs (to be completed at closure of Lot)
69a2fbcb-930f-4d89-bfec-5bdeb636dfa5 | checkpoint | Agreed Quantities
fda07e7e-c646-41df-8f0c-7427b9b93e5e | signoff | Agreed Quantities Sign Off
ef48327a-3afc-474e-9367-4afe94ba3fc2 | checkpoint | Closure of Lot
10f6a57c-8bc7-4fad-bd54-0e5d2ea58b59 | signoff | Closure of Lot Sign Off
84bc912b-174c-4748-a9e2-ded8fe4bafb2 | checklist | 30.01 - Asphalt | itp | Asphalt
538ab4ac-f50b-4b90-a1a7-c91e757d9f06 | section | Subcontractor ITP
d72f7242-a6c8-4938-ab3a-ba8ec11af627 | checkpoint-no-value | Attachments
82b4e3c8-6d93-4fb6-a0cc-cfaae492acb1 | section | Final Sign Offs (to be completed at closure of Lot)
0ce989c2-28ba-4cb9-b74a-c7deeb0e0dcc | checkpoint | Agreed Quantities
daeb8e71-685b-4afa-b2ea-0b4d4c240c2a | signoff | Agreed Quantities Sign Off
3b4fc93f-c182-4fa9-8c78-fc42c74cc0e9 | checkpoint | Closure of Lot
f144264d-fa39-460b-a2e4-ef715ab94351 | signoff | Closure of Lot Sign Off
5c57e5a5-4517-48d4-accb-0b4e8ac4bc65 | checklist | 45.01 - Road Surface Delineation | itp | 45.01 - Road Surface Delineation
cdf7255e-0c0e-4df2-9884-114a568988a0 | section | Details
de2185a9-c52a-41c3-927c-87a934fc67b4 | checkpoint | All material conforms to requirements set out in Clause 6
4a323c1f-0caf-500c-b826-abc162852f3c | note | Acceptance Criteria and Frequency (Project Specific) - Material product sheets
b0ca0590-9f25-5394-ad4e-a1461af0c51a | note | Check Item - Check Item
3916e19c-9fba-53b4-9aef-55603c0f9e6f | note | Reference - MRTS45 Cl 6
e3d5dbb6-fa41-463b-886d-720027a26f23 | checkpoint | Pavement markings not applied when freshly applied pavement markings may become damaged by rain, fog or condensation before they have dried or set.
c0517d95-bfda-50ca-ae36-17bc77049bc9 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
089c7397-c944-520f-954d-b41c1e356950 | note | Check Item - Check Item
8df38a4f-670d-5fe8-bc06-09372b233f68 | note | Reference - MRTS45 Cl 7.2
7205a8bb-da47-4c66-b0a6-087599a68c6d | checkpoint | Pavement surface is thoroughly dry and free from all dirt, loose material and other contaminants immediately before applying the pavement markings
f51b00d2-994c-5e27-b441-61f09e30882d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a2996ca3-7ea3-5379-bf18-e38bcc6bfe43 | note | Check Item - Check Item
ee2258f0-e483-5996-bd3e-6f2040b8ac87 | note | Reference - MRTS45 Cl 7.3
597a1b78-ea73-4247-85ca-a6b2843a893f | checkpoint | In addition to the above requirements, new bitumen sealed surfaces which are to receive pavement markings shall be free of volatile material and solvents.
4851de8b-8c7c-5f0d-a275-751e9d4982bd | note | Acceptance Criteria and Frequency (Project Specific) - Visual
dff97c9f-e6d2-5df6-af6b-4ed7133c2ed2 | note | Check Item - Hold Point 1
82675aba-92a7-551c-acda-4b4b6c8edc27 | note | Reference - MRTS45 Cl 7.3
8b7a4e5d-e940-43cd-9895-d1ddb70bccdc | signoff | Hold Point
c2d14a00-a2ef-4bc9-91b6-72edafc62fdd | checkpoint | Spotting approved by the Administrator prior to any application of pavement markings
1a76db4e-0241-58f4-bb51-a15cef55e6d5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1872d056-60d1-58ba-9ffd-a1bc243ebcff | note | Check Item - Hold Point 2
ba97e67b-dc49-56d0-9cb9-8a7314b56cc1 | note | Reference - MRTS45 Cl 7.4.1
fcbd4237-2433-49f9-98a2-73a32512a16d | signoff | Hold Point
c23466e4-3aca-4d63-9670-2e8584ebd668 | checkpoint | Construction procedure for application of pavement markings submitted to the Administrator
683fe73c-ac02-5004-909a-710b08aecb0f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8633ffff-5db8-5d0b-bf7f-e49839fe44a4 | note | Check Item - Check Item
719dd683-cb12-57db-906e-e733031ac07f | note | Reference - MRTS45 Cl 7.5
a03771c6-dbd7-4184-9811-1ff5a84a014e | checkpoint | All Markings are of uniform thickness and intensity
c1f1025e-3539-5e1d-90ed-6d5a63812acb | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e3cf00fd-2ade-527d-a1d3-03b00dd63cca | note | Check Item - Check Item
0a58c348-bfff-56ae-9bd0-fdd2ba048496 | note | Reference - MRTS45 Cl 7.5.2.3
8742dd9d-2540-4bde-afed-48a2bf0b3871 | section | Waterborne
db583523-9bcc-44e5-a034-96c2004fdead | checkpoint | Waterborne Paint not heated to greater than 65°C and consists of two coats of paint and glass beads with application rates for the paint as per Table 7.5.2.4
d5250c51-f5c2-5a7c-bfb7-c3c053cdd0e2 | note | Acceptance Criteria and Frequency (Project Specific) - Visual, Table 7.5.2.4
02e00051-f283-5e2b-9923-c56b15b44797 | note | Check Item - Check Item
c1a6ec97-b57b-5f7a-bad2-145cc3a4f15a | note | Reference - MRTS45 Cl 7.5.2.3, Cl 7.5.2.4
0d74664e-3209-44d4-9e9a-c6de29c9ac42 | section | Thermoplastic
1fb6e19b-031c-40ac-b916-ab85f49bce5a | checkpoint | If required, a primer of type recommended by manufacturer of the thermoplastic material shall be applied to the surface immediantly in advance of, but concurrent with, the application of thermoplastic material
8e7b334c-c5b8-5332-a5d0-1453530ce768 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
214b49da-922e-5971-85e7-74e444c5e18a | note | Check Item - Check Item
413c779a-9b27-541f-bb38-8763a73dd618 | note | Reference - MRTS45 Cl 7.5.3.1
d13be700-283a-42b0-b1ed-2c3c1743793f | checkpoint | Thermoplastic shall be applied at a temperature between 180C-200C or as per the manufacturers specifications
d9c83c74-ca18-52e9-ac1b-804316795755 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
bcb72235-e338-5d20-bf77-72061f0a6553 | note | Check Item - Check Item
8f0592ac-fde3-5c4c-a69b-4c70ad28d5eb | note | Reference - MRTS45 Cl 7.5.3.2
8bd53b31-8a99-409c-89a6-8b3072cccac3 | checkpoint | Thermoplastic applied at a minimum of 2mm thickness
1bf0790b-c121-5237-afee-2bfe56c3dddd | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a55c6069-fdeb-5e5f-aca7-c40fd81b5c59 | note | Check Item - Check Item
8f32e379-3e34-5f4d-b00e-b2bebe17389c | note | Reference - MRTS45 Cl 7.5.3.3
3fe2b083-1c07-421c-9db9-fb68478cd2d7 | section | Cold Applied Plastic
94ef0f20-290c-4798-b5ba-151d51c7120d | checkpoint | If required, a primer of the type reccommended shall be applied to the surface immediately in advance of, but concurrent with the application of the Cold Applied Plastic materials
08b4a06e-af9e-5adb-9445-1fe8b04e64ec | note | Acceptance Criteria and Frequency (Project Specific) - Visual
7e630c60-11d2-5fad-9328-5fb882aef5ba | note | Check Item - Check Item
8882ef60-3a9c-5217-8320-98d43fb3b40f | note | Reference - MRTS45 Cl 7.5.4.1
9526452d-825f-43e5-ba81-0d2061548b43 | checkpoint | Cold Applied Plastic shall be applied at a temperature as per the manufacturers specifications
a5b63e63-ad33-5388-9d45-471fd0477aaa | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a3c3c8fd-ec65-569d-8b05-d5b2a7a98c72 | note | Check Item - Check Item
6d0f1aa0-d713-5a96-93d3-cfd88c732629 | note | Reference - MRTS45 Cl 7.5.4.2
9ce1dfb4-95cd-4b45-a58b-c6a2cfa80f09 | checkpoint | Cold applied Plastic shall be applied at the rates specified in Table 7.5.4.2
a3176ad2-9162-5467-88b9-c5a9c4254d68 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
21b539b2-c635-5d7c-bc58-cdf9a44963e0 | note | Check Item - Check Item
c712a2bb-33e9-57f2-a8c3-d615cf43aaaf | note | Reference - MRTS45 Cl 7.5.4.2
ab73ea9e-fbf9-43d4-be82-0aaf3479710f | checkpoint | The use of Raised Retroreflective Pavement Markers shall be in accordance with Cl 5.6.2 of the MUTCD Part 2
abb27b58-d7c3-54d5-a4a0-d8b2c826802d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
7aa469a7-9310-50f1-b5de-f1a5d820bf5a | note | Check Item - Check Item
e6e86c41-e026-5272-9d7d-de01014b9c37 | note | Reference - MRTS45 Cl 7.6.14
208a255a-13ab-41d1-a735-2128de90d417 | checkpoint | Material complies with luminance and retro-reflectivity requirements.
39f3017a-cf51-5931-843a-b2576a32ad41 | note | Acceptance Criteria and Frequency (Project Specific) - Test procedure AS 4049.4
76f6a1c2-e389-5cde-9610-dcae07107aaa | note | Check Item - Check Item
bf1a1b03-9acd-59dc-984b-c93fbb024300 | note | Reference - MRTS45 Cl 5.3 & Cl 7.7.6
59be5bd3-5b5d-4732-ba8b-ee640565d446 | checkpoint | Material protected from damage by traffic or other causes until paint is dry and thermoplastic has hardened
1ee9f4b5-e29d-5118-9d34-e9718f43c5bf | note | Acceptance Criteria and Frequency (Project Specific) - Visual
09d86056-b547-5082-a5f9-42fbee4e111f | note | Check Item - Check Item
d9f3730a-8df1-585a-8167-5045d1b5859d | note | Reference - MRTS45 Cl 7.8
5e35b141-1867-4dc3-abb6-a7f2b77a70a8 | checkpoint | Completed Pavement Markings shall be uniform, clean and well-defined edges without deformation and conforms to dimensions as set out in the MUTCD
e51ebfde-52af-516b-937b-02bace90e57a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
eedf5034-b3c5-581a-98ae-1326a0bbea98 | note | Check Item - Check Item
27762877-79f3-5790-9af4-97104da99297 | note | Reference - MRTS45 Cl 7.9
5eccf31c-3339-4eb0-a41e-2ab84e61fce7 | checkpoint | Pavement Markings conform to all tolerances
749f387a-7ce7-5146-b45a-6d436c704242 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d89b97e6-39bc-5579-9cf3-99a67c646df6 | note | Check Item - Check Item
ebde4ad5-3cd6-5770-a69f-606c840dfb8f | note | Reference - MRTS45 Cl 7.9.1
58ad311c-ff3c-4ee7-a749-670cfe5454ec | checkpoint | Final Verification
82c33fe4-0d28-5616-a69a-d1db9a1485ff | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
c6e640ef-3819-5f47-b1cc-70a7b7d6720b | textbox | Print Name:
75d37323-f2fc-5f29-8728-3955be9df5f5 | date | Date:
b9bbcc4a-8032-5098-bcf8-b9916420b09b | note | Project Manager Verify that the Above has been Constructed according to Specification
bff3192a-c886-5b04-85c0-96e0d73a96cd | textbox | Print Name:
33797781-d0f0-56ec-8563-8e9121f51d5a | date | Date:
9105b9ec-c193-4013-935a-de97de84c6aa | signoff | Signature
90eb2cc6-3672-4f04-bd83-9d9c5f151463 | section | Final Sign Offs (to be completed at closure of Lot)
d5946007-ff0f-413e-90b3-4c8aa772f164 | checkpoint | Agreed Quantities
5966ee66-efff-451a-a3ae-3060af62028a | signoff | Agreed Quantities Sign Off
6c9727fa-aa70-4e6a-b286-000c5ae81061 | checkpoint | Closure of Lot
970545be-2ee6-4781-a42e-000b8d1ed0b3 | signoff | Closure of Lot Sign Off
6682b7f4-1d0c-4b4f-8c94-8ffe80285f40 | checklist | 51.01 - Environmental Management Systems | itp | 51.01 - Environmental Management Systems
eb6a1068-12bf-4f6b-aaf5-4dbc070cc3b1 | section | Details
6553e346-cb10-4b0b-9e92-e8f5d7435e10 | checkpoint | Environmental Management Plan (Construction) EMP( C) submitted in accordance with General Conditions of Contract.
fd97cfa3-cacd-512b-9ed4-6a80cdb8cf07 | note | Acceptance Criteria and Frequency (Project Specific) - Submission of EMP
ace6ade9-4247-5993-874e-2e3702db3387 | note | Check Item - Milestone
8398f830-73dd-5b9b-b80d-03551c23b869 | note | Reference - MRTS51 Cl. 6.3
2f8155f1-c0d0-4962-a599-ab275a6df0f2 | checkpoint | Works under the Contract shall not start until the EMP( C) is assessed for suitability by the Administrator.
ab2aee35-6f66-5a0d-9fb9-3eb56a2e649e | note | Acceptance Criteria and Frequency (Project Specific) - EMP Approved by Administrator
c277f01e-bf89-5459-9eed-278b48f63ecb | note | Check Item - Hold Point 1
ca2c50ef-e1ee-5a66-b993-a95557363f9b | note | Reference - MRTS51 Cl. 6.3
125c7021-87c7-4c82-9808-d745e1d57c3b | signoff | Hold Point
d751e0ea-4d6a-4363-9f8e-12353a95e2e5 | checkpoint | Any amendments to the EMP( C) shall be submitted on a monthly basis and be assessed for suitability by the Administrator.
daceb03c-581a-58e3-a735-05bd095c1b43 | note | Acceptance Criteria and Frequency (Project Specific) -
e7e2b46a-e982-57a3-aa8f-3a8d1c479a32 | note | Check Item - Hold Point 2
cbe71dc2-93b2-54dc-b6e1-d61c3a32ca77 | note | Reference - MRTS51 Cl. 6.4
7b91c8e4-4239-448a-9655-d2a0f3c46dda | signoff | Hold Point
f421ec12-53b8-4414-b6e9-c85701bce66c | checkpoint | Environmental site inspections to be conducted daily, against all licences, permits, approvals and other environmental performance requirements. All Inspection to be documented with records being submitted to the Administrator on a monthly basis.
8bfe219e-cfe3-557c-b08c-edb6841156d0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e5f3038a-2f91-5154-bbdc-8ca43e1b367d | note | Check Item - Check Item
d087b5c8-a778-57e1-9294-2a1ebbcbc7ca | note | Reference - MRTS51 Cl. 7.1
15ce6c7c-461c-4a56-ac36-2f4057261197 | checkpoint | Environmental records are to be included in the Quality Records under the Contract. Table 7.8 of this Technical Specification identifies environmental record requirements. Records and registers shall be made available to the Administrator upon request.
936ab1c5-a7fe-5830-b989-2cdf64862166 | note | Acceptance Criteria and Frequency (Project Specific) -
051f156d-9726-5a7f-ad64-ec19ed4ea24d | note | Check Item - Hold Point 3
f35a02c1-606a-5c3a-b4a7-a8b871944320 | note | Reference - MRTS51 Cl. 7.8
eeda058b-e4bb-4a73-9355-dc16e4f9f733 | signoff | Hold Point
03ed8bfd-1be0-4b9e-80d2-32518c4c390d | checkpoint | The Contractor shall be responsible for the management of Indigenous and non-Indigenous cultural heritage artefacts, sites and values within the worksite
c5e022bd-2598-5492-935b-08c2c5bf416e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
445eacbc-1fa2-5d4d-b417-7496eee3d325 | note | Check Item - Check Item
9de73df9-8300-5d47-9c72-caf022c6e9f6 | note | Reference - MRTS51 Cl. 8.4.1
c027da39-a92d-4200-88ec-b4caf653c15b | checkpoint | The contractor shall at all times take measures to assist in minimising noise associated with construction activities so as not to cause environmental nuisance or harm.
ad555c25-d919-56fe-8c3e-edeec126c072 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c1b61afb-1f55-54b7-b898-cee38e457069 | note | Check Item - Check Item
dbff064a-2f87-5219-9fc7-a462079feb03 | note | Reference - MRTS51 Cl. 8.5.2
a0b1c4e8-ec22-4b7f-afdc-16de9894b92e | checkpoint | Project records shall include all noise monitoring results if required
9022d9e6-6690-527c-8d9f-00e5c4f384ae | note | Acceptance Criteria and Frequency (Project Specific) -
73c53885-02e8-5054-8257-468c3397fc61 | note | Check Item - Check Item
f857fbe1-425d-5484-b41d-50c89a5fdb09 | note | Reference - MRTS51 Cl. 8.5.3
27181d91-4825-4eb8-a48e-31f02fbeac03 | checkpoint | Condition survey may need to be conducted prior to commencement of activities as per Annexure MRTS51.1 Cl. 5.5 Copies of condition survey to be forward to Administrator 5 working days before any works that cause vibration start.
90b35a27-641b-5732-ba36-22c1bc965ef6 | note | Acceptance Criteria and Frequency (Project Specific) - Visual (Survey Recorded)
155626d6-dd64-5a02-8b24-041609c8525a | note | Check Item - Check Item
ab3afd54-571a-5db2-8357-e93fe77e3ae2 | note | Reference - MRTS51 Cl. 8.6.2.3
ae7c4872-94c5-4f25-9230-951ecadb2514 | checkpoint | Project records that show compliance with the VMP and shall include all noise monitoring results (if required)
0fd55203-eb26-530a-9c13-27a983e15de3 | note | Acceptance Criteria and Frequency (Project Specific) -
f857e53b-2d43-5cc8-b71d-5e8c8e44e316 | note | Check Item - Check Item
1dbe8a06-dfa7-56aa-b3e9-0f3e020939c2 | note | Reference - MRTS51.1 Cl. 8.6.2
c07b3974-372d-4c82-8344-7fb75b12b5d6 | checkpoint | The contractor shall at all times take reasonable and practicable management measures to avoid cuasing environmental nuisance or harm due to air quality. Burning of material shall not be permitted
4178aced-87ba-5fe0-be61-927c45cdffb3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5296bce3-e5f5-5be1-8719-5d4c0148e7b9 | note | Check Item - Check Item
0fadf5e1-5d3d-57d9-90ad-aa725176ff30 | note | Reference - MRTS51 Cl. 8.7.2
d5d4559a-69ff-4a8b-bc6f-9f06ad27bd57 | checkpoint | The contractor shall be responsible for the management of acid Sulphate Soils and shall address the requirements of MRTS04 General earthworks including the requirements concerning the management of acid sulphate soils
1c82e653-9c3a-5de8-843b-179c032fadc4 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d2fafe64-0960-5536-9716-52f7493be1ab | note | Check Item - Check Item
668df4f8-003f-56cf-b9ab-820f4a5c9960 | note | Reference - MRTS51 Cl. 8.8
52b57581-5a76-45e3-bca8-d962d3ffe46c | checkpoint | The contractor shall be responsible for the management of contaminated sites ( contaminated soils, waste dumps, unexploded ordinances ) within the worksite . The contractor shall address the requirements of MRTS04 General earthworks including the requirements concerning the management of acid sulphate soils
802f8707-f878-560f-9735-d51e5bb6c9bb | note | Acceptance Criteria and Frequency (Project Specific) - Visual
512e3c14-718d-5438-9a01-749cac42a715 | note | Check Item - Check Item
d5b91b25-842c-5708-a928-6942c89b9645 | note | Reference - MRTS51 Cl. 8.9.1
2b3efecd-caa9-4c17-9f3d-d671c26e726a | checkpoint | The contractor shall take all due care to not harm native fauna. Areas of significance and related management requirements are stated in Cl. 7 of Annexure MRTS51.1. Contact details for emergency wildlife care shall be included on project emergency contact list.
1e6e353d-83d2-5103-b57d-717b27b17fd5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a492d3c2-4652-51a5-a1f7-fc2e3098d8d3 | note | Check Item - Check Item
e37a1d2f-5329-526b-9f20-56a2e4fce5a1 | note | Reference - MRTS51 Cl. 8.10.1
0fda055a-c6eb-4308-b127-bece14a27d8d | checkpoint | No waste or litter shall be burnt on site. No waste or litter shall be buried on site unless approved by the Administrator and the administering authority.
e6dc1b90-1243-592d-acda-088f0b03eb21 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
47702cb5-c4df-5c1e-9869-2bf668eacf8e | note | Check Item - Check Item
e0f45ee9-484c-5171-894a-325b1f1f9b29 | note | Reference - MRTS51 Cl. 8.13.2
04834e56-9c9d-49d0-ac53-314d800f1662 | checkpoint | The contractor shall be responsible for the management of all chemicals and fuels within the worksite so as not to cause environmental nuisance or harm. The contractor shall ensure spill kits response equipment are available on site for use in emergency
5691ddd3-b6fb-5ee5-be41-1764eace6119 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
bb25f937-44ca-534c-a41c-dfd7f3db9000 | note | Check Item - Check Item
83681b4b-f239-5057-adb6-54cba0b8ac61 | note | Reference - MRTS51 Cl. 8.14.1
b7bd1f7a-8c4c-401f-866b-326ad0a74588 | checkpoint | Final Verification
f21c0a99-0f80-5065-8be7-49349c8fb1b2 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
360095db-357c-5827-a51e-6ad8cc93b2c8 | textbox | Print Name:
5cd152a6-8efc-58a9-8963-77a1c2b73ee9 | date | Date:
8b20fae4-23a2-56e9-bd61-e043b61b5b37 | textbox | Print Name:
0b5ffc8a-3551-5023-b8c8-6b7165d7ca65 | date | Date:
15711264-70ad-4cf4-bdcf-f772f42b17b3 | signoff | Signature
72178bf9-b0f7-42da-ae5d-9e44764f4025 | section | Final Sign Offs (to be completed at closure of Lot)
0a6341c8-56a9-4c02-b449-220a6333ee04 | checkpoint | Agreed Quantities
99a30800-2c3e-4bc6-8a0f-07df57f6cd07 | signoff | Agreed Quantities Sign Off
68f7066b-72e0-4acf-b9b2-3b4a829868d8 | checkpoint | Closure of Lot
9474bd75-c50f-474b-b220-52d896a013b4 | signoff | Closure of Lot Sign Off
edbe577e-3a4c-4bff-9652-6f35b632671a | checklist | 52.01 - Erosion and Sediment Control | itp | 52.01 - Erosion and Sediment Control
501d5395-db9d-41df-99e4-0c218fd0a9c8 | section | Details
cc4b79bc-3b79-4aff-8301-abc227d03b4e | checkpoint | Clearing and grubbing (or the use of the area for stockpiles) for that section shall not start until the ESCP for that section is assessed as suitable by the Administrator.
c9f677fa-c424-5e4c-b82c-ce5a45aeedd2 | note | Acceptance Criteria and Frequency (Project Specific) - Approval of ESCP by Administrator
ab06c747-34aa-5b2c-893a-cf636d5161e5 | note | Check Item - Hold Point 1
da80b505-89eb-5b9d-ae28-3b7aaeb9707c | note | Reference - MRTS52 Cl. 6.1
02077c6d-c851-4635-bca2-acecbabc5051 | signoff | Hold Point
63349f86-d138-4821-93f0-b9518fef4933 | checkpoint | Prior to initial earthworks operations, the Contractor must install erosion and sediment controls associated with drainage paths flowing through the works area.
6dfe7c85-1f61-5f32-9b38-8e2d0703e420 | note | Acceptance Criteria and Frequency (Project Specific) - In accordance with approved ESCP.
875db058-913d-5ece-a37f-0639057eeaa0 | note | Check Item - Hold Point 2
35f1619a-9db4-5cd5-8eba-e3cb51a49086 | note | Reference - MRTS52 Cl. 7.1
78db0158-d58d-4590-a3b2-f8f02ecb63f7 | signoff | Hold Point
f11c2dde-d702-4159-be59-05e5050246be | checkpoint | Releases from site must not cause scour at the area of discharge. Water must only be released at the discharge point nominated within the ESCP and as deemed acceptable by the Administrator.
9dd09ece-590c-5b2f-8c17-0a3b1cd196bd | note | Check Item - Check Item
80bb0f20-dea8-5607-8e9a-457652f475a6 | note | Reference - MRTS52 Cl. 8.1
b5a651d5-fc72-4b49-970c-55ce413487de | checkpoint | The Contractor shall install a proprietary rain gauge and keep record of the rainfall depth of each rain event
a3f0ba17-fde6-58f7-8fbb-f92cc81a846f | note | Check Item - Check Item
cb446fb3-81f1-518f-b2ad-4f7dd293a3aa | note | Reference - MRTS51 Cl. 8.2.3.2.1
b74256cc-71da-4452-8cfa-8f1bbd410c99 | checkpoint | Final Verification
e9c33adf-055c-5616-9e18-71ded2b4b5b7 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
0cd52e28-f2e0-55a7-8d5e-d688d0fe5747 | textbox | Print Name:
278180c0-e825-527d-aa9d-849cbc5ecaf8 | date | Date:
1601b285-555d-5d42-a4b2-7c02277817bc | textbox | Print Name:
e2fa93a5-8ea7-5288-bbe0-e4a6e54a9a8e | date | Date:
7a45579a-c362-4304-b70e-8f14b7866e24 | signoff | Signature
e354a153-9480-4bcc-9d04-1cd10c6db209 | section | Final Sign Offs (to be completed at closure of Lot)
e89ab5e5-a6cc-45ec-9224-265978cc31c4 | checkpoint | Agreed Quantities
08a167a2-2a15-4e0d-a6f1-5a8458612814 | signoff | Agreed Quantities Sign Off
ca7a232f-695f-4fa4-a438-2b00adb1552b | checkpoint | Closure of Lot
65302275-50dc-4f45-9dec-221cf4c93391 | signoff | Closure of Lot Sign Off
b85cda36-cd04-4a6b-ac9f-468c4c18731d | checklist | 70.01 - MRTS70 Concrete | itp | 70.01 - MRTS70 Concrete
1288ec08-835b-493f-b484-c7eaa72b3e01 | section | Details
ffe92c3a-5979-4734-ad86-f13d61249eec | checkpoint | The Contractor shall nominate the special class concrete mix to be used in the Works not less than four weeks prior to the commencement of concreting operations.
9cb905cd-a42d-53d9-9d6f-70e776809538 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
93ce0219-67e6-5ef3-ab82-d3f469ed4394 | note | Check Item - Milestone
aceca9f5-685d-52c9-8939-3cf989ac9ec8 | note | Reference - MRTS70 Cl 9.2
ae217702-bfbc-4e54-acf4-327235668a1f | checkpoint | Procedure for hot weather concreting submitted 2 weeks prior to first concrete pour.
889e34e2-5a71-5353-8bb4-9d556c1a4abe | note | Acceptance Criteria and Frequency (Project Specific) - Visual
32b9d067-ae0f-5a4a-9847-a5cf42c46938 | note | Check Item - Milestone
ad4fe50e-e74e-51d1-bc70-954856644aba | note | Reference - MRTS70 Cl 13.1
cd2ef23c-5113-4d36-9fa4-a743ec3412ce | checkpoint | Procedure for curing submitted 2 weeks prior to first concrete pour.
af38ddce-b20c-50c3-a752-e6092a1f2bdb | note | Acceptance Criteria and Frequency (Project Specific) - Visual
475878c4-0890-5992-8776-1ff7701bc841 | note | Check Item - Milestone
011a04cc-d6b5-5b3e-b7e1-ca7938271a6c | note | Reference - MRTS70 Cl 15.11.1
03cacc99-a52c-4f9d-a134-98938fa5209a | checkpoint | Procedure for temperature control submitted 4 weeks prior to first concrete pour.
bb53b9df-49ff-57ad-81f3-109ffb3bf684 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c6ce586f-e621-5587-bde5-e7fe9752884b | note | Check Item - Milestone
30b0e903-5297-53a9-9c16-3987ecfdf132 | note | Reference - MRTS70 Cl15.5
a4c540ad-3a87-43e1-84cc-a10d3ab2edd1 | checkpoint | When requested by the Adminstrator, mix designs shall have a trial mix completed. Each trial mix shall be a Witness Point with a notice peroid of 3 days. The minimum volume of trial mix is 25% of the rated capacity of the mixer.
9fc4d844-72d4-5f50-be84-932d4da499d7 | note | Acceptance Criteria and Frequency (Project Specific) - f'c Each Mix
439306a2-5cdf-5dba-ad96-94b64b009201 | note | Check Item - Witness Point 1
eeeb497b-9d69-5442-92ee-28afaaa50504 | note | Reference - MRTS70 Cl 15.1.1
70962f22-94b1-40c0-a253-841078735ab7 | checkpoint | No concrete shall be placed in the Works until approval of the mix design has been obtained from the Administrator.
0f7128a3-a7b4-5c4a-aa93-2cc2f696f591 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
56bbfd09-ff47-52b7-b968-3ee4b1aff4be | note | Check Item - Hold Point 1
90033d93-f205-5bd9-aebc-aed874f3e258 | note | Reference - MRTS70 Cl 15.1
12b2411b-aae5-429d-90cf-ba298257c162 | signoff | Hold Point
ceb19034-1772-4fc2-af55-1cd4fafa044a | checkpoint | Concrete placed within 75minutes (conc. Temp<=32 degrees) or 1hour (32>conc. temp < 35 degrees) from the time of charging the mixer. These times may be extended at the Administrator's discretion where set-retarding admixtures are used. No concrete may be placed the temperature of the concrete is less than 10°C or exceeds 35°C.
35cb8810-fee1-59a8-a71c-33b3308ea1eb | note | Acceptance Criteria and Frequency (Project Specific) - 10< Temp <35 Continuous
1ca1e965-2232-5108-9e3d-bd3c373fefc6 | note | Check Item - Check Item
eedb9c6d-a1cf-50f0-95dc-f5998086a679 | note | Reference - MRTS70 Cl 13.1
f7a3dd7d-750e-4771-b06e-ebef4d730368 | checkpoint | Falsework details provided to Administrator at least 4 weeks prior to erection.
af3e7a29-b064-5be0-b3d5-2020408f8dbb | note | Acceptance Criteria and Frequency (Project Specific) - Visual
67021ca3-ec0c-52f6-943a-8e499a025806 | note | Check Item - Milestone
9f2868b7-8234-5f8d-a6ce-bae2972789e4 | note | Reference - MRTS70 Cl 15.3
e909724e-9c51-489a-bd4e-8e9245c7b966 | checkpoint | Design and erection of falsework, its founding, support and time, order and manner of release approved by the Administrator.
6b70f3b6-7e5c-5435-be57-6124af77d02c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f5223bbf-7e43-5449-8886-d6be203de610 | note | Check Item - Hold Point 2
d4c4dff2-4f90-51be-a8bc-8627f091642d | note | Reference - MRTS70 Cl 15.3
5ae7bdf1-a3bd-46ad-8e11-ef31e9026d5c | signoff | Hold Point
b18487e3-e218-4a6b-916d-a521a92409c2 | checkpoint | All formwork shall be subject to inspection and approval by the Administrator.
5b2ff10d-6663-5650-9d10-2a08b4db35f0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5880c4aa-0e2e-5142-b950-e9092a086cfa | note | Check Item - Hold Point 3
726a35ea-ed22-5d6f-a421-ade7d4b633e4 | note | Reference - MRTS70 Cl 15.4.1
d35d036e-1a84-46a9-bfb4-87cb060ed139 | signoff | Hold Point
2542631e-b347-45ea-beab-5fc489c4f7ab | checkpoint | Concrete operations shall not commence until all relevant procedures, listed in Table 5.2 have been approved by the Administrator.
c635d8f3-a091-54a1-8ca1-c2b779c83bea | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6384a721-4538-5ade-8702-a0eeb60d6800 | note | Check Item - Hold Point 4
27c5214f-58f2-579e-b11a-ec55e6637f1b | note | Reference - MRTS70 Cl 15.6
45b48f79-e467-4091-b805-3eaa26e5361e | signoff | Hold Point
f9e656e6-aaf2-41ec-a50d-3cdb1e03b568 | checkpoint | No concrete shall be placed in the Works until:
732bba72-4325-5b00-8bf0-04a3a5a2457f | note | a) the formwork and reinforcement have been inspected
2fe1a762-47a8-536f-878d-3218934830d0 | note | b) all foreign material has been completely removed from the forms
4c78f3b0-28ae-57bc-bc87-eaee8c5d9805 | note | c) the mixing, batching, and compaction equipment have been approved by the Administrator.
283440cf-4184-5f08-9488-61dd61dbd28b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e5d15498-d3b1-5a2f-b435-813f40303b3a | note | Check Item - Hold Point 5
a479597c-8a0d-5c48-900c-4f9ea4877a16 | note | Reference - MRTS70 Cl 15.6.1
fab8cf2c-0f8f-402c-88d9-b82e0068041b | signoff | Hold Point
f5fc1519-8f3a-48b1-b507-c0e3e842ae96 | checkpoint | Administrator to be present for placement of concrete, given 24 hours notice.
627e8b24-700a-592a-a3c4-9dedb7c789a3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b7676f74-8341-5a80-9087-d3388c4839a1 | note | Check Item - Witness Point 2
814234db-f69d-5d08-8126-78bf41a5437c | note | Reference - MRTS70 Cl 15.6.1
b6e3ac36-a07d-484a-a92e-f4cb292bc91f | checkpoint | Concrete slump is within tolerance (AS 1379 table 6) of approved target slump.
299abcd8-8e2c-538c-a84d-23d17f24cd93 | note | Acceptance Criteria and Frequency (Project Specific) - Slump Test:
8e5496ed-4e22-5de6-aa4f-be0a8841fafd | note | <60 - ±10
8467f85a-74ab-52bf-9391-068728feb18a | note | ≥60≤80 - ±15
c2af8c6d-230d-5b17-93b7-defc3b695fec | note | >80≤110 - ±20
d8050b8e-80f9-57cc-856b-3a42db1de7e9 | note | >110≤150 - ±30
11080a43-c313-5d3d-8a95-70e89cf30cb0 | note | >150 - ±40
cdf9cbd0-7775-5e1e-9377-1310d52d78d2 | note | (Every Load)
b9b30615-3239-541a-beff-1950ba0c2427 | note | Check Item - Check Item
72746d28-c1aa-53c0-8cce-60d109e77e5b | note | Reference - MRTS70 AS 1379 Table 5.1
55fb4458-2110-4e49-aba8-51ad1e1f8ae9 | checkpoint | Samples for testing taken as required in accordance with claus 12. - min 2 cylinders/sample.
13754e30-0e53-5a63-9f3d-3520a7d06ce7 | note | Acceptance Criteria and Frequency (Project Specific) - 1-3 Loads - Every Load
a95a8fd5-ba01-59e4-9b6f-60736ad7f4ba | note | ○ 4-10 Loads - 4 Samples
0129631f-ba73-5867-b3fd-2155bb2baccc | note | ○ 11-23 Loads - 5 Samples
84474153-c72b-5fbd-a6d2-824893882565 | note | ○ >23 Loads - 1 per 4 loads
a66421ed-3a64-59b6-900b-a9af73f46edd | note | Check Item - Test Results
59fd806b-72e0-546c-9104-db7e7f81529c | note | Reference - MRTS70 Cl 15.2.1 Table 15.2
7343955c-0474-4947-82d9-08a19ada1e7c | checkpoint | Compaction of concrete commences immediately after deposition in accordance with approved procedures and equipment - The number of vibrators to be used by the Contractor shall be not less than one for each 10 m³ of concrete placed per hour.
f8cb7e32-25f4-5de0-b483-ee0be6009c0e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
cdd2b4b2-c34b-5555-87d2-38bba3f45c9c | note | Check Item - Check Item
271a9962-2a63-58fe-b422-1c985b36b1e8 | note | Reference - MRTS70 Cl 16.5.2
03bd2f49-f9bf-445a-b84d-bc781a8e9f38 | checkpoint | Fresh concrete shall not be placed against concrete which has taken its initial set. If an interruption greater than 45 minutes occurs, without prio approval from the Administrator, or a cold join occurs, the precast member shall be rejected.
680d8a87-a7f3-5fbf-8bbd-b920a0ba5e68 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
00f3ba8f-091a-5b31-982c-7460573bb029 | note | Check Item - Check Item
696838d3-71e1-5451-9d22-227340a83c56 | note | Reference - MRTS70 Cl.16.5.1
8f173385-994b-49d6-96bc-3005f38c8597 | checkpoint | Construction joints shown in the Drawings are mandatory. The use of construction joints elsewhere in the concrete work shall require the prior approval of the Designer.
b45d3e2b-9031-51c6-8e5a-28434b0acb8c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1e291958-86d7-5b6d-831c-39c9121da5d0 | note | Check Item - Hold Point 7
61643713-7634-5332-bb71-1249172fe87f | note | Reference - MRTS70 Cl 15.13
173b2006-3e31-42a9-80d2-2b83bfc6ffd2 | signoff | Hold Point
f6aa9d4e-abfe-432f-b605-dd27e85bb4ee | checkpoint | Forms, falsework and centring shall remain in position until the times stated in Cl15.8 and table 15.8 have elapsed after completion of concreting.
8e688eba-6f76-5a53-a6b4-0b95e826a645 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
dfbcd29f-291e-519b-a03f-5037435acc1d | note | Check Item - Hold Point 6
f32d4fb8-ad0f-5d33-b7d0-5f7dda9bb181 | note | Reference - MRTS70 Cl 15.8
0a75d6f9-6c54-4248-85c0-3b470ab2d89f | signoff | Hold Point
8e4f24f7-78bb-4cc7-b946-b56e254b5342 | checkpoint | Forms shall be removed with care, without hammering and wedging, and in a manner which shall not injure the concrete or disturb the remaining supports. Centres shall be lowered gradually and uniformly in such a manner as to avoid injurious stress in any part of the structure.
b8d0126a-55b5-5879-baaf-7f4072ace737 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
7348067e-8d76-51c8-9269-0e6c80940437 | note | Check Item - Witness Point 4
2e1d7ed1-265e-5ef5-acf1-9d9de29544a6 | note | Reference - MRTS70 Cl 15.8
ec9a5feb-a4e6-45f2-b0ee-bd1edb4d60da | checkpoint | Following removal of forms
04b87dca-38ce-5d65-8968-b3e0fd04d6eb | note | ○ Fins and unwanted projections are ground off
a6e51662-25db-5867-a96a-7d78aab60ee2 | note | ○ Where required in the drawings surfaces achieve class 1 finish or are bagged within 4 hours of stripping, then cured
c2a0b7f0-315b-5bbf-8357-cf2195d0eae7 | note | ○ Where surface finish is not specified, class 2 finish is required. Where surfaces of concree do not achieve class 2, surface shall be bagged.
986941e3-8b6b-50fa-b378-e9792e3e53a8 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
db8e544d-d68f-585f-b984-19505a9f4aab | note | Check Item - Check Item
7312b8f2-d204-5259-9f13-36e54a46cfb4 | note | Reference - MRTS70 Cl 16.8.1
37300c20-634e-4710-af1b-8f8f66efaa8a | checkpoint | Positional tolerances, listed in Table 15.7.3, refer to the departure of any point, plane or component of a structure from its correct position within the layout of the structure as shown in the Drawings.
2091453c-d7d1-5eb7-80fb-0e40026a85eb | note | Acceptance Criteria and Frequency (Project Specific) - Visual, <Specified MRTS70 Cl15.7.3
aa0f7f3a-0f5c-5f38-b35c-ee705ba8f002 | note | Check Item - Check Item
15a05154-1b20-5c4f-9e32-0eeb4c7c63f8 | note | Reference - MRTS70 Cl 15.7.3
ff8b6894-27a9-4483-946f-9f3fb7b11b2f | checkpoint | Acceptance or Rejection of Hardened Concrete on the Basis of Strength
d497f74e-3a75-5104-9516-ed8266f6073a | note | Acceptance Criteria and Frequency (Project Specific) - a) < 0.9 Fc (Any sample)
5edf5e88-d685-5a01-b5d2-7b988425cd4e | note | b) < Fc (Ave 3 consective samples from Lot)
1f763625-f402-53fc-92ba-50d388f51458 | note | c) > 1.4 Fc (Ave 3 consective samples from Lot)
3c0e42ba-d41b-53be-9a22-bde611e88003 | note | In addition
ed0f4835-657f-5c6c-b3af-a503ae13df0c | note | d) < 0.5 (Fc+Ft) (10 or more samples for Class of concrete in 4 consective weeks)
26f81ae6-084f-577c-a752-9bddd07747c2 | note | Check Item - Test Results
b181b183-7d70-57eb-a97c-bb9931fa2053 | note | Reference - MRTS70 Cl 12.5 & Cl 12.4
3914a2de-47c7-4fa8-8443-3722dd66ba47 | checkpoint | Final Verification
d882729d-3aca-5379-baac-3c30842c78a6 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
66461a8b-e0a5-592d-a709-73dde246d58e | textbox | Print Name:
1c4d8ec4-f2a0-504a-baf5-048ad9dc858a | date | Date:
6b1cb988-01e3-5ca1-a0c6-7396517f836f | note | Project Manager Verify that the Above has been Constructed according to Specification
d7d2f477-2fd8-5cc8-a54f-a7c38ba0663e | textbox | Print Name:
94bd3949-9de6-5b43-97c8-f7060f5a8c33 | date | Date:
e5f83e78-f7c8-47ba-8c39-353d60b5769e | signoff | Signature
b9c516a4-7075-4612-a27e-3f6ec87b0386 | section | Final Sign Offs (to be completed at closure of Lot)
413bf376-6932-468b-87a3-434824c81414 | checkpoint | Agreed Quantities
9c8302ab-e86e-4427-bac5-3908fff741e8 | signoff | Agreed Quantities Sign Off
64330318-6f58-4d91-80c4-b86a11cb3290 | checkpoint | Closure of Lot
cce1bfc1-c20e-4c3d-9069-e862b93a1003 | signoff | Closure of Lot Sign Off
77094e12-80af-4680-ab31-426640ae0992 | checklist | Asbestos Removal | itp | Asbestos Removal
784f2fd0-fc6a-44b7-abdc-4639a8e223c5 | section | Subcontractor ITP
edd09d77-28b4-415f-92e0-7ca72b1229a4 | checkpoint-no-value | Attachments
e0988e1c-96ff-427f-addb-b0acddc1c1b2 | section | Final Sign Offs (to be completed at closure of Lot)
026a8f7b-122c-41a1-8dbe-181d66ee195b | checkpoint | Agreed Quantities
f4f76dab-cb0c-4789-9d31-2e1248d9d9c8 | signoff | Agreed Quantities Sign Off
5bc91423-d52d-4444-803e-102a829a3916 | checkpoint | Closure of Lot
e58eeca0-bca8-4d3b-a0a1-2c649ec4953c | signoff | Closure of Lot Sign Off
89881fb3-5fd3-4dff-b476-98cba01e1026 | checklist | Electrical | itp | Electrical
ea508996-d597-4bfd-a084-3bdafd90b504 | section | Subcontractor ITP
ab83349c-2dfc-4fcc-96f6-a85d6dc7172b | checkpoint-no-value | Attachments
74f0f78e-a496-44d4-ba55-7ca4a8518232 | section | Final Sign Offs (to be completed at closure of Lot)
fadd3aa0-bf06-459b-a6c4-5234c3f0fba9 | checkpoint | Agreed Quantities
0b55f0ce-d6b0-45ba-a127-ae937668915f | signoff | Agreed Quantities Sign Off
4ad25a9c-2c48-40c5-89fa-5d9902e28ace | checkpoint | Closure of Lot
9c0f0cd8-ddb1-4a31-8b71-3fd483536597 | signoff | Closure of Lot Sign Off