## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Post Completion Audit Checklist - FP&KC
section | 1.0 - QA Desktop - Final Completion Audit
checkpoint | 1.1 - All QA documentation completed
checkpoint | 1.2 - Final Comment/Sign Off
holdpoint | HOLD POINT
section | 2.1 - QA Onsite - Final Completion Audit
checkpoint | 2.2 - Timber edging in place for AC FP
checkpoint | 2.3 - Berm - soil and grass seed applied
checkpoint | 2.4 - Cracking
checkpoint | 2.5 - Line marking reinstatement
checkpoint | 2.6 - Water / drainage issues
checkpoint | 2.7 - TTM Removed
checkpoint | 2.8 - Sumps / Enviro controls removed
checkpoint | 2.9 - Permanent signage reinstated
checkpoint | 2.10 - Stormwater outlets reinstated
checkpoint | 2.11 - Furniture
checkpoint | 2.12 - Surface quality
checkpoint | 2.13 - Other Quality Observation
checkpoint | 2.14 - Expansion joints - Con 5mtrs & KC 3 mtrs
checkpoint | 2.15 - K&C Water Banding
checkpoint | 2.16 - Site Cleanliness
checkpoint | 2.17 - Final Comment/Sign Off
holdpoint | HOLD POINT