## ITP Cover Page
Wetland 03 Inspection and Test Plan
Project: Tauriko Enabling Project SP2
Number and Revision: DN1210 - 020-002 - Rev 1
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project SP2 |  |  |  |  | ITP Number: |  |  | 020-002
Project Number: |  |  | DN1210 |  |  |  |  | ITP Status: |  |  | IFC
ITP Description: |  |  | Wetlands 03 - Earthworks |  |  |  |  | Revision: | 1000 |  | 1
Contract Number: |  |  | NZTA 8287 |  |  |  |  | Drawing Sets: |  |  | 232735.02-WSP-DR-STW, 23273502-WSP-DR-GEO, 2-32735.02-WSP-DR-UDL
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  | Project specification : H29 Tauriko West Enabling Works Contract No.NZTA8287 Section 16, 20, 27
Quality Specified: |  |  | ISO9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval | 17/02/2025 |  | Nick Adams & Cordelia Girdler-Brown | [5 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
1 | IFC | 24/03/2025 |  | Nick Adams & Cordelia Girdler-Brown | [5 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | Nick Adams |  |  | #VALUE! |  | 24/03/2025 | Downer PM
Downer QM |  | Cordelia Girdler-Brown |  |  |  |  | 25/03/2025 | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)
Note on E10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Wetlands 02 or Wetland 03?
Note on P13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Daniel Barnard - please add project spec details here

## ITP Master Body
Wetland 03 Inspection and Test Plan
Project: Tauriko Enabling Project SP2
Number and Revision: DN1210 - 020-002 - Rev 1
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – PRE-CONSTRUCTION HOLD POINTS - MATERIALS, PERSONELL & THIRD PARTY APPROVALS
3.1 | Erosion & Sedimentation Controls | Confirm that Erosion and Sedimentation Controls are in place prior to earthworks proceeding | As-built Completed | Internal Hold Point | ESC As-built | Prior to Earthworks | H | SE
3.2 | AP65-2 - Source material testing - Crushing Resistance | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | < 10% fines passing 2.36mm under a load of 100kN | NZS4407:2015 Test 3.10 TCC-IDC-IT-4.3.1-4.7.1 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.3 | AP65-2 - Source material testing - Soaked CBR | NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR) | ≥60% | NZS4402 Test 3.15 TCC-IDC-IT-4.3.1-4.7.1 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.4 | AP65-2 - Source material testing -Weathering Resistance | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | AA, AB, AC, BA, BB, CA or CB | NZS4407 Test 3.11 TCC-IDC-IT-4.7.1 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.5 | AP65-2 - Production testing - Particle Size Distribution | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | Sieve Size % Passing 63.0mm 100% passing 37.5mm 68-90% passing 19.0mm 42-76% passing 9.5mm 26-58% passing 4.75mm 16-44% passing 2.36mm 10-33% passing 1.18mm 6-24% passing 0.425mm 3-14% passing 0.075mm 1-6% passing | NZS4407 Test 3.8.1 TCC-IDC-IT-4.7.2 | IANZ Accredited Report | Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
3.6 | AP65-2 Production testing - Shape Control | Tolerance allowed from approved grading curve (%) | Sieve Size % Tolerance 37.5 – 9.5 34-50% 19.0 – 4.75 18-40% 9.5 – 2.36 12-32% 4.75 – 1.18 6-24% 2.36 – 0.6 2-20% 1.18 – 0.3 0-15% 0.6 – 0.15 0-12% | TCC-IDC IT-4.7.2 | IANZ Accredited Report | Number of Tests Required Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
3.7 | AP65-2 Production testing - Maximum Dry Density and Optimum Water Content | NZS4402:1986, Test 4.1.2 - Heavy Compaction Test | Report Value Only | NZS4407 TCC-IDC-IT-4.7.1 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.8 | AP65-2 Production testing - The Solid Density | NZS 4407:1991 Test | Report Value Only | NZS4407 TNZ B/02:2005 7.5 TCC-IDC-IT-4.7.1 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.9 | AP65-2 - Production testing - Plasticity Index | NZS4407:2015, Test 3.4 Plasticity Index | ≤ 8 | NZS4407:2015 Test 3.4 TCC-IDC-IT-4.7.2 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.1 | AP65-2 - Production testing - Sand Equivalent | NZS4407:2015, Test 3.6 Sand Equivalent Washing method | ≥25 | NZS4407 Test 3.6 TCC-IDC-IT-4.7.2 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.11 | Geotextile | The Contractor shall submit the full details of the filter fabric they propose to use to the Engineer for approval prior to installation. Class D | Engineers Approval | PS 16.5.7 Appendix V | Delivery Docket/Material certificate | Results to Engineer for Approval | HP | ENG
3.2 | Imported/Site Won Material Testing - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
3.2.1 | Site Topsoil - Laboratory Testing for Soil Suitability | Soil Test Results from Hill Laboratories to confirm that topsoil suitable to for reuse Soil Reaction Electrical Conductivity Mechanical Analysis (texture) Stone Content Nutrient Levels of nitrogen, available phosphorus, available potassium and available magnesium Organic Matter Content Check for Toxic or Hazardous substances | Engineers Approval | NZTA P39:2013 3.1 | Laboratories Test Report | 10 equal samples taken from site, mixed together, then 1kg of soil sealed into a plastic bag and sent to lab for sampling | I | SE
3.2.2 | SITE WON MATERIAL (TYPE A2 NON-GRANULAR)- Maximum dry density optimum water content air voids and shear vane strength (su) with range of mositure contents | NZS4402:1986 test 4.1.2 heavy compaction test | Results from test | Appendix XVIII | Report | 1 set (3 tests) per material type and source | HP | ENG
3.2.3 | SITE WON MATERIAL (TYPE A2 NON-GRANULAR) - Organic content | Visual observation | Fill shall be free from organic, calcareous or other deleterious materials | Appendix XVIII | ConQA | Fill shall be free from organic, calcareous or other deleterious materials | HP | ENG
3.2.4 | SITE WON MATERIAL (TYPE A2 NON-GRANULAR) - Soil Permability | maximum soil permeability | 10-7 m/s | PS:16.5.5 Appendix XVIII | Report | 1 Test Per Source | HP | ENG
3.2.5 | SITE WON MATERIAL (TYPE A2 NON-GRANULAR) - Liquid limit | liquid limit | less than 65% (Engineers Approval) | PS:16.5.5 | Report | 1 Test Per Source | HP | ENG
3.2.6 | SITE WON MATERIAL (TYPE A2 NON-GRANULAR) - Moisture content | maximum moisture content | 6 % above (Engineers Approval) | PS:16.5.5 | Report | 1 Test Per Source | HP | ENG
3.2.7 | SITE WON MATERIAL (TYPE A2 NON-GRANULAR) - Prohibitied materials | deleterious materials | Not containing allophane, organics or other deleterious materials. (Engineers Approval) | PS:16.5.5 | Report | 1 Test Per Source | HP | ENG
3.2.8 | Pumice sand - Maximum dry density optimum water content air voids and shear vane strength (su) with range of mositure contents | NZS4402:1986 test 4.1.2 heavy compaction test | Results from test | Appendix XVIII | Report | 1 set (3 tests) per material type and source | HP | ENG
3.2.9 | Pumice sand - Organic content | Visual observation | Fill shall be free from organic, calcareous or other deleterious materials | Appendix XVIII | ConQA | Fill shall be free from organic, calcareous or other deleterious materials | HP | ENG
3.2.10 | Pumice sand - Soil Permability | maximum soil permeability | 10-7 m/s | PS:16.5.5 Appendix XVIII | Report | 1 Test Per Source | HP | ENG
3.2.11 | Pumice sand - Liquid limit | liquid limit | less than 65% (Engineers Approval) | PS:16.5.5 | Report | 1 Test Per Source | HP | ENG
3.2.12 | Pumice sand - Moisture content | maximum moisture content | 6 % above (Engineers Approval) | PS:16.5.5 | Report | 1 Test Per Source | HP | ENG
3.2.13 | Pumice sand - Prohibitied materials | deleterious materials | Not containing allophane, organics or other deleterious materials. (Engineers Approval) | PS:16.5.5 | Report | 1 Test Per Source | HP | ENG
3.2.14 | Pumice sand - Compaction | NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer Testing of the Subgrade where no Structural Fill has been placed, Scala's to be carried out. This test shall be undertaken on the cut surface to a depth of not less than 1m | Scala blows >3 | PS16.5.12 | Report | 4 test per 400M2 | HP | ENG
3.2.15 | Pumice sand - Bulk density, Dry density, Air voids | NZS4402:1986 - Test 5.1.3 sampling tube method for determination of the in-situ density | Results from test | Appendix XVIII | Report | 1 Test performed for every 10 NDM | HP | ENG
SECTION 4 - CONSTRUCTION - ACCESS TRACK
4.1 | Subgrade Level Confirmation | Confirm subgrade is 300mm from finished height | String lines - or equivalent are 400mm +0mm/-30mm Tolerances width -20mm +100mm | PS 20.14.5 | Survey as-builts | Every 20m chainage | I | SE
4.2 | Subgrade - CBR Testing | NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer Testing of the Subgrade where no Structural Fill has been placed, Scala's to be carried out. This test shall be undertaken on the cut surface to a depth of not less than 1m | CBR >7 Min 3 blows / 100mm | PS 27.4.2 Appendix XVIII | Scala Report | 4 test per 400M2 | I | SE
4.3 | Subgrade - CBR Testing | "NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level" Hand auger hole is required | "Average Minimum SU: > 60kPa Single Test Min SU: >50kPa 2-3m deep " | PS 27.4.2 Appendix XVIII | Shear Vane Report | 4 test per 400M2 | I | SE
4.4 | Subgrade - Proof Roll | Visual Inspection of Proof Roll | Displacement <15mm | Appendix XVIII | Visual Observation | Across stripped area | I | SE
4.5 | Hold point- QA Submission | Submit all Subgrade lift QA before proceeding with next pavement layer | Engineers Approval | Appendix V | Conqa Siggnoff | Once | HP | ENG
4.6 | Subgrade Fill - CBR Testing | NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer Testing of the Subgrade where no Structural Fill has been placed, Scala's to be carried out. This test shall be undertaken on the cut surface to a depth of not less than 1m | Min 4 blows / 100mm | Appendix XVIII | Scala Report | 4 test per 400M2 | HP | ENG
4.7 | Subgrade Fill- CBR Testing | "NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level" Hand auger hole is required | Average minimum Su > 125kpa Single test minimum Su > 100kPa | Appendix XVIII | Shear Vane Report | 1 set (5 test) per 100m3 of fill placed per area worked per day per lift | HP | ENG
4.8 | Subgrade Fill - Bulk desnity, Dry density, Air voids | NZS4402:1986 - Test 5.1.3 sampling tube method for determination of the in-situ density | Results from test | Appendix XVIII | Report | 1 Test performed for every 10 NDM | HP | ENG
4.9 | Subgrade Fill - Water content | NZS4402:1986 - Test 2.1 water content | Results from test | Appendix XVIII | Report | 1 set (5 test) per 200m3 of fill placed per area worked per day per lift | HP | ENG
4.1 | Subgrade Fill - Insitu density insitu compacted dry density insitu water content | NZS4407:2015 – test 4.3 nuclear moisture density gauge (ndm), direct transmission mode | Average maximum air voids < 7% Single test maximum air voids < 6% | Appendix XVIII | Report | 1 Set (5 Test) per200m3 | HP | ENG
4.11 | Subgrade Fill (Pumice sand) - Compaction | NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer Testing of the Subgrade where no Structural Fill has been placed, Scala's to be carried out. This test shall be undertaken on the cut surface to a depth of not less than 1m | Scala blows >5 | PS16.5.12 | Report | 4 test per 400M2 | HP | ENG
4.12 | Subgrade Fill (Pumice sand) - Bulk density, Dry density, Air voids | NZS4402:1986 - Test 5.1.3 sampling tube method for determination of the in-situ density | Average 95% MDD, min >92% | PS16.5.13 | Report | 1 Test performed for every 10 NDM | HP | ENG
4.13 | HOLD POINT- QA Submission | Submit all Subgrade lift QA before proceeding with next fill layer | Engineers Approval | Appendix V | Conqa Siggnoff | Once | HP | ENG
4.14 | GEOTEXTILE FABRIC - Placement of Geotextile Fabric | Place Geotextile Fabric Strength Class D across pavement area, with 500mm overlaps | Visual inspection | 232735.02-WSP-DR-STW 0302 | Visual Inspection and photos | During construction | WP | ENG
4.15 | SUBBASE (TCC AP65-2) - 3m Straight Edge | Formation check to ensure surface is smooth | +/- 15mm | PS 27.4.1 | Check Sheet | Every 20m Centres 1 each lane | I | SE
4.16 | SUBBASE (TCC AP65-2) - Stringlines or equivalent | Stringlines or equivalent to check finished height of surface | String lines - or equivalent are 150mm +5mm/-25mm | TNZ B/02:2005 5.1 232735.02-WSP-DR-STW 0303 | Check Sheet | 1 Set Every 20m Centres 1 set = 5 tests | I | SE
4.17 | SUBBASE (TCC AP65-2) - Compaction - NDM | NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode) | Ave >95% of MDD Min >92% of MDD | TNZ B/02:2005 7.5 | IANZ Accredited Report | 1 set (5 tests) 1000m2 | I | SE
4.18 | HOLD POINT - QA Submission | Submit all Subbase QA before proceeding with next pavement layer | Engineers Approval | Appendix V | All test reports Material Test Results Laboratory MDD NDM results | Once | HP | ENG
SECTION 5 - CONSTRUCTION - EARTHWORKS
5.1 | Subgrade Level Confirmation | Confirm subgrade is min 500mm below excisting ground level. | String lines - or equivalent are 300mm +0mm/-30mm Tolerances width -20mm +100mm | PS 21.5.15 e) | Survey as-builts | Every 20m chainage on all major contours | I | SV
5.2 | Subgrade CBR Testing | NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer Testing of the Subgrade where no Structural Fill has been placed, Scala's to be carried out. This test shall be undertaken on the cut surface to a depth of not less than 1m | CBR >7 Min 3 blows / 100mm | PS 27.4.2 Appendix XVIII | Scala Report | 4 test per 400M2 | I | SE
5.3 | Subgrade CBR Testing | "NZ Geotechnical Society 2001 - Guideline for Hand Held Shear Vane Test This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level" Hand auger hole is required | "Average Minimum SU: > 60kPa Single Test Min SU: >50kPa 2-3m deep " | PS 27.4.2 Appendix XVIII | Shear Vane Report | 4 test per 400M2 | I | SE
5.4 | Subgrade Proof Roll | Visual Inspection of Proof Roll | Displacement <15mm | Appendix XVIII | Visual Observation | Across stripped area | I | SE
5.5 | FILLING A2 COHESIVE MATERIAL - Subgrade CBR Testing | NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer Testing of the Subgrade where no Structural Fill has been placed, Scala's to be carried out. This test shall be undertaken on the cut surface to a depth of not less than 1m | Min 2 blows / 100mm | Appendix XVIII | Scala Report | 4 test per 400M2 | HP | ENG
5.6 | FILLING A2 COHESIVE MATERIAL - Subgrade CBR Testing | "NZ Geotechnical Society 2001 - Guideline for Hand Held Shear Vane Test This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level" Hand auger hole is required | Average minimum Su > 80kPa Single test minimum Su > 60kPa | Appendix XVIII | Shear Vane Report | 1 set (5 test) per 500m3 of fill placed per area worked per day per lift | HP | ENG
5.7 | FILLING A2 COHESIVE MATERIAL - Compaction - Clegg Hammer | ASTM D5874-16:2016 Clegg Hammer Testing | Non-Structural Fill Min CIV 10 Max CIV 12 | Appendix XVIII | Clegg Hammer Report | 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift | HP | ENG
5.8 | FILLING A2 COHESIVE MATERIAL - Bulk density, Dry density, Air voids | NZS4402:1986 - Test 5.1.3 sampling tube method for determination of the in-situ density | Results from test | Appendix XVIII | Report | 1 Test performed for every 10 NDM | HP | ENG
5.9 | FILLING A2 COHESIVE MATERIAL - Water content | NZS4402:1986 - Test 2.1 water content | Results from test | Appendix XVIII | Report | 1 set (5 test) per 200m3 of fill placed per area worked per day per lift | HP | ENG
5.1 | FILLING A2 COHESIVE MATERIAL - Insitu density insitu compacted dry density insitu water content | NZS4407:2015 – test 4.3 nuclear moisture density gauge (ndm), direct transmission mode | Average maximum air voids < 8% Single test maximum air voids < 10% | Appendix XVIII | Report | 1 Set (5 Test) per200m3 | HP | ENG
5.11 | FILLING A2 COHESIVE MATERIAL - Final Level Confirmation | Confirm subgrade is min 300mm below final level for topsoil | String lines - or equivalent are 300mm +0mm/-30mm Tolerances width -20mm +100mm | PS 21.5.15 e) | Survey as-builts | Every 20m chainage on all major contours | I | SV
5.12 | SUBGRADE FILL (Pumice sand) - Compaction | NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer Testing of the Subgrade where no Structural Fill has been placed, Scala's to be carried out. This test shall be undertaken on the cut surface to a depth of not less than 1m | Scala blows >5 | PS16.5.12 | Report | 4 test per 400M2 | HP | ENG
5.13 | SUBGRADE FILL (Pumice sand) - Bulk density, Dry density, Air voids | NZS4402:1986 - Test 5.1.3 sampling tube method for determination of the in-situ density | Average 95% MDD, min >92% | PS16.5.12 | Report | 1 Test performed for every 10 NDM | HP | ENG
5.14 | HOLD POINT - QA Submission | Submit all Subgrade QA before proceeding with next pavement layer | Engineers Approval | Appendix V | Conqa Siggnoff | Once | HP | ENG
SECTION 6 – AS-BUILTS
6.1 | As-Builts | As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets. |  | PS 16.7.6 | Survey Records/ Redpen markups | Post Earthworks | D | SV
Note on B8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please start this as Section 3 as you already covered section 1 and 2 in the cover page.