## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-SP2-020-002 ITP Earthworks Wetland 03 | itp |  |  |  |  | DN1210-SP2-020-002 ITP Earthworks Wetland 03 Rev 1
section | SECTION 3 – PRE-CONSTRUCTION HOLD POINTS - MATERIALS, PERSONELL & THIRD PARTY APPROVALS
checkpoint | 3.1 - Erosion & Sedimentation Controls
label | Detail - Confirm that Erosion and Sedimentation Controls are in place prior to earthworks proceeding
label | Acceptance / Conformance Criteria - As-built Completed
label | Standard / Specification - Internal Hold Point
label | Verifying Document - ESC As-built
label | Testing Quantity Required (based from schedule qtys) - Prior to Earthworks
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.2 - AP65-2 - Source material testing - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - < 10% fines passing 2.36mm under a load of 100kN
label | Standard / Specification - NZS4407:2015 Test 3.10, TCC-IDC-IT-4.3.1-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - AP65-2 - Source material testing - Soaked CBR
label | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
label | Acceptance / Conformance Criteria - ≥60%
label | Standard / Specification - NZS4402 Test 3.15, TCC-IDC-IT-4.3.1-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - AP65-2 - Source material testing -Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB, CA or CB
label | Standard / Specification - NZS4407 Test 3.11, TCC-IDC-IT-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - AP65-2 - Production testing - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Passing
label | 63.0mm ¦¦ 100% passing
label | 37.5mm ¦¦ 68-90% passing
label | 19.0mm ¦¦ 42-76% passing
label | 9.5mm ¦¦ 26-58% passing
label | 4.75mm ¦¦ 16-44% passing
label | 2.36mm ¦¦ 10-33% passing
label | 1.18mm ¦¦ 6-24% passing
label | 0.425mm ¦¦ 3-14% passing
label | 0.075mm ¦¦ 1-6% passing
label | Standard / Specification - NZS4407 Test 3.8.1, TCC-IDC-IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - AP65-2 Production testing - Shape Control
label | Detail - Tolerance allowed from approved grading curve (%)
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Tolerance
label | 37.5 – 9.5 ¦¦ 34-50%
label | 19.0 – 4.75 ¦¦ 18-40%
label | 9.5 – 2.36 ¦¦ 12-32%
label | 4.75 – 1.18 ¦¦ 6-24%
label | 2.36 – 0.6 ¦¦ 2-20%
label | 1.18 – 0.3 ¦¦ 0-15%
label | 0.6 – 0.15 ¦¦ 0-12%
label | Standard / Specification - TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - AP65-2 Production testing - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - NZS4407 TCC-IDC-IT-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - AP65-2 Production testing - The Solid Density
label | Detail - NZS 4407:1991 Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - NZS4407 TNZ B/02:2005 7.5, TCC-IDC-IT-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9 - AP65-2 - Production testing - Plasticity Index
label | Detail - NZS4407:2015, Test 3.4 Plasticity Index
label | Acceptance / Conformance Criteria - ≤ 8
label | Standard / Specification - NZS4407:2015 Test 3.4, TCC-IDC-IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.10 - AP65-2 - Production testing - Sand Equivalent
label | Detail - NZS4407:2015, Test 3.6 Sand Equivalent, Washing method
label | Acceptance / Conformance Criteria - ≥25
label | Standard / Specification - NZS4407 Test 3.6, TCC-IDC-IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.11 - Geotextile
label | Detail - The Contractor shall submit the full details of the filter fabric they propose to use to the Engineer for approval prior to installation. Class D
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.5.7 Appendix V
label | Verifying Document - Delivery Docket/Material certificate
label | Testing Quantity Required (based from schedule qtys) - Results to Engineer for Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 3.2 - Imported/Site Won Material Testing - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
checkpoint | 3.2.1 - Site Topsoil - Laboratory Testing for Soil Suitability
label | Detail - Soil Test Results from Hill Laboratories to confirm that topsoil suitable to for reuse
label | ○ Soil Reaction
label | ○ Electrical Conductivity
label | ○ Mechanical Analysis (texture)
label | ○ Stone Content
label | ○ Nutrient Levels of nitrogen, available phosphorus, available potassium and available magnesium
label | ○ Organic Matter Content
label | ○ Check for Toxic or Hazardous substances
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - NZTA P39:2013 3.1
label | Verifying Document - Laboratories Test Report
label | Testing Quantity Required (based from schedule qtys) - 10 equal samples taken from site, mixed together, then 1kg of soil sealed into a plastic bag and sent to lab for sampling
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.2.2 - SITE WON MATERIAL (TYPE A2 NON-GRANULAR)- Maximum dry density optimum water content air voids and shear vane strength (su) with range of mositure contents
label | Detail - NZS4402:1986 test, 4.1.2 heavy compaction test
label | Acceptance / Conformance Criteria - Results from test
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (3 tests) per material type and source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.3 - SITE WON MATERIAL (TYPE A2 NON-GRANULAR) - Organic content
label | Detail - Visual observation
label | Acceptance / Conformance Criteria - Fill shall be free from organic, calcareous or other deleterious materials
label | Standard / Specification - Appendix XVIII
label | Verifying Document - ConQA
label | Testing Quantity Required (based from schedule qtys) - Fill shall be free from organic, calcareous or other deleterious materials
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.4 - SITE WON MATERIAL (TYPE A2 NON-GRANULAR) - Soil Permability
label | Detail - maximum soil permeability
label | Acceptance / Conformance Criteria - 10-7 m/s
label | Standard / Specification - PS:16.5.5 Appendix XVIII
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.5 - SITE WON MATERIAL (TYPE A2 NON-GRANULAR) - Liquid limit
label | Detail - liquid limit
label | Acceptance / Conformance Criteria - less than 65% (Engineers Approval)
label | Standard / Specification - PS:16.5.5
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.6 - SITE WON MATERIAL (TYPE A2 NON-GRANULAR) - Moisture content
label | Detail - maximum moisture content
label | Acceptance / Conformance Criteria - 6 % above (Engineers Approval)
label | Standard / Specification - PS:16.5.5
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.7 - SITE WON MATERIAL (TYPE A2 NON-GRANULAR) - Prohibitied materials
label | Detail - deleterious materials
label | Acceptance / Conformance Criteria - Not containing allophane, organics or other deleterious materials. (Engineers Approval)
label | Standard / Specification - PS:16.5.5
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.8 - Pumice sand - Maximum dry density optimum water content air voids and shear vane strength (su) with range of mositure contents
label | Detail - NZS4402:1986 test, 4.1.2 heavy compaction test
label | Acceptance / Conformance Criteria - Results from test
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (3 tests) per material type and source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.9 - Pumice sand - Organic content
label | Detail - Visual observation
label | Acceptance / Conformance Criteria - Fill shall be free from organic, calcareous or other deleterious materials
label | Standard / Specification - Appendix XVIII
label | Verifying Document - ConQA
label | Testing Quantity Required (based from schedule qtys) - Fill shall be free from organic, calcareous or other deleterious materials
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.10 - Pumice sand - Soil Permability
label | Detail - maximum soil permeability
label | Acceptance / Conformance Criteria - 10-7 m/s
label | Standard / Specification - PS:16.5.5 Appendix XVIII
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.11 - Pumice sand - Liquid limit
label | Detail - liquid limit
label | Acceptance / Conformance Criteria - less than 65% (Engineers Approval)
label | Standard / Specification - PS:16.5.5
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.12 - Pumice sand - Moisture content
label | Detail - maximum moisture content
label | Acceptance / Conformance Criteria - 6 % above (Engineers Approval)
label | Standard / Specification - PS:16.5.5
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.13 - Pumice sand - Prohibitied materials
label | Detail - deleterious materials
label | Acceptance / Conformance Criteria - Not containing allophane, organics or other deleterious materials. (Engineers Approval)
label | Standard / Specification - PS:16.5.5
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.14 - Pumice sand - Compaction
label | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ Testing of the Subgrade where no Structural Fill has been placed, Scala's to be carried out. This test shall be undertaken on the cut surface to a depth of not less than 1m
label | Acceptance / Conformance Criteria - Scala blows >3
label | Standard / Specification - PS16.5.12
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.15 - Pumice sand - Bulk density, Dry density, Air voids
label | Detail - NZS4402:1986 - Test 5.1.3 sampling tube method for determination of the in-situ density
label | Acceptance / Conformance Criteria - Results from test
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test performed for every 10 NDM
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 - CONSTRUCTION - ACCESS TRACK
checkpoint | 4.1 - Subgrade Level Confirmation
label | Detail - Confirm subgrade is 300mm from finished height
label | Acceptance / Conformance Criteria - String lines - or equivalent are 400mm +0mm/-30mm
label | ○ Tolerances width -20mm +100mm
label | Standard / Specification - PS 20.14.5
label | Verifying Document - Survey as-builts
label | Testing Quantity Required (based from schedule qtys) - Every 20m chainage
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.2 - Subgrade - CBR Testing
label | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ Testing of the Subgrade where no Structural Fill has been placed, Scala's to be carried out. This test shall be undertaken on the cut surface to a depth of not less than 1m
label | Acceptance / Conformance Criteria - CBR >7
label | ○ Min 3 blows / 100mm
label | Standard / Specification - PS 27.4.2 Appendix XVIII
label | Verifying Document - Scala Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.3 - Subgrade - CBR Testing
label | Detail - "NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test
label | ○ This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level
label | ○ Hand auger hole is required
label | Acceptance / Conformance Criteria - Average Minimum SU:
label | ○ > 60kPa
label | Single Test Min SU:
label | ○ >50kPa
label | ○ 2-3m deep
label | Standard / Specification - PS 27.4.2 Appendix XVIII
label | Verifying Document - Shear Vane Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.4 - Subgrade - Proof Roll
label | Detail - Visual Inspection of Proof Roll
label | Acceptance / Conformance Criteria - Displacement <15mm
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Visual Observation
label | Testing Quantity Required (based from schedule qtys) - Across stripped area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.5 - Hold point- QA Submission
label | Detail - Submit all Subgrade lift QA before proceeding with next pavement layer
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - Conqa Siggnoff
label | Testing Quantity Required (based from schedule qtys) - Once
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.6 - Subgrade Fill - CBR Testing
label | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ Testing of the Subgrade where no Structural Fill has been placed, Scala's to be carried out. This test shall be undertaken on the cut surface to a depth of not less than 1m
label | Acceptance / Conformance Criteria - Min 4 blows / 100mm
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Scala Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.7 - Subgrade Fill- CBR Testing
label | Detail - "NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test
label | ○ This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level
label | ○ Hand auger hole is required
label | Acceptance / Conformance Criteria - Average minimum Su > 125kpa
label | ○ Single test minimum Su > 100kPa
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Shear Vane Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 test) per 100m3 of fill placed per area worked per day per lift
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.8 - Subgrade Fill - Bulk desnity, Dry density, Air voids
label | Detail - NZS4402:1986 - Test 5.1.3 sampling tube method for determination of the in-situ density
label | Acceptance / Conformance Criteria - Results from test
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test performed for every 10 NDM
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.9 - Subgrade Fill - Water content
label | Detail - NZS4402:1986 - Test 2.1 water content
label | Acceptance / Conformance Criteria - Results from test
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 test) per 200m3 of fill placed per area worked per day per lift
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.10 - Subgrade Fill - Insitu density insitu compacted dry density insitu water content
label | Detail - NZS4407:2015 – test 4.3 nuclear moisture density gauge (ndm), direct transmission mode
label | Acceptance / Conformance Criteria - Average maximum air voids < 7%
label | ○ Single test maximum air voids < 6%
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 1 Set (5 Test) per200m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.11 - Subgrade Fill (Pumice sand) - Compaction
label | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ Testing of the Subgrade where no Structural Fill has been placed, Scala's to be carried out. This test shall be undertaken on the cut surface to a depth of not less than 1m
label | Acceptance / Conformance Criteria - Scala blows >5
label | Standard / Specification - PS16.5.12
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.12 - Subgrade Fill (Pumice sand) - Bulk density, Dry density, Air voids
label | Detail - NZS4402:1986 - Test 5.1.3 sampling tube method for determination of the in-situ density
label | Acceptance / Conformance Criteria - Average 95% MDD, min >92%
label | Standard / Specification - PS16.5.13
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test performed for every 10 NDM
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.13 - HOLD POINT- QA Submission
label | Detail - Submit all Subgrade lift QA before proceeding with next fill layer
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - Conqa Siggnoff
label | Testing Quantity Required (based from schedule qtys) - Once
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.14 - GEOTEXTILE FABRIC - Placement of Geotextile Fabric
label | Detail - Place Geotextile Fabric Strength Class D across pavement area, with 500mm overlaps
label | Acceptance / Conformance Criteria - Visual inspection
label | Standard / Specification - 232735.02-WSP-DR-STW 0302
label | Verifying Document - Visual Inspection and photos
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - WP
label | Verification Activity: By - ENG
checkpoint | 4.15 - SUBBASE (TCC AP65-2) - 3m Straight Edge
label | Detail - Formation check to ensure surface is smooth
label | Acceptance / Conformance Criteria - +/- 15mm
label | Standard / Specification - PS 27.4.1
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - Every 20m Centres
label | ○ 1 each lane
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.16 - SUBBASE (TCC AP65-2) - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface
label | Acceptance / Conformance Criteria - String lines - or equivalent are 150mm +5mm/-25mm
label | Standard / Specification - TNZ B/02:2005 5.1 232735.02-WSP-DR-STW 0303
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.17 - SUBBASE (TCC AP65-2) - Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >95% of MDD
label | ○ Min >92% of MDD
label | Standard / Specification - TNZ B/02:2005 7.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) 1000m2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.18 - HOLD POINT - QA Submission
label | Detail - Submit all Subbase QA before proceeding with next pavement layer
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - All test reports
label | ○ Material Test Results
label | ○ Laboratory MDD
label | ○ NDM results
label | Testing Quantity Required (based from schedule qtys) - Once
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 5 - CONSTRUCTION - EARTHWORKS
checkpoint | 5.1 - Subgrade Level Confirmation
label | Detail - Confirm subgrade is min 500mm below excisting ground level.
label | Acceptance / Conformance Criteria - String lines - or equivalent are 300mm +0mm/-30mm
label | ○ Tolerances width -20mm +100mm
label | Standard / Specification - PS 21.5.15 e)
label | Verifying Document - Survey as-builts
label | Testing Quantity Required (based from schedule qtys) - Every 20m chainage on all major contours
label | Verification Activity: Activity - I
label | Verification Activity: By - SV
checkpoint | 5.2 - Subgrade CBR Testing
label | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ Testing of the Subgrade where no Structural Fill has been placed, Scala's to be carried out. This test shall be undertaken on the cut surface to a depth of not less than 1m
label | Acceptance / Conformance Criteria - CBR >7
label | ○ Min 3 blows / 100mm
label | Standard / Specification - PS 27.4.2 Appendix XVIII
label | Verifying Document - Scala Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.3 - Subgrade CBR Testing
label | Detail - NZ Geotechnical Society 2001 - Guideline for Hand Held Shear Vane Test
label | ○ This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level
label | ○ Hand auger hole is required
label | Acceptance / Conformance Criteria - Average Minimum SU:
label | ○ > 60kPa
label | Single Test Min SU:
label | ○ >50kPa
label | ○ 2-3m deep
label | Standard / Specification - PS 27.4.2 Appendix XVIII
label | Verifying Document - Shear Vane Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.4 - Subgrade Proof Roll
label | Detail - Visual Inspection of Proof Roll
label | Acceptance / Conformance Criteria - Displacement <15mm
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Visual Observation
label | Testing Quantity Required (based from schedule qtys) - Across stripped area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.5 - FILLING A2 COHESIVE MATERIAL - Subgrade CBR Testing
label | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ Testing of the Subgrade where no Structural Fill has been placed, Scala's to be carried out. This test shall be undertaken on the cut surface to a depth of not less than 1m
label | Acceptance / Conformance Criteria - Min 2 blows / 100mm
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Scala Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.6 - FILLING A2 COHESIVE MATERIAL - Subgrade CBR Testing
label | Detail - NZ Geotechnical Society 2001 - Guideline for Hand Held Shear Vane Test
label | ○ This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level
label | ○ Hand auger hole is required
label | Acceptance / Conformance Criteria - Average minimum Su > 80kPa
label | ○ Single test minimum Su > 60kPa
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Shear Vane Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 test) per 500m3 of fill placed per area worked per day per lift
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.7 - FILLING A2 COHESIVE MATERIAL - Compaction - Clegg Hammer
label | Detail - ASTM D5874-16:2016 Clegg Hammer Testing
label | Acceptance / Conformance Criteria - Non-Structural Fill
label | ○ Min CIV 10
label | ○ Max CIV 12
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Clegg Hammer Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.8 - FILLING A2 COHESIVE MATERIAL - Bulk density, Dry density, Air voids
label | Detail - NZS4402:1986 - Test 5.1.3 sampling tube method for determination of the in-situ density
label | Acceptance / Conformance Criteria - Results from test
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test performed for every 10 NDM
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.9 - FILLING A2 COHESIVE MATERIAL - Water content
label | Detail - NZS4402:1986 - Test 2.1 water content
label | Acceptance / Conformance Criteria - Results from test
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 test) per 200m3 of fill placed per area worked per day per lift
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.10 - FILLING A2 COHESIVE MATERIAL - Insitu density insitu compacted dry density insitu water content
label | Detail - NZS4407:2015 – test 4.3 nuclear moisture density gauge (ndm), direct transmission mode
label | Acceptance / Conformance Criteria - Average maximum air voids < 8%
label | ○ Single test maximum air voids < 10%
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 1 Set (5 Test) per200m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.11 - FILLING A2 COHESIVE MATERIAL - Final Level Confirmation
label | Detail - Confirm subgrade is min 300mm below final level for topsoil
label | Acceptance / Conformance Criteria - String lines - or equivalent are 300mm +0mm/-30mm
label | ○ Tolerances width -20mm +100mm
label | Standard / Specification - PS 21.5.15 e)
label | Verifying Document - Survey as-builts
label | Testing Quantity Required (based from schedule qtys) - Every 20m chainage on all major contours
label | Verification Activity: Activity - I
label | Verification Activity: By - SV
checkpoint | 5.12 - SUBGRADE FILL (Pumice sand) - Compaction
label | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ Testing of the Subgrade where no Structural Fill has been placed, Scala's to be carried out. This test shall be undertaken on the cut surface to a depth of not less than 1m
label | Acceptance / Conformance Criteria - Scala blows >5
label | Standard / Specification - PS16.5.12
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.13 - SUBGRADE FILL (Pumice sand) - Bulk density, Dry density, Air voids
label | Detail - NZS4402:1986 - Test 5.1.3 sampling tube method for determination of the in-situ density
label | Acceptance / Conformance Criteria - Average 95% MDD, min >92%
label | Standard / Specification - PS16.5.12
label | Verifying Document - Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test performed for every 10 NDM
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.14 - HOLD POINT - QA Submission
label | Detail - Submit all Subgrade QA before proceeding with next pavement layer
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - Conqa Siggnoff
label | Testing Quantity Required (based from schedule qtys) - Once
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 6 – AS-BUILTS
checkpoint | 6.1 - As-Builts
label | Detail - As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets.
label | Acceptance / Conformance Criteria -
label | Standard / Specification - PS 16.7.6
label | Verifying Document - Survey Records/ Redpen markups
label | Testing Quantity Required (based from schedule qtys) - Post Earthworks
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1210-018 ITP Gas Protection Structure | itp |  |  |  |  | DN1210-018 ITP Gas Protection Structure Rev 0
section | SECTION 3 – PRE-CONSTRUCTION - MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 3.1 - Reinforcing steel and Strands
label | Detail - All Reinforcement bars and strands used in structural concrete to be approved by the engineer prior to construction.
label | ○ Post tensioning strand to be high tension ASTM galvanized and complying with AS/NZ standard
label | Acceptance / Conformance Criteria - Test certificates shall be obtained from the manufacturer for all strand, cable and bar to be used in the work and copies shall be forwarded to the Engineer at least one week before the programmed commencement of any work incorporating these materials. Test certificates shall be traceable to the batch of material supplied to the work.
label | ○ High yield steel, Grade 500E, Seismic MA.
label | Standard / Specification - PS 18.3.3, 18.5.7 and 19.13.1
label | Verifying Document - Supplier data sheet/ Mill certs
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Concrete mix design
label | Detail - Approved mix design - Concrete shall be of the class as defined by NZS 3104 have a minimum 28 days compression strength as specified for various members: for Gas Main protection structure in-situ pour: 40mpa
label | Acceptance / Conformance Criteria - 28 Day concrete requirements:
label | ○ In Situ Footing and stitch pour for Gas Main Protection structure: 40MPA
label | ○ Screw Pile Shaft filled with 40Mpa Concrete
label | Standard / Specification - PS 19.3.3
label | Verifying Document - Approved Mix design
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Shop Drawing Approval
label | Detail - Shop drawing review and approval from Engineer and Production QA Records to be submitted
label | Acceptance / Conformance Criteria - Send shop drawings to the Engineer for review, at least 14 days prior to manufacture of any pre cast members. Any variations between the Drawings and shop drawings shall be clearly identified and brought to the attention of the Engineer.
label | Standard / Specification - PS 19.12.6
label | Verifying Document - Shop Drawing Approval, QA records
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Joint Sealing and Waterproofing Sealant
label | Detail - Pre approved joint sealant meeting the specification requirements
label | Acceptance / Conformance Criteria - Joints are to be sealed using a fuel resistant, multi-component polysulphide sealant designed for horizontal and vertical joints in concrete and is joint sealant pourable or gunning grade as appropriate.
label | Standard / Specification - PS 19.12.6
label | Verifying Document - Delivery dockets and supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to construction - Engineers approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - Screw Piles
label | Detail - The Length of the Screw Pile delivered to the site will be long enough for both, Type 1 pile (dia 168mm, 6.4mm thick) and Type 2 pile (dia 273mm, 12.7mm thick). Need to be 11.95m long with Helix as indicated on Spiral Drillers shop drawing of the pile. Helix to be 450mm dia 15mm thick for Type 1 pile and 750mm dia, 25mm thick for Type 2 pile. The External Bearing Ring for Type 1 pile should be 250mm and 41mm thick. For Type 2 pile 350mm and 39mm thick
label | Acceptance / Conformance Criteria - Site Inspection
label | Standard / Specification - Spiral Drillers Pile Details, Drawing No. 1
label | Verifying Document - Delivery dockets and Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Compressible filler board
label | Detail - Compressible filler board specification to meet the project requirements.
label | Acceptance / Conformance Criteria - Details of the compressible filler board proposed to be used as a construction joint shall meet specification requirements.
label | Standard / Specification - PS 19.12.6
label | Verifying Document - Delivery dockets and supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 4 – CONSTRUCTION - EARTHWORKS SUBGRADE
checkpoint | 4.1.1 - Cut Subgrade Inspection
label | Detail - Engineer to inspect all foundation surface inspections
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - Visual Observation
label | Testing Quantity Required (based from schedule qtys) - Across stripped area
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 5 – CONSTRUCTION ACTIVITIES - SCREW PILING, INSITU POUR, PRE-CAST CONCRETE
checkpoint | 5.1.1 - Survey Set out
label | Detail - Pile heads must be within +-75mm of the specified plan location. Pile heads must be within +-20mm of the vertical level indicated on the drawings
label | Acceptance / Conformance Criteria - The verified data is within tolerance as specified
label | Standard / Specification - AoS Design Report
label | Verifying Document - Survey data
label | Testing Quantity Required (based from schedule qtys) - Post construction
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | 5.1.2 - Installation Torque
label | Detail - The minimum pile founding depth for all helices shall be 9.5m below existing ground level AND Target Installation Torque 168mm dia shaft= 15000NM Target Installation Torque 273mm dia shaft=45000Nm Note: Max allowable Torque 168mm dia shaft=70000Nm Max Allowable Torque 273mm dia shaft=120000Nm-However on-site digger will allow Maximum Torque of 90000Nm
label | Acceptance / Conformance Criteria - Site Inspection
label | Standard / Specification - Spiral Drillers Pile Details, Drawing No. 1 and AoS design Report
label | Verifying Document - Site Inspection
label | Testing Quantity Required (based from schedule qtys) - 2 Site Visits
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.1.3 - Concrete Infill
label | Detail - Pile Shaft to be filled with 40Mpa Concrete
label | Acceptance / Conformance Criteria - Pile Shaft to be filled with 40Mpa Concrete
label | Standard / Specification - AoS Design Report
label | Verifying Document - Concrete Delivery Docket
label | Testing Quantity Required (based from schedule qtys) - Post Construction
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 5.1.4 - Top Plate Install
label | Detail - The bearing plate will be lowered over the top of the screw pile to its design height (200mm from base of abutment/wingwall cap). Once at height it will be tack welded in position. Bearing plate and stiffening ring to then be welded using a partial penetration butt weld.
label | Acceptance / Conformance Criteria - Site Inspection
label | Standard / Specification - AoS Design Report
label | Verifying Document - Site Inspection
label | Testing Quantity Required (based from schedule qtys) - Post construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2.1 - Pre Pour Inspection
label | Detail - Pre Pour inspection to check:
label | — Reinforcing
label | — Moulds
label | — Cover Spacer Blocks
label | Acceptance / Conformance Criteria - The Engineer shall be informed 8 hours prior to the casting of any unit, to allow the Engineer to attend the pre-casting plant to inspect before and during production of the units.
label | ○ Reinforcing shall be pre assembled wherever possible into rigid cages using a template or jig. Reinforcing shall be tied together with wire unless otherwise accepted by the Engineer
label | ○ Confirm correct type and location of cover block is used.
label | Standard / Specification - PS 19.3.2, 19.4.3 & 19.12.3
label | Verifying Document - Pre pour inspection checklist, Manufacturer QA records
label | Testing Quantity Required (based from schedule qtys) - Engineers Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2.2 - Concrete sampling and testing
label | Detail - Pre cast Methodology from Pre co to submit to Engineer and Compression Test Report
label | Acceptance / Conformance Criteria - For pours under 150m³: three standard cylinders shall be made for each 50m³ of concrete placed, or part thereof, for testing of 28 days compressive strength in an approved laboratory.
label | Standard / Specification - PS 19.4.3
label | Verifying Document - Slump Test/ Compressive strength test Report at 28 days/Pre pour inspection checklist
label | Testing Quantity Required (based from schedule qtys) - Engineers Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2.3 - Post Pour inspections
label | Detail - Post Pour inspection
label | Acceptance / Conformance Criteria - Following the concrete pour and stripping out form works: the concrete shall be inspected for Size, Shape, Features, inserts, reliefs, and Finish against the drawings.
label | Standard / Specification - PS 19.3.1
label | Verifying Document - Visual Inspection / Post pour checklist
label | Testing Quantity Required (based from schedule qtys) - Each Pour
label | Verification Activity: Activity - I
label | Verification Activity: By - ENG
checkpoint | 5.3.1 - Forms and Moulds
label | Detail - Tolerance on the placement of internal forms and moulds shall be +-5mm
label | Acceptance / Conformance Criteria - Moulds shall be rigid accurately formed and of sufficient strength and stiffness to prevent distortion under vibration.
label | Standard / Specification - PS 19.12.5
label | Verifying Document - Manufacturer QA records
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.3.2 - Pre Pour Inspection
label | Detail - Pre Pour inspection to check:
label | — Reinforcing
label | — Moulds
label | — Cover Spacer Blocks
label | Acceptance / Conformance Criteria - The Engineer shall be informed 8 hours prior to the casting of any unit, to allow the Engineer to attend the pre-casting plant to inspect before and during production of the units. Pre pour inspection for 1st pour, there after every 3rd pour
label | ○ Reinforcing shall be pre assembled wherever possible into rigid cages using a template or jig. Reinforcing shall be tied together with wire unless otherwise accepted by the Engineer
label | ○ Confirm correct type and location of cover block is used.
label | Standard / Specification - PS 19.3.2, 19.4.3 & 19.12.3
label | Verifying Document - Pre pour inspection checklist, Manufacturer QA records
label | Testing Quantity Required (based from schedule qtys) - Engineers Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3.3 - Concrete sampling and testing
label | Detail - Pre cast Methodology from Pre co to submit to Engineer and Compression Test Report
label | Acceptance / Conformance Criteria - For pours under 150m³: three standard cylinders shall be made for each 50m³ of concrete placed, or part thereof, for testing of 28 days compressive strength in an approved laboratory.
label | ○ For repetitive precast underpass units with 6.42m3 each pours undertaken on a regular basis, three standard cylinders shall be made for each of the first five pours of any one type, and thereafter three standard cylinders shall be made for every fifth pour of that type for testing of 28 days compressive strength in an approved laboratory.
label | Standard / Specification - PS 19.4.3
label | Verifying Document - Slump Test/ Compressive strength test Report at 28 days/Pre pour inspection checklist
label | Testing Quantity Required (based from schedule qtys) - Engineers Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3.4 - Post Pour inspections
label | Detail - Post Pour inspection
label | Acceptance / Conformance Criteria - Following the concrete pour and stripping out form works: the concrete shall be inspected for Size, Shape, Features, inserts, reliefs, and Finish against the drawings.
label | Standard / Specification - PS 19.3.1
label | Verifying Document - Visual Inspection/ Post pour checklist
label | Testing Quantity Required (based from schedule qtys) - Each Pour
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3.5 - Joint Sealing of Pre cast members
label | Detail - Joint sealing of pre cast members
label | Acceptance / Conformance Criteria - Joints are to be sealed using a fuel resistant, multi-component polysulphide sealant designed for horizontal and vertical joints in concrete and is joint sealant pourable or gunning grade as appropriate.
label | Standard / Specification - PS 19.12.6
label | Verifying Document - Post installation inspection check list
label | Testing Quantity Required (based from schedule qtys) - After placing pre-cast units
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 6 - BACKFILLING WITH IMORTED STRUCTURAL FILL MATERIAL
checkpoint | 6.1 - Backfilling of Gas main protection structure with imported hard fill
label | Detail - The backfilling on top of gas main protection structure to meet the earthwork specification and testing requirements. Compaction-Clegg Hammer
label | Acceptance / Conformance Criteria - Structural Fill
label | — Min CIV 18
label | — Ave CIV 20
label | ○ Non-Structural Fill
label | — Min CIV 10
label | — Max CIV 12
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Clegg Hammer Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.2 - Backfilling of Gas main protection structure with imported hard fill materials
label | Detail - The backfilling on top of gas main protection structure to meet the earthwork specification and testing requirements. Compaction-NDM
label | Acceptance / Conformance Criteria - Ave >95% of MDD
label | — Min >92% of MDD
label | ○ Non Granular Material
label | — Max Air Voids 8%
label | Standard / Specification - Appendix XVIII
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) per 400mm lift (every 2nd lift) of fill per 1000m2 of placed
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 7 - AS-BUILTS/ REDPEN MARKUPS
checkpoint | 7.1 - As-Builts/ Red pen markup
label | Detail - As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets.
label | Acceptance / Conformance Criteria - As built drawing red pen markups
label | Standard / Specification - PS 16.7.6
label | Verifying Document - Red pen markups
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - D
label | Verification Activity: By - SE
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature