## Example Checklist
Type | Name | Values
checklist | Exterior Cladding + Soffit Lining Works
checkpoint | Preclad / Flexible Wall Underlay & Rigid Air Barrier Complete
checkpoint | Window Head & Jamb Flashings Installed
checkpoint | Soffit Head Flashing Installed
checkpoint | Cavity Battens installed
checkpoint | First Fix Services to Soffits Installed?
button | · Comms | YES, NO, N/A
button | · Electrical | YES, NO, N/A
button | · Security cables | YES, NO, N/A
button | · Fire systems | YES, NO, N/A
button | · Plumbing | YES, NO, N/A
button | · HVAC | YES, NO, N/A
checkpoint | Approval to line soffits
checkpoint | Soffit Holes filled and sheets stopped
checkpoint | Soffit Painted
checkpoint | Soffit Vents installed
checkpoint | External & Internal Corner Flashings installed
checkpoint | Cladding Installed
checkpoint | Cladding Painted
checkpoint | Any additional photos, comments and observations
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Raise Remedial / Request trades QA / Sign Off
signoff | Click here to Raise Remedial / Request trades QA / Sign Off

## Durastruct Templates
Type | Name | Values
Checklist | Spalling Repairs
Checkpoint | Site analysis and clear scope of work defined
Checkpoint | Health and safety documentation completed
Checkpoint | Initial site photos
Checkpoint | Correct access system being used
Checkpoint | Site preparation
Tickbox | Removal of all loose concrete and Debris
Tickbox | Square cut edges with sufficient concrete depth allowed for
Tickbox | Reinforcing steel exposed with surrounding 30mm gap
Tickbox | Reinforcing steel has been primed
Checkpoint | Correct products and mixing procedures followed as per supplier specifications
Checkpoint | Reinstatement of concrete repair completed
checkpoint | Required concrete cover achieved
checkpoint | Repair structurally sound and effective adhesion
Checkpoint | Trowelled to smooth finish
Checkpoint | Correct PPE used as per H+S Documentation
Checkpoint | Site cleanup
Tickbox | Tools cleaned up from concrete
Tickbox | Excess materials disposed of correctly
Checkpoint | Project completion photos
Signoff | Scope of works completed
Checklist | Gunite Spraying
Checkpoint | Site analysis and clear scope of work defined
Checkpoint | Health and safety documentation completed
Checkpoint | Initial site photos
Checkpoint | Site preparation
Tickbox | Hoses Secured and trip hazards removed
Tickbox | Concrete Sprayer and compressor setup in a suitable location
Tickbox | All machinery in effective operating condition (serviced and greased)
tickbox | Correct compressor being used (at least 300cfm)
Tickbox | Compressor safety measures in place (e.g. whipstops)
tickbox | Correct water source and pressure obtained
Tickbox | Product in suitable location for ease of access
Tickbox | Overspray containment in place where required
Checkpoint | Correct water - product ratio settings being used upon application
Checkpoint | Correct application techinque used including circular motion and 1-2m distancing
Checkpoint | Gunite application to all specified areas
Checkpoint | Reinforcing steel covered with at least 50mm of concrete
Checkpoint | Correct PPE used as per H+S Documentation
Checkpoint | Project completion photos
Signoff | Scope of works completed
Checklist | Waterproofing Membrane Application
Checkpoint | Site analysis and clear scope of work defined
Checkpoint | Health and safety documentation completed
Checkpoint | Initial site photos
Checkpoint | Correct access system being used
Checkpoint | Site preparation
Tickbox | Pressure wash the area
Tickbox | Remove any spalling or concrete debris
Tickbox | Drop sheets installed
checkpoint | Seal any cracks or imperfections
Checkpoint | Proper product mixing procedures followed as per manufacturers instructions
checkpoint | Apply the waterproof membrane ensuring all areas are covered and 2x coats completed
checkpoint | Allow for correct drying times as per specifications
checkpoint | Site cleanup
tickbox | Tools cleaned out
tickbox | Waste materials disposed of correctly
Checkpoint | Project completion photos
Signoff | Scope of works completed
Checklist | Crack Injection
Checkpoint | Site analysis and clear scope of work defined
Checkpoint | Health and safety documentation completed
Checkpoint | Initial site photos
Checkpoint | Correct access system being used
Checkpoint | Site preparation complete
Checkpoint | Crack chasing complete
Tickbox | Required depth obtained
Tickbox | Cracks cleaned out and dust removed
Checkpoint | Seismic adhesive and nipples installed
Tickbox | Injection nipples installed to correct spatial distances
Tickbox | Adhesive is smoothed off to ensure resin containment
Checkpoint | Resin injected
Tickbox | Resin injected from the bottom ports first
Tickbox | Sufficient resin injection in each Port
Checkpoint | Completion
Tickbox | Resin is cured before removal of Injection ports
Tickbox | Injection ports removed
Checkpoint | Correct PPE used as per H+S Documentation
checkpoint | Site cleanup complete
Checkpoint | Excess materials disposed of correctly
Checkpoint | Project completion photos
Checkpoint | Signoff
Signoff | Scope of works completed
Checklist | Aquron Application
Note | Client Details
Note | Site Address
Note | Date
Note | Description of areas treated
Checkpoint | Before photos of areas treated
Checkpoint | After Photos of areas treated
Note | Square metres covered
Note | Litres used per area
Note | Spread Rate
Note | Number of Passes
Note | Pail batch numbers recorded
Checkpoint | Correct application technique and equipment used
Signoff | Sign here for sign off
Checklist | Joint/Crack Sealing
Note | Client Details
Note | Site Address
Note | Scope of works completed
Checkpoint | Health and safety documentation completed
Checkpoint | Initial site photos
Checkpoint | Crack chasing and cleaning complete
Tickbox | Cracks chased to sufficient depth
Tickbox | Cracks cleaned, brushed and blown out to remove debris
Checkpoint | Bond breaker installed where required
Checkpoint | Sealant installation
Tickbox | Joints mask taped
Tickbox | Product smoothed off and radius below ground level
Tickbox | Product installed as per supplier specifications
Checkpoint | Site cleanup and rubbish removal
Checkpoint | Completion Photos
Signoff | Job Signoff

## User Guide (PLEASE READ)
Type | Name | Values
checklist | This is where you type the name/title of your checklist
section | Section A - This is a section which helps you split your checklist
checkpoint | This is a checkpoint (all checkpoints have the options to PASS, FAIL, N/A by default)
checkpoint | This is a checkpoint with a dropdown (you can select only one option)
dropdown | Select: | Option 1, Option 2, Option 3
checkpoint | This is a checkpoint with a textbox
textbox | Description:
checkpoint | This is a checkpoint with buttons (you can select only one option)
button | Select: | Option 1, Option 2, Option 3
section | Section B - This is a section which helps you split your checklist
checkpoint | This is a checkpoint with a note
note | This is a note
checkpoint | This is a checkpoint with tickboxes (you can select more than one option)
tickbox | White
tickbox | Grey
tickbox | Black
checkpoint | This is a checkpoint with a signoff (you can send it to anyone within or outside of CONQA)
signoff | SIGN HERE OR REQUEST SIGNOFF
NOTE: You can customise ALL wordings under the 'Name' column and the options in the 'Values' column.