## Table 1
Inspection & Test Plan
Project Name : | 1747 NZ Safety Blackwoods |  | Lot Number : | n/a | Lot Code : | n/a | n/a | Date Issued : | 2025-03-25
Description : | HD Detention Tank |  | Location : | Eastern Boundary of Site |  |  |  | Rev : | A
Lot Code | Description |  |  |  | Spec Reference Special Conditions | Acceptance Criteria | Verifying Document | Verification / Witness - To Print and Sign |  |  |  | Date
[8 empty] | Contractor |  | Client's Rep.
[8 empty] | Print | Sign | Print | Sign
SW 1.0 | Agreements Prior to Install
1.1 | Agree on materials to be used prior to install, GAP 20 and A19 Bidim |  |  |  | N/A | CI | Email Confirmation
1.2 | Confirm Drawings and any additional instructions |  |  |  | N/A | CI | Correspondence and Procore Drawings
SW2.0 | Detention Tank Excavation
2.1 | Subgrade Testing of Detention Tank |  |  |  | C410 Rev 6 | CI | Photos and Testing
2.2 | Gap 20 Testing of Detention Tank beneath Tank |  |  |  | C410 Rev 6 | CI | Photos and Testing
2.3 | Laying A19 Bidim |  |  |  | C410 Rev 6 | CI | Photos and Testing
SW 3.0 | Detention Tank Install
3.1 | Tank Installation |  |  |  | N/A | CI | Photos
3.2 | Tank Connections |  |  |  | N/A | CI | Photos
SW 4.0 | Detention Tank Backfill
4.1 | Backfill on Sides of Tank |  |  |  | N/A | CI | Photos with Clegg Results
4.2 | Backfill on top tank with GAP 20 |  |  |  | N/A | CI | Photos with Clegg Results inlieu of Nucs
4.3 | Backfill on top tank with DQ65 to Subgrade |  |  |  | N/A | CI | Photos with Clegg Results
SW 5.0 | Signoffs
4.1 | Auckland Council Inspection |  |  |  | N/A | CI | Council inspection report
4.2 | ACO Sign off |  |  |  |  | CI | Email Confirmation or formal document
4.3 | Contractor PS3 |  |  |  | = | CI | Producer Statement 3
4.4 | Handover to client |  |  |  | = | CI | Handover documents
Rev. Status | Date | Reason for Rev. |  |  | HP - MANDATORY HOLD POINT |  |  | Signed by: |  | Engineer (Contractor) Engineer Rep (Principal)
A | 2025-03-25 | Issued for Construction |  |  | WP - WITNESS POINT |  |  | Signed by: |  | Engineer (Contractor) Engineer Rep (Principal)
[5 empty] | CI - CHECK ITEM |  |  | Signed by: |  | Leading Hand, Foreman Engineer (Contractor)
Comments / Required Actions :
Contractors Representative Clients Representative Signature: Signature: Print: Print: Date: Date: Revision 3