## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - HD Detention Tank | itp |  |  |  |  | ITP - HD Detention Tank
section | SW 1.0 - Agreements Prior to Install
checkpoint | 1.1 - Agree on materials to be used prior to install, GAP 20 and A19 Bidim
label | Spec Reference Special Conditions - N/A
label | Acceptance Criteria - CI
label | Verifying Document - Email Confirmation
checkpoint | 1.2 - Confirm Drawings and any additional instructions
label | Spec Reference Special Conditions - N/A
label | Acceptance Criteria - CI
label | Verifying Document - Correspondence and Procore Drawings
section | SW 2.0 - Detention Tank Excavation
checkpoint | 2.1 - Subgrade Testing of Detention Tank
label | Spec Reference Special Conditions - C410 Rev 6
label | Acceptance Criteria - CI
label | Verifying Document - Photos and Testing
checkpoint | 2.2 - Gap 20 Testing of Detention Tank beneath Tank
label | Spec Reference Special Conditions - C410 Rev 6
label | Acceptance Criteria - CI
label | Verifying Document - Photos and Testing
checkpoint | 2.3 - Laying A19 Bidim
label | Spec Reference Special Conditions - C410 Rev 6
label | Acceptance Criteria - CI
label | Verifying Document - Photos and Testing
section | SW 3.0 - Detention Tank Install
checkpoint | 3.1 - Tank Installation
label | Spec Reference Special Conditions - N/A
label | Acceptance Criteria - CI
label | Verifying Document - Photos
checkpoint | 3.2 - Tank Connections
label | Spec Reference Special Conditions - N/A
label | Acceptance Criteria - CI
label | Verifying Document - Photos
section | SW 4.0 - Detention Tank Backfill
checkpoint | 4.1 - Backfill on Sides of Tank
label | Spec Reference Special Conditions - N/A
label | Acceptance Criteria - CI
label | Verifying Document - Photos with Clegg Results
checkpoint | 4.2 - Backfill on top tank with GAP 20
label | Spec Reference Special Conditions - N/A
label | Acceptance Criteria - CI
label | Verifying Document - Photos with Clegg Results inlieu of Nucs
checkpoint | 4.3 - Backfill on top tank with DQ65 to Subgrade
label | Spec Reference Special Conditions - N/A
label | Acceptance Criteria - CI
label | Verifying Document - Photos with Clegg Results
section | SW 5.0 - Signoffs
checkpoint | 5.1 - Auckland Council Inspection
label | Spec Reference Special Conditions - N/A
label | Acceptance Criteria - CI
label | Verifying Document - Council inspection report
checkpoint | 5.2 - ACO Sign off
label | Acceptance Criteria - CI
label | Verifying Document - Email Confirmation or formal document
checkpoint | 5.3 - Contractor PS3
label | Acceptance Criteria - CI
label | Verifying Document - Producer Statement 3
checkpoint | 5.4 - Handover to client
label | Acceptance Criteria - CI
label | Verifying Document - Handover documents
checkpoint | Comments / Required Actions:
textbox | Rev. Status
date | Date
textbox | Reason for Rev.
checkpoint | Signed by:
note | Contractors Representative
textbox | Print:
date | Date:
note | Clients Representative
textbox | Print:
date | Date:
signoff | Signatures: