## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-159-CIV-PSDS-Line marking
ITP Description: |  | PSDS-Line marking
Discipline (e.g. CIV/STR/RAIL: |  | 159-CIV
Revision Number: |  | 0
Revision Date: |  | 2023-10-13
ITP created by:
ITP approved for use by: |  | Victor Mira
Special Notes to ConQA Team : |  | ITP for Progress Street
Inspection & Test Plan - Line Marking
|  |  | Document No.: | [5 empty] | Revision: | 0
[9 empty] | Date: | 2023-10-13
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | Vicroads Section 721February 2017 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | Vicroads Section 175November 2019 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Non Dependent | Vicroads Section 853 February 1994 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.2 | Type of marking material as shown on design drawings and shall conform to the Standard | Vicroads 721.A05 | Type as per relevant design drawings, obtain Conformance Certificates and test reports from supplier Provide the principle a list of materials that to be used with a certificate of conformance with associated test report | Document Review | Once | IP | SE/PE/SPE | Material certificate
2.3 | Raised Pavement Markers | Vicroads 721.A05 | Raised pavement markers shall comply with the relevant requirements of AS 1906, Part 3 as listed in Section 175. (ii) Temporary raised reflective pavement markers shall comply with the relevant requirements of AS 1906 as listed in Section 175, and shall be at least 100 mm in width and to a height of 50 mm with white reflective material on both sides and include protective covers for the reflective material | Document Review | Per Material | IP | SE/PE/SPE | Material certificate
2.4 | Adhesive | Vicroads 721.A05 | Hot melt bitumen adhesive shall comply with Section 853 - Hot Melt Bitumen Adhesive for Raised Pavement Marker Installation. Other types of adhesive materials shall only be used with the approval of the Superintendent | Document Review | Per Material | IP | SE/PE/SPE | Material certificate
2.5 | Line marking and Road marking Paint | Vicroads 721.A05 | All paints shall be approved under the Australian Paint Approval Scheme (APAS). Paint shall comply with the requirements of AS 4049.1 for solvent-borne paint or AS/NZS 4049.3 for water-borne paint as listed in Section 175. | Document Review | Per Material | IP | SE/PE/SPE | Material certificate
2.6 | Glass beads | Vicroads 721.A05 | Glass beads shall be used on all applications of material and for all pavement markings and shall conform to the requirements in AS/NZS 2009 and the Australian Paint Approval Scheme (APAS) Specification 0042. | Document Review | Per Material | IP | SE/PE/SPE | Material certificate
2.6 | Pristine glass beads (Type B-HR) | Vicroads 721.A05 | Glass beads shall be used on all applications of material and for all pavement markings and shall conform to the requirements in AS/NZS 2009 and the Australian Paint Approval Scheme (APAS) Specification 0042. Pristine glass beads (Type B-HR) Type B-HR glass beads shall comply with the properties of Type B (AS 2009:2006) drop-on glass beads, with an additional high performance retro reflectivity requirement, requiring the delivery of a minimum 450 mcd/lux.m², when tested in accordance with a modified Appendix M | Document Review | Per Material | IP | SE/PE/SPE | Material certificate
3 | Preliminaries - Procedures & Documentation
2.1 | Accreditation to Painting Contractors Certification Program | Vicroads 721.D01 | Provide evidence that the work is being undertaken by a contractor eligible for accreditation under painting Certification Program(PCCP). This Programme is administered by the CSIRO. Enter: Teambinder Approval number [free text box] | Document Review | Once | HP | Nominated Authority | ConQA Hold Point Release PCCP Accreditation
4 | Pre-construction Activities
3.1 | Surface preparation | Vicroads 721.A06 Vicroads 721.A09 | The area to be marked is dry free of dirt, gravel, flaking and other loose foreign material The area around making area is also clean to avoid tracking into the marking area Removal of existing unsound, obsolete or redundant pavement markings Removal of any foreign materials and debris within reasonable limits. | Measure, Visual, Document Review | Per Lot | IP | SE/PE/SPE | This ITP
3.3 | Redundant pavement / unsuitable marking markers removal | Vicroads 721.A12 Vicroads 721.A06 Vicroads 721.A08 | Where removal of existing pavement marking/unsuitable pavement marking to the standard is required, the method of removal shall be subject to the approval of the Superintendent before removal works commence. | Visual /Site Inspection & Document Review | Per Lot | HP* | Nominated Authority | ConQA Hold Point Release
3.2 | Set out the works for installation of pavement markings / raised markers | Vicroads 721.B05 | Painting/application of material shall not commence until the Superintendent has inspected the set out and given consent to proceed, unless a written exemption has been granted by the Superintendent | Survey Document Review | Per Lot | HP | Nominated Authority | ConQA Hold Point Release
5 | Construction Activities
3.4 | Application of pavement marking / markers | Vicroads 721 | Check conditions for application of marking paint & materials. (i) Paints and markers installed as per manufacturer’s recommendations. (ii) The same materials used with those nominated in the certifications. (ii) All longitudinal lines have been applied by the nominated machine unless approved by superintendent (iv) Verify markings are straight or with smooth, even curves where intended. (v) Edges are clean sharp cut off. (vi) Markings uniform in appearance, texture, width & thickness & free from unbeaded areas (vii) Waterorne Paint & Glass Beads application rate conform to the requirements of Vic road 721.E01 requirements. (viii) Markings are neat & free from traffic damage or other defects (ix) Marking protected from traffic until hardened | Visual /Site Inspection & Document Review | Per Lot | IP | SE/PE/SPE | This ITP
3.5 | Tolerances for new marking/marker installations | Vicroads 721.A10 Table 721.A101 | Pavement marking : Distance between the centreline of the marking and the centreline of the set out mark-<30 mm Distance between the centreline of the completed marking and the centreline of the previous marking-<15 mm Width of completed painted markings-±10 mm of the specified dimensions Width of completed markings for long life materials0 mm to +10 mm Length of completed stripes and blocks-0% to +10% of the specified length Gap between double lines--10 mm to +0 mm of the required 100 mm gap Raised Pavement Markers: (i)Markers in line with broken segments Transverse position-±25 mm of the centreline of segments Longitudinal position-±0.5 m of the specified position (ii) Markers in a longitudinal group Transverse position-±25 mm of specified position and ±10 mm of a line joining the centres of the end markers Longitudinal position-±0.5 m Spacing of markers within the group-50 mm of specified spacing (iii) Markers adjacent to an unbroken line Clearance to edge line-±5 mm of the specified dimensions Longitudinal mismatch between markers in transverse pairs-<25 mm Longitudinal position-Lesser of: 0.5 m or 10% (iv) Orientation of reflective markers-Lower edge of the reflective face at 85º to 95º to centreline of roadway or adjacent line Thermoplastic profiled lines (i) Tolerances on dimension Line width-+20 mm, -5 mm Line height-+2 mm, -0 mm Extrusion breadth-+10 mm, -0 mm Extrusion spacing-±15 mm Extrusion shape-±25 mm at any point from rectangular shape (ii) Tolerances on position Distance between the centreline of the marking and the centreline of the set out-<30 mm Length of the completed lines--0% to +5% of the specified length Longitudinal position of individual extrusions-±50 mm of any previously applied profiled lining | Visual /Site Inspection & Document Review | Per Lot | IP | SE/PE/SPE | This ITP
6 | Post-construction Activities
3.6 | Retroreflectivity Report | Vicroads 721.B06 (b) | Complete and forward Retro reflectivity Report in a form approved by the Superintendent showing the level of retro reflectivity determined for each test lot in accordance with the requirements of Clause 721.A12. | Document Review | Per lot | HP* | SE/PE/SPE | This ITP
| Job Completion Report | Vicroads 721.B06 (a) | For New Markings the Contractor shall complete and forward to the Superintendent a Job Completion Report (Pavement Markings). | Document review | Per lot When applicable | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /