## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource ID
checklist | ITP-086-CIV-PSDS-Signage Installation | itp |  |  |  |  | ITP-086-CIV-PSDS-Signage Installation Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-086-CIV-PSDS-Signage (Supply and Install)
label | ITP Description: PSDS-Signage (Supply and Install)
label | Discipline (e.g. CIV/STR/RAIL): 086-CIV
label | Revision Number: 0
label | Revision Date: 2/05/2024
label | ITP created by: Jason Lee
label | ITP approved for use by: VM
label | 1.1 Non Dependent
label | Reference: VicRoads Section 860 (Feb 2023)
label | 1.2 Non Dependent
label | Reference: VicRoads Section 714 (Feb 2023)
label | 1.3 Non Dependent
label | Reference: VicRoads Section 703 (Aug 2021)
label | 1.4 Non Dependent
label | Reference: IFC Drawings
label | 1.5 Non Dependent
label | Reference: A 1742.2:2009
section | Preliminaries - Materials
checkpoint | 2.1 Manufacture & Supply of Signages and Posts
label | REFERENCE: Section 860
label | ○ Section 860.06
label | ○ Section 860.07
label | ○ Table 860.071
label | ○ Section 714.03
label | ○ Section 714.06
label | ○ IFC Drawings
label | ACCEPTANCE CRITERIA: Signs are to be manufactured in accordance with Section 860 and IFC Drawings
label | ○ Warranties for the Signboard and Components, Sign Face Material, Giving of the Warranty and warranty Claims to be in accordance with Specification 860.07 and Table 860.071.
label | ○ Packaging and Storage of Sign to be in accordance with Specification 860.06.
label | ○ Signs and components shall be handled and transported so as to prevent damage.
label | ○ Signs shall be stored vertically in such a manner to prevent damage to the sign face, edges or components, taking into account any recommendations of the sheeting manufacturer.
label | ○ Post details shall be as shown on the Sign and Post Schedule and in accordance with the VicRoads Traffic Engineering Manual Volume 2. Steel posts shall be either:
label | — Hot dipped galvanised; or
label | — Pre-galvanised prior to forming
label | ○ Attach: TeamBinder Material Approval Ref No
label | METHOD: Document Review
label | FREQUENCY: Prior to works start
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: Conqa HP Release
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Preliminaries - Documentation
checkpoint | 3.1 Check for correct documentation
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Ensure that all employees and sub contractors are:
label | — Using the correct and complete set of drawings
label | — All drawings are the latest version
label | METHOD: Visual inspection
label | FREQUENCY: Prior to commencing any activity
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
section | Pre-construction / Pre-installation Activities
checkpoint | 3.1 Setting Out - Position of Posts and Signs
label | REFERENCE: Section 714.06 IFC Drawings
label | ACCEPTANCE CRITERIA: Set out work in accordance with IFC Drawings.
label | ○ The required positions of all posts and signs shall be checked and confirmed by the Superintendent before the erection of posts
label | METHOD: Verify
label | FREQUENCY: Prior to start
label | CATEGORY: HP*
label | RESPONSIBILITY: Surveyor, SE/PE, Nominated Authority
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
section | Construction / Installation Activities
checkpoint | 4.1 Foundation
label | REFERENCE: Section 714.06 (c), Section 703
label | ACCEPTANCE CRITERIA: All posts shall be set in concrete foundations to depths shown in the Sign and post Schedule and have hole diameters as per the below:
label | ○ Post sizes 32mm and 50mm nominal bore steel = 225mm diameter
label | ○ Post sizes 80mm to 150mm nominal bore steel = 300mm diameter
label | ○ Frangible hardwood posts 180mm x 100mm = 300mm diameter
label | ○ Concrete shall be 20MPa and complying with requirements in Section 703.
label | ○ Attach: Concrete Delivery Docket
label | METHOD: Measure, Visual
label | FREQUENCY: Per Lot
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE, Nominated Authority
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 4.2 Post Installation in Sockets
label | REFERENCE: Section 714.06 (d), Table 22 of AS 1742.2:2009
label | ACCEPTANCE CRITERIA: For Post Size 32mm Socket size to be 50mm Nominal Bore Tube
label | ○ For Post Size 50mm Socket size to be 65mm Nominal Bore Tube
label | ○ The socket should protrude 50 mm above an earth surface or 25 mm above a paved surface.
label | ○ The sign post must penetrate a minimum 450 mm into the socket.
label | ○ Depth of the socket should be as per Table 22 of AS 1742.2:2009.
label | ○ The sign post should be securely fixed into the socket by an approved vandal-proof method.
label | METHOD: Measure, Visual
label | FREQUENCY: Per Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 4.3 Backfilling of Post Holes
label | REFERENCE: Section 714.06 e
label | ACCEPTANCE CRITERIA: 32 and 50 mm Nominal Bore Steel Posts
label | ○ Posts holes shall be back-filled with concrete with a nominal strength of 10 MPa.
label | ○ 180 mm x 100 mm Frangible Hardwood Timber Posts
label | — frangible Hardwood Posts shall be erected in accordance with the drawings;
label | — post-holes for frangible hardwood posts shall be filled with a mixture of gravel and cement (4% by weight)
label | ○ Attach: Delivery Dockets
label | METHOD: Verify
label | FREQUENCY: Per Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 4.4 Sign Fitting
label | REFERENCE: Section 714.07
label | ACCEPTANCE CRITERIA: Signs shall be attached to the post or structure using the type and number of fittings as specified in the Sign and Post Schedule, or as follows:
label | — Signs up to 200mm in depth – one fitting per post
label | — Signs 201 to 900mm in depth – two fittings per post
label | — Signs 901 to 1200mm in depth – three fittings per post
label | ○ One extra fitting provided per post for each 400mm increment or part thereof above 1200mm.
label | METHOD: Measure, Visual
label | FREQUENCY: Per Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 4.5 Mounting of Signs
label | REFERENCE: Section 714.07 (d,e,i) IFC Drawings
label | ACCEPTANCE CRITERIA: Nominal Mounting Height for all signs in 2m from Road level to bottom edge of sign except keep left signs (R2-3) located in median islands, which are mounted 0.5m above ground
label | ○ Signs shall be positioned in accordance with the following tolerances:
label | (i) +/-40 mm of the height specified in the Sign and Post Schedule measured from the bottom of the sign or sign assembly to the lip of the kerb or edge of shoulder nearest the sign;
label | (ii) +/-100 mm of the pegged sign location or specified location.
label | ○ When a sign is to be mounted on frangible posts on a cut batter having a slope steeper than or equal to 2:1, the mounting height at the shorter post may be reduced providing that:
label | (i) the uphill corner of the sign is a minimum of 800 mm above the ground;
label | (ii) the sign at the longer post is 2200 mm minimum above the ground.
label | ○ Sign shall be installed such that the sign face is rotated away from the approaching traffic to avoid direct reflection (approximately 5⁰)
label | ○ After erection of each sign, all stiffening bars are to be removed.
label | METHOD: Measure, Visual
label | FREQUENCY: Per Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 4.6 Masking of Signs
label | REFERENCE: Section 714.08
label | ACCEPTANCE CRITERIA: Where indicated in the schedule, the Contractor shall mask the nominated sign(s) by placing a porous cloth or similar covering that conceals the sign text under both wet and dry conditions and does not void the sign material warranty. The masking material shall be held in position by wire mesh over the sign.
label | ○ Adhesive material shall only be applied to the masking material and not be applied to either the front or rear face of the signboard.
label | METHOD: Measure, Visual
label | FREQUENCY: Per Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
section | Post-construction / Post-installation Activities
checkpoint | 5.1 As-built Survey
label | REFERENCE: Section 714.05, IFC Drawings
label | ACCEPTANCE CRITERIA: Survey activities carried out to validate correct construction of signs, components and posts as per IFC Drawings and Section 714.
label | ○ Attach: Survey Conformance Data/Report
label | METHOD: Document Review
label | FREQUENCY: Per Lot
label | CATEGORY: IP
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 5.2 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed.
label | METHOD: Document Review
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP
checklist | ITP-159-CIV-PSDS-Line marking | itp |  |  |  |  | ITP-159-CIV-PSDS-Line marking Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-159-CIV-PSDS-Line marking
label | ITP Description: PSDS-Line marking
label | Discipline (e.g. CIV/STR/RAIL): 159-CIV
label | Revision Number: 0
label | Revision Date: 13/10/2023
label | ITP approved for use by: Victor Mira
label | 1.1 Non Dependent
label | Reference: Vicroads Section 721 February 2017
label | 1.2 Non Dependent
label | Reference: Vicroads Section 175 November 2019
label | 1.3 Non Dependent
label | Reference: Vicroads Section 853 February 1994
section | Preliminaries - Materials
checkpoint | 2.2 Type of marking material as shown on design drawings and shall conform to the Standard
label | REFERENCE: Vicroads 721.A05
label | ACCEPTANCE CRITERIA: Type as per relevant design drawings, obtain Conformance Certificates and test reports from supplier
label | ○ Provide the principle a list of materials that to be used with a certificate of conformance with associated test report
label | METHOD: Document Review
label | FREQUENCY: Once
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: Material certificate
date | Date Completed:
checkpoint | 2.3 Raised Pavement Markers
label | REFERENCE: Vicroads 721.A05
label | ACCEPTANCE CRITERIA: Raised pavement markers shall comply with the relevant requirements of AS 1906, Part 3 as listed in Section 175.
label | (ii) Temporary raised reflective pavement markers shall comply with the relevant requirements of AS 1906 as listed in Section 175, and shall be at least 100 mm in width and to a height of 50 mm with white reflective material on both sides and include protective covers for the reflective material
label | METHOD: Document Review
label | FREQUENCY: Per Material
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: Material certificate
date | Date Completed:
checkpoint | 2.4 Adhesive
label | REFERENCE: Vicroads 721.A05
label | ACCEPTANCE CRITERIA: Hot melt bitumen adhesive shall comply with Section 853 - Hot Melt Bitumen Adhesive for Raised Pavement Marker Installation.
label | ○ Other types of adhesive materials shall only be used with the approval of the Superintendent
label | METHOD: Document Review
label | FREQUENCY: Per Material
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: Material certificate
date | Date Completed:
checkpoint | 2.5 Line marking and Road marking Paint
label | REFERENCE: Vicroads 721.A05
label | ACCEPTANCE CRITERIA: All paints shall be approved under the Australian Paint Approval Scheme (APAS). Paint shall comply with the requirements of AS 4049.1 for solvent-borne paint or AS/NZS 4049.3 for water-borne paint as listed in Section 175.
label | METHOD: Document Review
label | FREQUENCY: Per Material
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: Material certificate
date | Date Completed:
checkpoint | 2.6 Glass beads
label | REFERENCE: Vicroads 721.A05
label | ACCEPTANCE CRITERIA: Glass beads shall be used on all applications of material and for all pavement markings and shall conform to the requirements in AS/NZS 2009 and the Australian Paint Approval Scheme (APAS) Specification 0042.
label | METHOD: Document Review
label | FREQUENCY: Per Material
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: Material certificate
date | Date Completed:
checkpoint | 2.6 Pristine glass beads (Type B-HR)
label | REFERENCE: Vicroads 721.A05
label | ACCEPTANCE CRITERIA: Glass beads shall be used on all applications of material and for all pavement markings and shall conform to the requirements in AS/NZS 2009 and the Australian Paint Approval Scheme (APAS) Specification 0042.
label | ○ Pristine glass beads (Type B-HR)
label | ○ Type B-HR glass beads shall comply with the properties of Type B (AS 2009:2006) drop-on glass beads, with an additional high performance retro reflectivity requirement, requiring the delivery of a minimum 450 mcd/lux.m², when tested in accordance with a modified Appendix M
label | METHOD: Document Review
label | FREQUENCY: Per Material
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: Material certificate
date | Date Completed:
section | Preliminaries - Procedures & Documentation
checkpoint | 2.1 Accreditation to Painting Contractors Certification Program
label | REFERENCE: Vicroads 721.D01
label | ACCEPTANCE CRITERIA: Provide evidence that the work is being undertaken by a contractor eligible for accreditation under painting Certification Program(PCCP). This Programme is administered by the CSIRO.
textbox | Enter: Teambinder Approval number
label | METHOD: Document Review
label | FREQUENCY: Once
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release, PCCP Accreditation
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Pre-construction Activities
checkpoint | 3.1 Surface preparation
label | REFERENCE: Vicroads 721.A06, Vicroads 721.A09
label | ACCEPTANCE CRITERIA: The area to be marked is dry free of dirt, gravel, flaking and other loose foreign material
label | ○ The area around making area is also clean to avoid tracking into the marking area
label | ○ Removal of existing unsound, obsolete or redundant pavement markings
label | ○ Removal of any foreign materials and debris within reasonable limits.
label | METHOD: Measure, Visual, Document Review
label | FREQUENCY: Per Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 3.3 Redundant pavement / unsuitable marking markers removal
label | REFERENCE: Vicroads 721.A12, Vicroads 721.A06, Vicroads 721.A08
label | ACCEPTANCE CRITERIA: Where removal of existing pavement marking/unsuitable pavement marking to the standard is required, the method of removal shall be subject to the approval of the Superintendent before removal works commence.
label | METHOD: Visual /Site Inspection & Document Review
label | FREQUENCY: Per Lot
label | CATEGORY: HP*
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
checkpoint | 3.2 Set out the works for installation of pavement markings / raised markers
label | REFERENCE: Vicroads 721.B05
label | ACCEPTANCE CRITERIA: Painting/application of material shall not commence until the Superintendent has inspected the set out and given consent to proceed, unless a written exemption has been granted by the Superintendent
label | METHOD: Survey, Document Review
label | FREQUENCY: Per Lot
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Construction Activities
checkpoint | 3.4 Application of pavement marking / markers
label | REFERENCE: Vicroads 721
label | ACCEPTANCE CRITERIA: Check conditions for application of marking paint & materials.
label | (i) Paints and markers installed as per manufacturer’s recommendations.
label | (ii) The same materials used with those nominated in the certifications.
label | (ii) All longitudinal lines have been applied by the nominated machine unless approved by superintendent
label | (iv) Verify markings are straight or with smooth, even curves where intended.
label | (v) Edges are clean sharp cut off.
label | (vi) Markings uniform in appearance, texture, width & thickness & free from unbeaded areas
label | (vii) Waterorne Paint & Glass Beads application rate conform to the requirements of Vic road 721.E01 requirements.
label | (viii) Markings are neat & free from traffic damage or other defects
label | (ix) Marking protected from traffic until hardened
label | METHOD: Visual /Site Inspection & Document Review
label | FREQUENCY: Per Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 3.5 Tolerances for new marking/marker installations
label | REFERENCE: Vicroads 721.A10, Table 721.A101
label | ACCEPTANCE CRITERIA: Pavement marking:
label | ○ Distance between the centreline of the marking and the centreline of the set out mark: <30 mm
label | ○ Distance between the centreline of the completed marking and the centreline of the previous marking: <15 mm
label | ○ Width of completed painted markings: ±10 mm of the specified dimensions
label | ○ Width of completed markings for long life materials: 0 mm to +10 mm
label | ○ Length of completed stripes and blocks: 0% to +10% of the specified length
label | ○ Gap between double lines: -10 mm to +0 mm of the required 100 mm gap
label | Raised Pavement Markers:
label | (i) Markers in line with broken segments
label | — Transverse position - ±25 mm of the centreline of segments
label | — Longitudinal position - ±0.5 m of the specified position
label | (ii) Markers in a longitudinal group
label | — Transverse position - ±25 mm of specified position and ±10 mm of a line joining the centres of the end markers
label | — Longitudinal position - ±0.5 m
label | — Spacing of markers within the group - 50 mm of specified spacing
label | (iii) Markers adjacent to an unbroken line
label | — Clearance to edge line: ±5 mm of the specified dimensions
label | — Longitudinal mismatch between markers in transverse pairs: <25 mm
label | — Longitudinal position - Lesser of: 0.5 m or 10%
label | (iv) Orientation of reflective markers - Lower edge of the reflective face at 85º to 95º to centreline of roadway or adjacent line
label | Thermoplastic profiled lines:
label | (i) Tolerances on dimension
label | — Line width: +20 mm, -5 mm
label | — Line height: +2 mm, -0 mm
label | — Extrusion breadth: +10 mm, -0 mm
label | — Extrusion spacing: ±15 mm
label | — Extrusion shape: ±25 mm at any point from rectangular shape
label | (ii) Tolerances on position
label | — Distance between the centreline of the marking and the centreline of the set out: <30 mm
label | — Length of the completed lines: 0% to +5% of the specified length
label | — Longitudinal position of individual extrusions: ±50 mm of any previously applied profiled lining
label | METHOD: Visual /Site Inspection & Document Review
label | FREQUENCY: Per Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Post-construction Activities
checkpoint | 3.6 Retroreflectivity Report
label | REFERENCE: Vicroads 721.B06 (b)
label | ACCEPTANCE CRITERIA: Complete and forward Retro reflectivity Report in a form approved by the Superintendent showing the level of retro reflectivity determined for each test lot in accordance with the requirements of Clause 721.A12.
label | METHOD: Document Review
label | FREQUENCY: Per lot
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Job Completion Report
label | REFERENCE: Vicroads 721.B06 (a)
label | ACCEPTANCE CRITERIA: For New Markings the Contractor shall complete and forward to the Superintendent a Job Completion Report (Pavement Markings).
label | METHOD: Document review
label | FREQUENCY: Per lot When applicable
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP