## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | OSD |  |  |  |  | Yes | OSD | 013692fd-9905-4916-98b9-38ac9ecbd392
checkpoint-group |  |  | section | Pre-Commencement
checkpoint-status |  |  | checkpoint | WorkSafe notification before trenching below 1.5m deep has been submitted
button | 5a7e9c2c-b35e-5a54-8e44-a6b711ffb039 |  | button | If required, trench shields are on site & ready for use | Yes, No
button | 56bdae12-f1f6-52d1-bad0-8db11a8cbbae |  | button | Dig Permit completed by contractor & attached | Yes, No
button | 0750a659-742b-5462-9fdb-6b4b0b626ad9 |  | button | Exclusion Zones have been erected as required (Attach photos below) | Yes, No
checkpoint-status |  |  | checkpoint | Existing in-ground services located and verified before excavation
checkpoint-group |  |  | section | Detail excavation
checkpoint-status |  |  | checkpoint | Excavation depths & locations confirmed prior to detailed excavation commencing
checkpoint-status |  |  | checkpoint | Any services (overhead / below ground) considered & isolated where required before excavation commences
checkpoint-status |  |  | checkpoint | Approval given to contractor to commence detail excavation
checkpoint-status |  |  | checkpoint | Excavation measurements align with drawings
boolean | 5173e16e-7ac8-5fac-bef8-33f2b648b704 |  | tickbox | Depth, Width & Length correct
checkpoint-status |  |  | checkpoint | Excavation works - completed to specification/drawings & Area left clean/tidy
label | fce3eef4-b550-5f62-a3e4-d2aaececf7ae |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checkpoint-group |  |  | section | Tanks/ Pumps / Chambers/ Grease arrestor Installation
checkpoint-status |  |  | checkpoint | Bedding material- correct type, grade and depth installed to support service
checkpoint-status |  |  | checkpoint | Product delivered is in good condition and correct as per specifications
checkpoint-status |  |  | checkpoint | Tanks/Pumps/Chambers/Grease arrestor Installed in the correct location and required depth
boolean | 6a13fc4f-d8bf-5b40-a947-1e34c36a4d24 |  | tickbox | Items are correctly sealed
checkpoint-status |  |  | checkpoint | Conduits installed - Provide photos
boolean | 3cbd4db9-f3fc-51d7-b092-86bd79513b31 |  | tickbox | Cables pulled through conduit
checkpoint-status |  |  | checkpoint | Installation 100% Completed - All final checks, documentation completed & attached - (Attach photos below)
label | 8b858392-40c7-551c-a9fe-4ab9e6a5b896 |  | note | FINAL - Pass when work(s) are completed (Any issues please comment below)
checkpoint-group |  |  | section | Backfill
checkpoint-status |  |  | checkpoint | Tanks/ Pumps / Chambers/ Grease arrestor covered and made safe
boolean | ebf1a9d6-46a5-59a9-b85e-92aa4e45d554 |  | tickbox | Trench suitably backfilled and compacted
checkpoint-status |  |  | checkpoint | Expansion lagging installed around pipes before concrete - If applicable
checkpoint-status |  |  | checkpoint | Rissers lagging has been installed - If applicable
checkpoint-status |  |  | checkpoint | HOLD POINT - Subcontractor QA Reviewed (Comment issues below)
boolean | 583288c3-4f40-53a0-b186-ada483928363 |  | tickbox | Test completed by contractor and confirmed to Ryman
label | bd00fff1-7816-536c-bd19-8245ddbc7c79 |  | note | Once reviewed & approved - Please attach (if applicable)
checkpoint-status |  |  | checkpoint | Works 100% completed to specification/drawings & Area left clean/tidy
label | a766c5ff-f386-592c-a355-c5af4ff394eb |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-flat |  |  | checklist | MSB & Comms Room |  |  |  |  | Yes | MSB & Comms Room | 0752a92b-0526-4bf4-afb8-dae0bdcc1ac0
checkpoint-status |  |  | checkpoint | Switchboards in place using suitable fixings to match mounting service No damage to external board has occurred during installation
button | d4be639a-ce7d-5e44-8955-7ff2d91045e3 |  | button | Ensure adequate pathways exist within board to accommodate all circuits and allow for future expansion | Yes, No
button | 9c52e8ad-29ed-510a-9c09-25e92ed5d470 |  | button | Install and loom in all circuits into correct cabinets | Yes, No
button | 21de70e1-e081-5fba-a84f-4446579755c1 |  | button | Ensure cable labels match switchboard schedule and construction drawings | Yes, No
button | 03b36014-3ff5-59c4-8800-8124186f05e9 |  | button | Cables are labelled as per specified requirements | Yes, No
button | 51b8f865-aa3e-5c09-9858-7d78f3c41f91 |  | button | Check all tightness of all terminals on all breakers and bars | Yes, No
button | ff9d13f6-6831-5a8a-b065-21a0927b637c |  | button | Ensure safety signage is installed and visible as per plans | Yes, No
checkpoint-status |  |  | checkpoint | Ensure all comms has been tested & commissioned
checkpoint-status |  |  | checkpoint | Ensure ventilation and exhaust fans are installed as per plans
checkpoint-status |  |  | checkpoint | Ensure FCU's (if required) are installed, tested & commissioned to provide sufficient cooling within MSB & Comms room
checkpoint-status |  |  | checkpoint | Final sign off - MSB & Comms room equipment installed as per the above ITP - Add general photos/comments below
label | 74535d43-4a16-500c-8be0-be991953b9e4 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Caretaker Toilet |  |  |  |  | Yes | Caretaker Toilet | 07a65704-7003-417c-bee2-29d5af155cd2
checkpoint-status |  |  | checkpoint | Floor wastes checked - Any issues comment/photo below
checkpoint-status |  |  | checkpoint | All rough-in pipework is colour coded to ensure no cross connections
checkpoint-status |  |  | checkpoint | All poly pipes located in framing to ensure no screw fixings will penetrate them
label | ebb3de1c-aa8f-55e3-8c02-fbfdc056dd48 |  | note | Any pipe running through a wall must be at 90 degrees
checkpoint-status |  |  | checkpoint | All Water & Gas risers are complete
checkpoint-status |  |  | checkpoint | All stacks are level/plumb
checkpoint-status |  |  | checkpoint | Ensure all services that go through fire rated walls to be treated with collars/fire rated sealant
checkpoint-status |  |  | checkpoint | Ensure rough in has been done as per specs
checkpoint-status |  |  | checkpoint | Final sign off - All plumbing work completed as per the above ITP - Add general photos/comments below
label | b6ac658c-e57c-5abd-98c0-da76e1424a59 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-sectioned |  |  | checklist | External Facade |  |  |  |  | Yes | External Facade | 0c709b76-1a2b-41fd-9787-c13119fa8c67
checkpoint-group |  |  | section | Hebel Work
checkpoint-status |  |  | checkpoint | Ensure hebel installed plumb & level with adjoining surfaces
checkpoint-status |  |  | checkpoint | Ensure gap between hebel & concrete 10‐15mm (max) & consistent
checkpoint-status |  |  | checkpoint | Ensure hebel panels are in full & not cracked
checkpoint-status |  |  | checkpoint | Final sign off - All hebel work completed as per the above ITP
checkpoint-group |  |  | section | Render Work
checkpoint-status |  |  | checkpoint | Ensure to use right dulux product & system as per specification & scope of works
checkpoint-status |  |  | checkpoint | Expansion cuts are consistent up & down & to substrate & also same cut thickness
checkpoint-status |  |  | checkpoint | Ensure surfaces flat & level & free of imperfections
checkpoint-status |  |  | checkpoint | Once render applied ‐ render allowed to sufficiently dry before primer coat
checkpoint-status |  |  | checkpoint | Primer Coat ‐ even consistent coverage on render
checkpoint-status |  |  | checkpoint | Membrane Texture Coat ‐ consistent coverage & texture, no roller marks, consistent sheen level
checkpoint-status |  |  | checkpoint | Paint thickness test to be carried out & report to be crossed checked DGain Alands external render & paint specification schedule
checkpoint-status |  |  | checkpoint | Final sign off - All render work completed as per the above ITP
label | ee7f00bd-97f4-5b46-80aa-5b9d852a6506 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-sectioned |  |  | checklist | SOG |  |  |  |  | Yes | SOG | 0c8d4602-fc8c-4a71-9af8-67809f562211
checkpoint-group |  |  | section | Prior to Concrete Pour
checkpoint-status |  |  | checkpoint | Materials used complies with design documentation
checkpoint-status |  |  | checkpoint | Datum point used & soffit RLs checked
checkpoint-status |  |  | checkpoint | Grids marked by builder
checkpoint-status |  |  | checkpoint | Confirm As-Built Survey of deck is complete
label | b3364fbd-3f18-562c-aa79-415e9114a171 |  | note | HOLD POINT - Attach As-Built Survey of Deck
checkpoint-status |  |  | checkpoint | Confirm Form Worker has received As-Built Survey of deck, and has rectified errors prior to any trades commencing on deck
checkpoint-status |  |  | checkpoint | Confirm all beams and decks constructed as per Structural Concrete Profiles
checkpoint-status |  |  | checkpoint | Install slip joints to all load bearing walls and corbels where required
checkpoint-status |  |  | checkpoint | Clean off decks and beams prior to pour, and ensure all exposed off-form soffits are free of any dust, stains and rust marks Hose down if necessary
checkpoint-status |  |  | checkpoint | Check if concrete has falls, and ensure shutters, timbers, spacers are used to create folds where necessary Cross-check the following drawings
boolean | 297e3be6-799b-5f3a-8dca-3204f3af8b56 |  | tickbox | Hydraulic Drawings
boolean | e39b8584-0f61-5f17-9796-0bbb9a33abf5 |  | tickbox | Architectural Concrete Outlines
boolean | 6114161b-231e-5593-92ce-88a22f149700 |  | tickbox | Structural Drawings
checkpoint-status |  |  | checkpoint | Check top RLs for all reinforcement, ensuring adequate concrete cover Confirm with Concreter
checkpoint-status |  |  | checkpoint | Confirm that plastic bar chairs are used everywhere, particularly at exposed off-form soffits
checkpoint-status |  |  | checkpoint | Attach Formwork ITP
checkpoint-status |  |  | checkpoint | Attach Formwork Engineer sign off certificate Confirm that certificate references props, braces and compliance with design & AS3610
label | ec9aa51d-c8a5-5c1f-873c-b65f8d68fbd7 |  | note | Attach Formwork Engineer's Certificate
checkpoint-status |  |  | checkpoint | Attach ALL Services Hydraulic ITP (for cast-in elements), include relevant mark-ups below
checkpoint-status |  |  | checkpoint | Attach Precast ITP (for cast-in elements), including relevant mark-ups
checkpoint-status |  |  | checkpoint | Attach Reo Fixing ITP
checkpoint-status |  |  | checkpoint | Attach Principal Structural Engineer Inspection Report, and confirm that all actions are closed out with photos sent to engineer
label | 0f91e2c9-1d4a-58e7-be21-02695ecc7e60 |  | note | Attached below as applicable
checkpoint-status |  |  | checkpoint | Attach Post Tensioning Engineer Inspection Report, and confirm that all actions are closed out with photos sent to engineer
label | 7d15ea9a-e9ea-545f-aafa-be0ca343296a |  | note | Attached below as applicable
checkpoint-status |  |  | checkpoint | Check quantity of concrete required prior to ordering
text | 5c197992-9f4a-5427-8f02-e218f1131b14 |  | textbox | Total m3 (as measured by Site Engineer)
text | 16a3b67d-52f5-509b-aa70-4335befe92bd |  | textbox | Total m3 (as measured by Foreman)
checkpoint-status |  |  | checkpoint | Confirm MPa, slump and agg size of concrete prior to ordering
text | 4aaa9c9a-6ced-5d27-971e-0aa3ab173393 |  | textbox | MPa
text | b832f6d8-e4fd-5baf-bc67-51ce18a2acb0 |  | textbox | Slump
text | 6de0347b-48b0-5c1f-97a9-b86ee455862e |  | textbox | Agg
checkpoint-group |  |  | section | During to Concrete Pour
checkpoint-status |  |  | checkpoint | Ensure concrete truck dockets have correct concrete strength, and attach delivery docket from each batch
checkpoint-status |  |  | checkpoint | Confirm concrete has falls to drainage points in slab
checkpoint-status |  |  | checkpoint | Ensure a representative from each of the following is on site and witnessing the pour
boolean | a9d5e0ec-09e1-5d32-a55b-fb6234599277 |  | tickbox | Formworker
boolean | edaa353b-1d2c-52ed-a4b8-9b74a38ed865 |  | tickbox | Electrician
boolean | 80e334eb-f243-5744-aa91-6ecc1ab131bc |  | tickbox | Plumber
boolean | 903dfbed-b0f1-57c6-b9b6-01b46b9cb848 |  | tickbox | Post Tensioner
boolean | 15c8b553-5291-5d74-8828-13040f01d028 |  | tickbox | Precast Installer
checkpoint-status |  |  | checkpoint | Confirm Form Worker has labour below deck inspecting all joints (particularly at columns & walls) and is immediately cleaning any slurry
checkpoint-status |  |  | checkpoint | Confirm that all protection to precast panels is maintained at all times during concrete pour
checkpoint-group |  |  | section | After Concrete Pour
checkpoint-status |  |  | checkpoint | Confirm Surveyor is out next day to carry out survey of finished concrete Attach As built Survey Plan
label | 7d21f71a-0daa-5524-8205-b7e5dd4aecb0 |  | note | Attached below as applicable
checkpoint-status |  |  | checkpoint | Confirm tolerance of finished concrete surfaces are in accordance with the specifications
checkpoint-status |  |  | checkpoint | Confirm saw joints are installed to engineers requirements
checkpoint-status |  |  | checkpoint | Confirm finish of concrete is adequate for application (broom/trowel/helicopter finish), refer to AS3610
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 1 day, and attach test results
text | 372ebef1-25ef-595b-801e-7e023216e2bb |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Confirm initial stress is conducted day after the pour, after concrete has reached 10 MPa on 1 Day results
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 4 day, and attach test results
text | f620b6af-179a-5122-9965-dea657511d2f |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Confirm final stress has occurred after concrete has reached 20MPa, and attach Stressing Records
label | a497fb62-2c2b-5ea5-9488-5bbbd04f41d6 |  | note | Attached below as applicable
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 7 day, and attach test results
text | b432e8fe-26ec-5ded-b698-74a822465ad4 |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 28 day, and attach test results
text | a4dfaf86-97f4-5e8b-9be8-d666c794de78 |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Attach Subcontractor ITP - Attached below as applicable
button | d4c19b4a-1b23-5822-b45b-af9899f038c3 |  | button | Subcontractor Sign Off | Yes, No, N/A
button | f4861301-32f8-58ba-afbb-93fe72c795ca |  | button | Aland Sign Off | Yes, No, N/A
holdpoint |  |  | signoff | Click to add Sign-Off Signatures
checklist-flat |  |  | checklist | Storage Lockers |  |  |  |  | Yes | Storage Lockers | 1176202c-0069-4871-aab9-10001b9f83e3
checkpoint-status |  |  | checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
checkpoint-status |  |  | checkpoint | Setout & alignment as per drawing (include revision below)
text | 873e0403-863f-5cc6-8088-760503dafbdf |  | textbox | Drawing & revision number(s)
checkpoint-status |  |  | checkpoint | Storage lockers installed to manufacturers instructions & standards
checkpoint-status |  |  | checkpoint | Final sign off - All storage lockers installed as per the above ITP - Add general photos/comments below
label | be598164-569c-5fb2-bd26-0439cbfdf4b0 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Mechanical Rough In |  |  |  |  | Yes | Mechanical Rough In | 16eb636f-6518-4dba-95c2-49d0ac31cc9e
checkpoint-status |  |  | checkpoint | All aircon has been roughed in & tested
checkpoint-status |  |  | checkpoint | All aircon vents are in correct spot
checkpoint-status |  |  | checkpoint | All service risers have been installed
checkpoint-status |  |  | checkpoint | Ensure all ducting sealed & sparged
checkpoint-status |  |  | checkpoint | All services that go through fire rated walls to be treated with collars/fire rated sealant
label | 240481b8-13d3-5373-9eab-066ca65ed6f2 |  | note | Relevant photo's/register has been completed
checkpoint-status |  |  | checkpoint | Duct work to be tear free & sealed prior to cleaning
checkpoint-status |  |  | checkpoint | Final sign off - All mechanical work completed as per the above ITP
label | f29db86f-ff9b-5988-b805-fb1e1905209d |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Ground Beams |  |  |  |  | Yes | Ground Beams | 18f67b16-8153-4088-a970-aa0edb23cf45
checkpoint-status |  |  | checkpoint | Any services (overhead/below ground) considered & isolated if required before excavation commences
checkpoint-status |  |  | checkpoint | Approval given to commence detailed excavation - depths and locations confirmed prior commencement
button | fe7de80f-426e-57ff-82e6-eac01c249ac6 |  | button | Footing RL Confirmed | Yes, No, N/A
button | 417009cc-242b-52fe-8ddb-3bc0105d4b43 |  | button | Any services (overhead / below ground) considered and isolated where required before excavation commences | Yes, No, N/A
button | 291f93f8-3279-5262-a75d-e9f886a7c51e |  | button | Approval given to commence detailed excavation | Yes, No, N/A
button | 95ce6804-7ddb-59d0-ad20-96f90da819af |  | button | Excavation checked, correct and approved | Yes, No, N/A
button | ffcde1b6-2374-5c3a-8c2f-886bbf2e1ef2 |  | button | Depth correct (allow for site concrete if required) | Yes, No, N/A
button | ea001ac2-23bd-5749-8961-87a02b1b3003 |  | button | Width correct (allow for boxing if required) | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Formwork correctly Installed
button | 2c596942-1b0d-540b-8288-b89331dcac4e |  | button | Set out - correct levels | Yes, No, N/A
button | 053a6b29-9d05-53a9-953f-38f8a71ae35d |  | button | Inserts, pockets, fixings, rebates etc | Yes, No, N/A
button | 0c3c0a2a-b1ee-59ca-ad59-98d9e770541e |  | button | Bracing, Fixing Propping & Supports | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Reinforcement installed as per plan including cover & chairs
button | fec4bb5a-faae-5091-87eb-f6f12e2ede45 |  | button | Reo spacing & grade as per specifications | Yes, No, N/A
button | 9eef224b-0c81-5e02-8c7a-8ee6c0ec515d |  | button | Starter bars, dowel bars, & mesh installed as per specifications | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Concrete strength/ Slump confirmed
checkpoint-status |  |  | checkpoint | Any waterproofing elements have been correctly installed and checked
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checkpoint-status |  |  | checkpoint | Final sign off - All ground beams completed as per the above ITP - Add general photos/comments below
label | 61d13879-f6cd-521d-8f47-0fd3464234c3 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-sectioned |  |  | checklist | Capping Beam (V140421) |  |  |  |  | Yes | Capping Beam (V140421) | 19809baa-ed04-4b66-a82d-97b5cd862747
checkpoint-group |  |  | section | Prior to Capping Beam Operations
checkpoint-status |  |  | checkpoint | Confirm RL’s of capping beam
button | 682e0dc5-7ba7-5bb8-a586-5dbab1af997e |  | button | Confirm excavation for capping beam has been complete and ready for formwork to commence | Yes, No, N/A
button | 11760787-4b0b-5e79-b9a7-b853f3ee8966 |  | button | Set out of capping beam complete | Yes, No, N/A
button | 850109e6-3708-5041-8539-0e8071c8e1c8 |  | button | Confirm engineers design of capping beam | Yes, No, N/A
label | fdb4f03a-cdf8-5af8-92b8-280dc3f2c03e |  | note | Attached/referenced below as applicable
checkpoint-status |  |  | checkpoint | Attach structural engineer inspection prior to concrete pour (All items closed out)
label | 24f5ef86-1917-541b-b439-4495858903d0 |  | note | Engineer inspections attached/referenced below
checkpoint-status |  |  | checkpoint | Concrete pre-pour checks - As per below
button | 937c5666-89b3-5694-bd50-dde69cc114d7 |  | button | Confirm mPa, slump and agg size of concrete prior to ordering | Yes, No, N/A
button | 80ffa77f-dee0-5b70-adbd-b838d06c5269 |  | button | Confirm formwork faces are clean and will provide required class finish | Yes, No, N/A
button | 00e2a77d-9fa4-5b9e-8cbf-939f8ae39f25 |  | button | Confirm formwork is adequately braced to reduce blow-out occurrence | Yes, No, N/A
button | ac05131d-13df-5b93-b6ab-0acda82429c7 |  | button | Confirm pile connection bars are clean and free of debris | Yes, No, N/A
checkpoint-status |  |  | checkpoint | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checkpoint-group |  |  | section | After Capping Beam Poured
checkpoint-status |  |  | checkpoint | Attach surveyors spot check – Confirm tolerance of finished concrete surfaces – Ensure no movement to the capping beam during pour
label | bd08ce92-b025-5007-8dda-2a22cc6a0133 |  | note | Confirm surveyor spot checks levels and attach markup
checkpoint-status |  |  | checkpoint | Confirm stripping is complete All exposed faces are clear of formwork
button | 6db83d0f-4d96-5d25-80ed-99c28c4debf7 |  | button | Confirm vibration was adequate – no air pockets, agg evenly distributed If not, comment rectification method required | Yes, No, N/A
button | 34e770b1-a985-5c44-9005-836dafee8e65 |  | button | Confirm no blow-out occurred If occurred, comment rectification method required | Yes, No, N/A
button | 33dfb269-bb98-593a-a10e-7cd88979a40a |  | button | Confirm finish of concrete is adequate (broom/trowel/helicopter finish) | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 1 day
text | bdf26422-ea0d-5ac1-a870-0863807264a7 |  | textbox | Test Strength Mpa
label | 46bb6174-b40c-5791-a2de-2feeb27a66e7 |  | note | Attach concrete test result
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 4 days
text | 1c0e5552-a0aa-5892-bf31-4075094b2620 |  | textbox | Test Strength Mpa
label | 0450d48b-4a3b-5dc0-8c3e-768f41ff707f |  | note | Attach concrete test result
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 28 days
text | 7c7a42e6-7fba-58c0-9ed7-7dd1f796f590 |  | textbox | Test Strength Mpa
label | c9b1d99a-5475-57f3-8f2a-ba12468c5d39 |  | note | Attach concrete test result
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Attach Subcontractor ITP - Attached below as applicable
button | 805b8edd-7ed6-539c-b7e8-a9b904689225 |  | button | Subcontractor Sign Off | Yes, No, N/A
button | 6bca9496-1ab6-5bb9-9fd0-535080403812 |  | button | Aland Sign Off | Yes, No, N/A
holdpoint |  |  | signoff | Click to add Sign-Off Signatures
checklist-flat |  |  | checklist | Commissioning Documentation |  |  |  |  | Yes | Commissioning Documentation | 1ae1bba6-b14a-4343-b8d2-efe6909c0b57
checkpoint-status |  |  | checkpoint | Commissioning documentation attached below
text | ac1cb691-657a-590a-a2ed-a0190efaefeb |  | textbox | Company Documentation relates to
checklist-flat |  |  | checklist | Balcony & Podium Waterproofing |  |  |  |  | Yes | Balcony & Podium Waterproofing | 1bb6fadc-2413-4e9e-a5ff-5ddd137e53ad
checkpoint-status |  |  | checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
label | 568fb2db-69d1-5bf3-8868-1c08a27469eb |  | note | Attach relevant photos below
checkpoint-status |  |  | checkpoint | Membrane system & methodology checked off AGainst Aland standard details & MSDS & guidelines
button | 85e5a2c8-a40c-5581-8fd9-380b58e852fa |  | button | Surface preparation as per application guide | Yes, No
button | 226f9bb3-d9e2-5ed3-a577-9d1db88b7ce2 |  | button | Substrate clean, structurally sound & ready to receive membrane | Yes, No
checkpoint-status |  |  | checkpoint | All corners, joints, gaps & cracks to be treated with a flexible polyurethane sealant Resiflex FC ‐apply selected Membrane as per datasheet & application guidelines
label | fff9187a-97b0-58ed-9f34-224edea6ef86 |  | note | Ensure sealant has fully cured before installing membrane
label | bfe0c044-5cc1-594e-88b9-e63ccc5fcd46 |  | note | Ensure Humidity, temperature & moisture are in accordance with manufacturer's recommendations prior to primer
label | 7aa21f2f-e360-51e2-b5e4-0a53fc2e1d96 |  | note | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint-status |  |  | checkpoint | Ensure all floor wastes & pipes have been primed in accordance with manufacturer's recommendations
label | 3ff6fe06-65e4-57d7-812c-6241625f50d5 |  | note | PrimeSeal MC to all surfaces at a rate of 3‐4m2/Ltr
label | e25a880d-4073-5df4-a5a4-3f80c7ac9b71 |  | note | Alternative primers Multiseal ‐ Primeseal SP at a rate of 5‐8 m2/Ltr
checkpoint-status |  |  | checkpoint | Balustrade base i.e. shoe base or angle base installed & grouted with structural grout (as required)
label | 7ba4c654-7210-5c03-81c3-18c30b6a9dca |  | note | Joint between bottom of base & substrate to be no greater than 10mm
checkpoint-status |  |  | checkpoint | Overflow at the ends of balustrades in place
label | 0c912e93-f425-5dff-8e5b-34e6f50c6ac0 |  | note | Approximate width of over floor to be 50mm
label | 154ef057-ee19-55ee-8532-b0ef0c07831f |  | note | Height of overflow must be lower than the bottom of subsill
label | 2c849b5e-56bc-550e-8798-93341a1c4785 |  | note | Angle to be installed between end of base & wall with top of angle to be at FFL
checkpoint-status |  |  | checkpoint | First coat of selected Membrane to entire areas as per DURAM recommendations
label | dcff4d0a-d4fc-5c8e-9342-748706de5818 |  | note | Note ‐ a total dry film thickness of min 1.2mm (1200 microns) in two finished coats. As such at min. Wet Film Thickness of min 0.75mm (750 microns) per coat is required
label | c36db381-132c-5835-b025-f772abd61605 |  | note | Apply membrane at a coverage of 0.75 ‐ 1 Ltr / m2 per coat
button | 0ceafcd0-f08a-5123-b9b8-083c9e0b99b2 |  | button | Allow the membrane coat to dry min 12 hours check the tackiness before applying next coat | Yes, No
button | 713e780f-5d7d-5e95-88dc-1d4565d72446 |  | button | Ensure humidity, temperature & moisture are in accordance with manufacturer's recommendations prior to second coat | Yes, No
checkpoint-status |  |  | checkpoint | Second coat of selected Membrane to entire areas as per DURAM recommendations
label | 28adc742-85ae-5507-b729-a652a30fc168 |  | note | Note ‐ a total dry film thickness of 1.2mm (1200 microns) in two finished coats. As such at min. Wet Film Thickness of 0.75mm per coat is required
label | 46ca8fc0-27ea-5471-8f29-7abf9ade8b68 |  | note | Apply membrane at a coverage of 0.75 ‐ 1 Ltr / m2 per coat
button | 34d6955f-b4de-5182-ad02-964d609cf92a |  | button | The membrane is to be applied in a minimum of 2 coats at a total coverage of 1.2 to 2 litres per m2. or relevant product TDS | Yes, No
button | 0ca6bc34-074d-52b2-b868-2b10840e4f6c |  | button | Allow 2nd coat of Multithane UV min. 12 hours BUT no longer than 24 hours before installing Multithane ATC top coat | Yes, No
checkpoint-status |  |  | checkpoint | Ensure humidity, temperature & moisture are in accordance with manufacturer's recommendations prior to final coat
checkpoint-status |  |  | checkpoint | Apply final coat of Multithane ATC at a coverage rate of 3 ‐ 4 m2/lte
checkpoint-status |  |  | checkpoint | Carry out dry film thickness test using Positector coating thickness inspection instrument
checkpoint-status |  |  | checkpoint | Rectification of defective works for failure of flood test & works complete
checkpoint-status |  |  | checkpoint | Ensure screed is fully dry ready for sealer application
checkpoint-status |  |  | checkpoint | Crystoflex membrane applied (note allow sufficient time for curing minimum 24 Hours)
checkpoint-status |  |  | checkpoint | Final sign off - All balcony & podium waterproofing work completed as per the above ITP
label | 0a7c6371-6a07-5f4f-a6f1-7d01eae6f9c7 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-sectioned |  |  | checklist | Shotcrete (V140421) |  |  |  |  | Yes | Shotcrete (V140421) | 2863ad70-2557-419a-9b77-c9ef276d3d1a
checkpoint-group |  |  | section | Prior to Commencing Works
checkpoint-status |  |  | checkpoint | Ensure zone for shotcrete has been excavated
checkpoint-status |  |  | checkpoint | Confirm reinforcement has not moved by concrete placement
button | 7b41962c-2c40-5fc5-9720-0f800f82e195 |  | button | Confirm that all mesh has bar chairs tied to steel to prevent dislodgement during shotcrete works | Yes, No, N/A
button | b8aa579d-6da8-5e62-8b9e-d36ca678bc71 |  | button | Confirm that reinforcement has been installed in accordance to structural engineer details prior to arranging for site inspection | Yes, No, N/A
button | 68d02ba0-4e8b-5e69-a392-3b919427267e |  | button | Where recessed column is located, confirm that reinforcement installation allows for rebated shoring zone | Yes, No, N/A
button | 816644a6-3bea-5d47-938f-675b4e9c7d48 |  | button | Confirm that min 300mm lap has been provided for mesh and plastic membrane at typical horizontal control joint | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Confirm no blow-outs have occurred
checkpoint-status |  |  | checkpoint | Confirm core drain has been installed in accordance with specifications
checkpoint-status |  |  | checkpoint | Confirm plastic membrane to rear face of shotcrete wall has been lapped and taped at joints
checkpoint-status |  |  | checkpoint | Confirm that structural engineer has completed inspection and provided signoff (incl defect closeouts)
label | 5c43985a-3e4d-524a-9509-e7957ae78c2c |  | note | Engineer inspections attached/referenced below
checkpoint-status |  |  | checkpoint | Confirm that inspection photos are taken and attached below
checkpoint-group |  |  | section | Shotcrete Works
checkpoint-status |  |  | checkpoint | Confirm that shotcrete is applied evenly in layers to avoid honeycombing
checkpoint-status |  |  | checkpoint | Ensure that shotcrete wall is troweled to agreed finish
checkpoint-status |  |  | checkpoint | Obtain subcontractor’s installation ITPs and shotcrete mix dockets
label | 3ffbb78b-25d8-5ed8-a654-a27701192c95 |  | note | Attached/referenced below as applicable
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Attach Subcontractor ITP - Attached below as applicable
button | 32f69e62-7a3d-59a7-9ac5-b3b0a96da075 |  | button | Subcontractor Sign Off | Yes, No, N/A
button | 78b22793-1eb5-5b4c-8029-069c95ea91e3 |  | button | Aland Sign Off | Yes, No, N/A
holdpoint |  |  | signoff | Click to add Sign-Off Signatures
checklist-flat |  |  | checklist | Tiling |  |  |  |  | Yes | Tiling | 2b8a941e-a9bc-43b4-b46d-c43bdf31b7a2
checkpoint-status |  |  | checkpoint | Correct tiles are being used in correct areas
button | 597ef029-ad28-55f2-9596-72c9e243e1fa |  | button | 5mm expansion to all junctions | Yes, No
button | f65f8e39-1643-5747-b69f-4e459571f4d6 |  | button | 1.5mm spacers being used | Yes, No
button | ccc08bdd-8723-5351-859c-b797eb8b73a2 |  | button | Tile lips are within tolerances | Yes, No
button | 4385c9d9-8e89-51ca-96ed-399fd137c9bb |  | button | Correct tiles are being used in correct areas | Yes, No
button | 41dd26cf-5b9e-5630-93e1-08ff38328ce7 |  | button | Angles & trims are straight & free off any defects | Yes, No
checkpoint-status |  |  | checkpoint | All floors fall to wastes & don't hold water
button | f52d0030-9b02-54ac-a0e9-0b2e74f9444a |  | button | Floor wastes are installed & free of any defects | Yes, No
button | 7987e6f5-c3c7-5326-bfcf-9f877bfdaeb3 |  | button | Wastes are free of any rubbish | Yes, No
button | 0657948d-0e9e-5c5b-9ecf-56f55aec66c2 |  | button | Check all falls to floor wastes to comply with BCA | Yes, No
checkpoint-status |  |  | checkpoint | Ensure all tiles are fixed correctly
button | 0bdd34b9-a9e9-51d8-8e7f-6b9421db5540 |  | button | Check all tile lips are within tolerances | Yes, No
button | cfdeec66-6386-5e99-a298-d79a97c7f267 |  | button | Check that glue has been applied notch trowel in accordance with manufacturer's specifications | Yes, No
button | 2769544e-34dc-590d-bb68-f7b435153514 |  | button | Walls have been laid straight & plumb, reveals are square | Yes, No
button | 619bdd3e-9b13-5413-9e0c-62abc87ac071 |  | button | Tiles have been laid 1m below 1m offset line | Yes, No
button | 780624a9-96f3-5281-8cb9-26086cd62a48 |  | button | Tiles have been laid to marker lines on mixers | Yes, No
button | f99020a3-cdb7-594c-8ce3-9bff2bff7502 |  | button | Full tile bond on door frames & work away to ensure cuts are in corners | Yes, No
button | 964d7b68-577f-585b-8fa2-c98c0ece9be4 |  | button | Double check tile batch before use in area | Yes, No
button | 3a39dc8b-0195-50bb-bb28-06a89087b4d5 |  | button | Check all tile lips are within tolerances | Yes, No
checkpoint-status |  |  | checkpoint | Ensure floor wastes are clean & free from any debris, area left clean
checkpoint-status |  |  | checkpoint | Final sign off - All tiling work completed as per the above ITP
label | 749b01f9-ab3c-583e-86f7-ace6d278a554 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Framing |  |  |  |  | Yes | Framing | 2d6406cc-3e47-4b9a-af0f-e7c994b92d69
checkpoint-status |  |  | checkpoint | All studs are set out correct, and are plumb level and square
checkpoint-status |  |  | checkpoint | All studs are installed as per manufacturer's recommendations and the BCA
checkpoint-status |  |  | checkpoint | All noggins are installed correctly
checkpoint-status |  |  | checkpoint | All sarking has been installed as per manufacturers recommendations
checkpoint-status |  |  | checkpoint | Penetration through fire rated wall have been treated
checkpoint-status |  |  | checkpoint | Door frames have been installed plumb level, square and in wind
checkpoint-status |  |  | checkpoint | All window and sliding door openings are as per plan and line up with above elements
checkpoint-status |  |  | checkpoint | All studs are level and in wind
checkpoint-status |  |  | checkpoint | All internal walls have been studded out and are as per plan
checkpoint-status |  |  | checkpoint | Weep holes have been installed correctly and at right height
checkpoint-status |  |  | checkpoint | Door frames to be infilled
checkpoint-status |  |  | checkpoint | Insulation installed as per AS/BCA (party walls & external)
checkpoint-status |  |  | checkpoint | Acoustic practices to be as per Australian Standards & BCA
checkpoint-status |  |  | checkpoint | Final sign off - All framing work completed as per the above ITP
label | d03d96a5-7320-55a2-a456-c6abcc39d65d |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-sectioned |  |  | checklist | NDIS |  |  |  |  | Yes | NDIS | 326d202d-3b61-4907-b452-df69890fc06f
checkpoint-group |  |  | section | Planning and Pre-Commencement
checkpoint-status |  |  | checkpoint | Confirm site setout is from the latest set of drawings, and has been approved “For Construction”
checkpoint-status |  |  | checkpoint | Insert DWG. No
checkpoint-status |  |  | checkpoint | Confirm meter marks have been clearly shown
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | General Requirements
checkpoint-status |  |  | checkpoint | The dwelling has the following noted features on an entry level or a level serviced by a lift: One kitchen, and One laundry.
label | f8d5e823-ca0c-551e-90b3-ff2a8efd9224 |  | note | One bedroom exclusively for use of a participant,
label | 206d6211-2ab0-5c85-89f7-a8c7c3b62e67 |  | note | One WC pan,
label | 0f4bf664-1a3d-51e0-897b-a4b955044a97 |  | note | One shower,
label | f202a49f-5b78-5dff-bdb0-784651695e0d |  | note | One hand wash basin,
label | c9b6bcc5-da79-5fa2-9b19-a6badc24b8cc |  | note | One living area,
checkpoint-status |  |  | checkpoint | General Requirements complete
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Pedestrian entry from the site boundary
checkpoint-status |  |  | checkpoint | A safe, continuous step-free accessway is provided from the front boundary of the site to an entry doorway of the dwelling. The accessway may include a walk way, step ramp or ramp and shall include any additional enhanced requirements of the particular design category as noted in this SDA Design Standard document.
checkpoint-status |  |  | checkpoint | 1:20 grade is permitted as a part of the accessway and where provided has incorporate the following:
label | 5160365a-6f6e-55a6-89e6-758ba6025a60 |  | note | • 1200mm length mid-landings, in the direction of travel (of the same width as walkway width) provided every 15M. Additional landing size has been provided as per AS1428.1 where a change in direction is required.
label | 2ac924eb-be2a-59ff-8ee3-7408e7ccd8cf |  | note | • The floor surface abutting the sides of a 1:20 grade walkway is provided with a firm and level surface which can be a different material at the same level and grade of the walkway, and extend horizontally for an additional minimum of 600mm, from an accessway unless one of the following is provided: kerb, kerb-rail and handrail or wall (min 450mm height) to comply with the requirements of AS1428.1.
label | 74cfb481-c307-5334-b2e6-54b746d48c12 |  | note | • Slip resistance shall be a minimum of P4 or R11.
checkpoint-status |  |  | checkpoint | 1:10 grade step ramp is permitted as a part of the accessway and where provided has incorporated the following:
label | d08b2040-34c1-556c-81c5-4cf59b4e9287 |  | note | • The maximum level change or transition which can be dealt with by a step ramp is 190mm and maximum length of ramp is 1900mm
label | 53cc09dd-d407-503f-a99a-b6d023b45ecb |  | note | • All features of 1:10 step ramp including landing sizes, handrails / kerbrails (if required) shall comply with the requirements of AS1428.1.
label | 2610d34d-1928-5a2c-9926-e16cebbd168d |  | note | • Slip resistance shall be a minimum of P5 or R12
checkpoint-status |  |  | checkpoint | Where the level difference is over 190mm, a maximum grade of 1:14 ramp is permitted as a part of the accessway and where provided has incorporated the following:
label | 8ce31ac3-f951-5d91-8e38-7e16b2b2daaa |  | note | • 1200mm length landings, in the direction of travel (of the same width as ramp width) provided at base and top of the ramp and at maximum intervals of 9M. Additional landing spaces shall be provided at turns and changes in direction as required under AS1428.1.
label | c223c0e1-dbf8-5092-9893-54f070fec4c1 |  | note | • All features of 1:14 ramps including handrail profile, handrail extensions and kerb rails shall comply with the requirements of AS1428.1
label | ea85bd44-5205-5a97-bd44-99c1a3bb9561 |  | note | • Slip resistance shall be a minimum of P4 or R11.
checkpoint-status |  |  | checkpoint | The minimum clear width of an accessway shall be 1200mm measured from a narrowest part of the accessway (for example skirting to skirting). This includes all ramps within the accessways.
checkpoint-status |  |  | checkpoint | Where provided, the minimum clear width of a curved accessway is a minimum of 1500mm with a minimum radius of the curvature as specified under AS1428.1. The crossfall shall be towards the centre of curvature.
checkpoint-status |  |  | checkpoint | Where a ramp or walkway is part of the accessway, level landings no less than 1200mm x 1200mm, exclusive of the swing of the door or gate that opens onto them, has been provided. The landing size shall increase based on the required gate / door circulation spaces or change of direction requirements as per AS1428.1.
checkpoint-status |  |  | checkpoint | Minimum vertical clearance along all paths of travel is 2000mm.
checkpoint-status |  |  | checkpoint | Pedestrian entry complete
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Car Parking
checkpoint-status |  |  | checkpoint | A safe, continuous step-free accessway has been provided from both; The front boundary of the site and From any car parking space associated with the dwelling (excluding staff only parking), to an entry doorway of the dwelling.
checkpoint-status |  |  | checkpoint | If providing a car parking space, for use of the participant, it has been provided with:
label | 20dd1279-97fb-5925-977b-0b9739881223 |  | note | Minimum dimensions of 3800mm (width) x 5400mm (length), An even, firm and slip-resistant surface of P4 or R11, A level surface with a maximum 1:40 gradient in any direction, and Roof over space with clear vertical clearance in accordance with AS2890.6
checkpoint-status |  |  | checkpoint | Based on the building classification, the NCC or the local government authority may require the provision of an accessible parking space in accordance with AS2890.6, in which case the full compliance with AS2890.6 is required.
checkpoint-status |  |  | checkpoint | Car Parking Complete
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Entrance, doorways and door hardware
checkpoint-status |  |  | checkpoint | A level landing area of at least 1500mm x 1500mm with a maximum 1:40 gradient and crossfall has been provided at the level (step-free) external entry doorway, on the arrival side of the door (i.e. the external side of the door).
label | 10616c32-6b62-5d9f-be0c-984509a69502 |  | note | The level landing area has been increased to accommodate door circulation spaces as per AS1428.1
label | 1391026c-cfa3-5451-8c46-33d576c68205 |  | note | Doorway threshold ramp (if required) is permitted to be within the landing area.
checkpoint-status |  |  | checkpoint | A step-free doorway threshold has been provided to an external entry doorway. Where the threshold at an external entry doorway exceeds 5mm and is less than 35mm, a doorway threshold ramp in accordance with AS1428.1 shall be provided with a maximum 1:8 grade as shown in Figure 4 of the NDIS Specialist Accommodation Design Standard
checkpoint-status |  |  | checkpoint | A step-free doorway threshold has been provided to external doorways leading to common or private open spaces. Where the threshold at the external doorway exceeds 5mm and is less than 35mm, a doorway threshold ramp in accordance with AS1428.1 shall be provided with a maximum 1:8 grade as shown in Figure 4.
checkpoint-status |  |  | checkpoint | The dwelling has provided all doors to and within all areas normally used by the participants), including all external doorways with a minimum clear opening width of 950mm, when measured in accordance with Figure 5 of the NDIS Specialist Accommodation Design Standard
checkpoint-status |  |  | checkpoint | All door circulation spaces (excluding internal door circulation spaces for bedrooms) has been provided in accordance with AS1428.1 to both sides of the door.
checkpoint-status |  |  | checkpoint | All internal doorways have a level (step-free) transition and threshold (maximum vertical tolerance of 3mm vertical or 5mm between abutting surfaces is allowable provided the lip is rounded or bevelled).
checkpoint-status |  |  | checkpoint | Doorways shall have door handles installed at between 900mm to 1100mm above the FFL.
checkpoint-status |  |  | checkpoint | Door handles selection and location comply with AS1428.1 as shown in Figures 6 and 19 of the NDIS Specialist Accommodation Design Standard
checkpoint-status |  |  | checkpoint | Doorway circulation spaces in accordance with AS1428.1 have been provided to all doorways (excluding exclusive staff use areas, non-accessible toilets and storage rooms).
label | 6fb50eb9-b6e9-5f29-8cf1-3fedcd450c1a |  | note | Door automation can be provided in lieu door circulation spaces that are required as per AS1428.1 to the latch side of the door.
label | 62c7175c-2af3-50c7-b965-f54eee88d1fc |  | note | Note that if door circulation is not provided as per AS1428.1 then door automation must be provided at the onset and not simply provision for door automation at a future time.
checkpoint-status |  |  | checkpoint | Power and control cabling to head of entry doors of participant bedrooms, one external entry doorway and one external doorway to an open area (where provided) has been provided for future automation. A capped GPO at the door head may be provided to comply with this requirement.
checkpoint-status |  |  | checkpoint | Entrance, Doorways and Door Hardware complete
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Corridors
checkpoint-status |  |  | checkpoint | All internal corridors and passageways has provided a minimum clear width of 1200mm when measured from skirting to skirting.
checkpoint-status |  |  | checkpoint | Width of the corridors comply with the requirements of door circulation spaces as per AS1428.1 based on direction of approach.
label | b1d8dcd6-7bde-5f7b-8423-e7adefc302b0 |  | note | Note: Where AS1428.1 requires corridor width of less than 1200mm, then a minimum clear width of 1200mm shall be provided.
checkpoint-status |  |  | checkpoint | Corridors Complete
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Windows
checkpoint-status |  |  | checkpoint | All window sills in living areas and at least one window sill in each participant’s bedroom are positioned no higher than 1000mm above the FFL.
label | f390a2d4-a326-5564-b135-52af2a2c9f72 |  | note | Note: Concession is reasonable in kitchen, bathroom and utility spaces.
checkpoint-status |  |  | checkpoint | Window controls are located within easy reach from either a seated or standing position (between 600mm to 1100mm above FFL).
label | 82aa78b1-be8b-5c98-aa18-b0405e1b8734 |  | note | Note: Concession is reasonable in kitchen, bathroom and utility spaces.
checkpoint-status |  |  | checkpoint | Power and control cabling to windows of bedrooms and living areas have been provided for future window blind automation. A capped GPO at the window head may be provided to comply with this requirement.
checkpoint-status |  |  | checkpoint | Provide lockable windows.
checkpoint-status |  |  | checkpoint | Windows Complete
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Sanitary Facilities
checkpoint-status |  |  | checkpoint | The entry level, or a level serviced by a lift, have been provided with sanitary facilities that include a WC pan, a shower and a hand wash basin.
checkpoint-status |  |  | checkpoint | The required WC pan, shower and hand wash basin referred to in Clause 7.1 have been provided within the same bathroom.
checkpoint-status |  |  | checkpoint | At least one WC pan on the entry level, or a level serviced by a lift, is AS1428.1 compliant (as per requirements for unisex accessible toilet and not as per ambulant toilet) and has been provided with either:
label | edf61062-6ae6-52a7-b441-340a49d1e384 |  | note | c/l of WC pan at 450mm - 460mm to side wall, 800+/-10mm front edge of WC pan from back wall, Minimum 600mm clear of cistern from front edge of WC pan
label | 837dcbf8-ea0c-5236-bef1-83cc0318bf64 |  | note | Minimum circulation space of 1900mm x 2300mm as required by AS1428.1
label | 24c0df7f-b3c7-50ee-aeb5-fca99c85f0ee |  | note | Toilet flushing controls shall be proud of the surface
label | 4246eaea-2158-5b08-92f4-63ae33d7d991 |  | note | Refer to Figure 8(a) for permissible basin encroachment zone. OR A minimum circulation space of 900mm to both sides of the WC pan for 2300mm from the back wall of the WC pan has been provided as required for Accessible Adult change facilities as noted in the NCC. Refer to Figure 8(b)
checkpoint-status |  |  | checkpoint | At least one shower on the entry level, or a level serviced by a lift, has been provided in a corner of the room with the following provisions:
label | 414e2870-9253-5d28-a546-19a6181372dd |  | note | The shower size is a minimum of 1160mm x 1100mm and provided with one of the two circulation spaces for shower as required by AS1428.1. Refer to Figures 8(c) and 8(d).
label | ba1f2d07-959e-5a80-9f83-b09e2d660fa6 |  | note | Shower curtain rail has been provided around the 1160x1100mm shower space.
label | 8a9c17c3-6265-54df-b4e0-be2dd2376ac4 |  | note | Only vertical support grab rail has been provided to the shower, with provision of height adjustable shower head and hose as per AS1428.1
label | aa7ff17d-dbee-5dbd-9fab-af7951fb72ac |  | note | Lever style shower tap has been provided and located in a zone between 900mm to 1100mm above FFL and between 300mm and 800mm from the internal corner.
label | 79572894-2eb9-5de1-ad08-103238905245 |  | note | Shower floor gradient is as required by AS1428.1.
checkpoint-status |  |  | checkpoint | At least one hand wash basin on the entry level, or a level serviced by a lift, is AS1428.1 compliant and has been provided with:
label | 207028dd-8f57-550b-b200-750bb6b56bf4 |  | note | A minimum basin depth of 430mm
label | 9b884d75-3962-556d-a607-8de7e45060eb |  | note | Minimum circulation space as required by AS1428.1
label | bf2bda61-5eda-59d8-bcc2-64b28e9a3376 |  | note | Encroachment free knee and toe clearance space as per AS1428.1 under the basin for a minimum width of 850mm, centred on the basin.
label | 4bfdf94e-3816-59a5-99c6-0f2a056bca84 |  | note | Sensor type or lever style tapware has been provided to comply with AS1428.1 and located such that the operable part of lever tap handle and water source are within 300mm from edge of hand wash basin.
label | db237167-5ca0-5d89-87d9-a609b5bedbd7 |  | note | Refer to Figures 9(a) and 9(b) of the NDIS Specialist Disability Accommodation Design Standard
checkpoint-status |  |  | checkpoint | If providing a fixed bathtub, it is clear of the circulation space requirements of WC pan, shower and hand wash basin.
checkpoint-status |  |  | checkpoint | Slip resistance of all floors to sanitary facilities is a minimum of P3 or R10.
checkpoint-status |  |  | checkpoint | Except for walls constructed of masonry or concrete, the internal side of the full sanitary room with the required WC pan, shower, hand wash basin and fixed bathtub (if provided) has wall reinforcement of minimum 12mm thick sheeting, from FFL and extending to a height of minimum 2100mm from FFL.
checkpoint-status |  |  | checkpoint | The WC pan has an adjacent side wall (on at least one side of the WC pan) with a 600mm minimum length of wall reinforcement, forward of the WC pan. In designs where the near side wall adjacent to the WC pan includes a doorway (and the wall is not available on the other side of the WC pan) then a 600mm minimum length reinforced wall is clear of the door frame.
checkpoint-status |  |  | checkpoint | Sanitary Facilities Complete
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Kitchen
checkpoint-status |  |  | checkpoint | A kitchen has been provided with the following minimum fixtures: a fixed cooktop (with a rangehood), an in-built oven, a sink (with tap) and a dishwasher.
checkpoint-status |  |  | checkpoint | At least 1550mm clearance has been provided in front of fixed benches and appliances (being the leading edge of the outermost bench and not from the face of cupboards or the kickplate and excluding handles). Where the appliances are not installed the recessed area provision for an appliance is a minimum of 700mm in depth.
checkpoint-status |  |  | checkpoint | Task lighting has been provided above workspaces. A minimum level of 300 lux has been achieved when tested at maximum intervals of 1500mm, directly over the surface of the benchtops.
checkpoint-status |  |  | checkpoint | A wall oven has been provided with features as noted below:
label | 1886d68e-dfa1-5bec-9ba5-7f1a91ad77df |  | note | Side hinged door with latch side of door next to accessible benchtop.
label | 7e9e92b0-f3cd-5dfe-ad50-30ac2a17bdbb |  | note | At least a part of the operable part of oven door handle is located between 600mm and 1100mm above the FFL.
label | 9c072494-1062-5044-aca0-b4235070052e |  | note | At least one shelf on telescopic rails within the oven.
checkpoint-status |  |  | checkpoint | An accessible benchtop has been provided with features as noted below:
label | 11946f11-a0b2-534f-b15a-2f30c8dc0074 |  | note | A benchtop surface of minimum 600mm depth has been provided right next to the cooktop and wall oven (on the latch side of the oven door).
label | 0d5f087d-ffbc-5d25-999a-93d4fb279011 |  | note | This accessible benchtop provides a minimum space of 900mm (width) x 440mm (depth) clear of any fixtures other than what is permitted under knee / toe requirements of AS1428.1 under the benchtop.
checkpoint-status |  |  | checkpoint | One height-adjustable benchtop surface, of 600mm depth,has been provided with features as noted below:
label | 885f9bd0-130f-5466-8f98-bf9313ce739e |  | note | A minimum space of 900mm (width) x 440mm (depth) clear of any fixtures other than what is permitted under knee / toe requirements of AS1428.1 under the benchtop.
label | 53424977-d68d-578e-825a-54e36ae544e8 |  | note | Height adjustment capability from 720mm clear space underneath height adjustable benchtop till 1020mm clear space underneath height adjustable benchtop (from FFL).
checkpoint-status |  |  | checkpoint | Types of appropriate mechanisms for operation of kitchen cabinetry shall be one or more of the options as noted below:
label | 217b5dbd-2016-5eac-a7aa-db0fc5141c15 |  | note | D pull cupboard handles located towards the top of below-bench cupboards;
label | afd0d952-70b1-57d8-94c7-02078bee255a |  | note | D pull cupboard handles located towards the bottom of overhead cupboards;
label | 0364ed49-3c66-5efb-9402-5c8796328a83 |  | note | Overhanging lip of minimum 20mm for overhead cupboards;
label | 4add73aa-f71c-5e5b-9344-834c230048f3 |  | note | Push to release mechanisms for both overhead and below-bench cupboards.
checkpoint-status |  |  | checkpoint | A cooktop shall be provided with features as noted below:
label | ad2a8e20-e64c-538d-8d23-258e8601feb3 |  | note | Either electric or induction
label | 0554a32b-3753-5aab-b40d-3aec9335faf2 |  | note | Shall be located at least 300mm from any internal corner or wall, excluding the splashback.
checkpoint-status |  |  | checkpoint | The cooktop controls shall be on the side of the accessible benchtop or near the front edge of the benchtop.
checkpoint-status |  |  | checkpoint | Lever or sensor type tapware has been provided to sink to comply with AS1428.1 and is located such that the operable parts of the lever tap and water source is not more than 300mm from the edge of benchtop.
checkpoint-status |  |  | checkpoint | At least one double GPO has been provided within 300mm from the front edge of the benchtop (from the edge within the kitchen area) and max height of 1100mm from FFL. GPO shall be located adjacent to a bench of minimum 600mm depth.
checkpoint-status |  |  | checkpoint | Drawer style dishwasher has been provided.
checkpoint-status |  |  | checkpoint | A pantry has been provided which is wheelchair accessible.
checkpoint-status |  |  | checkpoint | Slip resistance of all kitchen flooring is a minimum of P3 or R10.
checkpoint-status |  |  | checkpoint | Kitchens Complete
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Laundry
checkpoint-status |  |  | checkpoint | A laundry has been provided with the following minimum fixtures: a sink or tub (with taps).
checkpoint-status |  |  | checkpoint | At least 1550mm clearance has been provided in front of fixed benches and appliances (being the leading edge of the outermost bench and not from the face of cupboards or the kickplate and excluding handles). Where the appliances are not installed the recessed area provision for an appliance has been a minimum of 700mm in depth.
checkpoint-status |  |  | checkpoint | Basins, sinks and tubs has been provided with sensor type or lever style tap. The tap is located such that the operable parts of the lever tap and water source is not more than 300mm from the edge of benchtop/ laundry tub trough / bench.
checkpoint-status |  |  | checkpoint | Slip resistance of all laundry flooring is a minimum of P3 or R10.
checkpoint-status |  |  | checkpoint | Laundry Complete
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Bedroom
checkpoint-status |  |  | checkpoint | Bedroom size shall allow for a minimum Queen bed of size 1530mm x 2100mm.
label | e729e964-4d56-55b8-b836-9b5a58552a45 |  | note | Circulation spaces around the three sides of the bed (not including bed head side) includes:
label | 2846545c-90a7-5fc4-9aba-2dddb42649fe |  | note | Space with minimum width of 1540mm on any one side on the bed;
label | 85a16d26-c2e7-5910-81de-16f111e4759a |  | note | Space with minimum width of 1000mm to the other two sides of the bed.
checkpoint-status |  |  | checkpoint | The following door circulation spaces for bedroom has been provided:
label | 74493824-479b-528b-a562-79048cad03bc |  | note | Internal door circulation space of the door to bedroom is a minimum of 1540mm (width) and 1450mm (depth), as shown in Figure 16. This internal door circulation space is clear of the Queen bed of size 1530mm x 2100mm.
label | acdf6ae6-7562-54f3-aef9-49c3503ef35b |  | note | External door circulation space is as per AS1428.1 based on the direction of approach or a minimum of 1200mm when measured from skirting to skirting (whichever is more).
checkpoint-status |  |  | checkpoint | A robe of 1400mm width has been provided within the bedroom, clear of the required bedroom size and with a minimum space of 1540mm in front of the robe.
checkpoint-status |  |  | checkpoint | Following GPOs has been provided:
label | ef193a3c-901e-5fc4-a43a-83fb24cc4cf3 |  | note | Three double GPO on the wall where the head of the bed is likely to be, and At least one double GPO on the wall opposite the wall where the head of the bed is likely to be.
checkpoint-status |  |  | checkpoint | Bedroom Complete
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Living area
checkpoint-status |  |  | checkpoint | The family/living room accommodates a free space, minimum 2250 mm in diameter, clear of furniture.
checkpoint-status |  |  | checkpoint | Living area Complete
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Switches and Powerpoints
checkpoint-status |  |  | checkpoint | Light switches are positioned in a consistent location:
label | 1c7909e9-27dd-5abe-8b2f-35d421dea1d2 |  | note | Between 900mm – 1000mm above the FFL, and Horizontally aligned with the door handle at the entrance to a room.
checkpoint-status |  |  | checkpoint | GPOs are installed between 600mm and 1100mm above the FFL.
checkpoint-status |  |  | checkpoint | Light and GPO switches are rocker action, toggle or push pad in design with a minimum width of 35mm.
checkpoint-status |  |  | checkpoint | Dimmable lighting switches are provided in living areas and bedrooms.
checkpoint-status |  |  | checkpoint | Switches and Powerpoints Complete
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Flooring and Slip Resistance
checkpoint-status |  |  | checkpoint | All internal flooring (including wet areas) are firm, even and feature a level transition between abutting surfaces of a maximum vertical tolerance of 3mm or 5mm (provided the lip is rounded or bevelled).
checkpoint-status |  |  | checkpoint | All internal floor finishes have a minimum slip resistance of P3 or R10.
checkpoint-status |  |  | checkpoint | Carpets if provided within the dwelling, are provided with pile height or thickness not more than 11mm and carpet backing not more than 4mm bringing the total height to a maximum of 15mm.
checkpoint-status |  |  | checkpoint | Flooring and Slip Resistance Complete
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Internal Stairways
checkpoint-status |  |  | checkpoint | Stairways within dwellings feature a continuous handrail on both sides of the stairway.
checkpoint-status |  |  | checkpoint | A minimum clear width of 1000mm has been provided; between the handrails and handrail profile and handrail extensions shall be as per AS1428.1.
checkpoint-status |  |  | checkpoint | Stairway have no winders on landings.
checkpoint-status |  |  | checkpoint | Stairway have closed risers.
checkpoint-status |  |  | checkpoint | The stairway provide slip resistance of P3 or R10.
checkpoint-status |  |  | checkpoint | Internal Stairways Complete
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Use of Lifts
checkpoint-status |  |  | checkpoint | Passenger lift if provided within a dwelling or for access to a dwelling is as permitted under the NCC Clause E3.6, excluding the use of stairway platform lifts.
checkpoint-status |  |  | checkpoint | Lift door to provide a minimum clear opening of 900mm.
checkpoint-status |  |  | checkpoint | The lift car size is a minimum 1100mm (width) x 1400mm (in direction of travel).
checkpoint-status |  |  | checkpoint | Use of Lifts Complete
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Common use external areas, private open space and landscaping
checkpoint-status |  |  | checkpoint | All common use external stairways comply with AS1428.1.
checkpoint-status |  |  | checkpoint | Where individual letter boxes have been provided then, they are:
label | a151def7-2db9-5c1f-afa7-4204c1ea9d4d |  | note | Situated on a hard-standing area of 1540mm x 2070mm and have a gradient and crossfall directly in front which is less than 1:40 in any direction.
label | 26d9bea9-07e9-51d6-ba3f-ee243527b94b |  | note | H wheelchair access by a continuous accessible path of travel from the dwelling to the letterbox, Are lockable, The height of the letterbox is between 600mm and 1100mm above FFL.
checkpoint-status |  |  | checkpoint | All ramps and accessways provided to all external common use and external private use areas comply with the requirements of ramps and accessways as noted in Clauses 2.4 to 2.12 as applicable to the various design categories.
checkpoint-status |  |  | checkpoint | Common use external areas, private open space and landscaping Complete
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Storage
checkpoint-status |  |  | checkpoint | A dwelling has been provided with a storage cupboard with a minimum 600mm width and adjustable shelf heights.
checkpoint-status |  |  | checkpoint | Storage Complete
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Ceiling Hoists
checkpoint-status |  |  | checkpoint | Bedrooms has a provision for power and inbuilt structure, capable of installation of a constant charge ceiling hoist. The hoist is capable of going across the bed and down the bed. Min load capacity of the hoist shall be 250kg. Hoist is capable of being either ceiling mounted or wall mounted.
checkpoint-status |  |  | checkpoint | Evidence / Certification document has been provided for the building structure to be able to provide for a ceiling hoist in the future:
label | ae9f3d37-b400-525e-922d-9d96a3fa7c1f |  | note | For design stage assessments, the notation of the requirements on the assessed drawings or specifications is adequate.
label | ebe035b1-12fc-517e-83c9-d96fe978e6b8 |  | note | For final-as-built stage of SDA certification, the structure has been inspected and certified by a qualified structural engineer as being suitable for ceiling hoists with minimum load capacity of 250kg.
checkpoint-status |  |  | checkpoint | Ceiling Hoists Complete
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Heating and Cooling
checkpoint-status |  |  | checkpoint | Reverse cycle air-conditioning has been provided to living areas and bedrooms with control panels in an accessible location between 900mm and 1100mm from FFL and not closer than 500mm to any internal corner.
checkpoint-status |  |  | checkpoint | Where ducted air-conditioning is used, zoning of habitable rooms shall be provided.
checkpoint-status |  |  | checkpoint | Heating and Cooling Complete
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Emergency Power Solutions
checkpoint-status |  |  | checkpoint | Emergency power solutions shall be provided to cater for a minimum 2-hour outage in no less than 2 double GPOs in participant bedrooms and any provided automated doors that are used for entry or egress.
checkpoint-status |  |  | checkpoint | Emergency Power Solutions Complete
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Assistive Technology
checkpoint-status |  |  | checkpoint | Internet connection has been provided with the ability for high internet speeds to be maintained and stable in nature with wi-fi coverage throughout all areas of the dwelling.
checkpoint-status |  |  | checkpoint | A video, intercom or other communication system has been provided to enable communication between the participant and their supports when not within line of sight.
checkpoint-status |  |  | checkpoint | Assistive Technology Complete
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Fire Safe Design
checkpoint-status |  |  | checkpoint | Smoke alarms that are in keeping with a home environment has been provided in bedrooms and living spaces.
checkpoint-status |  |  | checkpoint | Emergency evacuation plan has been provided to the occupier or their supports, which may include a path of travel to a safe place.
holdpoint |  |  | signoff | HOLD POINT
checklist-flat |  |  | checklist | Bulk Excavation |  |  |  |  | Yes | Bulk Excavation | 33369d76-04b0-4a78-81a1-fc858b9102ef
checkpoint-status |  |  | checkpoint | Confirm dial before you dig documents are onsite - If applicable and attached below
checkpoint-status |  |  | checkpoint | Confirm correct disposal of classified material
checkpoint-status |  |  | checkpoint | Obtain geotech report, including load bearing capacity
label | 86439ea8-4d78-54b1-978a-8e63a292c34f |  | note | Geotech report referenced or attached below
checkpoint-status |  |  | checkpoint | Collection of tip dockets - If applicable and attached below
checkpoint-status |  |  | checkpoint | Confirm set out off boundaries & marked out
checkpoint-status |  |  | checkpoint | Confirm Bulk RL is within detailed excavation zones/limits
checkpoint-status |  |  | checkpoint | Civil engineer inspection carried out - Attached below as applicable
checkpoint-status |  |  | checkpoint | Attach Subcontractor ITP - Attached below as applicable
button | 65273839-5817-56c9-9e7a-12c75ff81bcd |  | button | Subcontractor Sign Off | Yes, No, N/A
button | 82cd7c0a-7afd-5c68-9969-3ac82944c6a4 |  | button | Aland Sign Off | Yes, No, N/A
holdpoint |  |  | signoff | Click to add Sign-Off Signatures
checklist-flat |  |  | checklist | Garbage Room (V90421) |  |  |  |  | Yes | Garbage Room (V90421) | 33528c2b-9a20-4064-a77a-59ce6b32e199
checkpoint-status |  |  | checkpoint | Coving perimeter of the floor
checkpoint-status |  |  | checkpoint | Epoxy floor and wall up to 15m high
checkpoint-status |  |  | checkpoint | Hot & Cold water taps installed
checkpoint-status |  |  | checkpoint | Check for need of hot water tank
checkpoint-status |  |  | checkpoint | All PVC piping to be fire checked
checkpoint-status |  |  | checkpoint | Garbage room exhaust fan installed correctly
checkpoint-status |  |  | checkpoint | Garbage room overhead lighting installed
checkpoint-status |  |  | checkpoint | Signage is clearly installed
checkpoint-status |  |  | checkpoint | Magnetic door holder fitted and functioning correctly on all entry / exit doors
checkpoint-status |  |  | checkpoint | Final sign off - All garbage room work completed as per the above ITP - Add general photos/comments below
label | fdb2fc92-e2b0-5ac3-a255-e40fa225f597 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Plumbing Rough-In |  |  |  |  | Yes | Plumbing Rough-In | 3616db28-d1c1-44cf-9193-3db12bc31ec6
checkpoint-status |  |  | checkpoint | Floor wastes checked - Any issues comment/photo below
checkpoint-status |  |  | checkpoint | 1m offset to floor height has been achieved
checkpoint-status |  |  | checkpoint | Mixers are in correct position (hole allowance to work with tiles)
checkpoint-status |  |  | checkpoint | All wall hung items have been allowed for in setout
checkpoint-status |  |  | checkpoint | All rough-in pipework is colour coded to ensure no cross connections
checkpoint-status |  |  | checkpoint | All poly pipes located in framing to ensure no screw fixings will penetrate them
checkpoint-status |  |  | checkpoint | All Water & Gas risers are complete
checkpoint-status |  |  | checkpoint | All stacks are level/plumb
checkpoint-status |  |  | checkpoint | Ensure all services that go through fire rated walls to be treated with collars/fire rated sealant
checkpoint-status |  |  | checkpoint | Pipework tested
checkpoint-status |  |  | checkpoint | Ensure rough in has been done as per specs
checkpoint-status |  |  | checkpoint | Ensure dummy fit‐out has been done
checkpoint-status |  |  | checkpoint | Final sign off - All plumbing work completed as per the above ITP
checklist-sectioned |  |  | checklist | In-Ground Sewer ITP (V140421) |  |  |  |  | Yes | In-Ground Sewer ITP (V140421) | 36af0a2d-9f12-4ec6-a73a-52fe023d7c73
checkpoint-group |  |  | section | Pits and Pipes
checkpoint-status |  |  | checkpoint | Is Approval from Local Water Authority Required If so please provide permit
holdpoint |  |  | signoff | Sign Off Required
checkpoint-status |  |  | checkpoint | Details
text | 3ccbfcaf-3f19-55b5-9e4c-e614ba8a360e |  | textbox | Engineering plan number(s)
text | 8846502d-e599-5329-9ba2-c4564ee60480 |  | textbox | Name of certified drainlayer
text | 4beb8833-601b-5a30-bd23-fe7b34eec789 |  | textbox | Location (pit to pit)
text | 01c37e4c-cb11-574e-b35d-a34bade5424f |  | textbox | Delivery Date (Pits and Pipes)
text | ea087054-07a6-5c6b-9ecd-454ecac943e6 |  | textbox | Is work area clear and available for construction
text | c353ceb1-9576-54dd-919b-0a5407850d83 |  | textbox | Do you have the appropriate plant / equitment to perform scope of works Provide details
checkpoint-group |  |  | section | Trench / Excavation Methodology
checkpoint-status |  |  | checkpoint | Method
boolean | 1b3c5389-dd7d-5e41-bbce-e9670c7ad075 |  | tickbox | Shield
boolean | 21b4c5fd-3394-5a5d-884f-2b9043ac1d63 |  | tickbox | Bench
boolean | 1827f2af-6d09-5735-be4c-2778ceac76db |  | tickbox | Batter
boolean | a937cdac-3358-5e51-9812-6929d8297916 |  | tickbox | Other
text | 283ea4ce-3668-50fd-89fe-72ed2729938f |  | textbox | If other, please specify
boolean | 19e3c7b8-0475-5101-83c0-498a690f8042 |  | tickbox | Certified / Tagged lifting Equitment
checkpoint-group |  |  | section | Product / Material check
checkpoint-status |  |  | checkpoint | Pits
text | d1962869-f976-5c46-9451-8961dfafaf39 |  | textbox | Type
text | dc82c8a6-f565-5607-aac5-8f0315e915bf |  | textbox | Size
checkpoint-status |  |  | checkpoint | Pipes
text | cd71a23e-9391-5d88-85b0-0e8ee4172103 |  | textbox | Type
text | 44e71476-44b5-5395-9521-dc5a48427db0 |  | textbox | Size
checkpoint-status |  |  | checkpoint | Lot / Building Connections
text | 00eee599-9418-516d-9909-a9a32ac10ff1 |  | textbox | Type
text | f02945f6-5821-5c9b-a9f4-6034327dcd7f |  | textbox | Lot number location
checkpoint-status |  |  | checkpoint | Bends
text | 16098d01-8447-502d-bb80-0838449ccf53 |  | textbox | Type
text | 73671efd-0e21-5a24-8c90-ff0385a36883 |  | textbox | Size
text | e2032a13-5186-5687-9170-c012ebcfbaf0 |  | textbox | Location
checkpoint-status |  |  | checkpoint | Quality Onsite Visual Inpection of Products/Materials - Defects to be Notified
text | ae85ef95-04b7-5cec-9425-7753730005b4 |  | textbox | Surveyors name
checkpoint-status |  |  | checkpoint | Set out / Off Set Check
holdpoint |  |  | signoff | Sign Off Required
checkpoint-group |  |  | section | Pit Installation
checkpoint-status |  |  | checkpoint | Pits
text | 780670b1-0d28-51d1-a231-3336526599c3 |  | textbox | Bedding and backfill type as per detail
text | 4ecfd557-640b-5f37-985a-5853dc4f4f2f |  | textbox | If under cutting required, note metreage and depth ( Approval Required)
boolean | 3f808fb5-4108-5ea0-86db-621f1f7408c0 |  | tickbox | Backfill to be compacted in 150mm Layers as per detail
boolean | d6260f49-e379-563a-8fb1-882114324485 |  | tickbox | External Concrete Bandage
boolean | b4901173-e360-5eee-8ee5-ed67a7c4226e |  | tickbox | Internal Benching
boolean | de2ca51c-f784-5665-8d16-3f93270728f6 |  | tickbox | Internal Plastering / Render / Sealent
boolean | cfc9f160-eb22-5dbd-92a4-3107cf21b318 |  | tickbox | Sealant Between Riser
boolean | 2b317290-6a15-5989-9fde-61f3008d9655 |  | tickbox | Steps Required
text | 66cc5141-0626-5ba3-9593-7e16d1b61e80 |  | textbox | Have pits been secured and covered through the construction phase to elemenate debris/silt
text | 3532c108-76dd-59e8-87b7-09c2a57e9205 |  | textbox | Pressure testing
checkpoint-status |  |  | checkpoint | Pipe invert levels through pit as per design
holdpoint |  |  | signoff | Sign Off Required
checkpoint-group |  |  | section | Pipe Installation
checkpoint-status |  |  | checkpoint | Pipes
text | 9309b47f-9129-556d-89b0-82f980aa5736 |  | textbox | Are pipes free and clean of debris before installation
text | 12c071c6-c279-57e2-bc27-eac983c5f179 |  | textbox | Bedding and backfill type as per detail
text | 02c1199d-4ead-5bcc-9e85-58dcae86f754 |  | textbox | If under cutting required, note metreage and depth ( Approval Required)
boolean | 1c877e6d-f8ee-5b50-b0f4-34a5d4e03fe9 |  | tickbox | Backfill to be compacted in 150mm Layers as per detail
checkpoint-group |  |  | section | Drainage Check
checkpoint-status |  |  | checkpoint | Backfill to be compacted in 150mm Layers as per detail
text | bd8f25c1-97fb-50dc-b12c-7790a8d954ac |  | textbox | Grade and Alignment Check
text | 0b98479c-f63b-5fb4-8738-4bb852a46982 |  | textbox | As-built measurements / Pick up Recorded Before Backfilling
text | f562b9ec-86ba-525c-9d30-78b5281d97da |  | textbox | Invert/ RL check
text | 237efe68-e874-50e6-8317-40f12faa366c |  | textbox | Pressure Testing
text | 3553c3f6-927a-515a-adf4-f38d8668ef65 |  | textbox | CCTV Pipe Inspection / data and comments supplied
checkpoint-status |  |  | checkpoint | Progress Photos
checkpoint-group |  |  | section | Service Connections
checkpoint-status |  |  | checkpoint | All Connections, Bends, Junctions installed
text | 6985ace6-7609-55c5-b1fd-94670afb88db |  | textbox | As-built measurements / Pick up Recorded Before Backfilling
holdpoint |  |  | signoff | Sign Off Required
checklist-flat |  |  | checklist | Cold Water Pump Room |  |  |  |  | Yes | Cold Water Pump Room | 3d0a5b51-be8b-4bfc-ba4e-3ce6c28a8b03
checkpoint-status |  |  | checkpoint | Ensure cold water pumps are installed as per plans
checkpoint-status |  |  | checkpoint | Pump isolation valves installed on all pumps
checkpoint-status |  |  | checkpoint | All pipe work tested to min 1200 kpa
checkpoint-status |  |  | checkpoint | Switchboards in place using suitable fixings to match mounting service No damage to external board has occurred during installation
button | ea1dd681-9809-5134-8331-0e9e83c43342 |  | button | Ensure adequate pathways exist within board to accommodate all circuits and allow for future expansion | Yes, No
button | cb5a7e58-9a10-563e-98ea-13277f72a0a0 |  | button | Install and loom in all circuits into correct cabinets | Yes, No
button | d13801cc-b0e1-5df5-9ec1-c0dcc22d66c0 |  | button | Ensure cable labels match switchboard schedule and construction drawings | Yes, No
button | 9063b643-e088-589b-977f-06c09a97b708 |  | button | Cables are labelled as per specified requirements | Yes, No
button | 7e33d653-440c-5c0d-9287-8f145c375638 |  | button | Check all tightness of all terminals on all breakers and bars | Yes, No
button | 1a059678-e5ed-5053-ac2f-61bd99b102ff |  | button | Ensure safety signage is installed and visible as per plans | Yes, No
checkpoint-status |  |  | checkpoint | Final sign off - Cold water pumps installed as per the above ITP - Add general photos/comments below
label | 8993bbe9-c764-5076-af7a-93ca945a9f9d |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Post Wall Linings |  |  |  |  | Yes | Post Wall Linings | 4411f321-6e9c-4f56-9002-8d221a1ceb53
checkpoint-status |  |  | checkpoint | Insulation has been installed
checkpoint-status |  |  | checkpoint | Insulation has been installed snug between framing members with no gaps
checkpoint-status |  |  | checkpoint | Fire rated walls have been sheeted to the ceiling
checkpoint-status |  |  | checkpoint | Fire rated walls have been fire caulked
checkpoint-status |  |  | checkpoint | Bathroom walls & ceilings have been sheeted with blue watercheck plasterboard
checkpoint-status |  |  | checkpoint | Bathroom's sheeted - Set to the floor to allow for good waterproofing junction
checkpoint-status |  |  | checkpoint | Ensure MSDS & installation guide has been followed
checkpoint-status |  |  | checkpoint | Final sign off - All post wall work completed as per the above ITP
label | 56aeab57-a8d1-594a-9d62-2f4194ed724b |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Building Authority Checklist |  |  |  |  | Yes | Building Authority Checklist | 46828ef8-eeec-4d78-94fb-5108f9bf8dc0
checkpoint-status |  |  | checkpoint | Ensure all Aland documentation is registered with the council - Atatched below
checkpoint-status |  |  | checkpoint | Electrical Compliance Documentation reviewed and attached
checkpoint-status |  |  | checkpoint | Hydraulic Compliance Documentation reviewed and attached
checkpoint-status |  |  | checkpoint | Mechanial Compliance Documentation reviewed and attached
checkpoint-status |  |  | checkpoint | Fire Services Compliance Documentation reviewed and attached
checkpoint-status |  |  | checkpoint | Lifts Compliance Documentation reviewed and attached
checklist-flat |  |  | checklist | Basement Tanking |  |  |  |  | Yes | Basement Tanking | 4883a5bf-f60e-4028-859b-bea27cdb6f13
checkpoint-status |  |  | checkpoint | PE film installed towards substrate, grey side facing installer (Blanket).
checkpoint-status |  |  | checkpoint | Overlap of 100-200mm at ends has been installed.
checkpoint-status |  |  | checkpoint | Substrate clean, dry & free from dust
checkpoint-status |  |  | checkpoint | Bentoseal Paste has been used to seal all penetrations.
checkpoint-status |  |  | checkpoint | Termination of membrane as per manufacturer's details.
checkpoint-status |  |  | checkpoint | Waterstop RX-101 at vertical spray break with 75mm cover has been
checkpoint-status |  |  | checkpoint | Installation of CETCO granules to perimeter floor/wall junctions.
checkpoint-status |  |  | checkpoint | Installation of RX101 to manufacturer's details using Cetseal Bead to secure to substrate.
checkpoint-status |  |  | checkpoint | Transition Sheet installed as per manufacturer's recommendations.
checkpoint-status |  |  | checkpoint | Installation of RX101 to perimeter of pile cap, using CetSeal follows manufacturer's recommendations
checkpoint-status |  |  | checkpoint | Detailing of blanket to perimeter of pile caps as per manufacturer's recommendations.
checkpoint-status |  |  | checkpoint | All Construction joints are cleaned out and ready for membrane Application
checkpoint-status |  |  | checkpoint | All Membrane Application is completed in accordance with CETCO Detail / ALAND SIGN OFF
checklist-sectioned |  |  | checklist | Courtyard Surfaces ITP |  |  |  |  | Yes | Courtyard Surfaces ITP | 4f5357bc-b764-430b-9f00-b337852ba3ed
checkpoint-group |  |  | section | Waterproofing
checkpoint-status |  |  | checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
checkpoint-status |  |  | checkpoint | Setout & alignment as per drawing (include revision below)
text | 85baf17d-ee99-564b-85c2-350dc97ade37 |  | textbox | Drawing & revision number(s)
checkpoint-status |  |  | checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application "No access waterproofing work in progress"
label | 708479fe-eb59-53b7-a5fe-041fd44df4ef |  | note | Attach relevant photos below
button | 7f46b9d3-b899-5309-a529-59d93d380720 |  | button | Membrane system & methodology checked off AGainst Aland standard | Yes, No
button | ab684fb9-ed6e-52d3-a4a4-59270da133c4 |  | button | Surface preparation as per application guide | Yes, No
checkpoint-status |  |  | checkpoint | Substrate clean, dry & free from dust
button | 26d367f6-cf20-5c12-b669-50bfc81026e7 |  | button | Ensure no high points or crevices are in the substrate | Yes, No
button | 3aa84b0c-85fe-5f5d-9545-a6cef2394e64 |  | button | Ensure substrate is structurally sound & ready to receive membrane | Yes, No
button | 92000e74-afef-5d4f-b538-d7290bfcd3a1 |  | button | Ensure humidity, temperature & moisture are in accordance with manufacturer's recommendations prior to primer | Yes, No
label | d2ca5592-1871-5fc6-92a5-d3cb75bee36f |  | note | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint-status |  |  | checkpoint | Ensure all floor wastes & pipes have been primed in accordance with manufacturer's recommendations
label | aaab720d-5f45-5836-8652-0e406928b14b |  | note | (PrimeSeal MC to all surfaces at a rate of 3‐4m2/Ltr ‐Alternative primers Multiseal ‐ Primeseal SP at a rate of 5‐8 m2/Ltr)
checkpoint-status |  |  | checkpoint | All corners, joints, gaps & cracks to be treated with a flexible polyurethane sealant resiflex FC
label | 19aac668-50e8-58fe-8279-c93d9ce6fe7f |  | note | Apply selected Membrane as per datasheet & application guidelines Ensure sealant has fully cured before installing membrane
checkpoint-status |  |  | checkpoint | Ensure Humidity, temperature & moisture are in accordance with manufacturer's recommendations prior to first coat
checkpoint-status |  |  | checkpoint | First coat of selected Membrane to entire areas as per DURAM recommendations
label | 0489b809-a2d4-563e-9712-b461eb26790d |  | note | Note A total dry film thickness of min 12mm (1200 microns) in two finished coats As such at min
label | 1cabcc3f-b8da-500a-9e1f-d271c571829a |  | note | Wet Film Thickness of min 075mm (750 microns) per coat is required ‐ Apply membrane at a coverage of 075 ‐ 1 Ltr / m2 per coat
button | 2a12a076-cb23-5b23-b82c-2435718e581d |  | button | Allowing the membrane coat to dry min 12 hours check the tackiness before applying next coat | Yes, No
button | 60a24d70-1497-5f41-88bf-7eec66d00661 |  | button | Ensure humidity, temperature & moisture are in accordance with manufacturer's recommendations prior to second coat | Yes, No
checkpoint-status |  |  | checkpoint | Second coat of selected Membrane to entire areas as per DURAM recommendations
label | 38f2ef59-3bd1-50af-8448-060ca66fbf32 |  | note | Note ‐ a total dry film thickness of min 12mm (1200 microns) in two finished coats As such at min
label | dd085a5d-2adc-5af9-9360-c7aede06873a |  | note | Wet Film Thickness of min 075mm (750 microns) per coat is required ‐ Apply membrane at a coverage of 075 ‐ 1 Ltr / m2 per coat
button | a4c0291a-ded6-523e-83dc-72331b8ae4c3 |  | button | The membrane is to be applied in a minimum of 2 coats at a total coverage of 12 to 2 litres per m2 or relevant product TDS 12 to 2 litres per m2 or relevant product TDS | Yes, No
button | a8657357-5701-5c3b-be1a-573932dc66fd |  | button | Allow 2nd coat of Multithane UV min 12 hours but no longer than 24 hours before installing Multithane ATC top coat | Yes, No
button | 8ee12f94-3d71-5b74-9b85-e05438b2e29d |  | button | Ensure humidity, temperature & moisture are in accordance with manufacturer's recommendations prior to final coat | Yes, No
checkpoint-status |  |  | checkpoint | Apply final coat of Multithane ATC at a coverage rate of 3 ‐ 4 m2/ltr
checkpoint-status |  |  | checkpoint | Carry out dry film thickness test using positector coating thickness inspection instrument
checkpoint-status |  |  | checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
label | 5fc1968f-80b3-536a-8bd1-fc0d16813a9d |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checkpoint-group |  |  | section | Surface Finish & Sign Off
checkpoint-status |  |  | checkpoint | Wastes installed correctly to specification (Correct height / level/ location)
boolean | 26b06ba7-4f0f-58bd-b4e9-79e84069a220 |  | tickbox | Waterproofer pushes sponge down 100mm and finishes his membrane & flood test
boolean | 9832bc5a-bf15-50b3-99d5-96537b4fd778 |  | tickbox | Waterproofer removes sponge and releases water and puts the sponge back in ensuring there are no debris left in the pipe
boolean | d4a72cea-1ffd-53c3-bef7-e29a670d30f0 |  | tickbox | Aland cleans and removes the sponge
checkpoint-status |  |  | checkpoint | Waterproofing membrane completed and ready for Pebble Washed Aggregate topper
checkpoint-status |  |  | checkpoint | Pebble surface installed to specification(s) - Correct level and finish
label | 2f039635-22fc-5305-9945-fafd2baf16c1 |  | note | Attach photos /comments below
checkpoint-status |  |  | checkpoint | Final Sign Off - All courtyard works completed to specification and as per above ITP
label | 6bca1e49-baab-521b-a6f0-18c7659161b9 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Car Wash Bay |  |  |  |  | Yes | Car Wash Bay | 524af7d9-f5fc-4b41-87bb-68b9f90acd6b
checkpoint-status |  |  | checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
checkpoint-status |  |  | checkpoint | Setout & alignment as per drawing (include revision below)
text | e97590a3-32e1-5508-b528-81aae7c95767 |  | textbox | Drawing & revision number(s)
checkpoint-status |  |  | checkpoint | Car wash bay installed as per manufacturer's instructions & standards
checkpoint-status |  |  | checkpoint | Car wash bay tested as per manufacturer's instructions & standards
checkpoint-status |  |  | checkpoint | Car wash bay commissioned as per manufacturer's instructions & standards
checkpoint-status |  |  | checkpoint | Final sign off - Car wash bay installed as per the above ITP - Add general photos/comments below
label | ec81b372-eac9-55d7-8edc-9addb6bdb6eb |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | General Waterproofing |  |  |  |  | Yes | General Waterproofing | 54ed34e4-45bb-4b8c-a581-513bd61798c3
checkpoint-status |  |  | checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application "No access waterproofing work in progress"
label | 402e0714-cc1a-5cac-a5a3-30139a2ba291 |  | note | Attach relevant photos below
button | 19c6a676-121b-5f34-92b9-2ea16498b59f |  | button | Membrane system & methodology checked off AGainst Aland standard | Yes, No
button | 24426ad8-551c-5a30-a163-d5578ec6c98c |  | button | Surface preparation as per application guide | Yes, No
checkpoint-status |  |  | checkpoint | Substrate clean, dry & free from dust
button | 1c51297e-115f-5356-ac74-8c47c677c09d |  | button | Ensure no high points or crevices are in the substrate | Yes, No
button | a29198a8-289c-5dc7-9315-e1c151c6c780 |  | button | Ensure substrate is structurally sound & ready to receive membrane | Yes, No
button | f9aa0798-e60e-5ee6-91c2-cc5f479b6cb0 |  | button | Ensure humidity, temperature & moisture are in accordance with manufacturer's recommendations prior to primer | Yes, No
label | 8903894f-1fa6-55f8-8f9a-449b8eb34f1b |  | note | HOLDPOINT - Do not proceed if above has not been signed off
checkpoint-status |  |  | checkpoint | Ensure all floor wastes & pipes have been primed in accordance with manufacturer's recommendations
label | 3b41e2d0-be58-516d-b364-15406a7f3ca6 |  | note | (PrimeSeal MC to all surfaces at a rate of 3‐4m2/Ltr ‐Alternative primers Multiseal ‐ Primeseal SP at a rate of 5‐8 m2/Ltr)
checkpoint-status |  |  | checkpoint | All corners, joints, gaps & cracks to be treated with a flexible polyurethane sealant resiflex FC
label | 1f3a47e8-320a-5bcf-aa14-4a799e0e8459 |  | note | Apply selected Membrane as per datasheet & application guidelines. Ensure sealant has fully cured before installing membrane
checkpoint-status |  |  | checkpoint | Ensure Humidity, temperature & moisture are in accordance with manufacturer's recommendations prior to first coat
checkpoint-status |  |  | checkpoint | First coat of selected Membrane to entire areas as per DURAM recommendations
label | 43068084-aa77-5eef-925e-b7f8d45fe7b3 |  | note | Note: A total dry film thickness of min 1.2mm (1200 microns) in two finished coats. As such at min
label | 4243013a-9247-55d2-8bc5-c966b720b8c8 |  | note | Wet Film Thickness of min 0.75mm (750 microns) per coat is required ‐ Apply membrane at a coverage of 0.75 ‐ 1 Ltr / m2 per coat
button | e6fd09b5-26ea-5120-9b96-e8a1d950ad59 |  | button | Allowing the membrane coat to dry min 12 hours check the tackiness before applying next coat | Yes, No
button | 2fd6eb48-6fb8-58ad-a5b9-d652421f3b0e |  | button | Ensure humidity, temperature & moisture are in accordance with manufacturer's recommendations prior to second coat | Yes, No
checkpoint-status |  |  | checkpoint | Second coat of selected Membrane to entire areas as per DURAM recommendations
label | 3be521cd-d3ee-5cb3-9335-66051dcd37ab |  | note | Note ‐ a total dry film thickness of min 1.2mm (1200 microns) in two finished coats. As such at min
label | 6174f1fe-c103-5835-ae3f-f5d4334d1565 |  | note | Wet Film Thickness of min 0.75mm (750 microns) per coat is required ‐ Apply membrane at a coverage of 0.75 ‐ 1 Ltr / m2 per coat
button | dae2b83b-6c11-5da0-af25-130036344c8b |  | button | The membrane is to be applied in a minimum of 2 coats at a total coverage of 1.2 to 2 litres per m2. or relevant product TDS 1.2 to 2 litres per m2. or relevant product TDS | Yes, No
button | dc6d951e-7d69-51e3-95a0-d5da79e7ef6e |  | button | Allow 2nd coat of Multithane UV min. 12 hours but no longer than 24 hours before installing Multithane ATC top coat | Yes, No
button | 6bfa4ec5-cd4e-520a-9285-51a694af7045 |  | button | Ensure humidity, temperature & moisture are in accordance with manufacturer's recommendations prior to final coat | Yes, No
checkpoint-status |  |  | checkpoint | Apply final coat of Multithane ATC at a coverage rate of 3 ‐ 4 m2/ltr
checkpoint-status |  |  | checkpoint | Carry out dry film thickness test using positector coating thickness inspection instrument
checkpoint-status |  |  | checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
label | bb20ea45-be04-5eef-acde-f6aa6e942c99 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Grease Arrestor Room (v040521) |  |  |  |  | Yes | Grease Arrestor Room (v040521) | 563cd798-061b-443d-9935-cfa8b0048af8
checkpoint-status |  |  | checkpoint | Ensure grease arrestors are installed as per plans
checkpoint-status |  |  | checkpoint | Isolation valves installed on all grease arrestors
checkpoint-status |  |  | checkpoint | Switchboards in place using suitable fixings to match mounting service, no damage to external board has occurred during installation
button | b8e5a085-193b-55f4-8ede-a0cc5dc7a847 |  | button | Ensure adequate pathways exist within board to accommodate all circuits and allow for future expansion | Yes, No
button | f80ed013-12c8-5976-84f0-5b340826d6b1 |  | button | Install and loom in all circuits into correct cabinets | Yes, No
button | d62f3bd5-df3a-5c75-8ce3-d16de14d3745 |  | button | Ensure cable labels match switchboard schedule and construction drawings | Yes, No
button | af7fc247-e513-5fdf-9501-8f792fc427b5 |  | button | Cables are labelled as per specified requirements | Yes, No
button | 14a6f669-c18c-51d8-951c-8c2307f8b9f8 |  | button | Check all tightness of all terminals on all breakers and bars | Yes, No
button | 88de5297-bd44-5819-80d2-fa44b2df073b |  | button | Ensure safety signage is installed and visible as per plans | Yes, No
checkpoint-status |  |  | checkpoint | Ensure adequate ventilation fans have been installed and are functioning correctly
checkpoint-status |  |  | checkpoint | Final sign off - Grease arrestors installed as per the above ITP - Add general photos/comments below
label | f3708f49-e941-505f-be45-dca99685edce |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Driveways /Footpaths /Hard surfaces |  |  |  |  | Yes | Driveways /Footpaths /Hard surfaces | 5ec5826e-dfcc-4c7a-92a1-0f49dd3d8bfc
checkpoint-status |  |  | checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
checkpoint-status |  |  | checkpoint | Setout & alignment as per drawing (include revision below)
text | ab5ccc41-f84e-50a8-8fe5-a803a4ebdb32 |  | textbox | Drawing & revision number(s)
checkpoint-status |  |  | checkpoint | All Surfaces have been poured as per specifications
checkpoint-status |  |  | checkpoint | All Surfaces are at the correct level/falls as per specifications
checkpoint-status |  |  | checkpoint | All Surfaces finishes are to specification
checkpoint-status |  |  | checkpoint | Final sign off - Driveways has been completed as per the above ITP - Add general photos/comments below
label | 2a40330b-91e1-515e-8408-55a8360686c5 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Water Connection |  |  |  |  | Yes | Water Connection | 63d59745-8f3e-4fd1-b740-69e5c8ca836f
checkpoint-status |  |  | checkpoint | Water has been installed throughout complex
checkpoint-status |  |  | checkpoint | Water has been tested throughout complex
checkpoint-status |  |  | checkpoint | All documentation for water install has been reviewed & documented by Aland
checkpoint-status |  |  | checkpoint | Final sign off - Water has been tested & installed as per the above ITP - Add general photos/comments below
label | 8ef97bd7-7c07-5af4-99d7-5f323e3866b6 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Jump Form |  |  |  |  | Yes | _TEMP - Jump Form | 66a2bd4b-ca6c-4d3e-8907-14a528f8cbcd
checkpoint-status |  |  | checkpoint | Confirm Class of formwork to all faces, as per the latest specifications
checkpoint-status |  |  | checkpoint | Confirm RL's of soffit & beams
checkpoint-status |  |  | checkpoint | Confirm any penetration sizing for any hoist/crane penetrations
checkpoint-status |  |  | checkpoint | Ensure formwork frames installed to enable clear & labelled access under deck for other personnel & for inspections
checkpoint-status |  |  | checkpoint | Ensure all formwork surfaces are cleaned & no rubbish remains on any soffits,sides,base of work
checkpoint-status |  |  | checkpoint | Ensure bases of all columns/walls are cleaned out prior to pouring
checkpoint-status |  |  | checkpoint | Check formwork is completed as per specified Class
checkpoint-status |  |  | checkpoint | Ensure no rubbish or excess water is present prior to concrete pour
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checkpoint-status |  |  | checkpoint | Formwork stripped in a safe manner
checkpoint-status |  |  | checkpoint | All timbers de - nailed
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 1 day, and attach test results
text | 1a6e363e-1187-54ac-940f-877a607bdc59 |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Confirm initial stress is conducted day after the pour, after concrete has reached 10MPa on 1 Day results
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 4 day, and attach test results
text | 20370f6b-0edc-5079-88dc-d5b3353aa343 |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Confirm final stress has occurred after concrete has reached 20MPa, and attach Stressing Records
label | 5152d4ad-2afc-5b77-af8a-1feef3f6157f |  | note | Attached below as applicable
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 7 day, and attach test results
text | bfebb350-02e1-53ca-a1f5-43a0264c32f0 |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 28 day, and attach test results
text | 3287da17-e572-5b31-a63a-79e816053701 |  | textbox | Test Strength Mpa
checklist-sectioned |  |  | checklist | Suspended Slab - FULL (V140421) |  |  |  |  | Yes | Suspended Slab - FULL (V140421) | 67d186b9-b95d-4d90-b816-4509272ec113
checkpoint-group |  |  | section | Prior to Deck Handover
checkpoint-status |  |  | checkpoint | Confirm deck is safe, handrails installed and edge protection is provided to full perimeter of deck
checkpoint-status |  |  | checkpoint | Confirm means of access to deck
checkpoint-status |  |  | checkpoint | Confirm Formworkers Deck Handover Certificate and ITP is received and sighted
label | ce2a81ab-b104-5ed6-9ca7-5ed5e0582048 |  | note | Attached below as applicable
button | 5c56c4d1-0458-5547-bd4c-d115c7b8887b |  | button | Attach Deck Handover Certificate | Yes, No, N/A
checkpoint-group |  |  | section | Prior to Concrete Pour
checkpoint-status |  |  | checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
checkpoint-status |  |  | checkpoint | Setout & alignment as per drawing (include revision below)
text | 0baf93ff-31cf-5e7b-a348-4e6dbb001c34 |  | textbox | Drawing & revision number(s)
checkpoint-status |  |  | checkpoint | Materials used complies with design documentation
checkpoint-status |  |  | checkpoint | Datum point used & soffit RLs checked
checkpoint-status |  |  | checkpoint | Grids marked by builder
checkpoint-status |  |  | checkpoint | Confirm As-Built Survey of deck is complete
label | aa5810a6-a8aa-57b9-a6b3-0e587da00f7f |  | note | HOLD POINT - Attach As-Built Survey of Deck
checkpoint-status |  |  | checkpoint | Confirm Form Worker has received As-Built Survey of deck, and has rectified errors prior to any trades commencing on deck
checkpoint-status |  |  | checkpoint | Confirm all beams and decks constructed as per Structural Concrete Profiles
checkpoint-status |  |  | checkpoint | Install slip joints to all load bearing walls and corbels where required
checkpoint-status |  |  | checkpoint | Clean off decks and beams prior to pour, and ensure all exposed off-form soffits are free of any dust, stains and rust marks Hose down if necessary
checkpoint-status |  |  | checkpoint | Check if concrete has falls, and ensure shutters, timbers, spacers are used to create folds where necessary Cross-check the following drawings
boolean | c5d3b216-076d-584a-9130-c401bf913f1c |  | tickbox | Hydraulic Drawings
boolean | 340c9d42-5d51-51ff-95fe-6c93468ce98f |  | tickbox | Architectural Concrete Outlines
boolean | 3a3374a8-b2f6-5f10-941e-1cb924309dd3 |  | tickbox | Structural Drawings
checkpoint-status |  |  | checkpoint | Check top RLs for all reinforcement, ensuring adequate concrete cover Confirm with Concreter
checkpoint-status |  |  | checkpoint | Confirm that plastic bar chairs are used everywhere, particularly at exposed off-form soffits
checkpoint-status |  |  | checkpoint | Attach Formwork ITP
checkpoint-status |  |  | checkpoint | Attach Formwork Engineer sign off certificate Confirm that certificate references props, braces and compliance with design & AS3610
label | 320b8424-204b-5776-8728-6d867ea9e339 |  | note | Attach Formwork Engineer's Certificate
checkpoint-status |  |  | checkpoint | Attach ALL Services Hydraulic ITP (for cast-in elements), include relevant mark-ups below
checkpoint-status |  |  | checkpoint | Attach Precast ITP (for cast-in elements), including relevant mark-ups
checkpoint-status |  |  | checkpoint | Attach Reo Fixing ITP
checkpoint-status |  |  | checkpoint | Attach Principal Structural Engineer Inspection Report, and confirm that all actions are closed out with photos sent to engineer
label | 68674972-de10-55bf-b976-ead77cced679 |  | note | Attached below as applicable
checkpoint-status |  |  | checkpoint | Attach Post Tensioning Engineer Inspection Report, and confirm that all actions are closed out with photos sent to engineer
label | 62953734-9d32-50b8-83ff-68ef88d7649b |  | note | Attached below as applicable
checkpoint-status |  |  | checkpoint | Check quantity of concrete required prior to ordering
text | 587c5a52-076f-5c93-ac63-de85052b25cc |  | textbox | Total m3 (as measured by Site Engineer)
text | a57e8b20-584a-5627-bb76-468bf32d967d |  | textbox | Total m3 (as measured by Foreman)
checkpoint-status |  |  | checkpoint | Confirm MPa, slump and agg size of concrete prior to ordering
text | ba96cce3-8f4d-5c44-a281-2636c60e9885 |  | textbox | MPa
text | 2da17568-ef8f-58bb-85c0-67a7f6b2cc48 |  | textbox | Slump
text | 8df038cc-25f4-5b95-8950-a4eacf78d8a4 |  | textbox | Agg
checkpoint-group |  |  | section | During to Concrete Pour
checkpoint-status |  |  | checkpoint | Ensure concrete truck dockets have correct concrete strength, and attach delivery docket from each batch
checkpoint-status |  |  | checkpoint | Confirm concrete has falls to drainage points in slab
checkpoint-status |  |  | checkpoint | Ensure a representative from each of the following is on site and witnessing the pour
boolean | 10f29766-edbe-5f5f-bdea-129de46bed42 |  | tickbox | Formworker
boolean | 89acb7d2-47ce-5667-a226-10cb76886b71 |  | tickbox | Electrician
boolean | eba93cd6-6aad-5f0f-9c46-5d4b7d18f4b8 |  | tickbox | Plumber
boolean | 624e3d6b-f3cb-5d67-8b58-a2c862331379 |  | tickbox | Post Tensioner
boolean | 0743d567-be35-53b0-a627-76d85b6eadcc |  | tickbox | Precast Installer
checkpoint-status |  |  | checkpoint | Confirm Form Worker has labour below deck inspecting all joints (particularly at columns & walls) and is immediately cleaning any slurry
checkpoint-status |  |  | checkpoint | Confirm that all protection to precast panels is maintained at all times during concrete pour
checkpoint-group |  |  | section | After Concrete Pour
checkpoint-status |  |  | checkpoint | Confirm Surveyor is out next day to carry out survey of finished concrete Attach As built Survey Plan
label | ed33b7e8-6771-585f-8c7a-e807e7293f58 |  | note | Attached below as applicable
checkpoint-status |  |  | checkpoint | Confirm tolerance of finished concrete surfaces are in accordance with the specifications
checkpoint-status |  |  | checkpoint | Confirm saw joints are installed to engineers requirements
checkpoint-status |  |  | checkpoint | Confirm finish of concrete is adequate for application (broom/trowel/helicopter finish), refer to AS3610
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 1 day, and attach test results
text | 3b06d852-abb5-553d-b4f7-11be0a7b5f25 |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Confirm initial stress is conducted day after the pour, after concrete has reached 10 MPa on 1 Day results
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 4 day, and attach test results
text | a3d2e37c-4e44-5c9c-b3b5-9e1b1adb3121 |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Confirm final stress has occurred after concrete has reached 20MPa, and attach Stressing Records
label | 879567ad-3b4b-5dd0-a4cb-1f852e80f32a |  | note | Attached below as applicable
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 7 day, and attach test results
text | e7dbc640-f336-551c-b627-1c278d2d7f0d |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 28 day, and attach test results
text | 69cbdff0-d5d7-5552-ac9b-0875e4d8d01e |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Attach Subcontractor ITP - Attached below as applicable
button | cdc55010-641e-5d78-9b06-4f0710e0d516 |  | button | Subcontractor Sign Off | Yes, No, N/A
button | bc36973c-7bef-5f9b-8957-55efb6408772 |  | button | Aland Sign Off | Yes, No, N/A
holdpoint |  |  | signoff | Click to add Sign-Off Signatures
checklist-flat |  |  | checklist | Soft Landscaping |  |  |  |  | Yes | Soft Landscaping | 6842d8d5-5c7b-44c3-8694-d6f3cdc2839b
checkpoint-status |  |  | checkpoint | Ensure all plants are planted as per drawings
checkpoint-status |  |  | checkpoint | Irrigation installed as per drawings
button | e5963f65-7708-56ce-b4ef-c98f8246fe85 |  | button | Irrigation leak tested | Yes, No
checkpoint-status |  |  | checkpoint | Outdoor furniture installed as per plans
checkpoint-status |  |  | checkpoint | Final sign off - All soft landscaping completed as per the above ITP - Add general photos/comments below
label | 619e0e5b-cbf4-5474-8ebc-6b4f005695dd |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Floor Wastes |  |  |  |  | Yes | Floor Wastes | 6ba1f22c-c521-4d64-9108-b055fd2a162c
checkpoint-status |  |  | checkpoint | Plumber checks all pipes for any cracks, or imperfections
button | 38861ccf-26a3-5ab8-8190-0da5b8898a2b |  | button | Plumber completes stack work | Yes, No
button | ad2f4760-dd2b-539a-b2d8-fa9dab75e1c3 |  | button | Plumber cuts waste flush with concrete and puts sponge inside | Yes, No
button | d16bb4b7-86e4-5a6d-b6c8-038f05b45c2a |  | button | Plumber caps off all other pipes | Yes, No
checkpoint-status |  |  | checkpoint | Waterproofer pushes sponge down 100mm and finishes his membrane & flood test
checkpoint-status |  |  | checkpoint | Waterproofer removes sponge and releases water and puts the sponge back in ensuring there are no debris left in the pipe
checkpoint-status |  |  | checkpoint | Tiler accepts that the waste is clean and has a sponge in it
checkpoint-status |  |  | checkpoint | Tiler completes his works (i.e sand cement & tile)
checkpoint-status |  |  | checkpoint | Aland cleans and removes the sponge
checkpoint-status |  |  | checkpoint | Final sign off - All floor wastes completed as per the above ITP
label | be201806-9a51-5b9d-bc19-3dc7a08bd860 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Fire Pump Room (V90421) |  |  |  |  | Yes | Fire Pump Room (V90421) | 6c91df38-ed4b-49c2-a10a-ddf25e05dfb1
checkpoint-status |  |  | checkpoint | Fire pump isolation valves installed on all pumps
checkpoint-status |  |  | checkpoint | All pipe work tested to min 1200 kpa
checkpoint-status |  |  | checkpoint | Pour concrete plinth for each fire pump
label | 7d519572-ee25-5627-93fd-8988226ed148 |  | note | Check height and dimensions as per drawings/specifications
checkpoint-status |  |  | checkpoint | Switchboards in place using suitable fixings to match mounting service No damage to external board has occurred during installation
button | 2c2492a5-4c11-5dde-a22f-2dc8fd9186bb |  | button | Ensure adequate pathways exist within board to accommodate all circuits and allow for future expansion | Yes, No
button | ad420682-95e2-5795-b6be-5b4aafc8707e |  | button | Install and loom in all circuits into correct cabinets | Yes, No
button | 30254168-1660-58d9-aee5-984b826fcdaa |  | button | Ensure cable labels match switchboard schedule and construction drawings | Yes, No
button | 1ebe5844-f4cf-5d67-908e-262e16fc522a |  | button | Cables are labelled as per specified requirements | Yes, No
button | ff45423e-07a7-5760-af37-1a2e7f1e880f |  | button | Check all tightness of all terminals on all breakers and bars | Yes, No
checkpoint-status |  |  | checkpoint | Ensure 1m Clearance around fire pumps
checkpoint-status |  |  | checkpoint | Ensure minimum 2m Height clearance - To floor or finish above
checkpoint-status |  |  | checkpoint | Ensure safety signage is installed and visible as per plans
checkpoint-status |  |  | checkpoint | All PvC pipes to be fire rated within pump room
checkpoint-status |  |  | checkpoint | FIP commissioned & is recognising fire pumps within the system
checkpoint-status |  |  | checkpoint | EWIS speakers installed as per manufacturers instructions
checkpoint-status |  |  | checkpoint | Final sign off - Fire pumps installed as per the above ITP - Add general photos/comments below
label | 81d12469-8946-5b9c-b257-fca487f46a0b |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Services Fit Out |  |  |  |  | Yes | Services Fit Out | 786a8105-a26a-47fc-9888-f3fe559f4328
checkpoint-status |  |  | checkpoint | All plumbing fitout have been tested & commissioned
checkpoint-status |  |  | checkpoint | Final running test of all plumbing items
checkpoint-status |  |  | checkpoint | All electrical fitout have been tested
checkpoint-status |  |  | checkpoint | All intercom points are installed & are level & in correct location
checkpoint-status |  |  | checkpoint | All security systems have been installed & tested
checkpoint-status |  |  | checkpoint | NBN has been tested & commision
checkpoint-status |  |  | checkpoint | Air con has been final tested & commissioned
checkpoint-status |  |  | checkpoint | Test fire doors install as per code closing & gapping around door
checkpoint-status |  |  | checkpoint | Fire door hardware test holes, closers & locks
checkpoint-status |  |  | checkpoint | Final sign off - All services fit out work completed as per the above ITP
label | 84f3b768-75f7-5fbc-b96e-263b2d586e3e |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-sectioned |  |  | checklist | Hydraulic Groundwork |  |  |  |  | Yes | Hydraulic Groundwork | 79b47a0e-1435-4650-917f-6bb581530b32
checkpoint-group |  |  | section | Pre-Commencement
checkpoint-status |  |  | checkpoint | WorkSafe notification prior to trenching below 1.5m deep has been submitted
label | 8a8fdedd-902c-51b6-aae0-91bb913b354f |  | note | If notification is required attach documents below
button | 871b0d6a-47ac-5f91-9377-ac019574513e |  | button | If required, trench shields are on site & ready for use | Yes, No
button | 5468355e-3ba6-51cb-b90e-6a63e99495fb |  | button | Dig Permit completed & attached | Yes, No
button | adc9f29a-f8c7-5ad7-9f7c-2872f9d7e988 |  | button | Exclusion Zones have been erected as required (Attach photos) | Yes, No
checkpoint-status |  |  | checkpoint | Works have been coordinated with other trades
checkpoint-status |  |  | checkpoint | Excavation depths & locations confirmed prior to commencement
checkpoint-status |  |  | checkpoint | Approval given to Trade Contractor to commence stormwater installation
checkpoint-group |  |  | section | Excavation Works
checkpoint-status |  |  | checkpoint | Excavation Checked, Correct & Approved
boolean | d20ea241-1ba6-5c51-9ef1-63ca1c7fea9f |  | tickbox | Depth Accurate
boolean | a4511b2b-13dd-5c6c-885c-324bd27a7bd1 |  | tickbox | Width Accurate
checkpoint-status |  |  | checkpoint | Excavation works - completed to specification/drawings & Area left clean/tidy
label | d921aff5-a38b-5e82-bcc4-9047a30c3101 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checkpoint-group |  |  | section | Stormwater Installation
checkpoint-status |  |  | checkpoint | Pit installation correct
button | 4daa0cef-1cbf-5cbd-a26f-0cabfca677e1 |  | button | Pit size correct | Yes, No
button | c94e1076-e1a7-5ac1-ab68-610c309791f2 |  | button | Pit location correct | Yes, No
button | 914af939-e6cf-54ce-a207-6c66aa78950c |  | button | Pit invert levels correct (In & Out) | Yes, No
button | 99633e78-4867-5c10-8cca-2b7347c47c53 |  | button | Pit finished RL correct | Yes, No
button | c7789472-5590-5c31-b5f1-fe6c653dceed |  | button | Pits covered & made safe | Yes, No
checkpoint-status |  |  | checkpoint | Bedding material is installed & correct to support service
checkpoint-status |  |  | checkpoint | Pipe installation correct
button | fbaca336-3e0a-560a-801b-078be015bc32 |  | button | Pipe size correct as documented | Yes, No
button | 8cf8ca45-dc81-53b8-b1a0-a3dceb777674 |  | button | Trenches have been backfilled & compacted correctly | Yes, No
button | a7d7a654-47e0-5fc2-8aa0-ef71f5ae7595 |  | button | Service location tape Installed (if applicable) | Yes, No
checkpoint-status |  |  | checkpoint | Provisions for Aggie Pipe Connection installed as documented
checkpoint-status |  |  | checkpoint | Expansion Lagging has been installed where service will be cast into concrete
checkpoint-status |  |  | checkpoint | Stormwater install completed to specification/drawings & Area left clean/tidy
label | cbf1d00e-7a11-5025-963b-007f87c3b952 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-sectioned |  |  | checklist | Shotcrete |  |  |  |  | Yes | Shotcrete | 7db0d099-1916-4760-8487-ba259ce69298
checkpoint-group |  |  | section | Pre - Spray
checkpoint-status |  |  | checkpoint | Ensure services/drainage correctly installed
checkpoint-status |  |  | checkpoint | Location of spray & heights checked and confirmed
checkpoint-status |  |  | checkpoint | Starter bars installed correctly
checkpoint-status |  |  | checkpoint | Correct mesh installed to meet required specification
checkpoint-status |  |  | checkpoint | Covers checked and acceptable for respective area
checkpoint-group |  |  | section | Shotcrete Spray
checkpoint-status |  |  | checkpoint | Correct concrete delivered, attach delivery dockets
checkpoint-status |  |  | checkpoint | Spray application correct & spoil removed
checkpoint-status |  |  | checkpoint | Spray completed and required finish achieved - correct heights achieved
checkpoint-status |  |  | checkpoint | Final sign off - All shotcrete completed as per the above ITP - Add general photos/comments below
label | aae66644-6729-589f-9161-0d0d0eb0f552 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Gas Connection |  |  |  |  | Yes | Gas Connection | 8a4f3ba7-3906-4ccb-9c5b-65b99c6641a5
checkpoint-status |  |  | checkpoint | Gas has been installed throughout complex
checkpoint-status |  |  | checkpoint | Gas has been tested throughout complex
checkpoint-status |  |  | checkpoint | All documentation for gas install has been reviewed & documented by Aland
checkpoint-status |  |  | checkpoint | Final sign off - Gas has been tested & installed as per the above ITP - Add general photos/comments below
label | 153eec2f-4fa1-52ab-a4ba-0c4a5cc8ea9f |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-sectioned |  |  | checklist | Sheet Pile ITP |  |  |  |  | Yes | Sheet Pile ITP | 8f32f146-50e7-41f4-adbe-eb2335e7617d
checkpoint-group |  |  | section | Foundation Pile Information
checkpoint-status |  |  | checkpoint | Pile Diameter
text | 391a030b-6900-5e4b-8bf3-43aee267e3b4 |  | textbox | Diameter (mm)
checkpoint-status |  |  | checkpoint | Approval of Socket
text | 185e23bc-dee2-5d21-a229-f91fd43c1a17 |  | textbox | Designed Pile Socket Length (mm)
text | 1b4a42b8-fec2-59ef-9499-fecb5de03649 |  | textbox | Actual Pile Socket Length (mm)
checkpoint-status |  |  | checkpoint | Pile Details
text | 5488e7dc-0f5e-5c39-8f24-6cc758f205a6 |  | textbox | Top of Steel RL (m)
text | f04273e5-8643-5333-8006-25a23d0d6ed8 |  | textbox | Length of Pile (m)
text | e055efbc-35d1-5298-b841-47160b096081 |  | textbox | Top of Concrete RL (m)
checkpoint-status |  |  | checkpoint | Check of excessive water in hole
checkpoint-group |  |  | section | Pile Reinforcement & Pre Pour
checkpoint-status |  |  | checkpoint | Reinforcement information
text | 9fa08c68-84c6-5ac1-bb3c-050338e2c3e1 |  | textbox | Main Bars
text | ee353170-7904-5f45-a91c-632cd76e45f6 |  | textbox | Ligs
text | 03e55353-d31e-5497-a588-82895382775c |  | textbox | Cage Length
checkpoint-status |  |  | checkpoint | Engineer/Building Surveyor Sign off
checkpoint-status |  |  | checkpoint | Commencement of Pour – Ok to pour
checkpoint-group |  |  | section | Pile Concrete Placement
checkpoint-status |  |  | checkpoint | Date of Pour
checkpoint-status |  |  | checkpoint | Concrete Delivery Docket
checkpoint-status |  |  | checkpoint | Pile Concrete Details
text | c5d5c4d2-ce6b-5bc8-a590-0efd72ecac04 |  | textbox | Concrete Strength (MPA)
text | d0b4ad3b-c75c-5ad6-845e-98cb33f6e399 |  | textbox | Cover (mm)
checkpoint-group |  |  | section | Pile Post Pour- Sign off
checkpoint-status |  |  | checkpoint | Post Pour requirement
text | d4129860-f5c9-5ff9-8e65-709ed9158c8a |  | textbox | Concrete Test Certificate number
text | cab8b1c1-b55d-5c84-911b-8d72af533dbb |  | textbox | 28 /56-day Concrete Compressive Strength (MPA)
checkpoint-status |  |  | checkpoint | Post Pour Signed off
checklist-sectioned |  |  | checklist | Pad Footings, Strip Footings, Lift Pits & Piles (V140421) |  |  |  |  | Yes | Pad Footings, Strip Footings, Lift Pits & Piles (V140421) | 90ecf608-dd34-4db3-8785-444ca93136fc
checkpoint-group |  |  | section | Prior to Concrete Pour
checkpoint-status |  |  | checkpoint | Attach mark-up plan
checkpoint-status |  |  | checkpoint | Confirm RL of sub-base
checkpoint-status |  |  | checkpoint | Confirm position of footing is in accordance with architectural setout design
checkpoint-status |  |  | checkpoint | Confirm starter bars to columns and walls installed in correct location
checkpoint-status |  |  | checkpoint | Check for reinforcement cover as per structural documents (especially at steps and ramps)
checkpoint-status |  |  | checkpoint | Obtain certificate from Structural Engineer and Geotechnical Engineer prior to concrete pour Attach certificates
checkpoint-status |  |  | checkpoint | Confirm waterproofing details installed as per manufacturer's specifications Attach waterproofer completed ITP (Applicable to Lift Pit Only)
checkpoint-status |  |  | checkpoint | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 7445f82d-f77c-5f57-b00a-17e82b00bfc0 |  | note | Attach photos prior to concrete pour
checkpoint-group |  |  | section | After Concrete Pour
checkpoint-status |  |  | checkpoint | Confirm tolerance of finished concrete surfaces
boolean | 2953a4ac-1970-5f6d-aa26-b59651ed95ea |  | tickbox | 50mm +/- in correct plane
boolean | e3976c4c-f6bb-5bbf-afb0-952fbd2a8e64 |  | tickbox | 50mm +/- from 30m straight edges
checkpoint-status |  |  | checkpoint | Obtain all concrete tests to be carried out on all concrete pours
label | 779064a6-80df-55bd-bd73-75da167469b4 |  | note | Attach Concrete Docket/results below
checkpoint-status |  |  | checkpoint | Check concrete strength results complete with specification
label | 9011b34a-a151-53ea-89f3-20d3e257532e |  | note | Attach results below as applicable in line with specifications
checkpoint-status |  |  | checkpoint | Attach Subcontractor ITP - Attached below as applicable
button | d77e00a4-b62d-567f-b697-6368f17b9dc0 |  | button | Subcontractor Sign Off | Yes, No, N/A
button | 591f19b9-e9de-5020-a419-777bd8e57943 |  | button | Aland Sign Off | Yes, No, N/A
holdpoint |  |  | signoff | Click to add Sign-Off Signatures
checklist-flat |  |  | checklist | Electrical Rough In |  |  |  |  | Yes | Electrical Rough In | 93854234-c196-41fa-8e74-3f9762c93f98
checkpoint-status |  |  | checkpoint | Power points have been installed as per the electrical plans including shaving cabinet strip light
checkpoint-status |  |  | checkpoint | All points & switches are in a functional area
checkpoint-status |  |  | checkpoint | All comms are installed to allow for good detailing around
checkpoint-status |  |  | checkpoint | GPO's are correct for air conditioning & functional
checkpoint-status |  |  | checkpoint | NBN provision conduits (draw‐wire) 1mm installed
checkpoint-status |  |  | checkpoint | Fire rating peno's completed in lobbies
label | 0a712df0-8c69-5e9e-9fb5-8799e6fea801 |  | note | Relevant photo's/register has been completed
checkpoint-status |  |  | checkpoint | Final sign off - All electrical work completed as per the above ITP
label | 83cc493d-f3f0-5519-9e90-78243be661a3 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Stairs |  |  |  |  | Yes | Stairs | 93f9d448-5ff4-4600-8e3d-9bcf29871f2d
checkpoint-status |  |  | checkpoint | Land stringers & backdrops secured
checkpoint-status |  |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status |  |  | checkpoint | Couplers & rebate boards installed
checkpoint-status |  |  | checkpoint | Riser heights confirmed
checkpoint-status |  |  | checkpoint | Going lengths confirmed
checkpoint-status |  |  | checkpoint | Correct Class of Finish
checkpoint-status |  |  | checkpoint | Couplers & rebate boards installed
checkpoint-status |  |  | checkpoint | Riser heights confirmed
checkpoint-status |  |  | checkpoint | Going lengths confirmed
checkpoint-status |  |  | checkpoint | Ensure lighting has been installed in stairwells as per plans
checkpoint-status |  |  | checkpoint | Final sign off - All stairs completed as per the above ITP
label | a3a90b7b-4205-534e-86f7-52f73970a2fe |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-sectioned |  |  | checklist | Excavation & Shoring |  |  |  |  | Yes | Excavation & Shoring | 9e21872e-99f4-45fd-ba3f-bb0e81809d65
checkpoint-group |  |  | section | Shoring
checkpoint-status |  |  | checkpoint | Locate all existing services
checkpoint-status |  |  | checkpoint | Confirm set out - Ensuring piling/spring remains within inside boundary
checkpoint-status |  |  | checkpoint | Confirm any vibration limitations/requirements
checkpoint-status |  |  | checkpoint | Confirm boundary set back to shoring wall
button | ebd40d17-6afd-5605-ac1e-0d16c8e64509 |  | button | RL levels to top of shoring wall confirmed | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Confirm de-stressing procedure for anchors with engineer
label | 0e2faf87-80ae-5f19-9ebe-7badd5dcc41c |  | note | Engineer procedure notes added below
checkpoint-status |  |  | checkpoint | Confirm level of excavation aligns with shoring wall levels/location
checkpoint-group |  |  | section | Excavation - Pre-Commencement
checkpoint-status |  |  | checkpoint | Confirm dial before you dig documents are onsite - If applicable and attached below
checkpoint-status |  |  | checkpoint | Confirm correct disposal of classified material
checkpoint-status |  |  | checkpoint | Obtain geotech report, including load bearing capacity
label | 4d9d3d55-aecb-5f5d-a05c-ec88d4be888a |  | note | Geotech report referenced or attached below
checkpoint-group |  |  | section | Excavation Works
checkpoint-status |  |  | checkpoint | Collection of tip dockets - If applicable and attached below
checkpoint-status |  |  | checkpoint | Confirm set out of boundaries & marked out
checkpoint-status |  |  | checkpoint | Confirm actual RL is within design tolerance
button | 4a3b1ddc-048e-5db8-a9d9-885537625c72 |  | button | Confirm set out of footings and pads | Yes, No, N/A
button | f433b594-78c8-5558-9b23-8c15ba49a5e4 |  | button | Confirm set out of in ground drainage | Yes, No, N/A
label | 731fd64b-0aae-5f9e-ac76-5067a26fefe3 |  | note | Excavation of footings not to exceed size as detailed on structural drawings
checkpoint-status |  |  | checkpoint | Certifier to inspect foundation in accordance with specifications
checkpoint-status |  |  | checkpoint | Geotech inspection of footings etc
label | 6a4fc736-68b9-59e6-899f-227b0390ec50 |  | note | Geotech report referenced or attached below
checkpoint-status |  |  | checkpoint | Confirm top of concrete footings is below surrounding finishes
checkpoint-status |  |  | checkpoint | Confirm sub-base is in line with engineers specifications/requirements
text | 76d8e1e9-ad45-5f34-9a35-4683aa683dd1 |  | textbox | Minimum thickening (MM)
checkpoint-status |  |  | checkpoint | Civil engineer inspection carried out - Attached below as applicable
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Attach Subcontractor ITP - Attached below as applicable
button | b1ec5327-a78f-5100-acde-cf2f68363bc2 |  | button | Subcontractor Sign Off | Yes, No, N/A
button | 74ac8c30-9a8b-59e7-9862-5c15b609b93e |  | button | Aland Sign Off | Yes, No, N/A
holdpoint |  |  | signoff | Click to add Sign-Off Signatures
checklist-flat |  |  | checklist | Rain Water Pump Room (v040521) |  |  |  |  | Yes | Rain Water Pump Room (v040521) | a11fb9f1-7f1b-4e43-ae7e-ec5fb0792b8c
checkpoint-status |  |  | checkpoint | Ensure rain water pumps are installed as per plans
checkpoint-status |  |  | checkpoint | Pump isolation valves installed on all pumps
checkpoint-status |  |  | checkpoint | All pipe work tested to min 1200 kpa
checkpoint-status |  |  | checkpoint | Switchboards in place using suitable fixings to match mounting service, no damage to external board has occurred during installation
button | 36eee77f-626b-5469-aefe-ccf1bfe22746 |  | button | Ensure adequate pathways exist within board to accommodate all circuits and allow for future expansion | Yes, No
button | 0cf6a292-e351-5979-a098-4cf00f39bcea |  | button | Install and loom in all circuits into correct cabinets | Yes, No
button | 18e6feda-b953-5b00-ad9c-27ba62155daf |  | button | Ensure cable labels match switchboard schedule and construction drawings | Yes, No
button | 89089400-6c38-5259-88fb-4af98b279c44 |  | button | Cables are labelled as per specified requirements | Yes, No
button | 31d43597-7048-5bd3-a7a6-856cac29a648 |  | button | Check all tightness of all terminals on all breakers and bars | Yes, No
button | 9dcb657f-6bd3-56a6-b0eb-33621a41aad1 |  | button | Ensure safety signage is installed and visible as per plans | Yes, No
checkpoint-status |  |  | checkpoint | Final sign off - Rain water pumps installed as per the above ITP - Add general photos/comments below
label | 7e2c92aa-43fb-5b17-b334-c0529e0e6000 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Detailed Excavations |  |  |  |  | Yes | Detailed Excavations | a21c80f8-b30d-4274-bb8d-131623ab6a53
checkpoint-status |  |  | checkpoint | Excavation depths and locations confirmed prior to excavation commencing
checkpoint-status |  |  | checkpoint | Any batters formed correctly
checkpoint-status |  |  | checkpoint | Any trenches/ pits / hazardous areas appropriately isolated
checkpoint-status |  |  | checkpoint | Any soft spots identified and appropriate remedial completed
checkpoint-status |  |  | checkpoint | Excavation checked, correct and approved
checkpoint-status |  |  | checkpoint | Bulk Excavation completed, reviewed and approved
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached
checkpoint-status |  |  | checkpoint | Final sign off - All detailed excavations completed as per the above ITP
label | 0cf9c33b-33b9-589e-86a4-584c2c59bed2 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Power Connection |  |  |  |  | Yes | Power Connection | a21ddcd8-2db3-4c2c-b0d2-b1beb7dd7221
checkpoint-status |  |  | checkpoint | Power has been installed throughout complex
checkpoint-status |  |  | checkpoint | Power has been tested throughout complex
checkpoint-status |  |  | checkpoint | All documentation for power install has been reviewed & documented by Aland
checkpoint-status |  |  | checkpoint | Final sign off - Power has been tested & installed as per the above ITP - Add general photos/comments below
label | 277ba132-575f-5b05-b5d4-4357ae82395d |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | NBN Connection |  |  |  |  | Yes | NBN Connection | a6d38751-b79f-4377-9b63-836b56188b03
checkpoint-status |  |  | checkpoint | NBN has been installed throughout complex
checkpoint-status |  |  | checkpoint | NBN signal has been tested throughout complex
checkpoint-status |  |  | checkpoint | All documentation for NBN install has been reviewed & documented by Aland
checkpoint-status |  |  | checkpoint | Final sign off - NBN has been tested & installed as per the above ITP - Add general photos/comments below
label | 33870dcd-3399-51e1-b332-e5a4f8de4edd |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-sectioned |  |  | checklist | KONE - Lifts |  |  |  |  | Yes | KONE - Lifts | ab3e3402-b73a-40eb-b05e-352e7104582a
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
checkpoint-status |  |  | checkpoint | Setout & alignment as per drawing (include revision below)
text | bf63164f-c945-5274-a8bc-7d2ad714c73e |  | textbox | Drawing & revision number(s)
checkpoint-group |  |  | section | Complete before KONE starts on site
checkpoint-status |  |  | checkpoint | Waterproof the pit & shaft
checkpoint-status |  |  | checkpoint | Weather & water protect lift lobby areas on all floors
checkpoint-status |  |  | checkpoint | Complete all penetrations as per KONE drawings
checkpoint-status |  |  | checkpoint | If steel construction - provide fixing points for rail brackets & lift doors according to KONE drawings
checkpoint-status |  |  | checkpoint | Provide accurate grid, datum & RL lines
checkpoint-status |  |  | checkpoint | Provide lighting in the lift lobbies & stairwells
checkpoint-status |  |  | checkpoint | Provide permanent access stairs to all floors
checkpoint-status |  |  | checkpoint | Provide public access to top floor life door with the control cabinet Control cabinet must not be in a private dwelling space
checkpoint-status |  |  | checkpoint | Build in all lifting points por beams as shown on KONE's drawings
checkpoint-status |  |  | checkpoint | Provide access so that equipment can be installed into the lift well Special holes may be required Guide rails are 5m long
checkpoint-status |  |  | checkpoint | Guard lift door openings in accordance with AS 4431
checkpoint-status |  |  | checkpoint | Provide space for our site personnel accommodation that is safe, clean & dry
checkpoint-status |  |  | checkpoint | Provide on site water, lighting & sanitation
checkpoint-status |  |  | checkpoint | Provide adequate space for storage of all lift equipment & all tools near the site accommodation that is secure, safe & dry (approx 50 sqm per lift)
checkpoint-status |  |  | checkpoint | Remove all builders equipment, materials & rubbish from the lift well & lobby areas in front of the lift well doors
checkpoint-status |  |  | checkpoint | Install permanent sub mains & dedicated telephone line to the top floor served terminating at the location nominated by KONE & provide 415V (5%) 3 phase + neutral + earth power supply Max fault level of 6kA
checkpoint-group |  |  | section | Complete while KONE is working onsite & prior to practical completion
checkpoint-status |  |  | checkpoint | Protect lift doors, architraves & lift fixtures from damage prior to lift hand over
checkpoint-status |  |  | checkpoint | KONE to place rubbish & excess packaging into bins on site provided by Aland
checkpoint-status |  |  | checkpoint | Security sub contractor to finalise security interfacing & operation
checkpoint-group |  |  | section | Complete at any time that is suitable for Aland
checkpoint-status |  |  | checkpoint | Supply & install any associated wiring that is required external to the lift shaft
checkpoint-status |  |  | checkpoint | Install any fire control equipment if required
checkpoint-status |  |  | checkpoint | If a lift is required to operate during a fire, then isolate those lift lobbies from fire & smoke in accordance with the BCA part E2 & recommendations of EN811 appendix G & Fig 2
checkpoint-status |  |  | checkpoint | Make good & clean up where lobby finishes meet architraves & lift call buttons etc
checklist-sectioned |  |  | checklist | Formwork & Reinforcing |  |  |  |  | Yes | Formwork & Reinforcing | ac3816f8-befd-43d2-b233-59ea73bf9649
checkpoint-group |  |  | section | Formwork
checkpoint-status |  |  | checkpoint | Confirm Class of formwork to all faces, as per the latest specifications
checkpoint-status |  |  | checkpoint | Confirm RL's of soffit & beams
checkpoint-status |  |  | checkpoint | Confirm any penetration sizing for any hoist/crane penetrations
checkpoint-status |  |  | checkpoint | Ensure formwork frames installed to enable clear & labelled access under deck for other personnel & for inspections
checkpoint-status |  |  | checkpoint | Ensure all formwork surfaces are cleaned & no rubbish remains on any soffits,sides,base of work
checkpoint-status |  |  | checkpoint | Ensure bases of all columns/walls are cleaned out prior to pouring
checkpoint-status |  |  | checkpoint | Check formwork is completed as per specified Class
checkpoint-status |  |  | checkpoint | Ensure no rubbish or excess water is present prior to concrete pour
checkpoint-group |  |  | section | Reinforcing
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checkpoint-group |  |  | section | Post concrete pour
checkpoint-status |  |  | checkpoint | Formwork stripped in a safe manner
checkpoint-status |  |  | checkpoint | All timbers de - nailed
checkpoint-status |  |  | checkpoint | Final sign off - All formwork & reinforcement completed as per the above ITP
label | b4241cb3-c017-599e-b902-40f90086942e |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Pad Footings |  |  |  |  | Yes | Pad Footings | b730866a-2929-4661-aef2-74595def3938
checkpoint-status |  |  | checkpoint | Excavation depths and locations confirmed prior to detailed excavation commencing
button | 484541b8-e204-5b08-b648-3307dc0dd44f |  | button | Footing RL Confirmed | Yes, No, N/A
button | 4dc458bb-1fc6-5c2a-8669-951685ee0bcc |  | button | Any services (overhead / below ground) considered and isolated where required before excavation commences | Yes, No, N/A
button | 0f3af2f0-f201-598c-8916-26459170a063 |  | button | Approval given to commence detailed excavation | Yes, No, N/A
button | c45d6c2e-e96a-5693-b384-b79a09cb19bf |  | button | Excavation checked, correct and approved | Yes, No, N/A
button | 4f446aee-0895-537c-9b5a-fa9eb6bbdea6 |  | button | Depth correct (allow for site concrete if required) | Yes, No, N/A
button | 74c5644c-f0f3-5dde-917e-10d4c6e700d0 |  | button | Width correct (allow for boxing if required) | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Pads/ footings battered/ edges left free of spoil
checkpoint-status |  |  | checkpoint | Detailed excavation spoil removed and work area left clean and tidy
checkpoint-status |  |  | checkpoint | Blinding installed and documented if required/ Dockets and photos scanned
checkpoint-status |  |  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
button | 82719b0b-2b90-5c94-9ca6-c932442d1f67 |  | button | Formwork sufficiently fixed and braced | Yes, No, N/A
button | f062700c-3469-5ae3-a515-40b786864b2e |  | button | Any rebates/ nibs / cast in items are correctly positioned, sized and appropriately fixed in place | Yes, No, N/A
button | 62d327de-3488-5da8-a5f9-2602c5ea8b76 |  | button | Service penetrations formed correctly and locations checked/correct | Yes, No, N/A
button | 5b7ae2ba-4f6f-583f-8008-6663a4dfe51f |  | button | Any control joints/ stop ends installed accurately and correctly braced | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Reinforcement installed as per plan including cover & chairs
button | 799e19c2-7373-511b-b46d-97caedd7b1c1 |  | button | Reo spacing & grade as per specifications | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Starter bars, dowel bars, & mesh installed as per specifications
checkpoint-status |  |  | checkpoint | Concrete strength/ Slump confirmed
checkpoint-status |  |  | checkpoint | Any waterproofing elements have been correctly installed and checked
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checkpoint-status |  |  | checkpoint | Final sign off - All pad footings completed as per the above ITP
label | a4daf18d-e191-5765-b52a-5bc23b256a52 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Carpark & Line Markings |  |  |  |  | Yes | Carpark & Line Markings | be9bd016-0d7f-4902-8d83-7c4aa4e0db17
checkpoint-status |  |  | checkpoint | Ensure all emergency lighting in car park has been installed as per plan
checkpoint-status |  |  | checkpoint | Check that all boom gates have been installed & tested
checkpoint-status |  |  | checkpoint | Check that all security systems within car park have been installed & tested
checkpoint-status |  |  | checkpoint | Check that all garage doors in car park have been installed & tested
checkpoint-status |  |  | checkpoint | Ensure all safety bollards in car park has been installed as per plan
checkpoint-status |  |  | checkpoint | Ensure all signage in car park has been installed as per plan
checkpoint-status |  |  | checkpoint | All line markings are completed in correct colour/Area according to specifications
checkpoint-status |  |  | checkpoint | All Numbering completed in correct colour/Area according to specifications
checkpoint-status |  |  | checkpoint | Final sign off - All line markings completed as per the above ITP - Add general photos/comments below
label | b795a612-0cce-551f-84be-c8042de8a782 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Pre Wall Linings |  |  |  |  | Yes | Pre Wall Linings | c0193683-d66e-4919-8ecf-b667af5a4ae9
checkpoint-status |  |  | checkpoint | Ensure FER, FEBQ & alternate solution reports have been read & requirements complied with
button | e68a5bf2-5902-5ee0-9f3c-936502f94c40 |  | button | Ensure all penetrations have been installed at a 90 degree | Yes, No
button | 1a4f5f1c-5822-5f6f-927f-e7333cc93208 |  | button | Ensure all penetrating pipes fire collars are installed in accordance with C3.15 of the BCA | Yes, No
button | baa19b4a-4ef8-54d7-856e-37da0afd73bb |  | button | Ensure all penetrating floor waste pipes have floor waste fire collars installed in accordance with C3.15 of the BCA | Yes, No
button | 8a89be50-5e62-55de-89d4-9ad1cae1315b |  | button | Ensure that penetrations around fire hydrant pipes have been filled | Yes, No
button | b8ef40b0-d53b-550e-aec6-d4e051958c20 |  | button | Remove redundant fire collars | Yes, No
button | edcf96f8-2864-5e3f-8f9d-3e0009ca6bd5 |  | button | Fill redundant Penetrations with concrete (min 200mm Thick) | Yes, No
checkpoint-status |  |  | checkpoint | Ensure all copper pipes & hydrant pipes have been insulated when passing thru a fire collar in accordance with clause C3.15 of the BCA
checkpoint-status |  |  | checkpoint | Ensure all fire collars have been installed in accordance with manufacturer's specifications & clause C3.15 of the BCA
checkpoint-status |  |  | checkpoint | Ensure that mechanical ductwork is suitably sealed when passing through firewalls
checkpoint-status |  |  | checkpoint | Ensure that suitable access is provided to mechanical fire dampers in accordance with clause C3.15 of the BCA
checkpoint-status |  |  | checkpoint | Ensure that services within the fire stairs are boxed out with a two way fire rated system (where required)
checkpoint-status |  |  | checkpoint | Ensure electrical cables have been suitably sealed when passing through a fire element in accordance with clause C3.15 of the BCA
checkpoint-status |  |  | checkpoint | Ensure that NBN collars have been installed with grafitex on both sides of the hebel walls in accordance with clause C3.15 of the BCA
checkpoint-status |  |  | checkpoint | Check that PEX pipes are adequately sealed in accordance with clause C3.15 of the BCA
checkpoint-status |  |  | checkpoint | Check that fire doors have been filled
checkpoint-status |  |  | checkpoint | Final sign off - All pre wall linings work completed as per the above ITP
label | f4e1d54d-3c77-5e4c-8e05-0962311dbd82 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Bathroom & Laundry Waterproofing |  |  |  |  | Yes | Bathroom & Laundry Waterproofing | c4cf7cef-ca5e-4006-af8e-8aff8332fbfe
checkpoint-status |  |  | checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application "No access Waterproofing work in progress"
label | ab90e87c-7b91-5f54-be3f-29cb146d6b22 |  | note | Attach relevant photos below
button | 1b2fa85c-40b8-59a4-a9f7-b3e430bfb544 |  | button | Membrane system & methodology checked off AGainst Aland standard details & MSDS & guidelines | Yes, No
button | 204429cb-f20e-5d98-8d34-22f17b83fe4d |  | button | Surface preparation as per application guide | Yes, No
button | 5139c964-85f0-5748-a966-6b25ee2bdc2e |  | button | Substrate clean, dry & free from dust. | Yes, No
button | 9ff305b7-eef5-5d73-bd84-95673c0e9274 |  | button | Ensure no high points or crevices are in the substrate | Yes, No
button | 8c01e01f-9821-5690-b7da-305edbb9f3f7 |  | button | Ensure substrate is structurally sound & ready to receive membrane | Yes, No
button | ddbbd4ef-f5f6-58ac-a953-da721ce46d80 |  | button | Ensure humidity, temperature & moisture are in accordance with manufacturer's recommendations prior to primer | Yes, No
button | b6110024-e35e-5ce8-964a-ac595b6d5fda |  | button | Do not proceed if above has not been signed off | Yes, No
checkpoint-status |  |  | checkpoint | Apply primer
button | 772450b2-d24d-5d31-9c5a-70cc6c3706f1 |  | button | Ensure all floor wastes & pipes have been primed in accordance with manufacturer's recommendations | Yes, No
button | 3f6e15f2-d36b-58d0-8412-713cfc3bc37c |  | button | Shower angle in correct position & level | Yes, No
button | b21b033d-9269-540b-814d-d356a19ecea8 |  | button | Door angle is in correct position & level | Yes, No
button | 0b8928ed-1a5e-5209-9a6e-f8ecb8bd4a62 |  | button | Door & shower angle are 3 mm gauge aluminium | Yes, No
button | 0c92b756-2648-5413-87fc-1d8e7039df17 |  | button | All corners have polyurethane bond breaker installed with min 15mm radios | Yes, No
button | d3ffdb2f-990c-5991-90f7-951a52bdbf42 |  | button | Ensure humidity, temperature & moisture are in accordance with manufacturer's recommendations prior to first coat | Yes, No
checkpoint-status |  |  | checkpoint | Apply first coat of membrane & turn membrane up the walls / pipes as required.
label | 664a50c8-2ffe-5860-a641-0f3b8192c93e |  | note | All floor wastes membranes to be turned down into floor waste
checkpoint-status |  |  | checkpoint | Waterproof walls of shower section up to ceiling. Seal taps & the like. 2x coats required
button | ef2848dd-3bca-5ca4-84aa-62b86b1ebe35 |  | button | Min 150mm kicker has been waterproofed (do width of roller 230mm) | Yes, No
button | 0ad269c9-75f8-50d2-bee3-f26508e089cb |  | button | Min 1500mm past shower screen has been waterproofed | Yes, No
button | ac3c7107-e56a-51a5-905e-5568cb7956a0 |  | button | Waterproof all shower & adjacent walls | Yes, No
button | 2655d542-bd0b-53c2-a0c0-0b5ca6d76450 |  | button | Ensure humidity, temperature & moisture are in accordance with manufacturer's recommendations prior to final coat | Yes, No
checkpoint-status |  |  | checkpoint | Apply final coat of membrane
button | e7b10b99-3d73-518d-98c6-17c92579c31e |  | button | Allow curing in accordance with manufacturers specification 24‐48 hours min | Yes, No
checkpoint-status |  |  | checkpoint | Carry out dry film thickness test using Positector coating thickness inspection instrument
label | 2c15f407-b744-57f6-be8e-863bf3f0dbaa |  | note | Total dry film thickness of 1.2mm (1200 microns) in two finished coats. As such at min.
label | 268d6f11-68c0-548d-b5e1-b5bf6eb209e9 |  | note | Wet film thickness of 0.75mm per coat is required ‐ Apply membrane at a coverage of 0.75 ‐ 1 Ltr / m2 per coat
checkpoint-status |  |  | checkpoint | Rectification of defective works for failure of flood test & all works completed
checkpoint-status |  |  | checkpoint | Final sign off - All bathroom & laundry waterproofing work completed as per the above ITP
label | 20509fd1-1dab-54a8-a9cd-fa7482136bc8 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Toilet |  |  |  |  | Yes | Toilet | c6bf494e-0462-4b28-ba6e-638327c937b1
checkpoint-status |  |  | checkpoint | Floor wastes checked - Any issues comment/photo below
checkpoint-status |  |  | checkpoint | All rough-in pipework is colour coded to ensure no cross connections
checkpoint-status |  |  | checkpoint | All Water & Gas risers are complete
checkpoint-status |  |  | checkpoint | All stacks are level/plumb
checkpoint-status |  |  | checkpoint | Ensure all services that go through fire rated walls to be treated with collars/fire rated sealant
checkpoint-status |  |  | checkpoint | Ensure rough in has been done as per specs
checkpoint-status |  |  | checkpoint | Final sign off - All plumbing work completed as per the above ITP - Add general photos/comments below
label | 6de2d11a-ee94-5f81-a088-d0d7b5fb8775 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Mechanical Fan Room |  |  |  |  | Yes | Mechanical Fan Room | c817a8ef-1605-4753-b817-7e024cbf3eac
checkpoint-status |  |  | checkpoint | Ensure all mechanical fans have been tested & commissioned
button | 6fb48696-4f95-57a9-9700-4bd839227a16 |  | button | Switchboards in place using suitable fixings to match mounting service No damage to external board has occurred during installation | Yes, No
button | 5abcd6d8-00b6-5938-8d34-769790618d7c |  | button | Ensure adequate pathways exist within board to accommodate all circuits and allow for future expansion | Yes, No
button | 261e25b2-78fe-58ed-882b-6827886faa6e |  | button | Install and loom in all circuits into correct cabinets | Yes, No
button | 0482ae87-e740-55c3-b5d8-b2dee450335d |  | button | Ensure cable labels match switchboard schedule and construction drawings | Yes, No
button | 3aa27a68-be9a-500d-b19c-873ea456b0d4 |  | button | Cables are labelled as per specified requirements | Yes, No
button | bc34217a-fb95-5718-8872-e9c543feea24 |  | button | Check all tightness of all terminals on all breakers and bars | Yes, No
checkpoint-status |  |  | checkpoint | Ensure safety signage is installed and visible as per plans
checkpoint-status |  |  | checkpoint | Final sign off - All mechanical fans are installed as per the above ITP - Add general photos/comments below
label | 5d3a3e28-1aaf-50cd-bdfe-ec62ca5ef1f4 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-sectioned |  |  | checklist | Precast |  |  |  |  | Yes | Precast | cb161b0c-e212-4458-868d-bfe19d432d9f
checkpoint-group |  |  | section | Pre - Erection
checkpoint-status |  |  | checkpoint | Latest drawings include bracing design
checkpoint-status |  |  | checkpoint | Precast Panels certification obtained
checkpoint-status |  |  | checkpoint | Set up of exclusion zone - Off-loading area
checkpoint-status |  |  | checkpoint | Set up of exclusion zone - work area
checkpoint-status |  |  | checkpoint | Crane slewing zone checked
checkpoint-status |  |  | checkpoint | Survey datum and grids checked
checkpoint-status |  |  | checkpoint | Support structure as per engineer design
checkpoint-status |  |  | checkpoint | Precast element set-out complete
checkpoint-group |  |  | section | Precast Element Erection
checkpoint-status |  |  | checkpoint | Shims set to levels & within limits
checkpoint-status |  |  | checkpoint | Dowel preparation complete as per drawings
checkpoint-status |  |  | checkpoint | Crane positioned as per chart check
checkpoint-status |  |  | checkpoint | Panel's lifted off truck as per SWMS
button | 1f20b85a-0fd9-5162-822a-834f0fa14755 |  | button | Panels lowered into position | Yes, No
checkpoint-status |  |  | checkpoint | Dowel alignment checked
button | 617268f6-912c-5d1f-9eb8-218bd6b85ba3 |  | button | Horizontal alignment checked | Yes, No
button | 420e23d0-bbf4-5d5c-8728-23f7013dbe79 |  | button | Vertical alignment checked | Yes, No
checkpoint-status |  |  | checkpoint | Bracing installed, pins, locks & bolts in place
checkpoint-status |  |  | checkpoint | Panels dowels grouted
checkpoint-status |  |  | checkpoint | Dry pack grout to panels underside
checkpoint-status |  |  | checkpoint | Brackets installed and grouted
checkpoint-status |  |  | checkpoint | Braces removed
checkpoint-status |  |  | checkpoint | Caulking internally as per approved spec
checkpoint-status |  |  | checkpoint | Caulking externally as per approved spec
label | 3abc1f78-9a73-563f-8492-1e0de5c66778 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
holdpoint |  |  | signoff | All work completed as per ITP
checklist-flat |  |  | checklist | Basement Fire System |  |  |  |  | Yes | Basement Fire System | cf7c4371-7d0e-4ca4-bc01-374cd0c8cbef
checkpoint-status |  |  | checkpoint | Confirm any pipework and cabling penetrating partition walls are sealed through penetration with Intumescent fire mastic
checkpoint-status |  |  | checkpoint | Sprinkler rough in complete
checkpoint-status |  |  | checkpoint | Sprinkler droppers / heads installed
checkpoint-status |  |  | checkpoint | Sprinkler floor isolation valve assembly installed
checkpoint-status |  |  | checkpoint | Sprinkler valves installed
checkpoint-status |  |  | checkpoint | Sprinkler tested to min 1200 kpa
checkpoint-status |  |  | checkpoint | Feed hydrant installed
checkpoint-status |  |  | checkpoint | Feed hydrant commissioned
checkpoint-status |  |  | checkpoint | All hoses installed as per plan
checkpoint-status |  |  | checkpoint | All hoses installed as per manufacturer's instructions
checkpoint-status |  |  | checkpoint | Pipework tested - Test results attached below
checkpoint-status |  |  | checkpoint | EWIS speakers installed as per manufacturers instructions
checkpoint-status |  |  | checkpoint | Magnetic door holder fitted and functioning correctly on all fire exits
checkpoint-status |  |  | checkpoint | Final sign off - Fire system installed as per the above ITP - Add general photos/comments below
label | 3b9056e8-3216-5ead-8dba-8184a4538373 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-sectioned |  |  | checklist | Columns |  |  |  |  | Yes | Columns | d52f7dd5-5f83-45d9-a51f-e9eb730e96e2
checkpoint-group |  |  | section | Pre-Column Pour
checkpoint-status |  |  | checkpoint | Survey points given for 2 points
checkpoint-status |  |  | checkpoint | Datum RL supplied by surveyor, pour height marked
checkpoint-status |  |  | checkpoint | Blockouts, couplers, cast-in elements installed
holdpoint |  |  | signoff | Request Sign Off from Site Engineer
checkpoint-status |  |  | checkpoint | Column box cleaned & oiled
checkpoint-status |  |  | checkpoint | Placement of column box over cage
checkpoint-status |  |  | checkpoint | Bracing props secured
checkpoint-status |  |  | checkpoint | Column plumbed
checkpoint-status |  |  | checkpoint | Correct class of finish
checkpoint-status |  |  | checkpoint | Final sign off - Columns completed as per the above ITP - Add general photos/comments below
label | 98819f33-3777-5676-8760-79d1548c8ef4 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checkpoint-group |  |  | section | After Column Pour
checkpoint-status |  |  | checkpoint | Confirm Surveyor is out next day to carry out survey of finished concrete Attach As built Survey Plan
label | 6f96d071-1fd3-5506-99cc-2ac25270bb45 |  | note | Attached below as applicable
checkpoint-status |  |  | checkpoint | Confirm tolerance of finished concrete surfaces are in accordance with the specifications
checkpoint-status |  |  | checkpoint | Confirm saw joints are installed to engineers requirements
checkpoint-status |  |  | checkpoint | Confirm finish of concrete is adequate for application (broom/trowel/helicopter finish), refer to AS3610
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 1 day, and attach test results
text | 78fcf0a7-4c34-54f8-ae26-550b5bf0aec4 |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Confirm initial stress is conducted day after the pour, after concrete has reached 10 MPa on 1 Day results
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 4 day, and attach test results
text | c9c29beb-13d2-597d-aeb0-0e446bd96e01 |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Confirm final stress has occurred after concrete has reached 20MPa, and attach Stressing Records
label | b66bb6d9-d41b-50e8-aa26-ad5ce916c808 |  | note | Attached below as applicable
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 7 day, and attach test results
text | 60d14f7c-09f8-5628-aa94-ed5616e21264 |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 28 day, and attach test results
text | a6d4fc3e-47e2-5749-9f05-e54620f8b9eb |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Attach Subcontractor ITP - Attached below as applicable
button | bab2f29c-7286-5a0b-93b0-636625c85d70 |  | button | Subcontractor Sign Off | Yes, No, N/A
button | fe9e5288-df17-5c0f-9d31-6adf62a89c8e |  | button | Aland Sign Off | Yes, No, N/A
holdpoint |  |  | signoff | Click to add Sign-Off Signatures
checklist-flat |  |  | checklist | Bike Rack |  |  |  |  | Yes | Bike Rack | dac9afe0-d3f9-4865-80dc-9899c6b7f2aa
checkpoint-status |  |  | checkpoint | Bike rack installed to manufacturers instructions & standards - Attach photos below
label | ca3ebe32-6fab-5c95-96b4-b4d76242cb82 |  | note | Ensure adequate fixings have been used & are tight
checklist-flat |  |  | checklist | Storage Room |  |  |  |  | Yes | Storage Room | dc275439-ca48-4068-9873-61175b4ebbd3
checkpoint-status |  |  | checkpoint | Storage lockers installed to manufacturers instructions & standards
checkpoint-status |  |  | checkpoint | Final sign off - All storage rooms installed as per the above ITP - Add general photos/comments below
label | 6e1801b0-50e4-5b7a-988c-a43f727704e5 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Apartment Fire System |  |  |  |  | Yes | Apartment Fire System | dc8a48db-4d8e-4ab9-9541-61b1224e6e4e
checkpoint-status |  |  | checkpoint | Smoke detectors & Sensors rough in completed
checkpoint-status |  |  | checkpoint | Smoke detectors & Sensors fit off completed
checkpoint-status |  |  | checkpoint | Smoke detectors & Sensors tested as per manufacturer's instructions
checkpoint-status |  |  | checkpoint | Sprinklers rough in completed
checkpoint-status |  |  | checkpoint | Sprinklers fit off completed
checkpoint-status |  |  | checkpoint | EWIS speakers installed as per manufacturers instructions
checkpoint-status |  |  | checkpoint | All fire signage installed correctly and visible - If applicable
checkpoint-status |  |  | checkpoint | Final sign off - Fire system installed as per the above ITP - Add general photos/comments below
label | 64d4d66d-7c8a-5223-8522-36bcbe5ba367 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Inspection Checklist |  |  |  |  | Yes | Inspection Checklist | e28b816d-8218-4ff5-8150-b9ca7e5724fc
checkpoint-status |  |  | checkpoint | Inspection Details
text | 3279ea90-8ed6-54fa-a633-cdbcab73f20e |  | textbox | Date of Inspection
text | 7e3798e3-5701-53b7-8971-07b2099171d5 |  | textbox | Inspection Type (Code)
text | ceb956c3-787d-5906-a86b-d42a3da1792e |  | textbox | Person/Company Inspecting
text | 0c250f07-0736-500a-b62e-a32e7b89ca81 |  | textbox | Area inspection relates to
checkpoint-status |  |  | checkpoint | Inspection outcome
select | 3c3ebc6a-95f1-5ca1-8677-79749addffed |  | dropdown | Inspection Result | Pass, Partial Pass, Fail, N/A
text | ed73bda7-d014-59a9-b7fc-bb6bdc4522a7 |  | textbox | Reason if Partial Pass or Failed
boolean | 625b5519-7eaa-5640-9bdc-add5dd0bf23a |  | tickbox | Inspection report attached below
label | 4911a68d-be8e-552b-9613-66134fccd7d3 |  | note | Remedial items to be photographed & Commented below
holdpoint |  |  | signoff | Request Sign-Off (3rd Party)
checkpoint-status |  |  | checkpoint | All Relevant Observation(s) Closed-Out & evidence attached - if applicable (Pass once completed)
holdpoint |  |  | signoff | Request Sign-Off (3rd Party)
checklist-flat |  |  | checklist | Suspended Slab |  |  |  |  | Yes | Suspended Slab | e2f73502-7c15-4082-8e4e-033ca79a782b
checkpoint-status |  |  | checkpoint | Materials used complies with design documentation
checkpoint-status |  |  | checkpoint | Datum point used & soffit RLs checked
checkpoint-status |  |  | checkpoint | Grids marked by builder
checkpoint-status |  |  | checkpoint | Surveyor points given for outside of building
checkpoint-status |  |  | checkpoint | Fillet & drip mould installed
checkpoint-status |  |  | checkpoint | Check set down position & RL
checkpoint-status |  |  | checkpoint | Check penetrations installed
checkpoint-status |  |  | checkpoint | Column blockouts installed
holdpoint |  |  | signoff | Request Sign Off from Site Engineer
checkpoint-status |  |  | checkpoint | Check back propping as per design
checkpoint-status |  |  | checkpoint | Blow off deck
checkpoint-status |  |  | checkpoint | Engage external consultant (engineer inspection)
checkpoint-status |  |  | checkpoint | Correct Class of Finish
checkpoint-status |  |  | checkpoint | Stripping, cleaning & materials removed
checkpoint-status |  |  | checkpoint | Final sign off - Suspended slab completed as per the above ITP - Add general photos/comments below
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 1 day, and attach test results
text | ac0bc984-6d8a-5e99-bafb-d9fe615d7afb |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Confirm initial stress is conducted day after the pour, after concrete has reached 10MPa on 1 Day results
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 4 day, and attach test results
text | 731ca016-5873-530d-87aa-ec6b5798c9c7 |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Confirm final stress has occurred after concrete has reached 20MPa, and attach Stressing Records
label | 450eaa21-0cb0-5832-8600-0e9d49f20e47 |  | note | Attached below as applicable
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 7 day, and attach test results
text | 0721004e-7038-53e6-894b-dbc91bc36779 |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 28 day, and attach test results
text | ecd1edba-d304-5d73-91e9-bd3a73c67cd9 |  | textbox | Test Strength Mpa
label | 61f3243b-8842-5cb2-b247-0214aceae912 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Underground Gas Checklist (V140421) |  |  |  |  | Yes | Underground Gas Checklist (V140421) | e50ce4aa-c85c-4f2d-9a5e-30edc4092f89
checkpoint-status |  |  | checkpoint | WorkSafe notification prior to trenching operations @ 15M deep or greater
checkpoint-status |  |  | checkpoint | Existing in-ground services located and verified before excavation
checkpoint-status |  |  | checkpoint | Site survey and confirm extent of works
checkpoint-status |  |  | checkpoint | Confirm area of work is accessable and acceptable to commence
checkpoint-status |  |  | checkpoint | Exclusion zone erected
checkpoint-status |  |  | checkpoint | Trench shoring/shield is on site
checkpoint-status |  |  | checkpoint | Excavation depths and locations confirmed prior to detailed excavation commencing
checkpoint-status |  |  | checkpoint | Bedding material is correct type, grade and depth
checkpoint-status |  |  | checkpoint | Gas service installed to correct depth of cover
checkpoint-status |  |  | checkpoint | Service indicator tape installed
checkpoint-status |  |  | checkpoint | joints are correct
checkpoint-status |  |  | checkpoint | Risers are in correct location - provide photos
checkpoint-status |  |  | checkpoint | Gas service tested to AS/NZS 56012013 Provide Photos
checkpoint-status |  |  | checkpoint | Trench suitably backfilled and compacted
checkpoint-status |  |  | checkpoint | Expansion lagging installed around pipes prior to concrete
checkpoint-status |  |  | checkpoint | clean up of work area
checkpoint-status |  |  | checkpoint | General photos, comments & observations during Cold Water Rough-In (Add below)
checkpoint-status |  |  | checkpoint | Underground Gas completed to specification/drawings & Area left clean/tidy
label | 5d72bec2-2810-50fb-8fc2-94aeb9aed24a |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-flat |  |  | checklist | Jump Form |  |  |  |  | Yes | Jump Form | e6367cff-014b-4841-a3c0-5acb1dfc73a8
checkpoint-status |  |  | checkpoint | Confirm Class of formwork to all faces, as per the latest specifications
checkpoint-status |  |  | checkpoint | Confirm RL's of soffit & beams
checkpoint-status |  |  | checkpoint | Confirm any penetration sizing for any hoist/crane penetrations
checkpoint-status |  |  | checkpoint | Ensure formwork frames installed to enable clear & labelled access under deck for other personnel & for inspections
checkpoint-status |  |  | checkpoint | Ensure all formwork surfaces are cleaned & no rubbish remains on any soffits,sides,base of work
checkpoint-status |  |  | checkpoint | Ensure bases of all columns/walls are cleaned out prior to pouring
checkpoint-status |  |  | checkpoint | Check formwork is completed as per specified Class
checkpoint-status |  |  | checkpoint | Ensure no rubbish or excess water is present prior to concrete pour
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checkpoint-status |  |  | checkpoint | Formwork stripped in a safe manner
checkpoint-status |  |  | checkpoint | All timbers de - nailed
checklist-sectioned |  |  | checklist | In-Ground Stormwater ITP (V140421) |  |  |  |  | Yes | In-Ground Stormwater ITP (V140421) | e8f96f10-c136-4c58-9da7-ba2d47f65b01
checkpoint-group |  |  | section | Pit and Pipes
checkpoint-status |  |  | checkpoint | Is Approval from Local Water Authority Required If so please provide permit
holdpoint |  |  | signoff | Sign Off Required
checkpoint-status |  |  | checkpoint | Details
text | 48127aa5-43c4-5726-aafa-44ea964fdf14 |  | textbox | Engineering Plan Number(s)
text | b3209950-c9d3-5ff6-9580-a928b74a2581 |  | textbox | Name of certified drainlayer and registration number
text | e4b9040a-56c4-52e7-9e53-fb3f532a72ba |  | textbox | Location (Pit to Pit)
text | 99a05c09-bbca-5353-bbad-d3d5d4fc9fa7 |  | textbox | Delivery Date (Pits and Pipes)
text | d74484fe-44fc-57a8-b4b0-31fc98e57c88 |  | textbox | Is work area clear and available for construction
text | 242b2042-a8a8-5003-a8f4-3bee8c1839a9 |  | textbox | Do you have the appropriate plant to perform scope of works Provide plant details
checkpoint-group |  |  | section | Trench/Excavation Methodology
checkpoint-status |  |  | checkpoint | Method
boolean | c7f06da1-d4f7-5bf7-8c53-aa138daeb9ae |  | tickbox | Sheild
boolean | 67055d81-1d55-55eb-91b0-9b7534afc8c5 |  | tickbox | Bench
boolean | 8b431399-17f4-59a1-b854-a89afb1146dc |  | tickbox | Batter
boolean | 603f5464-153b-5c77-869f-4fa9cc5b5849 |  | tickbox | Other
text | 87bb5d09-c23f-5fc5-94cf-f11b1bf0c595 |  | textbox | If other please specify
boolean | ff1fee5c-eff3-5a39-83dc-ace408448655 |  | tickbox | Certified / Tagged lifting Equipment
checkpoint-group |  |  | section | Product / Material check
checkpoint-status |  |  | checkpoint | Pits
text | f0e05536-21a4-5661-9acf-532a564862d3 |  | textbox | Type
text | fd6a4562-fb0e-5cb1-8199-34f03ceee6d5 |  | textbox | Size
checkpoint-status |  |  | checkpoint | Pipes
text | d3180144-51c0-57c2-8ee1-3db30f79cccf |  | textbox | Type
text | b2ac6d54-c741-5e06-b6cc-dc4e4be7ea72 |  | textbox | Size
checkpoint-status |  |  | checkpoint | Lot Connections
text | ee6bd475-8c50-56b8-aa98-7c4126a95f8f |  | textbox | Type
text | e7f0f7f3-f2c9-598a-9255-ce92bf015340 |  | textbox | Lot number Location
checkpoint-status |  |  | checkpoint | Bends
text | c9037a09-fa6f-5e18-b900-b00f76e78e22 |  | textbox | Location
text | 08c7ff02-63a2-56e7-a815-4cfb805dc8f4 |  | textbox | Type
text | c7fae1d4-004a-5a01-8445-a0d660f809f9 |  | textbox | Size
checkpoint-status |  |  | checkpoint | Quality Onsite Visual Inpection of Products / Materials - Defects to be Notified
text | cae2636d-4db2-5fb8-b296-9e1aa522681a |  | textbox | Surveyors name
checkpoint-status |  |  | checkpoint | Set out / Off Set Check
holdpoint |  |  | signoff | Sign Off Required
checkpoint-group |  |  | section | Pit Installation
checkpoint-status |  |  | checkpoint | Pits
text | 6a820800-b875-53b7-8da6-38742144091a |  | textbox | Bedding and backfill type as per detail
text | 5ace1d0c-54cb-5d5a-b1e8-d0204211a29d |  | textbox | Undercut weak unsuitable subgrade note chainage and depth ( Approval Required)
boolean | f3572820-65e1-5736-9e58-27c26ee703db |  | tickbox | Backfill to be compacted in 150mm Layers as per detail
boolean | b92566fe-2d3c-5025-9d5b-3a792c280cba |  | tickbox | External Concrete Bandage
boolean | 485534f8-150b-561d-ab16-7e3831190c18 |  | tickbox | Internal Benching
boolean | 1dde161c-2111-5952-8bbe-ee1df76b759f |  | tickbox | Internal Plastering / Render / Sealant
boolean | 3fea5960-87e5-5a23-976d-8cde7cf4bad7 |  | tickbox | Sealant Between Riser
boolean | 52817937-1d01-563d-869b-91359440caa5 |  | tickbox | Steps Required
text | a7b28fd1-8c0d-5b39-99a6-ecfae5005ec1 |  | textbox | Have pits been secure and covered during installation to reduce debris/silt
checkpoint-status |  |  | checkpoint | Pipe invert levels through pit as per design
holdpoint |  |  | signoff | Sign Off Required
checkpoint-group |  |  | section | Pipe installation
checkpoint-status |  |  | checkpoint | Pipes
boolean | 90aecfb4-7f4e-5feb-8700-ce9fe20cec30 |  | tickbox | Are pipes free and clean of debris before installation
text | 6402c56f-bddf-5cc0-86fd-946bca1cd994 |  | textbox | Bedding and backfill type as per detail
text | 0f08c38f-def1-530a-aeda-0b0d6dce6e61 |  | textbox | Undercut weak unsuitable subgrade note chainage and depth (Approval Required)
boolean | 0faec27b-373c-55f2-89c9-d93d13758156 |  | tickbox | Backfill to be compacted in 150mm Layers as per detail
checkpoint-group |  |  | section | Drainage Data
checkpoint-status |  |  | checkpoint | Backfill to be compacted in 150mm Layers as per detail
text | cb9564c6-4065-50ca-9d06-14a62eb328f9 |  | textbox | Grade and Alignment Check
text | a823603f-2668-55c9-9ca8-a48562ef47ce |  | textbox | Invert / RL Check
text | 3b92eb6c-4d23-5c24-853e-ab1f663cb17d |  | textbox | CCTV pipe inspection data and comments supplied
holdpoint |  |  | signoff | Sign Off Required
checkpoint-status |  |  | checkpoint | Progress Photos
checkpoint-group |  |  | section | Service Connections
checkpoint-status |  |  | checkpoint | All Connections, Bends, Junctions installed
text | f95dd6e9-63d0-5931-ac62-0c575f410913 |  | textbox | As-built measurements / Pick up Recorded Before Backfilling
holdpoint |  |  | signoff | Sign Off Required
checklist-sectioned |  |  | checklist | Detailed Excavation (V140421) |  |  |  |  | Yes | Detailed Excavation (V140421) | ec3598a8-8a6a-4be0-acf2-d8af27c9a4ff
checkpoint-group |  |  | section | Excavation - Pre-Commencement
checkpoint-status |  |  | checkpoint | Confirm dial before you dig documents are onsite - If applicable and attached below
checkpoint-status |  |  | checkpoint | Confirm correct disposal of classified material
checkpoint-status |  |  | checkpoint | Obtain geotech report, including load bearing capacity
label | 6ea0966d-674a-565d-ac26-ca17ef6eeb87 |  | note | Geotech report referenced or attached below
checkpoint-group |  |  | section | Excavation Works
checkpoint-status |  |  | checkpoint | Collection of tip dockets - If applicable and attached below
checkpoint-status |  |  | checkpoint | Confirm set out of boundaries & marked out
checkpoint-status |  |  | checkpoint | Confirm actual RL is within design tolerance
button | 2f8b1b6d-6198-5793-972d-789c0d988a62 |  | button | Confirm set out of footings and pads | Yes, No, N/A
button | cb6e5829-75a6-58c7-9bbe-6279dfa8306e |  | button | Confirm set out of in ground drainage | Yes, No, N/A
label | 02497b06-d821-59fa-a986-acf4d5227aae |  | note | Excavation of footings not to exceed size as detailed on structural drawings
checkpoint-status |  |  | checkpoint | Certifier to inspect foundation in accordance with specifications
checkpoint-status |  |  | checkpoint | Geotech inspection of footings etc
label | 779b6f3d-600f-558b-bc4f-d30685b1da8b |  | note | Geotech report referenced or attached below
checkpoint-status |  |  | checkpoint | Confirm top of concrete footings is below surrounding finishes
checkpoint-status |  |  | checkpoint | Confirm sub-base is in line with engineers specifications/requirments
text | cfdf2094-7355-566b-9621-5aca486406b6 |  | textbox | Minimum thickening (MM)
checkpoint-status |  |  | checkpoint | Civil engineer inspection carried out - Attached below as applicable
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Attach Subcontractor ITP - Attached below as applicable
button | 1d7c33a6-91d0-58f0-ad91-a1d5d0a6de35 |  | button | Subcontractor Sign Off | Yes, No, N/A
button | adffe30a-8d39-5ae5-a238-9514fb328ddf |  | button | Aland Sign Off | Yes, No, N/A
holdpoint |  |  | signoff | Click to add Sign-Off Signatures
checklist-flat |  |  | checklist | Carpet |  |  |  |  | Yes | Carpet | ed71bb96-afd3-4a69-86ca-27699f17b3bb
checkpoint-status |  |  | checkpoint | Correct underlay installed to specification(s)
checkpoint-status |  |  | checkpoint | Correct carpet (Colour & Type) installed to Specification(s)
checkpoint-status |  |  | checkpoint | Carpet installed as per manufacturer's instructions
label | dca1cfd9-b214-502c-b35d-8550a4f76494 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-sectioned |  |  | checklist | Rock Anchoring |  |  |  |  | Yes | Rock Anchoring | ee05135b-25f0-41dc-a0bf-c8562e1f2fe4
checkpoint-group |  |  | section | Prior to Works Commencing
checkpoint-status |  |  | checkpoint | Locate all existing services
checkpoint-status |  |  | checkpoint | Confirm set out and RL
checkpoint-status |  |  | checkpoint | Confirm type of anchor to be used
checkpoint-status |  |  | checkpoint | Confirm the working load of the anchor/ tendon
checkpoint-status |  |  | checkpoint | Confirm minimum depth for anchors
checkpoint-status |  |  | checkpoint | Confirm angle of anchors
checkpoint-status |  |  | checkpoint | Confirm strength of grout required
checkpoint-status |  |  | checkpoint | Confirm de-stressing procedure for anchors with engineer
label | e1af3978-8920-51bd-a977-21a540b72de4 |  | note | Engineer procedure notes added below
checkpoint-group |  |  | section | During Works
checkpoint-status |  |  | checkpoint | Confirm anchors are not damaged during insertion into bore hole
checkpoint-status |  |  | checkpoint | Confirm number of strands is in accordance with engineer drawings
checkpoint-status |  |  | checkpoint | Confirm bore hole is being flushed clean – water/ air
checkpoint-status |  |  | checkpoint | Confirm grouting is taking place same day
checkpoint-status |  |  | checkpoint | Confirm bond and free lengths have been met in accordance with engineer drawings
checkpoint-status |  |  | checkpoint | Confirm grout testing is taking place (results to be returned 28 days later)
checkpoint-status |  |  | checkpoint | Confirm design boreholes design depth has been reached and do not require re-drilling
checkpoint-group |  |  | section | After Works
checkpoint-status |  |  | checkpoint | Confirm grouting is reaching required strength after 7 days
checkpoint-status |  |  | checkpoint | Confirm stressing works have been completed
checkpoint-status |  |  | checkpoint | Confirm testing has been completed and passed loading test
checkpoint-status |  |  | checkpoint | Confirm anchors have not moved during testing
checkpoint-status |  |  | checkpoint | Confirm if additional anchors are required
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Attach Subcontractor ITP - Attached below as applicable
button | c22ba754-09fe-513e-9d34-08e94a7f3c85 |  | button | Subcontractor Sign Off | Yes, No, N/A
button | a2be0f77-1685-5fda-873a-80efefcd79f6 |  | button | Aland Sign Off | Yes, No, N/A
holdpoint |  |  | signoff | Click to add Sign-Off Signatures
checklist-flat |  |  | checklist | Underground Fire Service Checklist (V140421) |  |  |  |  | Yes | Underground Fire Service Checklist (V140421) | eef1fa01-b16d-42fc-8008-3d27f1a735bc
checkpoint-status |  |  | checkpoint | WorkSafe notification prior to trenching operations @ 15M deep or greater
checkpoint-status |  |  | checkpoint | Existing in-ground services located and verified before excavation
checkpoint-status |  |  | checkpoint | Site survey and confirm extent of works
checkpoint-status |  |  | checkpoint | Confirm area of work is accessable and acceptable to commence
checkpoint-status |  |  | checkpoint | Exclusion zone erected
checkpoint-status |  |  | checkpoint | Trench shoring/shield is on site
checkpoint-status |  |  | checkpoint | Excavation depths and locations confirmed prior to detailed excavation commencing
checkpoint-status |  |  | checkpoint | Bedding material is correct type, grade and depth
checkpoint-status |  |  | checkpoint | Fire service installed to correct depth of cover
checkpoint-status |  |  | checkpoint | Service indicator tape installed
checkpoint-status |  |  | checkpoint | joints are correct
checkpoint-status |  |  | checkpoint | Risers are in correct location - provide photos
checkpoint-status |  |  | checkpoint | Fire service tested to AS/NZS35002018, AS24192017 Provide Photos
checkpoint-status |  |  | checkpoint | Trench suitably backfilled and compacted
checkpoint-status |  |  | checkpoint | Expansion lagging installed around pipes prior to concrete
checkpoint-status |  |  | checkpoint | clean up of work area
holdpoint |  |  | signoff | Completion sign off
checkpoint-status |  |  | checkpoint | Independent inspection and testing complete
checkpoint-status |  |  | checkpoint | General photos, comments & observations during Cold Water Rough-In (Add below)
checkpoint-status |  |  | checkpoint | Underground Fire Service completed to specification/drawings & Area left clean/tidy
label | ee435b22-32f1-5d6e-b59a-555d347c34dc |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-flat |  |  | checklist | Joinery Fit Out |  |  |  |  | Yes | Joinery Fit Out | f009b5ef-4ded-4f18-89d4-c946ce462165
checkpoint-status |  |  | checkpoint | Shower screen has been installed level & tested
checkpoint-status |  |  | checkpoint | Door hardware has been installed & tested
checkpoint-status |  |  | checkpoint | Window & slider frames have been installed & fixed correctly
checkpoint-status |  |  | checkpoint | Sliders have visibility decals installed
checkpoint-status |  |  | checkpoint | All kitchen joinery & installed
checkpoint-status |  |  | checkpoint | Final sign off - All joinery fit out work completed as per the above ITP
label | 6d5cda96-c507-5b2c-a794-803775d42e5d |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Corridor/Common Area Fire System |  |  |  |  | Yes | Corridor/Common Area Fire System | f04f362a-685d-46f3-b3d8-f53918f7b6af
checkpoint-status |  |  | checkpoint | FIP installed as per manufacturer's instructions
checkpoint-status |  |  | checkpoint | FIP tested & commissioned
checkpoint-status |  |  | checkpoint | Smoke detectors & Sensors rough in completed
checkpoint-status |  |  | checkpoint | Smoke detectors & Sensors fit off completed
checkpoint-status |  |  | checkpoint | Smoke detectors & Sensors tested as per manufacturer's instructions
checkpoint-status |  |  | checkpoint | EWIS speakers installed as per manufacturers instructions
checkpoint-status |  |  | checkpoint | All fire signage installed correctly and visible
checkpoint-status |  |  | checkpoint | Magnetic door holder fitted and functioning correctly on all fire exits
checkpoint-status |  |  | checkpoint | Final sign off - Fire system installed as per the above ITP - Add general photos/comments below
checklist-flat |  |  | checklist | Blade Walls |  |  |  |  | Yes | Add Blade Walls | f4c2d55c-ef7c-42bb-9cba-7f7ab8f9f53c
checkpoint-status |  |  | checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
checkpoint-status |  |  | checkpoint | Setout & alignment as per drawing (include revision below)
text | 8a49a7e8-677b-55fb-b240-501dca912245 |  | textbox | Drawing & revision number(s)
checkpoint-status |  |  | checkpoint | Survey points given for 2 points
checkpoint-status |  |  | checkpoint | Land shutter bracing props secured plumb shutter
checkpoint-status |  |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status |  |  | checkpoint | Blockouts steps penetrations marked & installed
checkpoint-status |  |  | checkpoint | Steel tied & clear from Z bar holes
checkpoint-status |  |  | checkpoint | Couplers & rebate boards installed
checkpoint-status |  |  | checkpoint | Base of walls cleaned
checkpoint-status |  |  | checkpoint | Leave a piece of AFS out every 6 m where a stock length of reo will lap in order to ensure horiztontal bars are tied, lap is maintained & compaction can be physically viewed at this point
checkpoint-status |  |  | checkpoint | Closing shutter installed
checkpoint-status |  |  | checkpoint | Z bars secured wall straight & plumbed
checkpoint-status |  |  | checkpoint | Correct Class of Finish
checkpoint-status |  |  | checkpoint | Final sign off - Walls completed as per the above ITP - Add general photos/comments below
label | f37788d5-b88e-532e-a30f-66e378995315 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Internal Painting |  |  |  |  | Yes | Internal Painting | f4ef3b92-2386-4b73-8bd8-d96819bcd262
checkpoint-status |  |  | checkpoint | Ensure to use right product & system as per specification & scope of works
checkpoint-status |  |  | checkpoint | Provide adequate ventilation & removal of waste disposed correctly
checkpoint-status |  |  | checkpoint | Final sign off - All internal painting work completed as per the above ITP
label | e2091e72-dec6-5f4e-86a2-e775ff01e565 |  | note | HOLDPOINT - Once all above items have been signed off work may proceed
checklist-flat |  |  | checklist | Underground Water Checklist (V140421) |  |  |  |  | Yes | Underground Water Checklist (V140421) | f910b911-772c-42f6-8cae-bca48c6c2347
checkpoint-status |  |  | checkpoint | WorkSafe notification prior to trenching operations @ 15M deep or greater
checkpoint-status |  |  | checkpoint | Existing in-ground services located and verified before excavation
checkpoint-status |  |  | checkpoint | Site survey and confirm extent of works
checkpoint-status |  |  | checkpoint | Confirm area of work is accessable and acceptable to commence
checkpoint-status |  |  | checkpoint | Exclusion zone erected
checkpoint-status |  |  | checkpoint | Trench shoring/shield is on site
checkpoint-status |  |  | checkpoint | Excavation depths and locations confirmed prior to detailed excavation commencing
checkpoint-status |  |  | checkpoint | Bedding material is correct type, grade and depth
checkpoint-status |  |  | checkpoint | Water service installed to correct depth of cover - Provide photos
checkpoint-status |  |  | checkpoint | Service indicator tape installed
checkpoint-status |  |  | checkpoint | joints are correct - Provide photos
checkpoint-status |  |  | checkpoint | Risers are in correct location - provide photos
checkpoint-status |  |  | checkpoint | Water service tested to AS/NZS 35002018 Provide Photos
checkpoint-status |  |  | checkpoint | Trench suitably backfilled and compacted
checkpoint-status |  |  | checkpoint | Expansion lagging installed around pipes prior to concrete
checkpoint-status |  |  | checkpoint | clean up of work area
checkpoint-status |  |  | checkpoint | General photos, comments & observations during Cold Water Rough-In (Add below)
checkpoint-status |  |  | checkpoint | Underground Water completed to specification/drawings & Area left clean/tidy
label | e879f806-9b0e-5f4d-a790-ae54eb9dd4eb |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-flat |  |  | checklist | Mandatory Inspections |  |  |  |  | Yes | Mandatory Inspections | ff0e9c04-d305-4267-92fd-4563e84e1cdd
checkpoint-status |  |  | checkpoint | Consent
text | f194aa92-76de-50b9-a7b1-a7da7a1d9dbe |  | textbox | DA/CDC No
text | 0c6a678e-5ba3-5a5e-81f2-3f1a7d7ce4f5 |  | textbox | CC No
label | 92149130-b2f9-5592-941d-e642e3badb37 |  | note | The Following are Critical Stage Mandatory Inspections - They are required pursuant to Section 65 (b) of the Act & Clause 162A of the Regs
label | bfc15b02-a031-5c3e-82be-5b50e8a4246c |  | note | In the case of a class 2, 3 or 4 building
checkpoint-status |  |  | checkpoint | (a) after the excavation for, and prior to the placement of, any footing, and
checkpoint-status |  |  | checkpoint | (b) prior to covering of fire protection at service penetrations to building elements that are required to resist internal fire or smoke spread, inspection of a minimum of one of each type of protection method for each type of service, on each storey of the building comprising the building work, and prior to covering the junction of any internal fire-resisting constructions bounding a sole-occupancy unit, and any other building element required to resist internal fire spread, inspection of a minimum of 30% of sole-occupancy units on each storey of the building containing sole-occupancy units, and
checkpoint-status |  |  | checkpoint | (c) prior to the covering of waterproofing in any wet areas, for a minimum of 10% of rooms with wet areas, and
checkpoint-status |  |  | checkpoint | (d) prior to covering any stormwater drainage connections, and
checkpoint-status |  |  | checkpoint | (e) after the building work has been completed and prior to any occupation certificate