## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP-012-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0012 - Kerb and Channel | 077a9954-51c3-4509-bd1e-92dab7d13edb
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | f9086920-3640-52b5-b534-1360935b2cfe |  | date | Lot Created On
date | bbb3a5ac-c1c3-52fd-89b0-89bbc3c866ff |  | date | Lot Opened On
date | 63a51cc8-e908-5787-a1d4-527542bfc1c4 |  | date | Work Commenced On
select | 8d6a3fb5-6077-5220-bcf1-9010c782ee68 |  | dropdown | Lot Type | CIL-Civil Lot, DRL- Drainage Lot, EAL- Earthworks Lot, ELL- Electrical Lot, UTL- Utility Lot, STL- Structural Lot
text | 94a85f93-e25a-5a90-8e1b-5e5dc06973a1 |  | textbox | From and To Chainage
select | 6efbdcfe-260c-5142-b04a-c0ce9d2761a0 |  | dropdown | Construction Element | STOR - Stormwater
select | db5aa33e-34a9-5f4e-acdf-0baa93a538b2 |  | dropdown | Activity | KERC - Kerb & Channel
select | d4bb6e69-a07d-5ee9-92b5-8411c12c22ab |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | df21f506-9b6a-5bcd-854e-db315d148ba0 |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | 2122ebf3-f033-5106-aa36-8032955e8453 |  | textbox | Engineer Responsible
text | a0d15c84-0b02-58b3-bdc7-bcc60ccf508d |  | textbox | comments
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Check that current revision drawings are being used
label | 03c3c4f4-d4e1-5c29-8ef0-925f9efad60e |  | note | Frequency: Prior to Commencing
label | 19cb669f-345a-58e1-9799-357b4ce36337 |  | note | - - - - - - - - -
label | f69a62fd-e529-5e60-b94e-798d05f53833 |  | note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
label | db884241-f9cd-5017-b4e1-57a6290b1c8f |  | note | - - - - - - - - -
label | 6e3a1ed5-23ed-58a1-a382-4a546eab3adb |  | note | Reference Documents: Project Drawings / Drawing Register
label | c825b2e8-7bf3-5b06-803f-9576c6d65beb |  | note | - - - - - - - - -
label | 4d0399d7-b590-5d75-9a42-f0c5a7409a64 |  | note | Inspection / Test Method: Document review
label | 7ea51c3e-5e71-569d-b747-6eeb6bfe57f2 |  | note | - - - - - - - - -
label | eed3bd26-7d4f-5b64-add1-26e58fc92285 |  | note | Record of conformity: Latest Revision Drawings
label | 40903d2a-0149-58a8-860c-ec2322d86e24 |  | note | - - - - - - - - -
label | b2207207-aefd-5798-a795-05eec10772f1 |  | note | AP
label | 88be3834-aedf-514c-9eeb-5a25dd29ff5a |  | note | - - - - - - - - -
label | 761f938a-8ec3-59d8-a660-4c85502a69c6 |  | note | Responsibility: Site Engineer / Site Foreman
checkpoint-status |  |  | checkpoint | 1.2 - Mix design
label | 8402a322-29a7-5d82-9059-6f0bed4a86fd |  | note | Frequency: Prior to commencing
label | 69c131fe-c6ec-5ee7-8319-9c753330c2a4 |  | note | - - - - - - - - -
label | 8a58f279-0fcc-5f11-9bc6-4f7aaa57f1ea |  | note | Acceptance Criteria: Approved VR mix design to be used. Concrete being placed via extrusion machines have minimum cement content of 320 kg kg/m3. Where K&C is placed and compacted with internal vibration between previously placed formwork, concrete shall be: N32 portland cementâ€“based concrete
label | 2a140213-ef47-5ef2-b4f5-10397a7b9ff6 |  | note | - - - - - - - - -
label | 7e44499a-3c4a-56fe-a268-9bf72c727267 |  | note | Reference Documents: SD2001, AS1379, Section 703.05, 703.06, 703.07
label | 79178f8f-f039-5950-a9d7-a2a3dbb0c284 |  | note | - - - - - - - - -
label | 85a00654-8492-53b6-8aa2-fab50f8e7258 |  | note | Inspection / Test Method: Document Review
label | 9803f13f-62cd-5bd8-a141-c63f9c7a1106 |  | note | - - - - - - - - -
label | acf23adb-7712-56d2-98f0-cc703b32c967 |  | note | Record of conformity: ITP signed/Mix Design Certificate
label | 766ce301-2ae8-5b9e-b5f3-f01d18dd0da5 |  | note | - - - - - - - - -
label | 452adfdc-b499-5ca0-9f1b-931b33891670 |  | note | HP
label | c59a2826-bfb7-560a-af34-1f48319daa5c |  | note | - - - - - - - - -
label | 8f7794e5-a1ae-5a58-9649-6f8bd8b89787 |  | note | Responsibility: Site Engineer & Superintendent
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3 - Bedding Material
label | 4775c70d-8bfc-5b55-a131-bf7bc25ead3b |  | note | Frequency: Prior to commencing
label | 9f8e369c-e07c-5d80-ab74-3498a1bc67e3 |  | note | - - - - - - - - -
label | a63e8390-71a7-5d2f-a0f4-d2df9efddf61 |  | note | Acceptance Criteria: Bedding shall be size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
label | 68e3f42a-051a-5667-bfe3-60dc937e9496 |  | note | - - - - - - - - -
label | f04e0088-6ebb-5045-a239-4ed644bba863 |  | note | Reference Documents: Section 703.21 IFC Drawings
label | 32b12911-b423-5d72-a7c4-6d0fe8e3cf58 |  | note | - - - - - - - - -
label | 11e822cb-cee6-5aad-b6e0-250915899735 |  | note | Inspection / Test Method: Verify
label | 6a6980c8-384c-5592-9e51-a749e7993389 |  | note | - - - - - - - - -
label | 088441f9-8ad3-5d3d-9974-ff87e431d47d |  | note | Record of conformity: Material Conformance Certificate
label | 1a34448e-0115-50f1-bf51-9609474f3082 |  | note | - - - - - - - - -
label | 18333a42-7222-598a-8861-6167358890d5 |  | note | HP*
label | d3b80ada-03f5-58e3-ae09-1c4f26a95a83 |  | note | - - - - - - - - -
label | f6843afd-7ac7-5ae3-90f1-6be39f506516 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 1.4 - Curing Compound
label | 79c9f203-98ad-5818-875c-f06c33514318 |  | note | Frequency: Prior to commencing
label | 5c2553fc-a64c-589f-819b-fe4c4d1952ab |  | note | - - - - - - - - -
label | 8921b2dd-67d7-5cad-83bb-e53fe8ceee05 |  | note | Acceptance Criteria: Curing compound shall comply with AS3799
label | 31b71ab9-77fb-523d-8b20-fa2857ffd1ff |  | note | - - - - - - - - -
label | 45a54779-2b26-5daf-9d60-2d785595aea1 |  | note | Reference Documents: Section 703.10
label | 319fe73e-f956-581e-9089-a45437a14fed |  | note | - - - - - - - - -
label | 5926d2da-f316-5c37-a0d3-a3acb0f95283 |  | note | Inspection / Test Method: Verify
label | 103ec1e8-3927-5324-a724-37376e0db1c1 |  | note | - - - - - - - - -
label | dc1e60a5-7270-5892-810a-78a5f1bcc90e |  | note | Record of conformity: Material Conformance Certificate
label | 8db88d2b-0d33-530f-abf9-71a1098b74c5 |  | note | - - - - - - - - -
label | 5e5809ec-b868-59c5-8763-713cd3f5fd08 |  | note | HP*
label | 2ac15609-1b6b-5d20-ba36-b8a446bbf1d8 |  | note | - - - - - - - - -
label | 30e36550-82a0-529b-b6c6-a0a5d3a4564c |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 1.5 - Temporary drainage provisions
label | 0600bce6-790d-5594-97ed-3c85933f3d55 |  | note | Frequency: Prior to commencing
label | 66681e01-1050-553f-a602-00031c8a0acd |  | note | - - - - - - - - -
label | a2cdc689-fc98-5ff1-921e-5117eacf6a92 |  | note | Acceptance Criteria: If obstructing waterways ,culverts or channels, temporary diversion of discharge of drainage and storm water to be in place. Need to obtain prior written approval from the relevant waterway authority prior to diversion.
label | b187ca6e-cb8f-5b4f-857a-342d47a7ec48 |  | note | - - - - - - - - -
label | 7e6fce1b-b231-52a1-a298-d2d19c22a81b |  | note | Reference Documents: Section 703.18
label | 7072b56d-3834-5eb5-a15d-d386a65563c4 |  | note | - - - - - - - - -
label | 44ddafe7-524d-534f-a1d1-6be37eef9f30 |  | note | Inspection / Test Method: Visual inspection
label | e2b8e451-71a6-5bd6-b2b0-34ce674dda61 |  | note | - - - - - - - - -
label | cd1f74bd-9b64-59ee-88b1-a57c306673f3 |  | note | Record of conformity: ITP signed
label | 8664d83f-9264-53f4-9292-6f5a939ad91f |  | note | - - - - - - - - -
label | 4fafd8b5-6411-5a25-adba-c3da85ad844b |  | note | HP*
label | f294ba5e-69a9-570b-9d35-48bfc4bdf7ca |  | note | - - - - - - - - -
label | b945e4bd-1334-51e6-87ec-0470565dd98d |  | note | Responsibility: Site Engineer / Site Foreman
checkpoint-group |  |  | section | 2 - Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 2.1 - Setting out
label | 821a3170-a6a8-5a6b-b4d5-53649493e1a2 |  | note | Frequency: Prior to start
label | 1fd94a6a-c059-5d56-b5c7-326ee60e3d81 |  | note | - - - - - - - - -
label | bf4cd62a-9ba8-58fa-af3b-132f7c6fb71f |  | note | Acceptance Criteria: Set out work in accordance with drawing. The superintendent will review and confirm set out. The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | eddf8786-7871-5139-b6eb-af5421903b33 |  | note | - - - - - - - - -
label | c4ec2608-2551-5e80-b2e4-31216ce5066e |  | note | Reference Documents: Section 703.17
label | c0476831-9053-5b91-aeda-a9712ff75418 |  | note | - - - - - - - - -
label | de1c781c-4db2-519c-a89e-68055b0e4b48 |  | note | Inspection / Test Method: Site Inspection
label | 392fc2b1-2ec8-5b48-81f7-0224905f1dc1 |  | note | - - - - - - - - -
label | 73dcc3d2-81c9-500d-8225-c94bddf52680 |  | note | Record of conformity: ITP signed
label | 3fe78624-fbb1-5149-9f54-44b372f67f38 |  | note | - - - - - - - - -
label | 1d40f2ab-bde0-5794-aadc-cdc4071ebdef |  | note | HP
label | 88c654ed-086d-5f09-9fa8-2da9b270584f |  | note | - - - - - - - - -
label | 6da70bdc-1387-5479-8591-c2119738191e |  | note | Responsibility: Site Engineer & Superintendent
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.2 - Bedding
label | 32f51d7d-ca9c-5dfc-ab22-9bc111f23cea |  | note | Frequency: Each lot
label | 7364b37f-4305-5e6b-8e77-0a4e889db7d9 |  | note | - - - - - - - - -
label | a5fb4d9b-d48c-547f-8725-9e67875ee79e |  | note | Acceptance Criteria: Bedding to be compacted to a thickness of not less than 100mm. Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted .
label | bc5de1ec-3e35-52df-91f7-debca994ec17 |  | note | - - - - - - - - -
label | 3b8ea6a7-2ac4-54ed-b351-b79c8034eda5 |  | note | Reference Documents: Section 703.21
label | 72e9b41a-e907-51fa-81f3-fcd19c2a01fa |  | note | - - - - - - - - -
label | 07fd3614-1b05-56f8-8c2a-2112afa5a306 |  | note | Inspection / Test Method: Site Inspection
label | 5c7b111a-0ea8-50d3-9749-57835207e7d2 |  | note | - - - - - - - - -
label | b53745d7-f489-5877-bf9a-9d41bd48e4ce |  | note | Record of conformity: ITP signed
label | 5726c0b6-cbc4-5871-bf0f-7ec863332886 |  | note | - - - - - - - - -
label | 604f5faf-f2b3-561b-b596-c782f52886a2 |  | note | WP
label | cb8d0801-a90d-5543-a811-111551b54ea7 |  | note | - - - - - - - - -
label | 3b73eff6-b946-5c87-beaa-7e2d4586835d |  | note | Responsibility: Site Engineer & Superintendent
checkpoint-status |  |  | checkpoint | 2.3 - Formwork
label | d0bd00e6-2bac-5002-9fc2-b556feaa0902 |  | note | Frequency: Each lot
label | 2f2305a1-95ae-5f66-a784-a0564478817d |  | note | - - - - - - - - -
label | 023a91df-5388-5358-a8f8-3c4b5ab07e0f |  | note | Acceptance Criteria: Joints in formwork shall be constructed such that loss of mortar is prevented. Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
label | 12150cc8-a621-544e-81f7-16e873e35373 |  | note | - - - - - - - - -
label | 9c6c2094-1aa1-5fdf-a4fe-41eddc8e91e3 |  | note | Reference Documents: Section 703.12 AS3610
label | ebeb75b4-57a6-5979-a2e7-cce59c3c8ffe |  | note | - - - - - - - - -
label | e0daa7a6-5c67-5f28-8dc5-690f661a286f |  | note | Inspection / Test Method: Site Inspection
label | ff931d15-8aac-5e02-9a2a-90b468cea219 |  | note | - - - - - - - - -
label | 63974bb4-6606-5576-b2ff-f63f47ebf2e8 |  | note | Record of conformity: ITP signed
label | 4ef25b73-0276-5af7-8426-db37246661e8 |  | note | - - - - - - - - -
label | 59948fd6-8e5c-5d24-a6d9-ca80e819fc7b |  | note | WP
label | 333e53cd-8b39-50a6-af3f-179ca2d965d0 |  | note | - - - - - - - - -
label | 7aef8986-6d4d-5d98-8d12-34746b67e4ed |  | note | Responsibility: Site Engineer & Superintendent
checkpoint-status |  |  | checkpoint | 2.4 - Pre Pour Check
label | 5067fef1-782a-5309-8022-7cc5daeeb03e |  | note | Frequency: Each lot
label | 279fc57d-fffd-5197-be32-a3eb4cbad130 |  | note | - - - - - - - - -
label | 2b021afd-c980-5967-89f4-89104442fb72 |  | note | Acceptance Criteria: Bedding shall be moist but shall have no free water on the surface. Concrete shall not be placed when the air temperature measured at the point of placement is > 35Â°C or < 5Â°C
label | 9f93d2b3-080a-55d5-9a22-7f7b8dff3022 |  | note | - - - - - - - - -
label | 7248d0b7-2ffd-5b25-a1d2-ffc793603ce8 |  | note | Reference Documents: Section 703.09 Section 703.21 Section 610.17a), b) & c)
label | 52c437f5-97e5-5dc4-a492-fde10689e93d |  | note | - - - - - - - - -
label | a703bfd7-24b9-5126-b65f-fbfe29018e8d |  | note | Inspection / Test Method: Site Inspection
label | 5d08a497-feaa-5ef7-a4fe-d542f48a5322 |  | note | - - - - - - - - -
label | 435d3ba5-7151-5dae-a358-2a011ddf60bf |  | note | Record of conformity: ITP signed Ambient temperature-----Â°C
label | 0eb5447d-22e3-585b-97bd-dca5a429f345 |  | note | - - - - - - - - -
label | 9b9ff796-9a78-5684-9f1d-81acd29c20e0 |  | note | HP*/WP
label | 78883e20-f4c0-54ba-80d5-5da21bd3f3a7 |  | note | - - - - - - - - -
label | 9babebc4-1980-5084-9a97-f2951320673d |  | note | Responsibility: Site Engineer/Site superintendent
checkpoint-status |  |  | checkpoint | 2.5 - Concrete placement
label | a1a2bc3f-d385-51de-8dee-0486316f380b |  | note | Frequency: Each lot
label | 9c9a82cc-ff45-5df3-8490-5625afece3e7 |  | note | - - - - - - - - -
label | 8d485fc2-d95b-51de-b350-b89a149b25d2 |  | note | Acceptance Criteria: Temperature of concrete to be measured immediately prior to placing and shall not be less than 10Â°C or greater than 32Â°C. Concrete is to be satisfactorily compacted so that finished surface are free from surface pitting larger than 5mm diameter, honey combing or faulty patches. Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints. Machine Extrusion: Concrete is to be fed to extrusion machine at a uniform rate.
label | 6ddb3cb3-30e2-5097-ba31-24464ca72efd |  | note | - - - - - - - - -
label | 2d8daf94-5ebf-56a5-a4ec-62add5307301 |  | note | Reference Documents: Section 703.08 Section 703.23
label | b5aca965-4853-58d9-bbc5-55389eb118e3 |  | note | - - - - - - - - -
label | 954a5e5b-1ee7-5766-b883-224937dbc3b6 |  | note | Inspection / Test Method: Site Inspection
label | 94c038bd-7161-5a16-a247-c44cdb347cfe |  | note | - - - - - - - - -
label | d1dbd245-143e-5019-a21c-7653228da3c2 |  | note | Record of conformity: ITP signed Concrete Temperature ---Â°C
label | 9fc81721-0984-5ba5-93d7-08c3272b6ff9 |  | note | - - - - - - - - -
label | f8e1de68-99f4-5042-adb2-c893d04bd783 |  | note | IP
label | a8b1d499-c51a-56ff-b86c-6d00e4903fc0 |  | note | - - - - - - - - -
label | a6012995-dbc4-5192-8409-5bd99a0fbbef |  | note | Responsibility: Site engineer
checkpoint-status |  |  | checkpoint | 2.6 - Transitions
label | ff482e61-8ae7-5902-93ac-014454eb25b2 |  | note | Frequency: Each lot
label | 8153e2ec-b361-5630-9ce3-3e463d856e40 |  | note | - - - - - - - - -
label | 72b6843e-3974-5ec8-b738-b5f9054edca1 |  | note | Acceptance Criteria: Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
label | 06f8c096-dda6-5c2b-a225-ede3194325af |  | note | - - - - - - - - -
label | ce4dad3a-bc76-595d-bb44-c09c091d3fbf |  | note | Reference Documents: Section 703.24
label | f4e2120a-b121-55c3-a714-304e6fdd9c7d |  | note | - - - - - - - - -
label | c782e203-b91c-5a3a-9d3a-7c277beb0dbc |  | note | Inspection / Test Method: Site Inspection
label | fcec476c-df77-5dfc-a245-578f1fdb0c4d |  | note | - - - - - - - - -
label | 8857833d-a148-58e1-a686-7adfa9feed98 |  | note | Record of conformity: ITP Signed
label | bfed5462-e8b1-5c9e-9133-8a8d83f6ab48 |  | note | - - - - - - - - -
label | e20b6887-2c05-5c64-9683-00964bed69d8 |  | note | IP
label | 68616c8d-ab15-5a6a-a7ae-210eb4130ce5 |  | note | - - - - - - - - -
label | a72cd6b1-c9bc-5b52-9481-4624e8805eee |  | note | Responsibility: Site engineer
checkpoint-status |  |  | checkpoint | 2.7 - Surface Finish
label | 8f424198-14a0-51de-9a6d-53a46a147545 |  | note | Frequency: Each lot
label | e91afee6-07c7-5539-9655-afb1330ad92a |  | note | - - - - - - - - -
label | 61d5fdbc-5759-5585-af76-db2da4e7a0ff |  | note | Acceptance Criteria: All edgings shall be rendered to a thickness not exceeding 3mm and trowel finished. Renderings shall be applied within 30 minutes of extrusion. Concrete to have a neat appearance and uniform colour. Class 3 finish required for external surfaces. Class 4 finish required for permanently hidden surfaces.
label | 25669f6d-64c6-5a46-adf1-66f817528aea |  | note | - - - - - - - - -
label | 18744e27-6b5e-5bb5-bea4-b8b34257c7e4 |  | note | Reference Documents: Section 703.25
label | 14547fda-c5ab-5663-b891-081927b67379 |  | note | - - - - - - - - -
label | 8dd59177-931e-57cc-9d25-2ae4bf8ebd6c |  | note | Inspection / Test Method: Site Inspection
label | ffa44311-3d6b-5e77-8a98-db51f9a16f98 |  | note | - - - - - - - - -
label | 5887467a-d670-56d1-a74d-018883a12ac5 |  | note | Record of conformity: ITP signed
label | 56762e4a-3fdd-5c0a-a356-9d8cbf5a87cd |  | note | - - - - - - - - -
label | bc9f39b0-272c-561a-9a9c-691d0c8ed6c1 |  | note | IP
label | d460f7af-b488-50f6-927e-f9bc9ed27786 |  | note | - - - - - - - - -
label | a980acd9-0edd-5080-9a2b-eb41fc045fa4 |  | note | Responsibility: Site Engineer/ Site Foreman
checkpoint-status |  |  | checkpoint | 2.8 - Formwork Stripping
label | 2078b6e4-1685-5488-b93b-ad2dc69bf3e0 |  | note | Frequency: Each lot
label | f0aa4512-ce1a-5f92-bb19-eade37a81cdc |  | note | - - - - - - - - -
label | f605859d-75f5-599a-9952-6a6253f49b5c |  | note | Acceptance Criteria: Formwork shall not be stripped before the minimum time of: External faces 2 days Permanently hidden faces 1 day
label | 99fe3bd9-01ee-59ff-899d-76799d2f7dbc |  | note | - - - - - - - - -
label | cf918bfe-f4a4-534b-859a-87ae5ed53cbd |  | note | Reference Documents: Section 703.12 AS3610
label | d683cbc3-d023-5375-a499-1153068123a3 |  | note | - - - - - - - - -
label | 8f441eee-bd09-53be-b301-2f11d8c17160 |  | note | Inspection / Test Method: Site Inspection
label | c32f3e19-4b3b-5005-9857-a1a7b5d28ad7 |  | note | - - - - - - - - -
label | 37841320-38f2-5a79-8a77-3dc7e94d518b |  | note | Record of conformity: ITP signed
label | 72b457ff-ef8c-5abe-8aab-89be9d2f2960 |  | note | - - - - - - - - -
label | d8a30341-c698-54bd-847b-026fd95dbf1c |  | note | IP
label | 89c9f4e5-a610-5487-8511-90b6d5ec3043 |  | note | - - - - - - - - -
label | e6751a8c-70fb-5673-9773-cf3690e050cd |  | note | Responsibility: Site Engineer/ Site Foreman
checkpoint-status |  |  | checkpoint | 2.9 - Tolerance
label | 13813b6f-1541-59b7-a0c6-8ee38dd7141b |  | note | Frequency: Each lot
label | d7d49331-3a1e-5dcf-9e5f-bb2d28fa60f5 |  | note | - - - - - - - - -
label | 248db10d-3974-5fe6-b372-660084bb95ed |  | note | Acceptance Criteria: Match existing surfaces to within 5 mm from dimensions shown on drawings. Section dimensions to be with in 5mm and 15mm for width , for dimension less than 25mm tolerance to be Â±3mm. Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance 0 to +10mm. Except on curves or sharped areas, the deviation of the finished work from a 3m straight edge shall not exceed 5 mm at any point.
label | 0b3bbb22-977c-593f-a18f-5e600f23e13b |  | note | - - - - - - - - -
label | 658ee229-d782-5103-aeab-7558268f267a |  | note | Reference Documents: Section 703.15
label | ac929c6d-c540-53ba-8f2b-0e3f39570075 |  | note | - - - - - - - - -
label | 9acbe953-ce2d-5ac9-ab32-03001feb8d2c |  | note | Inspection / Test Method: Site Inspection
label | 8b257957-6699-5584-8865-6a2065c0ddcf |  | note | - - - - - - - - -
label | a10a2008-94a7-531c-a6fd-464ed7f9a65c |  | note | Record of conformity: ITP signed
label | 28f99d48-0055-58c1-998a-454f5a280a9c |  | note | - - - - - - - - -
label | 04072674-8aae-5c09-9869-79890bb4c3d8 |  | note | IP
label | 2b81a988-b268-513b-ad4e-119ecc92aaa7 |  | note | - - - - - - - - -
label | dcb7ba29-afd3-5efd-aca1-913f188ba55d |  | note | Responsibility: SITE Engineer/surveyor
checkpoint-status |  |  | checkpoint | 2.10 - Curing
label | 5a25d0b9-1358-5689-823f-32ac358228f8 |  | note | Frequency: Each lot
label | bf8a54f7-6534-5a6c-816a-932717daf06e |  | note | - - - - - - - - -
label | d1d9a21a-a88f-5119-89cb-5325c2824cf0 |  | note | Acceptance Criteria: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed. Concrete edgings shall be cured for a period of not less than three days after placing the concrete
label | b67dfed5-e62d-5fe6-9853-d615961c3d95 |  | note | - - - - - - - - -
label | 7a02e9f6-8851-5d18-8eb7-d90b0473a2f7 |  | note | Reference Documents: Section 703.10
label | 5c7606bf-7e02-54be-859e-0b854a9ef374 |  | note | - - - - - - - - -
label | c4659408-b95c-5b84-b1df-e490701656ba |  | note | Inspection / Test Method: Site Inspection
label | 8d15ab53-2c80-5d78-889a-17369fce3169 |  | note | - - - - - - - - -
label | d98a0d1a-dc08-599e-a1ea-91fb797916ef |  | note | Record of conformity: ITP signed
label | b40a1945-c941-57df-bdbc-31560e2b1cbe |  | note | - - - - - - - - -
label | 90d0b0f4-09c7-529b-b762-77dcb27ccd03 |  | note | IP
label | 0b7d563a-5a14-5d8c-a8dd-9557a02ca00b |  | note | - - - - - - - - -
label | 3f86e047-32b1-5df0-94c9-3289ac508ee3 |  | note | Responsibility: Site Engineer/Site Foreman
checkpoint-status |  |  | checkpoint | 2.11 - Joints
label | 202662c0-9c95-5f57-ae44-47b19f4e7cfe |  | note | Frequency: Each joint
label | 20ca555e-0bb5-5f98-9c5e-8b89ff12323e |  | note | - - - - - - - - -
label | f9e5485e-0c52-508b-b864-697ea658c84e |  | note | Acceptance Criteria: Transverse joints constructed at intervals not exceeding 2.5m. Groove cut 20mm deep and > 5mm wide on exposed surfaces, following with a vertical cut made through the base of the groove (depth >50mm from surface of section). Bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt material between the edging and the concrete paving or shared use path.
label | 3a74b83d-91ef-5f33-a3be-29427ce1b717 |  | note | - - - - - - - - -
label | 8df31700-162c-5a04-aea3-c8cc124878ea |  | note | Reference Documents: Section 703.26
label | 3384d50f-d31b-511e-998d-204bf4f6c3ff |  | note | - - - - - - - - -
label | d17ffa11-1074-5ddb-be36-551cbf45bad6 |  | note | Inspection / Test Method: Site Inspection
label | b2a1618d-30ff-5170-90c5-ec0a437e39b7 |  | note | - - - - - - - - -
label | a42a28f7-4d0c-57be-9222-c5af927ca51a |  | note | Record of conformity: ITP signed
label | fea26e42-67e1-546b-a916-4f573adfd5c3 |  | note | - - - - - - - - -
label | 4362bff5-e9c9-5bfc-995a-2b199a4648fe |  | note | IP
label | 6e0370b9-d219-50cc-9748-f4db3faaa6a4 |  | note | - - - - - - - - -
label | 3b8a3bd1-0bac-5957-9115-bbd79c0053cc |  | note | Responsibility: Site Engineer / Site Foreman
checkpoint-status |  |  | checkpoint | 2.12 - Backfilling
label | 8a2ff20f-0aa5-5192-9004-8348bb7c2c52 |  | note | Frequency: Each lot
label | 2c5b5e63-5088-5fd4-8d77-814886e6ed4c |  | note | - - - - - - - - -
label | 132799eb-6ad3-59cb-baa1-d48274d61cdf |  | note | Acceptance Criteria: No earlier than 3 days after casting, top soil material free from perishable matter, lumps or balls of clay, shall be placed and firmly compacted behind the edging in layers not > 150m thick and to a width not < 300mm behind the edging to the top of the edging.
label | 1e8117f7-f68e-55ef-9365-e3992f2a00d1 |  | note | - - - - - - - - -
label | 785f16d2-d984-583c-bf53-39e4e16c23b4 |  | note | Reference Documents: Vic Road spec 703.29
label | f19fd8b7-2e1e-5429-a687-b8e8ea59c6cc |  | note | - - - - - - - - -
label | c645e88b-8c02-5921-bff2-91330ce3ef39 |  | note | Inspection / Test Method: Site Inspection
label | 360fa6b8-dae4-5120-a1b3-006fce76a59b |  | note | - - - - - - - - -
label | e56412da-84f8-5ee0-a11d-29f5f4b35fc1 |  | note | Record of conformity: ITP signed
label | 14ea599c-d9d4-53a5-abdb-0636bf3df0db |  | note | - - - - - - - - -
label | 533d4b70-0df3-5cb0-89e9-eb813be61126 |  | note | IP
label | 55546ae1-37b3-5bb3-84d6-6ef46ca4b4ca |  | note | - - - - - - - - -
label | 10a1c14f-971a-5f16-90a0-d9432589eb2a |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 2.13 - Protection of Concrete
label | e399fc9c-c843-5326-88a1-9b4bb415a482 |  | note | Frequency: Each lot
label | ec257f57-d9fb-5657-a27b-98f9b3d6c8d3 |  | note | - - - - - - - - -
label | 3f436246-8fad-5500-9dee-f5745e22167f |  | note | Acceptance Criteria: All concrete shall be protected from damage from early loading.
label | d50c4d25-a980-56d0-b8c5-7d723e63dc25 |  | note | - - - - - - - - -
label | 088758e1-710b-5806-964b-1e685d068c43 |  | note | Reference Documents: Section 703.27
label | 8fb9e6cc-f643-547f-ab82-51d366608b2e |  | note | - - - - - - - - -
label | b080d957-f95e-5e64-92ac-7e3930d550ee |  | note | Inspection / Test Method: Site Inspection
label | 130136cc-5bc5-514f-aa2d-31a88299106a |  | note | - - - - - - - - -
label | 10afe4d0-f085-5cf3-8141-844983b1a22c |  | note | Record of conformity: ITP signed
label | ffd4acfe-95dd-5696-8fd6-8f77599dd5b0 |  | note | - - - - - - - - -
label | c5bcc2bb-1026-575c-886c-f04fbd09b750 |  | note | IP
label | 03f6fb18-6e52-5522-aedd-fd24f4fb9508 |  | note | - - - - - - - - -
label | 891e626a-01b3-5e9f-97b7-d29ecd37f8f8 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 2.14 - Cracking of Concrete
label | 7f851159-b474-5577-af3f-14dca6c40822 |  | note | Frequency: Each lot
label | 2a23315a-c366-533c-9d70-1531ca4a7f04 |  | note | - - - - - - - - -
label | 2ff4c6f3-cfff-551a-b09f-05bf927bca25 |  | note | Acceptance Criteria: The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm. Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
label | 31da604a-ce09-535f-8534-3d40d4fdb5ef |  | note | - - - - - - - - -
label | f14212c1-7fb3-5385-9dd0-26f31d8dff70 |  | note | Reference Documents: Section 703.30
label | 4b53271c-f0cb-5625-a8a3-1d038296bc7b |  | note | - - - - - - - - -
label | 9876ea18-6cb9-5d9e-9dab-393818fb6ffd |  | note | Inspection / Test Method: Site Inspection
label | c36f5e43-0e88-5d87-a0e7-3ff7fc8a6e71 |  | note | - - - - - - - - -
label | 01fb8f8c-49cd-577e-8a4b-ea258f362816 |  | note | Record of conformity: ITP signed
label | ae1c51c4-9b7a-5388-8909-48fba5d29a89 |  | note | - - - - - - - - -
label | 9b80d215-db8e-5bd9-8aef-3746c4d00fff |  | note | IP
label | bca573c2-2518-5455-a27b-9c8926ddad17 |  | note | - - - - - - - - -
label | 3344a68a-458f-5c85-945f-52956e4178a5 |  | note | Responsibility: Site Engineer
checkpoint-group |  |  | section | 3 - Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 - Survey Conformance
label | 97792f7e-7a32-577e-adfa-3c7db7ee0e75 |  | note | Frequency: Completion of each lot
label | b18ac26a-f660-5f32-8a5e-fc98fbc5d9a0 |  | note | - - - - - - - - -
label | f58b823a-17c4-527d-ae3f-4ed8e34ec6f0 |  | note | Acceptance Criteria: Survey to as built the works and to confirm the works are within the specified tolerances.
label | 849a651b-e7a6-592e-bfe3-03a452369768 |  | note | - - - - - - - - -
label | ea51b1f4-c033-5a2c-8651-836cac99b93f |  | note | Reference Documents: Section 703.15
label | 78df2864-61e9-5fd8-b0b8-30337f204484 |  | note | - - - - - - - - -
label | adff243a-fc34-553b-a0cb-e75c04814546 |  | note | Inspection / Test Method: Document Review
label | b6569e9a-f246-5303-930e-2a735ddaea5d |  | note | - - - - - - - - -
label | 6a8c0df2-5278-5f9f-94a0-0b3ef7a5c904 |  | note | Record of conformity: As-built survey records
label | 2b211048-a3be-55c5-95ad-f6ef9059edfa |  | note | - - - - - - - - -
label | 9fe5ee4a-28cf-51e0-afcc-cc2d6eaacad1 |  | note | WP
label | 440cf657-f36e-539b-9d12-00434017869d |  | note | - - - - - - - - -
label | 3b2e2d6a-3635-55b1-af48-1ad93f853bc9 |  | note | Responsibility: Project Engineer/ Surveyor
checkpoint-status |  |  | checkpoint | 3.2 - Non-conformance Report (NCR) Closure
label | f1afa088-a895-5301-9fa6-33e500cb096d |  | note | Frequency: Once, prior to closure of this lot / element / Work area
label | 5976a098-a6f7-59d2-84ba-d5e54c5e7c43 |  | note | - - - - - - - - -
label | 361fbbf4-9f17-5d88-8001-2593a3a8d615 |  | note | Acceptance Criteria: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | d4a853ac-90f1-51d7-93bd-085479561f33 |  | note | - - - - - - - - -
label | 84a3f3cc-ba7f-5915-9edf-1bd7f4525a68 |  | note | Reference Documents: Quality Management Plan
label | 4de77ef8-377d-5bc7-872c-c09dd5fbefe3 |  | note | - - - - - - - - -
label | 70c6fc18-a3a1-530c-8d5e-1bab1b0ee363 |  | note | Inspection / Test Method: Document Review
label | 9ad8b6db-27a8-5ec7-ace0-ba4e964b28e3 |  | note | - - - - - - - - -
label | 2abf77ad-d10a-5a7f-9be4-d0ff72bfafd2 |  | note | Record of conformity: This ITP
label | bcac742b-4d21-5a1f-866c-57d4bd11fea4 |  | note | - - - - - - - - -
label | c63576df-b27f-5dc6-a372-4ace55e5e4de |  | note | HP*
label | 91c3f567-1214-534a-95af-46295c64d59e |  | note | - - - - - - - - -
label | 6bcd2531-cdef-5d98-a727-b4c9ba5d829d |  | note | Responsibility: SE/PE/SPE
checkpoint-status |  |  | checkpoint | 3.3 - Red lines
label | c36c437e-7cb9-56fa-a93f-771bf8a8541f |  | note | Frequency: Once, prior to closure of this lot
label | 97c93aae-15b7-569d-9964-e8864e5be09e |  | note | - - - - - - - - -
label | 71eced55-49c9-574e-8b6c-c9a303b70d75 |  | note | Acceptance Criteria: All RFI's and deviations from drawing to be marked in accordance with CRU red line markup procedure
label | 3a0fadc1-2926-57e8-800f-df8b70019d11 |  | note | - - - - - - - - -
label | be9cac88-185c-5f78-9202-de2a035fafaf |  | note | Reference Documents: Quality Management Plan
label | d1290bd8-c946-5e3b-80dd-41316ce8a042 |  | note | - - - - - - - - -
label | a3a4aa35-6b7b-5a9c-a4b7-39cb9064e51e |  | note | Inspection / Test Method: Document Review
label | e8712c2b-34fa-58f2-98ea-3dd65f8ae1e2 |  | note | - - - - - - - - -
label | 7eea6f4e-64ef-5056-b0ca-96fd3e5d9271 |  | note | Record of conformity: This ITP
label | bdb4cd32-8361-5bb4-a02d-26fc75bd3f41 |  | note | - - - - - - - - -
label | c5b2ce25-049a-5bb4-ae5e-e2d1505e18b5 |  | note | HP*
label | 7d4793e9-c6d4-5610-aec4-2382ad103791 |  | note | - - - - - - - - -
label | 4cf50dce-aeb2-5dba-abe5-56fd1d968f40 |  | note | Responsibility: SE/PE/SPE
checkpoint-status |  |  | checkpoint | Final Inspection
label | 87c8807d-6c80-52a8-8e62-b1a56b6ab2d5 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 8e23e8a1-2750-50e7-868c-67764c82b6d5 |  | textbox | Print Name:
text | d1b01e5e-40da-5ed1-a948-0e36153e7e65 |  | textbox | Position:
date | 3e86a484-0225-5683-98ab-a3a4d4785ed8 |  | date | Date:
date | fffb949a-eb00-539c-aa62-d668523e1889 |  | date | Work Completed On
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification.
select | e55495b6-83d8-5c07-a3c0-19206d5a9a17 |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | 882ca9b3-d88c-5f08-997b-cd5b0c80d2dd |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | d357e510-4263-5f67-aa17-e212c6f0465f |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | 3eee74dc-cc5e-56d2-aae4-0b41576b0385 |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | 6291c940-e358-5944-b9df-8a0d1da54057 |  | textbox | Other:
select | 23c53ceb-ee14-535d-b4c1-c903ea1b11ec |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | 3e6f595f-6239-5004-9123-a3f01bca828c |  | date | Lot Closed On
text | 0c57586a-39c9-56c1-bf93-cb45e8bbfc80 |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-060-UT-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0060 - Installation of Unmetered VESI Public Lighting | 0eceab60-fe48-457b-9a4d-57d9fbc4d528
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | dc0bfab8-b480-53de-ba7c-db5f39fb82be |  | date | Lot Created On
date | 3a639071-272f-5972-83f2-581a41e99d87 |  | date | Lot Opened On
date | b608b136-fcdf-5360-b1d5-a1e3ed3b3432 |  | date | Work Commenced On
select | 58354e7d-7b23-57c0-b5c5-1fc5059021e0 |  | dropdown | Lot Type | CIL-Civil Lot, DRL- Drainage Lot, EAL- Earthworks Lot, ELL- Electrical Lot, UTL- Utility Lot, STL- Structural Lot
text | cb13579c-5b7a-503b-99a1-28c82485e93d |  | textbox | From and To Chainage
select | 7715c3a4-0044-5a99-99f3-7edc67f99599 |  | dropdown | Construction Element | ITS - ITS
select | 8beff9ce-b953-5d87-a635-69524d67fb0d |  | dropdown | Activity | STRE - Street Lighting
select | 79ba366b-ed52-5b5a-aa9e-c3fdc7a7f5f3 |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | c8b0f28a-b251-5ee1-b2a1-a79771f4a26c |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | 15acfafd-ae3e-5cbc-8f64-4d99ce288ea5 |  | textbox | Engineer Responsible
text | fba3bc80-da85-505f-9fb7-3a4bcf0aee79 |  | textbox | comments
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 Authority to commence contestable construction (ACCC) issued by Jemena
label | b2aa3bee-757f-5a39-a108-9b4a00fc2cfe |  | note | Frequency: Prior to Commencing
label | 1b6bab62-6915-5016-9e23-649b5d8b0582 |  | note | - - - - - - - - -
label | 5576b17e-704d-5368-8228-d32682fe0429 |  | note | Acceptance Criteria: Notification from Jemena
label | aba9c413-9685-529e-bf2a-cf1bbe5974bf |  | note | - - - - - - - - -
label | 8e0e2528-caf6-5631-8c90-dc338e9802a6 |  | note | Reference Documents: Record of notification
label | 45646b64-37ac-567f-8e2c-516e08d1d9a9 |  | note | - - - - - - - - -
label | 30fffebd-16e1-51b5-b962-d8267cf8db85 |  | note | Inspection / Test Method: Document review
label | 2e18ccc5-91c2-56fe-a262-acca86cdda21 |  | note | - - - - - - - - -
label | a328bde2-599f-5938-b747-5be53c32d97e |  | note | Record of Conformity: Saved correspondence
label | fffe43fe-ac3e-52ad-8150-e3b1880e272b |  | note | - - - - - - - - -
label | a1da2cc0-7d5c-54b2-81a4-bbd6fd3d2754 |  | note | HP*
label | daa3aa19-274e-5f7e-9759-cee7bf0c6573 |  | note | - - - - - - - - -
text | b6f229da-615d-5083-a046-95a47808f81d |  | textbox | Responsibility: Project Engineer /PM2
checkpoint-status |  |  | checkpoint | 1.2 Induction
label | f2edf5f6-4161-5774-aebb-edade9a97fb0 |  | note | Frequency: Prior to Commencing
label | f40e0650-504a-5ea9-873d-967fe7035c96 |  | note | - - - - - - - - -
label | 8afbf9d8-385a-5ce4-9b17-a0ec702b9751 |  | note | Acceptance Criteria: All personnel on site have been inducted to the CRG site
label | 83a884bf-5f65-5e5d-bc3e-d7a250bfe570 |  | note | - - - - - - - - -
label | 542a5e53-d9d5-5af9-92cd-8d141461c1f5 |  | note | Reference Documents: PMP Inductions Register
label | d63418a9-c90f-5367-a7a5-81f90c5f4dda |  | note | - - - - - - - - -
label | 5d5cf723-d43f-520b-8cd1-b73bf4265701 |  | note | Inspection / Test Method: Document review
label | 6f808f9a-9837-5272-bfb9-e14c039956d0 |  | note | - - - - - - - - -
label | ba7dda6f-69b1-5d2b-ae53-519ffa231d2b |  | note | Record of Conformity: Site induction signed.
label | 13e2da94-57aa-5a44-bc31-e9e937f0cfed |  | note | - - - - - - - - -
label | 3c75be6a-b303-5ec8-9eb7-07d19601d5e9 |  | note | IP
label | 971efdac-6790-5df2-b4b8-fb8b00b2f4ce |  | note | - - - - - - - - -
text | d2dd7c4d-322c-5988-b5eb-7474e8cdc5b1 |  | textbox | Responsibility: Site Engineer / Site Foreman
checkpoint-status |  |  | checkpoint | 1.3 Check that current revision drawings are being used
label | 8d0e1c8e-5abd-50f9-aaf7-bdca4cacf6a7 |  | note | Frequency: Prior to Commencing
label | 79865807-cb05-50e7-8289-a85c9f940cfe |  | note | - - - - - - - - -
label | 39d21b9d-35ca-5961-96ea-d5f8cc867bec |  | note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
label | e003659f-32a1-5a47-8f22-598367766851 |  | note | - - - - - - - - -
label | 51613a67-f777-54a1-9376-2703afa31efe |  | note | Reference Documents: Project Drawings / Drawing Register
label | e7a709d1-7b1c-58e8-bd97-5013bd576fe8 |  | note | - - - - - - - - -
label | eebc98aa-0750-59ca-8ceb-05e7d3166c9d |  | note | Inspection / Test Method: Document review
label | 3f771cdf-0a72-5739-b816-9832248f4fae |  | note | - - - - - - - - -
label | 42f5b6c8-b31a-5c08-9c40-4409550df0df |  | note | Record of Conformity: Latest Revision Drawings
label | c657ed8c-3e76-5669-a317-b51099e90ff5 |  | note | - - - - - - - - -
label | 6683349e-b3bc-58bd-a952-1370b9b618d4 |  | note | IP
label | 57c8cf59-edf2-5a30-b108-ca45e92547ab |  | note | - - - - - - - - -
text | 9512b003-3bab-58f8-98a9-0f1047d02063 |  | textbox | Responsibility: Site Engineer / Site Foreman
checkpoint-status |  |  | checkpoint | 1.4 Confirm understanding of current Environment Management Plan (EMP) related to the work area and that all prescribed environmental controls are in place
label | 0dde77da-db6c-5765-ba6c-481109bb5c02 |  | note | Frequency: Prior to Commencing
label | fddad270-1d03-5eb1-94df-311a5dd7a96e |  | note | - - - - - - - - -
label | b1b34fac-1978-55ed-b92b-65bb00a8e9b2 |  | note | Acceptance Criteria: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | f17eea6a-6a45-562f-90b3-d50cb153df2d |  | note | - - - - - - - - -
label | c03dc63b-f6b5-55b8-b293-80cf715ecece |  | note | Reference Documents: EMP, Site induction,
label | 0fdd3c29-0991-5d37-a29d-31e635e5e530 |  | note | - - - - - - - - -
label | 04389e33-7799-5b14-8020-97ed1bf7fcd2 |  | note | Inspection / Test Method: Document review & Site inspection
label | ebc90de0-dda2-5efc-aad6-4407fb1f7aaa |  | note | - - - - - - - - -
label | 794d484e-6c5d-5126-9c32-0732a39a6c0f |  | note | Record of Conformity: Signed ITP
label | bb9a5cfc-8040-577c-b5bb-960fcc2fb537 |  | note | - - - - - - - - -
label | 4d44c8ba-acb4-5df3-9df3-8dde56541c73 |  | note | IP
label | 5d4d555c-cbef-5f63-a56d-1729dfa7c6e3 |  | note | - - - - - - - - -
text | 97d15f82-280c-5e6c-a44f-ed0bdad77fb0 |  | textbox | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 1.5 Safety measures are in place, Safe Work Method Statement (SWMS) undertaken
label | c371cbac-24fa-56f5-b5ed-34ab8b60898c |  | note | Frequency: Prior to commencing
label | 7ea7e35e-290d-5ea3-ae25-707241cd0c1a |  | note | - - - - - - - - -
label | ed81a084-1809-50ec-8965-fc099b463fb4 |  | note | Acceptance Criteria: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
label | be40ebf4-a56f-5650-b672-3c0a30edeab1 |  | note | - - - - - - - - -
label | 1c54fe88-c3c9-5f0f-9b06-e05b00321149 |  | note | Reference Documents: Health and Safety Co-Ordination Plan
label | 0ab72076-8f6f-5774-a2f8-e73136b4d99f |  | note | - - - - - - - - -
label | 15a0c0c8-f6a0-5c2f-aa11-59e7bd1efa26 |  | note | Inspection / Test Method: Document Review
label | 044e097b-e4f3-53e6-abce-9d84e12aa62d |  | note | - - - - - - - - -
label | 9faaa1bf-3ae6-5e3e-be28-5027ab1f1951 |  | note | Record of Conformity: SWMS(s) signed
label | 9be30772-d3d7-5ed8-b2e9-4a50a338dab5 |  | note | - - - - - - - - -
label | 1fd390b0-c7b9-5369-a91f-d523c55ff559 |  | note | IP
label | d2ae00a5-33f0-5e03-aab6-552e7327d7a9 |  | note | - - - - - - - - -
text | 60e73220-f34f-56a0-9e6f-c1dd1caa8316 |  | textbox | Responsibility: Site Engineer & /Site Foreman Superintendent
checkpoint-status |  |  | checkpoint | 1.6 Ground Penetration Permit issued
label | 00000e43-39e3-59ac-b853-9e772f85ecc7 |  | note | Frequency: Prior to Commencing Work
label | 8bed18fa-c68d-5955-9bae-fa24826d0c1f |  | note | - - - - - - - - -
label | ff8f14bf-ae7c-53aa-8a72-e682b89ba7cb |  | note | Acceptance Criteria: Current Ground Penetration Permit signed and specific for the area where works will be executed.
label | 6792fad3-942c-5126-96b9-33401fd17c95 |  | note | - - - - - - - - -
label | 89541fbb-b4d6-52b0-82fd-c4f5bc34df3a |  | note | Reference Documents: Excavation Permit
label | ad3d071a-bd44-5899-8fa8-b79febd85cb7 |  | note | - - - - - - - - -
label | e4ec4283-2eea-5b20-9e85-f2a846c05f21 |  | note | Inspection / Test Method: Document review & Site inspection
label | c3459787-0285-59c3-ad1b-4418c4fd8f03 |  | note | - - - - - - - - -
label | 087e62dd-9d2e-5570-8b2d-21188c82c67c |  | note | Record of Conformity: Excavation Permit #
label | 5a2fdf19-8e56-5521-958f-c6aa7fb3f927 |  | note | - - - - - - - - -
label | f9891e7b-6264-5143-9b73-13a53d945661 |  | note | HP*
label | 29d92607-1f10-50b5-9bcb-1a1f013be838 |  | note | - - - - - - - - -
text | 39a773d4-632d-5ad4-82aa-107ccf0246e4 |  | textbox | Responsibility: Site Engineer
checkpoint-group |  |  | section | 2 - Installing of Lighting
checkpoint-status |  |  | checkpoint | 2.1 Staged Construction Audit - Civil Works
label | 455258f9-c775-5a2f-b023-e2ef24c9ecb1 |  | note | Frequency: Following Preliminary Works
label | 395900bb-baa0-57f6-a853-6da2ef81b95d |  | note | - - - - - - - - -
label | 797c737d-430a-5951-bc89-8cb09141c842 |  | note | Acceptance Criteria: Passed staged Construction Audit
label | 63553ebf-b16b-5c78-be13-927283b9bd77 |  | note | - - - - - - - - -
label | e77151e7-ab05-559c-b88d-92b7c3e39f4e |  | note | Reference Documents: Sub-Contract ITP/Checklist
label | 356b7ae7-880e-5a63-ac1a-62268dd79f09 |  | note | - - - - - - - - -
label | 782edab9-a65b-5cc8-89c3-ad72d71e7d4d |  | note | Inspection / Test Method: Inspection by Independent Auditor
label | bcce9b0f-be8a-51d5-b9d6-4e64d5089e39 |  | note | - - - - - - - - -
label | 45ec245c-d635-56d9-aa58-93023d3c2947 |  | note | Record of Conformity: Audit Report
label | fa50b165-fb63-5c76-9ec9-3f07b6ca3da5 |  | note | - - - - - - - - -
label | e86fd19f-aaa6-5bf6-99f7-7ce6e74f09cf |  | note | HP*
label | 72a85166-5943-5eaf-b325-c1ca79efb5c9 |  | note | - - - - - - - - -
text | 148f4207-5581-5bfe-89d2-636391998f91 |  | textbox | Responsibility: Sub-Contractor
checkpoint-status |  |  | checkpoint | 2.2 Staged Construction Audit – Cable Works
label | 96be8bcc-0063-5dcb-9297-5382ab6d2b25 |  | note | Frequency: Following Civil Works
label | 2011edb1-8bc0-5b99-9224-7e71c6282408 |  | note | - - - - - - - - -
label | dfb51bf5-d800-53d6-995f-2b6f88b434fe |  | note | Acceptance Criteria: Passed staged Construction Audit
label | addb932c-1f50-5e7a-9d67-db14b9a3da0d |  | note | - - - - - - - - -
label | 9b249e41-7037-5be2-a78b-e9ab8c7bc0f3 |  | note | Reference Documents: Sub-Contract ITP/Checklist
label | 6d3e9a8a-7d41-5acd-8d04-a7402043353e |  | note | - - - - - - - - -
label | 75645ac4-1d09-59bc-9b12-f8f1256cce65 |  | note | Inspection / Test Method: Inspection by Independent Auditor
label | 42d26dcf-c454-5c7d-b23a-7250881ec799 |  | note | - - - - - - - - -
label | 3ea08c41-4277-56e6-b4f5-9665a61faa07 |  | note | Record of Conformity: Audit Report
label | 9573483d-c53d-5b80-9d53-782b7c69c2e3 |  | note | - - - - - - - - -
label | 5167a8a9-665b-5017-aecc-87f956b608ce |  | note | HP*
label | 3690bf91-aace-5623-8208-089238ff14de |  | note | - - - - - - - - -
text | d979cad7-c74e-5e1a-8104-edee84aca61b |  | textbox | Responsibility: Sub-Contractor
checkpoint-status |  |  | checkpoint | 2.3 Staged Construction Audit – Handover
label | 38fef0ef-dede-5bd2-980d-edc7a8c93acd |  | note | Frequency: Following Cable Works
label | 2960b1d3-7b6c-5ef2-bdb9-ba8eb63207d6 |  | note | - - - - - - - - -
label | c1f0110c-84a2-51d6-995e-42c6f719cacd |  | note | Acceptance Criteria: Passed staged Construction Audit
label | 344b5c4d-b309-5e8f-b750-1356ac0e6b85 |  | note | - - - - - - - - -
label | 59ccdaaa-e3c7-5f7b-ae9d-f0cc4f912e6c |  | note | Reference Documents: Sub-Contract ITP/Checklist
label | f71b78ea-9dbd-59de-bac4-a8d6feefba0a |  | note | - - - - - - - - -
label | 968fb838-51be-5046-b822-79061a3bfc3c |  | note | Inspection / Test Method: Inspection by Independent Auditor
label | bb5d8be3-7b9c-58a4-83f1-40e2003723b8 |  | note | - - - - - - - - -
label | 840a1523-63b1-575d-b22f-1e5821af1450 |  | note | Record of Conformity: Audit Report
label | 853cb330-e874-58de-b8df-b9129a135dae |  | note | - - - - - - - - -
label | de8e4c44-08f2-5398-b06a-745b886a1687 |  | note | HP*
label | bb1c106f-c068-574d-a47c-720753addd03 |  | note | - - - - - - - - -
text | 4cbafbd0-112c-5b1e-b410-fee9ae82d2d3 |  | textbox | Responsibility: Sub-Contractor
checkpoint-status |  |  | checkpoint | 2.3 As-Built submission to Jemena
label | cfc139b4-a4dd-5c59-9f6d-c24384d4ab3d |  | note | Frequency: Following Cable Works
label | d96aa334-61a6-589e-8128-e5d0f26e95fd |  | note | - - - - - - - - -
label | 27970f7c-acde-5e22-8796-a7dff106a165 |  | note | Acceptance Criteria: Passed staged Construction Audit
label | 5eb35bcd-6ab4-59cf-89d7-71b7060a488a |  | note | - - - - - - - - -
label | adefc321-6385-58ea-b1c3-26e0d19dd8bc |  | note | Reference Documents: IFC Drawing
label | da5df6e4-6995-58f9-84dd-ec15ba262b6e |  | note | - - - - - - - - -
label | 77cd4dfa-44a1-5ee6-a862-e8e571500f39 |  | note | Inspection / Test Method: As Built Drawing
label | e6e82e0e-0f52-58df-b885-17d1a87d1659 |  | note | - - - - - - - - -
label | 9151660a-1263-5e0d-a088-31c8d4fc9d1b |  | note | Record of Conformity: Acceptance by Jemena
label | e4e65b4e-2e93-5307-9fd2-94fe4f8f4272 |  | note | - - - - - - - - -
label | 9cd74b02-2624-582b-8a02-e8611e01c7b7 |  | note | HP*
label | 6d4810c7-a791-5289-8a0f-bd33ef7b164f |  | note | - - - - - - - - -
text | 8452f01f-63e0-59c3-8996-7c7a3a2c243e |  | textbox | Responsibility: Fulton Hogan / Powerplant
checkpoint-group |  |  | section | 3 - Commissioning
checkpoint-status |  |  | checkpoint | 3.1 Pre Commissioning Audit
label | 18df7a1a-d2cb-5d00-8db4-4ce24e1ba4a0 |  | note | Frequency: Following as Built
label | 4fda8da6-ecb7-59d1-900d-99f334b19bb5 |  | note | - - - - - - - - -
label | 8276570b-77ba-57a8-bfd0-bf68b3e7ab70 |  | note | Acceptance Criteria: Passed Pre Commissioning Audit
label | f1be2f6d-3dc7-5e81-af09-583ce23de08e |  | note | - - - - - - - - -
label | 1615d89e-0e94-5d4d-8204-1e41f6523bec |  | note | Reference Documents: N/A
label | 4c6710b2-bbdf-5ef6-8bec-73dbb3e1ffbd |  | note | - - - - - - - - -
label | 1e68517e-0efe-597e-897d-ad31cf199bb1 |  | note | Inspection / Test Method: Inspection by Independent Auditor
label | ae804e6f-101e-50a8-8392-add60a5c0220 |  | note | - - - - - - - - -
label | a37d8247-c334-5524-bbac-cbccecf444c5 |  | note | Record of Conformity: Audit Report
label | 21dc1afe-182a-55f8-96b0-567fbba05530 |  | note | - - - - - - - - -
label | d3f86a53-521e-5c1e-86d0-239cb4cf026b |  | note | HP*
label | 255c2fff-25e0-557c-b093-8a3b7f650b5b |  | note | - - - - - - - - -
text | dafaf1a6-1ebd-5942-a326-e24b74d5f8f0 |  | textbox | Responsibility: PM2 (Powerplant)
checkpoint-status |  |  | checkpoint | 3.2 Commissioning
label | 4cd659e8-a2fe-5864-8d5e-a6bab79ccc36 |  | note | Frequency: Following Pre Commissioning Audit
label | 02ce1c84-1a6c-5143-b1eb-ecc97b041ebe |  | note | - - - - - - - - -
label | f9c002c8-2842-5ffb-bb52-1791c569a24f |  | note | Acceptance Criteria: Energization
label | ebf10329-a035-5fcb-88b7-c0f01de949b6 |  | note | - - - - - - - - -
label | cc3be79e-f578-529b-8804-c4d218ade98f |  | note | Reference Documents: N/A
label | 268988e7-9e75-57dd-a9a2-6d2ef4d6e051 |  | note | - - - - - - - - -
label | 242e5702-229b-5966-a292-e2d8e8c00c31 |  | note | Inspection / Test Method: Inspection by Independent Auditor
label | ca7063c3-b99d-5592-a758-988da42744cf |  | note | - - - - - - - - -
label | 32903d16-0f68-5e31-b3fe-dbab274bef33 |  | note | Record of Conformity: Switch on
label | 5a724d31-4961-56b4-8bf4-d75b7116a1cf |  | note | - - - - - - - - -
label | 77adee57-bb75-524c-acb8-eed6ab1c83e5 |  | note | HP*
label | f01c448b-b5ba-51bb-b4ee-774d95c373af |  | note | - - - - - - - - -
text | 69682a8d-49aa-53db-8f4c-90c40d216a83 |  | textbox | Responsibility: Sub-Contractor
checkpoint-group |  |  | section | 4 - Completion of Works
checkpoint-status |  |  | checkpoint | 4.1 Final Audit
label | 5a4f46f7-199d-5728-bcaa-4b5a77b55a17 |  | note | Frequency: Upon Completion of all Works
label | a5867fb6-4580-5d53-8a46-bfbc6f126923 |  | note | - - - - - - - - -
label | b9867554-14b8-5c59-b64c-856ae2aba42a |  | note | HP*
label | c7c02cc1-0ea1-5969-a52b-31fff7bfb1d0 |  | note | - - - - - - - - -
text | 3a7a410d-fb9b-5b78-bf6b-9a2de2274c4a |  | textbox | Responsibility: PM2 (Powerplant)
checkpoint-status |  |  | checkpoint | Final Inspection
label | 391e0d16-28e2-5d5e-8beb-05c29057e6a4 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | bedcb97b-48cb-55d5-b02c-be94fe9db483 |  | textbox | Print Name:
text | 581c1234-8822-5c2c-9b92-77acab46a1b0 |  | textbox | Position:
date | ed3a4637-01a7-5b31-a482-299ae6d2acc3 |  | date | Date:
date | 9de415d2-09cb-5208-bb9c-f8099c4c73b1 |  | date | Work Completed On
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification.
select | e5f1172f-e476-5b93-bcb6-0dd8ae258998 |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | 3768caee-da0c-5497-9750-81688ca1d78d |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | 37b7fa31-b2f8-57a1-ad46-70061e5ef178 |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | ad82452d-e189-5d17-b3bf-987fd701829c |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | 44858463-692f-5078-a177-6c9bdb114ab0 |  | textbox | Other:
select | df1d1a27-eb8f-57c7-b1e1-4b2bffb498db |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | 74f188cf-8139-5918-b062-6dbfb66c1122 |  | date | Lot Closed On
text | 983b7d84-3e72-5fda-8f49-77e32153797a |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-007-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0007 - Fill With Material Type A | 157354aa-edda-46f9-bf86-d614f331fe6f
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | 413faf81-221f-56ec-82b9-26643e141ba0 |  | date | Lot Created On
date | 4eca83d5-2c06-522b-803c-f8116e42b06e |  | date | Lot Opened On
date | 31b204d6-11b1-5729-b591-4769d23fb211 |  | date | Work Commenced On
select | ad22f34e-6907-5a63-a774-88f63c57dc33 |  | dropdown | Lot Type | EAL - Earthworks Lot
text | 26d5ee87-9003-5e4b-83ce-230da6f50d68 |  | textbox | From and To Chainage
select | dc67f8f1-4ff0-5efb-a440-e43051fee526 |  | dropdown | Construction Element | EART - Earthwork
select | a17ca367-d956-509a-af61-05dd3bbcd663 |  | dropdown | Activity | TACAP - Type A Capping
select | 42b45634-6a71-539d-8a3c-0a7dcf5b135a |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | c7cf6ebf-f1a7-59c8-92cd-c0ddb9793e29 |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | 38c08d11-dc2d-57df-b2c3-21ed030e2116 |  | textbox | Engineer Responsible
text | 2fdedbbd-be0e-519c-8f86-9f847a3978ea |  | textbox | comments
checkpoint-group |  |  | section | 1 - Preliminaries
checkpoint-status |  |  | checkpoint | 1.1 - Check that current revision drawings are being used
label | 83bf83b6-5313-54c6-bca9-bb217cb2ca37 |  | note | Frequency - Prior to Commencing
label | cdbd7dfb-03e1-587c-9f0e-15622cb5fa86 |  | note | - - - - - - - - -
label | afb73c94-ffe1-5ced-b0c0-5113432fff3e |  | note | Acceptance Criteria - Issued For Construction (IFC) and latest available revision used
label | 813009c4-a4f4-58bd-b2b7-0c569e4ed7fa |  | note | - - - - - - - - -
label | 4f6f0b3c-b3fa-5720-b349-f4d6f1d716dc |  | note | Reference Documents - Project Drawings / Drawing Register
label | a2ad2c74-dd2f-59a5-a55e-a57f96951968 |  | note | - - - - - - - - -
label | f24dcfe3-190e-5e4b-8772-001ee9910812 |  | note | Inspection / Test Method - Document review
label | f721a2e4-bb51-532b-90bc-d044963814d0 |  | note | - - - - - - - - -
label | 3c760bab-682e-50c7-ae45-2dda767f6c6e |  | note | Record of conformity - Latest Revision Drawings
label | cfd356d3-38ba-5b24-80da-95f16f275ff7 |  | note | - - - - - - - - -
label | 135d432f-7a4d-52eb-be19-f71d15883d85 |  | note | AP
label | 5471accd-5218-516e-8e96-892c775bec37 |  | note | - - - - - - - - -
label | 03d2321f-34d1-53a2-8861-988977c8176b |  | note | Responsibility - Site Engineer / Site Foreman
label | 66b1b1a0-b9c8-55fe-b536-09971201a5c3 |  | note | - - - - - - - - -
date | 5da60b87-28db-5a6f-ba3e-030b1811ff6c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Excavation Permit issued
label | cd690b8b-bdd4-582d-8978-fa077c7ed3b5 |  | note | Frequency - Prior to Commencing
label | 15356cba-1d2a-55bb-ba1a-f6f294eaf3d5 |  | note | - - - - - - - - -
label | e7a98ece-d946-587c-8fa0-36230fec4440 |  | note | Acceptance Criteria - Current Excavation Permit signed and specific for the area where works will be executed.
label | f24af4a1-ac6b-5e90-aa38-ca2f2a8e17fe |  | note | - - - - - - - - -
label | e786d3ba-8d82-5574-ba6e-1c9bf20d8970 |  | note | Reference Documents - Excavation Permit
label | c24885d7-6dc5-5b34-a663-b2cb2834a26c |  | note | - - - - - - - - -
label | 6870c072-bca6-56cf-9b11-4f26e68c1b82 |  | note | Inspection / Test Method - Document review
label | 8a717bd4-9617-5165-8ca2-52ac48a9202d |  | note | - - - - - - - - -
label | 93f87df9-6109-526c-aec6-aa89ab631cef |  | note | Record of conformity - Excavation Permit #
label | 3c883ee3-57ab-524d-9475-e28865b9912f |  | note | - - - - - - - - -
label | 02314d18-ce56-5c07-8f15-763942ea235d |  | note | IP
label | db4d648e-d2f6-5615-8264-39278f41e2f3 |  | note | - - - - - - - - -
label | cd516425-fe21-5f4f-9367-3bba301506d1 |  | note | Responsibility - Site Engineer
label | aa4913b7-0287-598f-bf6c-3b264a284056 |  | note | - - - - - - - - -
date | 2bde4be3-9d7d-513b-89a7-4813ad4111d8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Type A Material Approval
label | d11ac373-50ac-51f2-b6f4-c18cf0b48791 |  | note | Frequency - Prior to Commencing
label | 86e1f07e-3722-5bc9-ba2b-ba84e9825a14 |  | note | - - - - - - - - -
label | e6271a40-dca1-530e-9e7d-93ae504aaf0c |  | note | Acceptance Criteria - Prior to the import of Type A material, FH to provide the Superintendent, at least 1 week prior to the commencement of cartage, copies of test results to confirm that the proposed Type A material complies with section 204 of the VicRoads Spec.
label | d48bd243-75f0-50a4-8d6e-413df7fc483b |  | note | Type A Material shall meet the following requirements:
label | 5d3a1ba7-e4db-59dd-b7cf-c08cb0fb5032 |  | note | CBR ≥ 6%
label | aea6da92-b0ff-53e3-b601-61aae8c9c1aa |  | note | Swell ≤ 1.5%
label | 42d8423b-8324-5d80-9cab-acca495012f9 |  | note | Permeability ≤ 5e-9
label | b10d6042-1eee-5354-8551-ba53cf0d231d |  | note | PI (LL) = 6 - 25
label | bfae04b7-2652-5710-b4b9-1e6f57e08ad3 |  | note | PI x 0.425 passing ≤ 1000
label | 5fa7708c-7db4-5f01-a90a-6bd99dd58e3e |  | note | Grading:
label | a24133fd-0432-5491-9ef0-0175aeb01b1a |  | note | % passing 75.0mm sieve = 100
label | 05eec73c-612f-5a6d-891b-6d067f8fad94 |  | note | % passing 4.75mm sieve = 40 - 80
label | c54a1ad9-d509-5234-bf1f-3c21f06b77fa |  | note | % passing 0.075mm = 10 - 40
label | aadd8fe7-5b77-5fcd-8669-1028c79f7f22 |  | note | Attach: Test Certificates, Delivery Dockets
text | ce4dcf11-03a9-5dd9-9cdb-170a8d1ccc7d |  | textbox | Teambinder Approval number:
label | 31383765-1cc5-50ba-b2d0-672f3a83d064 |  | note | - - - - - - - - -
label | 97f2fe52-af66-5260-b495-acea3f541302 |  | note | Reference Documents - Project Specification
label | a758b953-b726-5167-a111-cd6ca979c5c0 |  | note | Cl. 3020.05
label | bfe1240c-6059-5e14-ad67-087bf24c33bb |  | note | VicRoads Specification
label | 31868038-4628-5bc7-958b-37607f10ff0f |  | note | Cl. 204.04(b)
label | 2c85c4c0-5cd4-5037-b214-d655a474b879 |  | note | Cl. 204.06(c)
label | 0df5340b-60ea-569a-9a57-f840904bc84f |  | note | Table 204.041
label | e24dc910-263b-5f88-a70a-ce08a24987c3 |  | note | - - - - - - - - -
label | ba5e0493-bacd-5a33-b7fa-0740e22ca458 |  | note | Inspection / Test Method - Site Inspection
label | 7a65263e-ee0d-584c-b8d9-b342384618fe |  | note | - - - - - - - - -
label | 6247e5c9-b059-5dba-9330-584072a25771 |  | note | Record of conformity - Teambinder Approval #
label | 7089d272-60cc-5b0a-bb41-d2152cbe9ba8 |  | note | - - - - - - - - -
label | 455e4bd7-a48b-5de2-bb50-66d313096f9e |  | note | HP*
label | a6a61373-0a55-5de3-b176-66513ab2e35e |  | note | - - - - - - - - -
label | e3c86d6e-7cc2-584a-bcae-7a9391b2be5e |  | note | Responsibility - Site Engineer & Superintendent
label | 55b68f2f-62e4-5cf8-b3af-b2d296a4fa1d |  | note | - - - - - - - - -
date | 60dc1f6a-1830-5d36-8e21-4678e2f5e4e1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 - Review of Subgrade Test Roll
label | 6e52faff-e5a2-5346-932b-26fa409d23cb |  | note | Frequency - Prior to Placing fill
label | 59576aa3-9f3b-5dc8-8dc6-8730703fefa5 |  | note | - - - - - - - - -
label | 17e7e24b-7381-55b1-92d3-243fecfe7943 |  | note | Acceptance Criteria - No fill is to be placed on the prepared areas until the the area has been reviewed by the Superintendent.
text | 56ad90b1-5473-5f87-9ffd-84544b04702a |  | textbox | Subgrade ITP Number:
label | 134bfa0f-c1b3-50ef-9327-69311d65f903 |  | note | - - - - - - - - -
label | 23f2a6f8-595d-5464-b94d-2e30f23eb95a |  | note | Reference Documents - VicRoads Spec.
label | 35f49d8f-cf44-576d-90a4-7f7618f4af9e |  | note | Cl. 204.12
label | 8539dc0c-eeda-52d8-a2d5-c9069fcfbccf |  | note | Cl.173.03
label | 7518ded3-9855-51f7-9cb2-76bece985676 |  | note | Cl. 204.10(b)
label | 94cc2bc0-80b9-5429-8968-1ebef5b7351a |  | note | Cl. 204.07(d)
label | 9ff624c7-99e7-536c-b3c4-740fef20a5fc |  | note | - - - - - - - - -
label | e4f0d795-3124-5120-9685-bd46aa964507 |  | note | Inspection / Test Method - Site Inspection
label | 08d98833-acbe-59a7-ba09-364712972ea1 |  | note | - - - - - - - - -
label | e15a9169-8af2-5caa-976b-717e1fca1c65 |  | note | Record of conformity - ITP visually reviewed by Engineer
label | ea76d49c-e151-528d-9d56-34ec936705f9 |  | note | Signed ITP
label | a63f2975-67bd-539f-b1f8-bde363edfad6 |  | note | - - - - - - - - -
label | f74e1c4b-382e-5d07-b8ec-c37523ad6217 |  | note | IP
label | 6238300d-7553-5b79-a24a-279418e3ac9b |  | note | - - - - - - - - -
label | c6a3e715-f802-57c4-8b77-c4bd06c70b70 |  | note | Responsibility - Site Engineer & Superintendent
label | f20f5960-a8d4-5d2d-8cd9-65b60c6df350 |  | note | - - - - - - - - -
date | 8aabd1d9-3efc-56ee-94e3-fc0525ed6a96 |  | date | Date Completed:
checkpoint-group |  |  | section | 2 - Fill Activities
checkpoint-status |  |  | checkpoint | 2.1 - Survey set-out
label | 8570b0ce-897d-5e74-b27f-d7205411e9a6 |  | note | Frequency - Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used.
label | b4a4ceca-930b-5042-927f-b3954737281c |  | note | - - - - - - - - -
label | 28fd853d-b297-5560-aa9b-8cbf8268e5be |  | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used. The boxing width shall not be less than specified or shown on the drawings and the edges of boxing shall not deviate by more than 50 mm from the designed offset from the centreline or design line.
label | 1e995fd2-3af0-5fc0-b1c3-4dd88af4d1dc |  | note | - - - - - - - - -
label | 32604506-a4c7-5037-952c-d0e77b25e1eb |  | note | Reference Documents - Project General Specification Cl.1190.06 Latest IFC Drawings
label | 7e57c400-7e25-534f-b22d-ae10ace35be0 |  | note | - - - - - - - - -
label | dd70dda4-31bf-56f4-a0c8-90494fca5378 |  | note | Inspection / Test Method - Site Inspection
label | 49f32e1a-cb7f-52eb-8e9d-56812724fb3d |  | note | - - - - - - - - -
label | b4c24f1b-6299-5795-8689-c576abe44f3a |  | note | Record of conformity - Survey records & pegs on the ground
label | 4145dc91-983b-56c0-957f-ff0bab870694 |  | note | - - - - - - - - -
label | d239827b-a749-5fa8-8505-cf9ccfa7d22e |  | note | SCP
label | ade66612-df92-592d-80d0-0abb7f0a9362 |  | note | - - - - - - - - -
label | 9aa871b9-bc33-5b04-9369-a2a1ea61e9e5 |  | note | Responsibility - Site Engineer & Surveyor
label | 94438e71-0f19-514f-998c-70602f4a1a26 |  | note | - - - - - - - - -
date | fc9d927d-6c32-5ea7-a620-5a5650747a59 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Placement of Fill
label | 521d4940-230d-52eb-84f0-84de30011331 |  | note | Frequency - Prior to Fill
label | 9f4dbabf-88e0-5c40-89b3-4c37ce641d18 |  | note | - - - - - - - - -
label | 7220a2ef-8779-58f3-9902-cdd83028f59d |  | note | Acceptance Criteria - Fill material shall be spread and compacted in layers not exceeding 200mm compacted thickness. Layers with a compacted thickness >200mm may be placed subject to approval from the Superintendent.
label | ddb78c05-cbd6-58c9-8c58-ab5b47438584 |  | note | Each layer shall be keyed in to the layer above by means of a textured surface
label | 1c4c78c9-4d98-5870-b480-149c132423d0 |  | note | Any rocky material present must be uniform throughout the layer.
text | 42d12f43-7823-55eb-b8c7-4d62bf0d9302 |  | textbox | RFI Number:
label | 97daf980-d04c-560f-b0ff-32ce0ee7b5a4 |  | note | - - - - - - - - -
label | 1f631b1b-020f-5ca2-beda-fe55f4b68049 |  | note | Reference Documents - VicRoads Spec. Cl. 204.10(d)
label | 34eb497c-7f42-53fa-9fe0-fc9d2f6b3d2b |  | note | - - - - - - - - -
label | 799dbeb2-3e95-5749-80c9-ce618c1108b9 |  | note | Inspection / Test Method - Site Inspection
label | 76edaef3-548f-5653-bac9-81d109045964 |  | note | - - - - - - - - -
label | e33b007a-c707-5c06-8481-dfecd2b145b4 |  | note | Record of conformity - Signed ITP
label | a5af0ab8-2613-58a1-afc8-7d5b090fbb65 |  | note | - - - - - - - - -
label | 2ca1ecbf-3639-5900-92cf-77fcd9885834 |  | note | HP*
label | e7fe6a17-cbe2-56b1-808a-4d392cf0e208 |  | note | - - - - - - - - -
label | 97b1d149-875c-5942-bb7b-fdb118cf1f62 |  | note | Responsibility - Site Engineer
label | f7bc22d1-4540-5032-a356-1e1c1293a7b0 |  | note | - - - - - - - - -
date | 3d2073ff-c6aa-5f46-b5ac-325b376a9cf3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - Preparation of final surface
label | 36a66939-323c-5b98-88d0-a988ae468bf4 |  | note | Frequency - Prior to placement of next layer
label | a94ebf57-f90d-522a-b3d6-d1b6a23a7e27 |  | note | - - - - - - - - -
label | 7276807a-06a4-557d-82b6-4f41bc3ffac4 |  | note | Acceptance Criteria - The level tolerances at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | 60ed2202-0d66-5d5d-b978-6f2ced0d5021 |  | note | Surface is smooth, hard, tightly bound and free from depressions which are capable of holding water Surface is not to be more than 15mm or less than 30mm from what is specified in IFC drawings
label | f1f6b5f0-41b7-5c05-947d-2f3b3cd63cd1 |  | note | - - - - - - - - -
label | 0cb23375-1f58-57be-b2ab-9e547036b02f |  | note | Reference Documents - VicRoads Specification
label | 95ac1ecb-3954-592b-9c23-bdc503c9e93f |  | note | Cl. 204.15
label | 95ff81d8-985f-5c0d-8512-6abd8030a564 |  | note | Cl. 204.03(g)
label | ad9b631f-5047-519d-88ee-66305fbfabc9 |  | note | Cl. 173
label | 8366c479-429a-53d1-8d30-87065191af1d |  | note | VicRoads Specification Table 204.03(f)
label | 952acc90-188f-5e4b-93ef-cfecffc8add4 |  | note | - - - - - - - - -
label | 32afc82c-507a-57de-8c75-46477b4d20fc |  | note | Inspection / Test Method - Site Inspection
label | 881f2024-c751-5b35-a675-767ad1ed19e2 |  | note | - - - - - - - - -
label | 90926b15-a221-55c9-857f-64e02294dbd3 |  | note | Record of conformity - Signed ITP
label | 888e708e-676f-52e8-b4e8-a1e4440c3343 |  | note | - - - - - - - - -
label | 5c2759ed-64a3-5234-a7d1-ba5815539da6 |  | note | IP
label | f890e337-a2f3-53ef-97b3-9bbb4fa5df23 |  | note | - - - - - - - - -
label | 6f2215a9-0230-5d07-82b9-d160315497d1 |  | note | Responsibility - Site Engineer
label | 579332e4-5365-57cc-994a-8ab5b3c540c8 |  | note | - - - - - - - - -
date | 2d57878a-18c3-5e57-bf01-0ecf92359fa1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 - Proof Roll - Top of placed layer
label | 629a0dac-7478-5202-bbee-1084ecf0d2d8 |  | note | Frequency - Proof Roll - Top of placed layer
label | 34bca4cb-8873-53c7-af7c-05ef9d276a9d |  | note | - - - - - - - - -
label | 41411319-d3d0-58a1-8845-8570d7a8f95a |  | note | Acceptance Criteria - Superintendent to be present during all test rolling.
label | ae97efb5-fb27-5df6-b88a-4e39fc819a4a |  | note | Fulton Hogan to provide not less than 24hrs notice to the Superintendent of the location and commencement time for test rolling.
label | 2d063e62-da54-5f23-b3a7-e4f29ef2621d |  | note | No fill is to be placed on the prepared areas until the the area has been reviewed by the Superintendent.
label | 9851c363-f837-5760-b3bc-01a143f003c2 |  | note | Where unsuitable material is encountered the Contractor shall propose in situ treatment and depth of excavation to the Superintendent for review.
label | a1d4049f-5af5-5c61-a049-5ee31262b9f7 |  | note | Where <10% of the lot area is deemed unsuitable, material shall be rectified as agreed by the Contractor and Superintendent
label | 0878e10b-cd05-52de-969a-86931852e096 |  | note | - - - - - - - - -
label | 79dec4b7-889e-54f7-a0c2-45a780a3e78c |  | note | Reference Documents - VicRoads Specification
label | 3683c44c-6a8f-5826-bfa6-802f6b2ab357 |  | note | Cl. 204.12
label | d3f5929b-78fd-58a6-9514-bcea7bbcfee3 |  | note | Cl.173.03
label | 79214783-cbe3-5612-92ba-29ee1a837f30 |  | note | - - - - - - - - -
label | 403c111a-efc5-5e45-bc68-bb36dffa52d8 |  | note | Inspection / Test Method - Site Inspection
label | 6d696017-6cdd-5c0f-923f-5f119e433175 |  | note | - - - - - - - - -
label | c36bdbdf-04a5-54b8-9633-4507d0d1fd36 |  | note | Record of conformity - Proof Roll Form signed.
label | 7843a348-6257-55be-8188-bede13bb65ff |  | note | - - - - - - - - -
label | 3f2b9785-5f87-50a0-8a7b-68c8c4e54d4c |  | note | HP
label | 2e749f51-6560-5db6-b3e5-04273632baf0 |  | note | - - - - - - - - -
label | c5bf3b75-2973-539f-a587-c432e0b4fe0b |  | note | Responsibility - Site Engineer & Superintendent
label | b83dde77-11dc-5f15-b0a9-ad55474268fd |  | note | - - - - - - - - -
date | ae7b27b3-e253-5791-b6aa-3cdce97f4bde |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.8 - Post-compaction Testing
label | 1600cf48-d409-533e-b136-a7f503f5d0ad |  | note | Frequency - Post-compaction Testing
label | e4a81ef8-08ae-5a26-ba4c-5e61062aa3b7 |  | note | - - - - - - - - -
label | c44b585d-926a-5f95-b9e3-1acfb80aaca3 |  | note | Acceptance Criteria - Type A Material shall be tested for the following:
label | bf944f1c-282d-53cf-bbfd-4cae6268967d |  | note | Characteristic Density Ratio ≥ 99%
label | cf13c945-83b9-55c1-9b77-376603642a35 |  | note | CBR ≥ 6%
label | 7c24a723-7397-57e9-bf48-44d919e3ece1 |  | note | Swell ≤ 1.5%
label | 7b1b7067-80db-539c-97c5-ce63bbe560ea |  | note | Permeability ≤ 5e-9
label | 60a4c7ba-cad4-571d-a75e-9a114ba57a93 |  | note | PI (LL) = 6 - 25
label | c119a248-3286-5141-bde6-ec26cb126abb |  | note | PI x 0.425 passing ≤ 1000
label | e0c573bc-3287-5fcb-b8f5-712dfa14de85 |  | note | Grading:
label | c294ad31-810c-504a-8789-484538a90c0e |  | note | % passing 75.0mm sieve = 100
label | a5a0d604-d32f-5cf4-82d6-51e3994218f2 |  | note | % passing 4.75mm sieve = 40 - 80
label | 34e7c92b-8ddd-58a4-b742-de1fbe54fa6f |  | note | % passing 0.075mm = 10 - 40
label | ee15df3a-0ff0-5862-a9a0-9a151bd7c76d |  | note | Subject to approval min frequency testing as follows:
label | 49d10102-1672-5c5d-b96a-3ba7ce0ba34b |  | note | Compaction & Moisture: 1 test per 2 lots
label | 056b3e52-3325-56f9-983b-e0507c20b3df |  | note | CBR & Swell: 1 test per 2 lots
label | 7074bfff-04f6-57be-95e9-5fcacb2cc9a9 |  | note | Grading: 1 test for every second lot tested for compaction
label | 266bba19-9b02-5d66-8f3b-a2b366627a09 |  | note | PI (LL): 1 test every 4 lots
label | 3727b5ab-dfa9-5348-a02e-acd05365a647 |  | note | Permeability: 1 test every 4 lots
label | f65d6495-4c90-560c-94da-d16fcca5ec5b |  | note | Attach: Test Reports
label | 4d64320f-3ebf-5318-ad56-31c1594ec4d6 |  | note | - - - - - - - - -
label | b5b7eee0-b440-5119-b05d-ff47d1b8ac93 |  | note | Reference Documents - Table 204.131
label | 16f33654-71c6-58d3-9a24-fcaf7bb50153 |  | note | Section 204.13
label | 249b2afa-cd10-521e-a3c2-7d0824588d5e |  | note | Section 204.14
label | 2377c77e-7ffe-55d5-9276-0927bd3c2a11 |  | note | - - - - - - - - -
label | 6374eac9-9426-5fe5-9d31-9bc42e970f79 |  | note | Inspection / Test Method - Site Inspection
label | 037b1983-6835-5997-896b-efd3bfcbc248 |  | note | - - - - - - - - -
label | dea53898-1801-5b8c-af4b-0b542c88b876 |  | note | Record of conformity - Attach Test Results
label | 6e0d74b9-d7ab-5460-b259-b7e62723f324 |  | note | - - - - - - - - -
label | f42d33a1-e85c-5f8c-98cc-4d9a1009b77e |  | note | TP
label | cc8ee653-861a-57ab-a29d-188c44582fc0 |  | note | - - - - - - - - -
label | 7cb25fb5-ef14-5659-aade-040853d96bbe |  | note | Responsibility - Site Engineer
label | 3e47ce3e-1375-5d67-a979-007b95059d5d |  | note | - - - - - - - - -
date | a676bcb9-f14e-5e4c-9a4f-7db7961bfe8a |  | date | Date Completed:
checkpoint-group |  |  | section | 3 - LOT Closeout
checkpoint-status |  |  | checkpoint | 3.1 - Survey As-Built
label | c3ebb6d2-1528-51b9-9e4b-bd753d82b0a0 |  | note | Frequency - Each lot
label | dfed8f42-1b18-5472-9503-4dd349c05047 |  | note | - - - - - - - - -
label | de197211-34b8-558f-91f2-19585627d382 |  | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | fa67f69b-be3c-5b8f-a5e9-718214a40664 |  | note | Scale A:
label | 45be3e26-a0be-529a-9f8c-a59d0a6a1819 |  | note | Min. No. of Measurements Per Lot: 80
label | c2ad4a3b-8d2b-564c-aab9-4f365ac651d2 |  | note | Range x (mean) = +5, -15mm
label | 24969940-e89c-56e4-95b3-48aa0868c1f9 |  | note | Max S (Standard Deviation) = 12 mm
label | 647d3971-e6f5-5a31-a2c0-9fff2ecac3e7 |  | note | Attach: Survey As-builts / Survey Report
label | 9e05c90d-247c-5460-a663-29498a480b2e |  | note | - - - - - - - - -
label | 2b79f704-cfc6-5df8-8116-2b346b961250 |  | note | Reference Documents - Section 204.03 (h), 204.16
label | bb400183-5c53-5637-9e15-b57956972bb4 |  | note | - - - - - - - - -
label | ba2e00a5-865a-5f42-baac-0720177099c9 |  | note | Inspection / Test Method - Review Document
label | 37c45d09-d78e-561c-a330-9ee732267f8e |  | note | - - - - - - - - -
label | c3f13828-52e7-585c-acbb-3bff7e59e52c |  | note | Record of conformity - Attach As-Built Report
label | e4c9389e-408a-5f87-89fd-7fd3344b89ef |  | note | - - - - - - - - -
label | 877829e6-d176-5d70-ba69-6d892812b242 |  | note | SCP
label | 7a8cebdc-5880-5638-9251-001ae02aa03b |  | note | - - - - - - - - -
label | 25dfee29-5062-5025-acde-5f9f97024768 |  | note | Responsibility - Site Engineer & Surveyor
label | f9cc090b-7c5b-50fb-8b4d-1a7cd438563b |  | note | - - - - - - - - -
date | 00590504-c9ce-5cb6-9e02-53ae93804cc3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Non-conformance Closure
label | bca8cee7-b2bd-541d-a266-14ead3ac4065 |  | note | Frequency - Each Lot
label | cf9a2439-604d-5286-8385-251081b88643 |  | note | - - - - - - - - -
label | 04d768b5-1fd9-5cab-a31b-c51f6ea90f98 |  | note | Acceptance Criteria - Ensure All related Non-conformances are recorded and closed out.
text | 9d10d40f-05cd-504d-94f6-4e57aa27eb4d |  | textbox | CAMS Case Number(s):
label | 11f102a7-f81b-52b1-80d0-98a31104cf71 |  | note | Attach: Closed NCR Report
label | 7d86770e-40ab-5358-b800-5a7b91a3654a |  | note | - - - - - - - - -
label | d749b54b-9d83-594c-82d1-0debe2c972a7 |  | note | Reference Documents - Quality Management Plan
label | 3f822681-e60f-53e6-81f7-e718b2072f55 |  | note | - - - - - - - - -
label | e635094c-4b47-517a-a0e7-3b76292f59c2 |  | note | Inspection / Test Method - Review Document
label | a67f60ff-8108-5fa5-aa26-82d824a4cfa7 |  | note | - - - - - - - - -
label | 33285110-e613-5c0d-ba01-6ae9910846e2 |  | note | Record of conformity - This ITP
label | 8f9f1e54-26e9-50bc-bc60-66c3ce900ceb |  | note | - - - - - - - - -
label | 3e0a6302-ea0a-5810-b8e9-ab467fa4df80 |  | note | IP
label | 60bd3e85-5d65-555a-946d-65e9a7086e4e |  | note | - - - - - - - - -
label | 54803571-8cd6-5acb-bf9b-c64f35a4896f |  | note | Responsibility - Site Engineer
label | 46244b3c-596f-5e73-a387-d1682a005124 |  | note | - - - - - - - - -
date | b7666894-de23-53e8-b494-228a1bdb9bed |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - Red Line Markups
label | 358f17e3-0627-53c2-b268-81b75c321b8c |  | note | Frequency - Each Lot
label | 9a076d2e-4e61-544b-a9b0-fc1041e6bf0b |  | note | - - - - - - - - -
label | c51b788d-dedc-5c7d-8dd5-e0d8bcb0bdee |  | note | Acceptance Criteria - Ensure any changes from design are captured in red-line markup drawings
label | 745ce23d-c573-5d4e-acdd-78abd0abfbef |  | note | RFI References
label | e51b6f59-f9ef-5a77-b9cc-19695c0b06cf |  | note | - - - - - - - - -
label | 17fb19d2-b8ec-5736-b13e-5ffaea7b2283 |  | note | Reference Documents - Quality Management Plan
label | 9074e078-048e-5bdd-a4b6-b4643af3f103 |  | note | - - - - - - - - -
label | 2fd7b5e1-9f6d-5d11-a1c2-2abe8d897408 |  | note | Inspection / Test Method - Review Document
label | b3ab5612-bdb0-5167-af9e-8737b097bbbb |  | note | - - - - - - - - -
label | 5749580b-d514-54ae-99b8-7bee3cb110c8 |  | note | Record of conformity - This ITP
label | e78811e0-8abb-578b-9998-38f8f9927461 |  | note | - - - - - - - - -
label | 23c951b9-6a82-5013-8346-8255359d657f |  | note | IP
label | 1d599f63-4757-551c-8d15-747e6f9fe908 |  | note | - - - - - - - - -
label | c9f1f2f2-7440-5a30-96c5-009784a7f74c |  | note | Responsibility - Site Engineer
label | ee52bb9c-be82-51e2-8a58-a5305f229aab |  | note | - - - - - - - - -
date | 61d3a786-566c-51de-b9d7-8eff6b878fed |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 - Final Inspection
label | febe7265-73cd-5943-8792-5505585fed14 |  | note | Frequency - Each Lot
label | 7d4c4d43-2e48-59f4-8c77-0289a7d9326b |  | note | - - - - - - - - -
label | b23f01d1-d427-5433-836d-80f6f910b0c9 |  | note | Acceptance Criteria - It is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
label | 18d4a835-5da8-55df-8003-d797a3ed6541 |  | note | - - - - - - - - -
label | c77d48f2-bfb9-5343-aaa0-fb0655d264df |  | note | Reference Documents - Quality Management Plan
label | 38ba96b3-a4e8-578b-b6a9-658d2b6ebd53 |  | note | - - - - - - - - -
label | 626025e8-239a-5a98-aed0-a190c080ee4a |  | note | Inspection / Test Method - Review Document
label | 7edd147c-e632-54e5-b946-11a5062fc9f1 |  | note | - - - - - - - - -
label | 92439361-bd2a-57a7-8f75-d1ec0e146196 |  | note | Record of conformity - This ITP
label | 1692b4d8-a698-5e33-a792-8bee5a0ead02 |  | note | - - - - - - - - -
label | 5b14fa86-578c-56ac-95db-07fb3ce24535 |  | note | IP
label | 8ad9b5b5-6858-5a5e-8790-5bb4f566bcb1 |  | note | - - - - - - - - -
label | 8e07488e-37d7-54a5-9c1c-2a40c26337c3 |  | note | Responsibility - Quality Manager
label | c1f2655a-bcfb-5918-b2f6-ee3e6f66f15a |  | note | - - - - - - - - -
date | 601e5faf-e1d2-54a5-a1ce-599e96806d3d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 1a07f000-d067-5d03-9800-9b60056ff94b |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 6cbf7655-1316-581c-8b00-915bb53e0ed9 |  | textbox | Print Name:
text | c771afb8-ba5f-5030-b1b7-ead3f43f1055 |  | textbox | Position:
date | cf106833-0ed9-5389-9cd6-b6a3d7149842 |  | date | Work Completed On
date | d094b1ba-67fd-5a25-84e5-c80309ef80a1 |  | date | Date:
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification.
select | e0502458-4955-5da7-9121-bcec35e40ea4 |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | 973eb200-3d87-5134-9fbf-faa283d95958 |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | 5f0a5488-c9fd-52c6-aef5-0d62390b7683 |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | 0e247126-60f5-54a7-8653-3c8fede6d693 |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | c4f08936-82b5-5e09-948b-bdb302882e74 |  | textbox | Other:
select | 2d966ca5-2053-571e-b759-be1fa549c152 |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | a2994a0b-d73f-5c65-b469-208e4e8689b4 |  | date | Lot Closed On
text | 4c117fc4-0480-5dc3-b25a-95eebdd8874a |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-079-UT-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0079 - Watermain Construction | 1ba60867-9f57-4091-b816-8b5de0e3acd9
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | 86ba8169-4514-5c41-8223-c13f34be4989 |  | date | Lot Created On
date | 3dc1d615-366a-56d0-8369-113a49b537b7 |  | date | Lot Opened On
date | d8592f62-53c7-51d0-aaa1-5e43917b4894 |  | date | Work Commenced On
select | 2561d6c9-1650-5983-af2c-9a97de1ff1a6 |  | dropdown | Lot Type | CIL-Civil Lot, DRL- Drainage Lot, EAL- Earthworks Lot, ELL- Electrical Lot, UTL- Utility Lot, STL- Structural Lot
text | b4b769ed-62a6-53d1-84a5-4b28f8625595 |  | textbox | From and To Chainage
select | 62200017-3922-5957-b450-cda1a4216075 |  | dropdown | Construction Element | UTIL - Utility
select | 780dfe68-078d-5a7a-9430-11bd888bd936 |  | dropdown | Activity | WATE - Water
select | 7326aa92-e844-5326-9613-816ce6e9c605 |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | eab1dd09-c651-5ec9-ba7a-28a78bd7b2a0 |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | 849bc200-0f3c-5419-bb82-ebd663e3d4de |  | textbox | Engineer Responsible
text | 5975b6bd-f0bf-591a-aa52-509aed240b4a |  | textbox | comments
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1 Issued for construction drawings
label | 71ce61ed-bbd0-5678-b98e-dc77386b6ec4 |  | note | Frequency: Prior to commencement
label | ee0689c7-af5c-563c-a4b4-b1770cd0848b |  | note | - - - - - - - - -
label | 7c779c0b-56a2-5295-b313-1a89b7071bda |  | note | Acceptance Criteria: Ensure the most current revision of drawings is used to conduct the works.
label | 9e0fe188-c502-5df4-b917-1273b4c9a0be |  | note | - - - - - - - - -
label | 05fe79d6-fc33-5686-a5ab-928313957ad3 |  | note | Reference Documents: IFC drawings
label | 1a43333a-246a-5110-91c6-e66101da40c8 |  | note | - - - - - - - - -
label | e80d3a96-b3bc-5296-86f2-12c6a2d3a7f1 |  | note | Inspection / Test Method: Review
label | e450c126-f066-5258-b95e-934f7640cda5 |  | note | - - - - - - - - -
label | 02fab799-aea3-54e0-911c-c7d664627353 |  | note | Record of Conformity: Compliance checklist - Daily Prestart Form
label | 104befd8-3616-5798-b847-3e67b1a217dd |  | note | - - - - - - - - -
label | 9b63e0ee-3ce1-5952-b5b6-28547afef91d |  | note | HP*
label | 15ece9bc-0870-5b61-852e-6132a3398cd0 |  | note | - - - - - - - - -
label | 75da4746-f00f-54e8-8721-8f20297fa5b9 |  | note | Responsibility: Project Manager/Engineer
checkpoint-status |  |  | checkpoint | 2 Permits with relevant authorities
label | 5e0ea6b8-c3a4-58b6-a070-276627b2a6cf |  | note | Frequency: Prior to commencement
label | 4143ccdd-116b-5055-b492-3c5ee5f0514e |  | note | - - - - - - - - -
label | 2c9ff944-1c13-5a91-8b58-5762d1fd2b65 |  | note | Acceptance Criteria: Permits to be obtained by relevant authorities
label | adb19514-be0a-56b2-9474-99d8fc48b449 |  | note | - - - - - - - - -
label | ac60abba-56ff-5dc9-9609-0e410671ad45 |  | note | Reference Documents: DBYD
label | 8f7fcea3-ba79-5099-912a-cb29a0b42d8e |  | note | - - - - - - - - -
label | 8118d3a1-0b1e-545a-89c1-390abce2dd6f |  | note | Inspection / Test Method: Review DBYD
label | 3c4bda8d-9816-53fe-aa16-f2949f22e323 |  | note | - - - - - - - - -
label | 2742ce32-dfba-5aaa-b997-06de6872c69c |  | note | Record of Conformity: Compliance checklist Excavation Permit
label | c8af969b-51c0-5ba9-93db-113d818cdd7e |  | note | - - - - - - - - -
label | 508ebe92-e859-5d74-aa78-f6fa7849fff9 |  | note | HP*
label | be76e49c-62f6-5975-bc9a-a33c50e4709d |  | note | - - - - - - - - -
label | 008f7e27-173d-5792-aceb-54a857c77696 |  | note | Responsibility: Project Manager/Engineer & Superintendent
checkpoint-group |  |  | section | 2 - SURVEY, SETOUT & LOCATION OF EXISTING SERVICES
checkpoint-status |  |  | checkpoint | 3 Survey set-out
label | 3641fe8f-3e2a-5c2f-946c-31dfb5c75a61 |  | note | Frequency: Prior to commencement
label | abc59b6c-76e7-56eb-9903-64cfce918f3a |  | note | - - - - - - - - -
label | 5cea5525-49ee-57bb-a345-361023492631 |  | note | Acceptance Criteria: Building line pegs to be installed prior to any excavation
label | d5840ddd-a670-510a-b2ba-30d6f7e321f1 |  | note | - - - - - - - - -
label | 90a7f299-b6b2-57ec-9e87-92bc4212acc2 |  | note | Reference Documents: IFC drawings
label | d8cce7b9-b78f-5e03-ade7-654336198432 |  | note | - - - - - - - - -
label | f71605dd-f6a7-5f8c-b1bf-d7af8576ab2e |  | note | Inspection / Test Method: Visual check
label | 4c3c2107-8529-5572-a455-372818b4b342 |  | note | - - - - - - - - -
label | fd33cba3-3b2c-5b77-bd03-1e00b6929d75 |  | note | Record of Conformity: Compliance checklist - Pipeline construction
label | b615ea00-b669-5256-a3df-2b9cdf74caa7 |  | note | - - - - - - - - -
label | a60d0226-ce37-5101-a108-fe88763ec0d0 |  | note | SCP
label | d495b59a-7cc3-5a1b-8930-388b2cfd7d6e |  | note | - - - - - - - - -
label | f1def94b-1289-5442-ac46-72ae2cd01906 |  | note | Responsibility: Surveyor
checkpoint-status |  |  | checkpoint | 4 Service location
label | 53fc9d33-93d2-52ad-abea-0efa2e5ba42b |  | note | Frequency: Prior to Excavations onsite
label | f7fd1676-58c5-56a7-b265-2326ce39174b |  | note | - - - - - - - - -
label | 771de4c6-9dc2-510c-98c7-e70a6104d5c9 |  | note | Acceptance Criteria: All existing services to be located and protections in place
label | a699e081-43e4-5126-9743-f1e37149d161 |  | note | - - - - - - - - -
label | 0ebb8d34-6d61-5ccf-a3d6-9602a459c286 |  | note | Reference Documents: DBYD
label | 52d023f0-1c66-552a-abcd-57f74d4e01bf |  | note | - - - - - - - - -
label | 8e181dcc-3718-5fac-835e-064373fcdc85 |  | note | Inspection / Test Method: Review drawings and DBYD
label | f4130936-cfc2-5c9e-8166-3126c354cd82 |  | note | - - - - - - - - -
label | c7a982db-2474-5469-8a86-bb18ab3998a3 |  | note | Record of Conformity: Compliance checklist Excavation Permit
label | 2fd0fe3f-3974-5f59-bfdd-f0469cdcfba7 |  | note | - - - - - - - - -
label | a828dbce-5d07-54c4-8b0a-3539b252d1e8 |  | note | WP
label | 98c293f2-3674-56cb-a9d7-0ec373f29b0e |  | note | - - - - - - - - -
label | eea2f853-11c1-57cf-a2a8-e92e1f71b93d |  | note | Responsibility: Site Manager/Engineer/Superintendent
checkpoint-status |  |  | checkpoint | 4.1 Installation of property service conduits
label | 9f5dc2ff-4b30-5215-b648-1380bceb0f6c |  | note | Frequency: Prior to commencement
label | 31dc1be7-8a66-5929-ac60-5aea5ff4de0b |  | note | - - - - - - - - -
label | 0a866673-110c-5d6f-af53-e1fec827fd17 |  | note | Acceptance Criteria: All service ducts required by road contractor to be installed prior to works to be inspected and ensure they meet MRWA standards
label | 90ff4799-c0f4-5c33-91be-23b1a17bd207 |  | note | - - - - - - - - -
label | 24fe0695-e193-51e1-8e89-5c50a77025a6 |  | note | Reference Documents: MRWA-W-110
label | 18a45155-d478-569e-a0ac-406aba6cfa36 |  | note | - - - - - - - - -
label | b83b500a-4977-51d2-9c24-23aeb69dcc34 |  | note | Inspection / Test Method: Visual check
label | 73e0a71e-20d5-50cf-b508-5af52a556a84 |  | note | - - - - - - - - -
label | b034c4e5-427d-5d1b-a5cc-a534eeb1df95 |  | note | Record of Conformity: Site Daily Diary Entry
label | 8f347212-e032-5b9e-b077-90e2f163a644 |  | note | - - - - - - - - -
label | e78db91d-4272-5e72-b96a-2c826460a020 |  | note | HP*
label | a5d026aa-d631-5de1-82c4-a56501af9c93 |  | note | - - - - - - - - -
label | c03d5582-3c10-5a1b-9be7-d1caed91804e |  | note | Responsibility: Site Manager/Engineer
checkpoint-group |  |  | section | 3 - MATERIAL CONFORMANCE
checkpoint-status |  |  | checkpoint | 5 Correct pipe and fittings onsite
label | 2044c14a-79d8-5423-9831-448cda6ae0dd |  | note | Frequency: When delivered
label | 4db879f8-faab-5fdd-a8fa-48d6b9d3382a |  | note | - - - - - - - - -
label | fbb675d8-21e8-585e-957f-66d5fbad3bed |  | note | Acceptance Criteria: Inspect materials in delivery against order. Pipe size matches plans
label | 0ed368aa-c8d1-5178-8276-7496181e4b5c |  | note | - - - - - - - - -
label | 063d7457-ca24-5a74-ba32-ab344d1a9c93 |  | note | Reference Documents: Delivery docket/ IFC drawings
label | 97988362-db32-50ad-a361-8ab2a8b3a826 |  | note | - - - - - - - - -
label | 40b6e963-1c43-5530-acac-8821ab616be3 |  | note | Inspection / Test Method: Visual check
label | a126c118-ede0-5639-8540-e5d5aedf4a96 |  | note | - - - - - - - - -
label | 94ff5875-3063-5c9a-a13f-9d0d02d1a633 |  | note | Record of Conformity: Compliance checklist - Pipeline construction
label | 05f43226-3f59-5ffb-b527-40620408e78b |  | note | - - - - - - - - -
label | 71c3ab1f-ff60-534e-8453-48b6ff95dbf8 |  | note | HP*
label | caaf1be7-bd12-56a5-bfda-66b85a147387 |  | note | - - - - - - - - -
label | 30823e9a-0a7b-5167-aa10-f63ed3171124 |  | note | Responsibility: Site Manager/Engineer
checkpoint-status |  |  | checkpoint | 6 Correct embedment / backfill materials onsite
label | d561db0b-d68d-5964-87a1-51219712ec11 |  | note | Frequency: When delivered
label | 5c3046cc-f2b8-5ac9-949a-4315a580258a |  | note | - - - - - - - - -
label | e56a0323-bc4d-53d5-855d-25b9cdab8163 |  | note | Acceptance Criteria: Inspect bedding material to ensure suitability
label | 4812d941-22dc-5fe4-ab7c-311604aa5c59 |  | note | - - - - - - - - -
label | 997ab262-aac4-52e7-9962-f88c2423d650 |  | note | Reference Documents: MRWA-W-201 to 203
label | e805feb2-f0b5-58ba-922e-883fb45ed0eb |  | note | - - - - - - - - -
label | 2de17da6-2461-594e-9b59-7189fd2fecb7 |  | note | Inspection / Test Method: Visual check
label | c01b5526-ddf5-5745-b356-5e095b8eec92 |  | note | - - - - - - - - -
label | c7cb2c2b-0c8b-5273-8b39-da67c76a955f |  | note | Record of Conformity: Compliance checklist - Pipeline construction
label | b7b40e50-0115-51f5-9273-09fa42f316fe |  | note | - - - - - - - - -
label | 5383dde4-6204-53e8-b1c5-c46c494425a9 |  | note | HP*
label | b09475ca-e8a1-5b10-a12b-f02af01523d0 |  | note | - - - - - - - - -
label | ffa13d4d-2633-53b6-8239-cc0a99f4d1d1 |  | note | Responsibility: Site Manager/Engineer
checkpoint-group |  |  | section | 4 - ENVIRONMENTAL & SAFETY
checkpoint-status |  |  | checkpoint | 7 Environmental controls
label | 65098306-7204-548d-a041-0c84b27f922a |  | note | Frequency: Daily
label | 9f532d33-76dc-5fce-86d9-8e992d547355 |  | note | - - - - - - - - -
label | 64a1ed90-43bb-5878-9ee0-951d490c979a |  | note | Acceptance Criteria: Ensure environmental controls in place and being maintained as per the site EMP (if the civil contractor is responsible for managing the site then as long as we do not distrust their controls this item can be ticked as N/A)
label | deefbfb2-0438-5ec3-a4d5-d1dd90b230a8 |  | note | - - - - - - - - -
label | fce295ad-0b2b-5b3c-9891-f1a892484949 |  | note | Reference Documents: EMP
label | 47bac0ef-b138-54c1-8bea-656a3b1dd62e |  | note | - - - - - - - - -
label | 2aca37d6-ea27-50d7-883a-eb7ed654cebd |  | note | Inspection / Test Method: Visual
label | 0cdd9e6b-8be2-55e2-b114-cb2e52c629e4 |  | note | - - - - - - - - -
label | eb6e4670-c918-54e2-a1b8-1ce4e06f3e01 |  | note | Record of Conformity: Compliance checklist - Daily Prestart Form
label | 36b401b5-9312-5d95-b911-a227951178cc |  | note | - - - - - - - - -
label | 0f6acd3e-2767-5217-90be-f47b734acf12 |  | note | HP*
label | cb0a8088-e03d-52a1-88d6-5303d4a6e649 |  | note | - - - - - - - - -
label | 6123005c-152c-555e-aa3b-6902513b2b0b |  | note | Responsibility: Site Manager/Engineer
checkpoint-status |  |  | checkpoint | 8 Safety controls
label | 75e87152-c09d-5ec6-a7bb-7290e66ecf54 |  | note | Frequency: Daily
label | 3517eacf-c638-5430-b52e-b80debb6d321 |  | note | - - - - - - - - -
label | c2484e31-49db-53ee-9002-bbab162f499e |  | note | Acceptance Criteria: Ensure safety controls are in place as per the relevant safety instructions and SWMS
label | eaaab401-2c4f-599a-a4f0-bbfe249d6f64 |  | note | - - - - - - - - -
label | dcc5cbe3-cb51-5500-8d96-445b3b64c8e8 |  | note | Reference Documents: SMP
label | a64d6897-ee94-566e-b978-5fbb972488bd |  | note | - - - - - - - - -
label | 6b9e1c8a-b426-5cb9-b5a2-597163f20d45 |  | note | Inspection / Test Method: Visual
label | 7f759aba-59c5-5cc5-b675-730ca503d8a2 |  | note | - - - - - - - - -
label | 4e0ae478-59e2-54d5-9e95-1c9694bb2f6d |  | note | Record of Conformity: Compliance checklist - Daily Prestart Form
label | 2b5f8350-1cf5-5683-a328-7d17b772a5a7 |  | note | - - - - - - - - -
label | d6c1da69-891c-5870-b97f-8a3d3058d1d3 |  | note | HP*
label | 48051d5c-f5ee-5ee5-b28d-285b67557264 |  | note | - - - - - - - - -
label | 97f01bfd-9957-502c-b2c3-b027f02cebbe |  | note | Responsibility: Site Manager/Engineer
checkpoint-group |  |  | section | 5 - TRENCHING & EXCAVATION
checkpoint-status |  |  | checkpoint | 9 Trenching
label | 637d656e-efed-5358-8351-d2441c27380e |  | note | Frequency: Prior to entry into open trench
label | 55864416-d365-5e90-a074-e7caf931e37f |  | note | - - - - - - - - -
label | 81ee81b5-2b82-5e7e-adfb-755eee005714 |  | note | Acceptance Criteria: Ensure trench width and depth are within tolerance
label | 64b8de9f-40d8-55df-bccb-b45a4490d82c |  | note | - - - - - - - - -
label | ac3df8cd-8f03-5f47-ad24-ed5579ba10f1 |  | note | Reference Documents: IFC drawings / MRWA-W-202
label | 27c4cf62-e238-5d67-b296-3c9a45cc3cc6 |  | note | - - - - - - - - -
label | c799c5b5-2554-5cfa-90ff-d60223d90133 |  | note | Inspection / Test Method: Visual
label | ec9a275a-64ae-5e03-8bfc-2c84f78afcac |  | note | - - - - - - - - -
label | a975f70f-861f-5805-b136-1dc69089c780 |  | note | Record of Conformity: Compliance checklist - Pipeline construction
label | db5d8acf-3585-59a6-9409-9fccb564c527 |  | note | - - - - - - - - -
label | a014c81a-c103-557a-b754-f9056e06ee8d |  | note | SCP
label | e2e2d251-9162-57a3-bfc9-41d4d4a5e100 |  | note | - - - - - - - - -
label | c12182eb-9c16-5dd3-a9dd-229cd5e0f90c |  | note | Responsibility: Site Manager/Engineer
checkpoint-status |  |  | checkpoint | 10 Trenching
label | e1e15287-4b96-59dc-b8a5-2ecddb7875de |  | note | Frequency: Prior to entry into open trench
label | 438d5fc6-eda7-5b92-ac5b-1edf019493be |  | note | - - - - - - - - -
label | a3a722e3-3b13-5ad0-ae6c-2675a84789e1 |  | note | Acceptance Criteria: Ensure trench foundation & wall firm, stiff & suitable
label | 1cc98260-2b6f-5fe9-b769-d12112a145b8 |  | note | - - - - - - - - -
label | 5e87becb-cfd5-55af-a5cd-a51ad30b5286 |  | note | Reference Documents: MRWA-W-202
label | 8f7eeefd-66c5-552f-b1bd-8ff6b2245240 |  | note | - - - - - - - - -
label | f6d0ff0a-52c7-594c-9577-e2063ecd5e8d |  | note | Inspection / Test Method: Visual
label | b5fec29d-b79b-5731-8567-7eb9d8ad5296 |  | note | - - - - - - - - -
label | 8053b1ab-9168-5c5b-b66f-fc1a90bcfb69 |  | note | Record of Conformity: Compliance checklist - Pipeline construction
label | 28494b4e-0e9b-5d0d-b01c-f908e75d3f31 |  | note | - - - - - - - - -
label | f4e41a1d-2e3c-5084-ba14-7639ea0dc8bd |  | note | HP*
label | 92d25a25-b480-5f6c-9746-02ef85a721cf |  | note | - - - - - - - - -
label | 3ba32795-ad63-5a9d-9572-8402dcf8a0d3 |  | note | Responsibility: Site Manager/Engineer
checkpoint-status |  |  | checkpoint | 11 Placement of embedment material
label | 7220bdda-b5cc-5877-8f0f-64d534d34aa2 |  | note | Frequency: Prior to backfilling of specified area of trench
label | 792a51da-7115-51b6-82e4-10e15e164445 |  | note | - - - - - - - - -
label | 7768c6d6-bf38-51ea-b59b-5557b3d8bcdc |  | note | Acceptance Criteria: Ensure pipe bedding depth is acceptable
label | 3b021843-3177-5929-9c31-4b346935297b |  | note | - - - - - - - - -
label | 5439df03-e302-5802-93eb-7a2c090a91a8 |  | note | Reference Documents: MRWA-W-202
label | 7dbda9c8-26a6-5506-9fba-d7a269c0ca7d |  | note | - - - - - - - - -
label | 965d4cea-49b4-53bf-b764-8207a8ed6d6b |  | note | Inspection / Test Method: Visual
label | 8af85bcb-bc5d-5b4a-b76c-1b0998da9382 |  | note | - - - - - - - - -
label | ad2b3c90-f87f-5809-aa84-6e78dcb1222d |  | note | Record of Conformity: Compliance checklist - Pipeline construction
label | c32143c0-ea12-5c63-b490-2c4c258a4238 |  | note | - - - - - - - - -
label | 5bd812c4-e62d-5ff7-94d8-108ea75edf58 |  | note | HP*
label | 9c029c85-a8e2-565b-8624-aafd3cea9c29 |  | note | - - - - - - - - -
label | ec958ad6-9f0e-5af5-ac88-20dca9560c16 |  | note | Responsibility: Site Manager/Engineer
checkpoint-group |  |  | section | 6 - PIPE INSTALLATION
checkpoint-status |  |  | checkpoint | 12 Pipe laying
label | cab76adb-f6e9-5e1e-865f-a2d6fd22242a |  | note | Frequency: Prior to backfilling of specified area of trench
label | d09fd656-129f-5a70-bed8-2e8bffd83b8d |  | note | - - - - - - - - -
label | 8bf41397-6ec2-5418-aa9f-dcbcb1ac5e6f |  | note | Acceptance Criteria: Ensure pipe joint deflection is acceptable and witness marks are applied and visible
label | 4e361f97-5ce5-5852-aaae-56f7a91696a3 |  | note | - - - - - - - - -
label | c051bc40-5016-585a-8112-deed06e920bf |  | note | Reference Documents: MRWA-W-103
label | fcb3c844-677f-53de-8083-41326f9a9786 |  | note | - - - - - - - - -
label | f8da28ad-3cb8-5dd4-801c-11a34fd26306 |  | note | Inspection / Test Method: Visual
label | 59b60331-9436-5eb2-8a58-0ce3bba75519 |  | note | - - - - - - - - -
label | 5332104c-8c52-5eea-9f14-15d30f5db732 |  | note | Record of Conformity: Compliance checklist - Pipeline construction
label | 3b011eda-4246-5bcc-a0ff-6c1491d0ad8c |  | note | - - - - - - - - -
label | 7550455b-cabb-5ce3-adb4-556d8e4be97e |  | note | HP*
label | 831673e2-579a-5939-b311-0f4a2a69ba14 |  | note | - - - - - - - - -
label | 13b2b34e-2c9b-59ba-860b-c70d85e9b572 |  | note | Responsibility: Site Manager/Engineer
checkpoint-status |  |  | checkpoint | 13 Property services
label | 298bf1cd-20d2-5e07-8e5b-42d5fcfa66c2 |  | note | Frequency: Prior to backfilling of specified area of trench
label | 72955a6f-ea20-5cdb-827c-bfbd490a3ebc |  | note | - - - - - - - - -
label | d527befc-254c-5c94-861d-5f44cbf58de8 |  | note | Acceptance Criteria: Ensure tapping collars are installed as per measurements on plans
label | 676e1c7b-2e72-563e-a499-f15c178f5a71 |  | note | - - - - - - - - -
label | a7e6b958-ae5e-56a0-ad42-3bb356f1bcf9 |  | note | Reference Documents: IFC drawings
label | 6a4e8c19-6a26-56b3-a52d-e0a498a4265e |  | note | - - - - - - - - -
label | 2b1b5ca9-004f-5ace-aeae-81ef54a6cbd3 |  | note | Inspection / Test Method: Visual
label | 1c9e5389-3468-5a23-9c85-d3e5463859d1 |  | note | - - - - - - - - -
label | 72322945-23e6-5b34-98c4-40cfc579ad4d |  | note | Record of Conformity: As constructed information / Compliance checklist - Pipeline construction
label | c515d233-454a-5914-ab8d-f535fdf21713 |  | note | - - - - - - - - -
label | ae2c7f85-84b4-506a-81fa-da5f82e3fb77 |  | note | SCP
label | 72121894-801c-5820-bd06-1f2565020bcf |  | note | - - - - - - - - -
label | 2b337e89-b53f-5cda-a254-3229860e1cc2 |  | note | Responsibility: Site Manager/Engineer
checkpoint-status |  |  | checkpoint | 14 Dual water property services
label | 124082dc-4e38-5b1c-8553-dea9453278a0 |  | note | Frequency: Prior to backfilling of specified area of trench
label | 621ad254-902a-5d92-a702-2301bc755a71 |  | note | - - - - - - - - -
label | 041680ef-bf89-5320-a0d5-86e930f61e78 |  | note | Acceptance Criteria: Ensure tapping collars are installed as per dual water specifications (to the left of the DW)
label | 36929bb8-b97e-51ab-a945-cc5a9156fd96 |  | note | - - - - - - - - -
label | d21c2bd3-4f22-54e4-bd43-c181fbf5188c |  | note | Reference Documents: IFC drawings / MRWA-W110 & 111
label | 7051f33f-ded2-502f-8969-46a5473dd9d4 |  | note | - - - - - - - - -
label | 00f219ca-fb82-5b43-a460-2f8d1152240f |  | note | Inspection / Test Method: Visual
label | 510c4d52-a55a-5d7c-bf97-eeed7fc572bf |  | note | - - - - - - - - -
label | abcc7586-93fb-52bd-92ae-aff59bafa762 |  | note | Record of Conformity: As constructed information / Compliance checklist - Pipeline construction
label | 9943b6fc-b36c-53f6-8aae-187665f480f0 |  | note | - - - - - - - - -
label | a5234a4b-aafe-5727-900e-1d8c2649ab29 |  | note | WP
label | 69f65e3a-a70f-5fa8-8111-16d24d5bdc9c |  | note | - - - - - - - - -
label | 543883fd-514c-5009-bc37-c7e800a77a2c |  | note | Responsibility: Site Manager/Engineer/Superintendent
checkpoint-status |  |  | checkpoint | 15 Valve installation
label | 5a6a6395-d7d3-5379-a73f-577566d24b00 |  | note | Frequency: Prior to backfilling of specified area of trench
label | cc5a1cb2-0b87-548a-9df0-891af3e1e787 |  | note | - - - - - - - - -
label | ab149d07-1b67-5960-bb46-fa9d3f51673b |  | note | Acceptance Criteria: Ensure valves are installed correctly.
label | 6afa7b40-5e2e-5c42-8c14-3bc241ff3eae |  | note | - - - - - - - - -
label | 3383516a-ef3f-5be6-9fcf-c3a4aca693c5 |  | note | Reference Documents: IFC drawings / WSA page 233 15.4
label | f08b4bfe-9fb0-5167-83ad-4a3fae3593cc |  | note | - - - - - - - - -
label | 968d51ab-3ce0-55b8-9464-4994ccdd428b |  | note | Inspection / Test Method: Visual
label | fc024d92-634e-53b5-89a4-ae0c4f4c6353 |  | note | - - - - - - - - -
label | 860eb661-f3b8-5b3a-8328-04ddb6601300 |  | note | Record of Conformity: As constructed information / Compliance checklist - Pipeline construction
label | 61c26649-6710-5f7c-9158-b1e143454ec0 |  | note | - - - - - - - - -
label | c0dd9b80-595f-5778-9563-42beb3ee4da2 |  | note | SCP
label | 935576d1-40c7-5d4c-9f3a-088cb89d18a8 |  | note | - - - - - - - - -
label | 8c439833-acb6-5c8f-a291-c0de78fa0a5e |  | note | Responsibility: Site Manager/Engineer
checkpoint-status |  |  | checkpoint | 16 Hydrant installation
label | 77466c97-a970-5fdc-b001-3fa14ab62b87 |  | note | Frequency: Prior to backfilling of specified area of trench
label | 5a47b4a3-703c-5c42-a2cb-b83ac88d69dd |  | note | - - - - - - - - -
label | 27b43153-9cc1-5774-ac9a-7567c0c25a1c |  | note | Acceptance Criteria: Ensure hydrants are installed correctly.
label | c265ca82-5703-5b15-b09e-122ae9841c83 |  | note | - - - - - - - - -
label | ff61f3d0-c46f-551d-9484-28f013b825dc |  | note | Reference Documents: IFC drawings / WSA page 233 15.4
label | d54fd15c-954d-5c0d-9b1c-4d6f8819ca9b |  | note | - - - - - - - - -
label | 62612203-a123-5fb1-9df2-4401626737cf |  | note | Inspection / Test Method: Visual
label | 91d29068-7af2-5028-9e8d-4fab22f9b3bd |  | note | - - - - - - - - -
label | 6d5b62a2-8019-5fc4-82d8-994d7a6aa761 |  | note | Record of Conformity: As constructed information / Compliance checklist - Pipeline construction
label | 47e0bf09-8692-5021-9e48-65b725f3fe5d |  | note | - - - - - - - - -
label | fad66766-75f7-5ef7-af3d-a0774abbf573 |  | note | SCP
label | c3081a56-7ee9-51c9-ab86-b995100f6818 |  | note | - - - - - - - - -
label | 2c22bc67-281c-5b8d-85c7-617d1b154622 |  | note | Responsibility: Site Manager/Engineer
checkpoint-status |  |  | checkpoint | 17 Washout installation
label | 35f86488-b17c-59b5-9e70-f396b637e73b |  | note | Frequency: Prior to backfilling of specified area of trench
label | 51d3ff25-1b05-564a-b0d4-ceef11b2f4b6 |  | note | - - - - - - - - -
label | 8687e48e-e0f0-50be-8bd7-a429abb1051a |  | note | Acceptance Criteria: Ensure washouts are installed correctly.
label | 887e388c-8700-5c8b-a6f9-cab3397dbeda |  | note | - - - - - - - - -
label | 7aacd66d-5da7-56f9-b50b-34fb3cd099f0 |  | note | Reference Documents: IFC drawings / WSA page 233 15.4
label | 16098f99-48e1-598b-85a8-d81420b884ec |  | note | - - - - - - - - -
label | 074b84dd-cf83-54a3-befd-63acd25b12ce |  | note | Inspection / Test Method: Visual
label | 1af390a4-4ba4-599c-a12a-519dda8dbd1b |  | note | - - - - - - - - -
label | 53c0cc8f-6ae5-53d5-95e1-469f9b5ba871 |  | note | Record of Conformity: As constructed information / Compliance checklist - Pipeline construction
label | b20e60e7-bf63-54b5-8a13-6571fdc04fa6 |  | note | - - - - - - - - -
label | 5e58eb1c-71ca-5499-b5e2-415d0c58b714 |  | note | SCP
label | 8ef2943f-6c66-56f2-88aa-86a27e5d563d |  | note | - - - - - - - - -
label | dbcb158d-8d3b-5b62-bca5-e100bddabf22 |  | note | Responsibility: Site Manager/Engineer
checkpoint-group |  |  | section | 7 - CONCRETE ANCHOR BLOCKS
checkpoint-status |  |  | checkpoint | 18 Acceptance of concrete delivery
label | 0126db76-d934-5061-a178-9f5dc6dcb36f |  | note | Frequency: When concrete is required
label | 7b7aacad-fac3-5951-b222-cf2b58d46725 |  | note | - - - - - - - - -
label | f83ade12-5a5b-5a9f-8b84-9a5bcfffad28 |  | note | Acceptance Criteria: Concrete delivered to site to be acceptable. WIN 25 WSA approved mix (20Mpa, 20mm rock , 80 slump)
label | b8a29a2b-89ce-5a45-a1e3-9a93eb2aa2aa |  | note | - - - - - - - - -
label | 16e17c5f-61d4-5a39-8c5b-f0414d4a58d1 |  | note | Reference Documents: Concrete delivery docket
label | 2a44b5ba-362d-505c-a075-a614b9f235e9 |  | note | - - - - - - - - -
label | fd7744a2-0106-54d2-a2a3-131a362ff28d |  | note | Inspection / Test Method: Visual
label | 3e401dba-d71c-5fb3-bcf3-8da0a3bd68ab |  | note | - - - - - - - - -
label | fae519f1-eae6-5808-bad6-9f66dae9cc4c |  | note | Record of Conformity: Watermain Anchor Block Checklist – Procedural Verification Checklist ITC-803
label | acbc4205-84f0-5215-ab0b-80737527734f |  | note | - - - - - - - - -
label | 64e18606-c4a8-58a7-b496-50bd30c36bc7 |  | note | HP*
label | ef3f1d60-00c4-5ad9-a733-cc2a65ac9cce |  | note | - - - - - - - - -
label | dee8341d-94ce-54e4-ae1f-db3f5c56431a |  | note | Responsibility: Site Manager
checkpoint-status |  |  | checkpoint | 19 Installation of anchor blocks and thrust restraints
label | 9ea0f5a6-fa1e-5616-a13e-4f4cb1e04f21 |  | note | Frequency: When concrete is required
label | f209600b-5014-5464-9cce-bc07a4102204 |  | note | - - - - - - - - -
label | f1d1f97c-affc-50f9-9bde-ecbc7d23fadc |  | note | Acceptance Criteria: Installed anchor blocks / thrust restraints are acceptable
label | 66c724e6-2c98-536e-ae97-53005a5215ea |  | note | - - - - - - - - -
label | 48a3bacd-0237-558f-acb6-0ea85bc268ca |  | note | Reference Documents: MRWA-W-204,205A & 205B
label | 157d8cb9-8854-5d15-8281-230fe0bfb4b1 |  | note | - - - - - - - - -
label | 1fa453f1-a1fd-5908-b36b-c8e0f775392b |  | note | Inspection / Test Method: Visual
label | 595d4e00-4533-5a4f-9318-910a734cb672 |  | note | - - - - - - - - -
label | 76979b51-0293-52a8-a272-2bee782dd9dc |  | note | Record of Conformity: Watermain Anchor Block Checklist – Procedural Verification Checklist ITC-803
label | a9116201-bc22-5b75-9566-e10e996e372e |  | note | - - - - - - - - -
label | 3d2a2ccd-1b30-562f-b1ef-7aa7a5f0df71 |  | note | WP
label | 278c5de8-3abf-580c-bd74-dfcdc0a94d5a |  | note | - - - - - - - - -
label | 34e8b4a1-8fc2-5df6-b434-945df6401fb1 |  | note | Responsibility: Site Manager/Engineer/Superintendent
checkpoint-status |  |  | checkpoint | 19.1 Correct steel reinforcement used in restraint
label | 0e8410da-0d9b-5f8b-b480-04f8b2eb09d5 |  | note | Frequency: Prior to anchor blocks being poured
label | 3bd5c115-6c78-5e83-a8c1-33b2335d45f4 |  | note | - - - - - - - - -
label | ddb69537-e0f6-5da4-a353-2c4ce0d73008 |  | note | Acceptance Criteria: Reinforcement is as per MRWA 205-A, 205-B and according to thrust area as noted in face sheet of project plan
label | e9a6dd85-9cd4-5d51-93b1-ce9bb7772026 |  | note | - - - - - - - - -
label | 5ed7c71c-a494-5bf3-8fd0-0465cde82120 |  | note | Reference Documents: MRWA W 205-A and 205-B
label | 76e95805-e2d8-59a7-865a-8b28f7e5befa |  | note | - - - - - - - - -
label | 7d3e5eb8-191b-5213-a4d3-f553bd5495da |  | note | Inspection / Test Method: Visual
label | 6e3fb4c2-fad5-5f9c-b795-04ec1df1b917 |  | note | - - - - - - - - -
label | dba9b224-2e25-5196-9a45-a81d62df4536 |  | note | Record of Conformity: Watermain Anchor Block Checklist – Procedural Verification Checklist ITC-803
label | a4155bf1-29a8-52b3-9ece-e39e0d220fb7 |  | note | - - - - - - - - -
label | fd9ea5b5-b1bb-52d9-b3e8-5b70885a7008 |  | note | WP
label | 4713806c-6df3-58a2-adc8-41649039e3fe |  | note | - - - - - - - - -
label | 3de0a9ef-2516-531a-8b43-a4b19aa49974 |  | note | Responsibility: Site Manager/Engineer/Superintendent
checkpoint-group |  |  | section | 8 - BACKFILL OF TRENCHES
checkpoint-status |  |  | checkpoint | 20 Placement of embedment overlay
label | 4ddd55f6-04fb-56b5-90cd-3d5d5a990ff7 |  | note | Frequency: Completion of pipelaying
label | 7e77266d-d42d-502f-9a5c-a7d4b4a2ed24 |  | note | - - - - - - - - -
label | d228e336-660c-5a98-8d4d-97a4eb963c77 |  | note | Acceptance Criteria: Ensure overlay depth & installation is acceptable
label | b43165b1-8bbc-5415-8b2c-a89ee5b33cbd |  | note | - - - - - - - - -
label | dd8f70d5-0b13-5a68-a5c9-33e2b77ec226 |  | note | Reference Documents: MRWA-W-202
label | a4fa2ecf-f6a9-5270-88e4-8d00289fd2bb |  | note | - - - - - - - - -
label | 7a8d0cb8-49a6-502e-9731-adda2e0c0d61 |  | note | Inspection / Test Method: Visual
label | 9d6ba961-8552-5f97-9fb8-8b942f2e210b |  | note | - - - - - - - - -
label | 88222bac-83f6-5cc2-b2b8-cf71cbfa0785 |  | note | Record of Conformity: Compliance checklist - Pipeline construction
label | ee36ac8c-b1be-5cf9-85a8-0e51c925fc4a |  | note | - - - - - - - - -
label | a40f8d76-b175-51e0-a5f4-aaab0497436b |  | note | HP*
label | 9c75e8c3-8a03-559c-b049-7fe3ed530662 |  | note | - - - - - - - - -
label | 4f707eba-de61-5fef-8a2c-4a698dfde611 |  | note | Responsibility: Site Manager
checkpoint-status |  |  | checkpoint | 21 Installation of detectable marker tape
label | 9e8fd6f3-3c2f-5f26-aeef-2bd64f6136fc |  | note | Frequency: Completion of pipelaying
label | 5a85303a-dc6d-51d8-8c96-16423cfd3e46 |  | note | - - - - - - - - -
label | 796437d7-2113-5c42-b891-514d01b50b37 |  | note | Acceptance Criteria: Detectable marker tape to be installed in first layer of backfill
label | 61c80408-eed6-50cc-ac33-6a3376c7c138 |  | note | - - - - - - - - -
label | 6a8a3cb7-123b-576e-9ae1-406d5926d87e |  | note | Reference Documents: MRWA-W-202
label | afa68cfc-f5da-545b-8844-6931d3039652 |  | note | - - - - - - - - -
label | e2ebf1a7-201f-50f9-a7dd-ba67644fd7f6 |  | note | Inspection / Test Method: Visual
label | 6eb05367-172c-57a5-a24b-19b79b7182e5 |  | note | - - - - - - - - -
label | 2569702e-98f0-57c2-93e5-dc0fda771931 |  | note | Record of Conformity: Compliance checklist - Pipeline construction
label | 451661e5-6b9e-552b-9993-c548b92def26 |  | note | - - - - - - - - -
label | 62a45931-adb8-5495-8458-d23c6604869f |  | note | HP*
label | 68adc165-d676-5d10-aa8b-1fcb2c1717fd |  | note | - - - - - - - - -
label | 3747812c-6a48-551f-ad27-68cde45e0b58 |  | note | Responsibility: Site Manager
checkpoint-status |  |  | checkpoint | 22 Placement of compactable material in trafficable areas
label | 152dad64-ac2b-5eb1-a1f7-b1807f9a89f9 |  | note | Frequency: Completion of pipelaying
label | 527ff08e-4c9b-57fc-bad2-46680f80376f |  | note | - - - - - - - - -
label | 8585b7db-f1ff-5ab9-ad4d-c057d0455bec |  | note | Acceptance Criteria: Backfill material to be acceptable & compaction of trench line completed
label | 36b8e78f-21ad-5521-a433-87491921878f |  | note | - - - - - - - - -
label | caafe78c-1929-58f1-a5de-26b5084f943c |  | note | Reference Documents: MRWA-W-202,202
label | 6aca51e2-2226-5091-b3bc-41c40ae62808 |  | note | - - - - - - - - -
label | 3229be67-cafd-511b-99e4-3f74e0e8ec61 |  | note | Inspection / Test Method: Visual / NATA if required
label | 334f41ee-995e-56fb-8c64-c57c79e9751a |  | note | - - - - - - - - -
label | 198e0439-a5a1-5185-a590-39eb0ded012f |  | note | Record of Conformity: Compliance checklist - Pipeline construction
label | ef7aaa8c-2e6e-5c1b-9f4c-6c9ea7e8f6da |  | note | - - - - - - - - -
label | c9a0507e-d48a-5741-8f35-6c8dce10e95a |  | note | HP*
label | 9c1a174e-0268-52c9-af8b-1e93db944177 |  | note | - - - - - - - - -
label | f930f1e9-092e-53dc-b17f-7711fa4ae778 |  | note | Responsibility: Site Manager
checkpoint-status |  |  | checkpoint | 23 Monitoring of WC1 works
label | cbbdf052-963a-5aba-8a48-cbed9d8ff027 |  | note | Frequency: Once per week
label | dc87b9e4-bd5b-5639-8fcc-cfed25abe31c |  | note | - - - - - - - - -
label | f09dba1d-2fe9-536a-a711-ff3658fc27ec |  | note | Acceptance Criteria: Crews compliance with all Fulton Hogan Procedures and SWMS
label | 6b743e12-0e84-561d-b942-560b0870e66d |  | note | - - - - - - - - -
label | ca75efa2-6349-56a5-bda2-436a0a003599 |  | note | Reference Documents: Pipelines SMP, SWMS, Trenching Procedure
label | 1dec8705-8d33-503f-b95a-6a978f759ad2 |  | note | - - - - - - - - -
label | 96c90eee-9246-59cf-a084-861ddb4a44a0 |  | note | Inspection / Test Method: Visual
label | d3017f7c-9322-54bd-9113-cffa97e5913d |  | note | - - - - - - - - -
label | 9b7881c1-00d3-5edb-960a-bcac7e0cc7fb |  | note | Record of Conformity: Weekly Site Safety Inspection Checklist
label | 792e5409-fdfe-5d3c-9bcc-63291af6f702 |  | note | - - - - - - - - -
label | 50ca9850-a135-5b1c-a302-f77ecb1c1d63 |  | note | HP*
label | 57337675-0c1b-52e0-ad88-7403663c9b60 |  | note | - - - - - - - - -
label | 43718b8a-e5d0-594b-8f35-70e9ec18b6de |  | note | Responsibility: Project Manager/Engineer
checkpoint-status |  |  | checkpoint | 24 Monitoring of WC2 works
label | 0c0eb51e-4d06-59e7-9de3-c63c7b9687ea |  | note | Frequency: Twice per week
label | 44e58e00-d184-554f-a13e-e5e5e573fbfc |  | note | - - - - - - - - -
label | ff116ab4-3af2-5f7f-acf4-6a206d6e64bd |  | note | Acceptance Criteria: Crews compliance with all Fulton Hogan Procedures and SWMS
label | 76542155-0ccd-5819-a8a5-27ffde4887cf |  | note | - - - - - - - - -
label | e63a52cb-ad07-5c2d-8641-73d510c9c62c |  | note | Reference Documents: Pipelines SMP, SWMS, Trenching Procedure
label | 4a5dea1d-3af4-5ee4-9633-58fd0535f2b2 |  | note | - - - - - - - - -
label | 6aa9f761-0170-5b5e-bc50-42ecb7495e95 |  | note | Inspection / Test Method: Visual
label | b91e4acc-aa6f-5853-87c6-5d9c32846557 |  | note | - - - - - - - - -
label | e4ba16ce-2867-503d-bc67-2f84248eea54 |  | note | Record of Conformity: Weekly Site Safety Inspection Checklist
label | 89b7b112-832e-59b4-8d05-23101e6653d6 |  | note | - - - - - - - - -
label | 6fc38a85-18cd-5afd-a4fe-1a9c640f3931 |  | note | HP*
label | 7a870caf-7234-5829-a97f-3bd1062d2cf7 |  | note | - - - - - - - - -
label | 83ef9b4c-6d0a-5c6e-8f23-acf40773ff9b |  | note | Responsibility: Project Manager/Engineer
checkpoint-group |  |  | section | 9 - QUALITY
checkpoint-status |  |  | checkpoint | 25 Swabbing and flushing, Pressure test and Chlorination works
label | 50fc12d4-f93b-52e7-b064-13f112815e48 |  | note | Frequency: Completion of pipelaying
label | 1645676a-0385-53a1-9541-aeacec47e132 |  | note | - - - - - - - - -
label | 330b076e-d64f-5d83-ac0c-9e5241a6ec07 |  | note | Acceptance Criteria: Pressure testing held for 5hr duration
label | 56ef3403-868a-540e-9d21-20f8d9e567b6 |  | note | - - - - - - - - -
label | 2f04b31a-f5db-5c4f-8734-451a1c985c7b |  | note | Reference Documents: WSA 03-2011 - 18.3, 19.2
label | a7e2d268-ebab-5144-ba00-3f47e91c5e9b |  | note | - - - - - - - - -
label | fcbf02f9-0783-573d-bc3b-0eb474f3c308 |  | note | Inspection / Test Method: Visual
label | 7c9c05d5-e920-5494-aec4-32a239967c87 |  | note | - - - - - - - - -
label | 36d7bbe1-66d4-5b0a-b393-802f3cd8d058 |  | note | Record of Conformity: Compliance checklist - Pipeline construction
label | fc3e3a05-78c6-579d-bc76-3014b0ec3fb5 |  | note | - - - - - - - - -
label | cd13ef2f-0b49-5e5e-bf47-d7ba11119c2b |  | note | HP*
label | 0bc4cf87-897b-5b95-bfb9-3d11496fe7ea |  | note | - - - - - - - - -
label | 56dfdc81-c4dd-563b-85ac-de31cd75a52a |  | note | Responsibility: Site Manager
checkpoint-status |  |  | checkpoint | 26 Water quality testing.
label | c7ab7923-798c-5f92-a3f8-bc7655fd3e6c |  | note | Frequency: Completion of pipelaying
label | de7f2487-e26a-5d4d-9ad8-ae0179858d99 |  | note | - - - - - - - - -
label | 0c8a5109-a9f0-5432-a47e-24c4d81c90ef |  | note | Acceptance Criteria: Conduct a bacteriological test on all new mains following satisfactory completion of swabbing/flushing and pressure testing of the water main
label | be1771d1-b35c-5574-af07-6b9d5ec84549 |  | note | - - - - - - - - -
label | bbb98c22-1a54-594a-841d-d5e56971bdde |  | note | Reference Documents: WSA 03-2011 19.7
label | b306f973-0de6-5c45-96f5-11efc9365268 |  | note | - - - - - - - - -
label | a7f382a6-560c-5f94-ad55-8274f630bc2f |  | note | Inspection / Test Method: Written
label | 26835f58-082f-5538-baa9-f01ef205d395 |  | note | - - - - - - - - -
label | 57e40b90-c9f9-582e-b84f-3b45d890b238 |  | note | Record of Conformity: The test results fall within the water quality parameter
label | 721b7bea-ccb4-5853-b941-144094daabb6 |  | note | - - - - - - - - -
label | 35e793a9-894f-5be3-81b5-600207db1f72 |  | note | HP*
label | 749ad4c9-bbc7-5cb9-a79b-35bfac6b2b19 |  | note | - - - - - - - - -
label | e93b5a13-640f-500e-b184-d48862e87153 |  | note | Responsibility: Site Manager
checkpoint-status |  |  | checkpoint | Final Inspection
label | 5651da0c-d093-538e-8d77-82419fd71190 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 83f02a91-2643-5324-9f6f-797f62cf3bf8 |  | textbox | Print Name:
text | 189df685-5a01-5932-a925-e247422a973d |  | textbox | Position:
date | d4945c29-1185-5adb-b42e-7fc59faf471c |  | date | Date:
date | 3900769b-ee99-5690-b1e8-b3f115ceb127 |  | date | Work Completed On
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification.
select | 3a83023f-5eb4-587b-8626-3d8567aa5ad2 |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | 4ea08ede-f0a4-5c54-b698-fe0a3d4f2dfd |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | 7489da2c-7f23-5677-bcd0-e54558e93f7b |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | 838ed1b4-3829-5333-8272-629fa60b0dd2 |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | 99c56142-7d0c-5664-bf5f-1a811df1b29d |  | textbox | Other:
select | fba8f37a-fccf-5773-a57e-1b40fd3aff87 |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | fd08b9b1-a2aa-5e5e-8b3d-d4b4493ec716 |  | date | Lot Closed On
text | 2d3ce72b-2cb5-5dbd-88e4-9c795f0145d0 |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-076-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0076 - Permanent Roadside Signage | 253d61d1-9266-4ec9-b862-bf62bb853847
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | 0d2be2c0-f3b1-5e77-8cfe-66d2e27b3361 |  | date | Lot Created On
date | e36afdd7-06a4-5a51-8c54-1e7e674b3d26 |  | date | Lot Opened On
date | 2f7aa24e-e973-5499-9380-065c18124201 |  | date | Work Commenced On
select | cb2db19a-c975-5c62-a215-c685e454bd54 |  | dropdown | Lot Type | CIL-Civil Lot
text | efe0ab13-06b9-5b3d-ae5d-4e5abdd8401c |  | textbox | From and To Chainage
select | 7ce93dc1-caab-53e7-96ae-0fdc1a714f90 |  | dropdown | Construction Element | SIGN - Sign and Pavement Marking
select | a8b077f4-9577-5357-88d9-0b5e8d24e52e |  | dropdown | Activity | SIGN - Sign
select | 453cb408-ae9a-58e0-bc61-dedc49d0cf3d |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | a57ad9e1-e6f6-5730-826c-d217c34abaa4 |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | ae13a636-5a23-5472-8c74-60c1e7de33d2 |  | textbox | Engineer Responsible
text | e8ccee81-9e8b-5a3f-a7df-06226f9f9a18 |  | textbox | comments
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Inductions
label | fd3bd6cd-ddb3-515b-bec0-d4f5d4c15816 |  | note | Frequency - Prior to Commencing
label | 33a6771d-01b8-5892-acad-e7d20ae3d3e8 |  | note | - - - - - - - - -
label | 25387492-1af3-590c-b9e8-c6a5a68e9efa |  | note | Acceptance Criteria - All personnel on site have been inducted to the CRG Site.
label | 0755ad78-504f-5cb1-8f46-8bf443f2587a |  | note | - - - - - - - - -
label | c7251ebb-fa0b-5fe9-9f0a-37cfd1c4afd3 |  | note | Reference Documents - PMP Inductions Register
label | 1b5035f0-41bf-5204-a647-c3e3522997aa |  | note | - - - - - - - - -
label | a121a975-c592-539b-b761-733573480b71 |  | note | Inspection / Test Method - Document review
label | f46cc005-02b5-5861-bfef-13a81d185669 |  | note | - - - - - - - - -
label | a310fa92-a89d-56bc-89cf-5aeac107ab92 |  | note | Record of conformity - Site induction card
label | f9f36731-6d16-5700-a05b-1f060c416335 |  | note | - - - - - - - - -
label | d5ff2444-4b2e-5b85-8c5c-78613e0a6c84 |  | note | AP
label | 101ec159-04fd-59f3-80ab-368f83866020 |  | note | - - - - - - - - -
label | 3b68b68d-d883-55e2-86e8-67f11075e65d |  | note | Site Engineer / Site Foreman
label | 9faee4f6-a7f3-5d14-8f87-63836f26cc98 |  | note | - - - - - - - - -
date | d9375499-56fa-50c3-8347-d0e32973be03 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Safety measures are in place, SWMS undertaken
label | 7ab8037c-110b-5097-b1b9-a64e95c16d80 |  | note | Frequency - Prior to Commencing Work
label | 0e6ed498-cd7e-5995-b3cd-d23d004e23ef |  | note | - - - - - - - - -
label | 236189b9-8987-5c12-9131-71d266da43b5 |  | note | Acceptance Criteria - As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
label | 82608e6a-c12b-52a5-8cf8-bdc87da9c0bf |  | note | - - - - - - - - -
label | 2c18e56c-a8e1-5ec3-84a1-eaa015a1178d |  | note | Reference Documents - Health and Safety Coordination Plan
label | 747214d8-6010-50c5-bc92-04cb0709d20f |  | note | - - - - - - - - -
label | cbb7def5-5a64-5e1a-96e4-6350983dc3c1 |  | note | Inspection / Test Method - Document Review
label | c1a53a65-adae-52e8-a469-30db41e3d3ec |  | note | - - - - - - - - -
label | 5feee1cb-4dd5-51c1-b315-de918e3becfa |  | note | Record of conformity - SWMS(s) signed
label | 7601331f-bf31-58e7-bf6e-cd3b3f966f22 |  | note | - - - - - - - - -
label | f76f8c39-e884-54ca-96a1-e52e387cb6de |  | note | HP*
label | 088283d9-505e-512e-bcd6-51f95dfd517b |  | note | - - - - - - - - -
label | cf0b3dbe-ed32-5a48-892a-99e5b6c585a6 |  | note | Site Engineer, Site Foreman & Superintendent
label | 0f5c873c-3af6-510f-bd56-105a398237cc |  | note | - - - - - - - - -
date | e0928a07-6ab6-5c4e-8c38-3b58e5f4f77d |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Check that current revision drawings are being used
label | 70ed377a-c63c-58fa-bc87-ae20d435542b |  | note | Frequency - Prior to Commencing Work
label | 6c732abe-4ab2-5cb3-80d0-7b49dd42316a |  | note | - - - - - - - - -
label | b141d1f7-9707-5b16-8d28-0a6a21f65890 |  | note | Acceptance Criteria - Issued For Construction (IFC) and latest available revision used
label | 315d0f40-543a-5cf9-91cc-8f09e16fe18f |  | note | - - - - - - - - -
label | 3364ce47-7b69-5ede-a632-ffd6a002a1c4 |  | note | Reference Documents - IFC Project Drawings/ Drawing Register
label | 686519b4-8be1-554c-aae7-4cb57316f137 |  | note | - - - - - - - - -
label | b53f026c-e703-5c14-8ecf-9c88878ebb92 |  | note | Inspection / Test Method - Document review
label | 04de7547-72b0-5c94-b20b-5c9f72fecb07 |  | note | - - - - - - - - -
label | 52beca64-c537-5385-b516-e514b90d24e9 |  | note | Record of conformity - Latest revision IFC drawings
label | 85113cd6-6871-55c9-bb96-116db50ceb1d |  | note | - - - - - - - - -
label | dd605d45-d3e9-554a-b317-8e2d91efa880 |  | note | AP
label | 986065fc-bffb-54c2-90a1-2d6dae49c6f5 |  | note | - - - - - - - - -
label | c6e078a8-2b8e-54cb-9c8a-502b636edb97 |  | note | Site Engineer / Site Foreman
label | e423e8f2-0be8-5955-a9ce-fa6fcbc32941 |  | note | - - - - - - - - -
date | 78d570bb-79cc-5bec-b9c5-53cfdfcfff75 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
label | 02e1768d-54da-5c57-bf94-7480d96df075 |  | note | Frequency - Prior to Commencing
label | e300cdb6-ac48-5514-90ac-4128d72eb06d |  | note | - - - - - - - - -
label | e765a2ba-c51f-563f-b160-17885870b500 |  | note | Acceptance Criteria - All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | 3c167be1-205f-5d1d-8cb7-d5885c68904b |  | note | - - - - - - - - -
label | 39698ef7-71bd-5cf6-b3c5-a871b0a931c9 |  | note | Reference Documents - EMP, Site induction, Project Spec. Cl.1200.09 Project Spec CI.1200.15
label | ae2743a6-0ed8-5221-a000-b09dbb089c42 |  | note | - - - - - - - - -
label | fbd97d3c-5850-53c5-96fc-7fed0ed8e101 |  | note | Inspection / Test Method - Document review & Site inspection
label | c12436de-4603-5424-bfa8-67e946f01f43 |  | note | - - - - - - - - -
label | 5b9aed9e-7029-5f98-81b8-3ca511706558 |  | note | Record of conformity - ITP signed
label | a6c7c30a-62b6-5de8-8a31-289f63772c39 |  | note | - - - - - - - - -
label | e4be5872-2ce4-539d-abfb-b599d8dbfc6a |  | note | IP
label | 0d3ea1cf-f536-5411-b958-b6b5e3fd8878 |  | note | - - - - - - - - -
label | e3e58a62-e0b7-590e-b509-c650dee98956 |  | note | Site Engineer
label | c8a43607-56c1-5e04-81fb-6ffa688e1d89 |  | note | - - - - - - - - -
date | c9dfc517-9889-505f-a5f3-c66c12538476 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 - Traffic Management (When required)
label | 04186f91-95dd-567f-8470-5312de0b183d |  | note | Frequency - Prior to Commencing Work
label | 8c2174ab-e8cd-5cc6-8b4a-e52880bee9c2 |  | note | - - - - - - - - -
label | 26594091-74c4-5591-bc9d-558f38ed4793 |  | note | Acceptance Criteria - Approved TMP and MOA
label | c9287d8b-973d-5836-b50e-acf580b15536 |  | note | - - - - - - - - -
label | 9d1f533d-376e-5332-86ae-3ae1c4b29a5a |  | note | Reference Documents - Applicable TMP no.:
label | 6213b619-02d9-5f02-a29a-99509381953f |  | note | - - - - - - - - -
label | 2303bb9c-4fde-5bee-aa27-80102de1327d |  | note | Inspection / Test Method - Document review & Site inspection
label | 847d0199-db3d-5534-949c-352efb06bcfc |  | note | - - - - - - - - -
label | 14149bcb-1e95-5e40-a778-d49b0492530d |  | note | Record of conformity - Approved TMP & MOA
label | dde3ff9a-1158-5656-a5c8-a35d33bd285f |  | note | - - - - - - - - -
label | fd6a9ab3-f0b5-5187-bfd4-4e4a9ddd14fb |  | note | AP
label | 4672d7ec-c228-5db7-904b-23b8bded1a0a |  | note | - - - - - - - - -
label | b525e9af-dbee-5765-b879-d3af67b7198a |  | note | Site Engineer
label | 9afa4d53-bbca-5a83-b792-ee30a5a1b76e |  | note | - - - - - - - - -
date | 99c7ed2d-77f2-5080-8499-5b468ebac912 |  | date | Date Completed:
checkpoint-group |  |  | section | 2 - Roadside Signage Install
checkpoint-status |  |  | checkpoint | 2.1 - Set out posts and foundations
label | 7171f8f0-a9a0-59bc-8be2-55d4f992c133 |  | note | Frequency - Prior to commencing install
label | 436f0f23-d335-5e61-86a4-12371cb08984 |  | note | - - - - - - - - -
label | fb7c6cd2-3788-52c7-a554-83b19c4e8349 |  | note | Acceptance Criteria - The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences.
label | e16e0840-accd-55f9-bd16-9c9941683238 |  | note | - - - - - - - - -
label | 7bb1d7eb-5ad4-5764-926d-7b6f416191e9 |  | note | Reference Documents - IFC Drawings Project Spec. Cl. 3070.03 VicRoads Spec. Cl.714.06
label | 77c4b65c-e9cb-55e8-a812-d4cdfbbfe4d7 |  | note | - - - - - - - - -
label | 56053fed-fb42-5524-938f-9b702651d9b2 |  | note | Inspection / Test Method - Document review & Site inspection
label | 73856ee6-9de8-5b26-b8e2-ef72cdadc6c2 |  | note | - - - - - - - - -
label | bad50702-b144-5ba0-bdee-dca15ef8319d |  | note | Record of conformity - Consent to proceed by Superintendent OR written exemption granted This ITP signed
label | 12227c2c-8462-57e7-bbb3-21675527b9b5 |  | note | - - - - - - - - -
label | b5b3648a-7a8b-5f6e-bb05-3cf808d4cfd9 |  | note | HP
label | 0aedee08-c2c7-5798-bb96-6285aee5d7f9 |  | note | - - - - - - - - -
label | 7e4add21-6f40-5fc3-8869-4ce027c06942 |  | note | Site Engineer / Superintendent
label | 81b65fb7-ebb1-5c93-acf7-aa66224811ea |  | note | - - - - - - - - -
date | 5aaf2f38-8fe5-5bd3-9fd7-9f32e2ff08da |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Material compliance
label | 57068490-d65b-54d7-8449-8aea7a970933 |  | note | Frequency - Prior to commencing install
label | 1a5db3b9-7fbd-557b-81fd-dab793d28da4 |  | note | - - - - - - - - -
label | 2aec6121-3ac7-56d9-b49c-ae8c3cc9070e |  | note | Acceptance Criteria - All road Signing must comply with the Technical References including the requirements of section 860 of the VicRoads Standard Specification Sections for Roadworks and Bridgeworks.
label | beb550e0-fa75-59bb-a20b-57cc739a74ab |  | note | - - - - - - - - -
label | f73bb742-3f00-5a5d-9215-61e0b5a9f2ec |  | note | Reference Documents - Project Spec. 3070.05(a) VicRoads Specification 860
label | 6dea6534-64ca-59e9-9ae6-7de5a51b7ae2 |  | note | - - - - - - - - -
label | 22fa8e77-19da-5acc-9caa-00bb12dc3ae8 |  | note | Inspection / Test Method - Document review
label | f3637dd2-3753-5fdc-86a8-e9cd088b2626 |  | note | - - - - - - - - -
label | 5464f77e-b6d4-5fb7-a32a-d5ba125465a6 |  | note | Record of conformity - Material compliance This ITP signed
label | 34576c2b-714d-5fd8-960b-f1e9f240f122 |  | note | - - - - - - - - -
label | d47c8ae7-1381-5767-8eff-0096e4918312 |  | note | IP
label | 972f5167-313f-5aa3-9d8e-d0c0f69622f5 |  | note | - - - - - - - - -
label | a8b9f06d-95f7-51d0-aa03-5a19e53df799 |  | note | Site Engineer
label | d330a0cd-2874-524b-a513-567cdc695ae2 |  | note | - - - - - - - - -
date | 4a69d2c6-15c6-5687-bf60-b1823ed74ed1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Installation method
label | 8783a1c9-43af-5951-8ecd-4617189ee6cb |  | note | Frequency - Once per lot
label | 261744b9-a23b-51a3-856b-ea2ea4eb9bce |  | note | - - - - - - - - -
label | cb715ec6-9971-52db-8435-2a7872843ef5 |  | note | Acceptance Criteria - The sign installation shall be as described in the sign schedule and as shown on the contract drawings.
label | b20e0c91-b80c-5232-b592-1421eabfca69 |  | note | - - - - - - - - -
label | 17eb7580-0656-58b2-8055-30e91cd77cf2 |  | note | Reference Documents - Project Spec. Cl.3070 VicRoads Specification 714.04 & 07
label | 6cfe6177-38d3-5313-ac4f-dd67e894624f |  | note | - - - - - - - - -
label | 6f348313-11fd-5be9-ae23-bfcd8fef9f4b |  | note | Inspection / Test Method - Document review & Site inspection
label | 1c6878ef-5192-5ea7-8688-337c4477c624 |  | note | - - - - - - - - -
label | 9a75b73b-5e60-579b-911c-b7b5fcd4e6fb |  | note | Record of conformity - This ITP signed
label | 595546c1-67b5-5852-86b8-b2ba7aa92320 |  | note | - - - - - - - - -
label | eb9599bf-4713-5303-a520-9c112b6e10a1 |  | note | IP
label | 50ffe66d-512e-5831-b30b-723bf3d5bb8d |  | note | - - - - - - - - -
label | c21f1bf8-fc96-588c-900c-6b4243cddda7 |  | note | Site Engineer
label | 03728cc0-6705-5ae3-be01-0b69ad4a7712 |  | note | - - - - - - - - -
date | 587a8cbc-1d3b-59e3-9ad7-8586425bf18c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Installation tolerances
label | 281736e6-f506-594b-bf54-10f79653b063 |  | note | Frequency - After completion of works
label | 05f8befa-45f0-52ad-becc-d1546180b6da |  | note | - - - - - - - - -
label | b503e5bb-8d98-546c-af8a-214917f8c788 |  | note | Acceptance Criteria - Verify signs were installed to tolerances stated in VicRoads Sec. 714.05
label | 3fb69f34-79e6-558c-b738-2fd91c42ea9d |  | note | - - - - - - - - -
label | 4a52bc40-ca04-522d-bf5b-8f4df6b8862e |  | note | Reference Documents - Project Spec. Cl.3070 VicRoads Specification 714.05
label | 08b0806e-8078-5588-b5ae-af4a69df7f25 |  | note | - - - - - - - - -
label | 57d3e3bf-3787-59c3-b87a-d25a2cd745a1 |  | note | Inspection / Test Method - Document review
label | ea87d552-7591-5739-9729-295897bc79b9 |  | note | - - - - - - - - -
label | a9216f9d-1199-59b9-93b8-797f99f7c258 |  | note | Record of conformity - Photos This ITP signed
label | 7de5fe46-9174-51b0-9dad-1e51eff482fc |  | note | - - - - - - - - -
label | 25021fbd-48ef-5407-83d9-7a88cfecbbdb |  | note | IP
label | 4edc60a0-180b-51c7-957a-8f3646394401 |  | note | - - - - - - - - -
label | 79597b29-c960-576f-8b5a-f859eec86208 |  | note | Site Engineer
label | d137eccd-daac-5258-9bd6-5df0dafbb19a |  | note | - - - - - - - - -
date | 41fabadc-6cc9-5080-b281-c0926d3fe3e7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 92a9dd54-76c4-5183-89ba-524c182a6789 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 662b2268-26c1-51b1-a031-42477336f130 |  | textbox | Print Name:
text | a1e901ef-6eae-597c-9eb4-0c42b2dd163a |  | textbox | Position:
date | 2b01d31c-abd0-5743-a1df-de2cfb712840 |  | date | Date:
date | 5d232172-bf32-5305-b3b5-3dde0f132ee6 |  | date | Work Completed On
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification.
select | d5027576-8fc7-5435-99e4-b841c959f8b6 |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | ff363d5c-4cb3-5f98-a7f7-206d6e23e646 |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | b9637bf4-893d-5936-ac7a-93007a6873b7 |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | e2b135ac-6c95-5970-8388-737410c5a310 |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | 5756ac4d-1939-5479-962f-bc25cc4ab592 |  | textbox | Other:
select | 52791bd0-f871-5088-857a-8d9be3907124 |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | c13caf39-bf77-5254-8788-7f149e01d724 |  | date | Lot Closed On
text | e719b8ee-525d-5bb8-a3e9-f3f0fac5c3b7 |  | textbox | comments
checklist-sectioned |  |  | checklist | Defect ID No: |  |  |  |  | Yes | Defecting Checklist | 271f5cf6-09fe-4d3f-8641-76d7bafc939a
checkpoint-group |  |  | section | Defect
checkpoint-status |  |  | checkpoint | Defect Identification
date | 8701a653-7e68-5322-ba34-8a5f05976416 |  | date | Identified on (date):
text | ad0e584e-2967-515c-bb00-a32501bc38da |  | textbox | Identified by:
text | 2a79d577-24ae-5a78-8819-dc3b936e69e4 |  | textbox | Process:
text | 41d2bc45-4ace-52e7-a408-de753f71d800 |  | textbox | Area:
text | 7ef5a324-a4da-5bf2-988b-bce11d762973 |  | textbox | Location:
text | f803d49d-f1e2-59c1-ac35-c6fbb3dc0972 |  | textbox | Client Reference (if any):
text | ef28bbc8-add5-59ad-8e0f-420dac7424db |  | textbox | CAMS NO. (if applicable):
text | b6901938-66b6-53fa-aeaf-27ed24228be0 |  | textbox | Description
boolean | 19517bc0-3d2a-50df-b1cc-61f59a027757 |  | tickbox | Photo Attached
checkpoint-status |  |  | checkpoint | Defect Rectification
date | 20db7d32-e57f-533e-891f-7e15943d5b49 |  | date | Completion Date:
checkpoint-status |  |  | checkpoint | Defect rectification accepted and closed (signed off by FH & Client)
date | ebedc7aa-7f4b-5a8f-83e7-a75c26ee5b8f |  | date | Date Completed:
text | a8067a07-371a-564c-b8d1-c43fbd81b0c9 |  | textbox | Fulton Hogan Representative
text | f2af2fa7-dd05-5062-b6d4-3083dff06751 |  | textbox | Client Representative
date | 4c47cb50-8bb9-5595-bdc0-1eb15f5e6501 |  | date | Date Signed off
holdpoint |  |  | signoff | Request Approval
checklist-sectioned |  |  | checklist | ITP-049-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0049 - TOPSOIL PLACEMENT AND LANDSCAPING | 2a942257-01a4-4006-96cc-0e3796632cb4
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | 71f4e832-399d-509b-89ed-ecfbb315e574 |  | date | Lot Created On
date | 990f32a5-b546-5dc2-bbe0-1c460e0abf1e |  | date | Lot Opened On
date | 2d1ae77c-00bb-5d10-809c-cafaa6cd04cd |  | date | Work Commenced On
select | 0add3e7b-46c3-5573-94c6-1e643401abd2 |  | dropdown | Lot Type | CIL - Civil
text | 7896ed92-bedf-53ed-8fce-feecad68819a |  | textbox | From and To Chainage
select | 99531f1b-9045-5d35-ad17-8bbde81f73ed |  | dropdown | Construction Element | LAND - Landscaping
select | b7756007-168a-571a-ada2-d8a3b828d103 |  | dropdown | Activity | CULT - Cultivation, HARD - Hardscaping, HYDR - Hydroseeding, MAIN - Maintenance, PLAN - Planting, RIPP - Ripping, TOPS - Topsoil, WEED - Weed/Grass Management, WSRD - WSRD
select | b0d5dfc2-58e6-5659-ab53-2850fc591534 |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | 76a66045-bd28-5c22-a156-398f2866b2a8 |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | 10ae6534-b4b0-55dc-8955-1a13e7cbecdf |  | textbox | Engineer Responsible
text | fe60d125-6bfa-5105-8637-30736df08a9d |  | textbox | comments
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Check that current revision drawings are being used
label | 6b145ed4-9019-5978-9d42-96e31f85ceac |  | note | Frequency - Prior to Commencing Work
label | 53c0919e-faf3-5901-8e6d-fd25ba28e2b7 |  | note | - - - - - - - - -
label | 65c47f61-1759-5f68-8028-8fbca2f7ef15 |  | note | Acceptance Criteria - Refer to latest drawings and latest available revision used
label | 98a44c38-045c-56d9-b1d9-7211db3224a1 |  | note | - - - - - - - - -
label | 72325eb9-abcd-55bc-b863-9f95234c8082 |  | note | Reference Documents - IFC Project Drawings / Drawing Register
label | 26edd15b-4b1c-57f7-8533-ae2af80ad6d5 |  | note | - - - - - - - - -
label | 89b0a92c-39b3-56d9-98de-e920c5004ad1 |  | note | Inspection / Test Method - Document Review
label | 4b7806dc-22fb-59e3-a660-6b6b853ba58a |  | note | - - - - - - - - -
label | 956855d3-9e0d-568c-90d1-ceb2a2d5bdec |  | note | Record of conformity - Latest Revision Drawings
label | a8433bff-9fd6-5a1a-a340-ca9c922a8952 |  | note | - - - - - - - - -
label | e08e1cd0-04e5-5646-b049-6a36dab3700e |  | note | IP
label | fbe8d406-6a57-5b51-9e6d-6f3f15aca255 |  | note | - - - - - - - - -
label | 6d2dfb88-1718-54f8-9b0e-0a8301a19dc9 |  | note | Responsibility - Site Engineer / Site Foreman
label | 89166a8e-4b4e-560f-8b05-11785c79259e |  | note | - - - - - - - - -
date | a7d9f653-bc00-592f-ba4e-d3f8553f8e1e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Submissions and records
label | aa08b65d-e370-5c68-89c0-dd772bcf9ee7 |  | note | Frequency - Prior to commencing works
label | e40e17a5-5793-561d-a28b-9e86d5cc5a8a |  | note | - - - - - - - - -
label | 28173e3b-a8e2-5ee5-8c51-8aa7bc6cc474 |  | note | Acceptance Criteria - Samples, records and certificates shall be provided to the Superintendent at least 10 working days prior to bulk delivery.
label | 63274200-6ef1-5524-ad00-ffa10e52219b |  | note | Following information shall be provided to the superintendent:
label | 1937dac9-f3cb-51ce-a2d6-b8b40be61218 |  | note | Inspections:
label | 822a0fd0-833b-55e3-9019-cd3499eb0395 |  | note | • Plant stock for all plant species
label | 4f7ff59e-df01-5c91-a212-303a6cc8d760 |  | note | Samples:
label | c62c81c8-0ec9-5b5f-9ab4-67d717a46d3f |  | note | • Mulch
label | e7423df6-36af-564f-a985-f4985b7a1c81 |  | note | • Imported topsoil
label | 52414ff9-1e2b-59a6-a863-5f21e8e84b75 |  | note | Records:
label | d164b02c-61b2-5636-8bab-4bbefd8b18a2 |  | note | • Evidence of origin of indigenous provenance plant material
label | 3ac76571-3ca8-5c5d-acdb-3bbd2914d223 |  | note | • Analysis certificates for grass seed
label | 459a6985-066b-56c8-830e-5cf4f8d37aed |  | note | • Details of suppliers
label | e13fded2-2340-5668-9c9d-646225b2bdaa |  | note | • Soil tests on imported topsoil
label | 22a8b357-e318-5efd-8e92-1f1f93bf37e7 |  | note | • Copies of fertiliser labels
text | 8a606d24-7e20-51b9-99dd-98bd259cbddd |  | textbox | Enter Teambinder Approval #:
label | fa6c6089-eed4-5ca1-b1ac-f40ebde11767 |  | note | - - - - - - - - -
label | af3b834c-08b2-543a-a4ad-b0deb6be58ff |  | note | Reference Documents - VicRoads Standard Section 720.03
label | b023bb91-b044-5e25-89a4-e884dd1c825c |  | note | - - - - - - - - -
label | cbea8032-8a78-5eaf-ad7d-a78316f2e17c |  | note | Inspection / Test Method - Document Review
label | 43b3788a-b0af-5168-9609-08f884ad7a5d |  | note | - - - - - - - - -
label | d3639994-1bfd-59d9-9d68-fafa90bd79d0 |  | note | Record of conformity - Records & Certificates uploaded to teambinder
label | 0feda0b9-2a9c-5fe8-86c0-2bca05f1bba9 |  | note | - - - - - - - - -
label | 04689d80-c9fc-5236-9aeb-5fcc425b8f97 |  | note | AP
label | 1ebcc416-2ddb-5141-8c99-d659da0622ac |  | note | - - - - - - - - -
label | 9632bdd7-4ad1-54e8-92d1-e5f22d0beb0f |  | note | Responsibility - Site Engineer / VicRoads Superintendent
label | b72a3c28-deed-52d0-bbd9-3a357e15628b |  | note | - - - - - - - - -
date | 5da67de3-5caa-50b5-8318-396ba281a669 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Supply of mulch
label | 419c12fd-969c-5e8a-b11d-688b70ae526a |  | note | Frequency - Prior to commencing works
label | 90e73abd-781c-5057-80af-28aac319085f |  | note | - - - - - - - - -
label | 2e6c347f-fa8b-5bd0-8429-80a61163d1e1 |  | note | Acceptance Criteria - Site mulch available from the chipping of on-site indigenous or non-weed vegetation shall be used where possible.
label | b5c6a740-bd78-52bd-852b-fd177d63569e |  | note | All wood mulch shall be supplied, delivered, handled and applied in accordance with AS 4454, and shall comply with Table 720.044
label | 0b60b3c7-c877-5b52-9b99-051568579548 |  | note | - - - - - - - - -
label | 2a21274d-69bb-56cc-80a3-9318ab8e7b03 |  | note | Reference Documents - VicRoads Standard Section 720.04
label | b080d980-3358-5086-95ed-7a18fdc6c9e4 |  | note | VicRoads Standard Table 720.044
label | c8da597a-31e1-5f7a-a964-018c24044ea3 |  | note | AS4454
label | e7c9a324-4772-544c-9c13-56d3ddee6153 |  | note | - - - - - - - - -
label | f8f1a862-4f32-5f26-aa1e-96f62f40e5e9 |  | note | Inspection / Test Method - Verify
label | 19c83178-5478-513e-a234-915798f08936 |  | note | - - - - - - - - -
label | a616fd65-5b3a-58f5-9b88-49d3cd0a4226 |  | note | Record of conformity - This ITP signed off
label | d25f1196-08c0-5b12-a085-44609c59a10e |  | note | - - - - - - - - -
label | 09ee2889-189a-5f7e-be5a-f7488f7fd758 |  | note | IP
label | 5fc68c3d-18c8-5e17-917d-661e5bb033fb |  | note | - - - - - - - - -
label | 73adf851-f2e4-5436-abc0-9fc9bd25fdb7 |  | note | Responsibility - Site Engineer
label | c298dbc6-44b9-5c5c-b729-5f8cd123eeaa |  | note | - - - - - - - - -
date | 28de5e49-f848-5fc4-86ee-0eee9f752d6b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 - Supply of topsoil
label | efd86f98-8603-5d38-ac62-0445bee5d9d6 |  | note | Frequency - Prior to commencing works
label | 6af886db-9fa7-540d-88fb-0bce4df019a1 |  | note | - - - - - - - - -
label | aee2436b-7404-52bc-a1cb-c4edbbafdf14 |  | note | Acceptance Criteria - Site topsoil shall be used wherever possible, in preference to imported topsoil.
label | a38f97ba-777a-5d29-8aa8-17479bc348ba |  | note | Where imported topsoil is used, the topsoil must conform to the properties specified in Table 720.042
label | 4c01420e-5dec-5d09-8839-b44e6b7e38c0 |  | note | - - - - - - - - -
label | 0a037ae8-a1da-5091-901e-4b77b0294a6d |  | note | Reference Documents - VicRoads Standard Section 720.04
label | d3eeba41-3aa0-5b11-9d80-7c800b7360af |  | note | VicRoads Standard Table 720.042
label | a1892069-5eca-5612-832b-85f359cd5e31 |  | note | - - - - - - - - -
label | fbf35eb4-8d85-5b92-a630-aecf79a95645 |  | note | Inspection / Test Method - Verify
label | cdd70ac9-4430-5fab-9d91-a0f4b422c297 |  | note | - - - - - - - - -
label | 31aeef9d-5cf9-55d7-ac3e-284b701ba7d7 |  | note | Record of conformity - This ITP signed off
label | d05da224-35f5-513c-991b-c7cded0f0672 |  | note | - - - - - - - - -
label | 26f11bc8-9221-5f08-a399-eacd12a76fa6 |  | note | IP
label | 7f75751c-7b81-52a1-aa82-5a497722e24d |  | note | - - - - - - - - -
label | b41f8637-8fdc-54f9-a399-5b3577c64a35 |  | note | Responsibility - Site Engineer
label | 050b8680-31c5-5c74-b063-158db3536e29 |  | note | - - - - - - - - -
date | d5e16e12-6cee-5f9d-9281-ef61865cb808 |  | date | Date Completed:
checkpoint-group |  |  | section | 2 - Construction Works
checkpoint-status |  |  | checkpoint | 2.1 - Setting out planting areas
label | 568ea008-340e-58db-86fe-c79d06e50d33 |  | note | Frequency - Each applicable lot
label | 33f0eaf4-9b7a-56f1-8940-e074a87a8d17 |  | note | - - - - - - - - -
label | 6963543c-5f5b-50b6-9620-7162d97ea5a9 |  | note | Acceptance Criteria - Planting areas are to be set out to the location and shape specified in the landscape drawings.
label | 03ab80de-2727-537a-92d4-37f4a8e449ca |  | note | Plant density requirements and planting offsets established in the plant schedule are to be adhered to.
label | dd048e3c-5394-517b-9dc4-b3938574765e |  | note | Plants shall be placed as shown on the drawings.
label | 6263c6a8-3c0f-594a-a4e2-f833a53934e8 |  | note | - - - - - - - - -
label | 35242c58-c61f-5cbe-be9a-f366463247ad |  | note | Reference Documents - VicRoads Standard Section 720.06
label | f92dc157-d0da-57fa-ae3f-469159d7eb12 |  | note | - - - - - - - - -
label | f91574c9-c3a1-5946-b314-97b13e99d37a |  | note | Inspection / Test Method - Verify
label | f511cd94-e6fa-540f-8cf0-2796c91c85be |  | note | - - - - - - - - -
label | 8846a9c7-2588-5e80-a604-9424693b351d |  | note | Record of conformity - This ITP signed off
label | 94b54c7a-9011-5b47-9362-926a167ae764 |  | note | - - - - - - - - -
label | 87d102a4-c57e-54f5-8c1e-0dc6e0ba1c00 |  | note | IP
label | 9550fa5d-4f81-5412-9aae-c0abc1e3504e |  | note | - - - - - - - - -
label | 68b1326c-b26f-5847-9d96-92297c723f31 |  | note | Responsibility - Site Engineer
label | 69739001-12c4-55f5-901f-248fd6272675 |  | note | - - - - - - - - -
date | 1e3a026b-05e3-56d1-8c55-7a71ee5db9df |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Site Preparation
label | 30a54162-5b5f-595d-8871-dc233feb4e4d |  | note | Frequency - Each applicable lot
label | 4bd84563-a154-51bb-9fc1-f41f8578589f |  | note | - - - - - - - - -
label | 9ab2a3a1-31c6-5128-b060-424bae51347e |  | note | Acceptance Criteria - Soil preparation shall be in accordance with Table 720.071
label | 89fb0237-cabf-591b-9c69-e23f9a9e020a |  | note | - - - - - - - - -
label | d384d9fe-12ff-5632-ae64-5ff0cfec53da |  | note | Reference Documents - VicRoads Standard Section 720.07
label | 6d7f1f49-b4ae-5d5f-a6e6-c75a5d8dad58 |  | note | VicRoads Standard Table 720.071
label | adbfce9a-80c3-5e0a-aa7d-bbb8aa8fc9f4 |  | note | - - - - - - - - -
label | 9c547fda-6758-58d7-9814-94606012b111 |  | note | Inspection / Test Method - Verify
label | 2c47bdbf-867c-591f-9d31-00dbd126928d |  | note | - - - - - - - - -
label | 8707a4f4-1a1a-5457-96db-1058e5fba7d5 |  | note | Record of conformity - This ITP signed off
label | 38eb58fc-2ea5-5e28-a5aa-2fd469a23659 |  | note | - - - - - - - - -
label | 3b4b308a-f201-5629-9c32-f7d6ddc8b32e |  | note | IP
label | af1e5193-f1a8-5521-913d-7d8b1bd0de62 |  | note | - - - - - - - - -
label | 7ffc1907-ed16-5071-b60d-c81d4cb4d0e7 |  | note | Responsibility - Site Engineer
label | d2c4f932-2507-5449-90c0-c60f7c0eabf1 |  | note | - - - - - - - - -
date | 238ea748-789e-5937-ac16-79241824986b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Ripping of subsoil
label | 03a8e753-7e3f-5c6d-a3ae-ff015854f5e9 |  | note | Frequency - Each applicable lot
label | e958a858-0a3f-59e8-97ca-df4158fc1eaa |  | note | - - - - - - - - -
label | 384cc5da-4f22-5d49-9561-fda40bc5e878 |  | note | Acceptance Criteria - All ripping works shall conform to the requirements of Cl 720.07 (b).
label | 9c27d07e-73e3-5300-938d-479429d2a881 |  | note | Ripped areas of planting, individual tree planting and grassing are to be made available for inspection prior to mulching, planting or grassing, and shall not proceed until the Superintendent acknowledges requirements for ripping have been met.
label | 0f55123d-8256-5e90-bfbb-9af145e86cb3 |  | note | - - - - - - - - -
label | 065224e7-1cde-54a4-9e77-705bed36c060 |  | note | Reference Documents - VicRoads Standard Section 720.07(b)
label | 334ac4cc-b5ee-5d2b-984e-31d6cc546a90 |  | note | - - - - - - - - -
label | 4481ee75-fa43-5372-903f-1366b17d60fd |  | note | Inspection / Test Method - Verify
label | 260ac9ed-507f-5608-8a8b-465f4db23f96 |  | note | - - - - - - - - -
label | 440c400c-d70f-5183-a382-926c42a3f908 |  | note | Record of conformity - This ITP signed off
label | f884d9d5-99af-5f5a-b42a-396d99b5f546 |  | note | - - - - - - - - -
label | 5e4b47ac-adec-56d5-bdc0-52b2c1958ffa |  | note | HP
label | 597c3324-dc34-52b8-b2d4-3d004172ff3c |  | note | - - - - - - - - -
label | 3475835d-c4a0-58b3-944d-6f3086b27957 |  | note | Responsibility - Site Engineer / VicRoads Superintendent
label | cccfcdb3-0d1b-57a6-9575-cdb385d471cf |  | note | - - - - - - - - -
date | 0bd5c28c-f289-5c33-98a5-c91b790bfbe5 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Topsoil Placement
label | 82441c42-b977-5bdc-824a-17ec61e5209c |  | note | Frequency - At completion of works
label | 5d6cff71-372b-5e4d-add9-c8eb46747f5f |  | note | - - - - - - - - -
label | ba99bcd5-41e5-5331-b357-48dbca395e3a |  | note | Acceptance Criteria - All disturbed and/or not paved areas shall be topsoiled according to Section 204 of VicRoads Standard for Roadworks and Bridge works, to the following minimum depths:
label | 9dcdfff2-87fc-50f7-9e30-e02e114677ef |  | note | • Batter slopes > 2:1 = 50mm
label | bc600e57-ea2d-5895-8105-906c0c3cd612 |  | note | • Tree and shrub plantation bed areas = 100mm
label | 7fc80a78-426d-5c91-9f14-37f4d769f571 |  | note | • Verge, 50mm outer edge / 20mm when within 100mm of the edge of seal or asphalt surface treatment
label | 4fe27ab0-f43a-5f0c-9f06-f75877d93a77 |  | note | • All other areas - 75mm
label | d66f9bc0-d4f2-5208-9b87-bb040dd26519 |  | note | Following subsoil preparation, topsoil shall be spread on planting areas and grassed areas. Topsoil shall not be compacted.
label | c31426c9-2f33-5031-8b26-c20e12c49e8a |  | note | - - - - - - - - -
label | e6e68106-e75a-5399-9dc2-afe3930696c0 |  | note | Reference Documents - Project Spec. Cl.3020.07(k)
label | 4535d08e-53d4-5cc3-9bed-820e08ad2e52 |  | note | VicRoads Standard Section 204.17
label | a2a51c7f-f611-59e6-ad70-e07d57829b1d |  | note | VicRoads Standard Section 720.07
label | ba22120e-d29d-563e-8e8a-f7a5bda16e2e |  | note | - - - - - - - - -
label | b392e5eb-850b-5151-9bd5-d94431fe74c9 |  | note | Inspection / Test Method - Site Inspection
label | 7bd27989-9eab-5a6a-bc86-4c63fcc56204 |  | note | - - - - - - - - -
label | 137f850d-fd9d-52ea-bfb6-1619c22a4c9a |  | note | Record of conformity - Signed ITP
label | 13d82815-88ef-516e-8c1c-11802db400d4 |  | note | - - - - - - - - -
label | 044c751a-f9ba-566b-9fa0-bf352316179a |  | note | IP
label | 9c9c91b9-b6fd-5e83-b2b5-e4874b26f60b |  | note | - - - - - - - - -
label | 5ed06d1c-e25b-5dd6-b8ba-c851271744ec |  | note | Responsibility - Site Engineer
label | f3710540-80cf-5e84-99b5-57e67f861633 |  | note | - - - - - - - - -
date | 8fce9bcd-b11e-5ce6-9815-48373108da54 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - Cultivation
label | a99ffc75-d706-5711-8701-918c88262eb4 |  | note | Frequency - Each applicable lot
label | b0e139e8-833c-54bd-850f-7cd850a60a4a |  | note | - - - - - - - - -
label | 2f150780-bf04-597d-b277-292da41febb4 |  | note | Acceptance Criteria - Cultivation shall be undertaken to break soil down to a tilth with 80% of the volume composed of clods less than 50 mm in diameter
label | c91a5537-dbe6-5484-9222-64826ad09672 |  | note | Prior to mulching, planting or grassing, area to be presented to Superintendent for approval.
label | 03dd073c-f89b-54c8-8201-e9972b0cf4f7 |  | note | In areas where topsoiling or cultivation is not practicable, the Contractor shall submit alternative methods to achieve an equivalent result to the Superintendent for review.
label | a2c6cb68-e5fa-5e85-9355-33b9b30b6666 |  | note | - - - - - - - - -
label | 54d4289e-7bac-5610-9e93-cb7646548d08 |  | note | Reference Documents - VicRoads Standard Section 720.07
label | 471ff738-dd9e-5626-8d42-42a594e538be |  | note | - - - - - - - - -
label | 3964bd2d-8d8f-5ceb-9e42-7022d0bfd6a2 |  | note | Inspection / Test Method - Verify
label | 732fa617-7a46-5fff-95d1-970ee3391741 |  | note | - - - - - - - - -
label | 08cc6052-c567-5314-bc4b-a03f87322eea |  | note | Record of conformity - This ITP signed off
label | d84eacb7-243a-59d9-8a76-1325d53a1d25 |  | note | - - - - - - - - -
label | 347980aa-f3b5-5a7d-98b9-96648ef29e93 |  | note | HP
label | 72d87840-6c7a-5eac-95f7-599bf02ed66a |  | note | - - - - - - - - -
label | f542b246-c388-58d3-b5ed-78d294aef61e |  | note | Responsibility - Site Engineer / VicRoads Superintendent
label | 45ea228c-d487-5f4a-b622-55092fc6add8 |  | note | - - - - - - - - -
date | f0ec52dc-9fa9-52a0-aa8e-ea48a4426759 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Bulk density of soils for planting and grassing
label | 0faf4d71-f4c9-58f8-8bce-80a8644b8db8 |  | note | Frequency - Each applicable lot
label | 9eba3ddf-ff91-5bdb-98ee-7b5e586774ba |  | note | - - - - - - - - -
label | d50cf9dd-0876-5126-a26c-97727a248ec7 |  | note | Acceptance Criteria - After cultivation and trimming, the Contractor may lightly compress topsoil for stability on slopes.
label | 07900e9c-aae5-5260-8f37-5fbee58bc64e |  | note | Vibrating plates shall not be used. Ensure the dry bulk density does not exceed the limits in Table 720.072
label | ef2a27a1-067c-59f8-bc00-63c23dd4db2f |  | note | - - - - - - - - -
label | 9b7168ae-3121-5263-9eda-6a3711f3a5ae |  | note | Reference Documents - VicRoads Standard Section 720.07
label | ff143f88-10e8-55f6-883c-d109c593518b |  | note | - - - - - - - - -
label | f34e42bb-3ae0-5410-8dd4-5fa56b96e341 |  | note | Inspection / Test Method - Verify
label | d9727fc9-19c4-55a2-b6e4-4616169adc21 |  | note | - - - - - - - - -
label | 74901c0b-fdf6-51c7-9784-9618a42306f5 |  | note | Record of conformity - This ITP signed off
label | d54a5388-7ec2-5b0e-aa21-9b91dfacb75d |  | note | - - - - - - - - -
label | 235c5a34-918f-5fc2-8616-439d5b3fdbdb |  | note | IP
label | bb4ce2a4-100a-5b5d-91ad-f6df753dba90 |  | note | - - - - - - - - -
label | 939b61b6-cba2-5229-bdd8-46f91fa35383 |  | note | Responsibility - Site Engineer / Site Foreman
label | 6408c77e-79a9-5445-a5d0-15c0541881b9 |  | note | - - - - - - - - -
date | 72dfb785-d53d-57f4-9c5d-49e3160f1753 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 - Topsoil finished surface levels
label | 7ed852a1-ca77-50f2-a639-fb19dca331e5 |  | note | Frequency - Each applicable lot
label | 632de927-a4fa-5529-8670-90d6b63cfbc5 |  | note | - - - - - - - - -
label | 3c9f9ac8-3b0f-5d78-9645-e3be694a8d09 |  | note | Acceptance Criteria - The finished level of grassed areas shall be:
label | 7751abf8-7db4-539c-8440-7a7a87baa738 |  | note | (i) not higher than 125 mm below weep-holes or damp-proof courses in adjacent walls;
label | 342980dd-cb34-5538-b179-82bea5c051fd |  | note | (ii) level with the bottom of fence plinths;
label | a1a04428-2288-5baa-82d8-6c279cf5dbb4 |  | note | (iii) level with adjacent pavements, kerbs, pits and other structures.
label | d90e1488-b879-57d8-8c51-7f0b07a5f6f4 |  | note | The finished level of garden bed mulch and/or topsoil shall be tapered so that the finished mulch and/or topsoil levels meet flush with the adjacent surfaces.
label | 47551a6d-7c8e-506c-b4ca-9a44dcb97d0a |  | note | - - - - - - - - -
label | 54bc2151-1df3-5693-b1d8-02ad71e1b327 |  | note | Reference Documents - VicRoads Spec. Section 720.07
label | f299ce9e-a57c-57c3-a903-dea9ff6b8224 |  | note | - - - - - - - - -
label | 1ccbe017-3183-506e-b055-35179c156ab6 |  | note | Inspection / Test Method - Verify
label | 2b96f422-0809-59b6-a363-0b563a53ed61 |  | note | - - - - - - - - -
label | 08bd9cdc-5b05-5b4d-bf7a-2e795715420d |  | note | Record of conformity - This ITP signed off
label | a056cd7a-644a-5149-a99b-0af28f72af68 |  | note | - - - - - - - - -
label | a8211ab5-3ed1-5233-b1f4-ece641863a91 |  | note | IP
label | 5892463d-fc0f-59e7-abed-070bc6668454 |  | note | - - - - - - - - -
label | ec694295-7a34-5a21-a9e3-c091744e85c3 |  | note | Responsibility - Site Engineer / Site Foreman
label | 4f585f52-be4d-596b-badf-6f3483d36445 |  | note | - - - - - - - - -
date | 4b565732-7ff0-5187-a3f2-817178e1144d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.8 - Planting
label | 66c12b4c-35ff-5791-9b79-4cdc554a873b |  | note | Frequency - Each applicable lot
label | 0f60da17-c467-5a1e-b9a7-9fd7d417fb2c |  | note | - - - - - - - - -
label | c2860a4f-0a83-5282-b14f-f325cdad045c |  | note | Acceptance Criteria - Holes in heavy soils or on batters shall be prepared so as to ensure adequate drainage.
label | fe71a042-e132-5c50-92dd-96507c2d1a1e |  | note | Planting holes shall be backfilled with friable topsoil free of debris, rocks and clods greater than 50 mm in diameter.
label | 8bc6b842-6369-599f-93c3-f1739d7097a4 |  | note | - - - - - - - - -
label | 5d2e5e91-008c-5c71-9000-c143babe194c |  | note | Reference Documents - VicRoads Standard Section 720.09
label | b8fd09cf-2fbe-5bdb-b550-4608fedb304e |  | note | - - - - - - - - -
label | 9c89efe9-de4b-5a67-8ea7-dba987f9ecba |  | note | Inspection / Test Method - Verify
label | 09a895fb-233f-565d-9f94-c092aa78f6de |  | note | - - - - - - - - -
label | 2084f5b8-b3a8-5fda-bdf3-2e0e70fd5c8d |  | note | Record of conformity - This ITP signed off
label | aa9136b3-4f75-506f-b7c3-457db7ae8a26 |  | note | - - - - - - - - -
label | 99e3b704-138d-579f-b68e-0fe7d28bfca5 |  | note | IP
label | 162a5e54-8395-523c-a2ad-b78a3a665a1f |  | note | - - - - - - - - -
label | 05d42d05-e992-575f-a1b4-9bfec7f216e9 |  | note | Responsibility - Site Engineer / Site Foreman
label | 4f67a6b3-d146-5155-962d-14c1e9e3fadc |  | note | - - - - - - - - -
date | 122a1655-9614-575d-9198-8a1cf383dad9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.9 - Mulching
label | f0072455-480c-5183-89d9-60ef08f27b2c |  | note | Frequency - Each applicable lot
label | 0b9e4552-889d-5b0b-a4a8-412cb3c39812 |  | note | - - - - - - - - -
label | 2a7497fd-e3c6-5fbf-a3ef-e031a435d7a8 |  | note | Acceptance Criteria - Install wood mulch to all Planting Areas unless otherwise specified.
label | fb348c10-e768-50a7-ba29-0523ec4a0213 |  | note | Mulch shall extend at least 1 metre beyond plant centres at the outer edges of all Planting Areas. If space does not permit this in median, separator or splitter-island planting, mulching shall extend to the back of kerb.
label | 32f632b2-887c-5999-a227-377a266f20d6 |  | note | The Contractor shall install 2 metre diameter mulch rings around all Individual Tree Plantings.
label | 7b15254d-edeb-5d77-ae31-fdceed69a8fa |  | note | Mulch depths in all situations shall be a minimum 75 mm and maximum 125 mm.
label | e1f9fd18-9423-5657-a2a4-f3b6bbd221e1 |  | note | - - - - - - - - -
label | 89be3c98-5207-5cce-80dc-bd3f6139b001 |  | note | Reference Documents - VicRoads Standard Section 720.08
label | 3c96604b-db6f-5660-ac46-f39587dc7dc3 |  | note | - - - - - - - - -
label | 89d4a5b8-95fe-5e05-bb22-09cb8f81fce7 |  | note | Inspection / Test Method - Verify
label | ac82eaeb-d507-5a9c-9104-350a219bc3f1 |  | note | - - - - - - - - -
label | cea7360a-5985-53a0-9b1b-ef137df317f8 |  | note | Record of conformity - This ITP signed off
label | f43ca6b4-511e-538a-884c-a93f14d0f53c |  | note | - - - - - - - - -
label | 9ed3aa38-e43a-5a14-a717-e0a0832f9b47 |  | note | IP
label | 64e1c859-2d92-58cc-819d-216332ac79e1 |  | note | - - - - - - - - -
label | e4e00021-6305-544c-ab2c-99c1197f18fb |  | note | Responsibility - Site Engineer / Site Foreman
label | 9a868ac7-a566-52be-9262-2080b31f6f49 |  | note | - - - - - - - - -
date | 33cac7ff-d0db-5b94-a08d-650f0160d370 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.10 - Grassing of disturbed areas
label | c5cd3834-7351-537c-a198-b6e3a7d785a0 |  | note | Frequency - Once installation of assets completed
label | 96f38644-f486-561a-b8a4-db1fa1341a8f |  | note | - - - - - - - - -
label | c6327ac5-3c2e-5e31-992a-c71fcd714593 |  | note | Acceptance Criteria - All disturbed areas shall be topsoiled and grassed, all areas to be cultivated to a minimum 50mm depth, and moistened prior to the application of grass seed and fertiliser.
label | 48d6c7f4-5d0c-5535-b5d1-396ef1295732 |  | note | A joint inspection of all grassed areas shall be carried out between the contractor and superintendent three months after sowing has taken place.
label | 07861679-66fa-5a51-8726-7b4b2ca53e35 |  | note | - - - - - - - - -
label | 3ca51e26-b232-53c8-8486-b6953a1335a8 |  | note | Reference Documents - VicRoads Spec. Cl.708.20
label | 19504d75-c1cd-546f-971a-68560c00c3ad |  | note | - - - - - - - - -
label | bae244db-a999-5eb3-bb1b-c92c27067138 |  | note | Inspection / Test Method - Visual Inspection
label | 02f7b1fe-2827-5824-b3fb-80d398ab375e |  | note | - - - - - - - - -
label | fba2b825-cb30-5de1-8e40-08ecce6d0df1 |  | note | Record of conformity - Site Photos
label | ac0e07a4-a4aa-545f-91cc-66036a387c2c |  | note | - - - - - - - - -
label | e1048e00-6391-5cf9-86b1-97b5f76a8d1e |  | note | HP
label | 5fc2136c-2696-5bd7-beed-37b77528c67e |  | note | - - - - - - - - -
label | d6555afd-5731-5a26-a234-905c88a1466e |  | note | Responsibility - Site Engineer / Superintendent
label | 896ec323-1f42-57d2-94b8-b30f7ae5603a |  | note | - - - - - - - - -
date | 0982f3ed-79af-54df-82aa-f14866676c67 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.11 - Grassing
label | cc26363a-112a-5beb-8cd7-6932eb36c5bd |  | note | Frequency - Each applicable lot
label | aa746b4b-0f24-57ca-998c-97f6e90bac47 |  | note | - - - - - - - - -
label | c7cba13c-bdd4-580e-936e-360f4d7a2edd |  | note | Acceptance Criteria - Grass seed shall be sown at minimum 100 kg/Ha (if drilled) or 200 kg/Ha (if broadcast), distributed evenly to achieve an even and dense grass cover.
label | 6a041d29-7b60-59a0-85ab-89c4d429b9db |  | note | Germination rate shall be minimum 80% cover within 8 weeks and 95% cover within 3 months of sowing.
label | 14e05c34-caa1-5ad5-9397-672c4c55d58b |  | note | - - - - - - - - -
label | e94c51ef-1fdb-56d7-a1dd-056f084ca128 |  | note | Reference Documents - VicRoads Standard Section 720.10
label | 65b51927-c6eb-5549-98e0-4867e0d0813d |  | note | - - - - - - - - -
label | 2e873e9c-cf1f-52e3-97fc-d9cbd47b5577 |  | note | Inspection / Test Method - Verify
label | 8b26afec-74ae-59d9-9b15-167d0c02459c |  | note | - - - - - - - - -
label | ac64c8ec-cb05-5d78-a4fb-84b2b75424c4 |  | note | Record of conformity - This ITP signed off
label | 04529e3f-f211-5db0-adc2-d74855f7c0d1 |  | note | - - - - - - - - -
label | 3dea45cf-6b67-5628-9bb6-aabcc30b6902 |  | note | IP
label | a2c0c58a-5f80-5465-93ac-26837a4f9f18 |  | note | - - - - - - - - -
label | f8d0720c-7d38-5512-b0d8-f2a606970fa0 |  | note | Responsibility - Site Engineer / Site Foreman
label | 5f7e0ed9-f164-54ae-87ab-ec342a016ea8 |  | note | - - - - - - - - -
date | aaac0db4-ce3f-5953-a671-0b2b5f40428b |  | date | Date Completed:
checkpoint-group |  |  | section | 3 - Completion
checkpoint-status |  |  | checkpoint | Final Inspection
label | ac613a67-1280-5bf6-abec-38072b19e6cf |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 4e14966f-9b53-5256-a401-52cc0a1afd50 |  | textbox | Print Name:
text | 6b59b68a-dfe0-5387-959d-5f167c55e5b0 |  | textbox | Position:
date | 788d2991-b6cd-52b2-8f9e-915ec3bcb792 |  | date | Work Completed On
date | 6857a5ed-61f8-5be3-a8fc-baa1a1e1fe00 |  | date | Date:
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification.
select | 6d2eb2d9-0b61-543f-80f3-f5bd1c256eda |  | dropdown | Is the relevant RFI attached to the Lot? | YES,NO,N/A
select | edbfa82b-4751-5a7c-84a9-65d08477fe5e |  | dropdown | Is the relevant NCR attached to the Lot? | YES,NO,N/A
select | 0f6f65ba-1051-5a23-b7b0-ce1d8ca3b18a |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES,NO,N/A
select | 2df7ff19-b5f2-57c5-9206-1844f145c095 |  | dropdown | Lot Plan or “Highlighted” IFC drawings (mud maps) attached to the Lot? | YES,NO,N/A
select | 9f1e5b7c-e3c6-55aa-bdfe-37393c7af907 |  | dropdown | Survey conformance records attached to the Lot? | YES,NO,N/A
select | cc3a6e57-276f-55fc-8f82-3f2e77365194 |  | dropdown | Subcontractor/ Supplier records attached to the Lot? | YES,NO,N/A
select | e82e7cb7-dba3-5a80-a40f-2c2d4fe430a8 |  | dropdown | Conforming Test Results attached to the Lot? | YES,NO,N/A
select | 075f8648-bf45-58d4-aa70-bef99becfb5b |  | dropdown | As built records attached to the Lot? | YES,NO,N/A
select | 1edb58ed-6d4c-568d-8a8e-b3e482e0b326 |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | d2b3a399-3bef-5390-82e7-eb8d02d679db |  | textbox | Other:
select | 8a9d7108-3a3c-5e91-a2f7-6af0cfa42c6c |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | 165ae27c-048a-5684-a3ae-5974d6b10c8e |  | date | Lot Closed On
text | 787f2d38-92b1-5b98-87b9-e76923fcfd1b |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-081-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0081 - Structural Crack Repair | 39c4a8ab-01fd-4c7b-afdd-1a521b2671f9
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | d0350451-e00d-5d8a-8b79-a817f77b7352 |  | note | Document Title: ITP-081-AX-LOT-XXX - Desc
label | 378a2e13-82e6-5257-a380-bba85ffa91bd |  | note | ITP Description: Structural Crack Repair
label | 68c7b7bf-42c0-50b2-a039-00f0c05b9295 |  | note | Document Number (in Teambinder): 1145-C200-FUL-QAC-ITP-0081
label | 53b7f91b-e029-5fbf-be39-bfd9fde6477c |  | note | Revision Number: 00
label | 92554cef-c8c0-55c6-8fde-a915294c51be |  | note | Revision Date: 04/05/2022
label | 6767c3bb-a183-52ef-b58f-79138ddd4663 |  | note | 1.1 VicRoads Section 610 Feb 2020
label | 78166a0d-3cd7-5596-a7ec-15fd53dc42f9 |  | note | 1.2 VicRoads Section 686 November 2018
label | 2696f4b4-8556-548d-9cb4-6fc84cb7c824 |  | note | 1.3 VicRoads Section 687 August 2018
checkpoint-group |  |  | section | 1 - Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | a747e6a7-ce3c-5759-8820-f48b08a5ee61 |  | date | Lot Created On
date | eb133d81-633a-589e-a1af-3b9bf9e83468 |  | date | Lot Opened On
date | a59b2679-eac7-53b7-ba7c-6f7fe664068b |  | date | Work Commenced On
select | 2ad79de0-dce0-5497-a669-d2865cb08477 |  | dropdown | Lot Type | STL- Structural Lot
text | 71401a90-8c1a-5f91-915f-d4d18031e752 |  | textbox | From and To Chainage
select | 74052956-701d-567e-9a63-0ad4766d54c1 |  | dropdown | Construction Element | SITE - Site General
select | c3c2ddb3-aafd-5e01-bec3-23bb8ae0f4c2 |  | dropdown | Activity | OTH - Other
select | 62fc49f9-38f3-51fa-973c-44c05707d2a4 |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | 6054e681-ac63-56f0-bba3-16c5253f138f |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | 4df475a5-273e-533d-9218-358149f4dcf8 |  | textbox | Engineer Responsible
text | cb9423df-f3ac-522e-8ab0-dad7c1f05860 |  | textbox | comments
checkpoint-group |  |  | section | 2 - Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 2.1 - Assessment of Crack
label | 31fbc0d6-20e5-5735-861f-83a7eef1fd62 |  | note | Frequency: For each element, prior to Works commencing
label | 58680cae-3a0b-5277-97da-dc120beb9d36 |  | note | - - - - - - - - -
label | f93058be-4e2b-53f4-85ec-06db6617de95 |  | note | Acceptance Criteria: Repair of cracks shall not be undertaken unless the cracked concrete structure has been assessed and the influence of cracks on load bearing capacity, serviceability and durability has been evaluated by the Contractor, and reviewed by the Superintendent.
label | 23b91cce-8ae7-5338-b8b3-f69141701c7e |  | note | Cracks to be determined either as active or inactive.
label | 5f0d4e23-5648-55c6-a7a4-10cba4e621db |  | note | Inactive Cracks:
label | 1a1e35b4-b666-549c-acc5-77274838d075 |  | note | <0.2mm - May be coated by protective coating system provided they are not associated with earth or water retaining concrete components.
label | 0a2152f1-7c92-5807-9088-bb4b71764132 |  | note | >0.2mm - shall be repaired via Resin Injection, Routing and Sealing or Gravity Feed method.
label | fa95137b-d076-5dfa-b7b1-1e39d1d72d25 |  | note | Active Cracks:
label | 37a84f81-92f8-5dcf-a84a-fba806091c09 |  | note | >0.2mm - shall be repaired via Routing and Sealing.
text | 2436c177-741d-514c-a563-f56ae09a747b |  | textbox | Teambinder Correspondence Approval number:
label | 37e028a0-539c-541f-98d4-44b95fdfdbe2 |  | note | - - - - - - - - -
label | 18c7e0d2-54ea-56a5-b56c-181b648b523a |  | note | Reference Documents: VicRoads Spec. Cl.687.01 Cl.610.24 (b)
label | 17fe5a97-93c0-5709-9492-170bcbab9c28 |  | note | - - - - - - - - -
label | 122ffb07-5f1f-5e21-93f5-f0ba99512ac3 |  | note | Inspection / Test Method: Visual Inspection
label | af7b1692-ccc4-506c-a465-e179b4f43a53 |  | note | - - - - - - - - -
label | c50251b3-f7ec-5588-ad06-7a8af550d5cc |  | note | Record of Conformity: Holdpoint released
label | d1d1681c-f560-54ca-ac27-c5e35482d6f3 |  | note | - - - - - - - - -
label | 7936b1cc-5f62-56f9-93a7-3d921b120e30 |  | note | HP
label | 85ebe7c0-e9cd-54b6-ab63-24c002f92191 |  | note | - - - - - - - - -
label | 05fddbf5-ef74-5c5f-af10-73b4e89234ba |  | note | Responsibility: SE/PE and Superintendent
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.2 - Work Procedure
label | 7b128d95-bc85-5664-b181-009b3f643a98 |  | note | Frequency: For each repair methodology, 14 days prior to Works commencing
label | 5f4e6503-2831-5494-9760-dafa6a516b35 |  | note | - - - - - - - - -
label | 5cf69cbe-a077-5b01-ac39-3777ba82d0e4 |  | note | Acceptance Criteria: Crack repair procedure should be submitted prior to repairs being undertaken and must be approved by the Superintendent. Repair of cracks shall not be undertaken unless the cracked concrete structure has been assessed and the influence of cracks on load bearing capacity, serviceability and durability has been evaluated by FH and reviewed by the Superintendent.
text | cfd704d0-af74-583d-b46d-f5beb024afdb |  | textbox | Teambinder Material Approval number:
label | 41c3d515-bef3-5a75-bddf-59aefa01e9e7 |  | note | - - - - - - - - -
label | bd63ec34-e532-5b3e-b023-f7c6af9106a4 |  | note | Reference Documents: VicRoads Spec. Cl.687.01 CI.687.09 (a) Cl.610.24 (b)
label | 1dda63fa-d434-5acb-95ce-a40d29655fe4 |  | note | - - - - - - - - -
label | 2480c1b8-c850-5012-ade2-c4fe99e1015b |  | note | Inspection / Test Method: Visual Inspection
label | 4759e0f6-27e5-55f1-95ff-0dcb0fd00080 |  | note | - - - - - - - - -
label | 85c523cf-123f-5c99-9ad9-bc55e15c8f62 |  | note | Record of Conformity: Holdpoint released
label | 727e2259-e36f-57bd-bc88-a673e4a90abf |  | note | - - - - - - - - -
label | ae80bbf3-99e6-59f4-9f42-cbf9b345018e |  | note | HP
label | bf44ad9e-558a-5a3f-9e71-5bed2cd0dc65 |  | note | - - - - - - - - -
label | e1b69d81-b2a1-5801-9af8-5424c3d2552c |  | note | Responsibility: SE/PE and Superintendent
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | 3 - Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 3.1 - Resin Injection/Gravity Feed (Inactive): Epoxy or Polyurethane Resin Selection
label | 4259e6cd-6ae5-548b-bba2-0f6f0d6c1414 |  | note | Frequency: For each product, prior to Works commencing
label | a3ddaeaf-bda8-52de-a4d3-658c8b4d17a9 |  | note | - - - - - - - - -
label | c48f9084-4082-58f3-9d52-b09e23f4c9ac |  | note | Acceptance Criteria: Product to be selected based on the following criteria:
label | fa0dbf60-3b92-5494-bb61-76e258103e8c |  | note | i. viscosity @ 20°C - 23°C 650cps max.
label | c2b907b3-53c5-5d67-ae7b-85018d2c9e91 |  | note | ii. compressive strength @ 7 days ≥60MPa;
label | 953d2df3-a915-5d85-826a-a93ccdca9118 |  | note | iii. tensile strength @ 7 days ≥25MPa;
label | b47a9d26-16c0-59ef-b0c5-69f5db6405fb |  | note | iv. flexural strength @ 7 days ≥50MPa;
label | 0d2fc045-7c54-5215-8cb5-ff4f27b7245c |  | note | v. adhesive strength at crack edges @ 7 days ≥2.5MPa (or concrete failure)
label | 9fef23f9-c248-5ae2-80f1-1070d0614052 |  | note | Note: For the resin injection or gravity fed applications only.
text | 1a6c4541-9432-5174-b325-31dcef8717e9 |  | textbox | Teambinder Material Approval number:
label | 49577d74-eed7-5a8a-806e-d8b98a254621 |  | note | - - - - - - - - -
label | 05cf5fd9-004e-524e-b5ee-eab6a73381dd |  | note | Reference Documents: VicRoads Spec. Cl.687.05 (a) Product TDS
label | e9461224-4f9c-584b-b76d-349bc4ec7f61 |  | note | - - - - - - - - -
label | 77d2bcf3-83a6-5d79-91e1-c22d6db77a67 |  | note | Inspection / Test Method: Document Review
label | ad36e3d4-0320-5be2-9b92-ea6b867fd64c |  | note | - - - - - - - - -
label | 89896374-b2ee-5239-a8fd-f20cf55df939 |  | note | Record of Conformity: Material Report
label | 1a8a1f50-00ef-520f-bf9f-98d95c41bdf7 |  | note | - - - - - - - - -
label | 9a984b6a-5c9e-55fe-a54f-b846e48b8fb2 |  | note | IP
label | 2badafe3-9a9c-5ad6-82f9-288c1021b101 |  | note | - - - - - - - - -
label | f7cb1461-3041-5168-9af6-c666820ef5d0 |  | note | Responsibility: SE/PE
checkpoint-status |  |  | checkpoint | 3.2 - Routing and Sealing (Active): Flexible Sealant Selection
label | 1f0b9dac-8500-5ca0-b7db-e968a68a91ac |  | note | Frequency: For each product, prior to Works commencing
label | 436e8393-cf4a-55b6-aaf5-c251d1c91f7b |  | note | - - - - - - - - -
label | 870ca50e-71ad-5ffe-b274-71ad526aea79 |  | note | Acceptance Criteria: Product to be selected based on the following criteria:
label | 4662d805-cbf4-5c33-adec-a525faac9587 |  | note | i. provide for a minimum expectant movement of ±25%;
label | d8bbd27b-cfb6-5a2b-b3b7-59cdb3808617 |  | note | ii. Whether or not the repair/sealant is subject to traffic (trafficable or non-trafficable)
text | 0faccee6-d95f-5830-81c3-2118d85f60fe |  | textbox | Teambinder Material Approval number
label | e7aa7cf3-aea5-5874-8894-58f30eb62640 |  | note | - - - - - - - - -
label | 7dd394b5-294d-575a-9769-1329cbda6cbe |  | note | Reference Documents: VicRoads Spec. Cl.687.05 (c) , Product TDS
label | 15765d30-ccea-5cb6-a096-c7efcf879e00 |  | note | - - - - - - - - -
label | 8d8cd405-ff39-56ac-a530-d31458405cdb |  | note | Inspection / Test Method: Document Review
label | 1585677c-e358-557e-b615-02f30c77bb74 |  | note | - - - - - - - - -
label | 772d740a-9b6a-5f12-aae3-0558e881c0ab |  | note | Record of Conformity: Material Report
label | c66a64d4-1355-56a9-8077-52856a3bc567 |  | note | - - - - - - - - -
label | f43c9bae-b578-5f3e-bdf5-24f31795e80f |  | note | IP
label | bcbe3c90-c739-5804-ab4a-33d19841788c |  | note | - - - - - - - - -
label | 000d5883-b8e3-5580-a2f4-6f6efd500866 |  | note | Responsibility: SE/PE
checkpoint-status |  |  | checkpoint | 3.3 - Routing and Sealing (Inactive): Epoxy Mortar or Paste Selection
label | ed717c91-cf30-563e-bd7b-29c85a5b88ef |  | note | Frequency: For each product, prior to Works commencing
label | 64b3b79f-e6cd-5016-8b82-e1343e76aca0 |  | note | - - - - - - - - -
label | 1ef6a9a6-ee73-51c2-b300-3a228f64f7ae |  | note | Acceptance Criteria: Product to be selected based on the following criteria:
label | 48df0755-3485-5762-b4c0-8971661a4a39 |  | note | i. compressive strength @ 7 days ≥60MPa;
label | ab878c55-f581-5059-bca3-3eaa273b68f8 |  | note | ii. tensile strength @ 7 days ≥25MPa;
label | 87772d8f-22c5-5f0c-964c-47aac03b2ac6 |  | note | iii. flexural strength @ 7 days ≥30MPa;
label | de16ee26-3e45-55f1-b949-7232eeaca30a |  | note | Note: For the routing and sealing, injection nipple/entry port placement and surface sealing applications only.
text | 8b2a2f0a-78b8-58dd-8c11-401321487059 |  | textbox | Teambinder Material Approval number
label | f56399f1-5bcd-5553-9270-aecc5907389c |  | note | - - - - - - - - -
label | 660686cd-7fc8-56ae-b2e3-6b90f304417f |  | note | Reference Documents: VicRoads Spec. Cl.687.05 (b) , Product TDS
label | 75b60e14-e2cb-5386-af42-01a7ad4f2134 |  | note | - - - - - - - - -
label | 06fae678-1e8f-5858-b702-9af6663d8254 |  | note | Inspection / Test Method: Document Review
label | 5553d37a-9246-5a10-9552-08bd818a296a |  | note | - - - - - - - - -
label | 901865d3-99d2-507f-9252-f8ecbb42f44d |  | note | Record of Conformity: Material Report
label | e24fa0f8-8946-58c3-bb98-a136436647fc |  | note | - - - - - - - - -
label | e9099de3-d4ee-5f80-949b-e1927bc797e8 |  | note | IP
label | bb406f03-c282-5e10-b753-147cff099132 |  | note | - - - - - - - - -
label | fde16194-608c-5b99-b559-a37310827445 |  | note | Responsibility: SE/PE
checkpoint-status |  |  | checkpoint | 3.4 - Protective Coating: Silane Selection - Inactive Cracks <0.2mm Width
label | 7b774ec9-91ba-5016-9c9a-284a2d7d4b6f |  | note | Frequency: For each product, prior to Works commencing
label | e237f960-85ca-5a04-b772-6fae7b8ebd9b |  | note | - - - - - - - - -
label | 159422b8-3645-578d-a204-b985d4bfc6cc |  | note | Acceptance Criteria: Product to be selected based on the following criteria:
label | 94b44775-bb33-59bb-9745-7902691dd7a7 |  | note | i. active ingredient: ≥95% (penetrant) ≥80% (solid silane) ≥80% (silane crème)
label | 8dcca035-e4d7-51b1-873d-8d4d5477b6ac |  | note | ii. penetration depth: 5mm min.
label | 6b00452e-7b34-5956-9320-096353ecda9c |  | note | iii. contain a fugitive dye to enable coated areas;
label | 32c3c1ee-5799-5cf5-ba81-b6af88ce0082 |  | note | iv. be compatible with a film-forming top coat;
label | 8e473b2d-5f30-54c4-beba-056a71d3928b |  | note | Note: For the protective coating of inactive cracks ≤0.2mm in pre-stressed elements and exposure classifications B2, C & U only - 0.2mm cracks are acceptable in other precast elements and exposure classifications.
text | ffecc039-5bec-5ae7-b21d-71f093fdf76f |  | textbox | Teambinder Material Approval number:
label | 969fbc6f-7086-53dc-ae50-ed6dfe097bc6 |  | note | - - - - - - - - -
label | 3d8cfb06-7300-5a5b-9783-df293baeab06 |  | note | Reference Documents: VicRoads Spec. Cl.687.12 Cl.687.05 (c) Cl.687.05 (h) , Product TDS
label | 8c42ae43-a0ed-5333-a5f5-16aab6832538 |  | note | - - - - - - - - -
label | 060f472e-24ab-5489-bd43-7a6af510d91f |  | note | Inspection / Test Method: Document Review
label | 6041154a-873f-54a2-b363-04a18ae34625 |  | note | - - - - - - - - -
label | 97ba8fca-3689-5100-9e1b-9b55c5de602b |  | note | Record of Conformity: Material Report
label | 92a75bc6-d0f7-5b51-b391-b560ee4f0fc6 |  | note | - - - - - - - - -
label | b3f8223a-150e-5b2d-80a1-5a8f02368355 |  | note | IP
label | d4b8e3cc-437a-55cb-8ce2-4a67780c9eba |  | note | - - - - - - - - -
label | c4231623-39f3-5226-9b45-170d2adec820 |  | note | Responsibility: SE/PE
checkpoint-group |  |  | section | 4 - Pre-construction activities
checkpoint-status |  |  | checkpoint | 4.1 - Contractor Competency
label | 2d94f058-7d17-55b0-a1cb-1a5c7113929d |  | note | Frequency: Once, for each personnel, prior to starting Works
label | 5de7a891-3adf-55e2-8306-a04478c33e5c |  | note | - - - - - - - - -
label | 4a111943-9e93-53f5-bf20-54aa977448fe |  | note | Acceptance Criteria: Personnel undertaking the concrete repair works shall have a minimum of 5 years experience in application. Documented evidence to be available.
label | d646abcc-f08d-5c69-bf2c-c8ab0a33f069 |  | note | - - - - - - - - -
label | 31413474-eab2-5ce2-8d58-305a4e2fedd0 |  | note | Reference Documents: VicRoads Spec. Cl.687.04
label | 89532020-9e33-5b79-af64-48145ddb8175 |  | note | - - - - - - - - -
label | 61ddcf2d-e940-58e8-a7fe-f4ddbc0dca6b |  | note | Inspection / Test Method: Document Review
label | 9d584172-b5fc-523c-a620-15bd7f8bae00 |  | note | - - - - - - - - -
label | e71a309e-fac6-5d6e-a009-4d917182c08d |  | note | Record of Conformity: Document evidence of adequate experience
label | 1e672104-4533-567d-841e-c01e268de779 |  | note | - - - - - - - - -
label | f4a7401d-e0ed-5ec6-a88b-a9dda355070a |  | note | IP
label | 3dd8f745-f430-5374-957d-2b654fab4faf |  | note | - - - - - - - - -
label | 3857e381-f299-5c88-b24f-f78d1b0716ef |  | note | Responsibility: SE/PE
checkpoint-status |  |  | checkpoint | 4.2 - Injection Equipment
label | 04f6ca95-2c34-531e-af6f-48af073e8aa2 |  | note | Frequency: Once, prior to starting the Works
label | 77777b9b-2d3f-574c-bd80-ca2cf293929c |  | note | - - - - - - - - -
label | d2284902-5137-560f-9d84-47520f3c037d |  | note | Acceptance Criteria: Injection equipment to be simple, easy to handle guns with pressure regulation or limitations in the operating range and be simple to clean and maintain.
label | 077603b8-9105-5e95-a63a-1e9ecfbc0e7c |  | note | Nipples/entry ports to have shut off valves or at least the ability to be capped to prevent leaks or air travelling back into the crack. Resin adhesive injection shall be performed continuously until cracks are completely filled. If port to port travel of resin adhesive is not indicated, the work shall cease immediately and the Superintendent notified.
label | e336af7a-3ea9-50ee-8358-c33564aca521 |  | note | Note: This ITP does not cover special purpose, multi-component injection pumps.
label | 839a0acf-4c1d-56c9-adea-0e81c9088a43 |  | note | - - - - - - - - -
label | 320ed45f-7834-5afc-9c81-1e6e7a788534 |  | note | Reference Documents: VicRoads Spec. Cl.687.06 (a) CI.687.09 (c) (iii)
label | 27e8271f-62c1-5b72-ae44-cef5ce700f2f |  | note | - - - - - - - - -
label | 43cb3494-7f89-51bc-9c6d-188466b76cb5 |  | note | Inspection / Test Method: Visual
label | 14dd5df0-0b73-5376-b744-350c350f4341 |  | note | - - - - - - - - -
label | e303c082-019c-5c91-b122-7ac70bc9453e |  | note | Record of Conformity: Signed ITP
label | 8f4672da-9fab-50f1-b687-d79d77dffd7a |  | note | - - - - - - - - -
label | ac71b232-e138-5632-bb75-92ff5fbb988e |  | note | IP
label | 03269220-e248-5eb8-abe6-c624c6a64409 |  | note | - - - - - - - - -
label | f62503c0-5505-5e4c-bef7-00145ffca7d3 |  | note | Responsibility: SE/PE
checkpoint-status |  |  | checkpoint | 4.3 - Weather Conditions
label | bc9b5aae-8d76-5c7a-85c8-0b3be362a821 |  | note | Frequency: Prior to each repair
label | ad5e3816-9d3c-5ddb-80f2-8934cf4ccb49 |  | note | - - - - - - - - -
label | 9984b987-66b8-53f0-bc9c-2f4d545db26e |  | note | Acceptance Criteria: Repairs are not to be undertaken when the ambient temperature is below 5°C or 5°C on a falling thermometer, or above 35°C.
label | aacbc3b4-b9a0-5642-a86b-8aaf839430c0 |  | note | Cooling the materials is allowed should the need arise if temperatures inadvertently rise during the repairs.
label | d85494ea-07ad-5374-9423-c0c0965d6195 |  | note | Where re-injection is required, this shall be carried out within the temperature-dependent period of the crack filling material given in the directions for use by the manufacturer. At high ambient temperatures, the use of cooling to influence the workability time of materials in containers is permissible.
label | 97a6bd4c-74fe-5ede-8005-44babc3ce868 |  | note | - - - - - - - - -
label | 4a01de9a-97ce-5ed6-a915-827bf983191e |  | note | Reference Documents: VicRoads Spec. Cl.687.05 CI.687.09 (c) (i)
label | 96f14414-40ca-5d05-94ea-fe76cc12ee2a |  | note | - - - - - - - - -
label | 89dc25f2-f9f3-582e-adee-7540e0844cba |  | note | Inspection / Test Method: Visual/ Measure
label | c68fe9eb-a17e-5787-a891-54f683ec7f6b |  | note | - - - - - - - - -
label | be482b11-e66b-5f38-b03b-06ab8a1b169c |  | note | Record of Conformity: Signed ITP
label | 5fd40c57-a4a9-5893-8057-30cf024059fd |  | note | - - - - - - - - -
label | d473b096-c078-5097-9e5b-5fca56d741a8 |  | note | IP
label | d72a1eac-d1e2-5cb9-94f0-6e56d836f141 |  | note | - - - - - - - - -
label | f752c1f0-11f3-51ca-aa77-a51b2db5d0dd |  | note | Responsibility: SE/PE
checkpoint-group |  |  | section | 5 - Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Surface Preparation
label | ab4178bb-080b-5f51-9456-7222d8df454c |  | note | Frequency: Each crack
label | 883e2239-6070-5e65-a0cb-69b7eb30dac6 |  | note | - - - - - - - - -
label | ad67c6f8-1fbe-5048-a3e8-a59e6bcddf3a |  | note | Acceptance Criteria: Cracks and surfaces located within 50mm each side of the crack to be cleaned of all loose particles, dirt, dust, curing compounds, grease or efflorescence by appropriate means (i.e. oil-free compressed air, industrial vacuum cleaners or flushing with high pressure water). Impurities, which inhibit wetting and adhesion or penetration by the crack filling material, shall be removed.
label | f2320494-55f8-55e7-bbd8-f6f8e765bfd6 |  | note | Where cracks and surrounding areas have been moistened during the cleaning process, sufficient time or accelerated drying-out needs to occur unless the crack repair materials are water tolerant
label | 0cd3e2ca-c6ce-5386-9071-f1aa4a5bb4fa |  | note | - - - - - - - - -
label | 300644d0-5004-5df8-9224-274e2ed6d021 |  | note | Reference Documents: VicRoads Spec. Cl.687.08
label | 7f0fbf0c-2ae4-5c85-9852-a13761f6264e |  | note | - - - - - - - - -
label | 597fb638-0dfe-5238-af04-9365411d580e |  | note | Inspection / Test Method: Visual
label | 980180b5-0ac1-51eb-b3ac-5613436fd00f |  | note | - - - - - - - - -
label | dd3c5931-d633-59e3-a257-5bcce122d427 |  | note | Record of Conformity: Signed ITP
label | c0097b8f-e09c-5acb-aff5-4a7c4f9b2a28 |  | note | - - - - - - - - -
label | e2a0b2f8-c632-5781-b99a-873e35294c0f |  | note | IP
label | cfa18793-5f22-509a-a690-7ba4338d9fd6 |  | note | - - - - - - - - -
label | 81dce741-d342-591c-a160-34e78afdad97 |  | note | Responsibility: SE/PE
checkpoint-status |  |  | checkpoint | 5.2 - Resin Injection: Inactive Crack Repairs
label | 4a5c8ac2-e285-5d5a-8d03-31303e1284a3 |  | note | Frequency: Each active crack
label | be62bf80-2fd1-5682-af85-8d5382d4b5ff |  | note | - - - - - - - - -
label | f858a76e-cc44-5622-8514-6500914a1a33 |  | note | Acceptance Criteria: Approved procedure to be followed, steps to witness:
label | 3f81ca93-3782-5498-a14b-395cf852bc77 |  | note | i. All materials in date and mixed as per the Product TDS;
label | 43953c9c-4fea-5d91-aad7-486774c75907 |  | note | ii. Each nipple/entry port coated in epoxy mortar or paste to create a water-tight seal to the entire perimeter;
label | a812d621-6ebe-5ed0-87cb-d76ea2b38eb4 |  | note | iii. Nipple/entry port placement central over the cracks at 200mm spacings maximum (where cracks are through the full section, nipple/entry port placement shall stagger);
label | a006e429-816c-5d7e-9ffa-fd788c5ecb91 |  | note | iv. Epoxy mortar or paste applied to the surface of the crack in between nipples/entry ports and the full height of the crack if within tolerance to eliminate resin leakage);
label | 49afc31b-e6ae-5525-8fbc-a13c3ecea1c0 |  | note | v. Once the epoxy mortar or paste has fully set, connect the injection gun to the lowest nipple/entry port (for vertical cracks) or at one end of the crack (for horizontal cracks);
label | 97acbfec-c5dc-5ae3-bfef-e28028ce5066 |  | note | vi. Initiate the injection, applying pressure until resin can be witnessed entering the next nipple/entry port;
label | e3db8922-7c64-549e-883c-04918f2dbadd |  | note | vii. Stop pressure and close the valve of the engaged nipple/entry port and connect to the nipple/entry port where the resin appeared, working either upwards (for vertical cracks) or along the crack (for horizontal cracks) until all nipples/entry ports have been filled;
label | ca8645e1-82e0-5774-9761-6b50d57618a7 |  | note | iix. Repair to be protected from damage or adverse weather while curing;
label | ff9b8ac7-818e-5bf4-a0ee-25eebb90b1ec |  | note | - - - - - - - - -
label | ad5ef80f-0c41-59d9-97e8-967851c274db |  | note | Reference Documents: VicRoads Spec. Cl.687.09 CI.687.14 (a) CI.687.15 Product TDS
label | 5ce58b51-88c4-5ce6-8a00-6f33159d9ed2 |  | note | - - - - - - - - -
label | 9380c2bd-5b30-5e66-9ac6-70923630f4a8 |  | note | Inspection / Test Method: Visual
label | c24584cf-ba0e-534b-b1b9-4775ec8dfb8e |  | note | - - - - - - - - -
label | a2b93e2f-afbf-5527-8773-ae169b6eaabc |  | note | Record of Conformity: Signed ITP
label | 36008d09-b86b-58cc-960f-be1094678a31 |  | note | - - - - - - - - -
label | 4a397f77-dc64-56c6-9697-3d380ba677c3 |  | note | IP
label | 9ad05614-5399-510d-9d8f-e63ac3220f62 |  | note | - - - - - - - - -
label | 11992c72-2c2f-56d3-b5d7-749c5e61869a |  | note | Responsibility: SE/PE
checkpoint-status |  |  | checkpoint | 5.2 - Routing & Sealing: Active Crack Repairs
label | 522e07c3-d582-5bb5-b336-f03ce47c972c |  | note | Frequency: Each active crack
label | 502104f0-fbc8-556a-bd3d-9fe1e07fbedb |  | note | - - - - - - - - -
label | 98ffafe9-d27c-5cf9-915b-7c9c16e3f3cc |  | note | Acceptance Criteria: Approved procedure to be followed, steps to witness:
label | bc8be5af-1e79-58e4-a561-76b920e90262 |  | note | i. All materials in date and mixed as per the Product TDS;
label | a30457ad-8983-52a5-bf6e-64d74843ef26 |  | note | ii. Saw cuts to be at a width to depth ratio of 2:1 and rectangular in section;
label | 3a2e0463-6e3b-56af-8c5d-00dddde80f2a |  | note | iii Surface dust to be removed;
label | 47754e77-6a66-58bf-afc7-faa1abbb823c |  | note | iv. Bond-breaking tape to be placed at the base of the chase/reservoir to limit sealant interface to 2 no. faces;
label | e9774f7e-326d-54a2-a01c-c919a5ad8c58 |  | note | v. Where required, masking tape to sides of the adjacent surface to create a neat finish;
label | 31beff94-20c0-5ec8-bffc-8c275e246b80 |  | note | vi. Sealant gunned or tooled into the saw cut to completely fill the void;
label | 7a3160de-1afd-5d50-886c-4030d4a9dea8 |  | note | vii. Product shaped with a suitable tool to recommended profile;
label | 80e86a88-2611-5762-bd38-4f141b00735d |  | note | iix. Repair to be protected from damage or adverse weather while curing;
label | d4cb4ee5-5491-5add-816f-0dcfc5e7b5b7 |  | note | - - - - - - - - -
label | a88ee68e-7f4f-5590-9b55-881edeeaaec3 |  | note | Reference Documents: VicRoads Spec. Cl.687.10 (b) (ii) CI.687.15 Product TDS
label | 81cffffc-d000-5cc0-a378-bfa411c0695a |  | note | - - - - - - - - -
label | 9dd66077-ee1a-5d38-a558-f763ad1e0436 |  | note | Inspection / Test Method: Visual
label | c0ca500f-2790-5198-a440-474e5306dee1 |  | note | - - - - - - - - -
label | b3bf1127-3591-52aa-9868-61d9f063023e |  | note | Record of Conformity: Signed ITP
label | 1ab39d44-9197-57b6-a464-c197b4398b59 |  | note | - - - - - - - - -
label | bd70e94d-0b3a-58d5-a960-9daa55c3f2f6 |  | note | WP
label | cc21fed7-c324-5bc3-a47f-efb656e784d5 |  | note | - - - - - - - - -
label | 796bcbe3-6361-54b1-aa81-295ab4b23cc7 |  | note | Responsibility: SE/PE
checkpoint-status |  |  | checkpoint | 5.3 - Routing and Sealing: Inactive Crack Repairs
label | aa0df729-bdbe-54bd-8c15-9ff57f61459c |  | note | Frequency: Each active crack
label | 5d554c43-a552-5b9a-b808-db46a0f894d8 |  | note | - - - - - - - - -
label | 00c4ecd8-5f1c-5769-8622-c7a2548e6daa |  | note | Acceptance Criteria: Approved procedure to be followed, steps to witness:
label | 05b3cd35-bab0-50b9-88dc-1e62fb9c4531 |  | note | i. All materials in date and mixed as per the Product TDS;
label | 594637b7-1a37-5628-933f-cadeb04d1e69 |  | note | ii. Saw cuts to be at a minimum width and depth of 10mm and V-shaped in section;
label | 393e0e1c-87a9-5443-adce-8d17e3ee4349 |  | note | iii. Surface dust to be removed;
label | beb72d50-3aa2-5a2d-9389-f71f484bc116 |  | note | iv. Epoxy mortar / paste placed into the saw cut to completely fill the void;
label | c4bf6ac4-47b0-53f3-b341-fbbb4b312ac2 |  | note | v. Product finished flush with the surrounding surface;
label | 4696cff1-aae4-5fa1-a54f-9b3ab46a313a |  | note | vi. Repair to be protected from damage or adverse weather while curing;
label | 9b2933db-7668-58f8-bebe-34e321e4fdc4 |  | note | - - - - - - - - -
label | 5f65c104-140b-5b44-948a-54f47d11ae8c |  | note | Reference Documents: VicRoads Spec. Cl.687.10 (b) (i) CI.687.15 Product TDS
label | 30348e51-1e43-5156-8346-497691949afd |  | note | - - - - - - - - -
label | 7809b5b3-35a1-5fe3-939d-a7d58371d8a2 |  | note | Inspection / Test Method: Visual
label | ce3066bd-4ea6-5100-b9ad-fbabd35ae0b9 |  | note | - - - - - - - - -
label | d94c90bc-1c6a-515e-91b1-602b3de68738 |  | note | Record of Conformity: Signed ITP
label | 501cadef-02cc-5a3d-bb86-b722a0d37988 |  | note | - - - - - - - - -
label | bce6159f-478f-5f67-867c-b9c0c6bc0414 |  | note | IP
label | ede936e8-b823-5bb0-aa53-67080972be39 |  | note | - - - - - - - - -
label | 97930195-c8e9-5c8f-a4f9-bcb50d6bc1b7 |  | note | Responsibility: SE/PE
checkpoint-status |  |  | checkpoint | 5.4 - Gravity Feed: Inactive Crack Repairs
label | 01625f8e-2a5f-513c-aa57-bdecb1d46b96 |  | note | Frequency: Each active crack
label | 196d0b70-98a1-593f-9d43-d8726db2ed12 |  | note | - - - - - - - - -
label | e3add9b5-ec44-599d-b0ed-7f99a9d2427d |  | note | Acceptance Criteria: Approved procedure to be followed, steps to witness:
label | b99f1ec6-98f6-5d93-b1ab-2bb2d2adc195 |  | note | i. All materials in date and mixed as per the Product TDS;
label | c4006f10-0ff5-551e-90a8-9cdd2e8de996 |  | note | ii. Where required, a water-tight reservoir, to be created with silicone or polyurethane sealant;
label | d736769d-ce83-573c-9510-64cb17a74fe1 |  | note | iii. Epoxy resin to be poured onto the crack and either sufficient amount contained in the reservoir (if used) or worked back and forth by suitable means (such as a broom) until no more material can be absorbed;
label | 6b811510-57d4-5606-925a-3f12a69bad48 |  | note | iv. Excess material and reservoir can be removed as the epoxy resin gels;
label | 790a2181-e9f5-52be-9f52-3068d440746c |  | note | v. Repair to be protected from damage or adverse weather while curing;
label | dafc7e44-7bdc-5c93-944a-4dfe748b5b73 |  | note | vi. Repair to be protected from damage or adverse weather while curing;
label | 210470de-be3b-5c4f-896b-05cae03f0018 |  | note | - - - - - - - - -
label | 748b3e61-14b9-59e1-a197-aebd38574d94 |  | note | Reference Documents: VicRoads Spec. Cl.687.11 (b) CI.687.15 Product TDS
label | 35fbb7d1-24d6-56b1-b480-dd569dcd6c23 |  | note | - - - - - - - - -
label | 2ccdcb27-74c6-52e4-864c-78fa75b2515c |  | note | Inspection / Test Method: Visual
label | 681d9cb0-5493-55e0-801f-d3fba482f2f0 |  | note | - - - - - - - - -
label | b16fef82-4d90-5308-8994-632886dcbe9a |  | note | Record of Conformity: Signed ITP
label | 11238b31-7b18-5ef1-a77d-b313eb65aa99 |  | note | - - - - - - - - -
label | 46cf8c2b-b707-51c9-b263-9477c4215eaa |  | note | IP
label | 13b85f51-c720-5a30-87f2-ff05bee6cae4 |  | note | - - - - - - - - -
label | 1ec70b98-6b4e-5e82-a830-f2f7cdd00241 |  | note | Responsibility: SE/PE
checkpoint-status |  |  | checkpoint | 5.6 - Penetrant Coating Method: Inactive Cracks <0.2mm Width Repairs
label | 1cab4ae4-4805-5566-aa8d-edcbf3d3f712 |  | note | Frequency: Each active crack
label | ceea2b00-15e0-53ce-9ad8-3279cd814f74 |  | note | - - - - - - - - -
label | e3374cf5-4545-5db7-b45c-d09e9b204a9f |  | note | Acceptance Criteria: Approved procedure to be followed, steps to witness:
label | 7f725786-96e1-5adf-bc91-040ea734ef12 |  | note | i. All materials in date and mixed as per the Product TDS;
label | 9e13cfde-ce7c-5394-94b4-075ee15e3dca |  | note | ii. Silane to be applied with an airless sprayer (for penetrant) or brush (for Solid Silane or Silane Crème) , working from low to high areas and approximately 150mm beyond the extent of the crack;
label | 64b4b55b-1c93-5881-985d-e7bf1513ca14 |  | note | iii. Application rates to be as per the TDS for each type of product ensuring wet appearance;
label | 31095e65-81b3-5f2f-ac1c-e35d25315f00 |  | note | iv. Re-coating if required;
label | 519bf71a-7bea-5047-9b71-eb802ac9fc0c |  | note | v. Repair to be protected from damage or adverse weather while curing
label | d854822e-5d1d-5870-bb72-65fcd2c64a15 |  | note | - - - - - - - - -
label | 665d5d82-5b25-527d-a035-6fc01466b6b2 |  | note | Reference Documents: VicRoads Spec. CI.687.15 Product TDS
label | 95134f1b-f633-5046-9e6d-a3da985e92b9 |  | note | - - - - - - - - -
label | d3239843-1a5e-5c47-8f71-840560c6c288 |  | note | Inspection / Test Method: Visual
label | f0042c09-ac64-5845-8539-e96dfcf06ef0 |  | note | - - - - - - - - -
label | 18e2787c-7477-588f-99a0-6d8dbbbee496 |  | note | Record of Conformity: Signed ITP
label | f651fe4f-91e5-5091-af3a-4bbe166a3f02 |  | note | - - - - - - - - -
label | 790df409-5c1e-57a6-893c-da7ecfc4c34e |  | note | IP
label | 662b2668-5808-51bd-ad4d-3e39048340df |  | note | - - - - - - - - -
label | 9788d57d-59fb-5464-9693-235a5c9338b1 |  | note | Responsibility: SE/PE
checkpoint-group |  |  | section | 6 - Post-Construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Curing & Finishing
label | b8a1b361-638a-5725-abd1-890c37f39075 |  | note | Frequency: Each crack
label | e4f10dc8-6497-52ee-b858-bf9545226163 |  | note | - - - - - - - - -
label | df66dae4-79c9-516e-964a-5adeeaab8dec |  | note | Acceptance Criteria: After the repair materials have cured in accordance with the manufacturer's recommendations, any surface seal, nipples/entry ports and repair materials can be removed by suitable means.
label | 62e6b7ea-8842-563b-b72b-c8cc9658a968 |  | note | The surface shall be ground smooth, leaving no traces (indentations or protrusions) of a repair and if the repair location remains exposed, a fairing coat can be applied where not being coated with a pigmented coating system.
label | 272d4641-8adf-5165-ada7-9718d1f032ba |  | note | - - - - - - - - -
label | 189e9e9c-c452-561b-915b-d38ee7c8c06c |  | note | Reference Documents: VicRoads Spec. CI.687.15 Product TDS
label | 810b3efe-f6fb-5980-b402-4a7cd017de0a |  | note | - - - - - - - - -
label | 84aa744c-8495-52fe-9b66-fcdab8031bc9 |  | note | Inspection / Test Method: Visual
label | 5f5834c5-968e-54c0-be42-90748e8c1e65 |  | note | - - - - - - - - -
label | 27660ebe-d854-5c6e-aa4c-737c25b02760 |  | note | Record of Conformity: Signed ITP
label | e04b0414-f772-5cdb-ad0e-bb21ac56203b |  | note | - - - - - - - - -
label | 6c6021c2-b91e-59e3-9de8-095f7edc6c71 |  | note | IP
label | 13cbdde8-5b36-5b13-9872-1cf099b6df92 |  | note | - - - - - - - - -
label | addd4ed2-0ecd-5d64-991f-85d589dd021a |  | note | Responsibility: SE/PE
checkpoint-status |  |  | checkpoint | 6.2 - Repair Verification
label | d5b5627c-5a90-5fda-9de6-41cccf8b2a56 |  | note | Frequency: Each crack
label | 62c6cc90-cd29-55f6-b2b5-dc523a4eab20 |  | note | - - - - - - - - -
label | e0a3a04c-32af-51ef-890b-48d364e3a971 |  | note | Acceptance Criteria: After 7 days minimum, 75mmØ core samples shall be taken to verify cracks are fully sealed.
label | 0a3feee4-c616-5d8c-accb-569b5a9297a0 |  | note | Cores to be located in conjunction with a covermeter to avoid reinforcement and approved by the Nominated Authority.
label | 522c5a57-c71d-59ed-b20c-3639a9a52e8b |  | note | 2 no. cores for the first 25m of crack and an additional 1 no. core sample for each 50m of crack or part thereof.
label | e83233b2-1fb9-5142-84c1-0bb8909f6929 |  | note | Core holes to be filled as per the cementitious repair ITP.
label | f4a7c232-18ae-5361-8b9c-53cb940a54d9 |  | note | Attach: Photographs of Core Samples
label | e016bfe1-4535-58ae-9d7e-837cb825204f |  | note | Complete: Structural Concrete Cementitious Repair ITP
label | 23c73a56-2131-5b50-a73f-64441dc45a47 |  | note | - - - - - - - - -
label | d5f5b193-e19c-5b72-9d3f-e3debcd60227 |  | note | Reference Documents: VicRoads Spec. CI.687.16
label | 7420b103-f385-554d-8e64-f82aedc0f686 |  | note | - - - - - - - - -
label | c13bab74-f9af-5d18-b92c-c9d0b98c804c |  | note | Inspection / Test Method: Visual
label | 9a7e3f2f-2785-5f53-a6ed-a2042337d2fa |  | note | - - - - - - - - -
label | bc52591f-8320-5c7b-858d-c6e1ab51c9ba |  | note | Record of Conformity: Signed ITP
label | 7f5f7a64-522d-55d8-8722-4c42e1bd59fe |  | note | - - - - - - - - -
label | b6b96691-2d7a-534a-afea-6719f6103632 |  | note | WP
label | 1177e4ca-371e-5a20-b394-95df6344300a |  | note | - - - - - - - - -
label | 0c4eedac-e5ba-5358-8454-adc9f11e3ef5 |  | note | Responsibility: SE/PE and Superintendent
checkpoint-status |  |  | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | 432d53ca-9e64-5817-bafa-55fb9256c1f4 |  | note | Frequency: Once, prior to closure of this lot / element / Work area
label | e7feed32-47f5-5908-8749-1d890e65838d |  | note | - - - - - - - - -
label | d6afd402-c62d-5b85-b305-db163ed35ff2 |  | note | Acceptance Criteria: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | e38feaf7-8b8b-5f45-9bec-098f1b1fb716 |  | note | - - - - - - - - -
label | e2743d6f-22a5-5c0e-b52c-b713713ca747 |  | note | Reference Documents: FH Quality Management Plan
label | dd3edbec-dec5-53ad-a7c4-c62ff96b4663 |  | note | - - - - - - - - -
label | 90d5d9ca-2c53-5621-8ae4-2037f1db5365 |  | note | Inspection / Test Method: Document Review
label | 70ddf1b8-6654-5f2c-8d4a-5eaea8dacd61 |  | note | - - - - - - - - -
label | 80c3e47e-5dd4-5d56-be7c-16a3f88ca92c |  | note | Record of Conformity: Signed ITP
label | 5ec8ba80-92e4-5ea5-9b0e-ff1c733999f9 |  | note | - - - - - - - - -
label | dcd528f3-a07f-55bb-954e-0e37aa6333eb |  | note | HP*
label | a9d11939-34a6-5c16-881b-c9fd07455df4 |  | note | - - - - - - - - -
label | 75c74614-49a5-5b4f-9379-6d04d496355d |  | note | Responsibility: SE/PE
checkpoint-status |  |  | checkpoint | Final Inspection
label | 491a9a47-5f7f-57d9-9b6b-b50b7156bd9a |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | d5f7cdc9-f466-5e54-8b00-07bd5ef9a77f |  | textbox | Print Name:
text | beedb7d8-63d3-5627-8f0d-6869d95feccb |  | textbox | Position:
date | dbb8bab7-b700-5cd5-a411-268e28298c42 |  | date | Date:
date | fbe4d0b5-75af-5e9d-825c-61ce1fd6a0d6 |  | date | Work Completed On
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification.
select | e7fee18e-88cb-58ad-83f4-d80f547ab559 |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | e382dc0b-5816-5a76-8efa-69f34b39d489 |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | abbb48a0-23b1-5a9a-8b74-ed3e9916121e |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | 1a494213-678a-5099-990a-0b607abd3191 |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | 23c55cfd-e65d-52f2-a722-014f8dfea322 |  | textbox | Other:
select | d5e0df85-67d3-53f1-89ef-dea6374e12c8 |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | 2342973a-70df-56b1-b236-d2acce2a83b0 |  | date | Lot Closed On
text | 0421b078-8133-5708-917b-f52064ff0560 |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-054-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | 3e3afbb9-cb21-409a-857e-8dbc0fdcc277
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | b0da2185-bdcc-5406-b65c-2a9a08619feb |  | date | Lot Created On
date | 251dd7f6-054a-5006-83d7-c5f007855219 |  | date | Lot Opened On
date | 865390b9-f42b-5889-a963-77209665ce9d |  | date | Work Commenced On
select | 7859a77a-6a4d-59a8-a737-b781a81b6666 |  | dropdown | Lot Type | CIL - Civil
text | 118c3ad1-b6c8-5464-b8b0-e984c3c5f7bb |  | textbox | From and To Chainage
select | 5a19d8c1-1f67-5ecd-92e5-e187ff01571f |  | dropdown | Construction Element | PAVI - Paving
select | b19a4823-0e84-50cd-a2e4-78d9c0ee1595 |  | dropdown | Activity | COHS - Concrete Hard Stand, COII - Concrete Infill/Island, CONB - Concrete Bay, DDAT - DDA Tactile, FOOT - Footpath, SHUP - Shared User Path
select | 9986da1f-9260-500f-a17a-6fdd731c0685 |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | 6e6f60b0-ae46-5371-af8e-3db43ce9c2e3 |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | 83f43ac7-2377-5d74-bce5-34e7932d3581 |  | textbox | Engineer Responsible
text | ec53ecdc-5a36-5d23-bf1a-4ad7a5381385 |  | textbox | comments
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Check that current revision drawings are being used
label | 0a8de265-3b7f-5303-9ca0-2e42db0bc759 |  | note | Frequency - Prior to Commencing
label | d01d2011-9369-596e-951b-f3474f5d0241 |  | note | - - - - - - - - -
label | df9adb09-de54-5d9b-83cf-d894052a65ab |  | note | Acceptance Criteria - Issued For Construction (IFC) and latest available revision used
label | 31348f6a-0fa7-5546-a4c6-b23e41bbb2ca |  | note | - - - - - - - - -
label | 03439f9a-691a-5c27-9465-6cf154226742 |  | note | Reference Documents - Project Drawings / Drawing Register
label | 04513cbc-7c81-570a-8465-272b334c2ae1 |  | note | - - - - - - - - -
label | 2e779324-b3c7-56f2-b02b-79e1506f5824 |  | note | Inspection / Test Method - Document review
label | 343b4295-badb-5d7a-8977-01be6a7a734a |  | note | - - - - - - - - -
label | 9f71bfff-d6f4-5916-be81-2433ee09928b |  | note | Record of conformity - Latest Revision Drawings
label | 9c697f71-83c9-53da-80d6-e03ac358d395 |  | note | - - - - - - - - -
label | 3feec88a-ec7b-557d-9da2-4df1753e32ca |  | note | AP
label | ffafe532-fd2f-5333-bc78-625eeb405c2a |  | note | - - - - - - - - -
label | cbeb5e73-723f-5cce-9c84-6d718e6c507c |  | note | Responsibility - Site Engineer / Site Foreman
label | 0d3c4c9a-fb3a-592b-a899-c0609a49fed1 |  | note | - - - - - - - - -
date | 735c118b-712e-5ecd-b3fe-6f34af54ba30 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Bedding Material / Base Layer
label | 8017d247-ded8-5d40-a512-a1a176181793 |  | note | Frequency - Once, for each mix design, prior to placement of material
label | 6cfb8b65-3d67-526f-aa1f-43b7269e2d88 |  | note | - - - - - - - - -
label | c357f0d0-a44d-5906-a149-cf3fe06f2018 |  | note | Acceptance Criteria - 20mm Class 3 bedding material conforms to specified requirements applicable to the class of product as detailed on the drawings.
label | 707848d2-7bec-564e-8f66-73bf30780896 |  | note | Material is registered with VicRoads in accordance with Code of Practice RC500.02
text | 93f779a8-6f94-5418-ad9a-f648a21d15f7 |  | textbox | Enter: Teambinder Material Approval number
label | eacdce78-576a-5754-a370-4d134cbb7ba4 |  | note | - - - - - - - - -
label | c1ded80d-3243-5ad6-8b44-11b2075cac19 |  | note | Reference Documents - IFC Drawings, 703.21, 812.04
label | 1059ce00-f4c7-5e78-9d58-b5be8014b3cc |  | note | - - - - - - - - -
label | a6a1aa2c-6e23-5105-84c9-d1320e9bf6b6 |  | note | Inspection / Test Method - Document Review
label | 3631abe8-d428-51a7-be50-98f7bfdd3a63 |  | note | - - - - - - - - -
label | 098f1519-6a82-575f-9005-f314dd32bbc7 |  | note | Record of conformity - Teambinder reference number
label | 6578fa45-a901-5eb4-a658-c2d79e3b17f9 |  | note | - - - - - - - - -
label | bc9a050f-0ca3-5043-aa97-fec76affd48f |  | note | IP
label | 9d280418-ec3e-5ad7-a941-549cd9356358 |  | note | - - - - - - - - -
label | 01ca8965-51f9-5343-917e-de4742dc45bd |  | note | Responsibility - Site Engineer. Superintendent
label | 2b3ce1f3-1ad7-58f1-8bd0-a207590be714 |  | note | - - - - - - - - -
date | b52fb808-a386-5acf-ba89-7ec78094c092 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Concrete Mix
label | c4005100-645f-5932-84d6-7bdf1e9e2712 |  | note | Frequency - Once, for each mix design, prior to placement of concrete
label | e51e8cfb-2016-5ef2-bc44-bf4d5a3ea7b4 |  | note | - - - - - - - - -
label | 1c3cfafb-15f7-5ce9-bcdd-2f82dd89b618 |  | note | Acceptance Criteria - Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings.
label | 5400a84c-e99c-5c6e-b67f-fb3fdfb939eb |  | note | Paving concrete mix conforms to AS1379. SUP concrete mix is registered with VicRoads.
label | e8c2bfce-d522-5944-9a4d-f16227b9dec9 |  | note | No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
label | 043d150b-20bc-565e-a89e-87e09eac960e |  | note | Concrete mix designs shall remain valid for 12 months from the date of registration, unless constituent materials and material proportions cease to comply with the specified requirements.
text | a62a236f-9d9c-5d66-acb8-5ce9cb386041 |  | textbox | Enter: Teambinder Material Approval number
label | f9d54e9e-90d8-59cc-aa73-b8676c526740 |  | note | - - - - - - - - -
label | e76879f8-2aa6-532e-a944-86e16fdf7e27 |  | note | Reference Documents - IFC Drawings, 703.05 (a), 703.07
label | 8e8c7d4d-48fd-520d-a618-8ce8f8667901 |  | note | - - - - - - - - -
label | 3cea36a2-bccd-59f8-b569-78ac0f35aacf |  | note | Inspection / Test Method - Document Review
label | 94fc7b0c-241b-5617-9024-51387be9f24a |  | note | - - - - - - - - -
label | 7ec08238-b193-5e09-8b28-f42fb6d7ca03 |  | note | Record of conformity - Teambinder reference number
label | ade8a154-c73a-58b9-af15-1dddd6c0bc18 |  | note | - - - - - - - - -
label | 2aa28823-5d25-5a65-b211-8827d95d540b |  | note | IP
label | 99df415e-48d0-5531-9f80-8b3278694da1 |  | note | - - - - - - - - -
label | 70819973-fdcb-5a94-b5e8-0f9bca4f0853 |  | note | Responsibility - Site Engineer
label | 847f48dd-0361-534f-a87c-1af0c5f383a5 |  | note | - - - - - - - - -
date | 62c6aa91-07ea-555d-9560-a22ea5551351 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 - Evaporative Retardant
label | da41ded5-e34b-5f1d-a286-27d42de5a73c |  | note | Frequency - Once, for each product, prior to placement of concrete
label | b541ee2d-397d-5e47-bc14-0e926691d927 |  | note | - - - - - - - - -
label | bacd79cc-7a39-5f54-b208-c8a7354a61f4 |  | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
text | 9b99490b-daf2-58d2-b788-cd77577ae34a |  | textbox | Enter: Teambinder Material Approval number
label | e1366c16-30f2-5dbc-99ef-40d900effca2 |  | note | - - - - - - - - -
label | 7c33399a-ceba-5c2e-aede-eb69e1aca7d0 |  | note | Reference Documents - 703.09
label | 51467fb3-c880-55e5-bc8d-a8b40c4f5027 |  | note | - - - - - - - - -
label | 019a5252-51a6-5dce-b82c-7f06f4a31b5c |  | note | Inspection / Test Method - Document Review
label | 87c9c3fa-593f-5a23-9b1c-2b2fb65ba769 |  | note | - - - - - - - - -
label | dadc9120-4c7c-5ef6-87f5-fe6d893df66a |  | note | Record of conformity - Teambinder reference number
label | a38218ef-763c-553e-9516-4dfa25db5ea6 |  | note | - - - - - - - - -
label | fe493841-4321-507d-a642-664bfe63e843 |  | note | IP
label | f9da8a4f-b7f6-5fa4-878a-223c41354f2c |  | note | - - - - - - - - -
label | 95e3d1bb-320c-55c5-8957-014b49e73c7c |  | note | Responsibility - Site Engineer
label | 0e6b7a87-aee2-5c45-8fec-388471c81232 |  | note | - - - - - - - - -
date | b71b1150-a544-5f7e-a4fb-2f8f1743ac9e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 - Curing Compound
label | f1141184-5370-57eb-a05c-098ceb86ff03 |  | note | Frequency - Once, for each product, prior to placement of concrete
label | 78b41f12-12ac-591f-8fda-518309f950ab |  | note | - - - - - - - - -
label | 36b4d1cd-4de2-59e0-ae4a-628d2ef86420 |  | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue,
label | 3239ca00-c550-52aa-a473-c48e0f6fb0a9 |  | note | to be submitted for review to the Nominated Authority.
text | d5efb84f-a817-59a6-823e-ea50f9c0dce0 |  | textbox | Enter: Teambinder Material Approval number
label | 038d2c0a-a43e-55d1-b158-1b8b6fa5fda6 |  | note | - - - - - - - - -
label | 4e93fc38-57a1-5ffb-88d3-a1371df574ff |  | note | Reference Documents - 703.10 (a)
label | 8665172d-6535-5349-8e54-6b11705c26e2 |  | note | - - - - - - - - -
label | 422fb35b-8ec1-5d11-b647-54cf401ef6ec |  | note | Inspection / Test Method - Document Review
label | d493ae0d-3bb0-5dd6-8ff1-06dd29d288c0 |  | note | - - - - - - - - -
label | fa945912-eb25-5007-aee4-e49b940202ea |  | note | Record of conformity - Teambinder reference number
label | e7da8ef2-38bf-52b6-9031-ed9aaa80ffdb |  | note | - - - - - - - - -
label | 01f99143-8c40-545d-91c4-e28f2b14a1f8 |  | note | IP
label | 9bc26fef-dfac-52f6-a6d3-5b3993511b83 |  | note | - - - - - - - - -
label | f8446c1d-3941-522d-966a-24898745c905 |  | note | Responsibility - Site Engineer
label | 055ca730-d4a8-52f3-8484-0409cc8e4c5b |  | note | - - - - - - - - -
date | 954b732b-7087-54fe-b2b3-886ada7ac7f6 |  | date | Date Completed:
checkpoint-group |  |  | section | 2 - Construction Works
checkpoint-status |  |  | checkpoint | 2.1 - Setting Out
label | e4f2bbf1-24cf-54f8-b399-617e3a8728ad |  | note | Frequency - Prior to Commencing Work
label | 12810e06-3d0c-5404-adc2-e797ec3bfd7b |  | note | - - - - - - - - -
label | 06e690e6-6204-5af9-8898-80a8b1329d85 |  | note | Acceptance Criteria - The Superintendent will review and confirm the set out.
label | 50dee203-eb5f-56bb-a19b-628f32709763 |  | note | The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | d66f1200-bd75-5bf5-9240-f5489151aefb |  | note | - - - - - - - - -
label | bfc2cba0-4121-5763-95fc-331fa30b8de4 |  | note | Reference Documents - VicRoads Spec Cl.703.17
label | ac6e3484-8dd1-5a2e-9bd7-cf135d71f980 |  | note | - - - - - - - - -
label | a7197bde-6715-56ca-bbcc-d70a25bec562 |  | note | Inspection / Test Method - Site inspection
label | 32eee2e3-f5be-5fb1-9f02-9c5ad02f8056 |  | note | - - - - - - - - -
label | 204e5e1b-ebb9-515a-b235-5f5d810d7ff2 |  | note | Record of conformity - CONQA Hold Point
label | 5cfcc07f-2e8f-5223-a325-feaeda88fbd3 |  | note | - - - - - - - - -
label | b4e54627-6942-573e-a315-dd956046a8c8 |  | note | HP
label | 2533a500-ac40-5cff-ad4e-68c1cee724f4 |  | note | - - - - - - - - -
label | 973622bc-59e7-5345-96bb-5ff9ac6efa9f |  | note | Responsibility - Project Engineer, Superintendent & Surveyor
label | 9d0565a8-df25-5ace-a550-71e508296602 |  | note | - - - - - - - - -
date | ec9e9dcd-fecb-5cf8-bf85-824d91b5a9fd |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Temporary Drainage Provisions (if required)
label | a10c6351-54c7-5150-ba10-c38dbaf864b4 |  | note | Frequency - Prior to Commencing
label | 2842195c-335d-5ef3-b6c3-35c5b53d6ff8 |  | note | - - - - - - - - -
label | aa7768bf-5b4a-57e3-a7b8-22d74744e84d |  | note | Acceptance Criteria - Before obstructing any waterway, channel or culvert, the
label | 5b7c02a9-3f45-5ce9-9311-f890bc95f6b9 |  | note | Contractor shall make appropriate provision for its temporary diversion, and obtain prior written approval from the relevant waterway authority.
label | 668ec615-59d3-59c7-8cac-49c6aa50b142 |  | note | The Contractor shall make provision for the safe discharge of drainage and stormwater at all times during construction.
label | 0d44e10d-f998-5a64-b3c2-7d7f4d34b83c |  | note | - - - - - - - - -
label | 1729a16c-be79-501c-94de-b70dce099f8c |  | note | Reference Documents - IFC Drawings, VicRoads Spec Cl.703.18
label | 09e2fc1e-06d0-52cc-a880-052460fabbe1 |  | note | - - - - - - - - -
label | e5aea98a-b6ed-5c00-9f5e-f10a9ab0d579 |  | note | Inspection / Test Method - Site Inspection
label | 83428047-2374-5b44-8007-7ee7387d235d |  | note | - - - - - - - - -
label | 10496ed7-dc2b-5ef3-9720-54ff913923d5 |  | note | Record of conformity - Written approval from relevant waterway authority. ITP Signed
label | dfe7b7bb-ffae-5159-8b8e-33b9da9994bf |  | note | - - - - - - - - -
label | d58e88f1-af39-5485-90f2-8a2379c1cb3f |  | note | AP
label | 9b506653-8dfe-55ca-a4f9-41c2be04c95d |  | note | - - - - - - - - -
label | 1f75ac71-3de7-5604-b728-390ea6dfc3a6 |  | note | Responsibility - Supervisor / Site Engineer
label | f91a44a2-ccb2-53b8-8d87-3e498fe018f8 |  | note | - - - - - - - - -
date | 01a1e625-9f54-5c82-b3af-151a32080c09 |  | date | Date Completed:
label | 52ea5409-183c-567c-b78d-dedca2f82d16 |  | note | - - - - - - - - -
checkpoint-status |  |  | checkpoint | 2.3 - Pavement Thickness Increases for Crossings
label | bc43df87-420a-5814-bf73-8f4735cf8494 |  | note | - - - - - - - - -
label | 36b30e98-54e6-55f2-954f-d41856be671d |  | note | Frequency - Prior to Commencing
label | cb804fa7-44ae-52da-9644-b42f2cca8025 |  | note | - - - - - - - - -
label | a71830b2-a668-5b0a-8551-4a6cfc2dae77 |  | note | Acceptance Criteria - Where applicable, excavation to allow for increase in the bedding and slab thicknesses at:
label | 43830fa5-cd2e-545d-a42e-1f1e952eb4eb |  | note | i. Pram crossings
label | 16bde5c5-2837-554f-9ee7-306e8fb138a2 |  | note | ii. Vehicle crossings (residential and/or commercial)
label | f3880ed1-b40f-5163-95f1-9a422c0b8d20 |  | note | iii. Established / existing mature trees
label | a1f0b238-2c73-54c5-9319-27383c9318a4 |  | note | Consult the Relevant Council drawings for dimensional tolerances for thicknesses, grades and ramp lengths.
label | 5bb5f747-57eb-5ef6-8180-c26c444545eb |  | note | - - - - - - - - -
label | 45bf4654-a002-51ca-8401-53931e4f80b2 |  | note | Reference Documents - IFC Drawings, VicRoads Spec, 703.16, 703.24, Relevant Council Drawings
label | 5bde7cee-d9a9-5574-9481-f62ab6ba53dd |  | note | - - - - - - - - -
label | 82f499cd-8b9b-5b09-b939-5b18bec2f07f |  | note | Inspection / Test Method - Site Inspection
label | bd4dca1a-71af-5ffc-ab48-4c154889face |  | note | - - - - - - - - -
label | 2d2e15df-251d-564b-ac7f-f4f6bac95079 |  | note | Record of conformity - ITP Signed
label | 55959c2a-98ad-5462-8143-a4d285b10c58 |  | note | - - - - - - - - -
label | 5ad419e0-31d5-541a-9925-9ed96ef7664e |  | note | IP
label | d4d74894-7ef8-5504-a9be-950cf777ae01 |  | note | - - - - - - - - -
label | 970a1b66-9217-53f5-8f63-727f0a28e989 |  | note | Responsibility - Superintendent/ Supervisor / Site Engineer
date | 22a348b5-b832-56ec-8e8b-7dbd686dc19c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Bedding Preparation
label | c2dbc52d-d468-5adb-8acb-5cbf500a0c32 |  | note | Frequency - Each Lot
label | 34563cd0-90dd-53b3-9b5c-04659b020895 |  | note | - - - - - - - - -
label | b725902e-5386-558b-b7e0-f6b162987f8b |  | note | Acceptance Criteria - All bedding material shall be as specified on design drawings.
label | 14e4545a-036a-5a53-9e92-d64fda533ec4 |  | note | Where not specified, bedding material used for cast in place concrete paving works shall be compacted size 20 mm Class 3 or Class 4 crushed rock or
label | 996e1ff1-145c-5d34-8697-6aeeb0a360e4 |  | note | Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
label | 919c7fb6-41f9-52f0-bf86-55295d2c09b6 |  | note | Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface.
label | 46568274-4fbd-58c8-b6c0-e2805b4fe1da |  | note | - - - - - - - - -
label | ad86f034-775f-5028-8862-05bb76f9fac0 |  | note | Reference Documents - VicRoads Spec, Cl.703.21, 812, 820, IFC Drawings
label | 602f1346-fa2d-588f-a945-a33cadd34561 |  | note | - - - - - - - - -
label | 619672a0-d3ad-5708-a8a9-635c9b278672 |  | note | Inspection / Test Method - Site Inspection
label | 4a3fb8e9-fca7-5001-8e85-ecff8916c03a |  | note | - - - - - - - - -
label | 66ed89ad-a6e5-53ff-8393-be90478a26d0 |  | note | Record of conformity - ITP Signed
label | 3649c2a3-d514-5a54-b502-ef93c768a382 |  | note | - - - - - - - - -
label | 4885048c-d564-5e22-adb9-dfe3c7590d46 |  | note | IP
label | c446c3ca-9def-5e97-abac-1ba4ff4ba11b |  | note | - - - - - - - - -
label | 3128d14b-518c-5c07-9648-f437db6953f2 |  | note | Responsibility - Supervisor / Site Engineer
date | 9a9c3149-c005-569e-a5d6-c469ee44f1ce |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - Formwork
label | 25ca0c3d-2287-5b2b-902b-e8305e3a7049 |  | note | Frequency - Prior to Commencing
label | 3d50063d-ae23-50bb-8f97-58a69d1080c1 |  | note | - - - - - - - - -
label | b0b06027-2c40-57a9-9e06-3c9f51693e39 |  | note | Acceptance Criteria - Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
label | 2f695878-05f2-59d3-a6d3-660344a92c3b |  | note | - - - - - - - - -
label | 2611d218-cacf-5822-b298-bfb7412dde65 |  | note | Reference Documents - VicRoads Spec Cl.703.12
label | 6b364d9d-c023-518b-b6a3-925ae74e9955 |  | note | - - - - - - - - -
label | f016d536-5966-56ed-9972-265231850bb2 |  | note | Inspection / Test Method - Site Inspection
label | ed206b9e-f4fc-5762-95b4-f85529ac9a2a |  | note | - - - - - - - - -
label | 0579ae34-6fc0-54a7-8a61-140f8e0d1b0e |  | note | Record of conformity - ITP Signed
label | afb2a352-d119-59f3-b4f4-e1a6f4be8c9b |  | note | - - - - - - - - -
label | 5d99b370-1048-5cec-8434-9670e8a040c4 |  | note | IP
label | ed0dbdef-cb66-5322-a486-ab2cff5d4cee |  | note | - - - - - - - - -
label | ff62d2d2-9d16-57dc-b732-45a0c34e07fe |  | note | Responsibility - Supervisor / Site Engineer
date | e7ff4d62-f4c5-5ea0-94bf-79b04c23a24f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 - Steel Reinforcement
label | 9032f35d-6fff-52b3-9047-1eb6d0fbfa37 |  | note | Frequency - Prior to Commencing
label | bb976308-7aa5-5e61-8eb4-f043212637d4 |  | note | - - - - - - - - -
label | e4ca29ed-3e90-513d-85d8-41dbbd01a0c1 |  | note | Acceptance Criteria - Steel reinforcement shall be placed in accordance with drawings and AS/NZS 4671.
label | 9a51cc91-b53a-5df0-b63a-2c24de66f755 |  | note | If not specified, mesh shall be placed as per VicRoads Spec Cl. 703.16.
label | 3446331e-af5b-5bf0-9fd9-5d97fad2ee0a |  | note | The minimum cover of any steel reinforcement to the nearest concrete surface shall be 50 mm unless shown on the drawings.
label | eaba4a02-06f1-5ad6-aec7-9e46e7aa86c5 |  | note | Reinforcement shall be supported using either concrete or plastic chairs.
label | caacb467-c042-590e-a17c-ee55e7f7eb81 |  | note | - - - - - - - - -
label | 3cc7cc8d-39bf-5e0d-b389-d30fe6686ecf |  | note | Reference Documents - VicRoads Spec Cl.703.13 & Cl.703.13, AS/NZS 4671
label | bb7efa89-9b6f-56f1-a99a-25dcb1c3757c |  | note | - - - - - - - - -
label | 93a3a339-e165-5a6f-8ac4-6aec02fea70b |  | note | Inspection / Test Method - Site Inspection
label | 4fe77b0d-8610-52bc-bc8a-d22003fdb5cc |  | note | - - - - - - - - -
label | 55aaee0a-1878-5a3f-bf82-7ecd0ceba65a |  | note | Record of conformity - ITP Signed
label | d4475cea-41a0-582d-a529-c748357f4cfe |  | note | - - - - - - - - -
label | 0dbeb828-62ef-58d6-b178-36e8af7b5c3f |  | note | IP
label | 07eed029-c220-5735-a6a4-72f44eee7aee |  | note | - - - - - - - - -
label | eec689db-96b1-54e9-9867-f2ab8d281244 |  | note | Responsibility - Supervisor / Site Engineer
label | 925942a9-2bab-5f32-b835-0e7bf83f1ef4 |  | note | - - - - - - - - -
date | 74a954b4-6b0d-5659-85e6-92618f29300f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 - Pre-pour inspection
label | 16c34612-da84-5f54-b578-0109ef8f2b88 |  | note | Frequency - Each Lot
label | 66bfd63f-0958-5a0c-b445-340573f93175 |  | note | - - - - - - - - -
label | 0b61bbb0-836c-52b3-a5a7-dd7d98b0bc5c |  | note | Acceptance Criteria - Inspection to ensure that forms, reinforcement dowels and other embedments conform to the requirements of the specifications and drawings.
label | 8f45390a-18e6-574f-bead-9e12baf559f7 |  | note | - - - - - - - - -
label | 84eafb04-9ba3-508a-9201-6e1f28b5afb6 |  | note | Reference Documents - VicRoads Spec Cl.703.05, Cl.703.09, Cl.610.17 (a)(b) (c)(d), AS 1379
label | 3816d0e6-ab56-55ee-bdf2-ac1ae86a14a8 |  | note | - - - - - - - - -
label | fb575314-a2c1-52cd-9fcf-c7b7bf6fd43a |  | note | Inspection / Test Method - Site Inspection
label | a74f9bdb-ae08-51bf-83fb-f7f1520efd45 |  | note | - - - - - - - - -
label | b28e9e84-6a91-51df-8e89-99ab441b27f1 |  | note | Record of conformity - ITP Signed
label | 2b315e0b-c810-5488-ab3b-bafa8e60c1e2 |  | note | - - - - - - - - -
label | c3228b97-ad7b-5ed2-a52f-f26917a6db06 |  | note | HP
label | 4f621e3d-46e7-5422-ba9b-0a14576770cb |  | note | - - - - - - - - -
label | 529252cd-9bec-5da5-ac4e-435f08f84b56 |  | note | Responsibility - Project Engineer, Superintendent & Surveyor
date | c109249a-51df-58c8-a251-5f700c4f5b82 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.8 - Concrete Testing
label | a6d67c9a-867c-592d-8b81-c108d81d32eb |  | note | Frequency - Each Lot
label | 9d28c679-9ead-5644-9754-82877eeff742 |  | note | - - - - - - - - -
label | 2082627f-1d09-504b-a49d-0ccd9ebe68ef |  | note | Acceptance Criteria - Concrete Testing Frequency: 0m³ to 50m³ = 1 sample
label | cdd8dcb1-f497-5c55-8ce5-81d7e7c5e42a |  | note | Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum.
label | c06d3eff-8403-5f78-9fa9-5a899a5ff81b |  | note | Compressive strength cylinders = 2 no. 28 day strength.
label | 080572a4-35c2-5c88-8ef2-4c5ea6be7256 |  | note | Slump Testing Tolerances:
label | 97be1011-d6bc-585c-993b-a8dd1e293432 |  | note | <60mm = ±10mm
label | aac1fea8-f20b-5bcf-968e-7309026cf908 |  | note | ≥60mm to ≤80mm = ±15mm
label | a956f123-25a4-51fd-97d1-d4a19138cec9 |  | note | >80mm to ≤110mm = ±20mm
label | 10051e93-0df1-5943-bdea-891ca916c51b |  | note | >110mm to ≤150mm = ±30mm
label | db782e60-b52d-5809-82de-89b7140c7dcf |  | note | >150mm = ±40mm
label | 77a506b6-e0b3-5493-962b-6889d2ea6abb |  | note | - - - - - - - - -
label | fa8ce1b6-8125-5072-8f07-a40721641ca0 |  | note | Reference Documents - VicRoads Spec, 703.11
label | 6eb82d2c-3c14-5cae-8845-e761ec5d5ec5 |  | note | - - - - - - - - -
label | 0dcb4cf9-a5e8-563c-a4cc-bf1ff8f5d6ee |  | note | Inspection / Test Method - Site Inspection
label | 4b6e8c8b-4f22-5912-b121-f906d5dbf98c |  | note | - - - - - - - - -
label | 14a347f4-7b91-5930-98cc-660e43a6dd98 |  | note | Record of conformity - Concrete Pour Record, ITP Signed
label | b93ba8f2-0f51-59a9-8cdf-f81572bcf422 |  | note | - - - - - - - - -
label | 391f96fe-8b70-56a6-aef0-84e5cf494238 |  | note | IP
label | 3bf655a5-9fc0-5eef-aa1c-5f022c96376b |  | note | - - - - - - - - -
label | f529ba51-653c-5e05-8c9f-de57322aa577 |  | note | Responsibility - Supervisor / Site Engineer
date | 582fd0c1-38b2-51e3-ae8b-88af0d951f8f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.12 - Curing
label | ac323fe4-3982-51b0-b509-d0f591dcf81a |  | note | Frequency - Each Lot
label | b642360a-a72e-59aa-8f68-5a0440051abf |  | note | - - - - - - - - -
label | a5f4ecdc-0aeb-5a37-99db-2974abc915a8 |  | note | Acceptance Criteria - The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed and
label | 462b0ce6-e341-5023-b1a0-bc1cdf3523c9 |  | note | shall continue uninterrupted for a period of not less than 7 days after placing the concrete
label | 2b75b0bb-b729-5b23-9cb1-3350f2bf7fca |  | note | Concrete shall be cured either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these
label | de9724e1-3850-58a1-95bc-d75a66b7cb50 |  | note | - - - - - - - - -
label | 35908968-eeb8-5fab-bc53-10ce594a4f4f |  | note | Reference Documents - VicRoads Spec Cl. 703.10
label | f19d01b5-aca7-51ab-bea5-6282e36e74c5 |  | note | - - - - - - - - -
label | 4674374d-515c-5157-afb0-9f603af25055 |  | note | Inspection / Test Method - Site Inspection
label | 6a5944da-a1d3-5973-84b2-18f6aaba74e5 |  | note | - - - - - - - - -
label | ce91a78a-359c-5f93-8413-9961193d4f52 |  | note | Record of conformity - ITP Signed
label | 99f41e27-7300-5f35-9db9-93ec91af9310 |  | note | - - - - - - - - -
label | c31899e2-e5b1-5059-9e4c-c2f4af6c03d0 |  | note | IP
label | 204c6e18-1890-588f-9047-a151291b5831 |  | note | - - - - - - - - -
label | 6e8201f0-58a2-564c-8791-b965edecc743 |  | note | Responsibility - Supervisor / Site Engineer
date | 1c36284b-e0fb-5f13-859e-69c8c5e96509 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.13 - Tolerances
label | 65910317-8f5c-5293-a3fa-f6adbe28b24f |  | note | Frequency - Each Lot
label | 1f16c1b1-e23a-5fbe-987b-65a78a18a311 |  | note | - - - - - - - - -
label | d413a169-7bdf-5e07-8158-9dcc48778531 |  | note | Acceptance Criteria - Concrete paving to match existing fixtures (e.g. pit covers, edgings and vehicle crossings) within 5mm. Deviation of finished work shall not exceed;
label | 4457ee09-493e-5ba6-bc9a-df09dc81b5d9 |  | note | 10mm from line or level; or 5mm from a 3m straightedge for curves and shaped areas.
label | c9382095-35b0-5c6d-842b-e8df7488ba4d |  | note | Deviation of section dimensions shall not exceed 5mm (except for overall width); 25mm for the overall width; and +/- 3mm for dimensions less than 25mm.
label | 6283d217-3fe1-5cd6-ace2-13bdec61de64 |  | note | - - - - - - - - -
label | b426485f-2c84-5516-91d2-85fb8ba801ad |  | note | Reference Documents - VicRoads Spec. Cl 703.15
label | 95232fc2-dd96-53bd-9e1e-3f26c0a231a8 |  | note | - - - - - - - - -
label | 42364d38-6143-5390-bd35-de64ba236476 |  | note | Inspection / Test Method - Site Inspection
label | ec483153-951c-57a4-af7d-2f07699d587d |  | note | - - - - - - - - -
label | 8bf5b0e4-a01f-5b2c-bc78-7488490c702d |  | note | Record of conformity - ITP Signed
label | 0e14d333-0238-525e-8010-b90f45549796 |  | note | - - - - - - - - -
label | 2eef51cb-8126-51ef-b993-eba7326a59bd |  | note | IP
label | 00f484b0-60c5-54cd-aec3-6881fe0b72dd |  | note | - - - - - - - - -
label | dc0d7e44-17bc-5e9e-a1d9-99f3aebd54fd |  | note | Responsibility - Supervisor / Site Engineer
date | 274a0c93-38ca-555e-a70e-1d76bd39a587 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.16 - Joints
label | 0005ad43-4996-5f54-9fe1-70a66a233475 |  | note | Frequency - Each Lot
label | a44dd2f7-0c6d-5d4a-a1c0-255d9fef968d |  | note | - - - - - - - - -
label | 69b2401f-0ffb-5c09-a7df-2d747bde5ea9 |  | note | Acceptance Criteria - Expansion Joints: shall be placed at intervals as specified by the drawings.
label | 63fc2dfd-b6ab-5b3e-a62f-482526f6fcf3 |  | note | Control Joints: at least 25% of the paving thickness deep and 5 mm wide shall be formed with a cutting tool at
label | 6515a22b-b7e6-5062-9ef9-ce84e8a935df |  | note | 2.5 m intervals along the full width of footpaths, other surfacings and shared use paths.
label | aad1161b-d850-5001-acf1-3b94fc4a501d |  | note | Between Concrete Paving and Shared Use Path: Except for medians <2.0m wide, bonding between the concrete paving or shared use path and
label | d3575329-ffb1-5221-b281-a927ede69d97 |  | note | the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt (ableflex).
label | 9c88dc6d-e726-58d2-a2c2-0346bb650fe2 |  | note | - - - - - - - - -
label | defec39f-91f9-5adf-b456-e014be6b0552 |  | note | Reference Documents - VicRoads Spec Cl. 703.26 (b)
label | ddb5825d-0804-5115-a298-bf8d23896ae5 |  | note | - - - - - - - - -
label | 74f3fe09-6455-5174-a27b-a7f5867ec5b7 |  | note | Inspection / Test Method - Site Inspection
label | 27b61dc3-fa6c-5afc-bc1c-01f90effcaf8 |  | note | - - - - - - - - -
label | 4e2da9c1-b43e-5280-b3a9-48459fa94650 |  | note | Record of conformity - ITP Signed
label | 27ec4978-113a-599d-997c-2ddd226d20fd |  | note | - - - - - - - - -
label | b79e66bd-2754-5af8-852f-4b2ced869552 |  | note | IP
label | d6adc45b-55ac-5619-a1de-b6a5da3bb2ba |  | note | - - - - - - - - -
label | ac2e10ae-7aeb-53dc-8020-4d8b980938ba |  | note | Responsibility - Supervisor / Site Engineer
date | dd7932e5-8e14-56f2-becd-c485e5e0a51c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.17 - Stripping Formwork
label | 95fc868f-1692-50a4-9e82-b0a7d1923704 |  | note | Frequency - Each Lot
label | 90becfae-06b1-5349-a78b-c2c99933bcbb |  | note | - - - - - - - - -
label | ea71313f-332b-518a-a46f-4948c3b7ab16 |  | note | Acceptance Criteria - Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
label | 8b159063-d85d-5d82-b8ab-cb5d130ee9c6 |  | note | i. 2 days for vertical formwork on external surfaces; and
label | 18028dad-3521-5856-aabf-cb87ac3e3f8c |  | note | ii. 1 day for vertical forms on permanently hidden surfaces
label | a6c7007e-d324-5136-b7e1-a4a6ca113141 |  | note | - - - - - - - - -
label | c50f7c01-fced-52de-afb3-5863ae43e4d6 |  | note | Reference Documents - VicRoads Spec, 703.12, AS3610 Table C2
label | 6c77a567-e10e-59ee-b189-091e2e8098ed |  | note | - - - - - - - - -
label | ee42a151-9379-53c5-af59-d8f63ca14ed5 |  | note | Inspection / Test Method - Site Inspection
label | db0ed55f-7291-507a-bbe2-aec323a287ac |  | note | - - - - - - - - -
label | 6b2a5df6-968b-539e-ad3e-d0da6271d860 |  | note | Record of conformity - ITP Signed
label | 4ce6425e-078e-5946-adaa-b4b9b8d3db72 |  | note | - - - - - - - - -
label | 1f5dd5a1-b778-5d2c-bc96-4a1375dcd23a |  | note | IP
label | fc6052db-e6bd-5198-95f9-10d9da1036c8 |  | note | - - - - - - - - -
label | b1701361-b53c-5ff3-9f29-0009848e25f5 |  | note | Responsibility - Supervisor / Site Engineer
date | c66f68a5-e53a-56c2-a929-4615d6678ef8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.18 - Protection of Newly Poured Concrete
label | 3f186282-2a75-558e-aaf8-082c2139fc26 |  | note | Frequency - Each Lot
label | 3856f278-8a3f-53ec-b1fd-aa8f26e0f722 |  | note | - - - - - - - - -
label | e0f06546-256a-526b-92d8-6eb02a613978 |  | note | Acceptance Criteria - All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
label | bd82b11f-5952-5fc6-849c-bbeafe37d6cb |  | note | Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or
label | 3c23c017-14b5-58c5-9c04-2244bc67d5ba |  | note | commercial vehicle crossings a minimum of four days after completion of casting of the concrete.
label | 0ecd4a4f-bca5-5f1c-9376-5654e85e36ac |  | note | Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
label | fd65be55-5740-5b57-93a5-d184f69e9486 |  | note | - - - - - - - - -
label | 55c9418c-7d02-570f-9b14-7ce099e122f4 |  | note | Reference Documents - VicRoads Spec, 703.27
label | c56bb3b9-f9eb-5bb3-a307-345f8ed543f5 |  | note | - - - - - - - - -
label | f4137e94-4a38-5c77-a6d4-57a9f1dee533 |  | note | Inspection / Test Method - Site Inspection
label | b4aaf8a5-24e6-51c4-bd43-78e87770ff8c |  | note | - - - - - - - - -
label | 12ab818a-feeb-5d26-8d24-09970b972564 |  | note | Record of conformity - ITP Signed
label | c2847402-89f0-539b-aa3c-6e6a525d2751 |  | note | - - - - - - - - -
label | 60ce6204-c4e7-5d6f-99c2-d326d9eb029c |  | note | IP
label | 1b832d6c-3642-513b-bf4d-8462512fe070 |  | note | - - - - - - - - -
label | d789b07e-a9ea-5629-a620-7a4bb857b313 |  | note | Responsibility - Supervisor / Site Engineer
date | ed8b44ca-5411-5a62-997f-dcd4f6772498 |  | date | Date Completed:
checkpoint-group |  |  | section | 3 - Post-Construction
checkpoint-status |  |  | checkpoint | 3.1 - Survey data captured for as-built purposes
label | d33480be-7f83-57de-b8f2-261ced5fc5cd |  | note | Frequency - Completion of each lot
label | faaa105b-3c3d-5b7c-850f-bdc29eef88d9 |  | note | - - - - - - - - -
label | cfef3d39-0dec-5e6b-b341-0a47b9c6d0ec |  | note | Acceptance Criteria - Survey to ensure and validate that all works meet level and location requirements.
label | ccb3b412-0539-53ff-997e-e97aba6ae078 |  | note | Review of existing survey control marks and any additional control marks providing verification of conformity of as constructed features with design.
label | 318ed303-c06c-5cac-a94f-88438f7e4fd8 |  | note | As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
label | 78c88bb9-8657-56a4-922c-ef7ec90bf23c |  | note | - - - - - - - - -
label | 68bd91c2-3c32-5891-b555-70f4db813d33 |  | note | Reference Documents - IFC Drawings / survey records
label | e38eb52e-b29b-50cf-a9bc-b86dea4902fd |  | note | - - - - - - - - -
label | 95fb71b5-d5d1-5034-9904-16390874eddc |  | note | Inspection / Test Method - Document review
label | 178e620c-8ed1-595c-8e59-0c643d319c0d |  | note | - - - - - - - - -
label | f608e92f-a87c-5eae-a19d-a415298e1175 |  | note | Record of conformity - As-built survey records
label | 2353c1c2-5efb-5411-ad5b-2f2395c86af9 |  | note | - - - - - - - - -
label | 802200fc-16e9-54cb-b6ac-d7326a2044f4 |  | note | SCP
label | 8b798ee0-7dc8-53d0-86a2-7191bf04741a |  | note | - - - - - - - - -
label | a811375e-0af2-5471-a77c-3a7d38894b1f |  | note | Responsibility - Project Engineer
date | 7dc0dbc7-75e8-5a32-aad0-161034fe1e86 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Cracking of Concrete
label | f71a0589-8833-590a-b23b-4f8e15cc2f45 |  | note | Frequency - Each Lot
label | 6db0b6b9-1625-53ac-9785-c463302bf755 |  | note | - - - - - - - - -
label | 44f04c88-6b01-58f3-aee3-6840205bc893 |  | note | Acceptance Criteria - The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm.
label | 1252df53-c234-58df-bb99-b782ccc0af9e |  | note | Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
label | 0964163b-d6bd-5859-a061-7d8fe2837539 |  | note | - - - - - - - - -
label | f29eec7b-a01a-5a08-96ed-4ad1e8bbe18b |  | note | Reference Documents - VicRoads Spec. Cl. 703.30, 687
label | e861e3e0-14ee-5439-9756-863170f73926 |  | note | - - - - - - - - -
label | b6077d83-4586-5dc7-a3f2-abbb031a105f |  | note | Inspection / Test Method - Site Inspection
label | 25dad343-57d2-57cd-89e4-16e998392067 |  | note | - - - - - - - - -
label | f2b7feb8-30c1-5904-80b5-3262bdb2bfc8 |  | note | Record of conformity - ITP Signed
label | c5ea889c-56b9-5f0b-891f-13045b176d81 |  | note | - - - - - - - - -
label | 7f556818-a76d-5b6e-bfd5-df4df894e908 |  | note | IP
label | cc35f8bd-92c9-5508-ba68-344d7d2e631e |  | note | - - - - - - - - -
label | e43f5466-097f-55ff-b516-d1b01d9bc976 |  | note | Responsibility - Supervisor / Site Engineer
date | 7a157dba-9334-55ef-83f2-5a031dd213d4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Compressive Strength Test Results
label | 7e54a8e0-7da3-5c0f-9d7e-e7331f997f49 |  | note | Frequency - Completion of each lot
label | 12045f94-a520-5daa-bdac-3b659b2062b8 |  | note | - - - - - - - - -
label | ba29699e-9c33-5aff-b6dc-bd610881b158 |  | note | Acceptance Criteria - 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | 6efe9a0f-b4e4-5cba-ad6b-ad44c2e61178 |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | 8b59c590-b0f4-5391-8f42-d3f94980393b |  | note | - - - - - - - - -
label | a8f72cdf-9151-5f2f-931e-0f108bff5540 |  | note | Reference Documents - IFC Drawings, Relevant Council Drawings, 703.11, Table 703.111
label | ca9f0e67-b3c6-57ab-8eb3-9b793056198f |  | note | - - - - - - - - -
label | 867f3a61-2500-5b9e-ac2f-d23a551d6b83 |  | note | Inspection / Test Method - Site Inspection
label | f53fd410-3e21-5ad0-a51d-08acf94d2303 |  | note | - - - - - - - - -
label | 6bb088af-0e52-568f-ba24-9c2993ad75e5 |  | note | Record of conformity - Attach: Compressive Strength Test Results
label | 123cbb8f-e0ae-53b5-9035-aae3d095cb76 |  | note | - - - - - - - - -
label | 623194e3-43d7-522d-98da-c3b2d9166b9d |  | note | IP
label | 5b9fe20b-e941-5527-aae0-c0478b88af7e |  | note | - - - - - - - - -
label | 8f7367a1-9c2a-54a6-8446-afa90c3fca91 |  | note | Responsibility - Supervisor / Site Engineer
date | 0ba48a76-2af3-5cd1-b128-ac9623047a98 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - Backfilling
label | 68a4ee2b-b328-5f47-9602-0ab36c76eb2c |  | note | Frequency - Completion of each lot
label | c7617002-53e4-56a1-8ed1-dca4bd879176 |  | note | - - - - - - - - -
label | 67992337-2829-5a4c-9a34-e2e63ea5048c |  | note | Acceptance Criteria - Where required, as soon as concrete has cured sufficiently and not earlier than three days after placing,
label | 8f4d3bc3-fd00-5e96-95d7-9c4520eb077c |  | note | topsoil shall be placed and firmly compacted in layers not exceeding 150mm and to a width not less than 300mm behind the edging to the top of the edging.
label | 9ebf80c0-d1ec-53da-8ff1-ebd5f8998aba |  | note | - - - - - - - - -
label | d80fb1a6-c879-5907-ab12-6895e54772da |  | note | Reference Documents - VicRoads Spec. Cl 703.29
label | 43a48b69-2d4c-5353-aa47-275b28e3227e |  | note | - - - - - - - - -
label | 08d873fe-4bc2-5b68-a356-b188067fb6d4 |  | note | Inspection / Test Method - Site Inspection
label | ffbd0db1-617d-5212-abcf-171dd76ac457 |  | note | - - - - - - - - -
label | ba5903bd-18a7-5cf3-8827-7b48f938b2d3 |  | note | Record of conformity - ITP Signed
label | 0ce3ce9e-2d7b-53fd-8e9f-8b1d19543847 |  | note | - - - - - - - - -
label | 3c87db92-32fa-5217-abab-37585296b92c |  | note | IP
label | 58673e78-7092-5e3b-8ba8-22ca1387559b |  | note | - - - - - - - - -
label | 664b2cce-f755-5472-aeeb-6fe4bcd590f4 |  | note | Responsibility - Supervisor / Site Engineer
date | 67b4f123-8bb0-5e78-a594-375fbc7ed1c0 |  | date | Date Completed:
checkpoint-group |  |  | section | 4 - Completion
checkpoint-status |  |  | checkpoint | 4.1 - As-built Survey
label | 5f758c05-f6c2-5ba3-9f13-1efb81e3eb20 |  | note | Frequency - Completion of each lot
label | 8ec35792-8221-5389-aea1-d50990ae3a27 |  | note | - - - - - - - - -
label | f103af81-3d45-5293-b70b-ed9a14453a6a |  | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that
label | 691830bf-a13b-5f65-975e-777f8f0f0d95 |  | note | all Works meet level and location requirements within the tolerances below:
label | 024a1da1-4dbb-5469-b8d7-81e1e4c702d8 |  | note | Departure from RL = ±10mm
label | 0b804a81-8064-529c-9780-883b527d5294 |  | note | Departure from alignment = ±10mm
label | 01e6c705-93fa-5fee-9ce2-1fd038be73f9 |  | note | Rate of change of deviation from RL or alignment = 10mm in 10m
label | 4cc1d59e-fd1a-5dc0-b62d-f7a257da4c8b |  | note | Irregularities in alignment = 5mm in 3m
label | 8105cf12-82a2-564c-bb27-36bce4848888 |  | note | Section dimensions = ±5mm
label | e13ece53-dbff-5a29-9770-b1c46217b0da |  | note | Section dimensions (less than 25mm) = ±3mm
label | ff8d809a-0e63-5eee-8b6d-652ca43518d0 |  | note | Width of pavement = -5mm, +15mm
label | 110d54be-0256-5b3d-8296-00ee18fceb10 |  | note | Where median surfacings are to be constructed between edge sections of the same level,
label | f8b0fdf8-cf34-594a-93b2-c7bdc86730ca |  | note | paving shall be crowned to produce a crossfall between 1% and 3% towards the edges.
label | 0dea4726-02d2-59f8-a2cc-544563cc6115 |  | note | Attach: Survey As-builts / Survey Report
label | f9d2c014-9a65-508c-b51f-c21ebe7da78d |  | note | - - - - - - - - -
label | 825f8216-420b-5d48-9174-ccee35732578 |  | note | Reference Documents - IFC Drawings, VicRoads Spec, 703.15
label | 38d9f864-c321-53e0-bab4-d5a351055469 |  | note | - - - - - - - - -
label | a7fc1b22-22d5-53b1-ab67-40d5e293fd97 |  | note | Inspection / Test Method - Document Review
label | c75bc282-568d-5da6-8c98-a63a00593c30 |  | note | - - - - - - - - -
label | 3970c441-0d44-5539-b3f9-f7522d5236ae |  | note | Record of conformity - ITP Signed
label | 1517adb5-c1f3-5c1b-8e5d-3aa53882c551 |  | note | - - - - - - - - -
label | e62afbf7-ea71-53bb-8023-0aab043d8d7e |  | note | IP
label | fe95474a-217a-5630-a5f7-0048ae9d8c17 |  | note | - - - - - - - - -
label | 5a2bfb8b-44ff-503e-aa5c-3641adac89ce |  | note | Responsibility - Site Engineer
date | abf1ce49-e71f-5936-8e21-e870e84d4fe9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Red-Line Markup
label | 8c93feb9-ec76-5453-b76c-d31afb5c7097 |  | note | Frequency - Completion of each lot
label | 1cbe2c9e-62b1-5cbd-990c-71bc52c57789 |  | note | - - - - - - - - -
label | 25d37f04-2f3a-5422-97ea-9355d4562677 |  | note | Acceptance Criteria - Capture any changes in design or RFI's as per approved red-line markup procedure
label | 0db9b059-9ba1-5669-88a6-a607cb34ed40 |  | note | - - - - - - - - -
label | e4b3b06a-26c0-554b-899b-4617a3a5cde5 |  | note | Reference Documents - Quality Management Plan
label | 74dc53fd-94bc-5146-b81b-975d4b5dd11b |  | note | - - - - - - - - -
label | e8bfd4e9-40dc-57bc-a252-0b37bf008e0b |  | note | Inspection / Test Method - Document Review
label | 35d5f25d-04c1-5f42-8faf-5d1d6f1e2e95 |  | note | - - - - - - - - -
label | 62d208e4-2a10-5f51-87e0-5bb5807db64b |  | note | Record of conformity - ITP Signed
label | 6c5dec41-c223-5cc5-bf36-2681a4411812 |  | note | - - - - - - - - -
label | efc69a88-1b72-504c-b55b-f54dca5a32d8 |  | note | IP
label | a80cdd4e-3727-5fbb-a1f0-8f908a2531ff |  | note | - - - - - - - - -
label | 0247c993-bc17-5ff6-8d0b-572b71191f22 |  | note | Responsibility - Site Engineer
date | f6a4ce51-4a8d-5920-ada1-3376cdd09394 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Non-conformance Report (NCR) Closure
label | 6b67ac39-a397-541c-b1b7-b9f51c967c2b |  | note | Frequency - Completion of each lot
label | 01cf9565-5733-5b3b-9ac1-f308827ac4bf |  | note | - - - - - - - - -
label | 78668a24-b38b-5252-b7b2-501909fab053 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 1872d1b4-5698-50f6-8dd2-403b1bec4af9 |  | note | - - - - - - - - -
label | 9618d7a6-2e73-50eb-8ef3-205681ad649d |  | note | Reference Documents - Quality Management Plan
label | 26e69eb5-4246-5388-888c-fd3bac338fda |  | note | - - - - - - - - -
label | bcf961d6-3edb-5dcd-97ce-148e858081a9 |  | note | Inspection / Test Method - Document Review
label | f760b9e8-ef2d-57d4-9aaf-cf105aa463e8 |  | note | - - - - - - - - -
label | 9aaf9366-9d80-5b14-a501-6ac7908815d9 |  | note | Record of conformity - ITP Signed
label | aeceb307-b08a-54c8-b0a9-5c8dcc76a5ec |  | note | - - - - - - - - -
label | 25b82f10-1fd4-5bf7-9c9a-f8a54d37720d |  | note | IP
label | daff46e5-cfaa-5972-8bb8-d7a2c50eb77f |  | note | - - - - - - - - -
label | 86b15532-ab7e-58f7-98fa-7c3385f093ac |  | note | Responsibility - Site Engineer
date | 45ef173d-a91a-50d0-b883-a06ac7be02f7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | f174f5e3-47cd-5f88-aaab-8c3fcabac5cf |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 41c9e182-b381-5040-852e-0d9c14ba5202 |  | textbox | Print Name:
text | e3de0e06-af01-5503-94b3-97dcbfecc3c3 |  | textbox | Position:
date | 72673ed7-aea1-5aa7-b1b4-3fd5eab2b024 |  | date | Date:
date | f8029f05-ae81-56ee-9fd8-f47235af8baa |  | date | Work Completed On
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification.
select | f3ee9e67-4607-580d-8d27-5bdb3196163a |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | 01065ef8-a315-5db0-be6d-c4f347bc6f97 |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | 8046ea8d-f2b1-59c7-8e35-cc0b4a57d133 |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | 5efa5816-a734-57d6-bd15-2aa503951973 |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | 4125af6a-391b-541f-84f0-2caacd1dfed2 |  | textbox | Other:
select | 7e27ef51-90cb-5e6b-9b63-f8007052e009 |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | 6ccb6457-24be-537a-9855-abda6922e246 |  | date | Lot Closed On
text | e3471712-ab99-52cb-a0ad-5ff49a825632 |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-084-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0084 - LIME STABILISATION OF EARTHWORK MATERIALS | 431e7191-c7f2-4c74-89c2-1cbc95610a98
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | bad58456-a391-55e7-9bc4-107ae2d8c933 |  | date | Lot Created On
date | 51094a6a-27b8-5956-a8d6-31ad4f2c5a96 |  | date | Lot Opened On
date | 4c92ad5d-6ee3-5835-82a2-a3078c04423a |  | date | Work Commenced On
select | 2e0ce2aa-cd35-5321-a2b7-04d351d6c711 |  | dropdown | Lot Type | EAL - Earthworks
text | 10a7893e-738b-500c-a838-0d775cabf00e |  | textbox | From and To Chainage
select | 47bcea02-cc2b-597c-978d-27dec65bbd6d |  | dropdown | Construction Element | EART - Earthwork
select | d51af0ec-e0f9-5416-aef2-570c8d911f49 |  | dropdown | Activity | TACAPLIM - TypeA Capping Lime Stab, TAVLIM - TypeA Verge Lime Stab, TBLIM - Type B Lime Stabilization
select | ed06ec03-11de-51a8-b939-8c0af2e18b03 |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | 124b7d0b-e1c2-5c51-b1f4-39995b6aba83 |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | 208fdc82-dcad-5471-a23a-597571494e45 |  | textbox | Engineer Responsible
text | 7d1569bd-bc65-5940-861e-31d29e6df45c |  | textbox | comments
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Induction
label | 5a0f5dcf-59be-529c-a67a-e87bfddd20fa |  | note | Frequency: Prior to Commencing
label | 7f42cd1d-1739-5690-8172-61d52a04efd3 |  | note | - - - - - - - - -
label | 7fd16195-5240-56a4-9f54-ebc52b1a9551 |  | note | Acceptance Criteria: All personnel on site have been inducted to the CRG site
label | 12423cb7-40bf-54b6-aff6-77ff2b7991bc |  | note | - - - - - - - - -
label | 45500dc0-b0f6-5f48-96d2-35cfa4317ef7 |  | note | Reference Documents: PMP Inductions Register
label | e2fa9367-888e-553c-bb30-83704739d0e4 |  | note | - - - - - - - - -
label | 55540eb7-7502-5b66-8853-dbd9c5ea6b27 |  | note | Inspection / Test Method: Document review
label | 6370ecd1-8bac-5a7d-bf0d-79efc455616f |  | note | - - - - - - - - -
label | db3db14c-a21e-5b2c-b3c2-05b91881912e |  | note | Record of conformity: Site induction signed.
label | 63e1340d-52ea-5206-86fc-9b0ef0109bda |  | note | - - - - - - - - -
label | d0f39cf9-7c93-5ab7-9ffd-780c37900418 |  | note | AP
label | 9e463341-c479-5619-a441-bae3f584fcbe |  | note | - - - - - - - - -
label | 8ea7489e-e2b9-5299-b44b-66c6ca33342f |  | note | Responsibility: Site Engineer / Site Foreman
checkpoint-status |  |  | checkpoint | 1.2 - Check that current revision drawings are being used
label | 17fcc206-f560-5e6f-8ee1-1d5f9d73cfcd |  | note | Frequency: Prior to Commencing
label | 76d9a278-73f7-5fc7-895c-92bc7b3172ab |  | note | - - - - - - - - -
label | 5e8bb86d-8341-5858-9a3f-acc75f880643 |  | note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
label | 8721f58e-cdef-5ffe-9fac-d31b7416188f |  | note | - - - - - - - - -
label | 2176f2ab-a4db-593f-b011-f8a69a0ea646 |  | note | Reference Documents: Project Drawings / Drawing Register
label | bc8f159f-f32b-5a46-870b-dd5efc70259c |  | note | - - - - - - - - -
label | 5a45e87f-1175-50ab-91eb-a23c7ef192fd |  | note | Inspection / Test Method: Document review
label | c7bebc0e-1378-549a-b8f9-fb49d6e52ed8 |  | note | - - - - - - - - -
label | c2640d1d-6489-5a0c-807b-e49c14b49e7a |  | note | Record of conformity: Latest Revision Drawings
label | 6ab11c5f-16e8-5761-a6d2-952fbc32eba6 |  | note | - - - - - - - - -
label | ae5af7c6-af94-52de-a710-fb1ec9629b37 |  | note | AP
label | 9dd089eb-641a-5bd2-836f-328abb68f2b6 |  | note | - - - - - - - - -
label | 23a00e67-6626-5c4d-b3fd-645bd548ee48 |  | note | Responsibility: Site Engineer / Site Foreman
checkpoint-status |  |  | checkpoint | 1.3 - Confirm understanding of current Construction Environment Management Plan (CEMP) and Environmental Control Plan (ECP) related to the work area and that all prescribed environmental controls are in place
label | d4dcbd42-3c9b-5d11-b2ee-2d33462cc9ad |  | note | Frequency: Prior to Commencing
label | c82d81f9-489a-5845-ab26-c5b9ccd2d8fd |  | note | - - - - - - - - -
label | a0ceb18c-18a5-5ace-ace2-d4361a95d4f2 |  | note | Acceptance Criteria:
label | 63c5bbf4-17d8-519c-99ed-6d19b3553457 |  | note | • All environmental measures to be implemented as per current CEMP, ECP and local authorities.
label | 81fc6b46-2670-50b7-8d3e-d0fa22212c7c |  | note | • Sediment control measures to be installed and protected; sensitive vegetation to be clearly identified.
label | 89d5bff3-5ce0-505e-9cfa-9bbe3fa10fbd |  | note | • CEMP to be provided to Melbourne Water, incl. details for all water quality/ turbidity monitoring both upstream and downstream of works site.
label | 9b6553bb-2ee2-51ed-a625-de97cf3976b2 |  | note | • Provision to MW of a ‘Groundwater Management Plan’, including a dewatering methodology and where the water removed from the creek will be discharged.
label | 9e08791e-f7ae-5533-af14-deb047465030 |  | note | - - - - - - - - -
label | c9e069b2-83fd-589f-9906-76b271d8549b |  | note | Reference Documents: CEMP, ECP, Site induction, Project Specification Cl. 1200.03
label | fb3d65e5-a962-5aea-a51c-0d0b46ef68ef |  | note | - - - - - - - - -
label | 77348d55-b429-5c2b-b417-05d2857dcbdc |  | note | Inspection / Test Method: Document review & Site inspection
label | b2b79a5b-4f70-5293-81ee-b05320869e43 |  | note | - - - - - - - - -
label | d328d90c-2680-5d20-b8e6-2bfa47209ab5 |  | note | Record of conformity: Signed ITP
label | 89d2c688-6ef2-5564-8d92-371230643c74 |  | note | - - - - - - - - -
label | 6e15054b-f5bc-5d64-ad61-3b6b4dc57a27 |  | note | HP*
label | 42f036cd-867b-567e-9b86-357909ab1d6c |  | note | - - - - - - - - -
label | ba0e9731-571f-5d16-9a1a-7471df66e3ec |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 1.4 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken
label | 711cc2a0-a575-5d0a-836d-861ea217aee7 |  | note | Frequency: Prior to commencing
label | c81bedef-1877-5a3c-af45-33afe0c1e66b |  | note | - - - - - - - - -
label | 63485170-4011-595a-a44e-5f8bb154f814 |  | note | Acceptance Criteria: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
label | 3a33e42a-0781-5ead-9133-4b38a674d48e |  | note | - - - - - - - - -
label | d5b707df-0fd2-554e-9cf9-d9195bd1d5fe |  | note | Reference Documents: Project Specs. Cl.1125.02 Cl.1125.07 Health and Safety Co-Ordination Plan
label | 56cd17f7-62c3-5db3-8df3-fa7abc0277a0 |  | note | - - - - - - - - -
label | 7b4166e5-1c9a-51c1-a037-ac7461b3851e |  | note | Inspection / Test Method: Document Review
label | 4d78c863-ebff-5307-a11e-0fd3021bc232 |  | note | - - - - - - - - -
label | e9cebd8e-04da-52fb-9d2e-bdaf86cd4eaa |  | note | Record of conformity: SWMS(s) signed
label | 50b9c6ba-3f7b-53a5-9902-9d69b0410457 |  | note | - - - - - - - - -
label | 3d3cf3c6-c150-576b-9edd-aa8b10cf729c |  | note | HP*
label | 4de898e5-ea7a-50ed-a831-ec655c67082c |  | note | - - - - - - - - -
label | 14c740c8-f84f-5f37-9049-94aa74789127 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 1.5 - Excavation Permit issued (if required)
label | 42a965cf-2e64-5e28-a2ce-e577e3074039 |  | note | Frequency: Prior to Commencing
label | 493daf0f-191e-5438-a1f7-5b40a6dc94dc |  | note | - - - - - - - - -
label | d87444d2-b8a9-57f6-891c-02da240f4f2a |  | note | Acceptance Criteria: Current Excavation Permit signed and specific for the area where works will be executed.
label | e334ee7d-2797-5aa3-8a1c-fe7a22f77c59 |  | note | - - - - - - - - -
label | 05316a9e-8504-50a2-823c-49878ba2eee4 |  | note | Reference Documents: Excavation Permit
label | 159ac5d5-eeaf-5516-8fc3-b932b17608a2 |  | note | - - - - - - - - -
label | cce2813f-d771-56f2-9b98-d1661c6a46d4 |  | note | Inspection / Test Method: Document review
label | 581379ea-8ff6-53b4-92b7-a71457152365 |  | note | - - - - - - - - -
label | f9026cb8-6d28-5770-924e-c4d11771bd59 |  | note | Record of conformity: Excavation Permit #
label | 02fe09d6-f20a-5032-9ba9-ff4f16e38fcd |  | note | - - - - - - - - -
label | 50cea333-2b49-5a1c-aab9-914f97933cb1 |  | note | HP*
label | dec74a71-5bb0-5d73-a2d5-a66aa77c22cc |  | note | - - - - - - - - -
label | f6ff0e25-b8d3-518d-97be-979282310f50 |  | note | Responsibility: Site Engineer
checkpoint-group |  |  | section | 2 - Subgrade Stabilisation Preliminary Documentation
checkpoint-status |  |  | checkpoint | 2.1 - Stabilised Subgrade
label | 392ecbbc-58ed-5d7d-be15-83ac774645ca |  | note | Frequency: Prior to Commencing Works
label | 1df63cc9-43a6-5afd-a671-5e1b85837cce |  | note | - - - - - - - - -
label | dc601914-c7a0-568a-885f-36271d103269 |  | note | Acceptance Criteria:
label | 6a76648d-943e-5525-9699-678635a834d6 |  | note | • Methodology & scope agreed with Principal’s Representative prior to works commencement, outlined in Work Procedure and design drawings.
label | f39e0856-10ce-50f8-afad-aca2da7bbe4e |  | note | • The Contractor must submit to the Superintendent for approval in accordance with the Review Procedures, a detailed procedure for lime or cementitious stabilisation not less than 10 Business Days before commencing any lime stabilisation work.
label | c1735d6b-7494-591a-a3dc-3a05b57cddcd |  | note | - - - - - - - - -
label | 559dfe24-9ed9-589d-ba9a-0b1f8a13d3f9 |  | note | Reference Documents: PS3020.07 (j) VicRoads section 290
label | 55a34426-0461-509a-9fa4-f9e2f992ca0d |  | note | - - - - - - - - -
label | 3918e8f7-9407-5820-bf62-d1e4f130f31e |  | note | Inspection / Test Method: Testing
label | f5a54e38-71a6-57f4-bb8b-7a2190004f83 |  | note | - - - - - - - - -
label | f4b746a8-3afa-57fc-a87c-9cac5ca420c5 |  | note | Record of conformity: This signed ITP
label | 9da3cefc-b3d4-57a7-9782-21a37e8c9ce3 |  | note | - - - - - - - - -
label | 919d9320-df60-564b-a268-a468e40427c1 |  | note | AP
label | d5158921-efb5-533a-a19d-428e03d42e49 |  | note | - - - - - - - - -
label | 6f05e7de-c7c0-5316-afc8-0fcb8da643ba |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 2.2 - Investigation and determination of design lime spreading rate
label | 25cd6062-280a-5104-8e53-3d2f1b1e6819 |  | note | Frequency: Each Lot
label | 42e6293a-e0de-51e7-95ba-4cd1c8e5bb82 |  | note | - - - - - - - - -
label | 880e289b-0d11-53ef-b9ae-2269c13fb2af |  | note | Acceptance Criteria:
label | fdc9d810-ed45-5f2a-885b-fdf09b95480f |  | note | • The Contractor shall not commence work until all mix design details including the stabilising binder spreading rates have been presented to the Superintendent for review.
label | 982fefd7-e110-56cb-9827-2737ad6d3100 |  | note | • If the Contractor is required to determine the Design Distribution Rate of the stabilised binder(s), evidence shall be produced to show that the material properties specified in clause 290.07(a) or clause 290.17(a) as appropriate have been met.
label | 92963212-f485-5dc2-8915-e4c86b3ddd2c |  | note | - - - - - - - - -
label | d3e9365f-73b3-5265-bcdb-5fc3bcb079a8 |  | note | Reference Documents: VicRoads section 290 CL 290.08
label | f5c3bac4-2b93-5669-a91c-967113fc5137 |  | note | - - - - - - - - -
label | 357741bb-00aa-5904-8e8f-ef8eefb32ff0 |  | note | Inspection / Test Method: Verify
label | 9a281f09-f973-5ac0-90a5-0a9419e1abec |  | note | - - - - - - - - -
label | 9bfeb81c-8f11-5520-9635-ce6aaa552056 |  | note | Record of conformity: Subcontractor Quality Docs
label | 622fc143-c9a0-5faf-88ed-e9d072613480 |  | note | - - - - - - - - -
label | cdeb755f-b9df-5b5e-be62-95a2d81f0397 |  | note | HP
label | 7f9e9632-5066-5826-8637-6c0f2586d9a3 |  | note | - - - - - - - - -
label | 3b8a7828-f266-52c1-ad23-a3d2772f3e7e |  | note | Responsibility: Site Engineer & Superintendent
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Material Selection
label | e791b3a1-a8c1-58fc-986c-c407088960da |  | note | Frequency: Prior to
label | ba4aafac-75c0-5099-a37e-a2a64f930b53 |  | note | - - - - - - - - -
label | 2c78951e-0e1d-5d92-bae9-1df40e3eda98 |  | note | Acceptance Criteria:
label | 622aac63-a9ab-5bb3-bffc-c5d413b89402 |  | note | • If Type GP is proposed, the Superintendent shall be first notified and evidence provided to show that the earthworks material can be mixed and compacted to the specified density within the Maximum Allowable Working Time for Type GP Cement.
label | aec93ed3-5f7e-583f-9950-aaf707136a19 |  | note | • Quicklime and hydrated lime shall meet the requirements of AS 1672.1
label | e7eff0af-97bd-5b94-93bc-f52bb937c620 |  | note | • The stabilising binder shall be selected in accordance with Table 290.061
label | 1ea17fd9-ee7f-5ead-8379-6347fd92767c |  | note | - - - - - - - - -
label | f3802f5c-79f9-50cf-81c6-e51bacc09a4c |  | note | Reference Documents: VicRoads section 290 CL 290.10
label | 853c54f2-85d9-5f2a-b30b-c212c74a57bc |  | note | - - - - - - - - -
label | 916e1644-da7c-5b04-8e50-93e90bb4548d |  | note | Inspection / Test Method: Verify
label | a603fe49-0cb4-56be-9b38-e7a0f583574e |  | note | - - - - - - - - -
label | 47db01e0-16f6-5e17-adf9-7e6aa061a55a |  | note | Record of conformity: Subcontractor Quality Docs
label | e847cdeb-6105-51ba-ac5c-76c1fde37ef3 |  | note | - - - - - - - - -
label | b7588ea8-3ae6-5a62-909f-0b9be7989417 |  | note | HP
label | 1722fbcd-abfa-57a6-9f9e-dfa146cdae60 |  | note | - - - - - - - - -
label | 295d8410-9fa0-5bcb-9aa3-3d0b8e91caa1 |  | note | Responsibility: Site Engineer & Superintendent
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Preliminary trial
label | eb1a364e-2f42-5e96-bd9c-90cc09d04d68 |  | note | Frequency: Each Lot
label | 0fb5b60a-5a13-5ff3-b23d-77ed3498c6fb |  | note | - - - - - - - - -
label | c9c89940-309a-5cc2-9b2a-4fc14a6d5d52 |  | note | Acceptance Criteria:
label | 9b2d15c8-256a-557f-b501-7dff59957401 |  | note | • Preliminary trial to be undertaken of the proposed stabilisation operation. Trial to determine:
label | b750cfae-28ae-5e04-b885-afbfabcd450f |  | note | – Effectiveness of plant
label | c88b858a-6c94-5f47-9668-72153394e4dc |  | note | – Number of passes required by the stabilisation to achieve uniform pulverisation and mixing
label | 45233f37-e126-5cbd-a1b1-c2b0b10978a5 |  | note | – Field moisture required to achieve specified compaction requirements.
label | 1c1a67e4-1ac8-55d1-91ac-6d6eae7f30a3 |  | note | – Rolling routine required to achieve specified compaction requirements
label | dbff7428-63da-5533-9568-7b2a14ff5309 |  | note | – uniformity of mixing of six random test holes.
label | 77dedb26-5a1f-585b-a04d-ab262aba8722 |  | note | – Lime stabilisation not to proceed until reviewed by the Principal’s Representative, with an outcome received within three working days.
label | 616d7e77-c989-567b-8007-51ef7ae10f18 |  | note | • Stabilisation shall not proceed outside the trial sections until the Superintendent has reviewed all aspects of the work. If the Specification requirements are not met for the trial, the Superintendent may direct that another trial be undertaken or that the work be re stabilised and presented for re assessment.
label | 04a71cb8-2acf-5e69-b0ff-56e3c8a25a3c |  | note | - - - - - - - - -
label | 99bec649-fdfa-5ce9-b7d8-06c069faf991 |  | note | Reference Documents: VicRoads section 290 CL. 290.11 CL 290.17c
label | 1011908e-d93f-5a51-bdcc-18ca38b3142c |  | note | - - - - - - - - -
label | 547bda7b-2667-5369-b4e5-490a1904e7db |  | note | Inspection / Test Method: Visual Inspection
label | f2c75ed2-8e98-5ea4-88bc-8d27c977f6d5 |  | note | - - - - - - - - -
label | 5cc9ecb8-e151-521b-a761-c5987eef5019 |  | note | Record of conformity: Subcontractor Quality Docs
label | 5ae58188-1cfe-5fd3-a29a-2f7cdf5d0da3 |  | note | - - - - - - - - -
label | 30456e04-76d0-5120-8cb8-ab9163bdc41f |  | note | HP
label | abe468fb-37f6-5b8d-a0ef-3380653a250a |  | note | - - - - - - - - -
label | 1706558c-06e6-54a6-87b9-bbe02d69dbde |  | note | Responsibility: Site Engineer & Superintendent
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Construction process - Lime Stabilisation
checkpoint-status |  |  | checkpoint | 3.2 - Preparation of Subgrade
label | 6406baeb-1bca-5520-a6c3-b928f8841243 |  | note | Frequency: Prior to construction of subgrade layer
label | 5fc9ab85-bec3-52b6-b6cd-a98fc0fdfaef |  | note | - - - - - - - - -
label | 7b3b6072-3c25-5e93-96b3-c83fc2f6c7fc |  | note | Acceptance Criteria: The top of the Type B material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03(g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water)
label | 13e107b0-88de-5841-a2be-609b30962969 |  | note | - - - - - - - - -
label | 4d444380-6262-5c18-8443-36a54e930b2f |  | note | Reference Documents: VicRoads Spec. Cl. 204.15Cl. 204.03
label | 10096ce7-c5fd-546c-a26a-02f683dc1319 |  | note | - - - - - - - - -
label | ee371fe8-a484-5cef-8131-a1ede844b21a |  | note | Inspection / Test Method: Site Inspection
label | f7aa514c-5600-5c35-8f84-ec1e4dfdb70a |  | note | - - - - - - - - -
label | 45d58ad9-0505-57db-8e02-46637420c1e8 |  | note | Record of conformity: Signed ITP
label | 593e9241-fcc3-5e21-9d66-3d1b75416eb2 |  | note | - - - - - - - - -
label | d4582125-825e-5363-8e75-2010aeb1acf8 |  | note | IP
label | 04fe3d3a-6b4d-5f21-b87e-106bb472be38 |  | note | - - - - - - - - -
label | 88fb4935-fc39-5090-b57a-b6fd3289632c |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3.3 - Proof Roll
label | 1dbf8f33-f50d-5665-bbca-ae3ff12ffb59 |  | note | Frequency: Prior to Placing fill
label | 00bc343c-e2a4-5ea3-ac44-f54768a15f72 |  | note | - - - - - - - - -
label | de833126-c2e7-519b-953c-ab00d6eec285 |  | note | Acceptance Criteria:
label | 34dcd12f-f109-5c40-ba99-ac9abda909cf |  | note | • Areas upon which fills are to be constructed, all layers of fill, and material within 150 mm of the cut floor level in cuts, shall be test rolled in accordance with Section 173. Superintendent to be present during all test rolling.
label | 64d4b44a-4309-51f6-9f14-71821c57889d |  | note | • Fulton Hogan to provide not less than 24hrs notice to the Superintendent of the location and commencement time for test rolling. Superintendent to be present during all test rolling.
label | 89578ced-b77f-51cc-aa78-9bfb0c95731a |  | note | • No fill is to be placed on the prepared areas until the area has been reviewed by the Superintendent. Where unsuitable material is encountered the Contractor shall propose in situ treatment and depth of excavation to the Superintendent for review. Where <10% of the lot area is deemed unsuitable, material shall be rectified as agreed by the Contractor and Superintendent
label | 638e76b9-cfe5-5d28-8b76-9a302bafeadf |  | note | - - - - - - - - -
label | 02f72f88-6f6a-5098-b3f4-0da36e555f03 |  | note | Reference Documents: VicRoads Spec. Cl. 204.12 Cl.173.03 CL.204.13(b) Cl. 204.10(b) Cl. 204.07(d) Cl 290.12
label | 4911029a-dbc3-5f43-b730-83031d64b758 |  | note | - - - - - - - - -
label | d9b35677-7981-5154-9c86-3e1177aef3b9 |  | note | Inspection / Test Method: Site Inspection
label | bc9d2b72-e178-552e-bed5-6144adedcf80 |  | note | - - - - - - - - -
label | f3252c84-85e5-525a-9a5e-d0769477c981 |  | note | Record of conformity: Area visually reviewed by Superintendent Signed ITP
label | 4d8c3e50-b33d-5c6c-b068-2739c265d55f |  | note | - - - - - - - - -
label | 9d6e6416-9d8f-59a7-b227-d38de7b0be51 |  | note | HP
label | e5e6132f-eac0-5b58-b63d-3611c34249e8 |  | note | - - - - - - - - -
label | 149c538d-281d-5dfa-82d3-4f20276c0b8d |  | note | Responsibility: Site Engineer & Superintendent
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Pre-treatment of earthworks
label | a1139730-f1b8-57df-9ba2-c4012c57a5ed |  | note | Frequency: Each Lot
label | 2d023294-9a09-5a54-9a28-130192de4114 |  | note | - - - - - - - - -
label | af25ed00-ea54-51e6-9de6-427155de5875 |  | note | Acceptance Criteria:
label | 784df25b-3999-554f-a49c-7619c1ea92d4 |  | note | • The area being stabilised by lime will need to be scarified/pulverised to the specified depth. Any rock particles greater than 75mm to be removed from the soil.
label | 054c179a-cb03-5b09-8bf3-732b698ee3ed |  | note | • The maximum compacted layer thickness for any stabilised material shall not exceed 250 mm, unless otherwise approved by the Superintendent
label | 1f8390e3-4514-55c4-9cdd-20350729306a |  | note | - - - - - - - - -
label | 47901521-cec8-5562-b5d1-8fcad4aec0f2 |  | note | Reference Documents: VicRoads section 290 CL.290.10 (b)
label | afd8f405-553a-57b3-87a7-c4aae2905fd0 |  | note | - - - - - - - - -
label | 9a4ffb86-1f81-5e13-a154-cce2deaf2d64 |  | note | Inspection / Test Method: Verify
label | 6ca7bd6d-7d6e-5099-b1ab-50940d0e1458 |  | note | - - - - - - - - -
label | 05668678-8262-5fa4-97c6-47f4cee0c5d0 |  | note | Record of conformity: This signed ITP
label | e9ce9f98-10dd-5fa2-bbfe-89281508d1d1 |  | note | - - - - - - - - -
label | cf6e104b-9344-5c00-bd4d-d8638c8ff876 |  | note | IP
checkpoint-status |  |  | checkpoint | 3.5 - Spreading of Lime
label | 35755468-a57c-5074-b909-5dffd821b7e3 |  | note | Frequency: Each Lot
label | bfa3764f-3364-54a6-900d-f47376d15390 |  | note | - - - - - - - - -
label | 72f59e72-28f2-5fed-be07-59440b85e987 |  | note | Acceptance Criteria: Lime to be spread uniformly over the prepared surface at the Lime spreading rate calculated.
label | deaa9796-5578-5551-acb8-0996eee1bcb1 |  | note | - - - - - - - - -
label | d63d024a-49e0-5ede-b552-454ce0670d62 |  | note | Reference Documents: VicRoads section 290 CL.290.10 (d)
label | fb1c7eb4-9796-5e43-a81b-be484d9c04ca |  | note | - - - - - - - - -
label | 175fdb01-a363-5142-8113-ff8f9511d6a8 |  | note | Inspection / Test Method: Verify
label | eb821e1c-f5c8-535e-bcb3-aa630e881cf5 |  | note | - - - - - - - - -
label | c29658c7-9c1e-5e3f-8f7a-6d9ad96ed847 |  | note | Record of conformity: This signed ITP
label | 90617317-761e-52f6-b8c5-5e8e4729e8ea |  | note | - - - - - - - - -
label | e74af931-c1da-5238-9042-d818a105fcbc |  | note | IP
checkpoint-status |  |  | checkpoint | 3.6 - Slaking of Quicklime
label | d8493b83-2c80-5d75-8f5d-38ec55ec3d69 |  | note | Frequency: Each Lot
label | aac8821f-0136-56c1-b827-8cbe676de99f |  | note | - - - - - - - - -
label | 3f4c8a34-7379-5433-be53-309bcac3dce4 |  | note | Acceptance Criteria: Quicklime shall be slaked with sufficient water to allow full hydration to take place.
label | ecc7af09-191c-5768-8ed2-4e546d6083a1 |  | note | - - - - - - - - -
label | dcb951d7-ead3-548b-b41d-ce7490b9d272 |  | note | Reference Documents: VicRoads section 290 CL.290.10 (e)
label | 8475f56c-4fad-5515-88ec-e2916446262b |  | note | - - - - - - - - -
label | 6b3a6b60-281d-5302-ae7b-11654b6da1d7 |  | note | Inspection / Test Method: Verify
label | 0d6e4d21-b7a6-5020-861b-e08f62aaa3e1 |  | note | - - - - - - - - -
label | 3b25ae9d-61f5-5d81-ae68-09cc3f3e25d1 |  | note | Record of conformity: This signed ITP
label | f4220970-2fe7-51e6-ad9e-c8241f6c9653 |  | note | - - - - - - - - -
label | dcb6ccf9-75cb-57bf-a639-cbc577aef57e |  | note | IP
checkpoint-status |  |  | checkpoint | 3.7 - Mixing
label | 0a90bc2c-0ce9-5f3d-8f72-f78f54f5c41d |  | note | Frequency: Each Lot
label | 05c2d1d6-53bb-56ce-bbe1-fc14b74aeacc |  | note | - - - - - - - - -
label | 6b4d4697-e040-53ef-9bb1-5406dfed0f83 |  | note | Acceptance Criteria: All lime to be mixed to the specified depth within 6 hours of spreading. The stabilised material shall be visibly inspected for uniform mixing by excavating test holes to the full depth of the loose material at six random locations within each lot.
label | 5d92e172-a87a-5a42-b4bb-72325b7654fd |  | note | - - - - - - - - -
label | bb160c50-6c21-59ac-b555-44f216b2f6b9 |  | note | Reference Documents: VicRoads section 290 CL.290.10 (f)
label | 42a2a6ed-5d13-5ffb-8955-a5ca3b785815 |  | note | - - - - - - - - -
label | f4d4e47c-9bb4-5dc3-ba06-8db4d7f81cb3 |  | note | Inspection / Test Method: Verify
label | f1d10183-3bab-51ce-923b-4ea38f6c6535 |  | note | - - - - - - - - -
label | eb78a492-4a66-521c-a912-b1c2f1c4ea8f |  | note | Record of conformity: This signed ITP
label | afc0ea41-b3eb-57d0-b5e6-11469289a97d |  | note | - - - - - - - - -
label | 61a93a76-434d-57c8-a850-bd482b3c4850 |  | note | IP
checkpoint-status |  |  | checkpoint | 3.8 - Compaction
label | 3480077c-8705-5050-a0f1-3add4331e2f0 |  | note | Frequency: Each Lot
label | 0f1e80d6-e141-5389-bf75-7db46385c8f8 |  | note | - - - - - - - - -
label | 56735bca-ce04-583f-b2ad-0bb62ffb9dfe |  | note | Acceptance Criteria:
label | 9ff6aa2e-72b1-5b23-bd5c-a14250da9480 |  | note | • Compaction of the stabilised layer shall commence immediately after mixing, but only after the requirements of clause 209.10(f) or (g) or (h), as appropriate, have been met
label | 57255a00-8339-5f00-b7b2-115b12fbf2b4 |  | note | • All compaction shall be completed within the times specified in Table 290.101 after addition of the stabilising binder.
label | fe31880c-dd4c-5a49-84f3-183f428fb739 |  | note | • If necessary during compaction, the Contractor shall water the material to maintain the moisture content within 80% to 100% of the stabilised material’s optimum moisture content.
label | 40d2367a-ce4e-51b5-9c09-04b3b9eb3015 |  | note | - - - - - - - - -
label | 5b53700c-b28e-5952-8a7d-7da8bb3e1845 |  | note | Reference Documents: VicRoads section 290.10.(i)
label | c0a44cdf-9223-5036-ae90-18beccd305a5 |  | note | - - - - - - - - -
label | 4eaf5e55-7446-5b77-bfcd-83fc04784302 |  | note | Inspection / Test Method: Verify
label | 323bfac2-fbcb-512c-8946-2c77b87137ca |  | note | - - - - - - - - -
label | cb649592-6990-5a38-af17-8138d24d0748 |  | note | Record of conformity: This signed ITP
label | 6c64df86-3d42-545f-b4af-523ee3ded1ac |  | note | - - - - - - - - -
label | f844d952-eed4-52ea-8db9-5a943cf40ce1 |  | note | IP
checkpoint-status |  |  | checkpoint | 3.9 - Trimming
label | e8a0fd2f-1601-59e2-af3f-4acca09d4f70 |  | note | Frequency: Each Lot
label | 695ca475-d4e2-599a-8591-5a1fc9babdb2 |  | note | - - - - - - - - -
label | 47e53a19-1a65-5347-8960-abd1b78e1409 |  | note | Acceptance Criteria: Surface may be trimmed before or during compaction to conform to surface level tolerances.
label | 17367bd9-37d0-5286-9e0f-5e171c9c34d8 |  | note | - - - - - - - - -
label | 9935fec6-d47a-5c6f-b044-c561b83b7468 |  | note | Reference Documents: VicRoads section 290 CL.290.10 (k)
label | e02265c1-eaf6-5ba3-abe4-2c362b249fc2 |  | note | - - - - - - - - -
label | 0cfb93d0-f889-5535-91fa-eeacda70c8b8 |  | note | Inspection / Test Method: Verify
label | 882f45cd-6e37-5db8-92e6-c05ac4197f86 |  | note | - - - - - - - - -
label | 7e80ddfa-0677-57aa-be1d-e845c9f6d883 |  | note | Record of conformity: This signed ITP
label | f9a5995d-988c-5833-a271-98677fe12366 |  | note | - - - - - - - - -
label | ab117209-19fc-551b-a119-e1f8965e6cf0 |  | note | IP
checkpoint-status |  |  | checkpoint | 3.10 - Curing and protection of compacted layers
label | afb9737d-6104-5ccb-84a3-5a907eed467c |  | note | Frequency: Each Lot
label | fa9d5a58-33ac-55c6-a5ef-7a5ed2ab8465 |  | note | - - - - - - - - -
label | fb9a3a2b-44d8-57ed-94be-023a9edfa9e9 |  | note | Acceptance Criteria:
label | b882a876-341c-5469-9cb3-81b2da581c3c |  | note | • The surface of the compacted layer shall be kept continually moist, and free from contamination until the succeeding layer is placed.
label | e8d2a6f1-0e60-5f47-8bbc-a853ec86fa16 |  | note | • If the stabilised material overlies an expansive material with a percentage swell exceeding 2.5%, the stabilised material shall be maintained at a minimum characteristic moisture ratio of 90%
label | 0162a35a-2d3e-5515-b28b-f3ac978942c9 |  | note | - - - - - - - - -
label | aedb328d-362c-5fb9-a110-23619dcbae0a |  | note | Reference Documents: VicRoads section 290 CL.290.16
label | 142f39ed-875a-5163-ae04-05d452a17cf3 |  | note | - - - - - - - - -
label | 64fe05d5-3aa7-5ca0-a54d-6bd42bd08c55 |  | note | Inspection / Test Method: Verify
label | 5d4882a9-53fc-5571-b180-8091a25de0f2 |  | note | - - - - - - - - -
label | f67f8dba-8d78-5be2-87f3-4fb09e5171ca |  | note | Record of conformity: This signed ITP
label | 04bbc471-90b4-5c2c-a6c2-8da3e7587d79 |  | note | - - - - - - - - -
label | 2932b16b-0315-586c-bd49-6ce13425b22d |  | note | IP
checkpoint-group |  |  | section | 4 - Acceptance - Pavements
checkpoint-status |  |  | checkpoint | 4.1 - Requirements and Acceptance of Lime Spreading Rate
label | 61093d8d-870b-56e8-9901-e87ad4a8fd64 |  | note | Frequency: Each Lot
label | fe29a1ac-9a28-506f-a262-f0005ca56684 |  | note | - - - - - - - - -
label | fa3dcd91-d536-5325-a0c7-928c442dee6a |  | note | Acceptance Criteria:
label | 0d792b46-83b0-54ee-aa08-a10bab99c8fc |  | note | • The Average Lime Spreading Rate and Uniformity of Lime Spreading Rate are to be determined by either the Mat/Tray System or the Continuous Weighing System, as described in VicRoads Clause 290.13.
label | e98cab4e-75eb-574e-bb1e-36d8a14385fe |  | note | • Evidence of results to be presented to the Principal’s Representative upon request.
label | 683c0f60-ffe5-5347-8bc0-d2ba702c7793 |  | note | - - - - - - - - -
label | 951e12c5-e668-5280-abb8-22618494ed66 |  | note | Reference Documents: VicRoads section 290 CL 290.13
label | e03287f7-ae65-5f81-9525-0ca604dfb619 |  | note | - - - - - - - - -
label | edd5b10e-0369-531d-9fb6-5f042d2e2e53 |  | note | Inspection / Test Method: Verify
label | eaad7275-5ccf-53ea-9194-bef22e58feeb |  | note | - - - - - - - - -
label | b254043b-72c3-5c8c-9df4-9148f5afe244 |  | note | Record of conformity: This signed ITP & Test Results
label | 8bac6c3e-bb15-533b-a82c-f514965e2a09 |  | note | - - - - - - - - -
label | e01c7a65-13c6-5b03-a3c6-e4d643fd2b13 |  | note | TP
label | d1cd65e9-fac1-5b7d-a294-77d630eb885c |  | note | - - - - - - - - -
label | ccfb7e34-7508-5926-9637-c89ccb2134bb |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 4.2 - Subgrade Testing
label | 7edc2756-39af-5db7-9544-efc4cca7802c |  | note | Frequency: Each Lot
label | 3f2c9d20-8810-5389-b59b-0f87b0edcac8 |  | note | - - - - - - - - -
label | 1350212d-5da0-5f84-aecc-c98823daa5f9 |  | note | Acceptance Criteria:
label | 1e1b1080-8ecd-5b91-ae84-44ad0470efdd |  | note | – Average dry density ratio of not less than 99% MDD (standard) for lime stabilised subgrade material.
label | a8599d68-ee52-54bb-bc32-dead0c2d72b6 |  | note | – Field dry density at three random locations throughout each uniform section, per scale A requirements.
label | 217f6977-f186-5caa-a3f3-d1746e4c2f36 |  | note | – Where the subgrade has been replaced with 200mm of Class 1 Crushed Rock, the field dry density is to be compacted to 99% (standard compactive effort).
label | 128f7289-e6ee-55e8-a130-f5be85c08227 |  | note | ○ Characteristic Density Ratio ≥ 99%
label | f8d13b40-c0de-5d35-ba65-1d7037909618 |  | note | • CBR ≥ 6%
label | 8b480b4d-419c-5eb0-bd19-291dccf22dc9 |  | note | • Swell ≤ 1.5%
label | 7e674f59-e39f-5cf7-b341-526a4bdf60a1 |  | note | • Permeability ≤ 5e-9
label | e0eab66d-2dfc-569f-83bc-3a898ecefb35 |  | note | • PI (LL) = 6 - 25
label | 61eb6248-a453-5175-a94c-bde15b3d12f3 |  | note | • PI x 0.425 passing ≤ 1000
label | 40ce64d2-b3a6-54d9-884a-4c734a065aec |  | note | ○ Grading:
label | 46fa9e35-1a41-5a89-80b8-41b04ef7b837 |  | note | • % passing 75.0mm sieve = 100
label | a7da44bf-f3d4-5b14-9e3b-bf8695f11e45 |  | note | • % passing 4.75mm sieve = 40 - 80
label | 220a3656-298e-5814-9911-f26f607d1734 |  | note | • % passing 0.075mm = 10 - 40
label | e06979fc-8c75-5845-bb91-e9309924d4aa |  | note | - - - - - - - - -
label | f05be061-7f9e-5611-a88a-72873e998cfc |  | note | Reference Documents: VicRoads section 290 CL 290.14, Table 290.141 for compaction requirement and Table 290.15 for the frequency of Testing
label | 0118129b-0d2c-531c-8f3d-c6aaf96f58a6 |  | note | - - - - - - - - -
label | d28fa21b-8340-5a38-8867-e59ff40f8a78 |  | note | Inspection / Test Method: Verify
label | f6dfa506-6446-5dc5-bc1b-e253a0b56f25 |  | note | - - - - - - - - -
label | 967b6fcb-d184-50a1-9346-a018f5fe81ce |  | note | Record of conformity: This signed ITP / Test Results
label | c9527e2a-64ed-59b6-bd1e-1b375463cfe6 |  | note | - - - - - - - - -
label | 9d01ffc1-1da6-5be7-bca3-18870cf9a0f8 |  | note | TP
label | c9e572f0-0cc0-5b01-b9f3-eeeed2e3e4ff |  | note | - - - - - - - - -
label | e3f9b49b-c2ef-5a25-aa6a-0f3e7cd573cb |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | Test Requisition
text | f41284b4-8973-5b4f-a762-c7972fc7afd3 |  | textbox | Test Requested on
text | 4e1c38d8-5457-5e6c-885f-fe568d743523 |  | textbox | Location
select | 77a94740-5367-5769-8498-99edacef672c |  | dropdown | Material Type | Type A,Type B,See comments
select | e9e20409-567e-5eb2-9083-0f1f915c13e7 |  | dropdown | Material Source | Holcim,Boral,See comments
boolean | 9a454284-cd2c-5f0d-b2eb-ca46db4d7619 |  | tickbox | Compaction Test (Standard)
boolean | 14f55b24-d80e-5210-8dc1-8e5172c85c35 |  | tickbox | Compaction Test (Modified)
boolean | d5ec320e-2e60-5c24-aad3-7c38975b5417 |  | tickbox | Maximum Particle Test
boolean | b386597d-9de4-5143-8db9-fd169979395d |  | tickbox | CBR/Swell Test
boolean | 9dfada47-d744-5b82-b866-b919189fb984 |  | tickbox | PI Test
boolean | 3b9ae2e9-b69f-5757-b471-92c9006ae48e |  | tickbox | Permeability Test
boolean | 3ed91647-6b81-51a0-9aa1-b9ae16f2430d |  | tickbox | Grading
boolean | be2ce7aa-3e0f-5c88-94f1-e2e6855ad997 |  | tickbox | Moisture
boolean | 4b032538-8bbb-53b5-b202-4f858f0d2e1b |  | tickbox | See comments
text | 4544bbb4-8b4e-5bb7-9558-77ed16178ae1 |  | textbox | Test Level/ Layer
holdpoint |  |  | signoff | Test Requisition
checkpoint-status |  |  | checkpoint | Final Inspection
label | 0f9b6bda-0398-54ea-ab8f-a04f7817bfd1 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | c536519a-7683-526f-95f1-b99b83fa37ab |  | textbox | Print Name:
text | 2fbeaff3-cdd3-5f41-81c7-ca2e73e42108 |  | textbox | Position:
date | 385faa9f-6fff-5a0d-8cb0-a5a67402e9f8 |  | date | Date:
date | eb5fc7a6-91ca-5b1f-90ba-8158144f77eb |  | date | Work Completed On
checkpoint-status |  |  | checkpoint | Lot Verification.
select | e6ff50ad-7497-5c70-8302-0b6dcf24dc47 |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | 52d94061-0403-5da8-a83a-1fd0a101c3f1 |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | 2b39331e-ebe8-555c-88ef-ce034fd7088b |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | 57d812c5-21c9-5db8-b2f2-8504eff8f481 |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | 111b029f-183d-5882-82f0-eb44a05fabea |  | textbox | Other:
select | 1fd269ea-66ca-5e9e-8838-8b85a35d5283 |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | b0c62341-98d3-510d-b9d0-48fe1a13fe2d |  | date | Lot Closed On
text | 81179eb1-5ee2-5351-a6ba-fb1e4e1f5aa9 |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-040-UT-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0040 - Gas Protection Works | 434f7c4e-fcde-4b90-a0e4-21f3328d4cba
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | 2882a552-fb46-5ba8-83d7-3c699233fab5 |  | date | Lot Created On
date | 0a61f5c9-adfa-5c27-964e-6bd566a865b2 |  | date | Lot Opened On
date | a40125cd-f641-5877-84cf-f7bf4e689ce6 |  | date | Work Commenced On
select | 21b63d96-24e4-5a89-a8bc-82fd0026dfdc |  | dropdown | Lot Type | CIL-Civil Lot, DRL- Drainage Lot, EAL- Earthworks Lot, ELL- Electrical Lot, UTL- Utility Lot, STL- Structural Lot
text | 7f30c403-125f-5bbf-a18e-3ef50e596f3e |  | textbox | From and To Chainage
select | 4bdd11b7-360b-5845-bee3-d442274c430c |  | dropdown | Construction Element | UTIL - Utility
select | 40570e5f-f491-524f-9ba2-4b7414ad7ed8 |  | dropdown | Activity | GAS - Gas
select | 98365bdd-6f9c-5b4e-a334-0605caaa0e35 |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | e5763b13-b181-56bd-b009-0e56b4d684bf |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | 4996ce62-2431-5667-bf88-7e560da8ac2f |  | textbox | Engineer Responsible
text | ebc10ef8-ee2e-52dd-8590-60a76766bb98 |  | textbox | comments
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Induction
label | a5dce85b-5fbc-50d9-a6f4-08d222aaf242 |  | note | Frequency: Prior to Commencing
label | 6056eaf4-8ff5-56ac-82e3-96a40572c29e |  | note | - - - - - - - - -
label | 45d5f042-1f13-5edf-9395-566a2711bb50 |  | note | Acceptance Criteria: All personnel on site have been inducted to the CRU site
label | 29cb3bb0-d98b-51a4-9bea-bcbc9383cdc3 |  | note | - - - - - - - - -
label | eda7a460-ab19-5e29-81e8-e28c40634bb0 |  | note | Reference Documents: PMP Inductions Register
label | b8ab1f52-8c4c-5d94-afdf-6ab2a987bec9 |  | note | - - - - - - - - -
label | 4eaf508d-7f4e-5941-a236-8d2f9f62844a |  | note | Inspection / Test Method: Document review
label | 22022f00-b401-5d2b-9f9a-69a47ea4fc29 |  | note | - - - - - - - - -
label | d6425480-3600-5bab-8ef0-9204463f8ca4 |  | note | Record of conformity: Site induction signed.
label | 281f4071-1547-59ea-936c-8b40b0be724f |  | note | - - - - - - - - -
label | 0eb31741-1ec5-586a-a93b-d86bbc7092ad |  | note | AP
label | bca12838-e24a-5850-afec-b3aefd91a0bd |  | note | - - - - - - - - -
label | 866a2312-8037-5f81-ae85-02c571a23fb1 |  | note | Responsibility: Site Engineer / Site Foreman
checkpoint-status |  |  | checkpoint | 1.2 - Safety measures are in place, SWMS undertaken
label | 5c248b42-aeab-511d-a898-9f9b3ddfe032 |  | note | Frequency: Prior to commencing
label | 3383e6f7-fdb2-5b12-81c5-4ec051e22f3a |  | note | - - - - - - - - -
label | 29dadb7c-0983-575b-9606-538b62e9be6d |  | note | Acceptance Criteria: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
label | 464abdd8-27ec-56a4-bd65-59bcbaffabeb |  | note | - - - - - - - - -
label | edbf9506-018d-52de-90ce-dc6d0bbd1940 |  | note | Reference Documents: Health and Safety Coordination Plan
label | 0c964057-7959-5f76-b989-2aa98643cf39 |  | note | - - - - - - - - -
label | ccaee862-b4a9-5c5e-bece-c86f934068c4 |  | note | Inspection / Test Method: Document Review
label | 207ffd24-a563-58d3-b4a5-95adbe60ae1f |  | note | - - - - - - - - -
label | e8522089-8d07-5f54-bc86-1d96f82639ed |  | note | Record of conformity: SWMS(s) signed
label | a3d831a7-2018-53ef-b17d-ca2bc631bd91 |  | note | - - - - - - - - -
label | 75724241-d3cd-584e-ad47-1114faf4c497 |  | note | HP*
label | 7283788d-cccc-5607-b811-7a48fa17dd20 |  | note | - - - - - - - - -
label | 25b3cf83-ddb5-5a8f-86ad-e356cc388b8c |  | note | Responsibility: Site Engineer, Site Foreman
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Check that current revision drawings are being used
label | cf542234-3614-5b81-a646-96b5e2603904 |  | note | Frequency: Prior to Commencing
label | 841046d1-5249-5fd9-87dd-ef9cca9f2528 |  | note | - - - - - - - - -
label | c6a64d86-010e-5894-acd3-d7d88b0077c5 |  | note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
label | e1e35304-8277-5f8b-9cea-6ffed620e07e |  | note | - - - - - - - - -
label | bb13ceaf-cc36-57d8-a8ac-8fce50c64967 |  | note | Reference Documents: Project Drawings / Drawing Register
label | 29236646-cfbd-5e7e-96a5-af2f10a13ee3 |  | note | - - - - - - - - -
label | d7f66dc8-4387-55a2-9a85-45f1080d4b5e |  | note | Inspection / Test Method: Document review
label | 6771573d-55c7-52a8-8173-116e9676b524 |  | note | - - - - - - - - -
label | f5b5907c-efc5-5a80-a229-3842d87e422a |  | note | Record of conformity: Latest Revision Drawings
label | 82cc52e5-6276-5bdd-9994-d88427a1bf8a |  | note | - - - - - - - - -
label | fa3a89dc-f94b-5f40-862e-1929c10fac98 |  | note | AP
label | b06869e5-d14b-53f3-8bc3-faf397791abc |  | note | - - - - - - - - -
label | 23d735a0-c73d-569e-897d-d45d4d6476a4 |  | note | Responsibility: Site Engineer / Site Foreman
checkpoint-status |  |  | checkpoint | 1.4 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
label | 54dfbedc-7e44-54ea-8df8-501d715c7cc4 |  | note | Frequency: Prior to Commencing
label | 5c43a774-ff33-5250-a748-ec3d692d1b0c |  | note | - - - - - - - - -
label | 43e42398-fea6-5965-bdb1-b6fcd17141a6 |  | note | Acceptance Criteria: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | 6e770e69-617b-5b55-a001-69c4f0e5e66a |  | note | - - - - - - - - -
label | 33593e63-c2ba-5cfb-96be-df832c2ff0bc |  | note | Reference Documents: EMP, Site induction
label | aa8989e0-190c-54c9-8acb-af94aa339498 |  | note | - - - - - - - - -
label | a654e6b1-c7c3-534b-a8c9-09e6c12d51cd |  | note | Inspection / Test Method: Document review & Site inspection
label | 920df541-da50-5631-a63c-2950c687c917 |  | note | - - - - - - - - -
label | 2abfc106-e7d0-5641-9139-210cf5b32527 |  | note | Record of conformity: Signed ITP
label | f26e3561-bdab-56b6-89b8-3d5a5310e470 |  | note | - - - - - - - - -
label | f67377d1-6055-540d-b265-0f746f6035c3 |  | note | IP
label | de5c988d-1174-568c-ac49-e4b7f6da7fd8 |  | note | - - - - - - - - -
label | a4820990-cdb6-5018-8680-de6742b53603 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 1.5 - Confirm suggested Asset treatment has been approved by Utility provider
label | 9b520a93-fb28-5cae-a88d-57919bc8dd73 |  | note | Frequency: Prior to Commencing
label | f54c7df0-1a82-5e76-a359-5fd8664fc5b8 |  | note | - - - - - - - - -
label | 764445c3-3939-5824-a98d-aca085c5123b |  | note | Acceptance Criteria: Ensure that adequate notice is given to the Utility Service provider and Superintendent prior to utility asset protection as per PS3120.06 part C Date of Notification: Date of Utility Provider approval:
label | b9c34c19-c45d-5e24-913b-c1a5adf132e0 |  | note | - - - - - - - - -
label | b0c9c5c0-b10b-53c5-996e-0b83d5aaf9e3 |  | note | Reference Documents: MRPV- ITC Delivery Contract
label | dc92eef3-dc4a-5151-89d4-4b17fd0f0954 |  | note | - - - - - - - - -
label | e012e14c-5728-54d6-a1d3-a0e690867459 |  | note | Inspection / Test Method: Document review
label | 9081b0df-b97c-53d6-b500-2b4c119f0b18 |  | note | - - - - - - - - -
label | 321b9a2c-0633-5662-b217-09df21fd1fc2 |  | note | Record of conformity: Signed ITP
label | 6196824f-91f6-5145-a229-319e1b7ed007 |  | note | - - - - - - - - -
label | b47f96c8-b58a-5c5a-8dcf-79931cd2e965 |  | note | AP
label | f426d2dc-6d4b-5c42-99f5-1f6767d761eb |  | note | - - - - - - - - -
label | 2311875b-1ca3-5eb0-81a6-148a4fea9939 |  | note | Responsibility: Site Engineer
checkpoint-group |  |  | section | 2 - Procurement
checkpoint-status |  |  | checkpoint | 2.1 - Approved materials ordered.
label | 948513b3-cbef-5e11-96cf-a65bbc43d265 |  | note | Frequency: Prior to excavate
label | e8cdbb9b-3665-57a3-8251-ac261a974a1f |  | note | - - - - - - - - -
label | 5cc5a9dc-7fbe-580c-815d-c0104044006e |  | note | Acceptance Criteria: Complying with AECOM Utility Protection Detail Drawings
label | 157824dc-f714-5dba-b1fd-9e6e2d0c114e |  | note | - - - - - - - - -
label | f386ff64-d1c4-5aa0-8d49-2ed74ed41899 |  | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2126
label | 8e154739-9735-52bb-bf14-a579abe77509 |  | note | - - - - - - - - -
label | 962f6b23-058b-53ba-8daf-5ee5ad532a7a |  | note | Inspection / Test Method: Site Inspection
label | 919fc636-cfe5-565e-86ce-a3719d53ef32 |  | note | - - - - - - - - -
label | 39986a0f-79bd-56a5-abc2-2dbec856bb5c |  | note | Record of conformity: Supplier's Declaration of Conformance.
label | 3ab4a1b5-901c-5d66-b8ce-d42114e658dd |  | note | - - - - - - - - -
label | e46b3115-378c-5dbc-a228-066c146260ca |  | note | SCP
label | 1675c568-3741-5871-bd55-ab430ee183e2 |  | note | - - - - - - - - -
label | e0d87231-0a64-5822-ac65-ff6ceca0f559 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 2.2 - Receival and Inspection of products.
label | c7c270cb-a744-5f78-92e2-046796cecbbc |  | note | Frequency: Upon receival
label | 3002420d-f4e7-5d1a-a7c4-8f43446f6a40 |  | note | - - - - - - - - -
label | ecf43d79-2b34-560e-ad9a-f47383bd8b75 |  | note | Acceptance Criteria: Approved Product and supplier. Right dimensions / specifications. Defect Free.
label | 8480bb78-e8ce-5ca0-bb2e-dd2a7eb34d20 |  | note | - - - - - - - - -
label | 317c5102-1c9e-5696-8d77-0f6c14d93e0d |  | note | Reference Documents: Receival & Inspection Checklist
label | 45fb9dc3-e013-5620-aed4-e8c21b99b040 |  | note | - - - - - - - - -
label | 2ea0c4a7-f1b6-5a96-8bb4-744ac3ca7e93 |  | note | Inspection / Test Method: Site Inspection
label | aa858698-af4c-5964-8a91-ee544477737b |  | note | - - - - - - - - -
label | e6acdef9-1d88-532e-90c3-9376156bfae1 |  | note | Record of conformity: Completed Receival & Inspection Checklist
label | 47f35468-9515-5ab7-aeeb-8b4f889b5a65 |  | note | - - - - - - - - -
label | 88d8b380-fbfc-5d0d-bd77-61b20d4df0bf |  | note | WP
label | bae76db0-8036-5760-85ed-a303601de4e7 |  | note | - - - - - - - - -
label | 28882dbc-7402-5c8d-b3e0-cb71a17b6b43 |  | note | Responsibility: Site Engineer
checkpoint-group |  |  | section | 3 - Construction Works - Detail 1 - Stabilised Sand Encasement
checkpoint-status |  |  | checkpoint | 3A.1 - Survey set-out
label | 643ecc9c-b57f-5b4c-82d0-57dadbb2690e |  | note | Frequency: Prior to Commencing
label | 4d602b8d-8468-5781-bd24-48838f304993 |  | note | - - - - - - - - -
label | f14f362a-cd6f-5db4-b0ee-15edafce6a1f |  | note | Acceptance Criteria: Latest available revision used
label | dabd3de2-ea96-59e0-8264-bdb5a528c1c8 |  | note | - - - - - - - - -
label | 51096811-fe85-574e-91f9-654ad1228040 |  | note | Reference Documents: Drawings
label | 64c1a1f9-96fb-5e87-a0cd-a6816f43eb87 |  | note | - - - - - - - - -
label | 586347e4-1739-502b-ab99-6fad11cc864a |  | note | Inspection / Test Method: Site Inspection
label | 5035556a-5837-5494-85ad-2be03fb1b7f5 |  | note | - - - - - - - - -
label | 14b18f73-8b81-5e85-8c8a-e620986cbcf8 |  | note | Record of conformity: Survey records & pegs on the ground
label | da6a528b-9b67-588a-87ed-c6df4cbb816f |  | note | - - - - - - - - -
label | 3c668652-cb9b-5c55-8b1e-982962378cb9 |  | note | SCP
label | 0b2f6213-806e-59d7-a7c4-7ac5f27f13b4 |  | note | - - - - - - - - -
label | 73b98680-022d-59fa-a73f-f58bd30e1449 |  | note | Responsibility: Site Engineer & Surveyor
checkpoint-status |  |  | checkpoint | 3A.2 - Excavate and expose Pipeline
label | 4426bf33-f40c-50c1-a7d5-a615061a5f59 |  | note | Frequency: During construction.
label | f79c2db1-72f3-5164-a763-9c7a47892e75 |  | note | - - - - - - - - -
label | c6876a49-6292-57f9-a7af-7615c0a604f0 |  | note | Acceptance Criteria: Ensure that the minimum cover requirements, horizontal and vertical alignments are within tolerances.
label | 9f77518a-e7e0-583c-9e14-9c1520444de8 |  | note | - - - - - - - - -
label | ab1d919c-0976-5d06-84b5-dd7f8d97f62a |  | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2126
label | 9db1839f-03ad-5f33-8fad-9fd48b994e9a |  | note | - - - - - - - - -
label | 36bdd697-eec3-53ca-8ea5-a1415d860e4b |  | note | Inspection / Test Method: Document review & Site inspection
label | 6b574ac2-f7b4-59c2-b13c-b868f13a6025 |  | note | - - - - - - - - -
label | 90bb8f37-e0cd-5912-a769-8b0998d1b639 |  | note | Record of conformity: Signed ITP
label | 28215bd5-d7b5-5dc4-9138-c4032a2536a7 |  | note | - - - - - - - - -
label | bd0627c2-45eb-5d07-b367-52102caabefd |  | note | AP
label | 75004a74-49c6-55e3-a49f-45538dc4f06e |  | note | - - - - - - - - -
label | fd4515dd-5bb5-5ea6-a7ba-cdddf3cca078 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3A.3 - Survey pick up
label | ec072f3b-1ed2-5733-ae60-8508dda36bf7 |  | note | Frequency: During construction.
label | 495c196f-5d28-5ccd-8bff-73b5acb17863 |  | note | - - - - - - - - -
label | 9df012fb-b2bc-57fe-a85a-bb08beedce7e |  | note | Acceptance Criteria: Once asset has been completely exposed surveyor is to complete a survey pick up at multiple points across exposed asset.
label | 12688a45-3069-56f7-8a7d-509e2d1f4695 |  | note | - - - - - - - - -
label | 7f972b69-8205-571d-a1aa-8323d978b44a |  | note | Reference Documents: As Built documentation
label | 123f626d-abde-5db5-81ca-09a987dd28b8 |  | note | - - - - - - - - -
label | bf2fe72c-dc58-5fdb-bbf2-bedbd24f1441 |  | note | Inspection / Test Method: Site Inspection
label | 2e35e74d-9ddc-58cf-8abc-4d0670f45c36 |  | note | - - - - - - - - -
label | d45e23b1-795d-5d5b-9f9a-48ef83f9fa99 |  | note | Record of conformity: Survey records
label | a07973c2-d045-5e0d-af80-47babc093fb5 |  | note | - - - - - - - - -
label | 1ccbfbf3-1c18-5cc9-a127-6765e5816718 |  | note | HP*
label | 056572e2-efcf-5266-8e85-f1227a6da6d0 |  | note | - - - - - - - - -
label | c2f08a94-b319-5812-b3a7-bfad5ca5d5d7 |  | note | Responsibility: Site Engineer & Surveyor
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3A.4 - Place pipe protection material
label | ce3eb18d-c714-5fd7-9bdb-399891ac2156 |  | note | Frequency: During construction.
label | e1995181-9b00-5d04-86be-51878d40bc6c |  | note | - - - - - - - - -
label | 96e8613d-0da8-57cd-8f5d-9abb4135f9cc |  | note | Acceptance Criteria: Detail 1 - Place 5% stabilised sand uniformly along length of pipe, work into place under pipe haunches. Min cover requirements - 300mm either side of Pipe, 150mm below pipe and 450mm above pipe. Marker tape to be placed above protection.
label | 6ba176f1-bc7c-5a71-bbc3-e99e4538a103 |  | note | - - - - - - - - -
label | 8031cda5-5c5c-565c-b13b-c2847ef7f00c |  | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2126
label | e27809b8-e036-5063-9608-b9d87600104e |  | note | - - - - - - - - -
label | 90e242fb-02c4-5561-a535-b7f7f2d56d7b |  | note | Inspection / Test Method: Visual
label | c31db8ad-f545-5534-91a0-9afad1e01087 |  | note | - - - - - - - - -
label | 5efb3600-ace2-5f47-a438-97c137880e86 |  | note | Record of conformity: Signed ITP
label | 3102f1c4-a153-5814-9e47-06ebc6a1da90 |  | note | - - - - - - - - -
label | f4c1cd25-ff66-54af-997c-80cbc09556c5 |  | note | WP
label | ed95c614-5543-50bb-afa1-d5adc699e23f |  | note | - - - - - - - - -
label | fa041d2c-c37c-567f-aef5-9547e5dd31b3 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3A.5 - Survey pick up - Encasement of Asset
label | a7b70192-fbcb-5b07-ac1c-f6448c7a4b6e |  | note | Frequency: During construction.
label | 88f78b34-5935-5359-b48b-5ee3655a0b72 |  | note | - - - - - - - - -
label | b0e5dd25-d471-5b67-a130-856eae043bdb |  | note | Acceptance Criteria: Once encasement of stabilised sand has been completed the surveyor is complete a survey pick up across multiple points on top of asset protection.
label | 9956b24e-1927-545e-b90f-041e2339d0a4 |  | note | - - - - - - - - -
label | 6001f6e7-d3fd-5277-848d-dd75db16b5f5 |  | note | Reference Documents: As Built documentation
label | 103fa29e-bb4a-5416-9134-1cb59d046c57 |  | note | - - - - - - - - -
label | 14b30791-3391-5491-9cd4-a74622dede1a |  | note | Inspection / Test Method: Site Inspection
label | 7c659967-a852-5b99-902e-e1da30df93eb |  | note | - - - - - - - - -
label | 313bd7ca-7926-577c-8907-994dc63b9881 |  | note | Record of conformity: Survey records
label | c66ca762-8889-57a0-9b5f-cecdb3c6078f |  | note | - - - - - - - - -
label | 81331ccd-dab6-5c84-9e8b-6708e7c0cdcd |  | note | HP*
label | 603ed611-83cf-584e-b523-dd0b04470d98 |  | note | - - - - - - - - -
label | 3c76e6a4-1fe2-5d6e-99e5-da39d2bc5f4a |  | note | Responsibility: Site Engineer & Surveyor
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3A.6 - Compaction Testing (where granular material forms part of permanent pavement)
label | f872660e-79b1-5c65-a603-f8456e81c6e2 |  | note | Frequency: Each Lot
label | 8f60d5bf-5b1e-5784-b467-5c14e8fe79ed |  | note | - - - - - - - - -
label | c1b8c2d9-37d3-5f0e-a61b-03d5de0afc5b |  | note | Acceptance Criteria: Material during compaction shall have a moisture content of not less than 85% Compaction Scale A requirements apply Lower & Upper Subbase layer - Not less than 98% Compaction Layer directly beneath bituminous surfacing 100% Compaction
label | 17631535-24fa-5f5a-91b4-16153a62cc6f |  | note | - - - - - - - - -
label | eabb470e-74d0-56d7-bf2e-91ed69b4829b |  | note | Reference Documents: VR304 Table 304.08
label | 6c8e93a1-1f73-5b5d-99ae-293dfe4c8c56 |  | note | - - - - - - - - -
label | 84d7411f-6a5f-5978-baba-b2258c2483dc |  | note | Inspection / Test Method: Compaction Test
label | 94fff31b-30ab-55ec-a6f2-9f1cf8ebcc61 |  | note | - - - - - - - - -
label | 72f0e758-8e27-5610-a6b9-d0d6b8646b94 |  | note | Record of conformity: Test Results
label | 9b8d7987-c64e-5d0a-b7d4-7e0afc6192b9 |  | note | - - - - - - - - -
label | ff73b306-6124-5849-be78-4f7d14023845 |  | note | TP
label | b74c1e57-35f4-5a2c-9f31-538bd6679dab |  | note | - - - - - - - - -
label | af510152-508d-56f7-b115-38b6a7154d88 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3A.7 - Post Compaction Grading (where granular material forms part of permanent pavement)
label | 571ab156-05af-5b0c-bf49-65ca2de430ae |  | note | Frequency: Refer to table 304.111 for various minimum frequency or testing for Grading and PL
label | aa456df8-a3d6-5335-988a-fcc8db753adb |  | note | - - - - - - - - -
label | 6e6e768a-78a1-5e35-a5ab-be40eb91b549 |  | note | Acceptance Criteria: Grading and plasticity testing to be conducted post compaction
label | a1cc1a39-b079-5c6b-b860-10f909695ea8 |  | note | - - - - - - - - -
label | 2d59440e-255e-5c5d-8592-cb8291036a9e |  | note | Reference Documents: VR304 Table 304.08
label | 814f5221-3f3f-5fb4-858d-f69673f582f6 |  | note | - - - - - - - - -
label | 8475eb59-e17b-58a4-9ea5-01604eabc5d1 |  | note | Inspection / Test Method: Compaction Test
label | c64d112d-2720-5e43-b8fc-b7b6a0665e77 |  | note | - - - - - - - - -
label | e16c67da-008a-5a75-bb04-b886a5f0ac76 |  | note | Record of conformity: Test Results
label | 26bb005d-2148-5840-bb56-435986d067e3 |  | note | - - - - - - - - -
label | f965be53-fc95-5293-a48d-2ed9c560d320 |  | note | TP
label | cf06d49f-e617-5055-b5ae-954c9044533a |  | note | - - - - - - - - -
label | 58923f55-14e3-5f65-9b3f-df15c9fd8b20 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3A.8 - Backfill Trench (where material forms part of permanent works)
label | a830a5cf-2a29-5651-ad52-68d45f31b035 |  | note | Frequency: During construction.
label | eee45d20-496a-544e-bea4-7312ec462e63 |  | note | - - - - - - - - -
label | a772d1f0-fad9-5237-a032-423f832024b9 |  | note | Acceptance Criteria: Superintendent approved backfill material is to be used for backfill asp 1145-C201-ACM-CVP-DRG-2126 Backfill is to be compacted in layers to achieve specified density uniformly throughout the depth of each layer. Material: Inorganic fill material with 75mm max. stone size (non trafficable) 95% Dry Density Ratio @ 1 test in each 900mm of fill & each 100Lm
label | a48ff5f1-1e02-5349-af82-23dde5e085a8 |  | note | - - - - - - - - -
label | eb49ef34-2bb1-540a-8744-3cb258d4f652 |  | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2126
label | 44dce49c-5aab-5c3e-9357-be5c0eb58adf |  | note | - - - - - - - - -
label | 7f25e4df-674a-5063-b08f-bb8954e0c4ce |  | note | Inspection / Test Method: Visual & Test Reports
label | dbce6008-0eed-5f96-a670-83cbeddfafe0 |  | note | - - - - - - - - -
label | 2a57792e-9b79-56dc-ba3b-8a39f4c44319 |  | note | Record of conformity: Signed ITP
label | 2f2304a6-08a6-5bb8-8d99-9762ab3abc50 |  | note | - - - - - - - - -
label | 27199674-4c82-57b1-8a6d-f94031141471 |  | note | IP
label | 743ec5f7-3934-507f-adc7-8045752af625 |  | note | - - - - - - - - -
label | 632fbfe4-9b19-57f0-b9fb-55c77eb7ec5f |  | note | Responsibility: Site Engineer & Superintendent
checkpoint-group |  |  | section | 4 - Completion
checkpoint-status |  |  | checkpoint | Test Requisition
text | cb3d3966-a9e7-5160-835a-80581d133c90 |  | textbox | Test Requested on
text | 2812f0f9-575c-5095-b2a1-941b6fd5faae |  | textbox | Location
select | 8f074d86-a8d1-5cad-87e6-dce28ca32b9b |  | dropdown | Material Type | Type A,Type B,See comments
select | 3e14e837-fcc5-56b2-a283-a61db8f40c2d |  | dropdown | Material Source | Holcim,Boral,See comments
boolean | 24c01b45-2fc4-5195-8e31-861a30b72fc5 |  | tickbox | Compaction Test (Standard)
boolean | 7b38f9ca-0e22-55a5-8b96-0bf31ab33fc3 |  | tickbox | Compaction Test (Modified)
boolean | 24bb656d-cfc9-51eb-88fb-5fe2727cf886 |  | tickbox | Maximum Particle Test
boolean | 3fd86082-aacf-5e82-ac4a-76457a449b8b |  | tickbox | CBR/Swell Test
boolean | c0918b70-d646-5187-90b7-4d2e3ee3e297 |  | tickbox | PI Test
boolean | 40ff92f5-4f23-5fc0-b060-8252a69f0782 |  | tickbox | Permeability Test
boolean | d78d8b3b-dfc6-5712-9a4a-34a841913de7 |  | tickbox | Grading
boolean | e6000dc2-4b20-5cbb-974d-8e4498514a2a |  | tickbox | Moisture
boolean | fbb86395-922c-5327-b081-30040439a4c1 |  | tickbox | See comments
text | e9332f0c-bee9-5446-88d1-c0cc3d87de1d |  | textbox | Test Level/ Layer
holdpoint |  |  | signoff | Test Requisition
checkpoint-status |  |  | checkpoint | 4.1 - Surface Reinstatement
label | b89def98-e8e8-57a9-beb4-bb0c2cef728a |  | note | Frequency: Completion of works
label | 09442995-3164-5c18-a33e-5aa5a44ce706 |  | note | - - - - - - - - -
label | f78b0c35-3987-53db-b1f4-f38ccfe675fa |  | note | Acceptance Criteria: Surface reinstatement similar to adjacent undisturbed materials, visually accepted by Superintendent's Represented
label | b3c35de9-aab8-564f-a1c1-5d8d4b34db62 |  | note | - - - - - - - - -
label | 27ef2102-581e-58b9-8087-27df91baddd6 |  | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2126
label | 4f161ce5-ca24-53ee-a8e4-5edcf433786a |  | note | - - - - - - - - -
label | 9535e301-5f66-5a35-9616-de1cb60e6757 |  | note | Inspection / Test Method: Visual
label | a8ee00db-12ac-5be4-9e13-c4ad98dff8b6 |  | note | - - - - - - - - -
label | 70e796ed-ad88-5506-850b-eb73b56b9021 |  | note | Record of conformity: Site Inspection
label | 4b80b3d5-e7d8-5603-93e4-2b18c748cae7 |  | note | - - - - - - - - -
label | 937b0c27-9c4b-571d-a22a-9271ae48a382 |  | note | IP
label | c3f93a8d-465a-54f1-b013-add7231edf8f |  | note | - - - - - - - - -
label | c745529e-9c52-5a01-b03b-26831d6af553 |  | note | Responsibility: Site Engineer & Superintendent
checkpoint-status |  |  | checkpoint | 4.2 - Survey data captured for as-built purposes
label | d390fa51-de91-5175-ab91-3b3a619de94b |  | note | Frequency: Completion of works
label | f1308124-b6bc-5917-9400-73752cec293b |  | note | - - - - - - - - -
label | 6df739b0-c238-5fb9-a465-995c7d026491 |  | note | Acceptance Criteria: As-built Drawings Tolerances as per WSA 02 - 2014-3.1
label | f4851bde-ef08-581e-b7c9-2bf4eba11fd2 |  | note | - - - - - - - - -
label | 527f2bf8-7529-5fc1-ac90-2a79947766da |  | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2126
label | cc176986-f91e-527b-b8fb-2943cb67e042 |  | note | - - - - - - - - -
label | 47bf9d18-faef-576e-9120-a7b05413bbef |  | note | Inspection / Test Method: Document review
label | c49b84d0-c810-5579-836f-2f06c0654db6 |  | note | - - - - - - - - -
label | 62f468f7-64c5-5c89-82e3-2cab6bddb325 |  | note | Record of conformity: As-built survey records
label | f1227df4-6c02-5108-a9a6-a4a4ef454ffc |  | note | - - - - - - - - -
label | 1dafdc7f-c7af-5643-8b42-d439698d4c1d |  | note | AP
label | bccdb242-bc1e-5708-bb93-672488a973b8 |  | note | - - - - - - - - -
label | 044c0a64-17c0-5053-817b-db610076d4b9 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
label | 393fc759-acd0-5541-bc29-b2ba632de0bd |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | c0beb703-dac0-5f8c-80bc-7ae22f90a774 |  | textbox | Print Name:
text | 6a9c61a1-ffb5-55c9-abcd-fb2b0f7a0ac5 |  | textbox | Position:
date | e447ad69-edc9-57c7-b743-65c89a7b26f3 |  | date | Date:
date | 90f78467-d547-5571-ace1-3da9d5bf848c |  | date | Work Completed On
checkpoint-status |  |  | checkpoint | Lot Verification.
select | 48b44941-ee7f-5093-939a-2afa28791c0c |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | 82bd8b63-fe2e-5e54-b7ab-6045284cb1fa |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | 2c2090fd-cc26-5002-86c1-b15b6e85375c |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | 58e69e74-68df-5812-9e8e-752926e837a1 |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | a3e270c7-659b-58d6-ad04-54857cedca26 |  | textbox | Other:
select | 47e8b1bd-9bdf-571d-8402-f4f4006bb102 |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | 4a621eec-d596-5368-bf69-ebc8931801f8 |  | date | Lot Closed On
text | f69d640c-1155-5b3e-a180-d50473b44821 |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-066-UT-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0066 - Directional Drilling | 464e2bba-b167-4250-b5d1-2fedcd7a21ed
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | 0510bf20-19ba-5e03-8267-d5768af6aa19 |  | date | Lot Created On
date | 9abdaf47-0de6-51e4-92bd-c5fa52e78b10 |  | date | Lot Opened On
date | 2d36f4cd-342d-520d-9bd4-1ea9ee0aa450 |  | date | Work Commenced On
select | e6737e1c-03f3-5ccd-a61d-cd20164cd387 |  | dropdown | Lot Type | CIL-Civil Lot, DRL- Drainage Lot, EAL- Earthworks Lot, ELL- Electrical Lot, UTL- Utility Lot, STL- Structural Lot
text | ea01f18e-285f-5149-b53f-180dcd10a309 |  | textbox | From and To Chainage
select | 0cd240a8-b569-54a5-905d-9836e5c2ab0f |  | dropdown | Construction Element | SITE - Site General
select | 13209d5c-8484-5f68-96fb-bb68ee511376 |  | dropdown | Activity | OTH - Other
select | 64420806-fa2d-52eb-ba4f-795f5e390a80 |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | 992b0341-a6b8-5065-8e17-d51ea8877019 |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | 7ac41804-faf3-50b4-b213-90449430b05c |  | textbox | Engineer Responsible
text | 9419c2da-b6f1-5314-84e5-25d603912e55 |  | textbox | comments
checkpoint-group |  |  | section | 1 - Preliminaries / Pre- commencement activities
checkpoint-status |  |  | checkpoint | 1.1 - IFC / Shop Drawings Submission & Approval.
label | 066fff23-c351-524a-8a05-e387ff7b90e1 |  | note | Frequency: Prior to Commencing
label | e013947b-9160-572f-919c-592940aa11f4 |  | note | - - - - - - - - -
label | 8b3be1bd-1ba0-54f7-9cb8-0bc570d61cc1 |  | note | Acceptance Criteria: IFC Construction Drawings & Most Current Revision.
label | 8e6be179-6960-543a-af72-d50ee46688c9 |  | note | - - - - - - - - -
label | 57c90699-2f1d-54b2-932e-596556ccf813 |  | note | Reference Documents: IFC Drawings
label | 91d8cbf3-baba-5502-9ae0-d50341d37885 |  | note | - - - - - - - - -
label | 64489d9c-4f7c-5e75-ad8d-656dd286e280 |  | note | Inspection / Test Method: Document review
label | 4097d97d-a4f4-565e-95fd-85916e6f64e9 |  | note | - - - - - - - - -
label | 78bc5823-b32d-5ff7-a9a4-05b6eaa89bb5 |  | note | Record of conformity: IFC Dwgs
label | def8868b-3bb8-5d34-9ade-c9cb06c57d33 |  | note | - - - - - - - - -
label | fbd77e93-456a-5817-aaab-2e9af2684d7e |  | note | HP*
label | b0da4052-3194-57f9-854f-0f92843ef825 |  | note | - - - - - - - - -
label | 9211ba1f-3cdf-5413-a53f-b7a65c022213 |  | note | Responsibility: Project Engineer
checkpoint-status |  |  | checkpoint | 1.2 - Survey Set-Out
label | 50275f27-80a3-5681-a5bc-09af77aa9902 |  | note | Frequency: Where Required
label | 3d968144-dd33-5b06-a774-250e85aa820f |  | note | - - - - - - - - -
label | 12bfc581-24bf-58bf-8d74-4b7899f487d3 |  | note | Acceptance Criteria: Qualified Surveyor to set out extent of works on ground
label | 4db49e08-0926-53c2-8ec9-d9a8d752d8a3 |  | note | - - - - - - - - -
label | b3da18e6-aa74-5643-8086-41387fc845c2 |  | note | Reference Documents: IFC Drawings
label | e4b4f735-41bc-553a-8683-0cdf1b54e1fe |  | note | - - - - - - - - -
label | 11cc4b5a-b31d-5dc1-a822-716c31519bc2 |  | note | Inspection / Test Method: Survey
label | 881d81e3-c9af-563e-add9-593c85ed9553 |  | note | - - - - - - - - -
label | 9b78b166-5e24-5627-9c9a-e70dc4cc44c7 |  | note | Record of conformity: Survey Calibration Certificates
label | e0ef0084-6b5b-569f-9404-8f47a22ffb02 |  | note | - - - - - - - - -
label | 69a1a44f-bdcd-5693-98b4-ceb3da657cb5 |  | note | WP
label | 1e3d9789-26ad-5dbd-b0c9-32a2510d94dc |  | note | - - - - - - - - -
label | 30d02e07-960d-5bc0-949b-e4b58e361838 |  | note | Responsibility: Supervisor
checkpoint-status |  |  | checkpoint | 1.3 - Excavation Permit/ Service Location
label | b8b06b3d-1456-5a60-a840-8b5bc1036c64 |  | note | Frequency: Prior to Commencing
label | 6eef006f-b9aa-5348-b402-488b2a30b5df |  | note | - - - - - - - - -
label | 8c1a07b2-e44e-5aa5-9aa0-2db6c8d91c3b |  | note | Acceptance Criteria: Identify underground services NDD/hand dig as necessary. DYBD documents
label | 788a4e13-ca3d-5d9d-8a87-60782d0b3567 |  | note | - - - - - - - - -
label | 3e4c520c-0669-5c9f-ba64-9d2b4535ed3a |  | note | Reference Documents: Dial Before You Dig
label | b5752426-8d5a-5f88-91f6-2799da0ae0bf |  | note | - - - - - - - - -
label | 1b7bdff9-766b-5bf1-a3ac-96d2554a8f48 |  | note | Inspection / Test Method: Survey
label | aa9dfc87-43ef-5639-93e1-a21d57c947ff |  | note | - - - - - - - - -
label | 454ac3e6-c63f-5274-b397-b0d5c3be6c75 |  | note | Record of conformity: Excavation Permit
label | 11d1bf36-8a56-5e72-9158-9304416a955b |  | note | - - - - - - - - -
label | 8500da4d-a8a6-54fe-82fe-ca4e6622d746 |  | note | HP*
label | 2c7bf04e-3d36-5d07-8d5c-56626f24e34f |  | note | - - - - - - - - -
label | 6ab5a59f-b631-51ed-86a0-59114b4b784e |  | note | Responsibility: Supervisor
checkpoint-status |  |  | checkpoint | 1.4 - Superintendent Notification
label | 5e222402-f9ab-537c-8156-ade96f84357d |  | note | Frequency: Prior to Commencing
label | 5ef08f4e-31e3-5879-a496-cbab97742186 |  | note | - - - - - - - - -
label | 306d93c0-4a18-545a-98fc-7efd0397b24d |  | note | Acceptance Criteria: Detailed proposals for boring under carriageways shall be submitted to the superintendent for review two weeks prior to the programmed commencement of work
label | 8b491862-ab91-51e9-844b-9dd39ff5c99b |  | note | - - - - - - - - -
label | 717f7404-e745-5baf-b7d6-f49e018dc8fd |  | note | Reference Documents: VR 733.03
label | b125b69c-88b4-544e-8771-0721aa491132 |  | note | - - - - - - - - -
label | 393d04bb-4548-5372-a2d9-f0dcd73ff2cb |  | note | Inspection / Test Method: Document review
label | 0cc5c96d-b586-5858-b27f-352d6146f621 |  | note | - - - - - - - - -
label | 62907807-7684-5caa-ba84-94860971c8f2 |  | note | Record of conformity: IFC Dwgs, This ITP
label | 186b7af1-0265-5d6c-abce-4a6a4085bbc0 |  | note | - - - - - - - - -
label | 6edbd5ee-14d7-5216-a466-f0b891f71fe1 |  | note | HP
label | c97c9c07-3c79-5bad-9f54-c83d8da0e6a7 |  | note | - - - - - - - - -
label | e6193f12-1253-5565-8b1a-5c3cee6fbc44 |  | note | Responsibility: Project Engineer/Superintendent
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | 2 - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Conduit Sizing
label | b621a40f-e2d8-56d7-99c5-a11e9415ea1f |  | note | Frequency: Prior to Commencing
label | c326283e-3c43-5c92-8f9d-e994dc70582f |  | note | - - - - - - - - -
label | d08624f0-1a78-58b9-ba59-4b1eb6b4daa6 |  | note | Acceptance Criteria: Conduit sizing to comply with VR table 733.021
label | d58b4e39-4879-54bb-b816-e393eb090c06 |  | note | 100mm HD UPVC
label | 1971f7b4-fa2c-54a1-b406-61223aa49c70 |  | note | Electrical – 114.1mm OD & 101.7mm ID
label | 0af0f6ad-29d9-5df3-8d61-e419e055ef09 |  | note | Comms – 114mm OD & 104.5 ID
label | 2d9c4f7c-0d0c-5b61-a807-23803ff18f12 |  | note | Water and Gas
label | 37831242-ae32-5a07-8369-75a3e36856df |  | note | Gas minimum size 40mm
label | bffb4938-e21b-5ff4-ace3-f824ed396ce4 |  | note | Water minimum size 40mm
label | 56c750a7-c67d-5dbe-bddc-f81d64e3f389 |  | note | HDPE Continuous Conduit
label | de65b0fc-fb97-52a7-b01c-5d63e355d87b |  | note | Electrical – 125mm OD & 103mm ID
label | e885c96a-8a20-58ef-92b5-93f9af66fa3d |  | note | Comms – 110mm OD & 90mm ID
label | 70ca173f-93d2-5c5e-9d26-2f9c84d9f30e |  | note | Water and Gas
label | a627810e-40fe-5178-9a3d-2ad26dab829a |  | note | Gas minimum size 40mm
label | 563dce05-1971-541a-aea4-a164289143fc |  | note | Water Minimum size 40mm
label | 866fe713-6ad4-5f3b-8a75-c79ebab6be03 |  | note | Excludes utility providers designs and requirements
label | a7b8c1b7-efbe-5f73-addd-1e922c38b9be |  | note | - - - - - - - - -
label | 7cab9045-9af6-587f-8815-bcd82d78bd1b |  | note | Reference Documents: VR SS, Table 733.021
label | e0cd4536-8dba-53fd-9fd5-2019fa84f78a |  | note | - - - - - - - - -
label | c474bdf1-59a2-5810-89f5-7823f73d7b3f |  | note | Inspection / Test Method: Site Inspection
label | f20c513c-134d-5a52-ae65-81cf56b11b60 |  | note | - - - - - - - - -
label | 299f6f83-5bcc-5956-a639-ac95f92aa42f |  | note | Record of conformity: This Checklist
label | 0c4b15b3-5541-5330-8530-0507c2e3dd27 |  | note | - - - - - - - - -
label | 69ecb6d0-12bf-5605-af81-acec996a69c2 |  | note | IP
label | d801e672-e2c0-5a4a-a2d8-ba9796c58a1e |  | note | - - - - - - - - -
label | f4c25ada-bf6e-53d8-9a0a-29cad11dadb6 |  | note | Responsibility: Supervisor
checkpoint-status |  |  | checkpoint | 2.2 - HDPE Pipe Inspection
label | ec1008f2-320e-5675-bf2a-c3f2c411db82 |  | note | Frequency: Prior to Commencing
label | 6fd2a179-3cba-5798-ba03-559bc5c087d9 |  | note | - - - - - - - - -
label | 2f086d8b-6aab-5461-87f7-a6dcbdb4b614 |  | note | Acceptance Criteria: Conduits are to be excellent condition and inspected for defects prior to use
label | db65c4f6-6991-5f50-8930-80de25d5ed1d |  | note | - - - - - - - - -
label | 8a4eea34-f87d-583d-b654-f2ffa5dd082d |  | note | Reference Documents:
label | 81435b53-0b6d-5354-ab90-cbf014a034b7 |  | note | - - - - - - - - -
label | 6c817d6e-5e1f-5e57-afdf-0d5fbd6877b1 |  | note | Inspection / Test Method: Site Inspection
label | fa3d6d91-1fff-5b7b-85b9-af8460f38dd7 |  | note | - - - - - - - - -
label | 3f9df5c7-e0a8-52ac-ad0f-23d92d37507e |  | note | Record of conformity: This Checklist
label | e15116da-b122-5b6d-9639-326f1586d2c8 |  | note | - - - - - - - - -
label | c7c79498-c431-57da-868f-2b735d08b5e5 |  | note | IP
label | bb52b16c-1c6d-5e44-afbb-e4376db2974f |  | note | - - - - - - - - -
label | 3d23a3ff-a345-55f0-b9e6-ab01f7ba9325 |  | note | Responsibility: Supervisor
checkpoint-group |  |  | section | 3 - Excavation
checkpoint-status |  |  | checkpoint | 3.1 - Entry/ Exit Points
label | cd4060cc-81e1-5bc3-a49e-12cdd9d40a30 |  | note | Frequency: Prior to Excavation
label | 1bff47a7-d596-5a6e-95a8-4c6d01ace0b6 |  | note | - - - - - - - - -
label | a01be9b3-51e1-520a-a2ea-3c547235b062 |  | note | Acceptance Criteria: Entry/Exit points to be established
label | 373828e0-1231-5905-827c-1a8ff4a50a3f |  | note | - - - - - - - - -
label | e8805ff7-0190-5866-ab3c-8c0c5ce42b4c |  | note | Reference Documents:
label | dfbeb9ff-2ba0-5600-8881-acdb78f6f458 |  | note | - - - - - - - - -
label | cd6cc1cc-321c-5d37-81d2-266f4dd080ea |  | note | Inspection / Test Method: Review
label | d8d4ad3e-d3aa-5de1-b272-4dac46a77b9a |  | note | - - - - - - - - -
label | 1cb25a93-e54f-5ce0-8742-067113f15232 |  | note | Record of conformity: This ITP
label | 4909450e-fb24-5269-bab7-63c04873d8b9 |  | note | - - - - - - - - -
label | 16ea7fcb-d17f-5a42-961b-5c2d3e575534 |  | note | HP*
label | 27e52879-b6b5-5174-8523-52c048f1c3a8 |  | note | - - - - - - - - -
label | 30275e0d-24c2-5669-8718-bc232297b1a3 |  | note | Responsibility: Project Engineer
checkpoint-status |  |  | checkpoint | 3.2 - Minimum Cover
label | bf299dd4-25fc-5e16-ac19-c618efd2480c |  | note | Frequency: Ongoing
label | 30b98569-4c86-5250-9ac9-63b6d9a97de7 |  | note | - - - - - - - - -
label | a95d1c18-24c4-5a43-9618-e65e5fc8e15e |  | note | Acceptance Criteria: Minimum conduit cover shall apply as per table 733.031
label | 8437f41d-3f19-50d7-bf2c-998fb142e2e7 |  | note | Under Freeway Pavement – 1200mm
label | a4481132-fc33-5c40-8a94-910a7fc15a80 |  | note | Under Arterial Road Pavement – 1200mm
label | e4a2a0cb-03a1-5e60-956d-17eb1dbd2966 |  | note | Under Local Road Pavement –600mm-800mm
label | f2f97429-8ae9-5ffb-8d59-2f847008309e |  | note | Under Open Drains – 750mm
label | 01f17e6b-7127-5317-acc8-444cf9035d54 |  | note | Under footpath or unpaved areas (LV Circuits only) – 600mm
label | b3f870f3-9926-5cc1-8e17-eeec39ddd57c |  | note | Under footpath or unpaved areas (Extra LV or Comms conduits only) – 300mm
label | 13c347d4-1fec-5399-aceb-2090cb4ea7c2 |  | note | - - - - - - - - -
label | 707f86fa-9c63-57ac-a0c4-145c000d90fa |  | note | Reference Documents: VR SS 733.031, Refer Individual asset owners specifications
label | b9689664-2d7b-5ab1-82f8-85af0867d504 |  | note | - - - - - - - - -
label | 6a0cb418-1119-5e1e-a68d-dd6b989ed62f |  | note | Inspection / Test Method: Survey
label | 4f3ca3d8-a3e2-5753-bfce-fc2c42fa4196 |  | note | - - - - - - - - -
label | 70c325ac-9fbe-526c-ba96-9314a36bd039 |  | note | Record of conformity: AS Builts
label | 5512dbee-3462-5af4-bce7-987e63720d0e |  | note | - - - - - - - - -
label | 11a42503-459d-50b7-8aa7-ca9135f8cda5 |  | note | SCP
label | 645ca6d0-5a27-53ed-b9e8-b24d6f1938e9 |  | note | - - - - - - - - -
label | a3da5171-e63f-528c-9891-28a78f34ddf2 |  | note | Responsibility: Project Engineer
checkpoint-status |  |  | checkpoint | 3.3 - Survey pick up / Bore Mark Out
label | 27f98a10-e346-5edf-a8cb-367d63fdaeb2 |  | note | Frequency: During Bore
label | cd237da5-b7c9-5f5e-b2ef-0c9a237e6608 |  | note | - - - - - - - - -
label | 4b3b766c-6475-555e-84cb-77b572b8f9a0 |  | note | Acceptance Criteria: Bore head to surveyed at approx. 2m intervals and tracked beneath road. Survey to also pick up as record of conformity
label | 4a52f8f9-f063-5fb0-9e86-09d8a24051a0 |  | note | - - - - - - - - -
label | 0d64d0c9-1662-5b52-a399-dc56be080f2f |  | note | Reference Documents: Bore Tracking Sheet. Survey
label | 6c5f4432-250b-5e14-9550-4e601b574e33 |  | note | - - - - - - - - -
label | 73055f9f-a50c-5b58-bf96-c9212f5138fa |  | note | Inspection / Test Method: Survey
label | d3267823-46d4-5d0b-a0fb-7eeac5382ec1 |  | note | - - - - - - - - -
label | adb666dc-5dda-593f-8a95-2b208137201a |  | note | Record of conformity: AS Builts. Bore Log
label | a8e5a871-7ad3-5273-bcac-d2bb24cfb7dd |  | note | - - - - - - - - -
label | 3b68287f-f77a-5edc-a512-38fed1a74e29 |  | note | SCP
label | 3e9a775c-f0b5-5422-b430-98544a55f1be |  | note | - - - - - - - - -
label | 61af9ff8-7227-55fa-bea9-96d33dbda283 |  | note | Responsibility: Supervisor
checkpoint-group |  |  | section | 4 - Completion
checkpoint-status |  |  | checkpoint | 4.1 - Entry/ Exit Points
label | 89f7fe56-b458-5604-913f-760876a75603 |  | note | Frequency: On Completion
label | 38d9a0bf-581d-5aa2-8eb5-c3a0276b6401 |  | note | - - - - - - - - -
label | f875d21b-b7b5-525c-980f-197eb149342f |  | note | Acceptance Criteria: Ensure clean fills is used to fill in Entry/ Exit points
label | 61c1b1b5-2dc1-51de-8c09-d4f1dd98357d |  | note | - - - - - - - - -
label | 4e100bf9-432e-55cf-b459-d55b34a862fc |  | note | Reference Documents:
label | c9b0307c-3943-5458-9a69-d75a87b008f5 |  | note | - - - - - - - - -
label | 8b648f26-7d5c-566a-966d-27efa9887aea |  | note | Inspection / Test Method: Review
label | 6c4d046d-3d9c-55fd-8cd6-e847eef90766 |  | note | - - - - - - - - -
label | 4807ee65-c7db-5086-9bd4-ae37377a9b5b |  | note | Record of conformity: This ITP
label | ea0fbf17-ffc2-5615-aad5-9882e10667c0 |  | note | - - - - - - - - -
label | dfd70f03-4dc1-5569-b17f-ffeb4ff67ce8 |  | note | IP
label | 617f978d-f586-5c1f-8763-4979bb329a37 |  | note | - - - - - - - - -
label | 8fa14dbb-de20-5ea2-b717-98ad827457bb |  | note | Responsibility: Supervisor
checkpoint-status |  |  | checkpoint | 4.2 - Grouting
label | 2ac31562-428c-58e7-8c5d-2d1f7b579768 |  | note | Frequency: On Completion
label | a79a1d0e-00b0-5c69-b513-3e7e9e36df94 |  | note | - - - - - - - - -
label | 65b6d3f6-afe3-5688-ab18-f4458213ae06 |  | note | Acceptance Criteria: Unless specified on drawings, grouting shall fill the voids at the low injection pressures without causing deformation to the conduits within bore holes. The ends of the conduits shall be sealed watertight to prevent ingress of grout.
label | 069d777c-f869-55ad-9afb-44784b849cc2 |  | note | - - - - - - - - -
label | db4db7d7-cff8-59be-ba6e-f3ecead875d3 |  | note | Reference Documents:
label | 31e71811-da27-56e4-971a-89b559cae6fd |  | note | - - - - - - - - -
label | 4d832a24-8c08-53b9-9761-0f543d141f7b |  | note | Inspection / Test Method: Docket
label | c690ab5c-0f35-5d80-b098-284af6d7db2c |  | note | - - - - - - - - -
label | f62ee604-5ce0-5c19-9ea9-b5f49720ddef |  | note | Record of conformity: This ITP
label | 6387a80b-c37f-5b19-b54a-6a45d4916b92 |  | note | - - - - - - - - -
label | 9b2dfff0-0403-5f65-801d-6015a01bd564 |  | note | IP
label | 758824de-a2f3-55b8-a7bf-77be6db4b4c7 |  | note | - - - - - - - - -
label | 9736af75-55b4-5de8-8a55-595b96008a56 |  | note | Responsibility: Project Engineer
checkpoint-status |  |  | checkpoint | 4.3 - Backfilling
label | acf4209e-842e-5229-bb5d-40aba3c02176 |  | note | Frequency: On Completion
label | 2831c533-070f-5122-bb14-231d60a31db0 |  | note | - - - - - - - - -
label | c70d9029-e75b-5c95-9d43-2b2bafcdbcde |  | note | Acceptance Criteria: Before Backfilling the bore access excavation, the pressure grouting shall be inspected by the superintendent or representative
label | e291509a-bf5b-591f-9375-1d05bc2634db |  | note | - - - - - - - - -
label | ed3718b8-2a22-5081-b2be-a5ff84a6329e |  | note | Reference Documents: VR 733.03
label | 9f93a2cb-152f-5bb8-9649-68c24f4c671d |  | note | - - - - - - - - -
label | 23c243be-b723-51b1-93dc-deca1ec0b22a |  | note | Inspection / Test Method: Inspection
label | b509cbad-e51e-5b2d-b788-f54eeee70fdb |  | note | - - - - - - - - -
label | 10f20761-1a3a-5a69-a1ff-218ec9d48a82 |  | note | Record of conformity: Inspection
label | 5b574b7b-1e14-571d-8e04-b7040879a443 |  | note | - - - - - - - - -
label | a415119d-a0ab-5b28-ae3f-6baa0b797976 |  | note | HP
label | 474b4d17-5007-5bfc-95a6-7cdcec21fccd |  | note | - - - - - - - - -
label | 81881699-43b6-5a19-bb89-47bd1d2d032d |  | note | Responsibility: Superintendent and/or representative
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.4 - Draw Cord
label | f2136f2a-387a-5cd3-8780-7a71fae80713 |  | note | Frequency: On Completion
label | 7a8c3406-1ad4-500f-a9d7-e69af4fafdc7 |  | note | - - - - - - - - -
label | 404253cd-0f02-5cd2-9d84-b133bc3cd6d5 |  | note | Acceptance Criteria: Each conduit for electrical wiring and communications cables shall be provided one synthetic draw cord not less than 3mm diameter and a minimum breaking strain of 1.6kN
label | d877edbe-02e1-5416-9ffb-9c4043125570 |  | note | - - - - - - - - -
label | e87d7042-c0e4-593b-9f6d-2c9983eff97c |  | note | Reference Documents: VR SS 733.05
label | b4187db9-a18e-553d-9aab-6b0f3ef7251a |  | note | - - - - - - - - -
label | 28b08bb1-13e1-59a8-9235-0722c8d9d79b |  | note | Inspection / Test Method: Inspection
label | 09e9a205-6559-5e41-80ea-b6404b1f3848 |  | note | - - - - - - - - -
label | 8463822c-ca23-5037-bec1-5f0bf9417994 |  | note | Record of conformity: This ITP
label | 2e58754e-0b5a-5b4f-ade0-48b510999e8c |  | note | - - - - - - - - -
label | a7308fcd-5b34-5ffc-862a-79ee3829f742 |  | note | IP
label | aa54601b-cd0b-5ca3-9145-f59e1f516da3 |  | note | - - - - - - - - -
label | 1b47f47e-217c-5a31-8eb9-778a0773d043 |  | note | Responsibility: Supervisor
checkpoint-status |  |  | checkpoint | 4.5 - Site clean up
label | 76553985-59c7-5cf4-b1d8-bd6ec4cf935f |  | note | Frequency: On Completion
label | ff26e060-0e83-57b6-8772-028d25c7781e |  | note | - - - - - - - - -
label | a5683c54-1b15-526b-abfc-9efc6f0064cb |  | note | Acceptance Criteria: Ensure site is clean and all garbage has been removed
label | 95174388-fb4f-57d5-98af-9c05d585bb31 |  | note | - - - - - - - - -
label | b9c77eea-f9be-5126-8b41-9a5c5d26640d |  | note | Reference Documents: VR 733.09
label | dfae66c2-d7c7-510e-a564-af387918f2db |  | note | - - - - - - - - -
label | 36ea458c-22ed-5171-959b-a87d31ad0878 |  | note | Inspection / Test Method: Inspection
label | 34a72e97-020c-5340-8b89-0eade6f4f271 |  | note | - - - - - - - - -
label | 361b501f-4cf3-57d9-a3a6-f55329360e1c |  | note | Record of conformity: This ITP
label | 2d84ece1-f59d-5871-8032-b0dbd1c3c20c |  | note | - - - - - - - - -
label | 11a72af8-f304-5ba3-a3c4-ba2c04d7dae9 |  | note | IP
label | b3017a22-af2f-5fcf-bb79-ff5db41bf544 |  | note | - - - - - - - - -
label | 88b0ad91-2594-5aec-8b05-57a3dd6a54cb |  | note | Responsibility: Supervisor
checkpoint-status |  |  | checkpoint | 4.6 - Records
label | 33dbfd6c-a69f-5d21-ab5c-6ffc2a1dfa4b |  | note | Frequency: On Completion
label | ac11f811-f29f-52a7-8593-2c53f883e53e |  | note | - - - - - - - - -
label | c455d24b-3bb5-566b-a0ce-5506c581101a |  | note | Acceptance Criteria: Bore Logs of the works to be supplied from subcontractor
label | 159d00c8-17a0-5d88-b8d2-547dc71fea96 |  | note | - - - - - - - - -
label | af6a3a31-3196-5b0b-891f-74b5d60ed795 |  | note | Reference Documents: Bore Logs
label | 111a990d-9dd6-5853-95c0-f794ee4127e7 |  | note | - - - - - - - - -
label | 4e483537-2f0e-5465-8e02-344a280004ac |  | note | Inspection / Test Method: Document review
label | 05d86901-fea4-5dae-90c2-38af4cb64a68 |  | note | - - - - - - - - -
label | 56db3d1e-0f4f-56b7-8d6e-43068687295d |  | note | Record of conformity: This ITP
label | a7d81922-1750-55f9-8dd9-4a49253d40a0 |  | note | - - - - - - - - -
label | 4f975ea3-c147-54f0-b421-9b5c8602538b |  | note | HP*
label | 85cfba16-b859-54e4-bb4f-d18ab2e990aa |  | note | - - - - - - - - -
label | cb7312d3-9663-5dc8-9b30-d21ac532f453 |  | note | Responsibility: Project Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
label | dc11d6bf-96b3-5e8d-b1ee-40091793ee38 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 53d5ef79-09ab-567e-944d-ec3d344baa76 |  | textbox | Print Name:
text | c323b967-9b1f-574e-b8cd-afc63a856b90 |  | textbox | Position:
date | 34a3c77b-4c5e-5dc9-968c-941b895a9d07 |  | date | Date:
date | 83936d7b-c9e2-54a1-a14b-04f8c4e5b4ed |  | date | Work Completed On
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification.
select | 587b55c8-a83e-560b-8ba2-0521126a759b |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | 7ce78df5-b147-5597-b016-ef6f4daa4f2c |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | 5d131f93-5179-5686-aa1b-782f3c5b2171 |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | 1b2b6811-c1d0-5b15-bd16-9f68b7a8419b |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | dbcda162-6faa-5916-a40d-ea604486b787 |  | textbox | Other:
select | 7c27545a-449f-55e7-85b9-d4d282e265cf |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | 3c0bbf84-fb6f-5c6d-9d5a-9dfa4575fb0d |  | date | Lot Closed On
text | 53bb9af6-921b-5a75-a3db-eda7fa99643e |  | textbox | comments
checklist-sectioned |  |  | checklist | Order Acceptance Certificate - Lot: |  |  |  |  | Yes | Order Acceptance Certificate | 4cd71ef6-21ed-4ca1-ba68-80946fb10a5e
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Order Acceptance Certificate - Details:
text | 58065ea3-8612-5c56-8432-47ef64d09904 |  | textbox | Subcontractor (full name of Subcontractor, ABN, Subcontractor's ACN and ABN)
text | 4d194c4f-397d-5a14-8033-3e9354c956f0 |  | textbox | Order No.:
text | 9ce93add-9e77-5a87-a9ae-2781efaf8566 |  | textbox | Delivery Site:
date | ebf2fe43-c7e8-505c-8ea2-4b89e51bfd2e |  | date | Date on which materials delivered:
text | d59ead29-7e72-530c-a037-cbb30c1badd2 |  | textbox | Inspecting Engineer:
text | a9648dd6-9bd3-565a-8a5f-dce3ad077364 |  | textbox | Delivery vehicle (registration number):
text | 0314a84c-559a-5af5-a302-78b78e87924a |  | textbox | Subcontractor's delivery personnel (full name)
checkpoint-status |  |  | checkpoint | The Subcontractor has checked all Materials included in this delivery and is satisfied that all of the Materials comply with the Subcontract.
checkpoint-group |  |  | section | Packaging Inspection
checkpoint-no-status |  |  | checkpoint | Fault ID:
label | 57862648-3160-5744-bf2b-6247b38359bc |  | note | OK = Meets all criteria
label | 7896bcff-57a1-5495-afda-0ebcd18e628c |  | note | QI = Quantity incorrect
label | 6991022e-3bf7-5646-96fd-ec9a67af7a51 |  | note | IN = Item incomplete
label | 0a338a64-9c7d-5426-9fd6-582c89ed60fd |  | note | MI = Make or type incorrect
label | eebf7b66-fc59-5f63-bdf6-9b9915e3596b |  | note | TD = Damaged in transit
label | 042ce3f9-c548-5b05-96ce-f9c6a16998dd |  | note | NI = Not properly Identified
checkpoint-status |  |  | checkpoint | 1)
text | f57d3e45-df6b-54c9-8ba8-379a7c64116f |  | textbox | Item ID:
text | 2390d8d8-289d-5d16-99e2-0ff808abe8af |  | textbox | Item description:
text | 540cf9f0-4d2d-57d8-aa39-bae42a33f7d5 |  | textbox | Units ordered:
text | 93ebf95c-5f9c-54d0-b45e-994e74e37a2e |  | textbox | Units delivered:
text | 42cebd35-3343-5e8f-9170-330a49359f76 |  | textbox | Special Storage/ Handling Requirements?
label | 922aadd7-e14c-5287-8851-1359876c5e2a |  | note | The following is for completion by Fulton Hogan
text | 0b20ffa1-6f8b-5bd3-a7e6-fdec98ab26e2 |  | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | 9fccd442-0f74-50dc-8305-78893ed9a389 |  | textbox | QA Docs Delivered?
text | 0787c437-9982-5e0e-86d9-b97ee6c91e8d |  | textbox | Defective?
text | 51a88e12-95f8-5fff-b453-10b4b03401cb |  | textbox | Number Accepted / Number Rejected?
button | b945f327-803d-5d15-902b-1c85575b722b |  | button | Fault ID: | IN, MI, NI, QI, TD,OK
checkpoint-status |  |  | checkpoint | 2)
text | ec7199bf-feb9-5e90-97be-684d328a1cd1 |  | textbox | Item ID:
text | f9e4cb3c-9473-5e40-a2c2-e70923d63daf |  | textbox | Item description:
text | c3daa8d9-c7c4-5179-9336-0899396e8ede |  | textbox | Units ordered:
text | 4742fa20-0438-5d7e-898c-6c595a21b3c5 |  | textbox | Units delivered:
text | f107de2d-a5c8-5149-b1f5-90e8e8d3d6cd |  | textbox | Special Storage/ Handling Requirements?
label | 839ed013-5b7e-5ade-ae97-03b8618b4ae3 |  | note | The following is for completion by Fulton Hogan
text | 4720806d-c381-5bf8-a2d2-16c9a437e685 |  | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | 4e451557-c45f-569d-8540-cb6e26878f3e |  | textbox | QA Docs Delivered?
text | d369c722-6feb-5aee-9cc2-8b829b3cd656 |  | textbox | Defective?
text | f9fdd534-8a63-5527-9c6d-050c34dd1a39 |  | textbox | Number Accepted / Number Rejected?
button | 8e3829d2-87cc-58e2-96c8-680ea4ae5400 |  | button | Fault ID: | IN, MI, NI, QI, TD,OK
checkpoint-status |  |  | checkpoint | 3)
text | 491892da-7787-5cb6-8bac-cad0f93324b3 |  | textbox | Item ID:
text | 58d86e4a-8e72-5545-b9a2-aedf65b284cb |  | textbox | Item description:
text | d1833c87-0323-5e16-a70f-b32f13eb0b8b |  | textbox | Units ordered:
text | fba80f19-9e21-5453-8c5d-979bf182b596 |  | textbox | Units delivered:
text | 696b9b56-866e-5fa0-b395-afee5b48523d |  | textbox | Special Storage/ Handling Requirements?
label | 7d575334-ae0e-51db-b640-f2e74aa6ebe4 |  | note | The following is for completion by Fulton Hogan
text | 40617772-828a-53d8-b55e-ce2799b7a792 |  | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | 90070218-1a01-583e-9077-cdb334de195d |  | textbox | QA Docs Delivered?
text | 9020b992-289a-57fe-94ef-df0168da81fc |  | textbox | Defective?
text | 5cbec1b5-4071-5d18-a5e4-23a376e467e7 |  | textbox | Number Accepted / Number Rejected?
button | f92324d2-54f7-5df5-9bcb-51b743135c8a |  | button | Fault ID: | IN, MI, NI, QI, TD,OK
checkpoint-status |  |  | checkpoint | 4)
text | 21e44a53-1a62-5bf5-b683-d93007c45b7a |  | textbox | Item ID:
text | d4f74ff5-5cc2-5526-b59d-d60a0de27263 |  | textbox | Item description:
text | a9eb79da-7b7d-530a-af05-0907303ea8f5 |  | textbox | Units ordered:
text | 18e72d79-3869-5c0b-aafd-7f959a41fcbf |  | textbox | Units delivered:
text | 974704c5-f543-55fa-927f-61f68b9f1ed4 |  | textbox | Special Storage/ Handling Requirements?
label | 33ae5019-3337-5961-93bd-ff22ae186f4b |  | note | The following is for completion by Fulton Hogan
text | c1f538eb-ce82-54d2-88ba-9e2ca42624f9 |  | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | fe63a6f7-8be7-5cd6-97bd-ef7ea50efd9e |  | textbox | QA Docs Delivered?
text | c09b6883-d150-5284-9eac-0d7707f6da50 |  | textbox | Defective?
text | 9080b640-51d0-50d3-982a-c2b236006c9b |  | textbox | Number Accepted / Number Rejected?
button | fb3d9619-861f-5106-aa68-4540d0b26dc1 |  | button | Fault ID: | IN, MI, NI, QI, TD,OK
checkpoint-status |  |  | checkpoint | 5)
text | 284b1a53-60d9-576c-8955-22893d9b10e2 |  | textbox | Item ID:
text | 46baa942-57db-5499-b75d-deb12146093c |  | textbox | Item description:
text | 606e0602-a544-5e5e-a027-60f3aa3022f9 |  | textbox | Units ordered:
text | 535b7214-36d5-54b9-9a6f-c5eac24e56ec |  | textbox | Units delivered:
text | db12f34d-c190-5a92-adf4-37d13a45e19e |  | textbox | Special Storage/ Handling Requirements?
label | 2f68fd67-8bad-5ac1-9d8e-a906b7cc7fe1 |  | note | The following is for completion by Fulton Hogan
text | 183b55a7-abf0-52a0-a8e9-604a9e237f03 |  | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | 73055674-b944-56df-8af5-bf8a37e1c586 |  | textbox | QA Docs Delivered?
text | 73898e67-9d5a-5277-a1a8-5c5ca1e9b326 |  | textbox | Defective?
text | 3589e069-3367-5262-a3a9-f98f1fa849f5 |  | textbox | Number Accepted / Number Rejected?
button | 499749d4-a2a5-5ef8-8a2e-3bd17dad96c5 |  | button | Fault ID: | IN, MI, NI, QI, TD,OK
checkpoint-status |  |  | checkpoint | 6)
text | 84621ab1-6e37-5cc0-a6ee-642bc17d9207 |  | textbox | Item ID:
text | f293b402-5f42-515c-aad1-11d1806c2f7b |  | textbox | Item description:
text | ab742d3c-4d92-571e-b208-ef8970747f47 |  | textbox | Units ordered:
text | 6a069697-dd78-5e2b-bd2e-301e2660d647 |  | textbox | Units delivered:
text | bb3ee157-5cd3-5720-a59c-a7f87a1567f9 |  | textbox | Special Storage/ Handling Requirements?
label | 3b73ef1c-5e99-5193-92a0-b3ba427ab37a |  | note | The following is for completion by Fulton Hogan
text | c05580b7-d35e-5440-abca-41cf61335ea8 |  | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | cd987fb8-f909-5b3a-ab43-73594f16c9d2 |  | textbox | QA Docs Delivered?
text | 042fce15-dcc8-537e-a1ea-e29c374cd98f |  | textbox | Defective?
text | 30e6ddd2-bd86-5795-8e63-283e2e4231df |  | textbox | Number Accepted / Number Rejected?
button | 6d18a629-0b72-589a-94ab-6e9a82433e41 |  | button | Fault ID: | IN, MI, NI, QI, TD,OK
checkpoint-status |  |  | checkpoint | 7)
text | fce2ecd1-66b6-5503-a5f2-a22d76b389af |  | textbox | Item ID:
text | a6c4a5f9-0cc5-568e-8327-b920f7aa3d10 |  | textbox | Item description:
text | e2383807-a597-5bd0-9087-62dc1a8dac3a |  | textbox | Units ordered:
text | b195dac2-1945-54bc-8c23-29f98d6d6480 |  | textbox | Units delivered:
text | 85861d29-5a3d-5efe-ac08-ee9df461a5ea |  | textbox | Special Storage/ Handling Requirements?
label | 26d2b5a3-069d-56e1-b656-4e8521c929f2 |  | note | The following is for completion by Fulton Hogan
text | 2b4baba7-d1be-56d9-9b73-2dc23787057d |  | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | 5117d8a3-704d-5691-9064-ff1c2fca63bb |  | textbox | QA Docs Delivered?
text | 4eb7dc5d-1867-5a45-abf4-dc8dc030de74 |  | textbox | Defective?
text | 9cc9900f-3365-5b4e-a202-8e48ab3a022d |  | textbox | Number Accepted / Number Rejected?
button | 3e76d77a-7a29-5a20-a4ed-e80a5da40182 |  | button | Fault ID: | IN, MI, NI, QI, TD,OK
checkpoint-status |  |  | checkpoint | 8)
text | 3d4f15fa-bc39-5fc9-b523-533471dd952f |  | textbox | Item ID:
text | ae29e9cf-6241-5de0-9bef-57795adc1eaf |  | textbox | Item description:
text | 2e5dbd6f-dca9-5072-aa9f-64a5b74276a9 |  | textbox | Units ordered:
text | a5feaad5-873c-5b8d-8972-bbcef66695b0 |  | textbox | Units delivered:
text | ec51fda0-8c16-5713-bc1c-544a68faf128 |  | textbox | Special Storage/ Handling Requirements?
label | a12788d2-11c9-5224-84d3-4bb0894397bb |  | note | The following is for completion by Fulton Hogan
text | 76adcd53-0909-54ae-98ff-eff1fe221baf |  | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | 5c5d5c2c-4dee-5db8-8c3b-879a69b93f71 |  | textbox | QA Docs Delivered?
text | 2785ef75-b47a-55a1-af7f-0ac99aeb5287 |  | textbox | Defective?
text | 795410cc-670b-5ef6-8df1-f17f97d0dbe3 |  | textbox | Number Accepted / Number Rejected?
button | 20f305b9-aa8a-5e13-a2bd-0c64c6ee8687 |  | button | Fault ID: | IN, MI, NI, QI, TD,OK
checkpoint-status |  |  | checkpoint | 9)
text | d5d733fc-e7d2-5caf-934b-35450dd54b77 |  | textbox | Item ID:
text | 5ec59114-c110-5b73-8e1e-1f37cb22a1b7 |  | textbox | Item description:
text | ddcf35cb-d185-5c48-8c69-0c699ba6f235 |  | textbox | Units ordered:
text | dcfad476-f6eb-57e9-b1e8-d54c553a6b27 |  | textbox | Units delivered:
text | 67e282e9-2c35-56ac-b966-99ac6a5bc06a |  | textbox | Special Storage/ Handling Requirements?
label | 90806342-9ce5-572b-b7a0-f9a77be2bc98 |  | note | The following is for completion by Fulton Hogan
text | ae18d54d-c524-55e9-8ba1-7b69b1dcfd9c |  | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | 1c5f90aa-2ed4-5cab-ad0b-bd45d9401fe6 |  | textbox | QA Docs Delivered?
text | 2a20e620-e90b-5b06-b14c-d67b876346f8 |  | textbox | Defective?
text | 8d56e232-2131-515f-b3af-91d14d823e64 |  | textbox | Number Accepted / Number Rejected?
button | d4400f5e-f834-5ec5-815c-2190cde90c93 |  | button | Fault ID: | IN, MI, NI, QI, TD,OK
checkpoint-status |  |  | checkpoint | 10)
text | b18f50e4-ecbd-5027-95a5-0a9ccb81a5aa |  | textbox | Item ID:
text | 1ca9d127-a953-5936-99c4-e1be8829050d |  | textbox | Item description:
text | 66b8afdb-f9a3-54d0-a6c8-762119445d73 |  | textbox | Units ordered:
text | 4c6eead5-64aa-565f-89e6-5f2e7353fd63 |  | textbox | Units delivered:
text | d261439f-bf67-56af-bbd2-ffde140a1058 |  | textbox | Special Storage/ Handling Requirements?
label | c4400991-5478-5ac1-8e57-a327c6dcea63 |  | note | The following is for completion by Fulton Hogan
text | 28e00e90-ec11-5a89-bd92-26b938250a7f |  | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | 98feb4b2-ea3b-596b-8662-037d526213a2 |  | textbox | QA Docs Delivered?
text | 3130dac8-c315-5395-aa51-da5421b62443 |  | textbox | Defective?
text | f4642255-ef5d-5e7c-b989-2b75a11fd02a |  | textbox | Number Accepted / Number Rejected?
button | 5a4f09a2-358f-505e-8c1e-c671aecc940a |  | button | Fault ID: | IN, MI, NI, QI, TD,OK
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Accepted by Fulton Hogan
holdpoint |  |  | signoff | Sign Off
checklist-sectioned |  |  | checklist | ITP-013-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0013 - Structural Concrete | 5210e9b4-9ed2-48fd-a6c7-3f29aa61738c
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | 89623fac-2352-584f-afb9-9f9776c72f47 |  | date | Lot Created On
date | bd5cd853-32d3-540e-b136-08b44d9cdc55 |  | date | Lot Opened On
date | d264adc7-f04e-5cd7-9c76-87ab0597a0a2 |  | date | Work Commenced On
select | cd4c73e5-dfa0-5a84-ae39-bd0fc8ee5644 |  | dropdown | Lot Type | STL - Structural
text | 1618d6bb-a46d-58dd-8e27-0b91e7d4c2fe |  | textbox | From and To Chainage
select | a30bbea9-7567-5045-bc4a-934829154791 |  | dropdown | Construction Element | STOR - Stormwater,SUBS - Substructure,SUPE - Superstructure,SUPE - Superstructure
select | 79768b7e-c72c-5101-81dd-58df05d70e7b |  | dropdown | Activity | DRAP - Drainage Pit,PIEH - Pier Head,OFSB - Off-structure Barrier,ONSB - On-structure Barrier
select | e2248142-6475-5075-a31c-aa17550561c4 |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | 333776e5-5a74-5711-82a9-934ff69e49a2 |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | ae12acfb-b06b-56f4-b8c4-01ce54a482b7 |  | textbox | Engineer Responsible
text | 2cde4d40-6d57-5ae9-a426-a821f107e90b |  | textbox | comments
checkpoint-group |  |  | section | 1 - Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | bdddd1c0-04d1-5320-98fa-610b05c04ce7 |  | note | Document Title: ITP-013-AX-LOT-XXX - Description
label | 1b0eb799-f4fe-5b61-b8da-ff3f7f9f8f08 |  | note | ITP Description: Structural Concrete
label | 6734ba87-2a75-596d-9743-6b1dc88b901c |  | note | Document Number (in Teambinder): 1145-C200-FUL-QAC-ITP-0013
label | 5dc6038b-2a6f-5878-b093-1c91a4b134d0 |  | note | Revision Number: 00
label | d2cd535d-f662-510b-ac67-c5bb0495c550 |  | note | Revision Date: 26/05/2022
label | 240e8bc2-38bc-5d41-b8f2-2d6e17b38649 |  | note | ITP created by: Omar El-Khub
label | 79727544-072b-55e8-80c1-6848574dae5a |  | note | ITP approved for use by: Babak Rudd
label | e5a9269d-bd61-57b2-83a1-dde4718e7e1e |  | note | 1.1 VicRoads Section 204 Dec 2015
label | 3b2cbc93-fc6b-5d73-a153-0e86b810aa48 |  | note | 1.2 VicRoads Section 602 Oct 2007
label | c0e97616-17d2-59dc-8ea4-5f2a82dbdf30 |  | note | 1.3 VicRoads Section 610 Feb 2020
label | b47f9a85-f0b4-5f46-98ef-27f249ac61fe |  | note | 1.4 VicRoads Section 611 Nov 2018
label | d5b534c3-979f-550f-bf7c-627c10c53df3 |  | note | 1.5 VicRoads Section 613 Jun 2017
label | 4d448263-dd5b-5a9b-bbe3-2aebbe4f5d92 |  | note | 1.6 VicRoads Section 614 Jun 2017
label | 37b55194-8e6d-55d4-9a02-53c1318eb2ce |  | note | 1.7 AS5100
label | fe45fcf5-4731-5d5c-8cf7-230bf397049a |  | note | 1.8 AS3810
checkpoint-group |  |  | section | 2 - Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Concrete mix design
label | 580eefbf-8fcc-56f9-bd66-3e2728f4cba4 |  | note | Frequency - Each Mix, not less than 4 weeks prior to the placement of concrete
label | d3eda1aa-ed99-544b-aff8-2a81607f5aa7 |  | note | - - - - - - - - -
label | 155efd30-99fe-5ae4-b968-471cfd2bf847 |  | note | Acceptance Criteria - Ensure all mix designs have been reviewed by the Superintendent, and allocated a registration number on the Register of VicRoads approved concrete mixes.
label | dd128741-3a7b-551d-a5b0-7547d4d0b8c3 |  | note | Concrete Mix is Registered with VicRoads.
label | 3045daeb-77dd-52af-9996-7b6398068063 |  | note | Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
text | 6127e61e-7288-5f4a-8fb2-7241725f9183 |  | textbox | Teambinder Material Approval number
label | ec45de6e-667b-527e-b733-e63f91786c8a |  | note | - - - - - - - - -
label | 2890f71a-95cc-5533-9863-0c17ed1292ce |  | note | Reference Documents - VicRoads Spec.
label | 84e32433-fea1-5c7a-bbbe-93428709aa70 |  | note | Cl.610.07(b)
label | 1c293e9b-462f-5592-a5ba-98ab769b48f0 |  | note | - - - - - - - - -
label | dc7da628-ee4c-5f53-b8c9-d28f56720772 |  | note | Inspection / Test Method - Document review
label | 547a134f-57b8-5674-b478-03e988df4d19 |  | note | - - - - - - - - -
label | 38676e63-e2e0-5513-8d57-93f9a94dad9a |  | note | Record of conformity - Approved Mix design
label | 114076af-9b29-5807-8477-4ad799cddf19 |  | note | - - - - - - - - -
label | a691ff01-d1dd-5e30-ad75-7cee09d9a4c2 |  | note | HP*
label | 1b4c5593-521f-57e5-889a-101a925eee7b |  | note | - - - - - - - - -
label | 7dfc82cc-e343-566a-bee1-0dbdb466d60d |  | note | Site Engineer & Superintendent
label | 1b47e396-c138-55a6-a927-86448812cf9e |  | note | - - - - - - - - -
date | 234156f7-ae56-518f-8c88-ed6280979ccb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Reinforcement Certification
label | a81f0ef0-04b9-5a0b-972a-4beaa0b4e3f3 |  | note | Frequency - Once for each supplier, 14 days of award of contract
label | 53cf9409-40fe-5ecf-a0dc-b967f91923b8 |  | note | - - - - - - - - -
label | 2197aec5-a9ee-5d01-8f99-aaf520909120 |  | note | Acceptance Criteria - Ensure the manufacturer and supplier of the steel reinforcement is in possession of a current certificate of approval, issued by the Australian Certification Authority for Reinforcing Steel (ACRS). Evidence of compliance submitted to superintendent within 14 days of contract award.
label | fd4d6dab-f7da-5a00-a685-07031b854f5a |  | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g. 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | 6ac8beee-52e9-576a-b98a-3ef223da89ae |  | textbox | Teambinder Material Approval number
label | 3d6472c4-631a-5832-b855-89872d0ea1dd |  | note | - - - - - - - - -
label | 8c643103-7ee8-542d-ab76-d30e09649d78 |  | note | Reference Documents - VicRoads Spec.
label | fd1f78e5-951f-5384-b651-744d21127c01 |  | note | Cl.611.04
label | 8c0f1219-a5e8-5a4e-8750-89f51da53e37 |  | note | Cl.611.05(a)
label | 57a70ea4-2eb5-5f2b-b50a-ecf0b032cea3 |  | note | - - - - - - - - -
label | 2ae0913a-5a6a-5fb1-abdc-ccb5f94e5edc |  | note | Inspection / Test Method - Document review
label | 02a8f195-6789-55f9-8a66-782dc2d6f89f |  | note | - - - - - - - - -
label | 027f09a7-87e7-5fa9-b89b-917c2452239a |  | note | Record of conformity - ACRS Certificate of Approval.
label | ddbdde63-ac3a-53c8-a724-b8f9bccda75e |  | note | - - - - - - - - -
label | d27e7624-9721-5e97-b86d-70ca9fe742a8 |  | note | IP
label | 61c925e6-2c35-5e1d-9d12-f0ec339a61ff |  | note | - - - - - - - - -
label | e4aaa093-1be7-5339-8520-f2c8b31535fc |  | note | Site Engineer
label | 5c6b69b5-fe54-5dd8-a740-06bf3b6a0a2b |  | note | - - - - - - - - -
date | de8b5946-905c-5810-b28b-d9f9747bc138 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Bar Chairs/Aspros Certification
label | cc6aa1ec-50ef-5e57-a597-ae834256ed7e |  | note | Frequency - Once for each supplier, 14 days of award of contract
label | c5111e0a-e5b9-5f21-90d4-042bbcea604a |  | note | - - - - - - - - -
label | 812c3c99-72b0-5442-bc94-b0aa9b528388 |  | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
label | f64b841a-06bc-5d95-9153-903a6da9494f |  | note | Concrete aspros require annual compressive strength and soluble salt testing is required.
label | 9ed79b7f-6fb8-51ff-9c1c-defaa3c07704 |  | note | Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
text | 31bb8b6a-254d-506e-9354-f1c909899440 |  | textbox | Teambinder Material Approval number
label | ef6960da-b453-5820-a4e7-61ce76f577f2 |  | note | - - - - - - - - -
label | a549c17d-adb7-538c-82bf-befa0488b57b |  | note | Reference Documents - VicRoads Spec.
label | a2da8356-8c06-57d1-a17b-d1afd33d85b9 |  | note | Cl.610.26 (a)
label | bad75990-d3dc-5c93-ad53-656b7d70cfe8 |  | note | - - - - - - - - -
label | d7b4f012-1536-528d-a152-8772640c3f26 |  | note | Inspection / Test Method - Document review
label | 7fee968d-7fb6-5266-9306-50c6e0daa9d5 |  | note | - - - - - - - - -
label | 925df293-01f2-5c78-8f59-6823dee6eb24 |  | note | Record of conformity - Approved bar chairs and aspros
label | 7a3cbbcb-735a-53cf-a622-637440e41420 |  | note | - - - - - - - - -
label | 0b333291-4adb-5dc3-9d21-fcad311ad621 |  | note | IP
label | a3047fdd-21cd-5e1f-8026-62cc89106887 |  | note | - - - - - - - - -
label | dda2f45a-7f4a-55d3-bcc2-9199ae59cde6 |  | note | Site Engineer
label | 5151f65d-97f7-505f-b9d6-97e28a4555c0 |  | note | - - - - - - - - -
date | b3af9321-36d9-5a8f-83f3-a02827b3650f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Evaporative Retardant
label | c6fff41e-8e33-5c03-b51f-f99208b4d929 |  | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
label | a9bd0569-e90e-573e-a9cf-ecec3ecfca28 |  | note | - - - - - - - - -
label | f862084a-5740-5f17-8985-c81518790d38 |  | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
text | 9dfe52ec-9654-525f-a759-06d8312cf839 |  | textbox | Teambinder Material Approval number
label | 24caaf03-f966-5448-be2e-f42fb4508b56 |  | note | - - - - - - - - -
label | c8a63774-13b2-53e9-977e-18dd93831358 |  | note | Reference Documents - VicRoads Spec.
label | b3aad2d0-e951-5406-9190-4db16bd921ce |  | note | Cl.610.17 (f)
label | d0e62156-b273-5302-b9c4-948dbbf38942 |  | note | - - - - - - - - -
label | 7a95345d-6b4d-55b4-9de4-4298ac589970 |  | note | Inspection / Test Method - Document review
label | f4ef9787-441b-5e42-954c-baa02d58e4d4 |  | note | - - - - - - - - -
label | 64ee376f-10a7-5270-a355-40e107c8b08f |  | note | Record of conformity - Approved evaporative retardant
label | ddd770e2-79e5-503d-85a3-3bca502cfedf |  | note | - - - - - - - - -
label | ec65c4c3-966a-5a45-a92b-96459d266bd2 |  | note | IP
label | 6bbce2cb-7b1e-5693-b73b-29357112e91f |  | note | - - - - - - - - -
label | b9ddf85a-8737-5085-8634-51b8694b5d97 |  | note | Site Engineer
label | a04b2ae4-3d41-58bd-9a8c-8f3bfbfe98a4 |  | note | - - - - - - - - -
date | 9ea62ae7-0ab9-5ad8-941d-00cbe26a3b34 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - Curing Compound
label | 7320de7d-a0ff-558a-8a61-0c85d49450b7 |  | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
label | 2fb0924b-ec06-5c8b-a936-af2f1be47e89 |  | note | - - - - - - - - -
label | 62568e40-bd99-5fbd-a1a7-88f929f0befb |  | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
label | a20c5415-9270-515a-bbc4-af338c667bf8 |  | note | Teambinder Material Approval number
label | 831d0519-7262-5cbc-ae04-9d813144e783 |  | note | - - - - - - - - -
label | 9a1425ef-bd75-535c-9207-bb5de0e017cc |  | note | Reference Documents - VicRoads Spec.
label | 5776e96c-f427-5f4e-9a95-db98d5b14933 |  | note | Cl.610.23 (b)
label | 2aa46c9b-aa17-5a99-a0a5-4154954c7d83 |  | note | - - - - - - - - -
label | e5418a7b-6a1e-57e9-bc24-7add66857534 |  | note | Inspection / Test Method - Document review
label | 68bf71af-fba2-5cfc-9f78-6800fd3f3072 |  | note | - - - - - - - - -
label | 1d8364e0-05b2-59c2-9acc-f0ef8c82f31a |  | note | Record of conformity - Approved curing compound
label | 83e34364-095d-5554-b46f-2624b36dda65 |  | note | - - - - - - - - -
label | 0ed9d9a7-2967-5134-8ef1-30f7f5eda478 |  | note | IP
label | 5c55d4fb-a7e0-5ad0-9161-7ae3e6e17975 |  | note | - - - - - - - - -
label | f3c2efb9-15f2-5e0c-b7fc-329ffafdca02 |  | note | Site Engineer
label | 04699796-7a70-5b88-ba7b-560c02503925 |  | note | - - - - - - - - -
date | 727eaa89-3d3b-5dac-b1cf-de5d41bd3dfb |  | date | Date Completed:
checkpoint-group |  |  | section | 3 - Preliminary Works
checkpoint-status |  |  | checkpoint | 3.1 - Concrete Placement and Compaction Work Method Statements
label | a4e918f7-d06d-5e5e-8f43-46e701b37a6c |  | note | Frequency - Once, 4 weeks prior to placement of concrete
label | 9c664970-cd70-50ab-8838-6f1c99759380 |  | note | - - - - - - - - -
label | bfb770c4-acdc-5b8d-ba92-4a10f7cb812e |  | note | Acceptance Criteria - Concrete placement and compaction WMS to be submitted for review to MRPV
text | 9cb242c3-89cd-5fda-b71d-89ed3bef1c1a |  | textbox | Teambinder Approval number
label | 0628e825-b414-5dfe-93dc-9295ad9f7c29 |  | note | - - - - - - - - -
label | d14bb513-f82a-54f2-a139-8604b6bea677 |  | note | Reference Documents - VicRoads Spec.
label | d94aeae3-c161-5587-89f7-60bbdac8697d |  | note | Cl.610.18 (a) (i)
label | 897f8c35-02a1-5d8e-a49d-475f17c63203 |  | note | - - - - - - - - -
label | 90684c4c-8912-5714-bbf7-413dd65967bc |  | note | Inspection / Test Method - Document review
label | b46d8666-6c36-5380-97ce-1aa87e62203c |  | note | - - - - - - - - -
label | d1b575eb-9d7a-51a6-8d82-803abc02a971 |  | note | Record of conformity - Approved WMS
label | dbf8e540-db62-5f61-a8d9-b7a7f1d4d8fb |  | note | - - - - - - - - -
label | 705afea5-cbfa-5070-812e-37c9c3c48da9 |  | note | HP*
label | 825d4b2a-286a-5f56-addd-d4f7dce239d1 |  | note | - - - - - - - - -
label | 337857d8-9e49-53e8-afe4-a9d54718bc40 |  | note | Site Engineer & Superintendent
label | 454c854a-c225-5230-a69c-f7b34361a93e |  | note | - - - - - - - - -
date | f0fe822d-e1d6-5fa8-bccf-6582400a8aac |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Concrete Sampling and Testing Procedure
label | f8308a8b-065f-52be-95b3-e1066017235d |  | note | Frequency - Once, 4 weeks prior to placement of concrete
label | 686732a3-0ada-55ee-97c4-33e28b444aa8 |  | note | - - - - - - - - -
label | 1ec040d2-09f8-55b8-ae33-242af14cb22c |  | note | Acceptance Criteria - Concrete sampling and testing procedure to be submitted for review to MRPV
text | 1f40102c-bf75-50c3-a59e-6d690fd1b164 |  | textbox | Teambinder Approval number
label | 0be53dea-5218-5687-9180-6d954f52a43f |  | note | - - - - - - - - -
label | 08618170-ec75-5359-a58a-11df525209f6 |  | note | Reference Documents - VicRoads Spec.
label | 539ee084-b086-5536-87de-22ee611c5bf9 |  | note | Cl.610.18 (a) (v)
label | 9389ca0a-40d0-59ec-b9c7-8a071b1137f5 |  | note | - - - - - - - - -
label | 3ab8e29f-d69c-57d7-b832-717f04335c81 |  | note | Inspection / Test Method - Document review
label | 33f99d20-6c46-5d41-bc13-e097323f8c89 |  | note | - - - - - - - - -
label | e21592d7-db6b-5dfd-8f89-abe20a77bc04 |  | note | Record of conformity - Approved procedure
label | 046e7a25-47cd-56f0-92d8-16b65b8f2a40 |  | note | - - - - - - - - -
label | 58b2cbd3-aa2c-5064-873b-c207ae5ff5c5 |  | note | HP*
label | d014e0fe-186b-5f9c-b433-12fb761a561c |  | note | - - - - - - - - -
label | 9fc896af-4e64-5753-930e-98ecc4466a6c |  | note | Site Engineer & Superintendent
label | fac13b1c-1a8d-54d4-8e08-0bfa23f05324 |  | note | - - - - - - - - -
date | c3b6728f-273b-5af3-ae5e-831cd010ef5a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - Concrete Placement and Compaction Toolbox Meeting
label | 63ab4952-d479-5bab-a12f-b651c45eb57e |  | note | Frequency - Once, 4 weeks prior to placement of concrete
label | de1b2de6-2a4d-5bef-aa53-fd9e248ac9fe |  | note | - - - - - - - - -
label | ca10850e-06f4-5f50-a3c9-f5cf741049e5 |  | note | Acceptance Criteria - Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
label | 157b622e-c101-510f-8584-67b8cd0647cb |  | note | Minutes of this meeting to be submitted to MRPV
text | 65a82547-c022-562a-979f-afe2774f090b |  | textbox | Teambinder Approval number
label | 49d1e995-05c9-5d43-92d8-1c24b62cab9a |  | note | - - - - - - - - -
label | fb6f51ae-a704-5284-9415-d3a9de9cee18 |  | note | Reference Documents - VicRoads Spec.
label | 89d5aee8-94a7-59a3-92f6-d1704519692d |  | note | Cl.610.18 (a) (iv)
label | 9fc561be-8d49-51c3-a277-b9bff25b2417 |  | note | - - - - - - - - -
label | 1ffaee08-77e6-54ca-86f7-1f5c42d2290d |  | note | Inspection / Test Method - Document review
label | 81598f8a-f652-5550-8387-e718217450d6 |  | note | - - - - - - - - -
label | 26543cde-5695-53bb-ad05-8e545b69ef5e |  | note | Record of conformity - Approved quality requirements
label | 75a13ed8-a6e3-5b94-9bc8-79ac3d98ca0b |  | note | - - - - - - - - -
label | 9250e1bd-1e36-514d-a699-96846022b327 |  | note | HP*
label | 9d126739-5ddc-5af6-a49e-fcac3ac1c0e2 |  | note | - - - - - - - - -
label | cbf8b1d6-6364-5f2d-ad62-bc5125bea4bb |  | note | Site Engineer & Superintendent
label | 596b9117-477c-5d74-a355-db2753d79988 |  | note | - - - - - - - - -
date | d67cb09a-9abe-53a0-912b-970588d5830c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 - Hot and/or Cold Weather Concreting Procedure
label | 16820701-9187-5595-9fbb-a4d5d5b94982 |  | note | Frequency - Once, 2 weeks prior to placement of concrete
label | 7475c93e-b095-527f-94d6-804bae5f4cc1 |  | note | - - - - - - - - -
label | d5a3731a-d602-5e17-9d3b-78e547c1b617 |  | note | Acceptance Criteria - Hot and/or cold weather concreting procedure to be submitted for review to MRPV.
text | 6e4cc57e-fb7e-5c4d-8c28-bb7516b1204f |  | textbox | Teambinder Approval number
label | 482fdd17-79f1-5413-b350-f6a8abd0f3b9 |  | note | - - - - - - - - -
label | b808c31e-f34c-5edf-a245-1f1a6f72f8cb |  | note | Reference Documents - VicRoads Spec.
label | 9238229c-4f17-5c5d-b4a5-7f4a4505d44b |  | note | Cl.610.17
label | 4a853c5b-ad4e-5b1e-a3da-96a91ee04f45 |  | note | - - - - - - - - -
label | b5fbfd01-dc73-5b35-a5c7-b9a100e6ad8a |  | note | Inspection / Test Method - Document review
label | f2da07af-5fce-5d1c-9014-121a92190d83 |  | note | - - - - - - - - -
label | 9a84a95c-dc2e-5afa-bb28-f2142b4cbbde |  | note | Record of conformity - Approved procedure
label | 72ceb703-0197-5e9a-976e-b01a1ed51775 |  | note | - - - - - - - - -
label | 74758826-b397-577e-a250-1e1010aaa36f |  | note | HP*
label | 80f30877-d7d7-5e33-943f-d0f9b51da68b |  | note | - - - - - - - - -
label | fed206cb-aee6-51ab-9a4c-d334fc63ad2a |  | note | Site Engineer & Superintendent
label | 7563e782-226f-5e03-9cad-c129aadb2735 |  | note | - - - - - - - - -
date | 63189825-f62b-50d5-9bd2-26facc79241d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 - Curing Methodology (for Concrete and Grout)
label | fa1a4c02-1a80-570f-9412-f65031b6e96c |  | note | Frequency - Once, 4 weeks prior to placement of concrete
label | 89967d94-58f9-5ba1-bd55-3a745dd72694 |  | note | - - - - - - - - -
label | b7f30b86-b98f-5452-9306-d5358a5f1ea1 |  | note | Acceptance Criteria - Curing methodology/procedure to be submitted for review to MRPV.
text | f110c652-ab9d-50ae-a001-effe7ae99734 |  | textbox | Teambinder Approval number
label | c64656c4-368a-5ce3-a816-51a222f1d820 |  | note | - - - - - - - - -
label | 2bfb0f65-6b41-548c-a72a-8853f33b92c3 |  | note | Reference Documents - VicRoads Spec.
label | 4955a03f-ac26-50fe-bc24-f0efe92b4d97 |  | note | Cl.610.23 (a)
label | e4378068-a0e1-5133-aa48-92d94e611462 |  | note | - - - - - - - - -
label | 2c29a986-0af9-59bf-a3cd-088163a37bab |  | note | Inspection / Test Method - Document review
label | af7c40b9-8b53-5673-8b2d-c88880e6269b |  | note | - - - - - - - - -
label | d27f9a95-5749-5610-9175-4918a1dce09f |  | note | Record of conformity - Approved methodology
label | 89d8c55e-d771-505d-b3df-860b41e2ca82 |  | note | - - - - - - - - -
label | 3a291e43-b66a-51a6-ab7b-6da587693984 |  | note | HP*
label | dfb2d493-f347-597a-b582-bff846bb8b6e |  | note | - - - - - - - - -
label | 85a63053-39e9-5246-be82-f44f203d6c2a |  | note | Site Engineer & Superintendent
label | ad9ad633-4581-503d-9d19-32a434d6ecd3 |  | note | - - - - - - - - -
date | 1a42dfdd-1a53-5f7c-979f-56708ef65939 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 - Concrete Drilling Procedure
label | a4785fef-763a-55ff-a09b-4938c9f1849e |  | note | Frequency - Where applicable, once, 2 days prior to drilling
label | 3e4b4249-dd49-54ef-b545-c30c2d67fb8f |  | note | - - - - - - - - -
label | 146f135b-938b-510e-ad59-0bed12b5c49f |  | note | Acceptance Criteria - Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
label | 514497f2-34bf-535a-8b13-01df0091b07f |  | note | The planned locations and drilling procedure shall be submitted for review to MRPV.
text | 1f7c413d-4cb7-5609-be52-827d656c7862 |  | textbox | Teambinder Approval number
label | 1fea2d92-5c66-5594-b2ae-166bfcbbafc5 |  | note | - - - - - - - - -
label | 1153add1-b297-51ac-9b00-a65004303f3f |  | note | Reference Documents - VicRoads Spec.
label | 6ab72c4f-a3b7-566a-83fc-5eda245882c8 |  | note | Cl.610.46
label | 25837d74-974f-5508-b238-21d5c7bd954f |  | note | - - - - - - - - -
label | 309dafdc-b5aa-563f-a824-89b433be552d |  | note | Inspection / Test Method - Document review
label | c77b8760-b2a5-5a6e-86aa-616378ddd182 |  | note | - - - - - - - - -
label | 39406123-eb65-5ea0-a259-72e8add34b91 |  | note | Record of conformity - Approved drilling location and procedure
label | 23127dba-8be0-593c-b4d1-d3b514fc9fc7 |  | note | - - - - - - - - -
label | 20ce7da6-d3d6-5601-b4b4-fcdee8425f22 |  | note | HP*
label | ee88e884-6a9b-5ab4-bb51-5a18fb3ce627 |  | note | - - - - - - - - -
label | 36d6ecc5-c9a0-5d21-9531-9ae758b2d09b |  | note | Site Engineer & Superintendent
label | c7b062d2-e13a-55ce-ad3e-008920a75e02 |  | note | - - - - - - - - -
date | 18224a12-8294-5df9-9ced-e53a1cd1858c |  | date | Date Completed:
checkpoint-group |  |  | section | 4 - Pre-construction activities
checkpoint-status |  |  | checkpoint | 4.1 - Check that IFC drawings are being used
label | de8b2349-5a48-55a5-a0e2-3470a48cd159 |  | note | Frequency - Prior to Commencing
label | 7245fe07-8967-593f-83c9-230f66c2b2f7 |  | note | - - - - - - - - -
label | 6693c949-0d19-53e5-9d8e-d9b5ecb51317 |  | note | Acceptance Criteria - Issued For Construction (IFC) and latest available revision on TeamBinder is used
label | c1c4f766-c51a-5881-abe5-cbbae2a3558c |  | note | - - - - - - - - -
label | 35bca3c1-965b-5f41-8a5a-63c0c42eff79 |  | note | Reference Documents - Project Drawings / Drawing Register
label | 1e05fcca-14e3-59af-bebf-59029cad4318 |  | note | - - - - - - - - -
label | ccaad7b5-33d5-5dc6-b8eb-023a252181ff |  | note | Inspection / Test Method - Document review
label | 923e04fe-8146-5165-9de2-87edfcba394f |  | note | - - - - - - - - -
label | ec2151c3-8a34-5fb2-a98b-b3d407608183 |  | note | Record of conformity - Latest Revision Drawings
label | 8cfa0fdb-921f-5b82-ae40-39c718e3f2ef |  | note | - - - - - - - - -
label | 72204971-6d17-512c-abdf-e5ce01448c4f |  | note | HP*
label | 2cac9808-d516-55d7-a6c8-e57b4f3079ef |  | note | - - - - - - - - -
label | baf57184-18a9-561b-b746-30ec07bbd771 |  | note | Site Engineer / Site Foreman
label | c91d3ccc-08b8-5dbd-b417-4f9bcddc67a9 |  | note | - - - - - - - - -
date | 098923b1-a466-5f57-bb83-47f36b24afb8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Survey set out works
label | 1c835e0b-7990-5aed-9ce5-2895fe6f6d6e |  | note | Frequency - Prior to Work Commencement
label | f2b0a438-465c-5959-aed5-cb2cee183d50 |  | note | - - - - - - - - -
label | 15612313-178e-5339-812d-95615d700dfb |  | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity. IFC and latest available revision used
label | 7a253919-8904-5640-b080-93120adeee19 |  | note | - - - - - - - - -
label | c612ec6d-8788-5d3a-86e9-6d9369996ddb |  | note | Reference Documents - Project Spec.
label | 144f9896-cca4-57e2-b1e2-751049c36d7f |  | note | Cl.1190.06
label | f077ab5f-3b9c-5933-8f82-6f69d0931aba |  | note | - - - - - - - - -
label | b1858a02-8769-5de8-a543-9b9df3ac674c |  | note | Inspection / Test Method - Site inspection
label | a55aa7d9-d7e3-5b17-93f6-115ece945f03 |  | note | - - - - - - - - -
label | 48640f16-5c0b-5492-a53c-bed767eec0b6 |  | note | Record of conformity - Survey records & pegs on the ground This ITP Signed off
label | 165cebf8-d016-5c10-990c-4f16f32bd663 |  | note | - - - - - - - - -
label | 5d5900f2-402c-5bb2-8ca0-9f852c744c92 |  | note | SCP
label | 59f9506c-a011-5e92-ab92-b96418483add |  | note | - - - - - - - - -
label | 9b459d2c-8a4a-5f1c-a26e-dfa053c867f9 |  | note | Site Engineer, Foreman & Surveyor
label | 18b9212e-b5e0-5e82-a012-666215ea000c |  | note | - - - - - - - - -
date | af1e7910-400e-569c-abd7-613eb3e30fd6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Excavation Permit issued
label | 37f45d6e-0cb9-5c19-9794-af8e4895e8f6 |  | note | Frequency - Prior to Commencing Work
label | 0da62d80-bfa4-55ba-bc77-4a792ad622d9 |  | note | - - - - - - - - -
label | 2d8ba990-22e8-5d6d-b815-d770507cbe22 |  | note | Acceptance Criteria - Current Excavation Permit signed and specific for the area where works will be executed.
label | ac849c8d-9bba-5d0a-a000-5e6c48bc6434 |  | note | - - - - - - - - -
label | 56e65ba2-cc23-5c09-b1c1-9d4068cbb183 |  | note | Reference Documents - Excavation Permit
label | c0eca90e-071a-54a0-819b-5fc1b296fb82 |  | note | - - - - - - - - -
label | 8cc90153-6805-5133-aab9-d71a91945255 |  | note | Inspection / Test Method - Document review & Site inspection
label | 10872467-a87b-52f0-af1d-b8446e2f163f |  | note | - - - - - - - - -
label | b337ddf4-56df-5b73-a406-3df21875458e |  | note | Record of conformity - Excavation Permit #
label | 5af1ead2-6b47-5af1-b218-3dfe36a62003 |  | note | - - - - - - - - -
label | 1eef8fe1-4619-5a16-a577-2057db19b84d |  | note | HP*
label | 8b408184-ceee-55d1-ab65-1dc6bd034711 |  | note | - - - - - - - - -
label | b1d2f72d-10b7-5975-b822-8bb2b1b22a6a |  | note | Site Engineer
label | 32c22e6a-7c68-5e76-9ac5-73c94c3b2072 |  | note | - - - - - - - - -
date | 8aab6aa2-29f3-5105-aa91-df2d908b03ee |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 - Excavation Inspection
label | 13622271-d35f-5b3b-a20c-a1b97f1c948b |  | note | Frequency - Where applicable, prior to placing blinding concrete
label | 9db130e4-dfff-55b0-985a-ca3d63404fe0 |  | note | - - - - - - - - -
label | 4b55c103-4926-5f16-818d-d4bae2885466 |  | note | Acceptance Criteria - Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
label | ff542fe9-c0bc-5885-977e-ec69d732329a |  | note | - - - - - - - - -
label | a5787fff-e663-5581-b395-012d81dc0e09 |  | note | Reference Documents - VicRoads Spec.
label | c990ebf9-2a54-5f96-a59f-ce1af093e4f6 |  | note | Cl.602.03
label | 2999b34e-0d5f-5629-9275-63a90b341501 |  | note | - - - - - - - - -
label | 24e48b3d-8391-5764-8e5b-30a4b657fdaa |  | note | Inspection / Test Method - Site inspection
label | 4929d0a5-5e63-5586-996a-bfc1204614de |  | note | - - - - - - - - -
label | 018f9dea-bc3e-52c6-adcc-3df5f4ac6eef |  | note | Record of conformity - Superintendent approval
label | b372576c-21b3-582e-aa68-93af3787fff9 |  | note | - - - - - - - - -
label | a55add28-25d6-5293-a8ea-a84f4fd8861e |  | note | HP
label | ad5d1516-4864-57a0-9790-764660a9722a |  | note | - - - - - - - - -
label | e62b751f-4195-5778-ab2c-7f7b4d1dd497 |  | note | Site Engineer/ Project Engineer
label | 379f14ae-2b00-5287-9a6d-d09c93197a51 |  | note | - - - - - - - - -
date | 2c036648-f091-5886-a71f-176adce8eb94 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5 - Construction Activities - Formwork
checkpoint-status |  |  | checkpoint | 5.1 - Formwork Design and Construction
label | f95c3e6d-814f-58e8-8dcc-9dc5103a63f2 |  | note | Frequency - Each Pour/ Type of element
label | 84f569b3-f553-51dd-9bb2-043080108b9e |  | note | - - - - - - - - -
label | 7b84c89b-6b20-5f46-99df-a2032b822d18 |  | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish. Formwork shall not be placed where steel & fixtures cannot be inspected.
label | 5429dbbb-04eb-5021-8bee-0ffbe6850d8d |  | note | - - - - - - - - -
label | ee5bf04b-ea6c-54f1-9fb4-7d00e0807fbe |  | note | Reference Documents - VicRoads Spec.
label | 3be5d218-c6a2-5730-87c5-1a149db5ecec |  | note | Cl.614.04
label | 98d1b2d3-7504-533d-a525-7fa2d3fc996f |  | note | CI.614.05
label | eb6a2852-302b-50bf-8544-554c6ae99793 |  | note | Cl.614.06
label | d5e2c59a-0e35-5895-8cb8-49401cdd28f9 |  | note | Table 614.041
label | 31a19e1d-888e-5ea0-a9c4-8a0f38745aaa |  | note | - - - - - - - - -
label | 571e283a-1c9b-533a-96d8-52fd2cfdab1e |  | note | Inspection / Test Method - Document review & Site inspection
label | d8bc79c4-7259-5a83-ae2b-641271c5e560 |  | note | - - - - - - - - -
label | a3e1bb91-b063-55bd-b065-76c54ef88744 |  | note | Record of conformity - Proof Engineering Certificate approved This ITP signed
label | b8e7b2cb-6608-54a7-8331-b748712bd9db |  | note | - - - - - - - - -
label | 363c65f5-7bb4-5381-8d38-cffd7b3bed1f |  | note | IP
label | 8ad361b9-e8c7-5a30-a192-b35e5c3e5038 |  | note | - - - - - - - - -
label | 86ce359b-5510-54ba-9ca8-d7becb166ad1 |  | note | Site Engineer & Superintendent
label | 33cd7675-7581-5b11-9c68-09332374cbdf |  | note | - - - - - - - - -
date | 98615745-4618-5544-9515-3ef1e05264fb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Formwork Certification - Formwork Inspection (Members Greater than 2m)
label | bd113c6c-f19a-5847-8393-cd4e3883cf2e |  | note | Frequency - Each element (where greater than 2m)
label | ef4be792-3ce6-5b87-b9f8-c787eece413a |  | note | - - - - - - - - -
label | a2f5ce0e-8bbc-5176-b000-3e9d2d46445a |  | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | ea934a71-2862-56e0-801a-951a1de298e2 |  | note | Abutments, pile caps, footings, solid piers, pier columns and walls, with heights greater than 2.0 metres
label | c9f61f42-37e2-540b-827c-817b9b8f909e |  | note | All other concrete members
label | 2e932635-defd-5a76-b10a-b1eb00dc93f8 |  | note | Any member for which self-compacting concrete is proposed.
label | c9dbdd0e-11db-52b9-ade1-2478f46762ea |  | note | Attach: Attachment A
label | d46b1728-3529-5e21-81b5-2af8da596f0a |  | note | Attach: Attachment B
label | 4da3f253-4040-555d-84b7-184d4d277d46 |  | note | - - - - - - - - -
label | 87e43e8f-8f0a-5ae6-a8aa-19432a9104b4 |  | note | Reference Documents - VicRoads Spec.
label | 347314c3-55f8-52bc-84e0-d6d62fb150e7 |  | note | Cl.614.08
label | 76171174-9154-54ec-b582-36a651018a8e |  | note | - - - - - - - - -
label | d0a6f415-64ae-5ac1-90f8-c9ee09cd3f00 |  | note | Inspection / Test Method - Document Review
label | 2134f6a2-826b-5757-98c8-8c4753a7520c |  | note | Visual
label | b4a64745-f876-5424-b6f2-0dc37c1f0f89 |  | note | Measure
label | 5eee4fe3-e7bf-5b98-9b04-a9b5951bb801 |  | note | - - - - - - - - -
label | 4f65e776-9524-53b4-b1d2-9ab29c308dc7 |  | note | Record of conformity - ConQA Hold Point Release
label | 34e4618a-fa2a-5977-8960-087cefeec2d8 |  | note | - - - - - - - - -
label | 3e575971-36c2-5c56-acdd-81d714a4df92 |  | note | HP
label | 081d0af5-c9d6-56a4-a232-0b25cada53e7 |  | note | - - - - - - - - -
label | 249af44a-bb37-5909-91f0-519e750f4d7d |  | note | Temporary Works Designer
label | 2235aeb6-6011-53a7-9c35-3568e9581f7b |  | note | Proof Engineer
label | e1d5423b-ebf3-55c2-a753-0c1a0d0283ff |  | note | SE/PE/SPE
label | fda02dba-3ee1-5289-8dd0-09011f61391c |  | note | - - - - - - - - -
date | 1ec1d90a-aa87-5d9e-9d73-aefbe57f3a6b |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 - Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
label | e4c5daba-6c64-53f8-a3ea-989ae246c6dd |  | note | Frequency - Each element (where 2m or less)
label | 46bd3627-9861-5462-924c-5faf49f86a29 |  | note | - - - - - - - - -
label | 63b78312-9bcb-5dcc-a437-0df297ec2b64 |  | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | 1e67ee0c-e620-5593-b2d4-4ee0d514cd4d |  | note | Abutments, pile caps, footings, solid piers, pier columns and walls, with heights less than or equal to 2.0 metres
label | e3fc342d-2d16-5e3e-ab27-04a3693a4510 |  | note | Attach: Attachment C
label | 765bf5d6-afc7-5520-aada-8e3c6c303269 |  | note | - - - - - - - - -
label | 7b1af325-d0a2-5435-94ec-170717ce228a |  | note | Reference Documents - VicRoads Spec.
label | 9e81db6f-bcfd-5fc9-9503-f4fe16037baa |  | note | Cl.614.08
label | 492c2b99-f285-5e02-8eeb-5dec3a52f5d6 |  | note | - - - - - - - - -
label | 17d9871c-6424-56c1-944c-a5052171f9b3 |  | note | Inspection / Test Method - Document Review
label | 40653d21-3f35-59dc-a21d-ebe165814257 |  | note | Visual
label | 9680d985-ea47-5e18-a5fc-3538c431eb2d |  | note | Measure
label | 2932ed12-9aa3-5b11-aac6-d3987609ac6a |  | note | - - - - - - - - -
label | 9d32c6a6-b35b-57bb-bd02-4143b1da347c |  | note | Record of conformity - ConQA Hold Point Release
label | c51e8c49-2aad-5134-8a98-00d37b1e9258 |  | note | - - - - - - - - -
label | 9f270120-a76f-595e-a84f-de786bda7310 |  | note | HP
label | c926a093-796f-5f14-adcc-909547105189 |  | note | - - - - - - - - -
label | e6fc8cc7-95f2-5a05-a067-32fc727ed1b2 |  | note | PE/SPE
label | 9b26731d-139c-5e6b-9ad9-695293e27d03 |  | note | - - - - - - - - -
date | 89a45f13-930d-58eb-a1c1-14c7e110236a |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 - Reinforcement Placement
label | 4395c50d-2373-5535-835c-a9c971e45b9a |  | note | Frequency - Each Structure
label | 8769543a-db2b-5697-9108-772b9fc9a5da |  | note | - - - - - - - - -
label | 8b5ce5e9-18c5-5abd-9c29-5aeb45472f25 |  | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | 2f4c09aa-12f1-559b-9b16-cfeed9888b15 |  | note | Projecting reinforcement is the correct length and location.
label | d1055979-2584-5f54-be76-7ba46e9c606b |  | note | Splice lengths achieve the minimum length and are in contact for this length.
label | 2a37a212-b182-5dd3-b6f4-4d96aeb60d60 |  | note | The reinforcement surface condition is free from dirt, debris and damage.
label | a590df53-7218-50a4-856e-519de31784e7 |  | note | The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | b8b69b12-f096-5aaf-a32d-8f8cefcb2a84 |  | note | Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
label | d1608b33-8836-54cf-a506-4610e651e9fe |  | note | - - - - - - - - -
label | 96b61fd4-a40e-534e-9561-852e386f710b |  | note | Reference Documents - VicRoads Spec 611.06
label | bf073f8f-5a35-5aea-aad7-7d3eb97c681d |  | note | 611.09
label | d43be27e-0990-5aea-9808-7ffa4cd5e612 |  | note | 611.1
label | b5f4924e-d4ec-53e0-a836-fdf1cbbddf76 |  | note | 611.11
label | a1ee14d3-8cb3-5f15-859a-6593c495d0d5 |  | note | 611.12
label | 2b682d54-9c20-53f1-8151-fdbd7ad4beb4 |  | note | - - - - - - - - -
label | ed9f2689-89de-5178-b21c-ff3726dce4ca |  | note | Inspection / Test Method - Measure
label | 0a7c28da-48dd-5faa-b2a4-3c075a41a67e |  | note | Visual
label | fcdfdb38-6d50-5857-872b-d75a2db42391 |  | note | - - - - - - - - -
label | a56303e1-b198-5d5e-be38-8d1e2fc0a22e |  | note | Record of conformity - This ITP Signed
label | bd8c9f58-2e1c-5c2b-84c4-1795e93a98d5 |  | note | - - - - - - - - -
label | d8f28c5c-9697-5ff0-ae4f-8e94a247d156 |  | note | IP
label | f51b78f8-f2fe-5def-a182-3b2fa09bed9c |  | note | - - - - - - - - -
label | 9dcf4e2a-1940-57f9-9de6-7ec915bb7245 |  | note | Foreman
label | 9525dd99-ac6a-5cc9-8e6d-2ec5e792aef0 |  | note | SE/PE/SPE
label | 2a3edcda-4556-56f6-94c4-7fba125e1782 |  | note | - - - - - - - - -
date | cf950ec6-9f06-5090-afd4-719a24020657 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Pre-pour Inspection
label | 23e2ac60-7abc-54f7-a582-f01ee1ed9da9 |  | note | Frequency - Prior to concrete pour
label | 96294161-0f18-5bc0-9c14-349441071092 |  | note | - - - - - - - - -
label | 590fee72-385a-55d8-869d-a2c0cf9de3ac |  | note | Acceptance Criteria - A pre-pour survey carried out by a surveyor.
label | 99af02ba-336e-5e2b-b2f2-91bf616a495a |  | note | Erected formwork within the tolerance as Cl.610.36.
label | f965ba00-0af4-5caf-befe-5cf6885c7979 |  | note | - - - - - - - - -
label | ba350131-cc82-5088-b58b-fc1c9189c7a1 |  | note | Reference Documents - VicRoads Spec.
label | 45f38f4a-2725-54b8-800d-974c2c57d916 |  | note | Cl.610.47
label | 1ffc74d9-5451-559a-8f13-6f611a7afbb2 |  | note | Table.610.471
label | 0b20bccd-38dd-59b6-b1dd-468404e9498f |  | note | Table.610.472
label | dd5d76de-c0c1-58ea-bddc-592f48e7c8cc |  | note | Table.610.473
label | 477d1c39-a1f8-5080-bca3-e3f2a6129e8b |  | note | Table.610.474
label | 670f2b55-ae99-5124-876b-342a1dfdd2a1 |  | note | - - - - - - - - -
label | 30d54d81-9abc-5e97-af76-558879ce9026 |  | note | Inspection / Test Method - Site Inspection
label | ac80a8cc-1732-538c-90f9-ad33f2d951f4 |  | note | - - - - - - - - -
label | 10537dcf-cd2e-55e6-ac12-a29bd33f717d |  | note | Record of conformity - This ITP signed/
label | 422d4d94-b718-5fd1-b6f6-6860ef2a42f7 |  | note | - - - - - - - - -
label | 70224d02-0a09-5099-884c-9113e913f77e |  | note | SCP
label | 5c756a4d-c541-5831-983e-e7c8e7c79cc2 |  | note | - - - - - - - - -
label | 25531554-275b-5911-bfc6-e48e54213c16 |  | note | Site Engineer/ Surveyor/Foreman
label | ca7b742e-3c82-5dae-b7eb-ae6a794e2407 |  | note | - - - - - - - - -
date | d002ad5b-11fb-5c98-b9ce-e284a6dfc765 |  | date | Date Completed:
checkpoint-group |  |  | section | 6 - Construction Activities - Concrete Pour
checkpoint-status |  |  | checkpoint | 6.1 - Construction Joint Preparation
label | bf4adc40-ee9d-546b-9be4-e8328b50d93a |  | note | Frequency - Each concrete pour, prior placing concrete (As required)
label | 5dd53bca-33de-530e-874b-0a875639dcbb |  | note | - - - - - - - - -
label | aef938d0-fd01-578a-adc8-9e5f0442e063 |  | note | Acceptance Criteria - Construction joint preparation in accordance with CL.610.20
label | dfd511ba-006f-5bab-a474-f4cd3a0cbd77 |  | note | Existing concrete to be roughened by removing all laitance and sufficient mortar to expose the coarse aggregate to a depth of 3mm.
label | 4a977315-b35b-5dee-8594-c092807579d2 |  | note | All surfaces should be cleaned, moistened with water with any excess removed immediately prior to placing concrete.
label | c55acd4c-45f4-56b9-8a9b-0fddd4fb3b7b |  | note | Joints shall be at the locations specified on the drawings
label | 0977fe47-52ed-5136-830c-fa4aa88c7af3 |  | note | - - - - - - - - -
label | 485016a6-7d69-5bff-a0f2-5c3717c74045 |  | note | Reference Documents - VicRoads Spec.
label | a95ef7e0-5d1c-52fb-a669-b231e2a31867 |  | note | Cl.610.20
label | f6ac7b5b-1038-5219-808f-84c0627403cb |  | note | - - - - - - - - -
label | e1cff250-dddd-53d8-a05b-3e3641577089 |  | note | Inspection / Test Method - Site Inspection
label | 55a5d35e-4168-52a8-bf5e-8aab5d189f51 |  | note | - - - - - - - - -
label | a5153b67-df78-5fbf-8ab2-4902fbcec27e |  | note | Record of conformity - This ITP signed
label | 37732175-af6b-5c58-a273-1404a28395ef |  | note | - - - - - - - - -
label | 470dd152-f2f3-556f-9eff-e1c7107c830b |  | note | IP
label | 2add5f80-8014-51ca-b919-5a257e965742 |  | note | - - - - - - - - -
label | f728b0fa-f639-523e-ad38-58b9fd162a17 |  | note | Site Engineer
label | c2d536b4-6750-54eb-91e6-0b833ef035f7 |  | note | - - - - - - - - -
date | 583ab676-2d0a-5b4c-b750-a34c3f86ae1d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Cast-in Items
label | 550d13f7-6f4c-578b-9010-7d90e29a6660 |  | note | Frequency - Where applicable, each element
label | d9a21102-7532-5b86-b9c9-7ccb4dee3fe4 |  | note | - - - - - - - - -
label | e11654fb-8a95-5abc-bb54-36c85c6e985f |  | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | 1a9cd49c-2e91-5df2-94df-22d3e6bb5e2c |  | note | Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | 52a9ee83-57fe-55c6-b1c3-3a6b9cc50ac6 |  | note | Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | ef779fb7-7b8a-5fbc-a69b-2fedcbb0c493 |  | note | Grout tubes shall be fastened at regular intervals to prevent kinking.
label | b8b6a6a5-7950-5d11-95f3-76f83dd0454d |  | note | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | fab0c0aa-bc6b-5dd1-8bce-93b2da23624a |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | 9dae9326-d605-52b4-8749-a53413db88a7 |  | note | ii. Running dimensions of a group of the above = ±6mm
label | 0470886d-1b93-5bff-a5ae-50950b612b60 |  | note | iii. Ducts and conduit location = ±12mm
label | a8755566-bc7f-5be7-bea9-406c136d40f4 |  | note | iv. Diameter of ducts and conduits = ±3mm
label | 3011e4a1-436b-57f2-9005-901ebf63d9ec |  | note | - - - - - - - - -
label | 0f16b086-1d39-5d48-beb8-3542597e9d19 |  | note | Reference Documents - VicRoads spec.
label | b1b8a641-f0a1-5c7c-87a9-18124a752dac |  | note | Cl.610.47 (a)
label | 831885d8-8625-5eb7-b8ee-ffadb8ca2eab |  | note | AS3180.1 Table 3.3.6.2
label | 721f10f4-214c-57cb-8335-ed05f44d5da2 |  | note | - - - - - - - - -
label | f66e31dc-e926-50eb-afa6-3232308b5661 |  | note | Inspection / Test Method - Site inspection
label | ace3e948-e448-516c-9075-36af2a4cb012 |  | note | - - - - - - - - -
label | fc9b2a40-b092-5a8a-8d32-8b0935d7fd6f |  | note | Record of conformity - This ITP signed
label | 4b25e30b-1b8d-5b76-bfb2-de92417a0917 |  | note | - - - - - - - - -
label | e9293ca0-9f94-54d2-9062-ecb5f65b0757 |  | note | IP
label | d6d82cef-d10c-544d-bd3b-1d58fac9d214 |  | note | - - - - - - - - -
label | 2a091511-a311-555c-acb3-0244953c4fdf |  | note | Site Engineer/ Foreman
label | 31713379-6f74-57f1-88a7-d656e0b25706 |  | note | - - - - - - - - -
date | f320ace0-fe91-535c-add9-64ded9a333cd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Weather Conditions & Evaporation Limits
label | 8b19ffeb-56cd-5338-94fa-efacf9615b60 |  | note | Frequency - Prior to concrete pour
label | 31e303d8-c016-5601-a4bf-28f0e6be0126 |  | note | - - - - - - - - -
label | c47d2cdb-8484-505b-b8a6-7ec64ed5dac8 |  | note | Acceptance Criteria - Unless otherwise approved by the superintendent, the following conditions must be satisfied when placing concrete:
label | f52cf40e-283c-5361-bf16-2257ef1a374e |  | note | a) The temperature of concrete, measured immediately prior to placing, shall not be less than 10⁰ C or greater than 32⁰ C
label | 44e84268-6c47-5528-a64b-d9ee8dd50bdf |  | note | b) Concrete shall not be placed if the air temperature is greater than 35⁰ C or less than 5⁰ C.
label | 1dad1242-7ff3-56ee-b9d4-a87e82023653 |  | note | c) Concrete shall not be placed during rain or when rain appears imminent. Freshly placed concrete shall be protected from the rain
label | de269ff9-9cdb-589a-b8dd-b291e488c40c |  | note | d) Rate of evaporation < 0.50 kg/m2/hr. If not, additional controls initiated as per 610.17. Refer to concrete pour record
label | 739372e9-e3b8-5212-ad29-d6c3cbeb9f22 |  | note | - - - - - - - - -
label | 4bad8a30-13b2-5e4e-b001-a1f140808cf6 |  | note | Reference Documents - VicRoads Spec. CI.610.17
label | 7375589d-99fc-5c7f-987c-98e70c9690af |  | note | - - - - - - - - -
label | 9ec36065-9253-52f4-b938-7299e496c86c |  | note | Inspection / Test Method - Visual Inspection
label | cf8a572a-529e-58ac-b7cb-e335fb35e770 |  | note | Concrete Pour Record
label | 29b1fa07-f4ab-53a1-9793-0e7295b5cddd |  | note | - - - - - - - - -
label | cb0c2985-77e8-5d26-a457-8aa91d5f1ee0 |  | note | Record of conformity - This ITP signed
label | 45aa75ee-bcc1-5d84-8d38-edacd6d4ad25 |  | note | Concrete Pour Record
label | 8779dbcb-ec35-53a2-9f2c-10892805d6d3 |  | note | Concrete Dockets
label | d834afa7-2cb4-5bbc-89eb-d7eca8becb9f |  | note | - - - - - - - - -
label | c1757a54-6527-5f18-ac35-ecde4f496270 |  | note | IP
label | 0cb0fc97-f2cd-5b7a-a693-6295cc135fb7 |  | note | - - - - - - - - -
label | f5fe9712-f649-5671-8d89-42ce3cf16e20 |  | note | Site Engineer/ Foreman
label | 63d7074b-d184-5a91-a327-539bf27b677a |  | note | - - - - - - - - -
date | 57006eb1-71e2-5502-9e3d-2caf3af3dae0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 - Concrete Testing - Sampling Frequency
label | 05e8467e-cc55-53d9-9d9a-8c1411301d4a |  | note | Frequency - Each concrete pour
label | adf76685-19ca-5151-a073-52c18ae51aa6 |  | note | - - - - - - - - -
label | 18ec7bc5-542f-57c4-96b4-474d85b58e1c |  | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 4f9f385f-99a8-52bc-8037-d8cde69a0fd1 |  | note | 0m³ to 10m³ = 1 sample
label | 7c3eee0c-bd08-5e19-87d8-23b6e4ea9a9a |  | note | 10m³ to 25m³ = 2 samples
label | 6d861def-54c3-5fa8-a6e3-68b4bf4707a8 |  | note | 25m³ to 50m³ = 3 samples
label | 7327894c-78e3-5854-ae18-db0067c92d75 |  | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | 380908f7-8b9e-5b04-a816-6454b0a50bc3 |  | note | For each additional 50m³ and additional sample shall be taken.
label | 43323513-042e-55e4-ba85-34fc975f3bbc |  | note | Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | 8f777645-fc2a-5cef-9f8c-a58b257dc853 |  | note | Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | b20b0bfb-2c96-5f77-b57b-20d7f890fadf |  | note | Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
label | 4320569c-0be9-56c6-8935-fb7b9abe9b00 |  | note | Record: Required information on the Concrete Pour Record.
label | fe36c6c1-f879-5080-966d-9b606b08b0f1 |  | note | - - - - - - - - -
label | cde89cf6-4b8b-520a-83eb-3120065cb9de |  | note | Reference Documents - VicRoads Spec.
label | cdc03bb0-d8d0-5dc4-8b99-8f8d05a76a91 |  | note | Cl.610.16 (b)
label | 8c740334-4d24-528d-b132-a9c24eed00a2 |  | note | - - - - - - - - -
label | f6a5b8a1-c157-5186-b78c-bc2d094917d1 |  | note | Inspection / Test Method - Testing
label | 95e9f4ec-a972-5d45-aad0-214a3e3a0df1 |  | note | Concrete Pour Record
label | 32433ba9-7745-58ac-b44e-fd46c50c8ce2 |  | note | - - - - - - - - -
label | 368b0067-28b4-5232-b460-1b4281cbdaa5 |  | note | Record of conformity - This ITP signed
label | 0c126d04-631e-5a96-b5c3-6ecb70e0dd52 |  | note | Concrete Pour Record
label | 4f536432-9a2a-5e2e-838a-a3cca33bcced |  | note | - - - - - - - - -
label | 5c9b9606-4d02-5171-a143-621b53c2cdba |  | note | IP
label | 776b7f83-acbe-5b95-b98f-9966a253d73e |  | note | - - - - - - - - -
label | af7d07cc-a8d8-50ee-92c4-32b4e38a9ccb |  | note | Site Engineer
label | 1e32b592-debd-525c-8795-d0b75535d664 |  | note | - - - - - - - - -
date | bce8d552-4aff-5839-840d-f4de32cb52c9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 - Concrete Testing - Slump
label | 091b3542-7aeb-5fa8-ab95-13896a3f312b |  | note | Frequency - Each concrete pour
label | 4aef4043-a441-56ff-a5b8-bc044eaaec3d |  | note | - - - - - - - - -
label | 0f703a7d-082e-5c9f-8bd9-da32f1fbe8ff |  | note | Acceptance Criteria - Slump testing tolerances =
label | 408b0f62-c71c-5d5a-9cff-11dc0136e87c |  | note | <60mm = ±10mm
label | 7bfe0a31-003c-5953-bffc-9ca702b2b5ad |  | note | ≥60mm to ≤80mm = ±15mm
label | b511ebb5-398c-58d1-ab7b-e8d3ffc0c0c6 |  | note | >80mm to ≤110mm = ±20mm
label | 137bfe06-644b-54ef-af49-4c680759dc42 |  | note | >110mm to ≤150mm = ±30mm
label | c5e1782e-8f6a-5e80-94e6-c225b6264bb7 |  | note | >150mm = ±40mm
label | 4cd15974-e1b2-5719-928f-d171e6dd4d54 |  | note | Record: Required information on the Concrete Pour Record.
label | f4b9f28c-d6da-5e75-a53b-5b947f9d386d |  | note | - - - - - - - - -
label | e18fd85c-ee77-5ea6-8e9e-8bca994d9b87 |  | note | Reference Documents - VicRoads Spec.
label | a7041fe3-9a2d-5116-b5a0-bf2eb6ee5b3e |  | note | Cl.610.16 (c)
label | 34b9df76-4169-52ed-a25a-33fa03298d1a |  | note | - - - - - - - - -
label | 3cd44d1b-2177-5431-b3ed-a335639cc6ef |  | note | Inspection / Test Method - Testing
label | c24c8daa-aeeb-5a06-87f3-6ecafc476897 |  | note | - - - - - - - - -
label | c89e7b14-2cde-52f1-aee9-2a9dfda44366 |  | note | Record of conformity - Concrete Pour Record
label | 1d15060d-e9c4-558a-9374-9193152eaac8 |  | note | - - - - - - - - -
label | 0b4b4a5e-5f15-593a-9e4f-370eb8e6cb17 |  | note | IP
label | 77048b92-d7dd-5487-8b8e-dad19a9fbcf0 |  | note | - - - - - - - - -
label | 52c24b55-b47d-5953-b084-35708d72e89e |  | note | Site Engineer
label | 9e04cdab-a4ff-5ffd-ba04-14853380c194 |  | note | - - - - - - - - -
date | fadfc7c0-4fa4-53ae-9c36-4837881051e3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 - Concrete Testing - Spread, Passability & Viscosity
label | 2f9c17b9-f57d-5dbb-ad09-0f8ec8bce9b3 |  | note | Frequency - Each concrete pour
label | d2706217-17dd-5baf-8f4c-cc549a88cf3c |  | note | - - - - - - - - -
label | 116fb05f-7dbb-5c50-b0d0-eeee6312ec75 |  | note | Acceptance Criteria - Spread range = 550mm to 750mm
label | 5d967384-11fd-52a0-8ceb-0e601f6491e1 |  | note | T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | ce9dc8fe-b40d-5787-a5a7-f4c3785ee2ff |  | note | Passability = ≤10mm (aggregate height differential)
label | 267c5377-93e8-59a2-bcd1-fa14d3e41818 |  | note | Record: Required information on the Concrete Pour Record.
label | 223af025-0c73-5884-a390-0baf9a517a92 |  | note | - - - - - - - - -
label | 029f0c24-b461-5165-8855-bdc1ee7ae03d |  | note | Reference Documents - VicRoads Spec.
label | 04695e04-1efe-5032-aac0-713e727b3a9f |  | note | Cl.610.13 (b)
label | 9b2c4d10-5b68-5f46-a72f-caf46563b009 |  | note | - - - - - - - - -
label | d664dcce-a9a6-5ae4-9786-876a85ae1fb5 |  | note | Inspection / Test Method - Testing
label | cc61a95a-3e21-5384-a37a-8a584c00cb3c |  | note | - - - - - - - - -
label | aed8ac81-61e7-5ef7-97ca-ae448edb49ae |  | note | Record of conformity - Concrete Pour Record
label | ac52a894-0df4-5cd7-9567-b39aee3057f1 |  | note | - - - - - - - - -
label | 0b03745f-1655-5a52-a2ed-807e0796afc4 |  | note | IP
label | e076b4c3-4351-582a-a188-414c345fff94 |  | note | - - - - - - - - -
label | fdc2c65e-373c-54c8-9d7d-fdaa5ea84c90 |  | note | Site Engineer
label | 730360d3-6a8e-5dbf-876a-d1218f1d7d16 |  | note | - - - - - - - - -
date | 8cdee55e-09b3-5c20-8ae2-1f118d7bba1c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 - Concrete Testing - Compressive Strength Cylinders
label | 754cddd5-7f74-5f4c-8631-3b1351338785 |  | note | Frequency - Each concrete pour
label | 59756483-8340-5b8c-a4a3-9dda4e9d3076 |  | note | - - - - - - - - -
label | 838cd123-0f08-5ed7-a006-2a4cce353400 |  | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
label | d162f7f2-552a-538c-a883-0122bbd6457b |  | note | Record: Required information on the Concrete Pour Record.
label | e5502f25-dc74-5793-825b-3b6f5c8eb495 |  | note | - - - - - - - - -
label | 0c064b3a-130c-5388-b783-ae1253ad22e3 |  | note | Reference Documents - Site Sampling and Testing Procedure
label | dc1381d3-326e-5332-bccf-c622ccedcb0c |  | note | - - - - - - - - -
label | a7f45682-f7cc-5146-9cd7-8e1d365f11e0 |  | note | Inspection / Test Method - Testing
label | 6224a788-a7d5-5137-a0a5-d28b0827c9f3 |  | note | - - - - - - - - -
label | 2727bdd0-9a0a-5b70-aa8e-54bd0877d113 |  | note | Record of conformity - Concrete Pour Record
label | f091be53-73ca-541d-934c-55301baf8c76 |  | note | - - - - - - - - -
label | 176490cd-501d-54fc-b05b-1b7127033a0f |  | note | IP
label | 8ca55e82-d101-5eac-8b91-344dab5780bf |  | note | - - - - - - - - -
label | b7541bfa-1ba5-5099-9548-49a67ec9faec |  | note | Site Engineer
label | 4c8480cc-7167-51f3-833a-5326d99f1752 |  | note | - - - - - - - - -
date | e807e36f-caec-5658-ae44-d611525f459c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.8 - Supply & Discharge Rates
label | 7a51e3c2-f3d9-5cd1-82bf-32152e04bfc8 |  | note | Frequency - Prior to concrete pour (each load)
label | e5ce45a9-2f40-5b3a-b2cc-e1f0761c7c92 |  | note | - - - - - - - - -
label | 5039fc7f-3faa-558d-9d1b-67c8fdd3690d |  | note | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed.
label | 986500c3-f682-5d9f-a052-35ddeca2db33 |  | note | No water is to be added once discharge commences.
label | 04576471-f75f-504c-96e7-f9132bba3fb8 |  | note | Maximum time between batching trucks is 25 minutes.
label | b89f223e-667e-5df2-af49-dbdd43db0c4b |  | note | Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
label | 139b5cd9-e595-50a5-8bfb-d8c23f667557 |  | note | Concrete that stiffens or is showing signs of stiffening shall not be used.
label | 8291b0d0-fbe1-53d6-9fb9-a66717134d0f |  | note | Concrete is not dropped freely from a height exceeding 2m.
label | ff33b308-3528-5ce5-ad52-87a854bb9278 |  | note | Concrete is not moved horizontally by use of vibrators.
label | a668d6e2-d665-58a4-bcfd-1efd3300c8c0 |  | note | Record: Required information on the Concrete Pour Record.
label | 85626e81-d8c5-5af1-a23d-819baa616b04 |  | note | - - - - - - - - -
label | f7835d49-281f-5e11-a182-243b136e1e95 |  | note | Reference Documents - VicRoads Spec.
label | 462dd417-4097-5800-a584-82dc11f51062 |  | note | Cl.610.13 (a) & (e )
label | b5d186d5-411d-5c46-9f04-c747208193aa |  | note | - - - - - - - - -
label | 9afeeeb6-7258-5710-81e2-089a83417858 |  | note | Inspection / Test Method - Visual Inspection
label | 57227885-4859-567a-8a77-38bfaf5e5eb9 |  | note | - - - - - - - - -
label | 24581ef5-3fff-58ad-b891-78248ecbf377 |  | note | Record of conformity - Concrete Pour Record
label | 03a3e0f9-a4f0-5109-b8c2-27f59bee81e6 |  | note | - - - - - - - - -
label | ae4d659b-ce90-53d8-9f70-ef7187a59454 |  | note | IP
label | 36bd6749-7264-5846-8b88-59c81f6c62b0 |  | note | - - - - - - - - -
label | 056dbd30-f41a-5ad9-a98d-e6a2526c00e3 |  | note | Site Engineer/ Foreman
label | a18d58a1-e758-5e44-a50d-fcc3a464eb0c |  | note | - - - - - - - - -
date | 66a5c5b0-b08e-5fd9-8d18-d9157f37e5b5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.9 - Surface Finishes
label | a9d43363-c207-5248-95ac-3031167cc6ac |  | note | Frequency - Each element
label | a4967c99-4d02-5ab3-b019-6614f027d5fc |  | note | - - - - - - - - -
label | 347d0b01-accf-5bc5-ae5b-6c527c9b0bb8 |  | note | Acceptance Criteria - Surface finish as per IFC drawings.
label | 499ce53d-e3d4-5d04-9d7e-4f42083b7320 |  | note | Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
label | d24f29b5-b34a-5c11-8137-ed27fceee0fd |  | note | Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | af2d61d0-49f3-511a-bf8f-63501ae4e766 |  | note | - - - - - - - - -
label | af3c108d-38fc-5dbf-a450-0cb135662d6e |  | note | Reference Documents - VicRoads Spec.
label | 19458ccf-d787-518f-a0b8-7a392441b7e8 |  | note | Cl.610.31
label | 0474b508-f4ef-5ddb-9630-569f03ee7871 |  | note | Cl.610.20
label | 85c26291-532e-50c8-99d5-afa0b6812bf0 |  | note | - - - - - - - - -
label | ea81fe9d-2aa7-536a-9089-4c58d2c192c1 |  | note | Inspection / Test Method - Site Inspection
label | aa04e8c3-52c6-5f72-b8c9-671d54a1e40c |  | note | - - - - - - - - -
label | c80754cf-bd70-547e-aa5f-e7c4d73ef240 |  | note | Record of conformity - This ITP signed
label | f8298714-7e3b-5f91-8711-ada5459498e2 |  | note | - - - - - - - - -
label | 3dccfe4f-aab7-5205-bdf9-40604e6cbb90 |  | note | IP
label | 8631d464-e2f3-5c56-9ac5-c2745503ae07 |  | note | - - - - - - - - -
label | 139ff38b-88b1-5dc6-baf6-de5b671f1975 |  | note | Site Engineer
label | 5b9c9934-8294-5f0c-bbf5-fbbc57cf9f53 |  | note | - - - - - - - - -
date | fb24d977-c094-5f1d-ba9c-579a137cc99e |  | date | Date Completed:
checkpoint-group |  |  | section | 7 - Post-pour Details and Inspection
checkpoint-status |  |  | checkpoint | 7.1 - Thermal Differential Monitoring
label | ce7befb9-ed65-5886-96ed-281e4fe98ec6 |  | note | Frequency - Each concrete pour
label | 05d5a74e-5c7f-5264-99aa-4f5783061b4f |  | note | - - - - - - - - -
label | a8e49a25-b3de-5f28-8b0d-30d8a49cd9ea |  | note | Acceptance Criteria - Maximum thermal differential between the core and exposed surface not to exceed 20°C.
label | 64ae5cce-7d72-501e-bd91-ce6edc35ca3c |  | note | Only applicable if the element has:
label | 88e1cccd-fd43-5307-ba1a-da58e4e46957 |  | note | i. the smallest sectional dimension exceeding 500mm
label | 9ea759c9-7b76-58e3-91fe-6985453bc0e4 |  | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
label | 68941fa6-e8b6-5aef-beb0-ca650afce150 |  | note | Attach: Thermal Monitoring Report
label | 006a0c7a-eeae-51b2-98b6-d68e7a1513f9 |  | note | - - - - - - - - -
label | b639e79b-fa08-57e5-84e7-4604bb7b008c |  | note | Reference Documents - VicRoads Spec.
label | 72fb14c4-ac47-5c9e-8ddf-981c2fe30904 |  | note | Cl.610.22
label | 944caab0-892f-55a6-bf82-8e675a0a4f0e |  | note | - - - - - - - - -
label | 6c5e9782-7099-581f-a2ce-8814d6fc07f2 |  | note | Inspection / Test Method - Site Inspection
label | 7fa9fed0-8fce-5c6f-8335-a05c26755d8a |  | note | - - - - - - - - -
label | 59160fe9-2f57-5af9-a99d-4ddb7101af0c |  | note | Record of conformity - Temperature data acquired and proposed control measures to reduce differential temperature submitted to Superintendent for review (if applicable)
label | 6948ea3c-e2a6-5799-8b86-2ee1e7f5b565 |  | note | - - - - - - - - -
label | f34ee2b4-df0f-5972-b792-ca3355a7b9fb |  | note | IP
label | 543e016e-cd36-5d2c-b366-45f78062b0bf |  | note | - - - - - - - - -
label | 3eda882b-29a8-5dc9-befa-c373aba3efc3 |  | note | Site Engineer
label | bbc767b6-cb5f-5400-81ff-1135629000f1 |  | note | Subcontractor
label | 518798ef-8c07-5d27-b0de-82e96aa897d2 |  | note | - - - - - - - - -
date | cef65a31-0dc9-5796-8b64-88bc6b8e6c1e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 7.2 - Early Age Compressive Strength Test Results - Removal of Formwork
label | 9b3dc8de-41c3-577e-bdef-7e81747de340 |  | note | Frequency - Each concrete pour
label | 81e696f8-0317-5f1e-b55e-4ab95360143d |  | note | - - - - - - - - -
label | ec3a803f-896c-5226-a153-d331e169f8f7 |  | note | Acceptance Criteria - Where IFC drawings do not nominate minimum strength development for removal of formwork, refer to Table 610.251.
label | d79a186d-85ca-5f37-96e9-6fad6fe3fdf6 |  | note | Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | 0240144b-1ca1-57bf-8604-1c8c7a849226 |  | note | - - - - - - - - -
label | cc6a21af-9e0a-5613-ba6f-134f257df59b |  | note | Reference Documents - VicRoads Spec.
label | cd9909ec-3a18-5a81-b246-3915d6c49ad2 |  | note | Cl.610.25 (b)
label | 56537ff8-836a-55b8-8b3e-9db241fe43f3 |  | note | Table 610.251
label | 4c1e70f2-c1b1-5052-b5fd-e798efd7e89e |  | note | - - - - - - - - -
label | 92ad80d7-391d-5660-bc52-d71de61222ce |  | note | Inspection / Test Method - Site Inspection
label | d10ff9fe-dd38-5573-9ad8-211e811a11a3 |  | note | - - - - - - - - -
label | e96ba9cb-dfef-5a9c-9313-9241d1c97dc8 |  | note | Record of conformity - This ITP signed
label | f8a7ebf3-f911-59a9-9454-a8b3e95b30ac |  | note | - - - - - - - - -
label | d48554cb-e245-51df-ac7c-3726302a5558 |  | note | IP
label | 52dadd5c-5e88-5f4c-b1fc-8952fead737e |  | note | - - - - - - - - -
label | 93170bfb-c961-55c3-8e8a-a98710c10982 |  | note | Site Engineer
label | d73f5d62-ec13-5a13-b1a8-9ad3db9f7790 |  | note | - - - - - - - - -
date | eb780b5b-cfb5-541e-a82c-be53b343d076 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 7.3 - Surface Inspection - Cracks
label | 423d6159-dfbe-573c-a1f7-2bd9c6d870ef |  | note | Frequency - Each element
label | f64bafaa-da4f-507e-9d96-11a45fed94cc |  | note | - - - - - - - - -
label | 654fde02-5b6a-5fab-8c53-43bccf0c3b60 |  | note | Acceptance Criteria - Repair procedure submitted to the Superintendent. Repair undertaken in accordance with VicRoads Section 687.
label | 02f29a35-bcb6-578f-a6f1-4c31417fffd6 |  | note | Cracks investigated and if greater than specified in the table 610.241, an NCR raised. Notwithstanding the requirements of this clause the acceptable crack width at the concrete surface of precast pre-stressed concrete elements shall not exceed 0.1 mm.
label | 47d95dba-4f1c-5c6f-9a56-a630e3c26119 |  | note | - - - - - - - - -
label | 0a78c04d-1fff-5918-b179-5f76d28aea36 |  | note | Reference Documents - VicRoads Spec.
label | 88353520-bd17-599d-95ca-650e1851d90a |  | note | Cl.610.24 (a)
label | f338985c-8742-5d63-8b92-ae24380f4e83 |  | note | Table 610.241
label | d57729d8-8902-521c-a6c8-306e9d644aad |  | note | Section 687
label | 40d284c1-7faf-5598-85b5-edc4f635a675 |  | note | - - - - - - - - -
label | 793b9577-6dcc-5d72-96a6-27e5ef4a599d |  | note | Inspection / Test Method - Site Inspection
label | 0ffb628f-2933-5751-bb03-1d12e0683e65 |  | note | - - - - - - - - -
label | 1104ed5d-de33-550c-b729-498cfc0f0f00 |  | note | Record of conformity - Superintendent approval (if applicable)
label | 55863ce4-9408-5810-b6e7-e6e14c45abc9 |  | note | - - - - - - - - -
label | 9932b1e1-a71d-5b0e-91ed-fa93f6c37904 |  | note | IP
label | 1a0dee38-0f5a-5517-9991-ea16d0579aab |  | note | - - - - - - - - -
label | aaec7a1b-0fe0-5788-8750-6692c404f3d4 |  | note | Site Engineer
label | 52007b70-092d-5595-990b-a0e7a75e39e2 |  | note | - - - - - - - - -
date | 7f63a685-b9a1-5d6a-a454-f3d9161a9f01 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 7.4 - Early Age Compressive Strength Test Results - Removal of Formwork
label | 46830225-de9e-53e8-a3c8-0438d89c552b |  | note | Frequency - Each Pour
label | 45f2ef77-a955-511d-b280-916739b1ec83 |  | note | - - - - - - - - -
label | 7533b5ae-61a1-5737-b228-2549cd7bbc14 |  | note | Acceptance Criteria - No fill is to be placed against concrete within 14 days of casting in accordance with the requirements of Clause 204.11 of Section 204. Proposed placement prior to 14 days from casting shall comply with the early application of loading requirements of Clause 610.16(l) or maturity testing requirements of Clause 610.16(m).
label | 138654ce-beeb-5ad7-9e21-afcf06590a0e |  | note | No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Superintendent.
label | a522b9b8-9806-5d49-bba7-874479238d38 |  | note | - - - - - - - - -
label | 0d426286-a1be-58f9-818a-1861708661e9 |  | note | Reference Documents - VicRoads Spec.
label | f3f3180c-ec07-5aad-92d8-4abd6149f6ba |  | note | CI.610.35 Cl.204.11(b)
label | 53469ed0-f638-59b4-b887-9507f9919092 |  | note | Table 204.111
label | fc20310f-51c8-5f8c-bad1-163ed4e19473 |  | note | Cl.610.16(m)
label | 36cf5e51-439e-5921-a07c-c47ebd576047 |  | note | - - - - - - - - -
label | bd1f8f2d-dce4-54e5-be09-52ffcbd53cbd |  | note | Inspection / Test Method - Site Inspection
label | b5cdb60f-c15f-54bf-99f4-75efd93fd8dc |  | note | - - - - - - - - -
label | d1ed08f4-440d-5af4-80bf-c3cdf037a386 |  | note | Record of conformity - Holdpoint released
label | f1d314f2-1814-53c1-8616-89d4352408fc |  | note | This ITP signed
label | b86bf711-fe75-5503-a1f3-c4c160d7a79b |  | note | - - - - - - - - -
label | 8c4e9643-34b3-58dc-977e-513c0dbea7e2 |  | note | HP
label | 4fce19cf-eb09-55fe-a657-2d419b4da73d |  | note | - - - - - - - - -
label | 9d71b939-c2e7-5594-b70b-30c697369b99 |  | note | Site Engineer/ Superintendent
label | 47cba3d6-db0c-59aa-be8d-bee61af3255d |  | note | - - - - - - - - -
date | 400d0fae-0e14-5e3f-b1e6-f3a5f4b78355 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.5 - Compressive Strength Result
label | 8d4312c9-4e55-5a91-8e8e-371b28b22688 |  | note | Frequency - Each Specimen
label | 9cf45ded-f8ed-5859-b15a-5ead9935e46b |  | note | - - - - - - - - -
label | 98ff676a-f9a2-5e52-abf6-d1141c3e857a |  | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | 3f569954-92fb-58d3-bf43-1f4fb93cc905 |  | note | 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | c5d195f4-58f5-54e4-8eb0-dd4b84cea0e4 |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | 771df255-6019-5ccc-a931-33cbb632b201 |  | note | Attach: Compressive Strength Test Results
label | 113df0fa-9673-59e0-9ee0-acfc75f31fb9 |  | note | - - - - - - - - -
label | 3623c178-9583-5b06-bb27-febbc424adc8 |  | note | Reference Documents - VicRoads Spec.
label | 9a9caa41-26e9-5004-9701-d1ee767064df |  | note | CI.610.16 (g)
label | f844b2d2-948f-5f06-b628-2576d466158d |  | note | Table 610.051
label | ebc6500b-cebe-5445-ba47-ba02af067b42 |  | note | - - - - - - - - -
label | 93134cd9-9040-5202-8a7d-0446b9d17c1e |  | note | Inspection / Test Method - Document Review
label | ba5863c5-05e6-553c-8110-6b67545ec110 |  | note | - - - - - - - - -
label | e13522fb-0dc2-5763-b817-12b1cf87592f |  | note | Record of conformity - Concrete Test Result
label | b6d221b5-0eb0-5c2d-bc23-07dd2233463e |  | note | - - - - - - - - -
label | 442b63ef-6ca9-5d08-b22c-d959487d8e45 |  | note | IP
label | a1190f05-fc05-54ec-b3c7-10b60c4cfcd1 |  | note | - - - - - - - - -
label | 0737f2e5-52bf-5e0d-ba87-4373bd82aa3c |  | note | Site Engineer
label | 4b485a82-f16e-5dee-bf00-a76835e87694 |  | note | - - - - - - - - -
date | dc35da6b-be09-5b95-a185-b96b48e3f2cc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 7.6 - Post Pour Concrete Cover
label | 47166fcf-aed1-5110-8e88-a45b217275a7 |  | note | Frequency - Every 25m2 or part thereof.
label | 1ffc6338-b056-5cb6-88d8-b38fd836910c |  | note | - - - - - - - - -
label | 94280a8c-f115-5c96-bc1d-981afd6c9edf |  | note | Acceptance Criteria - Concrete cover meter check one 3m² test area for every 25m² exterior surface area.
label | c6a901d0-8b72-5a6f-9b8c-ac327a6b3d24 |  | note | Minimum 10 no. measurements recorded in each area.
label | 83cc9a89-8022-5131-8a7e-f625c5e8b8a5 |  | note | Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
label | 6dac6ef0-1488-5533-a586-7c578a5f1cac |  | note | Attach: cover meter Check Record
label | 1e03089c-c625-54e3-b113-e7572f056cca |  | note | - - - - - - - - -
label | 7dba0c92-1bf4-571a-92b3-748085e2e45a |  | note | Reference Documents - VicRoads Spec.
label | 9126da31-7960-5bd6-8169-4239e0154569 |  | note | Cl.610.34
label | d54c9323-c117-5a36-aa38-c2f0cfe187a7 |  | note | IFC drawings
label | 9993c2e7-cf14-5799-bf19-d4e176b110f7 |  | note | - - - - - - - - -
label | 63fcf515-5576-565e-8f16-7497d75638bb |  | note | Inspection / Test Method - Site Inspection
label | 78b67b7f-60a1-5608-905f-8eb5a8678846 |  | note | - - - - - - - - -
label | e41e53e5-c535-579a-808d-db3f7924f0d4 |  | note | Record of conformity - This ITP signed
label | a55102f7-0a3d-5c0b-a304-07c86dc0e69e |  | note | - - - - - - - - -
label | f692eddc-0ea8-5061-ad11-abd760d320dc |  | note | IP
label | 64d46e8a-6753-53fe-ba2c-9e9a2be7ed4b |  | note | - - - - - - - - -
label | 2bc5a100-420f-57bf-97f4-a559b71ef2ac |  | note | Site Engineer
label | 5bf9708f-001d-5551-a845-a09f8c91e08e |  | note | - - - - - - - - -
date | 485471b5-21ae-5ec3-bce6-baa7170820d2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 7.7 - Prepare As Built Drawings
label | 0d0356a8-b71e-5b33-8e53-5ffa27f1697f |  | note | Frequency - Prior to lot closure
label | 539d74e2-c6b7-50a8-b17e-32e700819d3a |  | note | - - - - - - - - -
label | 07d7eb59-b7fc-52b6-bd6c-24d9bc4ef3d9 |  | note | Acceptance Criteria - As-built survey completed and drawings (IFC Mark up Drawings) prepared for the lot and copy of the drawings kept in the files
label | 9122df14-9ff9-5138-bd35-3aeb4cc864bc |  | note | The tolerances listed in Tables 610.471, 610.472, 610.473 and 610.474 are the allowable deviations of the finished product from the dimensions shown on the drawings. These tolerances will be a basis for acceptance of the work.
label | 60ff8e0a-4758-52a7-bd41-6531d93e890a |  | note | - - - - - - - - -
label | 907ec2ed-8ec2-59a9-a6cd-5cb70e787b1f |  | note | Reference Documents - IFC Project Drawings
label | 39ff6c24-c431-5bb4-9ba4-8946a6de6c86 |  | note | - - - - - - - - -
label | f73c9946-aced-53c0-9f86-ba354b7f2fd5 |  | note | Inspection / Test Method - Site Inspection
label | cc72bf04-8e72-505e-b3b7-c1ec85ef4616 |  | note | - - - - - - - - -
label | 54ac9242-eb5b-541b-ab71-7dd7dbd11051 |  | note | Record of conformity - As-built survey and drawings
label | 7d806854-b386-5a9a-b693-0ed34e2e5e95 |  | note | This ITP signed
label | 10d2b67c-e86a-5e55-aa29-2b60e30287a3 |  | note | - - - - - - - - -
label | f5bea387-fbcb-568a-af8b-31ce4c5ca7b2 |  | note | IP
label | f9896261-aba7-5996-8d0c-dcd2f2d67217 |  | note | - - - - - - - - -
label | 888cbebd-0378-5eb3-89fb-4985f2f0bc48 |  | note | Site Engineer
label | 393c3591-2599-5a4f-80c7-75c16489dd10 |  | note | - - - - - - - - -
date | 45d14d56-cf38-57bb-9add-d8eccda6d01a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 09a56997-442d-5732-bc00-ad4675dbfbc4 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | ad09f220-aa45-5719-85ed-18529ad61f9c |  | textbox | Print Name:
text | dd63fdb1-330b-5e6e-a546-7520c5d71c43 |  | textbox | Position:
date | 2655c01d-4fd9-5bf5-ac4c-d6bb81702fac |  | date | Date:
date | 73be5848-c035-5755-a875-8d3158307e29 |  | date | Work Completed On
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification.
date | 28e44bcc-d37a-5616-8278-6ec6e93dc51e |  | date | Work Completed On
select | 126c0cc5-0d8e-5d8e-b9c7-15f434612d45 |  | dropdown | Is the relevant RFI attached to the Lot? | YES,NO,N/A
select | 6d9ca1f6-838f-58ff-b783-bf0de1bc316b |  | dropdown | Is the relevant NCR attached to the Lot? | YES,NO,N/A
select | b5a7cd87-b63d-5cfa-8fa1-8fdf8f86e1c5 |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES,NO,N/A
select | 9b97c1c2-3a4e-50f6-87d7-cadbe4dfadb3 |  | dropdown | Lot Plan or “Highlighted” IFC drawings (mud maps) attached to the Lot? | YES,NO,N/A
select | 30d15730-24c1-56bf-a183-e24d6393bdb3 |  | dropdown | Survey conformance records attached to the Lot? | YES,NO,N/A
select | ed9843b9-260b-5410-b69d-bbf485622a1d |  | dropdown | Subcontractor/ Supplier records attached to the Lot? | YES,NO,N/A
select | a24f6c7e-27c9-5d98-9d15-7adf8f8c4545 |  | dropdown | Conforming Test Results attached to the Lot? | YES,NO,N/A
select | bd79fc28-16e6-529e-b13c-c34dfb4bb143 |  | dropdown | As built records attached to the Lot? | YES,NO,N/A
select | 74ed6677-2312-53b3-bc90-0676bf23578d |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | a98ccd77-2074-5fb7-aeda-00b94fb49a26 |  | textbox | Other:
select | 752f892f-7b70-51c2-b600-df65f6d4dba5 |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | 513511d1-c31e-580d-a44e-1cb104ec99a2 |  | date | Lot Closed On
text | 5ad8b5fc-0032-5c3f-b2c7-6418d6a38f12 |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-045-UT-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0045 - Installation of Traffic Signals | 52a975ec-c750-4831-a360-236ebacac6d5
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | c02ff5f1-ba78-5d3e-8c03-2101c25e3bca |  | date | Lot Created On
date | 6665003b-8b9c-5a9e-b3c5-679c9cfdfbe2 |  | date | Lot Opened On
date | d55bed56-9da3-5a3b-9dc7-37a2dbae7227 |  | date | Work Commenced On
select | 75028f47-3b38-51a8-923d-8cb7855355b1 |  | dropdown | Lot Type | CIL-Civil Lot, DRL- Drainage Lot, EAL- Earthworks Lot, ELL- Electrical Lot, UTL- Utility Lot, STL- Structural Lot
text | d9dd009d-f702-5892-b6ae-41e451c028c0 |  | textbox | From and To Chainage
select | d88b9afe-dbf2-5a50-b1cc-717751313bb0 |  | dropdown | Construction Element | ITS - ITS
select | 25b18b82-ead2-5504-a494-055fcdd4ebc4 |  | dropdown | Activity | TRAF - Traffic Signals
select | a10c025c-fde4-5d93-9df4-71ea47f880d0 |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | 62510eb3-d10d-5921-b9cf-2af39c8eb0d5 |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | 0d0b589f-7414-51c1-b873-f6328ebb2499 |  | textbox | Engineer Responsible
text | e1f19ad5-600c-5048-bcfd-8dadab24b264 |  | textbox | comments
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Induction
label | bc9b1ac1-be95-5afd-b288-0ee5896ac88e |  | note | Frequency - Prior to Commencing
label | c409cceb-5f22-5b70-bc30-3bc47f2efa6c |  | note | - - - - - - - - -
label | 829ee597-6f21-5005-9449-06d34c55a99c |  | note | Acceptance Criteria - All personnel on site have been inducted to the CRG site
label | 3472e516-32b3-551e-8511-8dd19c62fad1 |  | note | - - - - - - - - -
label | fd36123b-e0f2-5277-89f2-81f1b8023d7f |  | note | Reference Documents - PMP Inductions Register
label | d5f0be26-3ba5-5714-b19c-3b8a491dcc1e |  | note | - - - - - - - - -
label | e78feccc-4195-5680-8e97-8a799d3e6203 |  | note | Inspection / Test Method - Document review
label | 5b24ba77-b915-565b-b300-1acdc8efae0d |  | note | - - - - - - - - -
label | 53a34937-2e50-5b42-8aff-3ff5252b8465 |  | note | Record of conformity - Site induction signed.
label | 57f94bc2-b0c5-5a52-9ce2-ba8d79dd619e |  | note | - - - - - - - - -
label | 307c57ee-38f5-5b24-b63b-266f7d640ac3 |  | note | IP
label | ce9b4132-cbf6-57c8-b6f8-4e2a27d9a584 |  | note | - - - - - - - - -
label | f60d983a-7dcd-5438-b45c-18677adc5b10 |  | note | Responsibility - Site Engineer / Site Foreman
label | 0ad2545c-6fe7-5fc7-8fc8-72df5ae6d2ee |  | note | - - - - - - - - -
date | 84d42be9-b8b8-5556-ab08-0404d50e9dc8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Check that current revision drawings are being used
label | b349009d-6ed1-5a1b-be25-4255e7c3ce7f |  | note | Frequency - Prior to Commencing
label | 5e41fefc-5465-5c20-97dd-27d55c7e9ee7 |  | note | - - - - - - - - -
label | 877031e1-de9a-5007-aaf8-7635fdaf76d6 |  | note | Acceptance Criteria - Issued For Construction (IFC) and latest available revision used
label | 1c93fe0a-2c61-5263-b671-5bc015365054 |  | note | - - - - - - - - -
label | de9b2c79-155e-5a20-9ed3-b2f986147356 |  | note | Reference Documents - Project Drawings / Drawing Register
label | b649b362-807f-560a-a6a4-1f4447e0e03e |  | note | - - - - - - - - -
label | 415ede9f-1d63-5e3b-bb50-f0c97c54ca19 |  | note | Inspection / Test Method - Document review
label | 4e9af4cd-30b8-5cf3-b657-864e9f62afd7 |  | note | - - - - - - - - -
label | 2875821d-3672-52e7-9299-3bf7b67e8555 |  | note | Record of conformity - Latest Revision Drawings
label | 63da0948-0970-538f-add8-9a3312240676 |  | note | - - - - - - - - -
label | 04ede952-6e3d-5c8a-8b9c-233a135e5ee6 |  | note | IP
label | 6232c9bb-e94d-5593-beb9-079ac7d99488 |  | note | - - - - - - - - -
label | 8ab53368-397f-5919-909b-2e374bb65d04 |  | note | Responsibility - Site Engineer / Site Foreman
label | 48df6bf8-5736-5eac-9034-7d4f2126f610 |  | note | - - - - - - - - -
date | 4bb215c7-c4c1-5ef3-a6f2-6e7ab21574a4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Confirm understanding of current Environment Management Plan (EMP) related to the work area and that all prescribed environmental controls are in place
label | ba98c806-eb97-50be-b652-416f3bb0c3cf |  | note | Frequency - Prior to Commencing
label | 384906d4-440f-5152-8093-cfdc8d873465 |  | note | - - - - - - - - -
label | 592c1b04-c0bf-5a81-86b9-80c8147c3180 |  | note | Acceptance Criteria - All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | 52bf50b7-d4b8-544c-97af-ff3299e8e430 |  | note | - - - - - - - - -
label | d1076647-7e2c-5d41-b724-0263acc94d87 |  | note | Reference Documents - EMP, Site induction, Project Specification Cl. 1200.03
label | eea52508-181f-5ad2-b3b9-52ef01ce555b |  | note | - - - - - - - - -
label | 7dd92a91-8dfe-5faf-a14a-610c90b091ff |  | note | Inspection / Test Method - Document review & Site inspection
label | 478f4a15-26d3-50b4-b776-b6a89a0bd790 |  | note | - - - - - - - - -
label | 3a446fb1-f1a2-5fd1-a3a8-ef34591dfae7 |  | note | Record of conformity - Signed ITP
label | f31eb526-be3a-5155-8f62-947ec69c2c51 |  | note | - - - - - - - - -
label | f8da4179-34bb-5f64-9c3b-7ed2216451e8 |  | note | IP
label | 7a8e553a-51d2-5ac0-a2ff-00b39b73d2f9 |  | note | - - - - - - - - -
label | 3d377efd-3268-5035-86b7-2c61b2d28339 |  | note | Responsibility - Site Engineer
label | f8d36116-8749-5120-9d19-d6051c9807a4 |  | note | - - - - - - - - -
date | 1f16ab6a-928e-5628-abae-63fd3131f457 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken
label | 87638ccc-198c-5d32-9b68-c09d4f8fdaab |  | note | Frequency - Prior to commencing
label | 8e266c76-8bca-5623-b9eb-084974459415 |  | note | - - - - - - - - -
label | 826726fa-1c44-5eed-9f9a-ca06bb151c63 |  | note | Acceptance Criteria - As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
label | 07cda80c-f1da-5d44-aff0-8d38dcceb835 |  | note | - - - - - - - - -
label | 2889f99d-40f4-50e4-be04-959d81961e79 |  | note | Reference Documents - Health and Safety Coordination Plan
label | 5ae6a093-dee6-5182-8ce1-8140bac9eade |  | note | - - - - - - - - -
label | f75cca91-cf16-5412-87e7-ae1462cc8232 |  | note | Inspection / Test Method - Document Review
label | d95c7ec8-2f05-5734-aa0b-e99c892e8ff8 |  | note | - - - - - - - - -
label | 4cefa32c-e165-5375-8227-bbfd3c1dac20 |  | note | Record of conformity - SWMS(s) signed
label | 8c8849e2-0d73-5bff-8ac4-f84e56006888 |  | note | - - - - - - - - -
label | 2e380ddc-dd79-5b64-8f6a-1b5c8bea8656 |  | note | IP
label | 36b1b6ff-312e-5043-898a-27379a49196b |  | note | - - - - - - - - -
label | b656ca9b-de9c-571a-8054-3ca655a3c72c |  | note | Responsibility - Site Engineer & /Site Foreman
label | 251dae14-510d-5bc1-a919-b3bc3d4eff4d |  | note | - - - - - - - - -
date | 5d89cc2b-ff0f-500a-869d-4c4880ef51cf |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 - Ground Penetration Permit issued
label | 184ecc22-9d19-53d1-9d1a-22cf3ba76cf4 |  | note | Frequency - Prior to Commencing Work
label | fd975519-ba48-5ada-ab52-68c03b3d57ad |  | note | - - - - - - - - -
label | f892829a-28ca-5f60-8397-31fbca212e3a |  | note | Acceptance Criteria - Current Ground Penetration Permit signed and specific for the area where works will be executed.
label | 3f9b5506-14df-5f5e-a308-9c492038e389 |  | note | - - - - - - - - -
label | 7485b168-81ac-5cbe-a490-76503636f8d3 |  | note | Reference Documents - Excavation Permit
label | 5db36e95-b91c-5219-9708-4f4fa81fbcd0 |  | note | - - - - - - - - -
label | 8063cac1-c2fb-5431-8825-2adf406f1903 |  | note | Inspection / Test Method - Document review & Site inspection
label | 9f281c9a-dd45-533a-8a2b-bac3b6682f78 |  | note | - - - - - - - - -
label | c66bef9e-f22b-5eb1-ac50-d6882139f2ec |  | note | Record of conformity - Excavation Permit #
label | cfbdfd29-0e96-5733-ae55-29a92cb95188 |  | note | - - - - - - - - -
label | 55aff8de-5fa7-5cfc-bf78-4ab23a9cf8bd |  | note | HP*
label | 5eb3449c-139b-5b29-a839-89bbfd416f0c |  | note | - - - - - - - - -
label | b882800e-51e6-54ea-a426-04ad4b40f8ae |  | note | Responsibility - Site Engineer
label | 66042783-75e8-5573-bdb9-5c283163e93f |  | note | - - - - - - - - -
date | 7f4817c9-5270-5376-890d-59b33c8780bf |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Installing Traffic Signals
checkpoint-status |  |  | checkpoint | 2.1 - Civil Works
label | 3397a726-47ae-5f3f-8000-f0a48bde58db |  | note | Frequency - Following Preliminary Works
label | 7063d4c9-b9ee-542e-86fa-830498af507d |  | note | - - - - - - - - -
label | d71be1c2-c46f-5439-958f-a3304c7c66e0 |  | note | Acceptance Criteria - Works completed and subcontractor DoT Report completed in accordance with Section 730 & 733 of the Department of Transport Specification
label | 42cb2182-93e1-51f8-97fe-048c33eb27db |  | note | Pre-installation meeting conducted HP Sec 730.08 c -DoT Pre-Installation Report
label | affb87ab-29ba-5e74-ba55-735ec83ca2dc |  | note | Alternative foundations noted in Pre-Installation Report
label | 72e68caf-9f9d-50d5-bb1a-4a5084b324cb |  | note | HP Sec 730.11-DoT Pre-Installation Report
label | 9263a2f3-8e2c-568c-878a-f515631d92df |  | note | Proposed boring to be discussed, agreed and noted on Pre-installation report
label | aefce0b4-ccad-5a4c-a5d2-5e38a8abbad4 |  | note | HP Sec 733.03 - DoT Pre-Installation Report
label | da52a84c-10f0-5111-838b-200f8f5ee27a |  | note | Pre backfill inspections (conduit / foundation) carried out and signed off
label | 2450f77e-3f04-5d5b-808c-8a0bc8b39aea |  | note | HP Sec 730.11, HP Sec 733.03, HP Sec 733.06 -Healey's ITP FO41 Pit, Conduit, Foundation Installation
label | 0c92a347-608f-5cff-b6d5-46c8a6404cb0 |  | note | Pit lid Surround pre pour inspection
label | fa9967e4-92da-5e8e-b434-331078e0e682 |  | note | HP Sec 733.07 (c) -Healey's ITP FO41 Pit, Conduit, Foundation Installation
label | 5cc71032-a781-5ac9-b70c-7e40815b8ee4 |  | note | Grouting of bores to be inspected
label | 4127729b-a414-52ad-aeea-f2ac1eefe054 |  | note | HP Section 733.03 -Healey's ITP FO41 Pit, Conduit, Foundation Installation
label | 3f9536e2-33e8-59fa-9f17-9596f7ca68d5 |  | note | Concrete testing completed (Slump and Compressive Strength) In accordance with Section 610.16
label | e36e5620-ecd0-5528-aea9-9e0ca7ff9b8e |  | note | - - - - - - - - -
label | a6c98a29-32c7-5ee8-bbe4-50787fb81277 |  | note | Reference Documents - Healey's ITP FO41 Pit, Conduit, Foundation Installation
label | a750aae0-b47f-55d5-9156-f9425251b000 |  | note | (DoT) Pre-Installation Report
label | d9a8d54c-3273-5a9d-9ca3-cfb68a13b505 |  | note | - - - - - - - - -
label | 810bd9a8-0141-57f2-aaeb-37fb3edfb10d |  | note | Inspection / Test Method - Document review & Site Inspection
label | a7384abf-1970-5020-904b-77d8b1c13c58 |  | note | - - - - - - - - -
label | aca20eeb-bb71-54a2-a544-59d735a61ab5 |  | note | Record of conformity - Signed Pre-Installation Report
label | 0629dac4-7c41-5ce9-bfff-9acc668b65de |  | note | Completed Healey's ITP FO41 Pit, Conduit, Foundation Installation
label | 8f9c63ce-cd69-568a-8f96-24be53c68186 |  | note | Concrete test reports
label | dc980d8c-9d47-5484-ac53-18807e4433af |  | note | - - - - - - - - -
label | 29cf49f0-ded8-5a13-97dd-b969219c0e68 |  | note | HP*
label | 8f611838-d348-5529-a91e-8904da12e646 |  | note | - - - - - - - - -
label | 5d3c0bb3-3b60-5dee-b804-01e093f2ae5e |  | note | Responsibility - Site Engineer & Sub-contractor
label | f7d92cc8-0887-5e35-b46d-7bca45b8ecb0 |  | note | - - - - - - - - -
date | 39fce3db-fcdb-5823-8a1c-537bdee56bce |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Electrical Works
label | a4721b7a-b310-57b9-adf8-5a5066e06c89 |  | note | Frequency - Following Civil Works
label | 52563495-41cd-5001-acb6-06a0975d338d |  | note | - - - - - - - - -
label | ab850f18-4c28-5d1f-ac58-1ecc1fe352e1 |  | note | Acceptance Criteria - Works completed and subcontractor DoT Report completed in accordance with Section 730 of the Department of Transport Specification
label | 71f3b7f2-96f2-53af-8024-fd6cfb7c3a67 |  | note | 1) Traffic hardware inspected HP Sec 730 14 - DoT Pre Commissioning Report.
label | 836cf63d-f8c7-592b-a3ce-930027387270 |  | note | 2) Cabling Scheme agreed HP Sec 730.17 - DoT Pre Commissioning Report. - FO83 TSIR Electrical Checklist Inspection & Test Plan
label | 84d9263f-890a-5cc7-a878-5a975b8d2fb5 |  | note | 3) Electoral Tests & Flash Test performed HP Sec 730.17 -DoT Continuity, Insulation, Pre-Commissioning Reports, -HEALEYS - FO83 TSIR Electrical Checklist Inspection & Test Plan
label | db14cb76-ea8c-502f-836f-43ffc88e6890 |  | note | - - - - - - - - -
label | 2acb2817-c5dc-5b1c-8f42-f0717813a748 |  | note | Reference Documents - Healeys ITP FO83 TSIR Electrical Checklist Inspection & Test Plan
label | e3245b7d-7d13-53fc-af59-fb240589d340 |  | note | (DoT) Continuity Report
label | 0072a345-fa0b-595c-9191-58c6612be4cd |  | note | (DoT) Insulation Resistance Report
label | 58154bc9-13be-55a8-a14b-ba971d6142d1 |  | note | (DoT) Pre-commissioning Report
label | fc0baa16-6551-57ee-8e0d-ba0b8a6fea85 |  | note | - - - - - - - - -
label | ba1aa281-6f8d-5778-b41c-5000cb77a60f |  | note | Inspection / Test Method - Document review & Site Inspection
label | a0c7c434-596e-5921-bb3c-3aba3c2adf2c |  | note | - - - - - - - - -
label | 6610aa80-8858-519f-9ee2-f4cd0abcedd6 |  | note | Record of conformity - Signed & DoT Reports
label | e89741c1-67c4-5801-82d8-44c859678f92 |  | note | Completed Healy's ITP FO83 TSIR Electrical Checklist Inspection & Test Plan
label | 2b132198-473b-5529-9fc3-60dfc807a0b6 |  | note | Concrete test reports.
label | 25bd9519-aedb-57a9-a9bd-d5ca49ee6b05 |  | note | - - - - - - - - -
label | 2e5b6b25-84ed-55ad-b66f-6ec540bc5069 |  | note | HP*
label | 0569a5cc-dcab-57b4-b9ae-e16704fc2336 |  | note | - - - - - - - - -
label | 73cb8d3c-65c3-5fb4-b63f-2963d78bc5e4 |  | note | Responsibility - Site Engineer & Sub-contractor
label | b86fdf0f-cbaf-5724-86be-03e4b3fe19c5 |  | note | - - - - - - - - -
date | db0742ba-a9b0-5531-8ff0-bfd221565ab7 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Completion of Works
checkpoint-status |  |  | checkpoint | 3.1 - Completion of Traffic Signal Works
label | 830e6066-b6d2-5547-81f0-be1148c08cf1 |  | note | Frequency - Upon Completion of all Works
label | 8d0d0117-a2a9-5bf3-bb14-5ada64439614 |  | note | - - - - - - - - -
label | 5a675070-e35a-5cd0-a326-40a43a30aa9a |  | note | Acceptance Criteria - Works completed and subcontractor ITP completed in accordance with Section 730 of the Department of Transport Specification
label | adf0a7cc-f85c-5a34-9850-ff5dc3c78e79 |  | note | Reference Documents - (DoT) Commissioning Report
label | 8ea2181d-0a7a-5fad-9d02-77a3e8678d1f |  | note | (DoT) Power Consumption Report
label | 3887dedd-9d08-55f9-a1b1-7497ddd505fc |  | note | - - - - - - - - -
label | 492fc5b7-ed2c-54c0-942e-f52a6a07cf0c |  | note | Inspection / Test Method - Document review & Site Inspection
label | 11101cd1-b7e3-5c89-929e-85ecd414d030 |  | note | - - - - - - - - -
label | 4f9b04d7-d892-51fb-8a26-259591c95b6d |  | note | Record of conformity - Signed ITP
label | 42589ad6-8912-5c2e-a6f5-860e6815cb54 |  | note | - - - - - - - - -
label | 609e7c51-e931-592e-813b-e46add334dfd |  | note | HP*
label | 1d53cec4-0fea-5824-a6a7-a74ab22d5968 |  | note | - - - - - - - - -
label | 346063b8-9524-5b62-8768-6b68d6f35dfc |  | note | Responsibility - Project Engineer / Site Engineer
label | 1439d4ac-ea4f-583e-a838-f0a88ef8510e |  | note | - - - - - - - - -
date | 3f24fb28-6a1f-550a-8549-74214aff6325 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | 0ca5bc6c-b6d1-50de-b025-03ae793dca35 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | d0efaa67-07eb-5150-a510-524ca9676175 |  | textbox | Print Name:
text | 784b66fc-75a1-5512-b832-1bab0c0b1a68 |  | textbox | Position:
date | 60039129-fd09-515f-965e-7e318cd4ecef |  | date | Date:
date | 47b84fb4-efa1-5e9e-9463-113cf84eefb4 |  | date | Work Completed On
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification.
select | 036fef85-7d79-5f4e-84ca-fb26cb545159 |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | 084109fc-fc7d-59e9-871e-cf0e3d822db1 |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | 42b3b83c-ae66-5401-8197-d56e197eae67 |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | 18b7eb46-e3c2-5546-b752-49598320a3c7 |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | 53d64ae7-51f3-5b87-bd30-bf58a13beacf |  | textbox | Other:
select | 6d034cc0-d95d-5e2b-a973-0826e7015d08 |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | 3e951120-1d2e-5f62-a849-588ac2df8ad1 |  | date | Lot Closed On
text | 501a19cc-ec3e-5ad6-b0a5-45bfb4e918dd |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-026-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0026 - Guardrail Installation | 566c7382-95d1-484c-942e-d6c6de29f556
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | 64b656f6-ecb6-5dde-9fe3-59389776f3fa |  | date | Lot Created On
date | 2e66bb3f-b6a3-57fc-aea8-c842628df628 |  | date | Lot Opened On
date | 84477e93-a79a-5892-82ef-7b06699c1c2b |  | date | Work Commenced On
select | 5d7bef7e-9cff-55ba-870f-42347eb85eb0 |  | dropdown | Lot Type | CIL-Civil Lot, DRL- Drainage Lot, EAL- Earthworks Lot, ELL- Electrical Lot, UTL- Utility Lot, STL- Structural Lot
text | a9705c62-87ef-5ae0-a704-03c29acc7296 |  | textbox | From and To Chainage
select | 58a41c0b-8be4-5672-a472-fe51f47aaed6 |  | dropdown | Construction Element | SAFE - Safety Barrier
select | 388485aa-087f-5d66-8bd5-f9d898869b0b |  | dropdown | Activity | GUAR - Guardrail
select | 20a405bb-1dac-5296-bada-2f4e5f489d88 |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | 13dc53f3-5624-5713-99ea-de4d7e071e1b |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | 596a6451-c058-5590-b0c3-b20bcaeec699 |  | textbox | Engineer Responsible
text | 32421358-3600-556a-8338-0aa00f0dff41 |  | textbox | comments
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Work pack briefing
label | bcd383ec-725d-5fef-89f9-7b233a21c206 |  | note | Frequency: Prior to Commencing
label | d14e8d82-069f-5ca6-8d61-16e966fcc9e6 |  | note | - - - - - - - - -
label | 362b56d6-4173-516d-83d5-9eec47b67a70 |  | note | Acceptance Criteria: All personnel on site have been briefed on the relevant work park relating to scope of works.
label | 2962ad50-9403-530e-bb59-f12688a4ad52 |  | note | - - - - - - - - -
label | 4e94098c-82f3-503d-9983-566b87a58f75 |  | note | Reference Documents: WP
label | caf95550-e700-5505-9738-78ad3a7a5bf6 |  | note | - - - - - - - - -
label | fab235f1-184a-5754-8189-d7af108291fa |  | note | Inspection / Test Method: Document Review
label | 3ace1cf7-5a93-5f23-b813-f9dfd6cc73bd |  | note | - - - - - - - - -
label | 330a3c85-8f21-5e45-aa94-b421b8f82d94 |  | note | Record of conformity: Work pack signed.
label | 66dac89c-6148-5267-b99b-10ac7724e846 |  | note | - - - - - - - - -
label | a1f5034c-a755-5cbd-8b25-a20a26391c2c |  | note | HP*
label | debc3640-5943-556a-9abb-49dcbc4a386b |  | note | - - - - - - - - -
label | 7bce82db-4559-513a-b7ac-9657ddd46c5b |  | note | Responsibility: Site Engineer / Site Foreman
checkpoint-status |  |  | checkpoint | 1.2 - Check that current revision drawings are being used
label | 82612fc3-dd71-594e-bd03-4c5029315159 |  | note | Frequency: Prior to Commencing
label | 669a453c-e86e-5c46-b56c-3704c4cbe19e |  | note | - - - - - - - - -
label | 50abcb5d-5914-50ca-bf8e-8504887c149c |  | note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
label | c58d0fcf-90c6-571e-a203-5fde322bfa21 |  | note | - - - - - - - - -
label | 1a603d07-a025-5c79-b925-67bd4ebb614d |  | note | Reference Documents: Project Drawings / Drawing Register
label | 5204052f-6298-5f36-adc6-ef0796b2128c |  | note | - - - - - - - - -
label | c816e42f-898c-5535-b9a3-61087b086941 |  | note | Inspection / Test Method: Document review
label | 8c505722-17c9-5ad6-b3c0-be7659d907d2 |  | note | - - - - - - - - -
label | 181724e4-8e62-5641-a924-a06b691428df |  | note | Record of conformity: Latest Revision Drawings
label | dc8a1dfb-d880-5164-aba4-f73b59c04668 |  | note | - - - - - - - - -
label | 32e9b538-f96a-558e-b57c-cc1794e052ce |  | note | HP*
label | ddda46f9-e275-5f4f-a263-750d5b69d7d7 |  | note | - - - - - - - - -
label | 41951338-6314-54f1-a28e-bdf66635acd6 |  | note | Responsibility: Site Engineer / Site Foreman
checkpoint-group |  |  | section | 2 - Procurement
checkpoint-status |  |  | checkpoint | 2.1 - Steel Test Certificates
label | 4a2d8aa4-16aa-59c8-80c8-911a3c42bec6 |  | note | Frequency: Min 14 days prior to commencing
label | 21c934d0-d6e3-5b1b-a9fe-f6fd72101cdf |  | note | - - - - - - - - -
label | e872aea6-5d24-559f-b0aa-9f09bfeb8b4b |  | note | Acceptance Criteria: Only Safety barrier products listed in VicRoads Road Design Note 06-04 shall be used. All test certificates related to the supply of steel for the works shall be submitted at least 14 days prior commencement of installation.
label | fd06f89b-b0fc-5307-91d3-cc28eb0fe72c |  | note | - - - - - - - - -
label | 92921daf-9efb-5ab9-a75b-4438bcadf7b4 |  | note | Reference Documents: VicRoads Spec. Cl.708.05 (b)
label | 1225c2b2-f329-5894-9838-b3f3ec402dc5 |  | note | - - - - - - - - -
label | 768872bf-3446-55ea-a954-4da161f2c9b0 |  | note | Inspection / Test Method: Document review
label | 4cd478a8-faf2-5609-bef3-8ed6f7a94ded |  | note | - - - - - - - - -
label | 6d0c3728-d452-5c97-8a0e-9288a32bba3c |  | note | Record of conformity: Data Sheets Material Test Certificates
label | c735ba5a-0b0b-58f1-b854-9408295eee2e |  | note | - - - - - - - - -
label | 41e4ed2a-2b15-50dd-8e1b-baf72113e7fa |  | note | HP
label | 562ea87c-6514-50be-a75d-f46723dee268 |  | note | - - - - - - - - -
label | d0eba36e-e1fc-5440-8cc2-19b9ad445d4f |  | note | Responsibility: Project Engineer/ Superintendent
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.2 - Steel Material Properties & Protection
label | 96996346-101e-505d-8907-8b2fb7041b56 |  | note | Frequency: Prior to Commencing
label | dcdd49d1-759f-5c25-a41c-8fc47a2e9936 |  | note | - - - - - - - - -
label | 72fa97ba-6cda-5fc6-9efa-553d15399f5d |  | note | Acceptance Criteria: Guard fence steel component shall meet the strength, dimensional tolerances and surface protection as specified in VicRoads Section Cl.708.5.
label | cb7e99c0-3b60-5480-8503-d259bff37a7f |  | note | - - - - - - - - -
label | 2a5b953d-560a-5432-aa55-89e4243aa607 |  | note | Reference Documents: VicRoads Spec. Cl.708.05 (c), (d)
label | 75bd2a20-5ab1-5543-bab7-b937a06dd0b7 |  | note | - - - - - - - - -
label | d26eb886-3c44-51eb-b758-740071b82d05 |  | note | Inspection / Test Method: Document review
label | 31f36cab-84ed-594b-a18d-fa6ec535a228 |  | note | - - - - - - - - -
label | a60eccbe-77fc-53ae-a6cf-93919d542892 |  | note | Record of conformity: Data Sheets, Visual Inspection
label | de38f3f4-8a2d-51de-89ad-75a163fb48ad |  | note | - - - - - - - - -
label | cbc2da1b-2a91-5a36-b215-5ab99ee24b43 |  | note | IP
label | 2d769534-9193-56d5-a62b-100a58e940a0 |  | note | - - - - - - - - -
label | 4305beb9-acc2-5def-9b95-c57a3eb104eb |  | note | Responsibility: Site Engineer
text | 651a3826-a5a2-5be4-826c-7c70a92cdec9 |  | textbox | Teambinder Approval:
checkpoint-status |  |  | checkpoint | 2.3 - Identification of guard fence components
label | 71c1d135-722c-59d1-9627-bc80c41544b2 |  | note | Frequency: Prior to Commencing
label | 63e221f2-a9d9-57b3-a29d-6e26c2a33815 |  | note | - - - - - - - - -
label | 9f53cf93-fc32-57e8-ac5e-07bc315d65d1 |  | note | Acceptance Criteria: w-beam sections, both ends of posts and all plastic end treatments to be permanently marked in text not more than 20mm high with: name of manufacturer, batch number or date of manufacture and strength grade and base metal thickness of steel w-beams
label | 9b7d45a8-850c-51bf-8a1f-52b3e836a105 |  | note | - - - - - - - - -
label | 5fa5f72a-d2e8-575b-87e2-ffe50fa079ff |  | note | Reference Documents: VicRoads Spec. Cl.708.05(a)
label | f3a74016-4124-5e4b-b2c3-1778f6045a1d |  | note | - - - - - - - - -
label | 0436340a-f78b-55d5-a265-dd88fe9dcb83 |  | note | Inspection / Test Method: Inspection
label | bda5adb5-12c9-5eba-b76b-8cf2b88b54eb |  | note | - - - - - - - - -
label | 9a1c2be4-c7ab-594d-b6c3-4c2de73fe443 |  | note | Record of conformity: Completed Receival & Inspection Checklist (CRU-FH-CL-0001)
label | 32ace884-77b6-5c64-95b2-15e9fc5e53fa |  | note | - - - - - - - - -
label | de4fe44a-a65a-5395-ba66-25aadf3e8cdf |  | note | IP
label | 2117c075-8109-5d1f-b162-f81cbc64fd9b |  | note | - - - - - - - - -
label | 7d2ba96e-a3d6-5aee-8367-ffe48af9f8d3 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 2.4 - W-Beam Barrier with non standard requirements or other special measures
label | 67549a3c-74c6-5104-9cf9-6e9b47bafe77 |  | note | Frequency: Prior to Installation
label | a488cb08-1fbe-5b91-a958-dd1b6f63e01f |  | note | - - - - - - - - -
label | db49c9a1-f781-54e3-b5b2-664b7bbe79d5 |  | note | Acceptance Criteria: Prior to the installation of any w-beam barrier system where non standard post lengths are required or other special measures (e.g. shallow concrete foundations) are proposed to be used, the Contractor shall provide details of the measures proposed and evidence that the effectiveness of the barrier system will be maintained, for consideration by the Superintendent. Where shallow foundations that require a concrete ground beam are proposed to be constructed, the design shall be proof engineered by a VicRoads pre-qualified consultant.
label | be2a4e5c-8cd9-56e4-bfe1-9cd7d022c81f |  | note | - - - - - - - - -
label | 590c82d6-7caf-52eb-b3ea-c049c6844565 |  | note | Reference Documents: VicRoads Spec. Cl.708.08(a)
label | 5d4762d2-66b4-59a6-b17f-ff69893feddd |  | note | - - - - - - - - -
label | 3f98b65b-6499-55d5-8bf8-496aaae93ae2 |  | note | Inspection / Test Method: Document Review
label | 4a8b8f38-0176-5591-b33e-309e3624234e |  | note | - - - - - - - - -
label | 268fcb1f-a398-50ec-ad12-44262441c9f0 |  | note | Record of conformity: This signed ITP
label | 10eaf03c-f744-5566-bd9e-6658deb08485 |  | note | - - - - - - - - -
label | e8e17d5a-3155-5f88-98cc-a5030530cf43 |  | note | HP
label | cc5e67eb-0bfc-54cc-bf9d-8ce89f69dbe3 |  | note | - - - - - - - - -
label | 31a5c082-48d9-57d6-b347-ba8b4679061b |  | note | Responsibility: Project Engineer/ Superintendent
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.5 - Concrete mix design (As Applicable)
label | c78cfd0d-80d3-5a44-b597-fe0246d998a7 |  | note | Frequency: Prior to Commencing
label | 525d30e1-cd32-57fd-ac3f-1427073a424e |  | note | - - - - - - - - -
label | d164f7a6-37f1-5ac3-a579-7953f944a591 |  | note | Acceptance Criteria: Concrete to comply with the requirements of AS 1379 and VicRoads Section 703, for either: (i) Portland cement-based concrete, N20 strength grade, or (ii) Geopolymer binder-based concrete, 20 MPa strength grade.
label | bb33bff0-eab3-54d5-8e7b-521867ff22e0 |  | note | - - - - - - - - -
label | b8f618bf-34c5-5955-9b71-2b59d1848b1c |  | note | Reference Documents: VicRoads Spec. Cl.703 Cl.708.05(g) AS1379
label | ca2b26bd-cb05-5c09-aaee-34cee866b5a3 |  | note | - - - - - - - - -
label | dac7a379-ce76-5a7c-9e0c-cc7d837d6941 |  | note | Inspection / Test Method: Document Review
label | 8a547b3a-a798-57dd-b03a-978288558c90 |  | note | - - - - - - - - -
label | bc3c9ade-8cc3-5d57-98ca-dd0dc767d6fa |  | note | Record of conformity: Mix design approval
label | c1b55036-dcfa-541f-9242-b1ae548255f1 |  | note | - - - - - - - - -
label | 0387e5dd-d7e9-5250-8852-2c8ab7fbaf57 |  | note | IP
label | 3c46cf24-43b8-540b-9756-4f0b2e4bc8c9 |  | note | - - - - - - - - -
label | 9c2f6a29-d670-5549-b6d2-0f3bf23c3a5b |  | note | Responsibility: Site Engineer
text | 7a719f8a-bd2d-5f95-83a1-09777c0a763a |  | textbox | Teambinder Approval:
checkpoint-group |  |  | section | 3 - Guard Fence Installation
checkpoint-status |  |  | checkpoint | 3.1 - Approval of location and length
label | 4f2a213f-e552-5974-ab36-e11438eff4e6 |  | note | Frequency: Prior to Installation
label | cbad5501-900e-53c0-8b03-145b0b1c51b3 |  | note | - - - - - - - - -
label | 999715b9-ae82-5dc6-8db5-899a95c357ea |  | note | Acceptance Criteria: The required location and length of all guard fence shall be confirmed with the Superintendent.
label | a04bfa85-bc71-5749-91ef-72349797b406 |  | note | - - - - - - - - -
label | 6b48bb95-8650-51ab-a5fb-febea6a3eeab |  | note | Reference Documents: VicRoads Spec. Cl.708.08
label | eb359620-d75f-5f58-8a89-f36b6cffebb2 |  | note | - - - - - - - - -
label | eb534451-6070-5e34-bfd4-4e5749d3c64e |  | note | Inspection / Test Method: Document Review
label | 4744fc3a-31dc-534a-bff7-2f142139f894 |  | note | - - - - - - - - -
label | 48942932-059e-5beb-a978-fb9b5eac928a |  | note | Record of conformity: This signed ITP
label | 91f921b2-f702-5614-b0e2-531e303a9082 |  | note | - - - - - - - - -
label | b4027443-5f8f-5c1a-a193-dbd943c6cd86 |  | note | HP
label | 3a095a9f-efe5-54f6-94c4-48e2e81899b0 |  | note | - - - - - - - - -
label | d1822bf8-3913-51eb-b837-b4cb747df18a |  | note | Responsibility: Project Engineer/ Superintendent
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3.2 - Survey set-out
label | 3ef3593d-9c50-5c8e-8617-043b077c20e6 |  | note | Frequency: Prior to Commencing Excavation
label | 52e57c7d-ff9e-589a-bbfb-595e7948e7ac |  | note | - - - - - - - - -
label | 5ec8f687-1714-563c-a32c-4cdf9650c313 |  | note | Acceptance Criteria: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used
label | 241426fc-bb4e-51e5-ae22-d675a40320b9 |  | note | - - - - - - - - -
label | 9490da2f-2acb-51ea-8a06-731f8cbf759c |  | note | Reference Documents: Project Spec. Cl.1190.06 Latest IFC Drawings
label | 80a2d7ba-cc29-5c84-9055-ae5ee8508900 |  | note | - - - - - - - - -
label | 83ddb3b2-7070-55dd-8308-5385524d08f8 |  | note | Inspection / Test Method: Testing
label | e221350a-d764-5481-b464-fff32a36b43a |  | note | - - - - - - - - -
label | b1e3045f-547e-5777-a87a-095e542e3ef5 |  | note | Record of conformity: Survey records & pegs on the ground
label | 59796077-d04d-5b15-9068-95fdfbf40c5d |  | note | - - - - - - - - -
label | 18468481-cd5a-5643-836d-244b8a10b36c |  | note | SCP
label | 5d3d0422-06a5-5599-b9d1-0b85b914f60c |  | note | - - - - - - - - -
label | 80c37412-3da5-559f-8637-a32fdb6fd903 |  | note | Responsibility: Site Engineer & Surveyor
checkpoint-status |  |  | checkpoint | 3.3 - Post Installation
label | 52de93e5-205b-58d9-bd1c-2e4ec9f6ce2e |  | note | Frequency: During construction.
label | 6a2a0dee-1da9-5f8c-ac58-6debcae7687f |  | note | - - - - - - - - -
label | df535758-2a45-5730-95dc-0670a5937334 |  | note | Acceptance Criteria: Posts shall be installed to the depth, line and spacing shown on the drawings. Posts shall be orientated to the direction of traffic as shown on the drawings and must be installed by driving, provided there is no distortion or damage which may reduce effectiveness. If posts cannot be driven, then posts must be installed in holes with the base compacted to the same density of the surrounding soil. Backfill of the post hole shall be with clean, well-graded, non cementitious subbase or base course granular material and compacted to achieve the same density of the surrounding soil
label | 6f5d6032-5f3e-5eb9-80dd-0148c2ab968c |  | note | - - - - - - - - -
label | 4f469256-ca48-57c3-ba83-44e52fdffeb2 |  | note | Reference Documents: IFC Drawings VicRoads Spec. Cl.708.08(a)
label | d727ec8a-bdcd-5011-9968-f8c2d374e561 |  | note | - - - - - - - - -
label | d84b7243-0b06-552f-9cd0-e1f4ed40b7bc |  | note | Inspection / Test Method: Visual Inspection
label | 23e0501d-47b5-5ff6-8118-c62797b316a5 |  | note | - - - - - - - - -
label | 15f7b76d-9b69-5482-9dee-1144e595f969 |  | note | Record of conformity: This signed ITP
label | aa519f30-2dd0-5a43-a71b-f87caa9508e9 |  | note | - - - - - - - - -
label | 0ab05d75-1bf4-5ee8-a880-ad3678a45c43 |  | note | IP
label | 2c691c25-e513-5204-86ac-ee5165ba8cbd |  | note | - - - - - - - - -
label | 771dda74-630f-5fdc-a985-84e3d441d13e |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3.4 - W-Beams
label | 4a35c716-4ba7-5ee0-b638-dda5da621da5 |  | note | Frequency: During construction.
label | 227c21f4-430e-5810-a472-da1f805c8a39 |  | note | - - - - - - - - -
label | 205aa533-8515-55e5-abe5-91ca40400b39 |  | note | Acceptance Criteria: The w-beam sections shall be lapped so that the exposed ends face away from the near side approaching traffic. The edges of the w-beams section or backing plate adjacent to posts shall be fixed in contact with the post or post blocks and all bolts shall be fully tightened.
label | 30d36714-37e8-5a06-abe7-21d1caa3c31e |  | note | - - - - - - - - -
label | 08369238-3849-5442-a661-8ec71d24aa4a |  | note | Reference Documents: VicRoads Spec Cl.708.08(b)
label | 823b251d-6f72-5a4c-bcae-995931001e6b |  | note | - - - - - - - - -
label | 96b94772-e9ec-58ac-b32c-43462a787bef |  | note | Inspection / Test Method: Visual Inspection
label | c8c69bd8-c12e-5111-8e45-752b1c335a73 |  | note | - - - - - - - - -
label | b0d3bf7c-0e59-564e-8ecc-8176fd6eb050 |  | note | Record of conformity: This signed ITP
label | 5197473e-785f-5818-8e5c-0926c65ac515 |  | note | - - - - - - - - -
label | 702b59f7-bbbf-5f61-acb3-6b85fe061d83 |  | note | IP
label | 7e9a7c08-e9a5-524f-9db7-21e1cbdefd34 |  | note | - - - - - - - - -
label | 61f03dba-283b-5884-be9f-d7d8ab46d96e |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3.5 - Guard Fence Tolerances
label | 4eeb1e79-f65c-5b35-a781-58fa71de0d78 |  | note | Frequency: During construction.
label | 8de63bc9-1480-50b0-b45d-f530f4367eec |  | note | - - - - - - - - -
label | 3910c13e-254c-5edb-994a-cffd1edcdd5d |  | note | Acceptance Criteria: Ensure line and level are within tolerance: true plan position of posts ±20mm, line of w-beams from vertical profile ±10mm, w-beams from horizontal alignment ±20mm, posts from vertical ±15mm, orientation of block and /or post to w-beam +0, -15mm, dimension of holes +50, -0mm, top of bolt head relative to w-beam +5, -0mm, top of rail shall be within 25mm of level and 50mm of line. Variations from specified line and level shall not occur at a rate exceeding 15 mm in any 5 m length.
label | 53744d02-9bb6-52d1-9e2c-e82293c3ce67 |  | note | - - - - - - - - -
label | 5400553b-1595-53a1-aed1-740b2ac5c29f |  | note | Reference Documents: IFC Drawings VicRoads Spec. Cl.708.08(d)
label | e55aad52-aa7b-5b3c-9c7a-6675f1ea5290 |  | note | - - - - - - - - -
label | a47b96ce-4c7e-50bb-8074-09347be49115 |  | note | Inspection / Test Method: Verify
label | 92920c52-864c-5429-bcdc-45d505d175a2 |  | note | - - - - - - - - -
label | 228a1db4-045e-55f6-9224-c7bafc43e469 |  | note | Record of conformity: Survey Records
label | 367b020a-dec9-5fee-9882-4fdf3ae9da8e |  | note | - - - - - - - - -
label | 1c3cd551-578b-59ee-9ad6-4abc34b7ed96 |  | note | SCP
label | 93374db2-7ff7-5578-a930-8ec095c3a1b9 |  | note | - - - - - - - - -
label | e478a97b-51b4-582b-9628-f695e047f7cb |  | note | Responsibility: Site Engineer
checkpoint-group |  |  | section | 4 - Concrete Maintenance Strip
checkpoint-status |  |  | checkpoint | 4.1 - Dimensions and set-out
label | d36bdc20-9694-5d42-a59a-a3ec12dc6c17 |  | note | Frequency: After installation of guardrail
label | 08f3aaf8-d5aa-54d6-86c5-2ae37199b2e4 |  | note | - - - - - - - - -
label | 47ccafcf-f63c-5bcb-a8dd-e466c1858d86 |  | note | Acceptance Criteria: The concrete maintenance strip shall be placed parallel to the barrier, such that it extends a minimum of 300 mm clear of the rear of the post and 300 mm clear from the face of w beam. It shall be constructed with minimum 2% crossfall away from the road and shall be flush with the adjacent ground level so the finished level does not impede road runoff.
label | 4d9df998-ba07-57ef-9ca2-d17b0b96d3a9 |  | note | - - - - - - - - -
label | 55518ed9-6396-56c5-b0df-991804ae4d5d |  | note | Reference Documents: VicRoads Spec Cl.708.12
label | 4f72dc8b-f5bd-544d-9963-9c00db386912 |  | note | - - - - - - - - -
label | 37ab02e9-924f-5098-b635-ea8d5a3f26d1 |  | note | Inspection / Test Method: Visual Inspection
label | 11ef753c-484d-5dde-a793-ed544033f2de |  | note | - - - - - - - - -
label | 4d706467-63e9-5e63-9602-870806ea6fde |  | note | Record of conformity: This signed ITP
label | d5252230-1046-5f1c-bd7e-a04f27f2ff18 |  | note | - - - - - - - - -
label | efe73942-1fa1-5736-abe3-01a24aa03e89 |  | note | IP
label | 35ef8e2e-20c4-5bac-a314-88ec46d7ef3e |  | note | - - - - - - - - -
label | 273e1bfc-0cc4-5dc6-b727-5085fd616d26 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 4.2 - Bedding and concrete
label | 019f5866-f0d2-5ace-b402-99af56465ec8 |  | note | Frequency: After installation of guardrail
label | 6d2a049e-5dc8-5644-90f1-41ad27d197d5 |  | note | - - - - - - - - -
label | c6bda2dd-73f1-5980-a335-b71062e25462 |  | note | Acceptance Criteria: The concrete maintenance strip shall consist of 75 mm depth of N20 strength grade portland cement-based concrete or 20 MPa geopolymer binder-based concrete conforming to the requirements of clause 708.05(g), on 75 mm of compacted Class 3 crushed rock.
label | 822ada61-8813-5f9f-8823-790becec2e08 |  | note | - - - - - - - - -
label | 03a3998a-a7d6-5e0a-8c26-e9c537a1c97f |  | note | Reference Documents: VicRoads Spec Cl.708.12
label | e30c7d48-36eb-52ce-8e40-fe338d28eb42 |  | note | - - - - - - - - -
label | f6735d96-8e25-593c-9669-f3341fd9a4ed |  | note | Inspection / Test Method: Visual Inspection
label | 4850677d-8234-5662-b1ee-37dcccc65c99 |  | note | - - - - - - - - -
label | bb3582cc-2f5b-54bf-aa84-e93d3d751ae9 |  | note | Record of conformity: This signed ITP
label | 45b2a7e6-a84b-5dba-9953-f558b9888d22 |  | note | - - - - - - - - -
label | 8a4c733f-600b-5bcb-9eef-6483fd752219 |  | note | IP
label | 0fbf97ef-d048-55a0-8a65-bcebfd6ba3a9 |  | note | - - - - - - - - -
label | ef6bd466-7118-534c-8e28-2808059f2ba7 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 4.3 - Separation from Kerb
label | 58185e1d-99c5-5ed1-9917-06284b906cc0 |  | note | Frequency: After installation of guardrail
label | 99e19b8f-8be2-5959-94ee-750f87a1d2cf |  | note | - - - - - - - - -
label | 5285bbb0-d13d-54fa-96a2-aa09eead30d5 |  | note | Acceptance Criteria: Where the concrete maintenance strip is adjacent to kerb or pavement, separation from the kerb or pavement by the use of a cork expansion joint (or approved alternative) shall be produced. Full depth expansion joints shall be provided perpendicular to the line of the steel beam guard fence 200 mm each side of every post.
label | 7590c166-00dc-5a22-b2c9-fda3330df3f3 |  | note | - - - - - - - - -
label | fa8a8c7f-8750-5235-8c1d-09d8c1191e2b |  | note | Reference Documents: VicRoads Spec Cl.708.12
label | 49b746fe-fb9b-54de-ac51-308d2ac824d5 |  | note | - - - - - - - - -
label | bc3300ed-7cbc-5363-a731-b77ba4189718 |  | note | Inspection / Test Method: Visual Inspection
label | f75b8a0f-9a9e-593e-9d93-83140d6891f9 |  | note | - - - - - - - - -
label | 19f527c6-98b9-537a-b341-bef2180b8691 |  | note | Record of conformity: This signed ITP
label | 5b3b3d9c-ee27-5aa7-b9e4-218c5d70f946 |  | note | - - - - - - - - -
label | 1f87d8c5-9913-50bc-9ccf-e975ea4cf4a1 |  | note | IP
label | cdaacf61-a41c-585b-8b41-7fa96350fef1 |  | note | - - - - - - - - -
label | 7efc3d92-af90-5c0a-9d6e-5c9f1ee7ee91 |  | note | Responsibility: Site Engineer
checkpoint-group |  |  | section | 5 - Audit
checkpoint-status |  |  | checkpoint | 5.1 - Compliance Audit of Barrier System Installation
label | 5db1259c-0bdb-59c2-af2e-428fb512c72a |  | note | Frequency: Prior the issue of the Certificate of Practical Completion
label | 1732d062-817b-54c9-84ee-4e039ec82610 |  | note | - - - - - - - - -
label | 3fdfbe3d-a1eb-5644-898d-8e96b65c0b72 |  | note | Acceptance Criteria: A safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract shall be undertaken and a report prepared by the Australian Licensed Supplier of the safety barrier system. A Certificate of Compliance shall be provided certifying the product and for end treatment installed. A signed copy of the manufacturer’s Installation Checklist / Inspection and Test Plan as per the manufacturer’s Product and Installation Manual shall be completed and submitted to the Superintendent..
label | 91288a67-1a0b-5f22-962c-befb152a65a5 |  | note | - - - - - - - - -
label | ce454fde-3f03-5a00-ad4d-7c35296d1f67 |  | note | Reference Documents: VicRoads Spec. Cl.708.10 Project Specific Specification PS3090.07(f)
label | 484caffe-9fc2-5a6a-b4d3-3db72dbcfb1f |  | note | - - - - - - - - -
label | 539accc9-18b2-5f6e-ab3e-b9feb84f5021 |  | note | Inspection / Test Method: Safety Audit
label | 2faf58c7-c7d3-58cd-8bdd-534d03227ace |  | note | - - - - - - - - -
label | 3b625ee6-2e86-556e-843e-b650f3579eb0 |  | note | Record of conformity: Certificate of Compliance for each treatment installed Product and Installation Manual
label | d6f0005a-73e6-560e-9f46-8216591c189b |  | note | - - - - - - - - -
label | 37ef39e0-e48e-5b85-a403-c65ae7f82c01 |  | note | HP
label | 5e3eaa22-741d-5e1e-a881-5baa8a82126c |  | note | - - - - - - - - -
label | 5a4506ae-272c-5e21-a072-2007a0a64d1e |  | note | Responsibility: Project Engineer/ Superintendent
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | 6 - Completion
checkpoint-status |  |  | checkpoint | 6.1 - Delineators
label | f3ee5dc2-696f-57d2-bbe4-388a3bb9c431 |  | note | Frequency: Once installation of assets completed.
label | e4af4e62-a674-5e8e-bd53-f2b118acf886 |  | note | - - - - - - - - -
label | da5f94d8-6d2c-5781-b1c6-a51be26ea855 |  | note | Acceptance Criteria: Appropriately coloured delineators fastened to top of w-beam, comprising flexible plastic mounting brackets fitted with 100 cm2 of Class 1A retro-reflective material, as defined in AS/NZS 1906.2 The delineators shall be arranged so that vehicles approaching from either direction at night will only see: Red delineators on the left side of one-way and two-way roadways White delineators on the right side of two-way roadways Yellow delineators on the right side of one- way roadways Delineators not to be installed when the guard fence offset if greater than 4m from the traffic lane.
label | 86f22dde-f3a9-50fa-aeee-15d99e132674 |  | note | - - - - - - - - -
label | e05f873f-1be1-54f6-a7db-50101bf4718d |  | note | Reference Documents: VicRoads Spec. Cl.708.11
label | 72b0c9bc-8f2d-557b-9f40-344b00d8ba4f |  | note | - - - - - - - - -
label | 52a21a06-4c92-5e26-8d03-2df7fcc744bc |  | note | Inspection / Test Method: Visual Inspection
label | e1022277-e745-528c-9b33-53fe3ee47544 |  | note | - - - - - - - - -
label | 167b6db4-2567-5daf-aaff-c21ca94de9f2 |  | note | Record of conformity: Site Photos
label | 6497d9c7-55e6-58e1-9a17-b7a6e7f6f6be |  | note | - - - - - - - - -
label | 6dc9d8be-e0b2-5506-8911-af8fbdae01fc |  | note | IP
label | 61db144c-3a25-585f-95b3-bcd897bee5d2 |  | note | - - - - - - - - -
label | d8d1e000-5c26-5368-aa3f-0df90a36d609 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 6.2 - Grassing of disturbed areas
label | 927a544c-889d-5fa8-9a66-487531c72de0 |  | note | Frequency: Once installation of assets completed
label | 4881e0af-4ea1-572e-a3e7-ae1dd622ebf9 |  | note | - - - - - - - - -
label | 752bfbd6-7fe7-5bb2-b02e-3b66a6cd2d71 |  | note | Acceptance Criteria: All disturbed areas shall be topsoiled and grassed, all areas to be cultivated to a minimum 50mm depth, and moistened prior to the application of grass seed and fertiliser. A joint inspection of all grassed areas shall be carried out between the contractor and superintendent three months after sowing has taken place.
label | 8cc5a1ba-2d02-5841-ace1-9d51b8a9e0d4 |  | note | - - - - - - - - -
label | 9e92b691-ae78-5a89-9414-174f60304c04 |  | note | Reference Documents: VicRoads Spec. Cl.708.20
label | 6d819dd5-4dc1-52a1-a3d4-c0b25a29d675 |  | note | - - - - - - - - -
label | de9e32b1-24be-5535-9175-53cce995f06c |  | note | Inspection / Test Method: Visual Inspection
label | c4814206-7e16-5412-bf31-3eef02624105 |  | note | - - - - - - - - -
label | 9404ccf5-1d7a-5cce-a034-0dce14b930e1 |  | note | Record of conformity: Site Photos
label | c8370e69-b998-5c8e-97e0-13daae585b16 |  | note | - - - - - - - - -
label | a38a2e28-4152-5803-a138-ae98c01add9b |  | note | HP
label | d200b612-b630-5aa7-a0f1-1163f9499c14 |  | note | - - - - - - - - -
label | 6035e71f-dd60-569c-8765-4120856efdde |  | note | Responsibility: Site Engineer / Superintendent
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 6.3 - Quality Assurance
label | 95060dd8-c701-5bb1-9c06-83ba105ed90e |  | note | Frequency: Completion of works
label | 75ce7d51-de3e-52e1-bb6e-3646ecf05a21 |  | note | - - - - - - - - -
label | 07f1b1c6-ef5f-5535-829b-7ffb2678f2a3 |  | note | Acceptance Criteria: Submit all quality assurance documents to the superintendent including the following items: (i) As built information including changes to location of traffic barriers on site and details of loads used for assessment and design of any collision protection. (ii) Time and date of when traffic barriers were installed (iii) Certificate of compliance signed by the contractors representative and the licensed supplier, certifying that the proprietary product systems have been installed in accordance with the manufacturers installation manual and this specification.
label | 546cc984-ae77-5148-9f84-35ec8218efff |  | note | - - - - - - - - -
label | 8ced54b2-c89b-5275-947d-445297fa1956 |  | note | Reference Documents: IFC Drawings Project Specific Specification PS3090.04
label | 4f62e982-1b94-523e-8e58-2679d51eab2d |  | note | - - - - - - - - -
label | 6a823d3d-13c6-5e6b-8223-ceed7f3aa9f1 |  | note | Inspection / Test Method: Document review
label | 92f0e154-9922-531b-981c-ca1d0d444f3a |  | note | - - - - - - - - -
label | 9c9528e0-0a60-5fe8-9ce2-986e5aa25df6 |  | note | Record of conformity: As built Records and Certificate of compliance
label | 29c80bc2-51ca-5c8b-a444-d6e2b259946f |  | note | - - - - - - - - -
label | f2e2c43e-bffb-5b70-b6eb-b86bd7fb160e |  | note | SCP
label | edffd43e-c510-5784-827d-2c463422af11 |  | note | - - - - - - - - -
label | 9d32f74a-d4b3-58f0-afd9-99dee94e1a1f |  | note | Responsibility: Project Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
label | 27f450db-b85b-5c5e-92a9-ca770eda9a91 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 9b6c5f93-5d17-5f25-b774-a0ec8306c26f |  | textbox | Print Name:
text | 76bc44c2-d47d-5f3c-8f42-b77b91508641 |  | textbox | Position:
date | 319d8c50-a87a-5783-b6b5-53b31a5f2530 |  | date | Date:
date | 31e0bbbb-36d4-56fe-b231-9afe2a83a655 |  | date | Work Completed On
checkpoint-status |  |  | checkpoint | Lot Verification.
select | a9666584-c2cf-5757-b03f-329c02d9035c |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | f71ae1ca-3d89-5899-8608-fb9003f3df19 |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | 987a8550-dd1e-59f4-89e1-ed62fa2773e5 |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | 3bb467b8-8bfd-5a8d-ad6d-149e83b0a998 |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | 1499f20d-c01b-5a2d-887b-093eabd2bc11 |  | textbox | Other:
select | 9f96db78-c9e0-5bb4-ab07-335eb95106b8 |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | 4a02c97e-096c-513d-81ae-dbfceaf2002c |  | date | Lot Closed On
text | 56d119c2-2726-5782-8c9a-b93a427baf79 |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-065-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0065 - Wire Rope Safety Barrier (WRSB) | 604cb2eb-a424-4ff2-89d1-768603b3507a
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | 4869c4e4-ab8e-58f9-98b2-b91631071065 |  | date | Lot Created On
date | 4bffb7d3-8600-567f-9d72-587e1da1c6de |  | date | Lot Opened On
date | 6cfdb1eb-d2fc-5ada-ab47-27d609cad387 |  | date | Work Commenced On
select | 468b87ce-084e-5187-b5d0-18347bc239d1 |  | dropdown | Lot Type | CIL-Civil Lot, DRL- Drainage Lot, EAL- Earthworks Lot, ELL- Electrical Lot, UTL- Utility Lot, STL- Structural Lot
text | 906028d7-efcd-5c28-8e31-da4b70801277 |  | textbox | From and To Chainage
select | e8fd2c46-a024-5939-806f-0bc874387d2a |  | dropdown | Construction Element | SAFE - Safety Barrier
select | a1e3f7df-e791-59e7-a832-a75e839733dd |  | dropdown | Activity | WRSB - WRSB
select | dae8294d-03e0-55f7-8a3a-f76251f4c252 |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | e9173c4b-b1cd-5af5-a1bb-729450c0d9b6 |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | 7f94a5c1-e3e1-56a9-8ef3-81d72663b9ba |  | textbox | Engineer Responsible
text | d48bfbd5-fc6c-5204-86e5-7d59036fa816 |  | textbox | comments
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 157dcc5b-b952-5719-9cb4-8802a49b4079 |  | note | Document Title: ITP-001-AX-LOT-XXX - WRSB Install - CH XXXXXX - CH XXXXXX
label | b8ff1536-b555-5ab4-a27f-cfbea2ce0b05 |  | note | ITP Description: Supply & Installation of Wire Rope Safety Barrier
label | 1cb6d8b8-a62e-504a-aac6-45062496135a |  | note | Document Number (in Teambinder): 1145-C200-FUL-QAC-ITP-0065
label | c147ca5d-d38b-5474-9087-3e81a74e2daf |  | note | Revision Number: 0
label | bd11ea67-e4bf-52fc-9bf8-f94795d05de1 |  | note | Revision Date: 16/11/2021
label | 9c82bc79-294f-561f-b855-033e84c3cc36 |  | note | ITP created by: Omar El-Khub
label | 18f98735-8922-579f-a7a3-d06042b1f86f |  | note | ITP approved for use by: Beakal Likassa
label | 32142d0e-23e7-5dc0-a46e-d36a93ee7a2d |  | note | 1.1 VicRoads Section 711 July 2017
label | 110321b3-1af1-5dc9-a310-b4ff84528dd0 |  | note | 1.2 VicRoads Section 703 April 2019
checkpoint-group |  |  | section | 2 - Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Material Test Certificates
label | ed474b4e-5adf-5cd0-92e6-4c04a2cf621c |  | note | Frequency: Min 14 days prior to commencing
label | 20f0d8b2-1c43-5be4-91d3-acf7a9cd9ce5 |  | note | - - - - - - - - -
label | 1d16d5d1-1cf5-5b08-94b2-6ebeb16d10f8 |  | note | Acceptance Criteria: Only Safety barrier products listed in VicRoads Road Design Note 06-04 shall be used. The installation of the WRSB shall not proceed until the signed statement and certificates of compliance have been accepted by the Superintendent.
label | e5fb2dc1-e1a2-508c-909d-5704553ebd11 |  | note | - - - - - - - - -
label | 4d1eefe6-bb4d-539b-b818-3896aab6c097 |  | note | Reference Documents: Project Specific Specification PS3090.06 (c) VicRoads Spec. Cl.711.05
label | 02b5e2ef-9276-5622-94e0-3d6d318787bb |  | note | - - - - - - - - -
label | 7e6d1378-3e83-5790-9639-f8f533f0d5ab |  | note | Inspection / Test Method: Document review
label | 16573860-21eb-532b-a978-5252168ce0b0 |  | note | - - - - - - - - -
label | d05e28d1-f142-5e47-ae43-a42e86036d45 |  | note | Record of Conformity: Material Test Certificates
label | 44c1262d-b0bf-5ab4-8540-63b833ce2874 |  | note | - - - - - - - - -
label | 854074bc-6609-5dcc-b5f0-c95f9b7b486a |  | note | HP
label | e09c5418-b705-5c4f-b395-0f407c3cb28d |  | note | - - - - - - - - -
label | adeb9100-1639-5cfc-8d28-a79fe0b162fe |  | note | Responsibility: Project Engineer/ Superintendent
label | a9bd0947-a6d5-5563-a7d4-eebd155af46d |  | note | - - - - - - - - -
date | 341d2992-332f-5419-8a38-b2e97c299332 |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.2 - WRSB Material Properties & Protection
label | 2eb950c3-31ff-53a8-a725-70ebfea3ff2a |  | note | Frequency: Prior to Commencing
label | e2974243-e5e2-5f76-bd00-5c73f3ce4c3d |  | note | - - - - - - - - -
label | 9fbbf422-df48-5313-b71e-f9ff52a20c95 |  | note | Acceptance Criteria: WRSB material shall meet the requirements as specified in VicRoads Section Cl.711.04.
label | 6a1b5aa5-e1b4-59ed-b149-842aabb6afae |  | note | - - - - - - - - -
label | 6af57aac-7685-566d-86c0-5d7e43a8334b |  | note | Reference Documents: VicRoads Spec. Cl.711.04 Cl.711.11
label | 286867b0-12e8-5e18-a23d-1213ee3e3a54 |  | note | - - - - - - - - -
label | 177b0e96-9e2c-5dfd-a300-c45b0ef5cca6 |  | note | Inspection / Test Method: Document review
label | 1df51202-affc-549e-9a2b-5be54d49af62 |  | note | - - - - - - - - -
label | 75267d3e-d153-5d35-8b65-eec41b6bb950 |  | note | Record of Conformity: Data Sheets, Visual Inspection
label | 42f8241a-18ff-5808-8adf-0d295b584534 |  | note | - - - - - - - - -
label | 352fc0d2-efee-5851-b662-4bf1144ccb9f |  | note | IP
label | fb091fe8-d01f-51fe-849f-002ed4e18248 |  | note | - - - - - - - - -
label | 029fad53-9530-5bb7-b58b-60c0820a35cb |  | note | Responsibility: Site Engineer
label | 4a1780dc-70e7-5890-bc99-d759d917c18c |  | note | - - - - - - - - -
date | 28467c62-6c03-51c3-8434-1b36be3b821c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Concrete mix design
label | af613c5c-b80d-5623-87b8-35359734a665 |  | note | Frequency: Prior to Commencing
label | a34e5008-b18f-5e7a-8d9d-ce44e34466e8 |  | note | - - - - - - - - -
label | 2c7424a6-091d-58f9-9d09-ba8cd5961f27 |  | note | Acceptance Criteria: Concrete Mix is Registered with VicRoads. Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings. Where the soil is solid well compacted in situ material as agreed by the Superintendent, the crushed rock can be omitted and a minimum 100 mm depth of N20 strength grade concrete placed for the maintenance strip.
label | be850b48-13c1-5903-91b5-b71e2108bdbb |  | note | - - - - - - - - -
label | be30d5c0-9b5f-5517-a412-2c84753ab1c6 |  | note | Reference Documents: Project Specific Specification PS3090.07 (b) VicRoads Spec. Cl.711.15 (a) VicRoads Spec. Cl.711.07(iii)
label | 78f31bbd-d621-5b2f-b74e-9ad61237c9a9 |  | note | - - - - - - - - -
label | 1c42863b-f836-56ad-a70e-4ce97446e7fd |  | note | Inspection / Test Method: Document Review
label | 466c39dd-781c-5a28-b82a-e315fd4788ef |  | note | - - - - - - - - -
label | 83c9854f-c1b6-5157-9bb6-f9c65991c42d |  | note | Record of Conformity: Mix design approval
label | 0bc0df41-a5f8-558d-aae3-4fa8cd51ee3d |  | note | - - - - - - - - -
label | 5ce400c9-bdbf-59c5-bd3d-6609b584d707 |  | note | HP
label | 6e0a3ffd-b8c4-5b5b-bc39-9c3586c1add8 |  | note | - - - - - - - - -
label | 9f2833bb-16a6-58af-bf26-a612d7b48ee8 |  | note | Responsibility: Project Engineer/ Superintendent
label | c720ad3d-8e4d-5839-bad5-a066012513f5 |  | note | - - - - - - - - -
date | d7fc0f57-11be-55e1-a8f7-3cae31375139 |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | 3 - Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 3.1 - IFC Drawings
label | 6bccb36d-cc5e-5870-89e0-31cf4eb0277d |  | note | Frequency: Prior to Commencing
label | 34fb6403-a617-57b4-adfc-960776f74d49 |  | note | - - - - - - - - -
label | 06039c8d-e6bf-5b9e-a25f-d1f5bf2d1b79 |  | note | Acceptance Criteria: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 6829a414-7a81-5ad0-986c-b9d4b8036fe9 |  | note | - - - - - - - - -
label | f68a0f32-12cb-5d87-bbad-e880b7ac46fe |  | note | Reference Documents: Project Drawings / Drawing Register Quality Management Plan
label | 496ca9c8-2654-550b-87f2-ffdcbb424e2b |  | note | - - - - - - - - -
label | f2c4cf60-bfe8-5eb6-a521-f6199fc25428 |  | note | Inspection / Test Method: Document review
label | fbdfc8e9-45c4-5375-ade0-9c5ec108269a |  | note | - - - - - - - - -
label | 65f21bc5-560e-5cef-91cf-6625a59c1c66 |  | note | Record of Conformity: Latest Revision Drawings
label | a3f1a208-f6e4-5789-8229-554a0d1175d6 |  | note | - - - - - - - - -
label | 9462c69f-8946-5d64-8092-d96c79d45a18 |  | note | HP*
label | afab3b2a-f98f-5bc3-95d3-81d366f0b097 |  | note | - - - - - - - - -
label | 5564906a-8deb-5889-9c09-22ad665ed421 |  | note | Responsibility: Site Engineer / Site Foreman
label | 9e2a19f2-4dfe-5b3a-aeca-cd970802322f |  | note | - - - - - - - - -
date | b276e78d-4413-51f4-b22f-2cad6ee07ec8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Survey Set-out
label | 37953296-c242-51c9-8068-206442f3f6a4 |  | note | Frequency: Each element
label | 90980a21-aaf9-5bd6-bc4a-d245a0572a90 |  | note | - - - - - - - - -
label | dd49748c-6d88-5362-969e-218bfc27a60c |  | note | Acceptance Criteria: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per cl. 711.08. The WRSB shall not be installed until the set out alignment of the posts has been reviewed and accepted by the Superintendent.
label | 692c8622-1cbf-5c23-b609-855b9ebc76bc |  | note | - - - - - - - - -
label | 11559784-c542-5058-aa84-88386cea1943 |  | note | Reference Documents: IFC Drawings VR 711.08 VR 711.07 (c)
label | ebbfbf57-73b7-5f22-9e25-6866e0931fd3 |  | note | - - - - - - - - -
label | 97e9a1de-d238-51e5-942f-5262f86219b7 |  | note | Inspection / Test Method: Measure, Visual
label | 8d7d5f44-6c9d-5691-8d1e-27a44bd439f7 |  | note | - - - - - - - - -
label | 7d810538-2f25-5421-a192-9c7ae0b3e92e |  | note | Record of Conformity: As-Built Drawings
label | d78186be-1151-53cf-a9bc-690bc8824b6a |  | note | - - - - - - - - -
label | cf0adabe-937d-5d0e-8a05-3db189f064b4 |  | note | HP
label | b60ac286-882e-54f8-8a38-cbb5972724d7 |  | note | - - - - - - - - -
label | 25132833-853b-5120-b7c7-eec6e515a1c9 |  | note | Responsibility: Project Engineer/ Superintendent
label | ec2c0231-c938-5c19-9951-22f9c1e1ea1b |  | note | - - - - - - - - -
date | 167a2aeb-41d2-59f1-aa41-76c9548111ef |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | 4 - Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Post Foundations and Anchor Blocks
label | 6da16a38-53a0-551e-96c9-cff648958334 |  | note | Frequency: Prior to Installation
label | 0e10202d-570c-51b4-9951-f2e2bad792f4 |  | note | - - - - - - - - -
label | 76fefab0-e45a-5114-adcf-1c1eb6d42d6d |  | note | Acceptance Criteria: Anchor blocks and post foundations shall not be constructed until the design and manufacturer’s acceptance has been reviewed by the Superintendent. Anchor blocks and post foundation shall not be cast until inspected by the Superintendent.
label | ad84d689-c47f-529d-93b2-3eab478f0e65 |  | note | - - - - - - - - -
label | d48aad3c-5230-5292-b1cd-408a5f05e3c7 |  | note | Reference Documents: VicRoads Spec. Cl.711.07 (b)
label | d100aaed-2896-5fac-96a1-d8e5237cf689 |  | note | - - - - - - - - -
label | 82fb1211-5b22-5a5a-bd2f-1d28c150894f |  | note | Inspection / Test Method: Document Review
label | 18eaa776-78cf-582b-a60b-5d514c883a95 |  | note | - - - - - - - - -
label | 379a8a1f-c0ff-55ec-bd76-4a80c10788b7 |  | note | Record of Conformity: This signed ITP
label | 296b8651-36d9-5714-b54d-f4d86dd11c03 |  | note | - - - - - - - - -
label | 751d421a-310f-5124-8309-ba3ef066a552 |  | note | HP
label | c01128ba-7229-5837-b7fb-a986ee6a53bf |  | note | - - - - - - - - -
label | af8fd73a-910d-5817-9ea1-500731912b5b |  | note | Responsibility: Project Engineer/ Superintendent
label | ffeb3acc-f11c-5467-ab11-a5594e82a108 |  | note | - - - - - - - - -
date | 42e7b653-541d-5276-bdb9-5d2cd8c41f0e |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.2 - Tensioning of the Wire Rope
label | 2d021bd3-4389-5755-afc0-5d3444b0ca10 |  | note | Frequency: During construction.
label | 7d334919-769f-5488-ac2e-8bbb9d66613b |  | note | - - - - - - - - -
label | be6ce327-1023-5a1c-b46b-9719934c8c7f |  | note | Acceptance Criteria: Each wire rope shall be tensioned in accordance with the relationship between rope tension and ambient temperature, applicable to the proprietary WRSB system as per the manufacturer’s specification.
label | 042de469-a485-5aab-9546-8d43040a9521 |  | note | - - - - - - - - -
label | 30d9b117-94b2-500b-ba42-74f0acbe8be6 |  | note | Reference Documents: VicRoads Spec Cl.711.07(e)
label | 7a38b89f-fcec-5653-acb5-6fac90fb0b8b |  | note | - - - - - - - - -
label | 80d92c2b-d9ce-5708-bd56-0e889f6333f3 |  | note | Inspection / Test Method: Visual Inspection
label | 5867a653-328e-5881-a880-e8c1b3403d00 |  | note | - - - - - - - - -
label | 55c11123-4eb8-5a88-ba31-1b78c85439c0 |  | note | Record of Conformity: This signed ITP
label | e5f770b0-c1f8-5b8b-925f-345a1963643f |  | note | - - - - - - - - -
label | 696c85b8-0457-53b6-9ed3-38155e8a2192 |  | note | TP
label | f798ac21-8039-514b-b49b-1ba09299600a |  | note | - - - - - - - - -
label | 42dee79e-a037-5a34-9038-5088dd8ed271 |  | note | Responsibility: Site Engineer
label | e7b01bdd-5572-5d81-b283-b55e39a0b5cc |  | note | - - - - - - - - -
date | 0b911865-6444-5fd5-903f-1e173288d67b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Construction Tolerances
label | 3f41d50a-15d5-5972-868c-d23d5b61f932 |  | note | Frequency: During construction.
label | 0e97f35c-4e2b-5aaa-9ca5-ed4150c26b7c |  | note | - - - - - - - - -
label | 318314a2-e1f9-5472-86b7-648a4f583562 |  | note | Acceptance Criteria: Tolerances for construction of the WRSB system shall be in accordance with the lesser of the manufacturer’s specification or as follows: (a) vertical tolerance on the height of the WRSB shall be ± 20 mm from the design line (b) longitudinal line tolerance for the WRSB system shall be ± 20 mm in plan view (c) tolerance on post spacing shall be ± 25 mm. WRSB height shall be measured from the road pavement when it is located within 1.5 m of the edge of pavement. For distances beyond 1.5 m, the WRSB height shall be measured from the ground surface at its location.
label | a59494c0-c317-5cc7-89ff-e7a781b2b32f |  | note | - - - - - - - - -
label | 6620dec3-261a-5bd0-8c94-77bce8418c05 |  | note | Reference Documents: WR-STD-064, WR-STD-050 VicRoads Spec. Cl.711.08
label | df702035-b181-5fd3-9505-81ad2e2fa0c7 |  | note | - - - - - - - - -
label | 37f14eba-fabd-5708-a3b3-15fe24328ae1 |  | note | Inspection / Test Method: Verify
label | d682f570-00e4-569a-959f-cce0898ed7aa |  | note | - - - - - - - - -
label | 9b4e654f-c806-5459-b2ef-e64497d45987 |  | note | Record of Conformity: Survey Records
label | d01cf934-6b24-5dd8-9d86-27eb059a1268 |  | note | - - - - - - - - -
label | a8088676-a4d4-5c01-9fe4-eabe0af2923f |  | note | SCP
label | ab0ead7d-1501-55e9-a248-f0de7a083ef0 |  | note | - - - - - - - - -
label | b74f121f-dda6-5c58-8f45-32aff6ab31bd |  | note | Responsibility: Site Engineer
label | 3300061a-0cb6-5320-811c-47864b6afcd7 |  | note | - - - - - - - - -
date | 4477bb35-f839-5973-b689-37396d46e317 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 - Concrete Maintenance Strip
label | 7019862d-3739-52f2-9bc9-9a22ad717576 |  | note | Frequency: During construction.
label | 56cd36ec-54bf-55f4-b922-7b96c2fdee7b |  | note | - - - - - - - - -
label | 43113dfe-5eef-5970-9a9a-02ae22a46d7f |  | note | Acceptance Criteria: Maintenance Strip beneath WRSB and terminals as indicated on drawing and/or as nominated in Table 711.151. The concrete maintenance strip shall be - Placed parallel to the barrier & have min 300 mm clearance to WRSB post. - min 2% crossfall or same slope as abutting pavement - Shall be constructed flush with the adjacent ground level - Shall be min 75mm N20 concrete conforming to the requirements of clause 711.04(b) - Shall rest on min 75 mm of compacted Class 3 crushed rock. Crushed rock may be omitted and substituted for min 100mm depth N20 strength grade concrete subject to Superintendent approval. Dummy joints at least 20 mm deep and 5 mm wide shall be formed at 2 m intervals across the full width of the concrete maintenance strip. Expansion joints shall be placed at intervals not exceeding 12 m.
label | bf8edb3b-cec9-5260-8b2c-ce6e1fe274e7 |  | note | - - - - - - - - -
label | c11cc395-f67c-5fbb-a45b-2cb374b9c710 |  | note | Reference Documents: Project Specific Specification PS3090.07 (b) VicRoads Spec. Cl.711.15 (a)
label | 8a1cd916-b177-5371-a04e-383913c48e13 |  | note | - - - - - - - - -
label | f3e41b13-7e11-5cb8-a9f0-767be16c079d |  | note | Inspection / Test Method: Verify
label | f925626d-680a-5a11-9451-4763ad5f8d6d |  | note | - - - - - - - - -
label | a608d665-55db-5ec4-b52b-3a50da77da80 |  | note | Record of Conformity: SCP & Test Report
label | 921d79da-fb06-5dcc-bc74-105e6602d458 |  | note | - - - - - - - - -
label | ecda5803-1e13-5071-be3c-e129a399e915 |  | note | TP, SCP
label | ef91ba13-1646-5415-8f56-3d7f02d49d87 |  | note | - - - - - - - - -
label | e8e5ffc5-66ad-50d2-8ad3-3bf89bab4f10 |  | note | Responsibility: Site Engineer
label | d73a04b4-fccc-59f7-a5ff-f995f1f9390d |  | note | - - - - - - - - -
date | fa66d301-40f9-50d3-812b-ffb436cdde35 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 - Pre-Pour inspection
label | 5afcfa2a-b4aa-550c-bb8b-88e9530eb373 |  | note | Frequency: Prior to Commencing Excavation
label | 958441f8-f652-503b-a232-1f68bece7d8b |  | note | - - - - - - - - -
label | 3a796207-f4b9-561d-a5e4-57fff77e8383 |  | note | Acceptance Criteria: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used.
label | e0660ce3-4749-58d7-bf4b-6104e694f681 |  | note | - - - - - - - - -
label | cea643ca-8f82-573b-9ba6-22bc754bc37f |  | note | Reference Documents: Project Spec. Cl.1190.06 Latest IFC Drawings
label | eae59889-7c84-57b7-9f7b-d8f47414065e |  | note | - - - - - - - - -
label | b0a861b7-d777-5211-86be-6730c39be288 |  | note | Inspection / Test Method: Testing
label | 095b1295-72e8-5a53-8335-83ead1feb2e9 |  | note | - - - - - - - - -
label | 51bc12bc-0479-5209-abae-a5ed7beb8cce |  | note | Record of Conformity: Survey records & pegs on the ground
label | 60701294-1de3-5214-aff4-16f3ae67bc86 |  | note | - - - - - - - - -
label | eb4e5ab9-d705-5ac8-b603-a79e58e90c62 |  | note | SCP
label | 504026ce-e8be-54d3-aa8b-88c37f8266f0 |  | note | - - - - - - - - -
label | 45732f55-f7ee-5a06-83da-625fa22a9295 |  | note | Responsibility: Site Engineer & Surveyor
label | be5ee4b3-1b6b-58b2-a483-b2cd29318a13 |  | note | - - - - - - - - -
date | bbca4ea3-c3aa-58db-b458-8315a0240ace |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 - Concrete testing
label | 313c997a-19c7-5584-bc9a-77cb32b25147 |  | note | Frequency: Every 50m3 pour
label | d4f62249-3cdf-5b70-b2e9-4df16c7bb43e |  | note | - - - - - - - - -
label | a2f5f45f-736f-576a-a5ae-1991bfe0c821 |  | note | Acceptance Criteria: Concrete shall be N20 standard strength grade. Sampling and testing of the strength of the concrete shall be carried out. One sample shall be taken for every 50m3 of concrete poured for each strength placed on any one day. Test to include: - 1 x 7 day compressive strength - 2 x 28 day compressive strength - 1 x Slump Test
label | ba090c60-5918-5b99-aad7-b8e739bf680f |  | note | - - - - - - - - -
label | a2a39437-c03f-5722-9a92-45f7b2bd7144 |  | note | Reference Documents: VicRoads Spec. Cl.703.11
label | 47252e93-61f8-59d3-b746-3a468f405fb6 |  | note | - - - - - - - - -
label | a07b3ffe-7d2d-5ae0-991d-8aa3f19462a0 |  | note | Inspection / Test Method: Verify
label | e4958156-eb86-5aa3-b57a-5e2f1bfbc9a5 |  | note | - - - - - - - - -
label | 66b92dd4-da47-5f5c-98ad-60e320cc69a3 |  | note | Record of Conformity: Test results
label | 6796213c-9e2f-579b-b541-6eb49620af63 |  | note | - - - - - - - - -
label | af205ed3-fb12-57ac-ab9b-a07fd3868682 |  | note | TP
label | 93281c0f-1f32-5239-8370-a0b76230be43 |  | note | - - - - - - - - -
label | 3c4fc632-f6f6-5250-a374-97e04710ff61 |  | note | Responsibility: Site Engineer
label | 193ccb62-a961-5ea7-92e7-b4785516f524 |  | note | - - - - - - - - -
date | d319bd17-41ac-5e54-83fe-83050c7b6184 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 - Curing of concrete maintenance strip
label | da24e4d3-fee2-5e68-ace0-e2d9b00168c4 |  | note | Frequency: Each Pour
label | 9158d298-e108-52ea-b1e3-56f0a26a9428 |  | note | - - - - - - - - -
label | 61fe8c43-6fb2-5995-a670-2ab3041c3291 |  | note | Acceptance Criteria: Concrete shall be cured either by water curing, wet hessian,polyethylene sheeting adequately sealed against moisture losses, curing compound or combination thereof. Curing compounds to be in accordance with AS3799.
label | 427fc9b4-378f-5ce7-9f68-f81bd86d294b |  | note | - - - - - - - - -
label | ec6d0a7c-3607-574b-a732-e5aefe01687b |  | note | Reference Documents: VicRoads Spec. Cl.703.10
label | 8361e5f8-bfa0-5347-90f7-50f39b466375 |  | note | - - - - - - - - -
label | b5928dbe-35da-5835-9342-6fbb4d789dcc |  | note | Inspection / Test Method: Visual Inspection
label | af3675f7-a145-5911-9ac4-d3112b334178 |  | note | - - - - - - - - -
label | e6bf9916-572d-5063-b38a-463651aafce2 |  | note | Record of Conformity: Site Photos
label | de430efb-37bd-5831-b4f1-7c19c16eef98 |  | note | - - - - - - - - -
label | 94f1241e-e710-5956-a691-b56e007a8b5d |  | note | IP
label | 5cd553df-6c42-58d5-b025-bc3ed528cdb8 |  | note | - - - - - - - - -
label | a963d054-a07b-52bf-abcf-4c9888cfbc77 |  | note | Responsibility: Site Engineer
label | 95f039cd-a0db-5511-885a-9c54995d4b3a |  | note | - - - - - - - - -
date | f6acf98f-c8e3-5533-996f-0fc7ce161163 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Test Requisition
text | c99f64fb-208c-5b87-884a-0845d2437136 |  | textbox | Test Requested on
text | 8f13459f-dc05-5e20-9343-ad13516884e3 |  | textbox | Location
select | 38e802cf-eee4-507d-bf7c-e34cf0c2aca6 |  | dropdown | Material Type | Type A,Type B,See comments
select | aa9da704-fe22-5a5d-964e-4c24e025bf5c |  | dropdown | Material Source | Holcim,Boral,See comments
boolean | 6527d2f0-f577-50bb-88af-5a1bdda60106 |  | tickbox | Compaction Test (Standard)
boolean | 0dee4e17-ef6e-574d-bc3a-150a001856ec |  | tickbox | Compaction Test (Modified)
boolean | 6345eeb5-aa2c-56ed-924c-ea216101ac8f |  | tickbox | Maximum Particle Test
boolean | 6469922f-3de3-5240-81c7-8447eca2d4d9 |  | tickbox | CBR/Swell Test
boolean | 83c69c84-80a5-533d-81a8-66f34fb1becb |  | tickbox | PI Test
boolean | 3ea87605-7a4b-5800-a0f2-98570230c811 |  | tickbox | Permeability Test
boolean | 2e00d8f4-2f91-5970-851c-7051b8e0bb80 |  | tickbox | Grading
boolean | ed76b6db-7236-514e-99b5-3e84b8b60ac8 |  | tickbox | Moisture
boolean | f570bd01-bea4-5d8e-aa26-819f83972683 |  | tickbox | See comments
text | 1697ec08-aea5-503f-9d9c-12df44fb65cd |  | textbox | Test Level/ Layer
holdpoint |  |  | signoff | Test Requisition
checkpoint-group |  |  | section | 5 - Post-Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Compliance Audit of Barrier System Installation
label | 746bb6ae-6ef2-5c94-a1f4-27942fc9e081 |  | note | Frequency: Prior the issue of the Certificate of Practical Completion
label | 289f18a5-64da-578b-b477-83e84ba5b3ba |  | note | - - - - - - - - -
label | 33e21ecd-92a4-5ccc-a6da-e8f15b0b9ff2 |  | note | Acceptance Criteria: Prior to the issue of the Certificate of Practical Completion, FH shall arrange for a safety barrier compliance audit on all WRSB installations constructed under the Contract. A signed copy of the manufacturer’s Installation Checklist / Inspection and Test Plan as per the manufacturer’s Product and Installation Manual shall be completed and submitted to the Superintendent..
label | 0d0c5a92-2f82-5509-969d-b22006215f0b |  | note | - - - - - - - - -
label | 4604cd76-3d1b-500b-b676-f1c15aba186c |  | note | Reference Documents: VicRoads Spec. Cl.711.09 Project Specific Specification PS3090.07(f)
label | 8fed5fb3-dcc6-5488-8919-0bc7e3296a15 |  | note | - - - - - - - - -
label | 3885e3dc-effe-5d52-8b33-2e06426b626a |  | note | Inspection / Test Method: Safety Audit
label | 0eccd050-1002-578a-8476-40d200b92b9e |  | note | - - - - - - - - -
label | c2740ee6-6360-552a-8829-68301672cea2 |  | note | Record of Conformity: Certificate of Compliance for each treatment installed Product and Installation Manual
label | 6c0d7e6d-5ef8-54b2-bcb1-856b3db70540 |  | note | - - - - - - - - -
label | c5713f99-e33c-554e-b641-2219423d2531 |  | note | HP
label | ad3eb72c-a8ea-5170-aad7-7114c78c0045 |  | note | - - - - - - - - -
label | 0c3f2048-a09e-5286-94af-77a64c66dfe8 |  | note | Responsibility: Project Engineer/ Superintendent
label | 010ff95f-4dc7-569a-a967-b9c50b0263b7 |  | note | - - - - - - - - -
date | c1d1cf46-688d-5713-9aac-2c8816279974 |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.2 - Delineators
label | f3e14268-5c1c-533d-a08d-0b8a7e288eab |  | note | Frequency: Once installation of assets completed.
label | 751d8a2d-d77e-5979-9b9f-7391fb032fb5 |  | note | - - - - - - - - -
label | fc0bbfd9-8eeb-5f09-9158-b37d42cbdcb5 |  | note | Acceptance Criteria: delineators shall be fastened to the WRSB system, comprising post caps fitted with 50 x 100 mm Class 1A retro-reflective material, as defined in AS/NZS 1906.2, or placed on the front top of the post above the wire ropes. Delineators shall be installed at approximately 12.5 to 15 m spacing. Delineators shall not be placed on flared sections. The delineators shall be arranged so that vehicles approaching from either direction at night will only see: - Red delineators on the left side of one-way and two-way roadways - White delineators on the right side of two-way roadways - yellow delineators on the right side of one- way roadways Delineators not to be installed when the WRSB offset if greater than 4m from the traffic lane.
label | c0bb3b8c-dec9-5a63-aac0-f5e2c74831e3 |  | note | - - - - - - - - -
label | 9574ce81-a1c7-57c3-81fd-c40e7e48992f |  | note | Reference Documents: VicRoads Spec. Cl.711.10
label | 8bc27fd5-deff-503b-ae6a-4755316aea14 |  | note | - - - - - - - - -
label | 3a55eb69-b681-57b5-a895-35b302027f5e |  | note | Inspection / Test Method: Visual Inspection
label | 8fe93db1-0acb-504e-afd1-98b5fe788d9c |  | note | - - - - - - - - -
label | 6f6af10b-9f33-5d02-969a-bbd0457e87e4 |  | note | Record of Conformity: Site Photos
label | ea43b156-ac98-58e3-8765-693f302c253f |  | note | - - - - - - - - -
label | 96a566f7-8c8a-57fd-bbcb-ba836f784222 |  | note | IP
label | 13ae17ca-fbd6-5267-a4ed-681148da70a2 |  | note | - - - - - - - - -
label | 7f2748a2-57a9-5972-8f2d-1ab5d79640d3 |  | note | Responsibility: Site Engineer
label | dd067ebf-b3eb-5982-be0b-5a375877b0d4 |  | note | - - - - - - - - -
date | dc701bf0-cdad-5109-8ec9-8c6cf190107e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Compressive Strength Test Results
label | cfe3a6df-6131-51cc-b29e-3086961a6d6e |  | note | Frequency: Each cylinder
label | c8b40263-d5d2-5325-891c-e82873ec73f7 |  | note | - - - - - - - - -
label | 613d9fd3-91df-5df4-8a3d-0acffda91c95 |  | note | Acceptance Criteria: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly. 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength. Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | 20d4247c-6f3c-5e88-99f5-c3a3c2df8092 |  | note | - - - - - - - - -
label | 74fa82d6-81be-5813-b0d7-70b9e7f314cd |  | note | Reference Documents: IFC Drawings VicRoads Spec. Cl.703.11
label | 74833130-9823-549b-a32d-597b00e5bed3 |  | note | - - - - - - - - -
label | cb03a222-0a45-58c4-a0be-c5164565e9b5 |  | note | Inspection / Test Method: Document Review
label | 38906601-c40f-5ef3-ae5f-5484e1b7959d |  | note | - - - - - - - - -
label | c09aa7c0-c1e3-5fd0-89b8-329d8aa68bea |  | note | Record of Conformity: Compressive Strength Test Results
label | b0317baf-be17-52d4-9e1b-ce24570f4378 |  | note | - - - - - - - - -
label | 18bdbb94-8cd9-581d-b1b5-7c52b60212e3 |  | note | IP
label | 62c29249-941e-5e98-b10b-c913cf78a71c |  | note | - - - - - - - - -
label | 87697ead-4734-5e1b-85be-0137fd75e6cc |  | note | Responsibility: Site Engineer
label | 5f372323-54a1-56fc-933f-f421467d8295 |  | note | - - - - - - - - -
date | e39611d9-9129-50b7-aacb-5a94d5348307 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - As-built Survey
label | 33eb861c-9fc8-5879-aebf-d8a91ea32e10 |  | note | Frequency: Each element
label | b180d5cc-a990-572d-b170-47491bf29a84 |  | note | - - - - - - - - -
label | d4123d47-88f9-5be0-aa8f-c38271c873fd |  | note | Acceptance Criteria: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per 711.08 as applicable to the element.
label | 671fd6a6-dbda-5a5b-823d-b722630aa942 |  | note | - - - - - - - - -
label | a18c0bd0-baef-59b5-b150-5a89e7760773 |  | note | Reference Documents: IFC Drawings 711.08 Survey As-builts / Survey Report
label | df95844b-d11f-5efe-ae8f-dcf9099bc308 |  | note | - - - - - - - - -
label | 550ef6b9-f5bd-55c9-b51f-c63a54d984eb |  | note | Inspection / Test Method: Document Review
label | 21be63c2-d9e1-5dbb-81ca-d9d98463a46e |  | note | - - - - - - - - -
label | 405a8628-990e-56b0-b5f4-ef72ccd097c6 |  | note | Record of Conformity: Survey As-builts / Survey Report
label | 9444f29e-b23d-5cfb-a7a8-94c99a92cdf7 |  | note | - - - - - - - - -
label | c7622eed-612d-5889-a372-95ff0d1a1b2c |  | note | IP
label | a07d9084-539b-5fdb-a35f-7cdc144c96aa |  | note | - - - - - - - - -
label | dd713c04-220e-5159-a144-0efd4f15d6e0 |  | note | Responsibility: Site Engineer
label | 85050790-7040-512c-a7bd-dfe3dcebb6ef |  | note | - - - - - - - - -
date | 173f947f-76ad-5c87-9e6d-6be9c717853b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Non-conformance Report (NCR) Closure
label | 77ef09d1-2f2d-5adf-9c36-06a5c1673f4e |  | note | Frequency: Once, prior to closure of this lot / element / Work area
label | 61dc6e40-95f1-5c6c-b17b-c5e4f9c9aaca |  | note | - - - - - - - - -
label | e5904829-4fbc-5add-b33f-26d0ef4dc667 |  | note | Acceptance Criteria: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
label | 331174c5-5804-5d47-bba8-14e41a8d3968 |  | note | - - - - - - - - -
label | 47a148f5-97ad-5003-810d-2858dd2dcdb2 |  | note | Reference Documents: Quality Management Plan
label | 70ddf8a8-eac8-53c3-8f06-211d66dbf9e9 |  | note | - - - - - - - - -
label | a357cb1e-9f22-5f22-8723-b30ffddd0b8d |  | note | Inspection / Test Method: Document Review
label | 25c45762-7725-50b8-9b4a-4a6bac457d05 |  | note | - - - - - - - - -
label | d97670fe-5431-5fc3-a1cc-321ec94e5c16 |  | note | Record of Conformity: This ITP
label | 7c77cebd-a75c-5a72-8d41-49824f200d42 |  | note | - - - - - - - - -
label | 8c9ad663-c80a-58fd-bddb-9084d3352066 |  | note | HP*
label | 30f35d5c-cfa0-594c-abaa-efe93ecd4630 |  | note | - - - - - - - - -
label | 867bd664-c82b-561c-914e-feac7fd931cf |  | note | Responsibility: Site Engineer
label | 47de179e-3eac-5c80-b6e6-7798d5d8d416 |  | note | - - - - - - - - -
date | e417501c-07bc-5784-bdf2-c7a50c18ccc9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Inspection of Grassed Areas
label | 3fc0cf04-8b15-5fb2-b930-ea8070d1278a |  | note | Frequency: Each element
label | b5debbe0-7f15-5868-9c49-3ec644fb6a90 |  | note | - - - - - - - - -
label | 4235758e-9b3e-5955-b140-95bb453a4c79 |  | note | Acceptance Criteria: A joint inspection of all grassed areas shall be carried out between the Contractor and Superintendent three months after sowing has taken place.
label | f6b8c065-f0fa-55b3-b710-077329d4530f |  | note | - - - - - - - - -
label | e78aa87d-acaa-5195-8528-53ea461185b7 |  | note | Reference Documents: VR 711.22 (a)
label | b73bb08c-98f1-5675-a8ed-0c7817d8b313 |  | note | - - - - - - - - -
label | 04385ef4-c86e-5805-a439-aa78a3ea316a |  | note | Inspection / Test Method: Visual Inspection
label | 523d64e9-bb35-5980-b38a-29e7d65fc9c5 |  | note | - - - - - - - - -
label | 43c3c96c-b4f6-566e-afd3-546f0a136c89 |  | note | Record of Conformity: This signed ITP
label | 1b2728da-353a-5d8d-956e-764ce50cdf76 |  | note | - - - - - - - - -
label | df304e0b-1383-53cb-ac19-f86a52144d7c |  | note | HP
label | 088c1cb2-6a4f-5c84-94d4-0d8d14420183 |  | note | - - - - - - - - -
label | 686c96d5-23ab-50ab-871a-ec986cf115af |  | note | Responsibility: Site Engineer/ Superintendent
label | d6d18319-d260-59b9-bc56-519b7a3c76a3 |  | note | - - - - - - - - -
date | 6635065e-7232-53e8-93a9-9b1011a24aff |  | date | Date Completed:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.7 - MRPV Quality Final Inspection
label | b0cc6965-5275-5c60-87e7-dff16e1aaac9 |  | note | Frequency: Completion of works
label | 4bff7a68-a929-5a30-a0ed-384aa78c006b |  | note | - - - - - - - - -
label | 45719de9-0a3f-5e5f-aed4-3212b686a3f3 |  | note | Acceptance Criteria: Lot Signoff by quality team
label | 496de039-25ea-5549-9af4-db70c1865127 |  | note | - - - - - - - - -
label | 981b68cc-925e-5621-92fa-22f1f4489838 |  | note | Reference Documents:
label | 0271fbe5-771a-5240-a2bc-4479f0baf704 |  | note | - - - - - - - - -
label | 9a7c36da-7c1d-5d15-9dff-0e10b72a007a |  | note | Inspection / Test Method:
label | 73672fdd-fb67-591c-80ac-66f67441d0d5 |  | note | - - - - - - - - -
label | d6cec57e-55c0-5adc-bf37-1ad316d15d12 |  | note | Record of Conformity:
label | 95fb1211-701f-5edf-94c5-1a0f12f97a81 |  | note | - - - - - - - - -
label | 87c60da9-82ce-58d8-a522-8f9a73c67b6a |  | note | SCP
label | 00c1117c-96e7-5728-bf35-9e25facb2cb0 |  | note | - - - - - - - - -
label | ee83ad48-d498-5cde-93e2-46cab5d21f34 |  | note | Responsibility: Quality team
label | 4fbaa68d-03cb-5a09-bd10-02a31ba7c14c |  | note | - - - - - - - - -
date | b6fade2d-47f9-5f9a-a0e8-a2bbcb87ed94 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 24d07c87-7136-50c0-aa10-4be827e3df40 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | c386c52a-2929-56dc-8466-bf8857b51790 |  | textbox | Print Name:
text | 2060e62e-09e9-5f9b-9646-fc4394d606d5 |  | textbox | Position:
date | dc9d27a9-f4e6-5cf4-9a5f-c157af140592 |  | date | Date:
date | b5835fef-3c70-53f7-a865-70fe3071017b |  | date | Work Completed On
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification.
select | 172a4d91-aa96-50ee-807a-c11301f45c04 |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | 012d9923-9148-5e32-8868-79808b9d963b |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | 7137d40a-c397-5045-b736-d616cfad1814 |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | 88045a3a-c4c0-5328-85d9-84c78fe10c53 |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | 61bcc308-54ad-588f-b24c-40437ae61e1c |  | textbox | Other:
select | 1fa6ed51-a39f-5c40-81d7-bcef9b18a46a |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | 8893350e-e12c-5574-b789-d5b9e5e3cde2 |  | date | Lot Closed On
text | ba4a369f-5b72-529f-ba30-92622ca9f7c5 |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-010-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0010 - Subsoil Drainage | 6f726905-41bb-4a7b-9ee4-dee5210a57e3
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | b8f3b9be-e446-5942-a544-d504e4b3d3e0 |  | date | Lot Created On
date | 4b9adfb9-c218-575c-beb7-bd44a4facd95 |  | date | Lot Opened On
date | 516f59b2-f6a4-56aa-a018-74b705385be4 |  | date | Work Commenced On
select | 35a2904b-bdab-5711-8ec9-da49ce9ef114 |  | dropdown | Lot Type | CIL-Civil Lot, DRL- Drainage Lot, EAL- Earthworks Lot, ELL- Electrical Lot, UTL- Utility Lot, STL- Structural Lot
text | dff6d962-122e-52dc-b82f-6723c6b7b415 |  | textbox | From and To Chainage
select | b770e0e0-1f53-557c-9ec1-b158687b8a9b |  | dropdown | Construction Element | STOR - Stormwater
select | e67b5e6b-569c-51dc-a595-73bb7879fcce |  | dropdown | Activity | SUSD - Sub Surface Drainage
select | f88c87c5-5dca-5cff-af21-aef8b53ecc0e |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | 55d275c9-3522-50a2-b96e-388cf00c38dd |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | a55634d5-8d8a-5c7b-9a91-aea0ed507006 |  | textbox | Engineer Responsible
text | 94660f7d-1d5d-5b7d-bff6-ef535026c8ac |  | textbox | comments
checkpoint-group |  |  | section | 1 - Material & Methodology Approvals
checkpoint-status |  |  | checkpoint | 1.1 - Subsurface Drainage Pipes
label | e5927028-9f84-5b56-bae8-5c9c955446fe |  | note | Frequency: Prior to Commencing Work
label | c085220e-be9e-50b8-ac82-b42d5c946104 |  | note | - - - - - - - - -
label | dabdb380-380d-51d4-8c20-475c956666c2 |  | note | Acceptance Criteria: Ensure all subsurface drainage pipes ordered are Category 1: perforated plastics Class 1000 and Precast concrete Class 2.
label | ac6cb323-cf69-5023-86dd-90ce9314a695 |  | note | All subsurface drainage pipes shall have a maximum perforation width of 1.5mm and a minimum length of 150mm/m2.
label | 6060f8df-7149-5df2-a183-65d1ac18346d |  | note | - - - - - - - - -
label | 2e51b7e3-738d-5f8a-bc45-2886ff6cf4c7 |  | note | Reference Documents: VicRoads Spec. Cl.702.04
label | 43e19d0f-d8b1-5974-b1ef-556ac53147aa |  | note | - - - - - - - - -
label | e91c53e8-9598-5644-ae60-fc44624e0e64 |  | note | Inspection / Test Method: Document Review
label | 81bda2f4-b20a-536e-ba2f-0618d4916e15 |  | note | - - - - - - - - -
label | 6c13ac55-9831-5a04-a30c-f8d7f1575240 |  | note | Record of Conformity: Insert Teambinder Material Approval Number
label | 562e63ad-bd4c-5476-89e9-69217789caa9 |  | note | - - - - - - - - -
label | b03b1164-d431-5a3f-b0d0-3462a1f4299f |  | note | IP
label | a5104cba-3e49-5e57-8b10-9e32e8de1005 |  | note | - - - - - - - - -
label | 789cc4c3-0113-5cbd-bf0b-f498363f006d |  | note | Responsibility: Engineer
text | 38e54a57-6e02-5b94-b4bf-ef7bd4943506 |  | textbox | Enter Teambinder Material Approval Number:
checkpoint-status |  |  | checkpoint | 1.2 - Drainage Geotextile
label | a5a668eb-a8cb-528f-8e62-e97af099711e |  | note | Frequency: Prior to Commencing Work
label | c4f27cf4-4796-5709-9084-d6a5b275d234 |  | note | - - - - - - - - -
label | ce815aed-438a-507e-925c-6a9547110cf4 |  | note | Acceptance Criteria: Type 2 drainage (NFC) Geotextile filter to meet requirements of a First Stage filter as per Table 702.061
label | 6226a6b1-9c70-5ccf-92e7-da5a60a9e52a |  | note | - - - - - - - - -
label | 4a1b7f9e-6b76-597c-825a-e26926f4dde5 |  | note | Reference Documents: VicRoads Spec. Cl.702.061
label | e57f25ab-8725-5348-ac8c-099f146fb6fd |  | note | - - - - - - - - -
label | b2a59722-27c2-5026-ad91-e02d21833559 |  | note | Inspection / Test Method: Document Review
label | 51e61c06-dbbe-5c06-a2b5-c2e56de8e339 |  | note | - - - - - - - - -
label | 14a2856e-6d16-56cc-929c-83d596744121 |  | note | Record of Conformity: Insert Teambinder Material Approval Number
label | 78666382-8f77-5099-a5e7-fa2e1aa7bccc |  | note | - - - - - - - - -
label | 7265961d-d6fc-51fe-9890-b6f797baa8b5 |  | note | IP
label | a5bd7890-5680-5cca-bd71-f9ecef812d66 |  | note | - - - - - - - - -
label | bc148583-d88d-5dd7-b1c1-aa684cd1ec68 |  | note | Responsibility: Engineer
text | 741afeb6-7756-58e7-9537-9bbf3b6f7dc6 |  | textbox | Enter Teambinder Material Approval Number:
checkpoint-status |  |  | checkpoint | 1.3 - SSD Backfill Material
label | be6fffcc-2eee-5bf6-8ebd-e72413c0f5be |  | note | Frequency: Prior to Commencing Work
label | 92c3f453-1e94-5e73-b407-e238887f3049 |  | note | - - - - - - - - -
label | 2528f249-7ed0-52e0-a595-450eba6d5dbc |  | note | Acceptance Criteria: Type 2 and 3 backfill material types to be reviewed against specification and approved prior to ordering and use.
label | db693077-e3c9-5949-925b-1581b098ed74 |  | note | Minimum testing requirements are reflected in line with 702.13.
label | d1230d0e-03aa-5d38-9036-f5c38d847216 |  | note | Type 2 NFC Grade B4 Filter Material
label | 4d34856f-7cb1-5232-ae0f-5112a25b59f5 |  | note | Type 3 Sand Filter Grade A4 to A6 Filter Material.
label | b40c0d26-cdfe-5693-9dfe-dc51ddb98af5 |  | note | - - - - - - - - -
label | 228040bd-2fc9-597c-94b8-672a1486c6a8 |  | note | Reference Documents: Project Spec. Cl.3030.05(a), Table 702.131
label | 4ad7fbe5-9e3f-53df-9e58-93fe6a5c04b5 |  | note | - - - - - - - - -
label | bb51456e-4393-508f-baa1-22e7cd6fdfe4 |  | note | Inspection / Test Method: Document Review
label | d79430c5-5701-582d-ad88-5f1d63e9a5ef |  | note | - - - - - - - - -
label | 9a710fe6-5723-5394-b6ef-4475ff697e85 |  | note | Record of Conformity: Insert Teambinder Material Approval Number
label | 3de3f0b8-3b96-5dce-a8b5-43ce391e467b |  | note | - - - - - - - - -
label | 68f03b4e-5afe-5654-a960-feb0aa1eb0d2 |  | note | IP
label | 62a7f994-f013-5c12-8a6c-df91e901b01d |  | note | - - - - - - - - -
label | c2bd0711-6b3c-576b-bfe2-db6852d1fb50 |  | note | Responsibility: Engineer
text | 5785c953-13ee-5427-b7d3-a0227d1638d7 |  | textbox | Enter Teambinder Material Approval Number:
checkpoint-status |  |  | checkpoint | 1.4 - Terminals & Pits
label | aeed6607-6feb-5a88-a7bd-9a0897e53ccf |  | note | Frequency: Prior to Commencing Work
label | 542685d5-f363-54bc-a967-4ec587dad322 |  | note | - - - - - - - - -
label | 6ffc81e3-3f5c-5669-80f5-bec7c0feb2de |  | note | Acceptance Criteria: Terminals and Pits
label | 556b47bb-a811-501c-a46e-9e41975168da |  | note | Flushout Risers SD 1631 and Type S1 Pits reflect VR SD 1611.
label | 32f1076b-4899-504f-8798-d02af83b5055 |  | note | - - - - - - - - -
label | 8b6e0939-fcf4-54d4-906f-7ee0ec0e046f |  | note | Reference Documents: SD 1611 Issue D SD 1631 Issue E
label | 1d6ca93c-9714-515f-962a-696388a0bb79 |  | note | - - - - - - - - -
label | 8ae1c66a-8df3-519c-a8b4-b94ca1c5981b |  | note | Inspection / Test Method: Document Review
label | 1631b5df-98d9-54e3-8e25-0184a3952f18 |  | note | - - - - - - - - -
label | 33b848f5-eae0-550b-b1d1-ba33d4ff4e2d |  | note | Record of Conformity: Insert Teambinder Material Approval Number
label | 1dc54554-1eca-5033-a8c2-ba9e8b53d132 |  | note | - - - - - - - - -
label | eab2341f-126d-518f-8288-2139a66ead4e |  | note | IP
label | fed4fcc7-c960-5bfe-92a9-8a3b17b41e4f |  | note | - - - - - - - - -
label | ab64beb0-8799-560c-b5d4-4416c1f6dae6 |  | note | Responsibility: Engineer
text | 90896ea9-af4c-5c46-a65d-dc934854d7e8 |  | textbox | Enter Teambinder Material Approval Number:
checkpoint-status |  |  | checkpoint | 1.5 - Compaction Methodology
label | ac274d92-ed3e-5f35-98b0-2bec7b6982a3 |  | note | Frequency: Prior to Commencing
label | 9e0bf446-8f1a-52c1-99f5-11f24c3aea6e |  | note | - - - - - - - - -
label | f194d4c3-e594-5699-b963-c3100e0de8d6 |  | note | Acceptance Criteria: Ensure compaction methodology of No Fines Backfill developed and submitted for review prior.
label | 8a8c7dc5-4db0-531d-b1fe-2422363b68bf |  | note | - - - - - - - - -
label | 4e603d3e-f759-5ec2-8b47-e3af8c1a330f |  | note | Reference Documents: VicRoads Spec. Cl.702.09(g)
label | bf10f3e1-e33b-5fd7-88c1-52501c240912 |  | note | - - - - - - - - -
label | ffc89554-01d2-5897-82ed-c6b18829bc5b |  | note | Inspection / Test Method: Document review
label | 12e08467-b78b-5590-a0dd-41491a0c6740 |  | note | - - - - - - - - -
label | 9955bd27-0c31-5d7c-ae26-4e82216a3bbc |  | note | Record of Conformity: Insert Teambinder Reference number
label | 20e2f957-b9b1-5d97-964c-9dd0060aec62 |  | note | - - - - - - - - -
label | fd4c9a72-596c-53c9-8322-a54ad998bb0a |  | note | HP
label | 8d12d564-9eac-54ca-b028-5c1885e0d79b |  | note | - - - - - - - - -
label | df7d2ca7-d782-5848-b4d6-26f7c024c7f6 |  | note | Responsibility: Superintendent / Project Engineer
text | 7442ebdd-7c8a-5ba4-bd80-6c607184dcae |  | textbox | Enter Teambinder Material Approval Number:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | 2 - Preliminary Works
checkpoint-status |  |  | checkpoint | 2.1 - Check current revision drawings are being used
label | b71d820d-8b17-5914-a6ee-f399c2284efe |  | note | Frequency: Prior to Commencing
label | 0d6b34b8-4d55-5437-88a2-dffc73c5934b |  | note | - - - - - - - - -
label | 8e6c0895-14f8-5e45-a13b-86ac68e29262 |  | note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
label | 2bc4a807-226b-521a-8985-592ebc9a13fd |  | note | - - - - - - - - -
label | 870d384c-596d-5fd2-b6fe-0f5e1c07f985 |  | note | Reference Documents: Project Drawings / Drawing Register
label | 5e373caf-881f-5b71-b5ef-34904adc9e2f |  | note | - - - - - - - - -
label | 17171f1c-2522-59d8-ac69-2c355c36739f |  | note | Inspection / Test Method: Document review
label | 5444389b-3d2a-5493-bc43-c9650367c394 |  | note | - - - - - - - - -
label | 8de5badf-4fe1-5279-8c10-7a65c52f26dc |  | note | Record of Conformity: Latest Revision Drawings
label | 3071fe62-33c9-5187-8eb5-8872e4b03235 |  | note | - - - - - - - - -
label | 50f11d56-fb74-55fc-9f36-d08f5911e9fb |  | note | AP
label | 52440adf-dcad-5c54-8891-f8276e534ef6 |  | note | - - - - - - - - -
label | 5e014b18-93d1-5169-a48e-3d677572bca1 |  | note | Responsibility: Site Engineer / Foreman
checkpoint-status |  |  | checkpoint | 2.2 - Excavation Permit issued
label | 829a15ae-94f2-5dd6-be1d-5ddd51173b22 |  | note | Frequency: Prior to Commencing
label | 3cbdf403-ce44-5f31-bead-9fa0a0fafe40 |  | note | - - - - - - - - -
label | 2cb5cef0-38c6-5158-9d3c-2f77454acbf0 |  | note | Acceptance Criteria: Current Excavation Permit signed and specific for the area where works will be executed. Ensure DYBD Plans and Drawings relating to the particular area are available, current and where applicable highlights temporary services installed by Contractor
label | 07bd4951-fc6f-568a-bd11-e5d193c61efc |  | note | - - - - - - - - -
label | 5577ec6c-905f-533d-910f-8c325fd7cf8f |  | note | Reference Documents: Excavation Permit
label | bf877fa3-00d2-5345-a309-2a4fd28a23c4 |  | note | - - - - - - - - -
label | efd9c995-77ef-5479-8cf2-de0d7e4b068c |  | note | Inspection / Test Method: Document review
label | 2af6a5b5-5c24-5b61-9199-b7cbf3d140ee |  | note | - - - - - - - - -
label | cd145366-1013-52ca-a7f1-cf1a628614bb |  | note | Record of Conformity: Excavation Permit #
label | 3106066e-2e14-5997-b9fc-3b237afb0590 |  | note | - - - - - - - - -
label | df3dfcf4-0602-51f8-8538-101b456a89b4 |  | note | HP*
label | 2d7eec84-4e67-56af-ab23-757c4e8a4e10 |  | note | - - - - - - - - -
label | 8eda3bad-6e53-5110-8cb9-8095de837573 |  | note | Responsibility: Site Engineer
checkpoint-group |  |  | section | 3 - Subsurface Drainage Works
checkpoint-status |  |  | checkpoint | 3.1 - Suitability of Materials
label | b6126539-a608-51e1-84e5-1b4d2a78fa51 |  | note | Record of Conformity: Signed ITP
label | b5c291b1-c06c-5891-9a2e-a7ede571e2ba |  | note | - - - - - - - - -
label | 300c92ea-09e1-5c2e-a7d3-7d90fba5cd48 |  | note | IP
label | aac45eb0-ba9f-5495-9315-672b96a17c55 |  | note | - - - - - - - - -
label | 1fb15237-88c0-5f82-aa08-c25af8f618f9 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3.2 - Managing Existing Drainage
label | 39d2fcfd-9a1c-5aef-95ad-a32e6195a902 |  | note | Frequency: When placing drainage
label | 5d003208-b397-5df5-97b0-7aabcda028bb |  | note | - - - - - - - - -
label | 2744fc66-3eac-5cd8-9889-883befae38a6 |  | note | Acceptance Criteria: Ensure removal and disposal of all redundant pre-existing subsurface drainage assets.
label | 77e112e2-8b32-5fc8-95ca-a62f67452bee |  | note | The area is backfilled with Type A material to subgrade or surface level.
label | 0734f01a-30eb-5c01-83a4-ea1aea98380f |  | note | Where backfill is required above subgrade level, backfilling must be with pavement material that matches the pavement design for that pavement.
label | e52dba03-af29-5394-83df-f52577fc168d |  | note | - - - - - - - - -
label | 11c03cbf-9084-5fbf-963f-0d96d582c217 |  | note | Reference Documents: Project Spec. Cl.3030.07(c)
label | 7ee11e32-1184-5a84-872c-36e8adc2c15d |  | note | - - - - - - - - -
label | 02c61df1-5612-5628-94b4-a5e146cf3d0d |  | note | Inspection / Test Method: Site inspection
label | 8413b798-09db-5da1-ace7-4b46f04a8809 |  | note | - - - - - - - - -
label | e0a44964-4ebb-5b09-bf15-c98d6b1e7e43 |  | note | Record of Conformity: Signed ITP
label | 4234a79c-c955-5f1d-a269-06ea20205409 |  | note | - - - - - - - - -
label | bc4090ca-9231-5e70-bc7b-5a4c06355c43 |  | note | IP
label | 9b97b62f-d085-5cf0-bf99-45c402bd85f9 |  | note | - - - - - - - - -
label | 07f3476b-408c-5546-ba85-a47b22908dad |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3.3 - Excavation of Trench
label | 361530b2-c077-5b36-8b09-8b4aadbe1964 |  | note | Frequency: When placing drainage
label | 7b460664-5e5f-5199-b6b4-1ed70bf2aa09 |  | note | - - - - - - - - -
label | bdcd2da8-0928-56c9-841b-57717ce2de38 |  | note | Acceptance Criteria: The base of the trench shall be sufficiently compacted and not more than 50mm below the invert level of the pipe to be placed.
label | 7ea3bbc1-d95a-58f9-a074-b71585b220a4 |  | note | The top of any subsurface drainage pipe shall be at least 300 mm below the subbase and setup for the subsurface drain type.
label | 9766e83f-8b57-5311-9a6e-8312944027d9 |  | note | Grade of trench to be not flatter than 1 in 250 gradient.
label | 3234c0b1-c504-5fb6-98a9-041495963951 |  | note | Base of the trench shall be inspected to verify compliance with the requirements prior to placing bedding in completed excavations.
label | 4c0cd88e-b36d-5178-a9cc-aecbcfd7b4ba |  | note | - - - - - - - - -
label | 66c64909-2752-51b2-ac8d-022c74d818c1 |  | note | Reference Documents: VicRoads Spec. Cl.702.08 VicRoads Spec. Cl.702.09(a)(b)
label | af4ce76c-2338-5e74-baa2-b945b357755f |  | note | - - - - - - - - -
label | 400dbf1e-f19e-5585-8658-506ed2b1964d |  | note | Inspection / Test Method: Site inspection
label | 05c49ea7-2394-5dda-b69a-4e648f964e5b |  | note | - - - - - - - - -
label | 9e5e8112-dc2b-5501-8fd3-39baebf6d42a |  | note | Record of Conformity: Signed ITP
label | c5143ae9-66ab-5179-bfd1-eed528507b43 |  | note | - - - - - - - - -
label | df204f8f-1143-5070-9fb9-e5a907c166ae |  | note | HP
label | 9a2449ba-eaf9-50e3-a86e-6bacbafa5b1d |  | note | - - - - - - - - -
label | a83165aa-9c35-51f7-9460-08eee3310053 |  | note | Responsibility: Superintendent / Site Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3.4 - Use of Geotextile
label | 5d3f83c4-a446-5c78-bbc3-671d874302a9 |  | note | Frequency: When placing drainage
label | aaf3d033-8448-53f6-b6a4-1c81711e1ba8 |  | note | - - - - - - - - -
label | 1eca2e27-0a17-5429-b443-41f2c1ab1c0e |  | note | Acceptance Criteria: Where geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contact with the wall when granular material is placed.
label | 985c29f9-5d2c-5872-9456-e052bab9eafd |  | note | The appropriate Subsurface Drainage Type 2 (B4 NFC filter) or Type 3 (Grade A4 to A6 filter) has been setup prior to backfill.
label | 24a347e8-f8e7-5779-86b7-b4649bc42b84 |  | note | - - - - - - - - -
label | ca02b27f-d81b-5c4c-ae68-3e7e0621ac2c |  | note | Reference Documents: VicRoads Spec. Cl.702.08
label | 50e4f9bf-a830-5a2e-8570-969fb5a06248 |  | note | - - - - - - - - -
label | 33b6178e-83bd-5f23-b2ee-0ed0c77abbf0 |  | note | Inspection / Test Method: Site inspection
label | c0cac4fe-a1b6-59d3-a37b-88c8674eb99b |  | note | - - - - - - - - -
label | 92b6272a-ba02-516f-9271-c9fb1518064d |  | note | Record of Conformity: Signed ITP
label | 4dc24efe-0b92-5c9e-b556-e1668b2e6466 |  | note | - - - - - - - - -
label | dc3b4ffd-9213-5bfc-9a68-5c26d6994d9c |  | note | IP
label | 0fd5a6d3-958b-5c73-adfe-75c4d9987850 |  | note | - - - - - - - - -
label | cc3f33a4-a1d1-5fd5-aa14-56248d6e5463 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3.5 - Installation of Subsoil Drainage
label | 9d6764a6-ddbe-546c-accb-c417fced5b35 |  | note | Frequency: When placing drainage
label | ae905300-466e-5e80-a9c3-0e0e11f3e6e2 |  | note | - - - - - - - - -
label | 4c45b69e-e4dc-50e6-9608-afd77dfa717d |  | note | Acceptance Criteria: Ensure bedding of thickness between 25-50mm is placed across the bottom of trench and graded to level.
label | 2a768a6e-4047-53b3-8bd1-35620a55fd88 |  | note | Pipes are firmly in place, slotted pipes positioned so openings are in lower half of the pipe.
label | 25618bbd-2dac-5143-b038-6276e72b0129 |  | note | Flushout Risers, S1 Type Pits and Outlets are appropriate positioned to reflect the subsurface drainage design.
label | be750bae-1bbc-54be-821d-1be0b8775a22 |  | note | - - - - - - - - -
label | 68895621-df04-5711-82ce-c9e6a179226f |  | note | Reference Documents: VicRoads Spec. Cl.702.09(d)
label | 3be95f88-b65c-5aa9-b253-b7da106bd69a |  | note | - - - - - - - - -
label | 4548c387-1683-5502-8fd9-6389e6d8dc22 |  | note | Inspection / Test Method: Site inspection
label | 43ae4cf8-ef39-5587-9133-4103a73c28e5 |  | note | - - - - - - - - -
label | d2bac44e-2ad2-593c-b700-d69c1871be58 |  | note | Record of Conformity: Signed ITP
label | 0b66e35c-d0fb-5eae-9071-21a2d70646a5 |  | note | - - - - - - - - -
label | 53526238-051c-55c4-9e49-3d9a9373ac62 |  | note | IP
label | 474329c5-d3cf-59a9-bae9-410be22b64f3 |  | note | - - - - - - - - -
label | 442857e7-b0ac-5792-b15d-d1e60d1d71c3 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3.6 - Placing of Granular Filter Material
label | 3047799f-2cfa-51d5-9721-d10204cb6bb7 |  | note | Frequency: When placing drainage
label | 0579c205-1d1d-5c07-ac4f-69854f944856 |  | note | - - - - - - - - -
label | 8f61f1cc-0ccb-5dad-a8c2-2da8392abf34 |  | note | Acceptance Criteria: Filter socks must not be installed on subsurface drains backfilled with no fines concrete (Type 2). (HP)
label | 1536e111-b6f7-5938-b5e4-148c87358b36 |  | note | Filter material shall be moistened and compacted with minimal disturbance to pipes. The loose thickness of layers shall not exceed 300 mm.
label | d5b02def-621d-57ce-9af1-fcf91b145a14 |  | note | For Type 2 (NFC) No-fines concrete shall be placed and compacted within 1 hour of mixing.
label | c9b8b9da-1c95-5082-a0c5-3e46aeaf3902 |  | note | - - - - - - - - -
label | a4bd392b-a5fe-5043-9c0a-a6d7eeedfb75 |  | note | Reference Documents: VicRoads Spec. Cl.702.09(g) Project Spec. Cl.3030.05(b)
label | 001afff5-7bf2-5d9b-8467-223310a49db3 |  | note | - - - - - - - - -
label | 4c5b9a1f-4faa-5bc1-8a1d-93ba3da3cdb8 |  | note | Inspection / Test Method: Document Review
label | 3a0ff6a6-0010-5513-a1c6-8fd8d0904fed |  | note | - - - - - - - - -
label | 569895cf-36dc-5e88-aff3-d664d850b0de |  | note | Record of Conformity: Signed ITP
label | 48e86c07-556e-5ded-b167-afa155cba410 |  | note | - - - - - - - - -
label | 6612fed6-9b20-5152-967d-7fae05cb5f46 |  | note | IP
label | 9bcbacd8-32af-50a4-a059-4581f4cae81d |  | note | - - - - - - - - -
label | 147e95d7-eecc-5a73-8483-30338c06af41 |  | note | Responsibility: Site Engineer / Foreman
checkpoint-status |  |  | checkpoint | 3.7 - Installation of Subsurface Outlet marker posts (If required)
label | 7f8752cf-5323-5cdd-833f-f2edfbc3d6be |  | note | Frequency: After drainage is placed
label | 6f5291d2-12c7-5ded-a63c-f90058889dac |  | note | - - - - - - - - -
label | 25e71990-ade7-579e-8dfb-42c083d75d81 |  | note | Acceptance Criteria: Marker posts installed at all subsurface outlets, and must be 75 mm diameter x 1500mm treated pine inserted 600mm into the ground.
label | 93b5c240-1afa-54a7-9c44-f59371bc28d1 |  | note | - - - - - - - - -
label | d2dc34e3-f3d3-542c-bd48-c0f90708f8d6 |  | note | Reference Documents: Project Spec. Cl.3030.07(b)
label | 34f8ca42-8fc0-5b6c-bc7a-34a01af03f27 |  | note | - - - - - - - - -
label | 4760d73f-8d30-5923-9ebc-b1dc0197a088 |  | note | Inspection / Test Method: Site inspection
label | 4a662806-9f58-55da-8dd2-5a76c982a5e1 |  | note | - - - - - - - - -
label | d3cf6fa3-0e18-5b57-a016-3dcf6ea0bf5f |  | note | Record of Conformity: Signed ITP
label | 93a41b0d-a41a-5f0d-af3e-02ee61bce1f9 |  | note | - - - - - - - - -
label | 4792a47b-6513-5a27-bded-00ebb2c0edd1 |  | note | WP
label | cd9a25b6-4ec3-5f30-9fa9-78309109618c |  | note | - - - - - - - - -
label | 57b2bdcd-0df0-5ece-971f-d4078108d3fd |  | note | Responsibility: Site Engineer / Foreman
checkpoint-status |  |  | checkpoint | 3.8 - Flushing Test
label | 6df60297-0f8a-5a52-b201-d346a2a50121 |  | note | Frequency: After drainage is placed
label | a4b3481f-3ce4-52fe-a997-d31ff405b267 |  | note | - - - - - - - - -
label | 0f359665-83e4-5909-9c19-f1aac39e7a14 |  | note | Acceptance Criteria: Flushing test shall be witnessed by a representative nominated by the superintendent and shall confirm that the drainage line is free of obstruction.
label | 43b6fc2c-822d-5fe3-855a-078b9f532814 |  | note | - - - - - - - - -
label | 96b8c2d2-abe6-58be-9af8-ac44a140c5af |  | note | Reference Documents: VicRoads Spec. Cl.702.09(h)
label | 35613f10-82ba-52f0-8a53-e804a89de832 |  | note | - - - - - - - - -
label | 0f34a2a5-af4d-5b69-96cd-4fa292cca173 |  | note | Inspection / Test Method: Site inspection
label | f6e308aa-c36a-5caa-af6b-4b0433a43e5e |  | note | - - - - - - - - -
label | d3b5ab0b-e50a-5445-a18d-b9e04d69ce58 |  | note | Record of Conformity: Signed ITP/ Record of flushing tests
label | e0b576c1-8cfa-5e7a-ab21-0d434d3ce5ca |  | note | - - - - - - - - -
label | 90ec7360-0b6b-5417-ae43-b1c3f3cd16a4 |  | note | WP
label | 20b4cf05-d472-5cf6-a81c-8479714d70ed |  | note | - - - - - - - - -
label | 65c793cb-7e87-5227-a203-bdd32b0a0f07 |  | note | Responsibility: Superintendent / Site Engineer
checkpoint-status |  |  | checkpoint | 3.9 - Inspection and Completion
label | 2e3b19f6-8fb4-5e4a-baab-166bb53f9701 |  | note | Frequency: After drainage is placed
label | f0cc677c-2d39-5cc3-a376-c8c9c815b6c3 |  | note | - - - - - - - - -
label | d4673731-ace1-5d8a-8767-9fecf3707e3f |  | note | Acceptance Criteria: All subsurface drainage lines constructed shall be inspected, after completion of the flushing test as stated in clause 702.09(h) and prior to placement of asphalt, by an independent testing organisation using closed circuit television (CCTV),
label | 0793f070-9946-5616-b201-dc726c72e456 |  | note | Verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
label | 18cec18b-8640-5667-b8a8-4ef99d076521 |  | note | Placement of asphalt cannot proceed until after this inspection. CCTV is completed, damaged or deformed drainage pipe removed and replaced. Along with waste and defect free condition of lines verified by the Superintendent.
label | 579ce323-744c-5d7e-874a-c4a452172f68 |  | note | - - - - - - - - -
label | 0b98a40b-2ab8-5181-b211-00c631d70f19 |  | note | Reference Documents: VicRoads Spec. Cl.702.09(h)
label | 1f4d3a09-ae0d-5b06-a0f0-9461d2f6453e |  | note | - - - - - - - - -
label | 003d36d0-bdec-53e4-9525-92138f409c2c |  | note | Inspection / Test Method: Site inspection
label | 3a82bc96-39da-57f6-ba2e-34d4e50d4cab |  | note | - - - - - - - - -
label | 4fef94e1-a641-5788-9353-0d37c986cae7 |  | note | Record of Conformity: Signed ITP/ Record of flushing tests
label | 8bbe4d9a-d9f1-5070-9f9a-b1c2cadaed8d |  | note | - - - - - - - - -
label | e1548a96-9a44-5596-88a3-b7499ae0f9d9 |  | note | HP
label | bbea26e3-230c-5582-b92a-ce81f09c8014 |  | note | - - - - - - - - -
label | 8bb38d54-b784-541f-854e-7311c37126ee |  | note | Responsibility: Superintendent / Site Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | edf68a01-a11a-54a8-9cce-5abec84361da |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 50fb1311-8c89-5f3f-9a99-bc9f18735a15 |  | textbox | Print Name:
text | 8db77b64-62b4-5fa9-909a-274a3f979c7c |  | textbox | Position:
date | 1afde231-2c2b-52d8-9191-975069f07ebe |  | date | Date:
date | 1938dca1-93fc-5298-b5b5-7114d84e509d |  | date | Work Completed On
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification.
select | 5e9063dd-fee2-5d76-9b05-4dcdc7d83520 |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | 670272bf-1220-55b1-98de-995f667c33a0 |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | 2398bb7a-7f1d-5b46-b083-0fd9b2d34b55 |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | 513b527e-2365-5acf-a0e0-aeb16c21bbaf |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | e1200789-3698-5747-86f3-51de5f222039 |  | textbox | Other:
select | 2e37ac99-d2ff-5fe1-adb7-a53c52a86fba |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | c49d5bb8-5fbb-5271-b397-77f25cff8a7c |  | date | Lot Closed On
text | 743be6c6-e8f6-567f-897f-345724dfa900 |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-011-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0011 - Cement Treated Crushed Rock | 72a3b4fa-8a3a-474a-9c06-a590a8981aef
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | c5e03e15-0e18-5136-aa18-97385ab5b171 |  | date | Lot Created On
date | dec3a2bc-d682-50e1-a524-a1924aebf36e |  | date | Lot Opened On
date | 5b20e283-2b75-50d6-aa12-0bdc112df30f |  | date | Work Commenced On
select | 1a1c60c1-66c5-54a8-81e8-0917c4c284ff |  | dropdown | Lot Type | CIL-Civil Lot, DRL- Drainage Lot, EAL- Earthworks Lot, ELL- Electrical Lot, UTL- Utility Lot, STL- Structural Lot
text | 58a63d9c-4020-57ba-adca-9097c09f2e41 |  | textbox | From and To Chainage
select | 4dd5c4d5-becd-52c3-8e71-88011c7d0ab7 |  | dropdown | Construction Element | PAVE - Pavement
select | 16c24e00-0071-533c-b75d-ed45fb7a3021 |  | dropdown | Activity | SCTCR - Subbase - CTCR
select | b33b61cf-4643-569d-89df-effc79e0fda0 |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | ad93c7ed-a76c-57fd-9e55-eb8f3e8adfa3 |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | b702d330-a0fb-5b2e-87be-1a8eb7ce3922 |  | textbox | Engineer Responsible
text | 9140c7dd-eab6-5cb0-b23a-31fdee999078 |  | textbox | comments
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Check that current revision drawings are being used
label | 8b302701-2ca8-5dd7-916d-8dc8e1f7757b |  | note | Frequency - Prior to Commencing
label | 61df6261-e425-57c2-b2f7-9efee030e9a4 |  | note | - - - - - - - - -
label | 43dda34f-219b-5fcf-a058-15444e8c1697 |  | note | Acceptance Criteria - Issued For Construction (IFC) and latest available revision used
label | 3f88cca2-982a-5815-a3c8-d7deea88d21f |  | note | - - - - - - - - -
label | 8958daee-ce3b-58a5-b2a0-040f34328a12 |  | note | Reference Documents - Project Drawings / Drawing Register
label | 00fa0616-0810-50fc-8a79-27176bf6e967 |  | note | - - - - - - - - -
label | 448c71e9-9c7b-5e93-a310-272082c95db0 |  | note | Inspection / Test Method - Document review
label | 1a539965-afbc-5172-b6ec-495241811817 |  | note | - - - - - - - - -
label | f59a47fc-2512-52be-b589-858c8aed0bc3 |  | note | Record of conformity - Latest Revision Drawings
label | 0d6f6262-476f-5ff2-9dec-518235d70639 |  | note | - - - - - - - - -
label | 968a6841-166e-5f22-b106-9f39af5faa49 |  | note | AP
label | 1f4a7cc1-fabf-5590-b932-1211587629b0 |  | note | - - - - - - - - -
label | fbafdbf1-af2e-56e9-9e08-c777bd768cb8 |  | note | Responsibility - Site Engineer / Site Foreman
label | 14e14c9c-2ae4-534f-8ae8-479a866ab801 |  | note | - - - - - - - - -
date | 309975d4-968e-592e-8ce0-f70466eb13c8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Submit Mix Design - Cement treated crushed rock (CTCR) mix
label | 792ab7eb-95c2-58a2-9de9-a96471b52340 |  | note | Frequency - Prior to commencing
label | 8e28473c-33f7-52ba-ac01-f30c6b0e2a82 |  | note | - - - - - - - - -
label | 87a1ec80-3030-5177-a59e-088881f5095a |  | note | Acceptance Criteria - Cement treated crushed rock mixes for use on specified works can be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175.
label | c35f5258-12e4-5eb9-9064-4fb3c3a7c01e |  | note | - - - - - - - - -
label | 06e1cac7-029d-5e51-a77d-bce6dc57764d |  | note | Reference Documents - VicRoads Spec. Cl. 815.05
label | c33c11ee-6395-5e35-8e20-f5dce07d210f |  | note | VicRoads Spec. Cl.306.04
text | 4c1bf01e-985d-51ea-8f9f-087aa66a293d |  | textbox | Team Binder Approval Number:
label | a87b5915-5da1-5b68-857c-a9fc72e8cdd9 |  | note | - - - - - - - - -
label | 70d40c12-96cf-5272-9fe6-aeab10920837 |  | note | Inspection / Test Method - Document Review
label | 616fb92b-e283-5a62-a76f-bc77cf47dfe3 |  | note | - - - - - - - - -
label | 86e720dd-a482-5939-8f47-97a65c06d7f9 |  | note | Record of conformity - Issue to TeamBinder: VicRoads registered cement treated crushed rock mix
label | 698354ca-98ae-53e1-8c81-7980511805ad |  | note | - - - - - - - - -
label | e47a4e74-ff55-53d7-a66f-7f65136d0c16 |  | note | HP
label | 2a6fd40d-6763-5fbe-bad3-740b9217b0e4 |  | note | - - - - - - - - -
label | aca9ed7a-4591-5002-8ef7-0ea41c2d1c5f |  | note | Responsibility - Site Engineer & Superintendent
label | 1a13c4f5-1257-5df1-ba47-8e9260e3d7ad |  | note | - - - - - - - - -
date | fd63842e-5204-5cdd-82dd-9715dad85ad0 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Survey Set-out
label | 26ea724d-7fd7-55b7-b74a-8d5663ab0a8c |  | note | Frequency - Each Lot
label | 2d3559e1-625f-5dc7-b2d7-1e4ae1ece8da |  | note | - - - - - - - - -
label | aa68686d-b826-5d23-8887-665538b5df0a |  | note | Acceptance Criteria - Survey to set out works in accordance with IFC Drawings
label | 735656e5-1e7c-5a1e-97ac-15c732578f78 |  | note | - - - - - - - - -
label | 481c866a-e936-52b8-8106-6c6f3ef2393f |  | note | Reference Documents - IFC Drawings
label | 7afba0df-08b9-578b-9dca-08faa553a01d |  | note | - - - - - - - - -
label | 658209b3-8e63-5500-8de2-7571f552520d |  | note | Inspection / Test Method - Measure
label | 8684bf3d-80b9-5294-b5fe-332d9d5f386a |  | note | Visual
label | 74bbb109-9faf-5222-b25a-abae1dbe612a |  | note | - - - - - - - - -
label | b028d00d-64dc-5a2a-b795-80c37ac53d92 |  | note | Record of conformity - Signed ITP
label | 988176bc-e606-548e-a4be-865799d3c894 |  | note | - - - - - - - - -
label | 986229d3-4681-5eac-ad57-adf168e91f65 |  | note | IP
label | d3b70241-0b48-5f5d-86d7-de9b504b300f |  | note | - - - - - - - - -
label | 61bd886a-3058-5ec0-855a-905eb9aaf440 |  | note | Responsibility - Site Engineer
label | 96699829-21c5-59d7-8dd7-9a788e8b91ed |  | note | - - - - - - - - -
date | 956e8e2b-90a5-5087-b671-2f29ace789fe |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 - Previous Layer Level Conformance
label | ad5d86f9-6960-598a-811e-a590b87595eb |  | note | Frequency - Each Lot
label | f54957c7-f780-5563-a9d1-ec669a67fbf0 |  | note | - - - - - - - - -
label | 8e40f4f5-224f-5db7-a3c7-4857844a57e7 |  | note | Acceptance Criteria - Confirm previous layer (prior to CTCR layer placement) conforms to IFC drawing and specification requirements.
label | 9588e627-e9a8-5785-ae81-034faaa9e7ea |  | note | - - - - - - - - -
label | 8f01b79d-a0c6-52cb-ae7b-945d10d494ff |  | note | Check the previous fill level/survey (e.g. fill, foundation . Subgrade, base course etc) to ensure CTCR minimum thickness requirements is achieved.
label | d62f8953-19cf-5e6e-8534-37fc15a3861d |  | note | - - - - - - - - -
label | 29e70f2f-f2b3-59e1-a06c-36e3b09fc669 |  | note | Reference Documents - IFC Drawings
label | 80e6bbba-32c1-5e38-8b00-4cb99dd576d9 |  | note | - - - - - - - - -
label | d8aa52f0-4384-5b4e-b9f7-e489c857e2f5 |  | note | Inspection / Test Method - Document Review
label | 51e8b627-292f-5c2f-a24a-68966671d368 |  | note | - - - - - - - - -
label | ed9f3baa-ac09-5ce9-8dd2-9378b400203b |  | note | Record of conformity - Signed ITP
label | c780edaa-c43c-58c4-a9c9-e878f11db0f3 |  | note | - - - - - - - - -
label | 9dcc2edf-ba0c-565a-bfc4-38cf22fdaf96 |  | note | IP
label | eb2c15a8-7ad0-501a-bc33-d24d673b444f |  | note | - - - - - - - - -
label | d5ef3033-ead9-50f8-a574-4affebf6382b |  | note | Responsibility - Site Engineer
label | dca664be-2a21-565c-9615-df6b21aa0682 |  | note | - - - - - - - - -
date | 0e154c50-dcc9-5430-b0fd-cad7a0d7ba67 |  | date | Date Completed:
checkpoint-group |  |  | section | 2 - Placing Fill
checkpoint-status |  |  | checkpoint | 2.1 - Lot Size
label | 341abbc3-b2da-564d-b2a8-2ddcdabb780b |  | note | Frequency - Check prior to placing material
label | 9ee77d96-68ac-5206-99b1-b1e3686672d9 |  | note | - - - - - - - - -
label | bc135891-eb11-5241-9ed3-ba7656577eec |  | note | Acceptance Criteria - The maximum size for a single lot shall be considered a single layer of 4000m2
label | 938ba504-1462-5e4b-9b2f-ed3e1be1d4a6 |  | note | - - - - - - - - -
label | 3a146f76-e5e0-5aa9-b395-931c9815ddbb |  | note | Reference Documents - VicRoads Specification Cl.306.03(b)
label | ac694b2f-ac30-55c6-ae88-f376f858f21c |  | note | - - - - - - - - -
label | 7e611293-e8c2-5970-bfd0-1ec63afc03f5 |  | note | Inspection / Test Method - Site Inspection
label | fcec1c30-851e-51fc-ab07-e46648d6804b |  | note | - - - - - - - - -
label | daa0d149-54c3-5a6b-a416-872c8435be00 |  | note | Record of conformity - Signed ITP
label | 9ac5b572-6e67-54b8-a293-586ebe667cbf |  | note | - - - - - - - - -
label | 4f272c30-7b2c-56e9-a2e8-71ed2cddbd8e |  | note | IP
label | 00628384-1e25-56b0-aa19-bc2bf1c36e1e |  | note | - - - - - - - - -
label | 01c75afe-083d-5e7b-bbc2-cbbbb8440276 |  | note | Responsibility - Site Engineer
label | 67ae0087-6688-5696-ac8c-fb6db7db9a0d |  | note | - - - - - - - - -
date | d7eb7b5f-5d5b-5c5f-b8f3-835d7e0c0f11 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Hold Point - Alternate Binder
label | 12b48bf3-e574-5235-b47b-d66fe8b7dd7b |  | note | Frequency - Prior to Placing Material
label | 94565670-9968-58fa-9491-4f588cc08dae |  | note | - - - - - - - - -
label | 388d74d8-e67f-5fa6-869e-ef4e179b990d |  | note | Acceptance Criteria - If a binder other than those listed in Table 306.091 is proposed for use, laboratory test results must be produced to show that binder satisfies the required working time and strength determined in accordance with the VicRoads Test Method.
label | 75dc228e-e294-5116-b2c4-a841b3ea5b0f |  | note | - - - - - - - - -
label | d0cc6a29-a8c9-5e09-97d0-28738095cf22 |  | note | Reference Documents - VicRoads Specification Cl.306.09(a)
label | 522ce360-c3da-5dd4-b22a-28869afd9dcd |  | note | Table 306.091
label | 1ab84cdc-7518-5de9-a3f5-da04ab7c81e0 |  | note | - - - - - - - - -
label | 1c5bce75-2922-5dd4-8cc9-fd60eb699087 |  | note | Inspection / Test Method - Site Inspection
label | 3051c8c4-09cc-5a69-bcb2-f6ee5e26e2e3 |  | note | - - - - - - - - -
label | 43035da4-333e-50b2-adf1-09944c043770 |  | note | Record of conformity - Test Records
label | 880fcdf6-f1f8-5cd7-9a11-fd2d2a37db3e |  | note | - - - - - - - - -
label | 6bec6ba2-d6fc-54a9-b91a-8451ccdd47ff |  | note | HP
label | 30c7b843-6ea7-5904-b665-79ca538ac635 |  | note | - - - - - - - - -
label | a27e54bf-f3b5-59af-a47c-2a0504af8b39 |  | note | Responsibility - Site Engineer & Superintendent
label | ef7a5301-7be1-5bfd-a840-aa18e08cf0a1 |  | note | - - - - - - - - -
date | f1b2aaa7-4311-543f-aa30-b32cbc9d2f50 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Transverse Joints
label | 4dcae285-e9fe-5096-a566-71b60278c609 |  | note | Frequency - Check prior to placing material
label | dea7d35c-b884-5852-a771-88f506517761 |  | note | - - - - - - - - -
label | e0516971-e0b1-558d-9ce9-25ed9e9a290b |  | note | Acceptance Criteria - Material should be spread to minimize number of joints
label | 920f5e8a-ca55-557c-8a5c-1c802ab5e69a |  | note | Transverse joints offset from one layer to next by not less than 2 metres
label | 557615b6-66c2-5595-84ca-82dc25232b75 |  | note | In any layer, transverse joints in adjoining paver runs shall be offset by not less than 2 m
label | 3682b9c5-4b68-598e-9269-d1c04dc1d153 |  | note | - - - - - - - - -
label | 446f8d4c-121f-5130-934c-2ecb7be5ba1b |  | note | Reference Documents - VicRoads Specification Cl.306.08 (a,b &c)
label | 215cec76-fce6-52f3-a685-683b3ce93282 |  | note | - - - - - - - - -
label | e214591d-a20d-5754-9dec-cacc31642054 |  | note | Inspection / Test Method - Site Inspection
label | e8c77445-35d6-51cf-b6ad-d1e19b9017cc |  | note | - - - - - - - - -
label | 920d4c65-d91e-5ec3-be24-fae782cd51cb |  | note | Record of conformity - Signed ITP
label | c3810f7a-e8e6-5a54-a2ec-2b2557bf2bbc |  | note | - - - - - - - - -
label | f4f4eec8-3e3a-51b3-90b3-082d4d2a241e |  | note | IP
label | 385e68c9-de27-5aee-988f-15d699df9e8b |  | note | - - - - - - - - -
label | b7c43504-f279-5bb8-b379-fb87fb2fb895 |  | note | Responsibility - Site Engineer
label | f38b5e01-7ab8-55e4-b508-c3a2835f231f |  | note | - - - - - - - - -
date | 0f3e02d8-fc72-5ac5-8c51-d5afeb363905 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Longitudinal Joints
label | e50e8439-b448-5040-9345-7fb7083c188e |  | note | Frequency - Check prior to placing material
label | ea65277f-82c8-55e1-b643-5905c9f0fca8 |  | note | - - - - - - - - -
label | 619afd3e-bdfe-5708-8cf5-abe448d9ccf2 |  | note | Acceptance Criteria - Material should be spread to minimize number of joints
label | 39440d24-e71e-5687-b989-9b4d0a7dc187 |  | note | Longitudinal joints offset from one layer to next by not less than 150mm
label | 122d823b-9379-5eb2-910a-2671f81abb1f |  | note | Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
label | 0d25827a-e7df-56f9-aa0f-50bb4c7e231e |  | note | - - - - - - - - -
label | 7b955d03-622f-5925-959e-357fcf280e55 |  | note | Reference Documents - VicRoads Specification Cl.306.08 (a,d &e)
label | f7983d2a-51e5-52a1-b267-9bfd156cc396 |  | note | - - - - - - - - -
label | 3ec40274-19ce-5281-a609-dc7d990126ac |  | note | Inspection / Test Method - Site Inspection
label | f9f29bc5-dfa5-5363-82e1-dc51b9ab12a5 |  | note | - - - - - - - - -
label | beee696e-9b72-5bc0-8f12-9def331ea47e |  | note | Record of conformity - Signed ITP
label | e871c2d8-8da2-53a4-a312-6e7465c1c15b |  | note | - - - - - - - - -
label | 527ed9cc-603c-536a-84f6-adde1c102098 |  | note | IP
label | 76a4c4e1-b540-5e46-aab1-f00a929ecd2e |  | note | - - - - - - - - -
label | 4f8f47b7-a948-5c8f-9f7f-5f447cac1161 |  | note | Responsibility - Site Engineer
label | 5f3e4732-5e82-555f-b343-3cebc949eab4 |  | note | - - - - - - - - -
date | 82d86ed1-d4ff-59aa-9e4e-ca22553e99d8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - Layer Thickness
label | e5ae58af-5541-5788-8485-7a65838b4490 |  | note | Frequency - Check prior to placing material
label | ac76ad92-9d9a-558a-9d53-fbd88fb5bd79 |  | note | - - - - - - - - -
label | f46db5e5-eb1b-53b1-9bdf-8a508c34ba7d |  | note | Acceptance Criteria - Compacted layer thickness should be not less than 100mm and not greater than 180mm.
label | d9da9f06-d272-599b-84d8-4dfb761dc60c |  | note | - - - - - - - - -
label | 4a94e7b5-f0cd-573b-8924-9d9138dfa3df |  | note | Reference Documents - VicRoads Specification Cl.306.11
label | 11f98c44-9e1f-5f3f-ab0f-d00714384414 |  | note | - - - - - - - - -
label | 88d8934f-1fed-5b0d-91f9-62afba4d3cdd |  | note | Inspection / Test Method - Site Inspection
label | b5f3d79d-f588-5564-858d-54f242300784 |  | note | - - - - - - - - -
label | 9b9c96f3-71c7-508e-89fe-36babf6fe3a3 |  | note | Record of conformity - Signed ITP
label | 4e981969-83a5-57fe-93cf-ed5496a46f8a |  | note | - - - - - - - - -
label | 83d537e3-8b56-5d1a-9ab5-89c76f0decf8 |  | note | IP
label | 3b025eb9-e2ee-51f0-80a1-1411a8855e28 |  | note | - - - - - - - - -
label | 727c5752-82a5-51e4-ab69-3e807d6d6740 |  | note | Responsibility - Site Engineer
label | 928894d7-ff64-59d4-88db-048e0a9bc203 |  | note | - - - - - - - - -
date | 12ccea30-bcb8-56b6-b2d4-1fd621553923 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 - Delivery, Placement and Working Time
label | b9d87ed2-5da8-504c-9a2b-4c8b77adfd37 |  | note | Frequency - Each Lot
label | 357f247e-28f0-5598-a580-26080fd0a7a2 |  | note | - - - - - - - - -
label | 435439f6-7100-5445-891f-2312d8e02e74 |  | note | Acceptance Criteria - Review delivery dockets to ensure all information required as per 306.07 (b) is recorded and meets the specification requirements.
label | 2ad9465b-bfcb-52e7-a18d-36f222393a0a |  | note | Working Shall Not be more than specified for each binder: Rapid Setting (GP) - 2hrs (Oct-Apr) 3hrs (May-Sept) Medium Setting (GB) - 3hrs (Oct-Apr) 5hrs (May-Sept) Slow Setting (Slag) - 8hrs (Oct-Apr) 12hrs (May-Sept)
label | 5a9b6569-541a-5b65-869b-b6616597f8c3 |  | note | - - - - - - - - -
label | 10ab176e-ac74-5e05-a193-4ef78921a2be |  | note | Reference Documents - VicRoads Spec. Cl.306.07
label | 405612f6-3663-5df8-81d9-a369870a7586 |  | note | VicRoads Spec. Cl.306.09
label | 155cb056-17f1-55b3-82dd-2bd556dfcf26 |  | note | Table 306.091
label | 800511c4-4e19-50b9-8ebf-aa7b4e4518c2 |  | note | - - - - - - - - -
label | 512cdc3a-a07c-553f-b082-05098ed8e327 |  | note | Inspection / Test Method - Site Inspection
label | d5ca206c-9b76-518b-b2ff-06d9b3bf8743 |  | note | - - - - - - - - -
label | 7136a15a-2681-5c22-957c-d5c08cdb610e |  | note | Record of conformity - Signed ITP
label | ecdd1266-0f1d-5eb1-998c-4c5d39955ef8 |  | note | - - - - - - - - -
label | 608f739f-6a16-50ce-8f40-7c5ebd7d779a |  | note | Attach: Delivery Dockets
label | ed94180c-d565-5129-a322-29496ac50139 |  | note | - - - - - - - - -
label | b5d492e5-4517-5a78-8a0e-bca6597d7b26 |  | note | IP
label | 468768cc-8283-5240-9710-9a9e4fad768b |  | note | - - - - - - - - -
label | ab1752a5-a82a-55ef-bd6f-dd4e2265e2dc |  | note | Responsibility - Site Engineer
label | 43e997b7-180e-5b25-a9be-ed964972b240 |  | note | - - - - - - - - -
date | 1e085dcf-0ddf-5e63-bcce-8f1931ee7671 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 - Water
label | f0fd1998-84d2-563d-9820-23614c0bb050 |  | note | Frequency - Each Lot
label | 581f2f6e-5628-5494-903e-dac3d520d4bd |  | note | - - - - - - - - -
label | dc053589-c243-53e0-b7b0-18a6cb651731 |  | note | Acceptance Criteria - Except for the purpose of curing, no water shall be added to the cementitious treated material.
label | d7237664-b0d7-5b9d-9a87-5c8e0e7b4d4b |  | note | Water shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
label | 527a77cb-a8b4-5e35-aebe-c5ecec2fee08 |  | note | - - - - - - - - -
label | 7dfc2da2-36e3-5e36-8292-fd7bb97b5334 |  | note | Reference Documents - VicRoads Spec. Cl.306.06
label | 0a8d3214-aeff-5e88-a5d4-699f8c843fd4 |  | note | - - - - - - - - -
label | cb788fe3-2da8-5f33-a539-dff39729b801 |  | note | Inspection / Test Method - Site Inspection
label | c06353dd-7221-57ac-a96b-49332bf64d0b |  | note | - - - - - - - - -
label | 4e0788fd-4319-5487-807b-5cc26f7920d6 |  | note | Record of conformity - Signed ITP
label | bc289088-aa54-5190-a30e-c40b01e5e058 |  | note | - - - - - - - - -
label | 5baffb1d-f445-57e9-98ae-85257a0cd2d2 |  | note | IP
label | 156ffb30-20b7-5acf-a2e1-ff2eabb80139 |  | note | - - - - - - - - -
label | 8edcb614-c15b-5405-8e26-c89308e3975d |  | note | Responsibility - Site Engineer
label | b01e541e-a6d6-5812-8aaa-a1d94fdf8011 |  | note | - - - - - - - - -
date | dc0316b1-7f3e-55a3-8a96-dd596b5fe290 |  | date | Date Completed:
checkpoint-group |  |  | section | 3 - Testing Requirements
checkpoint-status |  |  | checkpoint | 3.1 - Determine Testing Scale
label | 23d33378-8747-5cb7-a7f0-a320a28dbe0a |  | note | Frequency - Prior to Testing
label | 3b9db9e7-cf9b-5d8c-8f0f-b9b1a5045ae6 |  | note | - - - - - - - - -
label | eec9ad79-973b-55e1-b732-ea5fc93c6b94 |  | note | Acceptance Criteria - Compaction Scale Required is Scale A.
label | 28a4b6c8-ba88-5c2d-9e10-3ce8465565f5 |  | note | - - - - - - - - -
label | 6b256164-9f44-5485-bd37-d3ee924b3d27 |  | note | Reference Documents - Project Specification Table 3040.064
label | 43a8febf-c79b-5dc2-89f0-fc5128dff7a5 |  | note | - - - - - - - - -
label | 4746e68f-4de2-5e3c-8078-ddbc33d12f88 |  | note | Inspection / Test Method - Document review
label | e46d9d40-eeba-535c-b084-8287a977918e |  | note | - - - - - - - - -
label | d717033d-4c60-5be0-8b17-c2a51f122bbb |  | note | Record of conformity - Signed ITP
label | a7847862-ab6f-538f-8b5e-c3cb61ed5a45 |  | note | - - - - - - - - -
label | e8455e35-cb9a-5de9-9ded-efba429db887 |  | note | IP
label | a2328fbd-cf87-596b-818d-235ecad28b7a |  | note | - - - - - - - - -
label | 9d1130a3-cab0-53ce-8bbb-a6964c4a82d6 |  | note | Responsibility - Site Engineer
label | 71e96480-2cf7-56ff-a811-ea91a97d9145 |  | note | - - - - - - - - -
date | 265ed30e-e772-5c19-925e-f24215da6727 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Compaction - Modified Compactive Effort & Moisture content
label | b047158e-d131-578c-961a-eb506600424f |  | note | Frequency - Six tests per lot
label | a358eb14-ed5e-5171-9eab-a2362882063f |  | note | - - - - - - - - -
label | 4e91358e-5e29-51a0-81df-6a2fe6670480 |  | note | Acceptance Criteria - Characteristic Value of MDD to be 96% or greater. Moisture content at the time of spreading and compaction, is within +0.5% and -1.0 % from the Modified optimum moisture content.
label | 98bc847f-9e5b-5f3e-8e58-5f454a98e106 |  | note | - - - - - - - - -
label | 7c2c0b89-871a-5a69-a853-1d25dd920930 |  | note | Reference Documents - VicRoads Specification Cl.306.09(a)(b)
label | d8eb48fa-8d4d-5aa4-bdf5-15afd1a19db3 |  | note | - - - - - - - - -
label | 66f1deee-5797-5fa0-8c6a-8d7fac392af8 |  | note | Inspection / Test Method - Document review
label | a0de5e3e-7459-5d7f-a514-d7ceb30c6f64 |  | note | - - - - - - - - -
label | 37dec858-9c5d-5fde-a335-74398447bce4 |  | note | Record of conformity - Test Records
label | e484110a-e6ec-5e92-98ab-ef66af203bfc |  | note | - - - - - - - - -
label | cacadad3-7db6-52b3-a632-8466468b3105 |  | note | IP
label | 77699f76-b589-58db-af15-0ed4dbfcd1b6 |  | note | - - - - - - - - -
label | e53cd810-62b0-56a0-b22e-66e61cb8408f |  | note | Responsibility - Site Engineer
label | 33ca8fc3-8056-53c2-b747-31a2a44f807a |  | note | - - - - - - - - -
date | 3016ed51-72f6-53eb-96f3-efb1e9293d01 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - Surface Shape
label | e620c06b-2f9f-59e9-8348-32aeb3276afe |  | note | Frequency - As required per Lot
label | 0209e21a-5ba2-51c1-ab3e-5c76f190db64 |  | note | - - - - - - - - -
label | 4f098c62-883b-5b83-8d84-c147a5265222 |  | note | Acceptance Criteria - No point on the surface of the cementitious subbase layer shall vary by more than 8 mm from a 3 metre straight edge placed in any direction. Water shall not pond on the surface of the cementitious treated subbase
label | c76724b0-5195-5edd-bc27-53db165c9de4 |  | note | - - - - - - - - -
label | 76c0bc97-3990-5b65-907d-6bc66dd6bfa6 |  | note | Reference Documents - VicRoads Specification Cl.306.03(c)
label | fda8ec90-ad58-538e-bb05-8195011a964d |  | note | - - - - - - - - -
label | f416a7e7-b986-595c-b912-8a50c6194b02 |  | note | Inspection / Test Method - Document review
label | d0da6c8b-298c-5399-b597-019727f3df54 |  | note | - - - - - - - - -
label | 10fefe55-ec97-5281-a8bb-da9c185851ab |  | note | Record of conformity - Straight Edge Verification records
label | f78d5df8-ef00-52e3-9c88-7cd972b7faaf |  | note | - - - - - - - - -
label | af669436-c34f-5751-98db-5aba17155c39 |  | note | IP
label | 38e9bc20-b82d-57cc-9846-7f157de373a1 |  | note | - - - - - - - - -
label | d68f3ea5-c4b1-5eb8-8856-dc9caf27f815 |  | note | Responsibility - Site Engineer
label | 5059747d-cfbe-5418-937f-a5dedb2cc23e |  | note | - - - - - - - - -
date | 8a24ca1c-7d16-5708-9de1-5d07bd4c1299 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 - Surface Level
label | 4ba229b1-2d23-52c1-8f38-650f41a0ad19 |  | note | Frequency - Minimum 80 measurements per lot
label | 0cc4df23-e5b1-53a5-9924-7e9691289d77 |  | note | - - - - - - - - -
label | aa14b904-c4ed-5029-a99e-5f59c8c4dec4 |  | note | Acceptance Criteria - Subgrade:
label | 3b87f67d-0fe9-501a-8767-d3af9557aca6 |  | note | – Mean value of all level readings to range between +5/-15
label | e0714f45-dc3d-5f91-b4f0-80844a966e30 |  | note | – Standard deviation of all level readings to be less than or equal to 12 Subbase:
label | 2cf88dbe-a5b2-5b50-9bd2-5edaa5efbef9 |  | note | – Mean value of all level readings to range between +4/-8
label | 7a21a937-c6fb-51e6-9348-b112e7772d64 |  | note | – Standard deviation of all level readings to be less than or equal to 8
label | 00e6218a-b9bd-5138-9af9-ab4394eb9e27 |  | note | - - - - - - - - -
label | 87091ac7-a0e4-5562-81ad-057b1e7114e4 |  | note | Reference Documents - VicRoads Specification Cl.306.03(b)
label | 302c1af2-579d-5d52-95d3-ca89983bf27e |  | note | Table 306.032
label | 77456773-a273-5219-ad05-1ddd69076c76 |  | note | - - - - - - - - -
label | 85fe6336-6a72-5e0f-9922-d490ca30bc3b |  | note | Inspection / Test Method - Document Review
label | ea491a3f-f654-53d0-939b-5c9c029274fa |  | note | - - - - - - - - -
label | c24aafe1-2325-5b57-bdba-7b7fc5e7ed4e |  | note | Record of conformity - Survey Report
label | 7ee0721e-99c7-5358-bf58-51a6cf986dad |  | note | - - - - - - - - -
label | 1327fe19-1feb-5074-8e38-f0de34243318 |  | note | SCP
label | b04d04a6-996f-519e-a178-67637b1d195d |  | note | - - - - - - - - -
label | 6b1e5cf6-6678-5c70-80d8-fe83bb665125 |  | note | Responsibility - Site Engineer
label | 9d2b2219-a5a7-534c-ab31-48f6fd0bba24 |  | note | - - - - - - - - -
date | dace130d-6ba0-525e-883e-f77ecf38fbf6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 52675fbb-32c5-501f-b6b7-6a424e1d6d3e |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | f4b4c88a-e455-5563-b2e7-a84f5736aa78 |  | textbox | Print Name:
text | d0caf819-8bd0-5428-b2d1-530b1f50fdca |  | textbox | Position:
date | d38541ee-eddc-5d1c-bb68-2e8e3fd56d08 |  | date | Date:
date | 03e27f14-69c8-5478-aba3-863857204d54 |  | date | Work Completed On
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification.
select | d488d0ee-f333-5607-97ce-cc815db009bd |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | ab7b874a-a8bb-5dba-a74b-66890ca37742 |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | 46b4b42d-7ac4-5277-b6b5-d0945324c58d |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | a74950b5-b278-5c5a-8d43-62279736e203 |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | fb415885-fe3d-5d3f-a605-56cf499d6f8d |  | textbox | Other:
select | cf79b46c-e917-5cb1-a7e0-f448066cd46d |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | 295e5b90-56f5-5fb1-84f1-de27ed676829 |  | date | Lot Closed On
text | 8400646f-5cad-5e22-ae6f-a8c494b8c249 |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-016-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0016 - Bored Pile Construction | 9108e340-54fc-4ea0-9d05-aae48b003723
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | 9470c89f-8288-5371-bcb1-683f831de732 |  | date | Lot Created On
date | 642b041e-0157-551c-a08a-cb409934a988 |  | date | Lot Opened On
date | 9998ef0e-9e72-5a72-a0bc-677a2b9959a1 |  | date | Work Commenced On
select | 12ec8372-6a75-5685-bb12-e183e3d78044 |  | dropdown | Lot Type | CIL - Civil Lot, DRL - Drainage Lot, EAL - Earthworks Lot, ELL - Electrical Lot, UTL - Utility Lot, STL - Structural Lot
text | e550ee93-79ed-5b79-8bab-0b8cd4868a1d |  | textbox | From and To Chainage
select | 31f8913a-3f74-5620-907d-8456be92353d |  | dropdown | Construction Element | FOUN - Foundation
select | f2d0346e-5955-5125-a72e-3a4b277c2ec7 |  | dropdown | Activity | BORP - Bored Pile
select | f8ef3c24-7922-5eb1-9786-e0ea4612fd4f |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | 2ccdb8ff-b78c-53cb-998d-ec0b1efdcf6f |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | 3846c1ea-84b4-5be6-b03b-4781f09edd41 |  | textbox | Engineer Responsible
text | f0209d0f-38cf-5919-bb6b-6d86430b4c7e |  | textbox | comments
checkpoint-group |  |  | section | 1 - Preliminary Works / Design and Submissions
checkpoint-status |  |  | checkpoint | 1.1 - Induction
label | dc69fe4f-2927-5eed-8d51-7ec415f5396e |  | note | Frequency: Prior to Commencing
label | 546ef0ee-6a87-54d8-8742-4aca166ce964 |  | note | - - - - - - - - -
label | f1b61500-e339-5670-8388-0510a63352ba |  | note | Acceptance Criteria: All personnel on site have been inducted to the CRG site
label | 4435852c-7dec-5a6f-ac3f-18889684eeeb |  | note | - - - - - - - - -
label | eab03875-3513-5a7c-81c1-656eed51c2bc |  | note | Reference Documents: Site Induction Register
label | 12f8a4e0-60db-5407-8f81-adfd0ac8f389 |  | note | - - - - - - - - -
label | 464774b7-3728-562f-ad52-915de1efd59e |  | note | Inspection / Test Method: Document review
label | 85c2150d-fca4-55a5-8625-9bb0ba429993 |  | note | - - - - - - - - -
label | 4db4a3e1-1c02-5fd5-9c19-0357445148bd |  | note | Record of conformity: Site induction signed.
label | 2eaa54a8-5f8a-51b1-a01c-cd5a3442ca8d |  | note | - - - - - - - - -
label | 36e7ceef-a7d9-5f3d-89ad-bac3901f5bfb |  | note | HP*
label | 70d992d5-ee26-53fd-ba6c-ccfb8ee3f3f2 |  | note | - - - - - - - - -
label | 91f92f57-ccfb-5520-9441-ea938a91a9a5 |  | note | Responsibility: Site Engineer / Site Foreman
checkpoint-status |  |  | checkpoint | 1.2 - Work pack briefing
label | e2bf3668-0eaa-568e-a04c-215beebcd696 |  | note | Frequency: Prior to Commencing
label | 709efc91-f573-55de-a2e1-ccbd954cb089 |  | note | - - - - - - - - -
label | dd6c3a0f-3bb5-5c24-91e0-45f04cb3ab58 |  | note | Acceptance Criteria: All personnel on site have been briefed on the relevant work park relating to scope of works.
label | ec8ce36e-5d9c-5239-b0fd-aa668220f2b8 |  | note | - - - - - - - - -
label | 8c67c823-8dc2-505d-a881-1533175fa5ee |  | note | Reference Documents: WP
label | 4079b96b-335a-5fd6-a651-4558958056bb |  | note | - - - - - - - - -
label | 86bbf4b0-f967-57d1-a07f-c468364fbadc |  | note | Inspection / Test Method: Document Review
label | 5d45ea71-3c56-53ad-b9bb-6519406b14db |  | note | - - - - - - - - -
label | d8b2d85c-1f9f-58e8-963b-48e9b699893c |  | note | Record of conformity: Work pack signed.
label | fa4cda53-42d2-54e3-8711-20b588c3f056 |  | note | - - - - - - - - -
label | 0e788b57-7a34-53c8-a59c-494bb5c2a0a1 |  | note | HP*
label | bd002e1e-4027-5218-bc01-7201e187a205 |  | note | - - - - - - - - -
label | d133ddd8-d685-52cb-b006-cab96c9a165a |  | note | Responsibility: Site Engineer / Site Foreman
checkpoint-status |  |  | checkpoint | 1.3 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken
label | 0d17df8a-f571-5bb1-8a70-204e5b6eb807 |  | note | Frequency: Prior to commencing
label | 471e360f-9c59-5fad-bdf3-d34b9c06c114 |  | note | - - - - - - - - -
label | 8f053ab6-297d-5362-8811-1e8f07912690 |  | note | Acceptance Criteria: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
label | a20c401c-8a10-5e8b-b2ff-e15a1e0252e9 |  | note | - - - - - - - - -
label | abb51c34-4bb0-58c6-9f5d-57e8c24ca803 |  | note | Reference Documents: Health and Safety Co-Ordination Plan
label | bf4f083e-2e7c-5142-85cb-c34813ee0f41 |  | note | - - - - - - - - -
label | bef0debc-5e3d-5889-a0b9-ae83255c2b21 |  | note | Inspection / Test Method: Document Review
label | a1c8baf4-9b50-566f-b2f7-390583387585 |  | note | - - - - - - - - -
label | 07d300fb-0032-5d29-b684-295c4066008d |  | note | Record of conformity: SWMS(s) signed
label | 2328a072-45d6-5230-a798-631dbe7c061f |  | note | - - - - - - - - -
label | eed284e8-b365-529d-8b7b-1b93c4a50d46 |  | note | HP*
label | b8d91945-eeda-5d44-b775-64ea3287f315 |  | note | - - - - - - - - -
label | 970f27ac-5043-503b-94c0-beff2bd85743 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 1.4 - Check that current revision drawings are being used
label | 0ede8ae8-41c2-54ac-abe4-8cf8a7441566 |  | note | Frequency: Prior to Commencing
label | f74e9451-f60c-5716-8356-81b28e494e94 |  | note | - - - - - - - - -
label | 6ae35365-7dcd-534c-bb49-773f8bad3476 |  | note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
label | 91d605c0-93ff-5770-acb1-2e6204b302cf |  | note | - - - - - - - - -
label | 95a584de-85aa-509c-a260-f600249878ea |  | note | Reference Documents: Project Drawings / Drawing Register
label | 65caa2cf-13f9-55fc-a8a2-f89a765f25b6 |  | note | - - - - - - - - -
label | d7290a81-77e0-556a-a305-447dbef70482 |  | note | Inspection / Test Method: Document review
label | adf4a7be-9fe9-51f0-a5e8-4e4e0c5b438c |  | note | - - - - - - - - -
label | 438d63b1-d219-5ba9-a15f-ddb1fd3be3e9 |  | note | Record of conformity: This ITP Signed
label | 2430e25d-8cf0-518a-a8be-6bad145fe9b2 |  | note | - - - - - - - - -
label | 215091e0-7eac-566c-b191-da795c695819 |  | note | HP*
label | a85f8c5d-e456-5c95-8c03-5b3081469d56 |  | note | - - - - - - - - -
label | 0a33f83f-f63d-513f-9950-9c416f647194 |  | note | Responsibility: Site Engineer / Site Foreman
checkpoint-status |  |  | checkpoint | 1.5 - Confirm understanding of current Environment Management Plan (CEMP) related to the work area and that all prescribed environmental controls are in place
label | 3565156c-2b01-58b5-811e-bfd40cf348fb |  | note | Frequency: Prior to Commencing
label | d246b354-638d-5930-8e53-4fd6065a4447 |  | note | - - - - - - - - -
label | 54e96d51-e68a-5361-81f7-83b23dedc0c5 |  | note | Acceptance Criteria: All personnel on site have been inducted and briefed on the requirements of the CEMP. All environmental measures including sediment and erosion control to be implemented as per current CEMP.
label | 081a5490-6950-5267-a3db-d684a4268add |  | note | - - - - - - - - -
label | 6c3249dd-e41b-5bb0-9f98-02ab572e8fad |  | note | Reference Documents: CEMP
label | 37c2cd52-dc35-5609-8511-659b61d106d8 |  | note | - - - - - - - - -
label | fd64fa9c-698c-528a-89b4-287d18ba2e9e |  | note | Inspection / Test Method: Document review & Site inspection
label | 2b520bae-7c22-5675-9ba3-8b2df072af29 |  | note | - - - - - - - - -
label | ae921873-9a52-5d22-bb6f-ebc173c30382 |  | note | Record of conformity: This ITP Signed
label | 78d1a428-9c11-52f5-a9e0-e82b71c713f4 |  | note | - - - - - - - - -
label | 322ec191-f0eb-51b5-9d49-e48e1d2ea3f9 |  | note | IP
label | 14bbe912-4f0b-59dd-a009-d297819e18ed |  | note | - - - - - - - - -
label | c93ca0e0-f102-5e37-a938-472a78979e42 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 1.6 - Excavation Permit issued
label | 1cad79ab-e91a-5649-bf8b-4cd06dd7d5a2 |  | note | Frequency: Prior to Commencing Work
label | 805fa348-940e-591e-ad20-1f6930bd3016 |  | note | - - - - - - - - -
label | e2966e24-8e32-5039-bf8b-1d7b427307a6 |  | note | Acceptance Criteria: Current Excavation Permit signed and specific for the area where works will be executed.
label | c8ba18fe-97ea-5f50-91a9-9eb9f21ebcea |  | note | - - - - - - - - -
label | ffe87a8d-1cc1-5158-9481-a53a31128a85 |  | note | Reference Documents: Excavation Permit
label | 5256c8c5-27db-56a6-9d4f-aaa958073ea1 |  | note | - - - - - - - - -
label | ca59627e-d940-586a-96fb-714db73b0ef7 |  | note | Inspection / Test Method: Document review & Site inspection
label | fa9f194a-b37c-562b-90fd-70d84c7ef7fe |  | note | - - - - - - - - -
label | 4105a8de-a570-5b90-811a-c65237af6438 |  | note | Record of conformity: Excavation Permit #
label | 49b55e7b-9e11-5e21-9014-9267007c5a17 |  | note | - - - - - - - - -
label | 52ad18d4-5669-544a-a8e7-e236fe110974 |  | note | HP*
label | 91ffc05c-0ab5-5880-92d8-74e247bfaf22 |  | note | - - - - - - - - -
label | 0118ac5f-79b5-51cb-b9a2-7d3b9f2500d2 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 1.7 - Traffic Management (When required)
label | c2315c35-c18e-511f-b9f7-e16be94d3145 |  | note | Frequency: Prior to Commencing Work
label | cb6cde1e-46a8-53fa-881e-fceda9a8295b |  | note | - - - - - - - - -
label | 45d91b6d-97e2-5733-a77a-48356e7fe343 |  | note | Acceptance Criteria: Approved WTMP and MOA
label | b8986edb-9aa4-5326-89cd-3ad316192350 |  | note | - - - - - - - - -
label | 01607292-3013-5d97-a44e-59d67cde8edd |  | note | Reference Documents: WTMP
label | 4a726a54-91be-59ec-8f5f-7025f5a6d7c3 |  | note | - - - - - - - - -
label | c7b2e3b3-f824-5a0c-b24d-b56d6ed5bef1 |  | note | Inspection / Test Method: Document review & Site inspection
label | 18805fbb-cb5a-5fbf-bde3-a8332d92010b |  | note | - - - - - - - - -
label | d29d69c1-d178-5fc1-92fa-a7fbafe693fb |  | note | Record of conformity: Superintendents Correspondence
label | 69269e86-cedc-50bf-87f4-38c2732029ce |  | note | - - - - - - - - -
label | 056dbe9b-8b46-5051-936c-8908d0e9aff3 |  | note | AP
label | 38b68378-500d-5ba3-b1ee-c7454c6bfa18 |  | note | - - - - - - - - -
label | 87dcee6d-1683-5680-980a-9112a3d53ca1 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 1.8 - Mix design
label | 5db029b9-90a7-55b1-a51d-891959eff701 |  | note | Frequency: No less than 4 weeks prior to commencement of activity
label | ce8460d1-96df-5ac6-9ba6-5a9fca5e7ebd |  | note | - - - - - - - - -
label | c6040e21-b134-5a0a-b4fa-62054c3dd902 |  | note | Acceptance Criteria: The concrete mix design details shall be submitted for review by the Superintendent not less than 4 weeks prior to the placement of concrete. Concrete shall not be placed until the mix design has been reviewed by the Superintendent, and allocated a registration number on the Register of VicRoads approved concrete mixes.
label | 081730bc-cdec-550a-83de-4a8355b6d652 |  | note | Concrete mix designs shall remain valid for 12 months from the date of registration, unless constituent materials and material proportions cease to comply with the specified requirements.
label | 47314ce1-3b1b-5520-881a-1f2a685d49b9 |  | note | - - - - - - - - -
label | ed853613-680e-5656-a58d-49414db82d46 |  | note | Reference Documents: VicRoads Spec. Cl.610.07(b)
label | 7e808f0b-ec4b-5384-b9ff-47e3edd49b81 |  | note | - - - - - - - - -
label | e1d6df09-ad4f-58a5-beb4-9969b40ce83d |  | note | Inspection / Test Method: Document review
label | 75967714-4e69-5d2d-8755-593e711d56ec |  | note | - - - - - - - - -
label | ce5b445d-1be6-5fbb-82ba-e95b6b142386 |  | note | Record of conformity: Approved Mix Design
label | 97f3afd8-c8fb-5d71-b70c-e8bac66af460 |  | note | Allocated registration number on the Register of VicRoads approved concrete mixes.
label | 036d8780-4bae-5f3a-9ab3-09781b7b381a |  | note | - - - - - - - - -
label | 509adcc5-020c-5ec5-bd6d-f31b3a9a419a |  | note | HP
label | 9166c39a-bd9b-59b0-896f-6de848f0a079 |  | note | - - - - - - - - -
label | 0f765674-b610-575d-a5f0-235a1bda3089 |  | note | Responsibility: Project Engineer & Superintendent
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.9 - Steel Reinforcement
label | 8760f045-22d1-51b7-b37a-7918d243452c |  | note | Frequency: Prior to commencing works and no more than 14 days after contract award
label | d50d0ecb-6a10-50b3-824b-fc3653d9b588 |  | note | - - - - - - - - -
label | 5caac51b-ffce-54bc-ba62-d57d53f3f0de |  | note | Acceptance Criteria: Steel reinforcement shall comply with the requirements of Section 611. Unless otherwise shown on drawings, bars shall be grade 500N. Allowances should be made when preparing the steel reinforcement schedule to achieve the specified tolerances on member dimensions, concrete cover and location of steel reinforcement
label | 2b83a8a7-e66d-5a5d-a14a-310157dfcd1e |  | note | Manufacturer of steel reinforcement materials must be in possession of a current certificate of approval, issued by the Australian Certification Authority for Reinforcing Steel (ACRS). Evidence of compliance with this clause shall be submitted to the superintendent within 14 days of award of the contract.
label | e9c3ef22-74a7-5ebb-a279-d80ed321a50d |  | note | - - - - - - - - -
label | 8b737217-1580-5cdc-b7aa-ecff1562a411 |  | note | Reference Documents: VicRoads Spec.
label | ed129e50-de4b-5560-90d8-db3e4624652b |  | note | Cl.611.03(a)
label | cb32f037-c6d1-540e-97f2-33e73f8bc339 |  | note | Cl.611.04
label | bc2a973c-9c74-5e97-b69a-28efc47a03d7 |  | note | Cl611.05(a)
label | 4cf3e100-858a-5a34-b25d-1afef9dd8b1f |  | note | - - - - - - - - -
label | a572644b-51ad-5c39-b6d6-35e310fce6c5 |  | note | Inspection / Test Method: Document Review
label | f100962a-c1be-540b-8fe2-66da61097ee4 |  | note | - - - - - - - - -
label | bc3eedf4-1a9b-5f0c-ad72-e2294754a9c7 |  | note | Record of conformity: Submitted Product Details
label | db42bf53-e325-55ea-b252-0e2f3687815f |  | note | - - - - - - - - -
label | c3daefeb-a9cd-530d-802a-62c6f6d35949 |  | note | HP*
label | d0da58fa-7b44-5298-8197-11eccc44940c |  | note | - - - - - - - - -
label | d2c4e37a-04fd-559c-9c5c-e3ce23fcc0e7 |  | note | Responsibility: Project Engineer
checkpoint-status |  |  | checkpoint | 1.10 - Quality Procedure for pile construction
label | 37900ba0-6733-526b-8063-32b495a71fb5 |  | note | Frequency: No less than 4 weeks prior to commencement of activity
label | 9f3bc1bc-349d-55cb-93e9-67b69aaf0fef |  | note | - - - - - - - - -
label | 61c0c34c-9319-59d5-9b90-9c84a9017365 |  | note | Acceptance Criteria: A quality procedure for the construction of the piles shall be submitted to the Superintendent not less than 4 weeks prior to the commencement of the piling works. Piling works shall not take place until the quality procedure has been reviewed and approved by the Superintendent.
label | e1fd79df-61cb-5ead-8296-0789981158c1 |  | note | Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials, and the method of placement of concrete under water has been reviewed by the Superintendent.
label | d1c9bb0a-95f1-5acf-9d68-38ece63a8be9 |  | note | The Contractor shall submit the procedure for placing concrete in bored piles, under water and in dry bores, for review by the Superintendent at least four weeks prior to concreting.
label | 25162713-fab6-541a-9fcb-8a2e939610f4 |  | note | Concrete shall not be placed in bored piles, under water or in a dry bore until the proposed method of placement of concrete has been approved by the Superintendent.
label | 60996b58-aa90-5f84-a4b8-3ef8082838fd |  | note | - - - - - - - - -
label | 0eecb4e4-73e6-5869-8815-a8901e224b71 |  | note | Reference Documents: VicRoads Spec.
label | 8b5ba7a5-7ca9-5221-8cf8-fdecd2db413c |  | note | Cl.606.03(a)
label | a495e896-c927-5ced-a633-f4c6102fdaad |  | note | Cl.606.06(a)
label | 56fedf67-d6b7-5a95-8060-7d42093ca7a3 |  | note | Cl.610.18(c)
label | d4ad183f-321e-50c2-a455-edb15d4996b6 |  | note | - - - - - - - - -
label | 4ac9ed43-adbf-5e2e-9818-f043126a7021 |  | note | Inspection / Test Method: Document review
label | c166fa39-686c-589c-ac1f-f36f993c2add |  | note | - - - - - - - - -
label | da27afa4-738d-5a16-b046-3867d70bd2de |  | note | Record of conformity: Approval of Quality Procedure for piles construction
label | 87764a5c-03f3-5360-9e19-3835e8d486a0 |  | note | Procedure for placing concrete reviewed
label | 454c0299-1cc2-5fb0-bc0b-c74c4cea6757 |  | note | - - - - - - - - -
label | 97056944-6329-5258-bcb3-79b4a6864413 |  | note | HP
label | 61a78550-bcd0-5d5a-a18b-09159f18f25c |  | note | - - - - - - - - -
label | 9a08f5cf-acfc-52f3-bd1a-c302f1f8e7aa |  | note | Responsibility: Project Engineer & Superintendent
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Boring
checkpoint-status |  |  | checkpoint | 2.1 - Survey set-out
label | 1db36842-bbb3-52b9-aebf-596819d6c4ba |  | note | Frequency: Prior to Commencing
label | 561f1fec-d63c-5ea1-8353-0718c6f161e6 |  | note | - - - - - - - - -
label | 297c1af8-49c3-5093-a6db-a4e00056a155 |  | note | Acceptance Criteria: Survey to ensure and validate that all works meet level and location requirements. Review of existing survey control marks and any additional control marks required for the works. The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity.
label | 22dc564d-223c-5524-bff4-a281c21b7a24 |  | note | - - - - - - - - -
label | 7fc2ee7c-4b98-5630-bfba-db682ce14249 |  | note | Reference Documents: Project Spec. Cl.1190.06
label | b7482430-4235-504b-b8d6-fe5c22e4c6e1 |  | note | Latest IFC Drawings
label | ef11b993-0904-594c-b33a-f0bec25b8fe0 |  | note | - - - - - - - - -
label | eb20934f-0bd4-5713-ac6d-e7f2a48ca045 |  | note | Inspection / Test Method: Site Inspection
label | e46ab6fc-881d-5a1c-82d2-ba9da906bf1a |  | note | - - - - - - - - -
label | 948d9211-c5a4-5851-be2a-f055dd44d47c |  | note | Record of conformity: This ITP Signed, Survey Records
label | 44b40d6b-4c51-51bb-b59b-3de8701c6c52 |  | note | - - - - - - - - -
label | 6d25bc8a-4243-5cbf-9fbe-4fd669d07c02 |  | note | SCP
label | b19f6c5b-18d9-5202-be9e-4d3137c79940 |  | note | - - - - - - - - -
label | 360396a4-45bd-549c-b2b4-0acbada73083 |  | note | Responsibility: Site Engineer & Surveyor
checkpoint-status |  |  | checkpoint | 2.2 - Protection of Adjacent Piles
label | ad2b878a-c8cb-5892-9850-4070c8f80a6c |  | note | Frequency: Prior to Commencing
label | b51a96c1-e25f-5dcf-93f3-8e225e86bdd9 |  | note | - - - - - - - - -
label | 21ede96c-49ab-58f8-94d7-fbd095f2550d |  | note | Acceptance Criteria: No pile shall be commenced within 2.5m clear distance of a newly cast pile until the concrete in the pile has attained a strength of 15MPa
label | a367bfe2-b23b-562f-88ea-d835336d5ceb |  | note | - - - - - - - - -
label | 58568ba9-856f-56d2-8093-ef629f734feb |  | note | Reference Documents: VicRoads Spec. Cl.606.04
label | 26cda1ef-c36c-5a45-88ef-879ec7a143ef |  | note | - - - - - - - - -
label | 30bdc91f-0291-5199-8126-1ec6d2de5a21 |  | note | Inspection / Test Method: Visual Inspection
label | c51c45be-53a0-539a-92a3-430f3819d003 |  | note | - - - - - - - - -
label | 44c6eb2c-32a9-5e57-8d75-209559bebbb7 |  | note | Record of conformity: This ITP Signed, Bored Pile Checklist
label | 3f49e86a-c697-5f70-b283-245be59b184a |  | note | - - - - - - - - -
label | f0b06174-5229-5698-94fb-cfcabfc0da80 |  | note | IP
label | 97ac4019-3f7c-52f9-9142-a6115c562b33 |  | note | - - - - - - - - -
label | 2fe0a2e4-31a4-5d9a-8a07-28a9da34de4e |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 2.3 - Excavation levels
label | 1427bcf4-a3e8-55a9-9ccc-c0450050055a |  | note | Frequency: Each pile
label | b77095f1-bb23-5b14-979c-d7f1f12eb932 |  | note | - - - - - - - - -
label | badb2844-513c-5547-93d0-46acff5ecd15 |  | note | Acceptance Criteria: Check the toe levels conform to the drawing.
label | 1a73db28-b9aa-5593-8758-8faa4997846f |  | note | - - - - - - - - -
label | c01ad651-0700-544d-9ea2-81c6d5148e44 |  | note | Reference Documents: Latest IFC Drawings
label | 0f47431a-d33a-5ecf-bd81-296275e4f25f |  | note | - - - - - - - - -
label | 67f44378-500e-536e-b670-66340d4a15f7 |  | note | Inspection / Test Method: Document review
label | a8f2139e-8740-5ec6-add8-04c5b40ed96f |  | note | - - - - - - - - -
label | 0a8d6d3d-d9df-59cf-9d03-edd2f23d1445 |  | note | Record of conformity: Bored Pile Checklist CRG-FH-CL-0006
label | b6565bd5-5261-5e17-aac8-0a80344c2e03 |  | note | - - - - - - - - -
label | add65dda-0edb-51bb-a9a0-128f09fa76eb |  | note | IP
label | 11e6dc20-a937-5753-80d4-1ab7374d0883 |  | note | - - - - - - - - -
label | d151b7db-539d-56e6-bb56-980308677057 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 2.4 - Inspection of Pile Excavation
label | ef06541f-c89c-5e2e-9058-fa64a76fbe37 |  | note | Frequency: Each Pile, a minimum of 48 hrs notice given to the Superintendent for arrangement of the inspection of the pile excavation
label | 4c00fb4c-af34-5d97-8d4e-9d786fcdced1 |  | note | - - - - - - - - -
label | bbb75e95-6d19-59ff-bd0a-38ab2d0b3dff |  | note | Acceptance Criteria: The temporary casing (where used) shall not be removed, nor shall reinforcement and/or concrete be placed until the pile walls and base have been inspected by the Superintendent and that the inspection has confirmed that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
label | a13a6798-f9cc-5013-9711-911d0461f8d7 |  | note | - - - - - - - - -
label | 32ff3fc2-0e01-5324-b555-fd8e009d0269 |  | note | Reference Documents: VicRoads Spec. Cl.606.05
label | cf35167b-a27b-5b4a-92d4-b6d7923d7c8a |  | note | - - - - - - - - -
label | ccadedbd-005f-5a2b-a2ec-81586a1b5e97 |  | note | Inspection / Test Method: Site Inspection
label | faae29fd-4ef6-5470-861c-cc49bf0a8de2 |  | note | - - - - - - - - -
label | ffb1a42d-9db7-5461-95f4-8c2da595590c |  | note | Record of conformity: Pile walls and base inspected by Superintendent, This ITP signed off
label | c353748b-027b-5ecd-9193-789f0eb657de |  | note | - - - - - - - - -
label | 4757d796-adf2-5fdb-a413-a0f04283cdab |  | note | HP
label | 2a695df7-df6d-5978-89e6-402cd368d0de |  | note | - - - - - - - - -
label | 12f1e87a-17f2-5da1-ab3e-7439ad6310fb |  | note | Responsibility: Site Engineer & Superintendent
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Check reinforcement cages
label | ff8ac8fe-aa09-51a0-a39e-e99794441153 |  | note | Frequency: Each pile
label | 7ed39972-f216-55ab-b754-3a57da584468 |  | note | - - - - - - - - -
label | 2e732604-e0f7-535c-8d66-fc0ff08c6fa1 |  | note | Acceptance Criteria: Steel Reinforcement shall be securely held during placing and compacting of concrete. Steel reinforcements shall be made of concrete blocks of a strength similar to the structure, strong enough to withstand the imposed loads without movement of the steel reinforcement. No other materials to be used as supports.
label | 29b21273-08b7-5b07-822f-eb546563c488 |  | note | Spacers and supports for bored pile steel reinforcement shall be placed at intervals of no more than 2 m along the full length of the steel reinforcement cage to ensure that the specified concrete cover to the steel reinforcement is maintained.
label | 27c15f21-f271-51d0-a26e-199790b2f0a9 |  | note | Reinforcement as per drawings and specification.
label | b4095342-a73b-59ce-8b52-338ff7348953 |  | note | - - - - - - - - -
label | 7d1f9fa7-fe47-5c37-b5bc-392757cec9d1 |  | note | Reference Documents: VicRoads Spec.
label | 58341619-e143-595f-bcb7-088f5ea8a29b |  | note | Cl.606.06(a)
label | 08969adc-ed36-5b02-9b88-ed311a36a777 |  | note | Cl.611.03(a)
label | 05626b6a-36ee-591d-9775-5732e6c21df3 |  | note | Cl.611.04
label | 5883311c-b580-59e9-ab95-bcdde058d994 |  | note | Cl.611.10
label | 65bc8271-fab1-57d5-abbf-5f3df13fedfc |  | note | Project Specification
label | 257e00f1-7c29-5138-91a3-cfe617366d99 |  | note | - - - - - - - - -
label | 131b7bad-beb1-50e8-9951-8a825f0f7b86 |  | note | Inspection / Test Method: Site Inspection
label | 56db9ee1-7394-5394-a621-0c9c5b12d47c |  | note | - - - - - - - - -
label | 3b2c186c-fa25-5a23-aa51-29fbcef2c316 |  | note | Record of conformity: Bored Pile Checklist CRU-FH-CL-0006
label | 1f909e03-d4f7-521f-84d3-a322bd18da0e |  | note | - - - - - - - - -
label | e852542a-d4d3-551f-9359-47bb34573c00 |  | note | IP
label | 00241a2c-795b-553a-9891-453f27d17c60 |  | note | - - - - - - - - -
label | ba06da14-3926-584f-970f-288efad5a80a |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 2.6 - Pre – pour checklist
label | fb03d168-2f7b-57ac-a92a-e708ef478a64 |  | note | Frequency: Each pile
label | 9a0d71e5-83f6-5222-ae00-930e28159e59 |  | note | - - - - - - - - -
label | 7033f7bd-e240-5ada-8f3d-88961fe58d8b |  | note | Acceptance Criteria: Bored Pile Checklist completed and signed.
label | 1e17b4f1-d0ba-5b55-8a3a-b16c5c59f072 |  | note | - - - - - - - - -
label | 243add8b-d467-5927-9e29-29f976ba1164 |  | note | Reference Documents: Work Pack
label | c3b7ac3c-5f11-5931-a462-2422d9024c26 |  | note | - - - - - - - - -
label | f4b367e0-57ee-54ad-b29b-7ae550a4b835 |  | note | Inspection / Test Method: Site Inspection
label | 9a8cdcf4-0066-5bf9-be34-7a8e8124d2fe |  | note | - - - - - - - - -
label | d68beebd-3901-5587-bac1-c3a4a30257ef |  | note | Record of conformity: Bored Pile Checklist CRG-FH-CL-0006
label | 848559a5-062d-55da-91d4-9ef9c6bd0609 |  | note | - - - - - - - - -
label | 152998f5-22d6-57f3-8fff-778efb209c4e |  | note | HP*
label | 9357f3d9-f5be-56f7-911d-9deec9c57c69 |  | note | - - - - - - - - -
label | 1e6b5755-6fe2-5f1c-9430-0892b56bcc56 |  | note | Responsibility: Site Engineer
checkpoint-group |  |  | section | 3 - Placing and Finishing Concrete
checkpoint-status |  |  | checkpoint | 3.1 - Carry out sampling of concrete
label | 2640fc8d-ad46-5ef4-b9a2-805a3607c7f0 |  | note | Frequency: As per table 610.161
label | d8899796-4d05-5bd9-8662-099bb48010bd |  | note | - - - - - - - - -
label | 3764827a-d37f-53d3-84e5-35bcff2bf404 |  | note | Acceptance Criteria: Slump flow: 550-800mm spread
label | a2cc4788-c9e2-55f2-b6d4-2c01f31afa66 |  | note | T500 time: Achieve a spread of 500 mm within 1 to 5 seconds
label | a98e051f-7637-5982-8c45-71520f3e922c |  | note | Passing ability ≤ 10 mm.
label | be033ebf-79e9-5926-aee0-a965b0be13dd |  | note | Observations as per Table 610.131 of VicRoads Spec.
label | ecb60699-cff4-5959-a7c3-2608e046efd9 |  | note | – Three cylinders taken from the same sample used to test. 1 cylinder crushed at 7 days. 2 cylinders crushed at 28 days
label | 00e77687-db2c-549b-b718-e435f8ad3ccf |  | note | – Number of samples taken shall be as per Table 610.161
label | b45dd9c2-5956-56a4-9b13-d4743a5daf60 |  | note | - - - - - - - - -
label | 7cd4f508-0136-5627-aaef-47b1a1a21bd4 |  | note | Reference Documents: VicRoads Spec.
label | 65e70041-db43-53c3-bfd8-90f680dd9453 |  | note | Cl.610.13(b)
label | 0511e752-325c-5b1b-8a44-6c8b0af76a17 |  | note | Cl.610.16(b)
label | c3755d10-3e94-5ecf-ab0e-b68978363771 |  | note | Cl.610.16(n)
label | 1f239f5a-cd48-51ac-9275-727a306c3e3a |  | note | Table 610.131
label | aa27702a-b2ae-50e0-a1da-8531fd4006ce |  | note | Table 610.161
label | 311af692-3241-5dd1-861a-4a0ea19c7f05 |  | note | - - - - - - - - -
label | 5eddfd14-e30b-57a7-ae3b-7372651d3e52 |  | note | Inspection / Test Method: Site Inspection, Site Sampling
label | aed563df-f070-5c8a-8ab3-249c6edf168b |  | note | - - - - - - - - -
label | eb261bd8-fc63-54ec-aaf3-0a1b726865e6 |  | note | Record of conformity: Concrete Pour Record CRG-FH-CL-0003 and Bored Pile Checklist CRG-FH-CL-0006 completed
label | e48fe400-c5de-5d0c-b5bd-37a7a2f1cfe7 |  | note | - - - - - - - - -
label | 311913b6-7908-5049-abc1-3a7114553bc6 |  | note | IP
label | 83fe8081-761e-5af2-ae74-81a794f5d628 |  | note | - - - - - - - - -
label | 43889e52-4f08-54bb-8ec9-8cdbcfba85bb |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3.2 - Place Concrete
label | 77fc28f5-9241-5ade-ab57-04597bfa93c8 |  | note | Frequency: Each Concrete pour
label | 9eb8204c-870b-5fdb-9666-1d45f6b57c6d |  | note | - - - - - - - - -
label | 43367c1c-0430-5cbf-9503-c4ef0b4ec365 |  | note | Acceptance Criteria: Piles shall be concreted within 24 hours of completion of the pile excavation.
label | 47482bb5-0449-5bf7-a4ce-8de934cf1c0d |  | note | Discharge time between truckloads for the same cast to be <45 mins.
label | d5d7e730-81f0-50e7-a5e6-1a5ef9189e5b |  | note | All concrete to be placed within 60 minutes from batch or as specified in the approved VR mix.
label | b6d0cc60-8a6e-58fc-9e7b-ee5c73eefdc7 |  | note | Each batch (truckload) of concrete delivered to site shall be visually inspected to ensure consistency of concrete supply, and the estimated slump shall be recorded on the identification certificate for the batch.
label | 5058f583-0fd2-57d6-9d05-b82829d127e6 |  | note | Piles places in the dry shall be constructed to a minimum of 300mm above pile cut-off level to allow breaking back of contaminated concrete at the top of the pile.
label | a72e7a27-9a3c-540d-98a0-b08fae3a0b19 |  | note | - - - - - - - - -
label | ff010d12-0a29-50d2-9cb5-57fe754d3efe |  | note | Reference Documents: VicRoads Spec.
label | 95168c98-fdc6-5a57-a114-8192b4d502ac |  | note | Cl.610.16(b)
label | b624940d-5378-5e2a-a2fa-966327e56149 |  | note | Cl.610.16(c)
label | 0c6f866f-0e20-5b93-b5ba-a1690dc0c3fb |  | note | Cl.610.13(f)
label | e501454e-7d42-524e-948b-da56210241c4 |  | note | CL.606.06(a)
label | 7a2bb556-7e7a-5454-83a4-c367449938c6 |  | note | - - - - - - - - -
label | 12dbb0e5-a7ab-5b5c-ae75-c8e6808ff72c |  | note | Inspection / Test Method: Site Inspection
label | 926b0303-194f-5a65-bc7b-1fec1efa4d83 |  | note | - - - - - - - - -
label | 76ff800c-4d98-597b-8d8f-c86b52806f52 |  | note | Record of conformity: Concrete Pour Record, Bored Pile Checklist, Concrete dockets
label | 51ec21f7-0115-5df5-a278-1d3a8ab5b4b0 |  | note | - - - - - - - - -
label | 1db71b52-8568-5f93-af68-591c813e4669 |  | note | IP
label | c5bfe90e-ab58-58e4-b533-808fcbff8b22 |  | note | - - - - - - - - -
label | 058e23e7-13d0-5180-a949-2228d552906e |  | note | Responsibility: Site Engineer
checkpoint-group |  |  | section | 4 - Testing Requirements
checkpoint-status |  |  | checkpoint | 4.1 - Pile Testing
label | 90afd58c-2796-5dac-9128-6a02c59d76d2 |  | note | Frequency: Representative Sample determined in consultation with the Superintendent.
label | 26407198-f350-5b30-8e57-de0ff0dd530c |  | note | - - - - - - - - -
label | 0916b162-96d6-5142-a1ed-1657f9044cb7 |  | note | Acceptance Criteria: Unless dispensation is granted, a representative sample of piles shall be tested by a consultant prequalified to VicRoads as per the requirements of Section 606.07 including:
label | 9819a897-4ef2-530b-a213-6aa688966cef |  | note | (A) Integrity Testing - First 6 piles constructed, then 1 in 3 remaining.
label | 87061f52-ce26-52f0-8a63-7273412986fb |  | note | (B) Static Load Testing
label | a5022319-1f37-552f-9705-c389bf10e831 |  | note | (C) Dynamic Load Testing - 1 in 10 Piles with a pile depth within 2m.
label | 52a887d7-4907-5cb8-8160-528d86629db7 |  | note | Results including raw data are to be provided to the superintendent per the timeframes requested but no less than 48 hours after collection of results.
label | b3df06f3-6c74-51a2-a208-1adb808312b3 |  | note | - - - - - - - - -
label | f6f4db33-03ad-575d-84d3-02cd0f423588 |  | note | Reference Documents: Project Spec. Cl.3050.07
label | 987c56cc-e359-5293-96e4-fc1b6639a1a4 |  | note | VicRoads Spec. Cl.606.07
label | 06b7ba9e-a03c-5573-ba49-218d00238df4 |  | note | - - - - - - - - -
label | 13260bef-63d2-5e9c-8ce6-c4f4b271a88f |  | note | Inspection / Test Method: Test report
label | 8defc519-e8e7-5516-a81e-7b768e75bfe8 |  | note | - - - - - - - - -
label | d71aec36-c383-5b4c-9ee2-ee9ea5bb3662 |  | note | Record of conformity: Test reports provided to Superintendent, This ITP signed off
label | a2b12f86-88de-527e-9d19-b3bc7f467c7c |  | note | - - - - - - - - -
label | 35dd8d3d-c0de-58f0-aaf8-3c45f0be1e1d |  | note | HP
label | 4747dd63-8c11-58f7-9bb5-47d3bf7d0495 |  | note | - - - - - - - - -
label | 59fffdb8-baf2-5814-beac-47d82f1cfb09 |  | note | Responsibility: Site Engineer / Superintendent
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Concrete Test Results
label | f9bb735c-bad8-5c47-9a68-b1d0a81421c5 |  | note | Frequency: Each sample
label | ef0a6bd1-b951-5070-9d43-d23e81ee6ae0 |  | note | - - - - - - - - -
label | a90aa11d-9193-565c-b7b5-ef8961f67807 |  | note | Acceptance Criteria: Minimum 7 day strength (26MPa) achieved as per table 610.051
label | 997f5f98-d548-50d8-bacf-12acd2bcebea |  | note | Minimum 28 strength (40MPa) achieved
label | d833dcd7-59f1-58ff-9a58-ac9b3e8c5cef |  | note | Strength average of tested cylinders
label | a88a7b02-90a5-5cb2-a0bc-40ba7f43f87a |  | note | - - - - - - - - -
label | e47dad48-81ea-5a63-952d-ab2f2cce00eb |  | note | Reference Documents: VicRoads Spec. Cl.610.05
label | 93e9e68b-2a80-5672-80b2-a8e17a868ec9 |  | note | Table 610.051
label | 79ce608e-c6d8-5b91-8881-2c9017ce017b |  | note | - - - - - - - - -
label | 84d1b5e5-aa81-50f6-88e0-9f3e8759ab5c |  | note | Inspection / Test Method: Test report
label | 026aba0d-79f2-5118-9557-27bc55409c92 |  | note | - - - - - - - - -
label | 502044a7-43ba-5f62-8aae-021610141924 |  | note | Record of conformity: Compressive Strength (MPa) Test report, This ITP signed off
label | 795608bb-6114-5b2b-ab9c-1d2ba9253498 |  | note | - - - - - - - - -
label | 032ecffb-7933-51a7-917c-f82272e43070 |  | note | TP
label | e1d9a134-8253-5553-8e93-7ff9b2dead39 |  | note | - - - - - - - - -
label | 4a5d2424-a073-5f9c-95b8-1201fecd869e |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 4.3 - Tolerance Check & As Built survey
label | b38a540e-7fd8-5717-9124-3cc71dcf10a9 |  | note | Frequency: Each pile
label | a26a08a0-6eb2-5158-92a7-51153a24f360 |  | note | - - - - - - - - -
label | 4f232d64-f5b9-5448-b1de-a73e8acb6e68 |  | note | Acceptance Criteria: Check Tolerances & Survey Pile positions:
label | fb0f564d-62b3-5b89-a70d-81b5cadbcc43 |  | note | (a) pile head shall finish within 75 mm of the specified plan position;
label | 1ca6c4a3-3f81-5d25-8c12-8b1a8a8bf188 |  | note | (b) variation from the vertical or the specified batter/rake shall not be more than 1 in 100;
label | e1c9024f-67c7-58b2-a418-0a0ab00ec70e |  | note | (c) where piling excavation has developed a curve or out of verticality, the offset from the theoretical straight pile line shall not exceed 150 mm over a length of 15 metres or proportionally for greater or shorter lengths.
label | 0a947ec8-285c-5484-b32d-f5cb1a60645f |  | note | Mark all details correctly on as-builts
label | 269a4553-36c4-57a0-afd2-933b6b51cf5b |  | note | Pile head position & verticality
label | 1f3f8ac2-c4b5-55c9-8f4b-7137d0375fad |  | note | - - - - - - - - -
label | 49233f8a-96bd-5449-80e4-bd087f8bd99b |  | note | Reference Documents: VicRoads Spec. Cl.606.08
label | 5b6394c3-972d-5997-81b0-afec95a17647 |  | note | - - - - - - - - -
label | 81d8e4de-ce47-5ef4-a127-767ed9d452c9 |  | note | Inspection / Test Method: Site Inspection/ Document review
label | 5752dcfe-d0cd-5f69-9c96-3380037eb99a |  | note | - - - - - - - - -
label | 8220fd79-bac2-55bc-8140-60875f268d82 |  | note | Record of conformity: Survey report
label | 76f37e8d-82e0-56f4-96c4-51a57d8fb011 |  | note | - - - - - - - - -
label | 471b52a6-b692-51cf-93a1-6945e880622c |  | note | SCP
label | 2718d159-4051-5f6c-a2c6-0e5cf1522d57 |  | note | - - - - - - - - -
label | c3f332ae-0bc5-5499-849e-cece8e36239f |  | note | Responsibility: Site Engineer & Surveyor
checkpoint-status |  |  | checkpoint | Final Inspection
label | e50d0a3b-6add-5660-8ae9-4102d62653e3 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 9d21d895-fb67-5207-b007-29b80aa302c7 |  | textbox | Print Name:
text | 50281eba-042b-5735-aa61-49db8ae03025 |  | textbox | Position:
date | 4e5118f5-cfde-5f72-aa9a-e5a58b82b817 |  | date | Date:
date | 20df2447-f5e0-593c-8dbe-28c6f98b617e |  | date | Work Completed On
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification.
select | f7ed7d43-9069-5851-ba3c-3349174fa4f6 |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | 78862ab0-0b37-5a0c-ad92-4c57a2b242ef |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | 2133f34e-e893-598f-89fe-32f05947295c |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | 3b667f51-52c9-5882-9a75-0de5d51a1b0a |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | 403e1251-debc-5862-ac0c-612eeb026ab6 |  | textbox | Other:
select | 5a52d94a-31ee-59dd-bf85-b26f8cc6f2a5 |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | fad37994-e3ae-5faf-9ce1-b0e18acfecc3 |  | date | Lot Closed On
text | 41561548-5a78-5c59-81d3-9843a73631ee |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-075-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0075 - Asphalt Placement | 9fb03d06-6160-4b7b-a83b-cfefade42822
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | 7259c212-4d32-53f7-8b08-fc26aa673693 |  | date | Lot Created On
date | 13daca31-3160-5100-87f1-851c69bfd3db |  | date | Lot Opened On
date | 40d6ece3-6d12-5132-9f2e-ca455aab5046 |  | date | Work Commenced On
select | 0eae25c0-5c9d-5301-860f-c7afdb3cbc43 |  | dropdown | Lot Type | CIL-Civil Lot, DRL- Drainage Lot, EAL- Earthworks Lot, ELL- Electrical Lot, UTL- Utility Lot, STL- Structural Lot
text | 5568eb93-9e50-5343-a89d-aa8d226645fe |  | textbox | From and To Chainage
select | 24c1f5fa-3e57-5c15-8e99-6062858d4176 |  | dropdown | Construction Element | PAVE - Pavement, SURF - Surfacing
select | 5add4aee-e12f-507d-beea-b6768e129f12 |  | dropdown | Activity | BASA - Base - Asphalt, INAS - Intermediate - Asphalt, ASWC - Asphalt Wearing Course
select | 1d70a2fa-872a-5404-b434-b3731b89aa26 |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | b9a3d81d-81bc-5bbd-ac31-7583e1aced08 |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | dcf21f33-880e-5979-adf9-8c4dafb84f95 |  | textbox | Engineer Responsible
text | f5f189e3-ce03-5c0a-81c4-dd58550d4029 |  | textbox | comments
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 Submission of Mix Design
label | 1b7bc405-ec7f-5a15-bdf4-c8e465bc2bd6 |  | note | Frequency: Prior to commencing paving
label | 99809eb4-8047-5bdb-a5d3-682ab1547ea5 |  | note | - - - - - - - - -
label | 836e698f-4948-5b83-bd66-b026aa4a63e5 |  | note | Acceptance Criteria: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
label | f5703050-e7ff-56ef-9e8c-60f52658c998 |  | note | - - - - - - - - -
label | a53eb7df-03ae-5117-bbad-c5b2bb99c4e6 |  | note | Reference Documents: VicRoads Spec. Cl.407.06
label | b0aed64d-18eb-5168-82ac-3b9f95efa441 |  | note | - - - - - - - - -
label | 4f2d2ac6-a6ac-5e87-9329-c35df229f7ea |  | note | Inspection / Test Method: Correspondence of receipt of mix design
label | d91ff0d5-2a67-50ef-9ada-a19b82f4fea6 |  | note | - - - - - - - - -
label | 316cc0c1-bd97-5e01-a4eb-eeb5b1dce1cb |  | note | Record of Conformity: VR approval Completed ITP
label | 97eec926-02ce-5d3d-9bf5-0d66a24d2f7e |  | note | - - - - - - - - -
label | d673e282-1c3c-50fe-af56-0cfddd3a150a |  | note | HP
label | 874039e7-8b76-554c-8d7c-e0fbd4d52f83 |  | note | - - - - - - - - -
text | bfc2a3b0-d3f2-56ac-90de-be62cb2b6a77 |  | textbox | Responsibility: Site Engineer/ Asphalt Supervisor / Superintendent
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.2 Ensure underlying lot conforms
label | 2b930925-852c-5dfc-9595-e88b9d86b92f |  | note | Frequency: Prior to Commencing
label | 5d5fc687-6b76-5b4b-88fd-d2c78bdc6a16 |  | note | - - - - - - - - -
label | 30365570-37b1-5730-866d-d066b79a1ab6 |  | note | Acceptance Criteria: All quality information received for lot (includes levels, area and volume) and NCRs (BIRs) approved.
label | b7ec6abf-2511-564f-a935-f6fa08151c36 |  | note | - - - - - - - - -
label | 13844e14-4ce7-5634-94bb-dc77f0d25781 |  | note | Reference Documents: Relevant ITP for underlying lot
label | 0e5c313f-6649-55cf-a531-be948b4c2194 |  | note | - - - - - - - - -
label | da0ef21c-0bed-5d37-8dae-8bea3e9c5e56 |  | note | Inspection / Test Method: Document review
label | 6d339af9-40b9-52a5-8289-901b3a5a2a26 |  | note | - - - - - - - - -
label | dacee665-29bf-51ab-9ca3-db3acffab0cb |  | note | Record of Conformity: Inspection and Test Plan
label | 65bf06c5-f123-5f14-b55e-e38fc26af2a3 |  | note | - - - - - - - - -
label | ffe9ca3f-c17a-5524-b9d1-541a9fc2f76a |  | note | HP*
checkpoint-status |  |  | checkpoint | 1.3 Visual Inspection of underlying lot
label | aaff4602-97a2-56f7-bd9a-746d3aa43a3e |  | note | Frequency: Prior to Commencing
label | 198275b5-0a7d-5349-94ef-5eaab5827d60 |  | note | - - - - - - - - -
label | 62e1cc2c-3fde-5c6d-9a06-a16d0be7801f |  | note | Acceptance Criteria: If the execution of any part of the work under the Subcontract is dependent upon the quality and completeness of an existing surface or work performed by Separate Contractors, the subcontractors shall visually inspect the existing surface or Separate Contractor's work for matters including the following:
label | 1b7f582d-e784-566c-a2ca-37eeb83223e1 |  | note | (i) Homogeneous surface and pavement material
label | 2ff35f40-48ea-5b7e-863a-cde69b8d847b |  | note | (ii) Uniform in texture
label | 1d91882c-ab47-564c-94e7-c112069c7bcd |  | note | (iii) Free from tearing and scabbing
label | aa3a9148-20f0-5bee-8955-e2800b0f4b70 |  | note | (iv) Free from laminations
label | 911fe582-5557-5d32-99e0-1ce19b5f2a56 |  | note | (v) Free from loose and foreign materials
label | 0ee074ba-bad8-5232-80d0-49fe21fc0ed0 |  | note | and immediately notify the Contractors Representative of all matters discovered that a competent contractor who specialises in the type of works performed under Subcontract should have discussed by such inspection which in the Subcontractor's opinion render such work unsuitable for the proper execution of the work under the Subcontract.
label | 55723bb9-b91f-5555-8670-31a4befcfcc7 |  | note | - - - - - - - - -
label | f5c37ad9-801c-58fc-b3fe-d0c05479b83a |  | note | Reference Documents: CTW-175S Special Condition 11 (Refer Downer ITP - 1145-C200-FUL-QAC-CHK-0001)
label | 4be24681-2833-53fa-8f51-6d4544f5a544 |  | note | - - - - - - - - -
label | e5bb216f-37d1-50e0-8dd7-165d72d8e45e |  | note | Inspection / Test Method: Visual Inspection
label | 422b1ff5-7d8e-5793-b4f6-60dc66a042b9 |  | note | - - - - - - - - -
label | 0582fb5a-47b6-5b77-8d22-705add6281e9 |  | note | Record of Conformity: Inspection and Test Plan ITP Signed
label | 9d287059-893a-52ed-9f22-3c9650ed9e30 |  | note | - - - - - - - - -
label | 27a39220-ba25-5d35-97d1-e3b8506ed2ef |  | note | WP
label | aad5410a-5196-5156-8a86-f90b6ae55696 |  | note | - - - - - - - - -
text | a17501da-f65b-5eeb-a2b5-4d0dbf98e4a4 |  | textbox | Responsibility: Site Engineer/ Asphalt Supervisor
checkpoint-status |  |  | checkpoint | 1.4 Ambient Conditions for Placing
label | 72d00199-f019-50fc-a402-d1483e5bd32d |  | note | Frequency: Prior to commencing paving
label | dd23532b-08fa-52e9-8a39-29625298785a |  | note | - - - - - - - - -
label | 327557dd-8c13-566d-85ed-b12f346ba8b5 |  | note | Acceptance Criteria: The majority of the surface area to be paved has a temperature greater than or equal to the following:
label | 207f3065-fda3-5fde-9fb0-056963b337c7 |  | note | Base & Intermediate Courses: 5°C for conventional binders or
label | 793fcf66-6eb4-57eb-8a9d-181ef6f997dd |  | note | 10°C for PMBs & Class 600
label | 191f024f-21ce-5034-91e2-5153f4ffe215 |  | note | Wearing Courses: 10°C for conventional binders or 15°C for PMBs
label | 7b704b05-f21d-53ce-8eaa-0585d97529bf |  | note | - - - - - - - - -
label | 340c1295-e6fe-5481-a057-b6c518829d38 |  | note | Reference Documents: 407.13
label | 33ca463b-ad02-53a2-a788-0e4756a4a8e4 |  | note | - - - - - - - - -
label | d9cd0ea2-220b-5ed5-b4f6-f84c88ed5827 |  | note | Inspection / Test Method: Verify
label | 0198cb12-b985-5f83-828b-174b46f22324 |  | note | - - - - - - - - -
label | 09898ea6-3f4d-5cdd-bf1e-ea1f5f8e755d |  | note | Record of Conformity: Thermometer / gauge
label | c3e3b7cc-fa97-5435-829a-ef712d894639 |  | note | - - - - - - - - -
label | 3e7ac92a-f3d8-5ff6-be97-262615157772 |  | note | IP
label | 80719627-ae38-5228-97ba-845468143f4a |  | note | - - - - - - - - -
text | f07c976b-4735-56fa-a13a-32fe7387dc08 |  | textbox | Responsibility: Site Engineer/ Asphalt Supervisor
checkpoint-status |  |  | checkpoint | 1.5 Planning of Joints
label | c72d38d0-8f75-5ea2-b303-0bdcaf24f239 |  | note | Frequency: Prior to commencing paving
label | 701478fd-b0fe-5d30-a754-da34e5f3a399 |  | note | - - - - - - - - -
label | 7536df86-b75d-57ff-9965-c07191da1e90 |  | note | Acceptance Criteria: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client (MRPV):
label | bfb0d414-34a9-53d7-bd33-fe27c5261d87 |  | note | (i) Transverse Joints Offset from layer to layer by at least 2m
label | 6240f938-0fb9-5fe7-8431-597cbb2489fa |  | note | (ii) Longitudinal Joints Offset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. V
label | 142500fa-7590-5949-9f1d-a30b9dbdbb80 |  | note | (iii) Wearing course shall be on lane lines.
label | bce5c6a8-5552-5f1b-96ec-88dfeeff2052 |  | note | - - - - - - - - -
label | 62d9be92-52e7-58cb-9f24-35af6379a9e1 |  | note | Reference Documents: 407.17 (b) & (c) Pavement Drawings
label | 28a2ddfa-5aae-5aca-9e0f-13fa6f7e76f9 |  | note | - - - - - - - - -
label | c18f4bed-870a-590c-806b-2525c28ef117 |  | note | Inspection / Test Method: Measure and mark out runs by tape measure or survey
label | bb9bb864-fc5f-5aa4-a8e8-2f57c4f3d12d |  | note | - - - - - - - - -
label | e56f0cb5-baaa-536e-9be4-4ed3d2a71b95 |  | note | Record of Conformity: Paving Plan
label | d47264ea-9b37-51af-a02e-92a4c97c8c3b |  | note | - - - - - - - - -
label | 1960d1ba-6a83-5d08-8ecd-6e08ba2437f9 |  | note | WP
label | 95e3e8aa-9b51-5253-8c7d-91a61bdcb44c |  | note | - - - - - - - - -
text | a431e0cf-b196-5d9e-9260-47401e2c0684 |  | textbox | Responsibility: Project Engineer/ Asphalt Supervisor Superintendent
checkpoint-status |  |  | checkpoint | 1.6 Longitudinal Joints with existing Pavement
label | fde1c66a-e814-5776-9bc9-a10cf3f80ed1 |  | note | Frequency: Prior to commencing paving
label | 3f442c34-d5cf-5886-acbd-8ccd41c12806 |  | note | - - - - - - - - -
label | 3c85accd-0863-5691-b0b0-6d59bfdd54f5 |  | note | Acceptance Criteria: Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm. Depth of step to be cut to the full depth of each individual layer.
label | 7cd74247-85e5-58d9-9123-40477c9509e5 |  | note | - - - - - - - - -
label | 323d9aa1-7fee-58fc-a81f-d5280ba94ff2 |  | note | Reference Documents: 407.16 (c) Project Specs. Section 3040.06 (d)(vii)
label | 4737c6ae-f0b2-5f57-a65a-bdeec6b7cb15 |  | note | - - - - - - - - -
label | d738f46a-d830-5250-be41-c45f48b7dacb |  | note | Inspection / Test Method: Visual Inspection
label | 7ef66568-4127-5db1-83bc-e301d573c7ef |  | note | - - - - - - - - -
label | 156574e4-50fb-5618-ae15-1aba8efabdf8 |  | note | Record of Conformity: ITP Signed
label | 80c0e9a1-f058-569f-aec1-6d0f83c7e3c1 |  | note | - - - - - - - - -
label | da532611-bce6-549f-9d2e-d19d709e30ff |  | note | WP
label | b13f4a92-70ca-53a6-93c0-09d8bd6266d9 |  | note | - - - - - - - - -
text | aad81b11-88c6-5baf-9ebd-a607d7711b13 |  | textbox | Responsibility: Project Engineer/ Asphalt Supervisor
checkpoint-group |  |  | section | 2 - Asphalt Placement
checkpoint-status |  |  | checkpoint | 2.1 Commencement of placement
label | bd380ff1-1d6e-5bcd-97c6-5f26bfa6f44c |  | note | Frequency: Prior to commencing Paving
label | e8a3dc2e-479e-52ac-b711-9e273887511e |  | note | - - - - - - - - -
label | 6adacc4b-3bee-5be8-a224-26527e5f3c7a |  | note | Acceptance Criteria: Approval to place asphalt on the sub-base or granular base for a new pavement or for an ordinary of an existing bituminous surfaced pavement.
label | 42aa520e-3a02-5ed6-b972-08bfa6d453c2 |  | note | - - - - - - - - -
label | 95f57fc8-5cc6-5375-a501-c2f579f3f167 |  | note | Reference Documents: 404.13 405.07 407.18 (Refer Downer ITP - 1145-C200-FUL-QAC-CHK-0001)
label | cfce967e-e8fa-5d7a-8ab2-f2e0417ba0cc |  | note | - - - - - - - - -
label | 94970856-4b1f-5666-b15f-b386c8004072 |  | note | Inspection / Test Method: Visual Inspection
label | dbbb7971-7dff-516b-ac97-6b637cb5eb93 |  | note | - - - - - - - - -
label | efa9e288-b9b2-5608-8505-5c1e9ebafb10 |  | note | Record of Conformity: Inspection and Test Plan
label | d4a51404-3538-597e-acce-07036ecc7d46 |  | note | - - - - - - - - -
label | cba5a7eb-0939-5b3f-ad6d-fd925caa2823 |  | note | HP
label | ad31d05a-4442-5b66-978c-8e2f3afee684 |  | note | - - - - - - - - -
text | 4ba9e079-5aee-5956-a50f-8b3d18450565 |  | textbox | Responsibility: Site Engineer/ Asphalt Supervisor / Superintendent
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.2 Cold Weather Placement Management Plan
label | 39d18939-83c1-536d-a2ab-695490b6b895 |  | note | Frequency: Prior to commencing Paving (Seasonal)
label | 85016376-bcf5-5250-8392-05e6b845224f |  | note | - - - - - - - - -
label | 9ee47e44-6d54-5b87-b5b8-c872676e95c6 |  | note | Acceptance Criteria: Prior to commencing cold weather placement of asphalt, the Contractor shall submit a job specific cold weather placement management plan to the Superintendent for review.
label | c5071c69-364a-5736-9418-81c8c69b6905 |  | note | - - - - - - - - -
label | bc491a11-e967-57f4-8ef1-594bdfa780f2 |  | note | Reference Documents: 407.17C
label | dcb1e94f-9cbf-5db1-81c2-10375f00d5ff |  | note | - - - - - - - - -
label | f1696e4a-f2bf-5aad-a0c7-cf4354af43e6 |  | note | Inspection / Test Method: Document review
label | 9a8177ae-ec16-5699-8962-8ff0ded5a8cf |  | note | - - - - - - - - -
label | 299d9b61-435b-5523-9182-22dbcf306f57 |  | note | Record of Conformity: Inspection and Test Plan
label | caad0d50-393c-56b7-b26e-b24ddb1dfab1 |  | note | - - - - - - - - -
label | a83e3fdb-79fc-5cfe-b6a6-47f3d5430cd4 |  | note | HP*
label | b2f987ec-b954-5a49-9305-7bd27cfbb74c |  | note | - - - - - - - - -
text | aec6fbc2-7ad9-5b74-b6e6-603640ea2278 |  | textbox | Responsibility: Project Engineer/ Asphalt Project Manager or Engineer
checkpoint-status |  |  | checkpoint | 2.3 Mix Design Confirmation
label | ebd75b7e-9672-58a2-9fe1-6ca4ff5d5e39 |  | note | Frequency: Each lot
label | 505332fc-3b32-58a5-90e4-4369a1e063a5 |  | note | - - - - - - - - -
label | 4a0e450b-e147-5e44-abca-f137d61b5c37 |  | note | Acceptance Criteria: Check correct mix design as per pavement design has been delivered prior to laying mix.
label | b3efbf6d-f4ea-5ba7-bcc3-ef63151172e8 |  | note | - - - - - - - - -
label | a8c02e2e-3530-5c20-a7cc-b401870c2e80 |  | note | Reference Documents: VicRoads Spec. Cl.407.06
label | c3f4bf24-3535-5d64-a849-0a2e4068df68 |  | note | - - - - - - - - -
label | 28b8009e-5968-5d0a-871b-a21d69113d06 |  | note | Inspection / Test Method: Visual Inspection & Delivery Docket
label | 05e5be36-fc65-52d2-b2b7-2469c79f9dad |  | note | - - - - - - - - -
label | 3e9b52b5-8c18-53c1-889f-d04c6a5960b3 |  | note | Record of Conformity: Delivery docket Completed ITP
label | 7c51c8e4-1dec-59ca-b671-f1b3b42b1e24 |  | note | - - - - - - - - -
label | 13d709a0-565a-5176-8984-019c0afe69f5 |  | note | HP*
label | d5d677c2-e78d-558c-9440-88814c90d72d |  | note | - - - - - - - - -
text | 53731290-e82c-50eb-a634-20038c768f66 |  | textbox | Responsibility: Site Engineer/ Asphalt Supervisor
checkpoint-status |  |  | checkpoint | 2.4 Running traffic on Placed Asphalt
label | 1592859b-4913-50cf-8d23-4cac464844e1 |  | note | Frequency: During Construction
label | dd029045-2004-569f-8622-cc41eaffb3fe |  | note | - - - - - - - - -
label | 022a43aa-7ee7-5907-8636-b646c04bfa36 |  | note | Acceptance Criteria: Traffic not to be placed on asphalt placed until Fulton Hogan agree the surface temperature is less than the required mix temp. (SMA 40°C) to receive traffic.
label | cb27388c-b02c-51f4-8215-e3a30cf2cc28 |  | note | - - - - - - - - -
label | b6b2be9c-7b08-5fa2-906a-006f81f16ae5 |  | note | Reference Documents: 404.14 (Refer Downer ITP - 1145-C200-FUL-QAC-CHK-0001)
label | de41dc82-2391-5c48-83e5-1cf22812cd85 |  | note | - - - - - - - - -
label | 895aa249-bc28-5570-a541-fcd14e926a11 |  | note | Inspection / Test Method: Verify
label | e5c30ee0-4071-588b-8df2-1df50d194b9c |  | note | - - - - - - - - -
label | a962adaa-ba25-5b53-bd83-2fe3274a22de |  | note | Record of Conformity: Inspection and Test Plan ITP Signed Thermometer / gauge
label | 81513d53-62a8-59cf-b639-ba054a6859bc |  | note | - - - - - - - - -
label | b343c188-6ea1-50bb-8712-fde2b95de838 |  | note | HP*
label | fc7ab151-3e0f-56aa-9b7d-bdde9813693c |  | note | - - - - - - - - -
text | 3a647b1c-bd25-564a-9166-cae997f5ecc3 |  | textbox | Responsibility: Site Engineer/ Asphalt Supervisor
checkpoint-group |  |  | section | 3 - Testing
checkpoint-status |  |  | checkpoint | 3.1 Placing Material
label | df4cc8f9-348f-5d13-90f8-e34a04f4d741 |  | note | Frequency: Per Lot
label | 89a51625-574b-5826-9b31-4130260c28fa |  | note | - - - - - - - - -
label | f972a175-fc8b-596f-ae35-f9f3155515ac |  | note | Acceptance Criteria: 407.21 - DGA as per 407.22 405.08 - RGG - not less than 3 passes with steel wheeled roller. 3 passes to be made within time to compaction cessation substrate (pavement) temperature is between 7° and 10°C.
label | 937f2b59-76fd-541d-ac5f-d1e35dd3306f |  | note | - - - - - - - - -
label | 77c7cca5-3feb-53ed-ad87-422d60df1486 |  | note | Reference Documents: 407.21 405.08 404.14 417.12 (Refer Downer ITP - 1145-C200-FUL-QAC-CHK-0001)
label | fa4f4dc8-45e9-5e66-b0bc-b0553640c2b2 |  | note | - - - - - - - - -
label | 478db5f8-d179-5de2-963f-7f025b05a8ce |  | note | Inspection / Test Method: Material Sampling & testing
label | 2c56a9ed-d782-50e8-a1a9-d7822aefd300 |  | note | - - - - - - - - -
label | 79173c39-3725-5c41-b308-9794738d1f0e |  | note | Record of Conformity: Visual Inspection/ Compaction test results Visual Inspection/ Visual Inspection/ Field Report/
label | 0d202948-b305-5de7-8ec1-b0af9fc16581 |  | note | - - - - - - - - -
label | 6ec6aac2-915e-5a69-bea9-3954b4dce4f7 |  | note | WP
label | 09aadf28-876d-51e7-995a-ff3aaf7fe795 |  | note | - - - - - - - - -
text | 57fc325d-c265-5eb8-9936-27d70128738c |  | textbox | Responsibility: Site Engineer/ Asphalt Supervisor Superintendent
checkpoint-status |  |  | checkpoint | 3.2 Survey Level Conformance
label | d46e491e-0ec0-5f51-a062-d61df1a79fbd |  | note | Frequency: Per 4,000m2 at completion of work
label | ff5b42f4-5e66-5115-af5d-0b33b8bfda0a |  | note | - - - - - - - - -
label | bb903d04-11d3-5654-91de-f1a4b98796fd |  | note | Acceptance Criteria: 407.293 Surface Level Tolerances for Sub-base and Pavement Courses
label | 59c0c244-068d-54e0-a9f2-e30624c6ebfa |  | note
label | d5a4e06a-d14a-53ea-882a-bedfdb97c2d4 |  | note | Scale of Surface Level Measurement -
label | 7058371c-29f9-5b07-80fb-036e5e7f4195 |  | note | Granular or CT Subbase
label | 411286ac-90a6-5cd7-92fa-af6b14465c3a |  | note | Range (mm) Max S. (mm)
label | f050e46d-cfcb-5f21-8213-94fe3bc3b568 |  | note | Scale A - +4 to -8 8
label | 394dc754-a73b-5374-90da-07a061f5a13a |  | note | Scale B - +6 to -12 13
label | dc1aa46d-c6cd-517b-a3c0-5d8220d96cc8 |  | note
label | 586dc592-5053-54cb-978c-2d37c47b23f7 |  | note | Asphalt Layers
label | 0bb3535e-25a2-512f-8e0a-c6fbbc10df0c |  | note | Range (mm) Max S. (mm)
label | c48fee44-4eed-50a7-861b-aeae1eb69905 |  | note | Scale A - +/- 5 8
label | 69f7e68b-a842-57a9-967d-ca91b538f63e |  | note | Scale B - +/- 8 10
label | 1c8cddea-19e6-5311-97da-68ee40b8083c |  | note | - - - - - - - - -
label | 4e3cfbe2-bb41-53f0-b8f6-00b1478cf679 |  | note | Reference Documents: VicRoads Sec 407.293 Surface Level Tolerances for Sub-base and Pavement Courses
label | 87e1f692-e06e-59d5-b27d-7d3b0512fc81 |  | note | - - - - - - - - -
label | 20de65b5-eddd-52e9-8d4f-33afcad7a05c |  | note | Inspection / Test Method: Document Review/ Site Inspection
label | 1e12e947-6d46-5946-b43b-0ca576333e71 |  | note | - - - - - - - - -
label | 37f481ee-5ff8-50cc-b7ae-d9fd803ab7dc |  | note | Record of Conformity: Survey Conformance Report
label | 0e3da3a8-5c50-5fd1-95ed-33f81b8e7371 |  | note | - - - - - - - - -
label | 61e20774-8f64-5f8b-aab8-003e849b95b3 |  | note | SCP
label | bd874cca-827e-5546-965a-89a9258d7af4 |  | note | - - - - - - - - -
text | 74babae4-d9c8-5861-82bc-b3bcb904ad67 |  | textbox | Responsibility: Site Engineer/ Surveyor / Survey Manager
checkpoint-status |  |  | checkpoint | Final Inspection
label | d9aa14ce-c91c-550b-b4c4-da6f98a628d3 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | c9c49635-fdf3-55e4-8bc7-edb64cf450a8 |  | textbox | Print Name:
text | 4c29872d-52bd-53c1-b611-8114cec4c5c1 |  | textbox | Position:
date | fe782c80-70be-5a48-bca5-bc20cbe8023b |  | date | Date:
date | 96b51711-8d1e-5fde-9a3d-4390851cb490 |  | date | Work Completed On
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification.
select | ca3765fc-75a6-5bd9-bdf0-49a84e8fbd38 |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | 3e657a69-17bd-5205-83c5-918836f3278e |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | 4c3594a6-ded3-5ba6-8ede-343429275632 |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | be667405-a55c-5e13-8a72-a6e9cc7be73b |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | 60903ee6-0e56-53c6-ac3a-fe97236d953b |  | textbox | Other:
select | e2e9b5f6-8c91-5b85-bf3a-bf47b6a19391 |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | 7ffc4b5b-99cf-5ad0-b25a-eea777abf3c9 |  | date | Lot Closed On
text | 5659eec9-427d-50fb-b125-26b7bb4270c8 |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-083-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0083 - Precast Concrete Install | a83efb4c-2072-41e7-82b8-aa612fb0496b
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | 1d64b2c3-746e-5c3e-bc2e-ce914d070810 |  | date | Lot Created On
date | 3b03c7a5-268f-57be-8f43-0f689adfade7 |  | date | Lot Opened On
date | 79568f46-98ef-52c0-ab2b-d544c95a028e |  | date | Work Commenced On
select | 83854d9c-30b9-5b2a-8e45-30dd3c6cda13 |  | dropdown | Lot Type | STL - Structural
text | 816bb12a-10b4-5d5b-981f-f2e9648c135d |  | textbox | From and To Chainage
select | 5294d271-079c-503b-b648-d9e9f3d970ea |  | dropdown | Construction Element | EMBA - Embankment,SUPE - Superstructure,SUPE - Superstructure
select | ef041f3a-0b75-545f-86e2-ffb609a3bfe2 |  | dropdown | Activity | RETW - Retaining Wall,OFSB - Off-structure Barrier,ONSB - On-structure Barrier
select | 6837f60d-c0b9-5b92-8fa5-efb0103e4ab0 |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | c93bef9c-ae04-5ab8-b9c1-c8a40c9e0d7c |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | c1b10765-15d5-5761-83b2-5454ab617d24 |  | textbox | Engineer Responsible
text | 8daef74e-b743-5ce8-bf48-3162164afa31 |  | textbox | comments
checkpoint-group |  |  | section | 1 - Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 55dda094-fcef-5969-81c5-089d14a04272 |  | note | Document Title: ITP-083-AX-LOT-XXX - Description
label | 52a08e27-461d-5278-b64f-519ace4027ab |  | note | ITP Description: Precast Concrete Install
label | 6dc2de25-19c9-5d23-b862-0bff9b31aaf7 |  | note | Document Number (in Teambinder): 1145-C200-FUL-QAC-ITP-0083
label | e024f0f2-192d-5099-ae59-a148ca8f0be8 |  | note | Revision Number: 00
label | 2b7f92ad-d668-5dee-9600-116d27718141 |  | note | Revision Date: 03/06/2022
label | e451f99e-0188-5a60-9843-4b5810bbf224 |  | note | ITP created by: Omar El-Khub
label | b5c80c5d-d8fa-5bf0-94d8-007e40d63c0c |  | note | ITP approved for use by: Babak Rudd
label | bbe674f6-e076-5f5c-8fd7-7241092fbd88 |  | note | 1.1 VicRoads Section 610 Feb 2020
label | 5a75eb5f-e0db-5203-8717-7847e109c955 |  | note | 1.2 VicRoads Section 620 May 2009
label | fdd62128-e20f-5bc3-82ee-664301b786fc |  | note | 1.3 VicRoads Section 630 Oct 2013
label | 4b8bb21a-a5d4-5489-8b2f-3b94f51e4325 |  | note | 1.4 VicRoads Section 671 Oct 2013
label | 21c499df-45fc-5203-914b-6518124070b3 |  | note | 1.5 AS5131
checkpoint-group |  |  | section | 2 - Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Precast Elements
label | d7d5fb0f-4247-5c95-9e98-10d71db443f8 |  | note | Frequency - Each element
label | e2a862ff-98be-5e61-b16a-ac302801938b |  | note | - - - - - - - - -
label | 27bc8f22-50ee-585e-bce5-f7bce7c5b6d3 |  | note | Acceptance Criteria - Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | a0caa089-f6af-508e-a94f-23295c9aaa38 |  | note | i. Certificate of Compliance / Birth Certificate
label | c86bb90b-6674-5f47-a860-c4d7234347bc |  | note | ii. Compressive strength test results
label | 177937b7-38bb-5d77-adcf-738907580981 |  | note | iii. Precast Lifting Design
label | bfde8633-f5f6-5a92-ab9f-dad95b5b408e |  | note | iv. Pre-pour check sheet / ITP
label | a250c60f-a850-5c2a-b140-723a396090a4 |  | note | v. Post-pour check sheet / ITP
label | 2d5c2a82-b367-519f-a4a7-27dc6069d0d4 |  | note | vi. Covermeter check record
label | a6156925-413b-5f82-9461-f50967d53f60 |  | note | vii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast shown in Cl.610.47
label | 4b0cedca-bd02-578f-a514-531948f559ae |  | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
label | b5eac316-a59b-5538-8ff5-dd6c809b794f |  | note | - - - - - - - - -
label | 2827428a-3ff0-51c1-982b-703f5b92b361 |  | note | Reference Documents - VicRoads Spec.
label | 444d4725-c009-5b5b-b005-680325a039dd |  | note | Cl.610.47
label | 79016eb3-7600-56c4-b02c-397357827624 |  | note | - - - - - - - - -
label | f26c470e-4af7-52df-abb3-821b73d5fad8 |  | note | Inspection / Test Method - Document Review
label | 0bd6055b-69bc-5f2d-a8ec-257b4f406ed4 |  | note | - - - - - - - - -
label | 32d3aa49-321f-5a91-9d87-dcec028866a7 |  | note | Record of conformity - Material Report
label | fa79bd58-29a0-5bff-8301-8f38b39aa015 |  | note | Signed ITP
label | 3aa1189f-d515-57b1-a2a6-b868e7935047 |  | note | - - - - - - - - -
label | 37cdabdd-9d9a-5159-87bc-636c6f347aca |  | note | IP
label | 06b827ac-f069-5e13-9e34-f97f532df218 |  | note | - - - - - - - - -
label | 1f0217f5-8d1f-5754-9042-44df39a4ff58 |  | note | Responsibility - SE/PE
label | 754d303b-d596-591c-8630-c1e834d5cb7f |  | note | - - - - - - - - -
date | e982d5ac-365a-5007-b6ab-7421ceb119e7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Joint Sealant
label | 7b88c251-5aa2-51c8-a074-d61d780fc2a3 |  | note | Frequency - Once, for each product
label | 1c98ab92-b42c-5543-b601-50a96b2cfad8 |  | note | - - - - - - - - -
label | 9a57e2d2-d503-51a2-b83c-c2d8290544fe |  | note | Acceptance Criteria - Details of the joint sealant used to seal around the precast element to be submitted for review to the Nominated Authority.
text | e5bdb79d-3a43-5349-9dd7-ef6aae050266 |  | textbox | Teambinder Material Approval number:
label | e24720dc-ee74-5d8d-a8ae-8ec09d97e02b |  | note | - - - - - - - - -
label | 5e7745ab-d165-5c3e-b320-174c3d33c14b |  | note | Reference Documents - FH Quality Management Plan
label | 96b0ea76-8da1-5dce-aaf5-ad3a597d94b1 |  | note | - - - - - - - - -
label | 3d8fb2f7-0eaf-50ca-809c-75cf59393271 |  | note | Inspection / Test Method - Document Review
label | 12373875-b922-5390-a3ec-98ccc71e8b5d |  | note | - - - - - - - - -
label | 8e45f693-2f1f-5c21-bd25-3243cbc03b4d |  | note | Record of conformity - Signed ITP
label | 771c6c8e-4189-5cb5-afb5-8614beda3ad2 |  | note | - - - - - - - - -
label | b1439bf0-1b08-5543-a9b0-83af81eff17b |  | note | IP
label | 5c959b56-9e19-5d9b-987f-156f5e2c07bf |  | note | - - - - - - - - -
label | 7cef14b8-de8b-57e8-b78c-e470442bcf08 |  | note | Responsibility - SE/PE and Superintendent
label | d60f0f07-aba0-544f-b6ca-b35a0443f024 |  | note | - - - - - - - - -
date | fa716069-0db7-541b-a2c5-253dfadf9cea |  | date | Date Completed:
checkpoint-group |  |  | section | 3 - Preinstallation Activities
checkpoint-status |  |  | checkpoint | 3.1 - Survey Set-out of Precast Elements
label | ec0eb7a4-25f2-598a-bd26-2633adb60d6d |  | note | Frequency - Each element
label | df4a02ac-a612-524b-9499-6e445cc40b93 |  | note | - - - - - - - - -
label | 2f7fce6a-6cf3-5b96-b686-fd9a49d568dd |  | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per Cl.610.47 as applicable to the element.
label | 60aa70ee-52b4-5530-9389-c48c2be77366 |  | note | If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast.
label | 82257c5d-079a-5049-a460-c28eb463e8cf |  | note | Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius.
label | a65c0cd1-11ea-57cd-adf3-af55219dfccd |  | note | - - - - - - - - -
label | 9e663a26-28dd-5dfa-adc6-62196a5a080b |  | note | Reference Documents - VicRoads Spec.
label | d16121f7-62aa-5872-88c1-62f8ad9ed4bd |  | note | Cl.610.47
label | cf167637-8303-590f-98ca-b4916529d34f |  | note | - - - - - - - - -
label | b244d0cc-4aa2-51de-8527-e25eaaff4e37 |  | note | Inspection / Test Method - Visual/ Measure
label | 596013c5-30b9-58c0-861d-9e8154f4bee4 |  | note | - - - - - - - - -
label | a1e58570-7ce3-5660-9f7c-d97544ce51ff |  | note | Record of conformity - Signed ITP
label | 6b3d2fc4-2267-59da-98ec-331d7c1862c0 |  | note | - - - - - - - - -
label | 3da0a5c5-728e-5ade-9c04-31e14a66a750 |  | note | SCP
label | 923433da-d88c-5e64-b037-9b2cfe4567f2 |  | note | - - - - - - - - -
label | 2fb901a5-7133-532f-8cf0-8f320ccb31c1 |  | note | Responsibility - SE/PE
label | a5c6be89-4318-5df3-b5f0-3616842dc5fb |  | note | Surveyor
label | 6b60b94d-2be4-5ad2-b69f-43b3cf21bc7e |  | note | - - - - - - - - -
date | 3b0083cb-4b7f-5c09-b594-674cc4a809be |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Sealing Strips, Backing Rod & Bitumen Board
label | 39b8e5d1-bb25-5bde-b458-b36da3ef1bf5 |  | note | Frequency - Where applicable, each installation location
label | 5c1da474-c815-5d25-a313-c0c40079e76a |  | note | - - - - - - - - -
label | c774cc23-e4b7-5bb2-bb2e-8f5a94fd89d1 |  | note | Acceptance Criteria - Adhere any sealing strips, backing rod or bitumen impregnated fibre-board into the positions shown on the IFC Drawings or where grout or concrete ingress will affect the end use (such as around conduits).
label | fc98e219-2e7c-51f7-a5a8-14388596155a |  | note | Backing rod should be compressed enough to prevent movement during the concrete or grout pouring activities.
label | 24a7bea2-8252-5bcf-b61b-aa8fae8534ff |  | note | - - - - - - - - -
label | 08c00c8f-50bc-55f4-be3f-20aad48b5557 |  | note | Reference Documents - IFC Drawings
label | c3755117-b159-5708-9c1c-a01bc3c01078 |  | note | - - - - - - - - -
label | c5eed545-2b19-544e-bc5b-21cb4e248467 |  | note | Inspection / Test Method - Visual/ Measure
label | a8be7bb7-a6b0-5cf7-881a-eed6f1e493dd |  | note | - - - - - - - - -
label | 3200cae3-e584-529d-b707-fbd5ba7d8804 |  | note | Record of conformity - Signed ITP
label | b2af78f2-88e0-559d-ad56-784c206736a8 |  | note | - - - - - - - - -
label | 199feaa4-545d-5708-ae0b-9871aa23bbc5 |  | note | IP
label | 49ec6f2a-2157-59d9-ab3e-6b04409e96d6 |  | note | - - - - - - - - -
label | 9ee807cf-3afd-56c0-8de8-47f7af94f4cc |  | note | Responsibility - SE/PE
label | 24fcede6-4469-5ecd-b788-f890a98d2352 |  | note | Surveyor
label | f1a5a696-2423-58e0-b356-83d9f52b470a |  | note | - - - - - - - - -
date | f74209fc-cf2f-55fb-a13b-c6b987351b6a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - Materials Inspection Checklist
label | 894b3f72-09d0-52d8-8542-72c443efc77b |  | note | Frequency - Each element
label | 906ec2e8-2446-5772-bb40-bc57d7d14edd |  | note | - - - - - - - - -
label | ca25cb51-662c-5d71-adb0-84c45b2fa87e |  | note | Acceptance Criteria - General inspection of precast elements for defects including cracks, damage, exposed reinforcement and where applicable, damage to coatings.
label | 2aef64ce-8c8c-5d03-acb4-66235969d671 |  | note | Confirm that the cast in lifters (anchors or loops) are the correct size and orientation as per the Precast Lifting Design (they should be clearly labelled on the end to be connected to).
label | 250c838e-704f-5599-8406-5756f2d9613f |  | note | Elements shall have unique identification and orientation marked (if applicable).
label | d9c7bd86-76e4-5816-9aaa-069862596ecb |  | note | Complete: Materials Inspection Checklist in ConQA
label | 2c31e08e-f66d-5b1f-ae47-611a323e4e13 |  | note | - - - - - - - - -
label | 6eaea873-6f5e-5552-a4df-5e0f3c8c90f0 |  | note | Reference Documents - VicRoads Spec
label | 3f2c6e2e-f1b9-5680-965a-cb5653df871a |  | note | Cl.620.06
label | 26aeff6b-7cc7-5dda-827d-f927d1187006 |  | note | 620.07
label | 2ca8dc55-ab02-5816-b64e-6a3bc5e56e62 |  | note | FH Quality Management Plan
label | 927c8b5d-20a5-59a1-9734-8a01d9bd5a45 |  | note | - - - - - - - - -
label | c83e0392-9a92-52d1-ad0c-f5f63c94882e |  | note | Inspection / Test Method - Visual Inspection
label | 41b1471f-8f5d-5405-bf4f-ea088177f4ff |  | note | - - - - - - - - -
label | 2de58b79-dfb7-5640-8b6f-0f682fff60e3 |  | note | Record of conformity - Signed ITP
label | e37d46b6-8cca-5a8e-83c7-a40c75210892 |  | note | Material Inspection Checklist
label | 38fc0080-8eec-5eb2-87f2-a0c1cbd77d9c |  | note | - - - - - - - - -
label | fc087edd-2772-5842-9bb3-e7609c9cc052 |  | note | IP
label | 7f2c9854-b396-58ba-b27c-f4bb584107b9 |  | note | - - - - - - - - -
label | 39f323ab-9380-598e-ae1d-d6dad6ac19ef |  | note | Responsibility - SE/PE
label | d621c8d2-8381-5a1a-b85a-6459d3ee8900 |  | note | - - - - - - - - -
date | 0ab750fd-8e18-52eb-8cc9-62467984036e |  | date | Date Completed:
checkpoint-group |  |  | section | 4 - Installation activities
checkpoint-status |  |  | checkpoint | 4.1 - Precast Handling
label | 4c6bba73-10b3-5645-9c14-2270bbcc0a89 |  | note | Frequency - Each element
label | 98f7f159-93d2-5a5b-86e4-7cd251dd693c |  | note | - - - - - - - - -
label | fb4e22de-f68f-5bfa-addd-270f5d10e587 |  | note | Acceptance Criteria - Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
label | 8186e099-9d9c-5b1b-9b4c-ebb305b3077b |  | note | - - - - - - - - -
label | 761eb029-9b6b-55c5-bf19-55bff0c2f8a4 |  | note | Reference Documents - VicRoads Spec.
label | 856f77a5-b927-560d-9c33-25201761a905 |  | note | Cl.620.07
label | 35403cb0-4254-5934-800a-4aad0ee9d1c9 |  | note | Crane Lift Study
label | abff1d3c-8505-56c9-b62f-cf1393f2367e |  | note | - - - - - - - - -
label | d3bc3e64-2c9e-5694-8a8f-b856b00e82c0 |  | note | Inspection / Test Method - Visual
label | ce346a88-d975-5793-b7cb-89486cf7465b |  | note | - - - - - - - - -
label | d28b0ba8-fa3b-56b3-b1d3-4a188217f2d3 |  | note | Record of conformity - Signed ITP
label | cc6bab31-d90d-5933-a609-cc0f5e16fff2 |  | note | - - - - - - - - -
label | 1a955380-d36f-5a42-aee4-f95a3f1fb882 |  | note | IP
label | de777b92-0ffd-575c-ad98-4b00a6301794 |  | note | - - - - - - - - -
label | c0ece1dc-36f6-5f58-887c-f4c10d4326d3 |  | note | Responsibility - SE/PE
label | 0a36cdf1-d302-5cc0-ad0a-d1cf9e4e3ba9 |  | note | - - - - - - - - -
date | 54272968-ab31-5264-91b5-3c421414bff7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Precast Placement
label | af50f8c1-5a68-525a-b18a-0980f8a148ee |  | note | Frequency - Each element
label | 3afa88b0-683f-561c-bd6a-1a6eb6aee477 |  | note | - - - - - - - - -
label | 4e4d033b-791a-5d03-a5ed-2e4300e8aa22 |  | note | Acceptance Criteria - Precast elements shall be placed onto the bearing shims and not released from the crane until sufficiently braced or restrained by bolted connection, in accordance with the approved temporary works design and/or IFC drawings.
label | dc9ee135-7b7c-55a0-9b82-a172a9ab0953 |  | note | Make any adjustments necessary by lifting the unit and adding/removing shims or adjusting the levelling bolts so that alignment between units, overall height and position remains in tolerance.
label | 5b4330f8-6c2a-541e-aa29-426f4ccf1e63 |  | note | The nominal gap between elements is as per the IFC Drawings.
label | 8f5100d6-f0c5-54f4-90f1-54ec7bac7765 |  | note | - - - - - - - - -
label | 59395b19-233b-5c74-a32a-95b8d85d3ac2 |  | note | Reference Documents - VicRoads Spec.
label | 38ae6843-0c33-507b-ab9a-539d8c9e985f |  | note | Cl.610.27
label | 4e970e96-8233-5558-bdbd-9f040b3635c7 |  | note | IFC Drawings
label | 0ffd2d5b-b178-5a3e-8c6c-aa88991b1d5b |  | note | - - - - - - - - -
label | 6caeea5a-bf64-5441-a497-2847f1f10058 |  | note | Inspection / Test Method - Visual
label | 0904239e-ddad-5bb6-b039-c71a2628b971 |  | note | - - - - - - - - -
label | 608c4f95-428d-54f6-aecc-2a9fa1c8a529 |  | note | Record of conformity - Signed ITP
label | 8fb98454-4ef9-55f5-9533-149db9224ad1 |  | note | - - - - - - - - -
label | 90f7b6ea-ed13-536f-ba84-f95abbccf4a7 |  | note | IP
label | 96ac8c8d-0cf4-5d06-af97-90faef2dba4d |  | note | - - - - - - - - -
label | 7b658ff8-6025-519e-a626-fa9c226a50c9 |  | note | Responsibility - SE/PE
label | a3315998-d812-5ac4-86d0-ca75ac5efb94 |  | note | Surveyor
label | 53c55854-4122-5a84-bf9f-dc8f8171b4d0 |  | note | - - - - - - - - -
date | 9aa8e997-3f1f-5996-aa51-5999b18209e2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Draw-string in Service Ducts
label | 7430a0c5-ad9f-55b2-89ac-3e69f095a532 |  | note | Frequency - Where applicable, each element
label | 5520ed4d-5fd6-5b08-8abd-a5ada39ff692 |  | note | - - - - - - - - -
label | abaa466b-231e-5d90-b3d3-9f05f29d4d44 |  | note | Acceptance Criteria - Place a continuous length of 3mm galvanised wire or high-strength nylon draw string so that it can be terminated at any junction boxes.
label | f7ba4910-0e80-529f-b1bc-f8c8d17346af |  | note | - - - - - - - - -
label | 53889f12-50e8-57bc-97a2-51a695cfa7d1 |  | note | Reference Documents - VicRoads Spec.
label | b403a672-0928-5f46-a33a-1b449406392c |  | note | Cl.671.03
label | b9d4da93-369b-57f8-93f1-ad72bd6b6c6f |  | note | IFC Drawings
label | d5a2d498-717f-5246-aaff-5bac92eecaf2 |  | note | - - - - - - - - -
label | e050458d-db78-5e9a-a288-74b94a15b650 |  | note | Inspection / Test Method - Visual
label | ad372034-cdb3-5cce-8b1f-b631617a86be |  | note | - - - - - - - - -
label | 3c78113b-4ab7-5dcb-b585-3f1c892087c7 |  | note | Record of conformity - Signed ITP
label | 6e939a6a-36f6-56a8-a770-f1312e646877 |  | note | - - - - - - - - -
label | c222b9e0-e0ab-5640-902a-eaf1a43ebbf9 |  | note | IP
label | 8c215eaa-79d5-5dd1-a390-ef8cf3447edd |  | note | - - - - - - - - -
label | b4b4f8ae-df16-52e2-b0cb-85ffc9429757 |  | note | Responsibility - SE/PE
label | c90fde95-c1df-5945-a8f9-fea698cfeb42 |  | note | - - - - - - - - -
date | eb738bf9-1628-52b7-9d71-07eb0418812e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 - Precast Traceability
label | 5f0eee63-8c09-559d-b53f-b57ab79443a0 |  | note | Frequency - Each element
label | a8261571-cde3-5720-8aa7-a1b2843c93cf |  | note | - - - - - - - - -
label | e27c8623-b3d2-5f3a-ac6c-e8de474abf6d |  | note | Acceptance Criteria - All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
label | 97972ae7-1817-52b5-b49f-3b140e7d9c05 |  | note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
label | 2477f850-8137-5222-9508-21b3c18e5e65 |  | note | - - - - - - - - -
label | 3c6cc57e-2b88-52bc-a2c1-7878796c89ed |  | note | Reference Documents - VicRoads Spec.
label | 3a5d0d85-f3cb-573f-bed0-52bb42bdc9ff |  | note | Cl.620.09
label | 3f23dc8b-d25e-5ced-a46c-f19d134a0499 |  | note | - - - - - - - - -
label | a9c61e3a-0bcb-5a16-bc1d-5e2082530822 |  | note | Inspection / Test Method - Visual
label | e27364eb-3bd4-5c43-ac50-1eaa30b691db |  | note | - - - - - - - - -
label | 44b04ec2-bce1-57d0-8ffc-476c9638282c |  | note | Record of conformity - Signed ITP
label | 68e64dea-9024-5b55-81a3-f3c62a0b62aa |  | note | - - - - - - - - -
label | 9e676d5b-9753-52b3-b7b8-ee7a425df73c |  | note | IP
label | 79048376-b6e0-5226-96e9-35bf2d2c26c3 |  | note | - - - - - - - - -
label | 720a2a1f-790f-5575-8d6b-f026ccd6a5d5 |  | note | Responsibility - SE/PE
label | 56e42b42-f49f-59d8-935b-bb41a43a8663 |  | note | - - - - - - - - -
date | 44826238-9d21-5c4d-a88d-e9be7aa439bc |  | date | Date Completed:
checkpoint-group |  |  | section | 5 - Post-installation activities
checkpoint-status |  |  | checkpoint | 5.1 - Joint Sealant Application
label | 458d6eda-bfe6-57d4-8ac1-dda319a79488 |  | note | Frequency - Where applicable
label | 78e48ef9-9834-588c-8ee0-ab956a0d8249 |  | note | - - - - - - - - -
label | bf49f74d-92cb-53d2-9247-830ab0621045 |  | note | Acceptance Criteria - The gap between each precast element or at interfaces with other structures should be sealed with an the approved sealant on top of a backing rod.
label | aa2df3be-1c17-557c-ac51-8d7bef2fc0fb |  | note | - - - - - - - - -
label | 73b705f2-945f-56e2-988d-5dd0ef8fe323 |  | note | Reference Documents - IFC Drawings
label | 7371c1fa-0197-5c4d-addd-1463a254e02a |  | note | - - - - - - - - -
label | edc470cb-155c-52bf-bb75-a69991407de3 |  | note | Inspection / Test Method - Visual
label | a2203aee-8be7-59a5-bada-0261298dd649 |  | note | - - - - - - - - -
label | 89fb53ff-66cf-54ea-802d-dc9002a0f0e1 |  | note | Record of conformity - Grout Pedestals & Bearings ITP
label | 6f27a63c-84ae-5f0b-be5c-9912470441f2 |  | note | - - - - - - - - -
label | 9b36dcf7-5d35-5dd6-967e-137a5d3ad0ba |  | note | IP
label | 3bbb95ae-4fe6-5b74-9b21-c2a37697bfd7 |  | note | - - - - - - - - -
label | f0468e6c-9416-52e5-8201-8db2cbef744f |  | note | Responsibility - SE/PE
label | f276e039-e1a8-502f-8f80-e8c368e6bed3 |  | note | Surveyor
label | ae55d600-8eed-5d19-87af-97a80462b30a |  | note | - - - - - - - - -
date | ad82653b-5c7b-5ed9-aacf-03cfc6f59a30 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Flowable Grout Pour
label | 175d9776-ebbb-53d7-954b-52039b4764a0 |  | note | Frequency - Where applicable
label | 42660d96-65f5-5bf5-988a-fdecc14eef4d |  | note | - - - - - - - - -
label | 8130dcf6-eb8f-5fa9-ab53-edaed80144e3 |  | note | Acceptance Criteria - Grout shall be poured at connections between elements and/or in the gap between the bottom of the precast element and top of the bridge deck/foundation following full sealant application.
label | c2263a51-43c1-54d2-96f3-51afaf7f090f |  | note | Complete: Grout Pedestals & Bearings ITP
label | ba744b7c-8b36-58ad-9cfb-7b1407ba1d9d |  | note | - - - - - - - - -
label | bf8c73c8-deb5-525a-aeed-42e10c2736e5 |  | note | Reference Documents - IFC Drawings
label | 117e023a-2ae7-5d4e-9069-28769ccb2ed2 |  | note | - - - - - - - - -
label | b067277a-7946-5e7b-82e1-64d8d8cd2f71 |  | note | Inspection / Test Method - Visual
label | f88d3020-5b57-5dce-aad4-91f8f9b448f5 |  | note | - - - - - - - - -
label | 650338a0-6e5b-522d-a404-25ab61d545e2 |  | note | Record of conformity - Grout Pedestals & Bearings ITP
label | 62e6687a-0859-59d1-aece-8b53ba8be131 |  | note | - - - - - - - - -
label | c7350c7d-0c0f-545f-adef-76ff7363795a |  | note | IP
label | cfab6dea-532a-59d3-8bcc-1d912a63cd1f |  | note | - - - - - - - - -
label | 903030bd-2ed4-513c-9534-73863a178f44 |  | note | Responsibility - SE/PE
label | 3a84c1ca-004e-5a6e-a6fc-988b9a014148 |  | note | Surveyor
label | 9b8cd3ca-c2f8-50fd-b19c-4dfcc860cad8 |  | note | - - - - - - - - -
date | 61e690f9-369f-5ed7-be69-a6fdce826e58 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Barrier fencing
label | 5563616f-b32e-5ba3-a200-3315c2bddffb |  | note | Frequency - Where applicable
label | e9231cea-8f1b-5d50-a184-eff897a799de |  | note | - - - - - - - - -
label | a67e16ca-9ad9-587d-b3d7-1027e7e9dbb8 |  | note | Acceptance Criteria - Where applicable.
label | fc4c739a-e3e4-5711-9db2-138605b268f3 |  | note | Complete: Steel Barrier Fencing (Supply & Installation) ITP.
label | 29f41fbd-274f-5fd8-b029-5e9f85782ef4 |  | note | - - - - - - - - -
label | bb109321-d34a-5234-8e3f-30b058599ae1 |  | note | Reference Documents - IFC Drawings
label | 82985c24-537b-505b-a398-e47ce292e783 |  | note | - - - - - - - - -
label | a031165b-6bcf-5b5e-bcc8-1e2222747b8d |  | note | Inspection / Test Method - Document Review
label | fa8de290-d1cf-5d53-9d13-f582705885b0 |  | note | - - - - - - - - -
label | f5d89cc5-844d-5eca-ade5-265c0a3dc3ca |  | note | Record of conformity - Structural Steel Barrier Rail (Supply & Installation) ITP
label | 480189d0-1f4f-5dac-8328-b7e7ac310b62 |  | note | - - - - - - - - -
label | 53841263-002d-57dc-a78c-ca3e02d8b1c5 |  | note | IP
label | cfd756f8-5862-5d50-94f5-bd7f28de3121 |  | note | - - - - - - - - -
label | e3924801-65c2-525f-9291-8e279e262b43 |  | note | Responsibility - SE/PE
label | 1bcbd3fd-b67a-572e-af58-44a1bb62a002 |  | note | Surveyor
label | adb69e0d-31c0-51d3-944f-eec431d762a6 |  | note | - - - - - - - - -
date | d965d180-1605-5d4d-8a0b-533fc24c261a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - As-built Survey
label | 497a7fb4-8521-5aff-bc10-46428285fee7 |  | note | Frequency - Each element
label | ced52d15-de9f-5989-93c2-f2edad9e0084 |  | note | - - - - - - - - -
label | 817ff4a7-9dd2-582a-8859-6c9de9bee672 |  | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances in Cl.610.47
label | 2275339e-07b7-5e44-858e-689f53024d00 |  | note | Attach: Survey As-builts / Survey Report
label | 4de31b99-a071-5e8b-8fc9-57ec62828c45 |  | note | - - - - - - - - -
label | 6f9ef60b-3290-517e-844d-a5875cbe22fc |  | note | Reference Documents - VicRoads Spec.
label | cc608786-7ed3-5989-af79-52be9f049e76 |  | note | Cl.610.47
label | 65e4d4f6-6804-5dad-8ad1-10f5c078de8c |  | note | IFC Drawings
label | cd68885b-2472-5164-9785-29ff5b58113d |  | note | - - - - - - - - -
label | a8aa3dd3-8c31-593a-a387-798eabf3d4b8 |  | note | Inspection / Test Method - Document Review
label | a8b3085d-d990-5b2c-a923-e5d5ac23fff2 |  | note | - - - - - - - - -
label | 6e3b27d6-0e93-56d9-a403-4c3581d2d725 |  | note | Record of conformity - Signed ITP
label | bcca2746-33d2-5649-b261-a8beccd60a03 |  | note | - - - - - - - - -
label | fb6f8301-f055-5d12-b13e-0e754de6be1b |  | note | IP
label | 4b29c789-7c3a-567e-b084-56b48c040e17 |  | note | - - - - - - - - -
label | 6d8a67a2-3cf0-599e-aca2-d40308759a2b |  | note | Responsibility - SE/PE
label | ee50563b-1962-5616-a81e-ff25a3fc88b8 |  | note | Surveyor
label | a9ac3baf-04ee-5874-b3d9-3b710b78b685 |  | note | - - - - - - - - -
date | 535c50ca-c888-58a1-841b-b61809d4585f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Non-conformance Report (NCR) Closure
label | a976a1af-1f31-58c9-81ed-ec4b497cc5f8 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | c55ef204-e466-57ed-ba23-a801115aaffa |  | note | - - - - - - - - -
label | ae073dba-3186-5e52-a140-a38fcddfca54 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 8dd09611-3be4-5535-83c0-d0194281c2fe |  | note | - - - - - - - - -
label | ed77e5c2-519d-5b73-8c3e-0b9a8baf0656 |  | note | Reference Documents - FH Quality Management Plan
label | c3d0b0f6-86b0-5a4e-a316-6d2eb3100c29 |  | note | - - - - - - - - -
label | 13473713-7332-53e0-b69d-143ba5b8bff2 |  | note | Inspection / Test Method - Document Review
label | fe35efb0-af08-593f-bcfb-e7aa6c791fe0 |  | note | - - - - - - - - -
label | a08ca9b2-4cf1-5374-844a-59666795c765 |  | note | Record of conformity - Signed ITP
label | ee31b202-b601-5904-b451-b667a2d983c4 |  | note | - - - - - - - - -
label | 3eeaaa11-750b-582c-b25f-34422eae6654 |  | note | IP
label | 8abf7bfe-d939-5237-9ebb-5a3cfb76502c |  | note | - - - - - - - - -
label | b16d672b-ecd1-5384-a210-706f357a55e5 |  | note | Responsibility - SE/PE
label | 99536755-dd7e-572f-a352-1b673f0a6a34 |  | note | - - - - - - - - -
date | dac40f6c-99a8-537b-b6ba-17f7c1f74ec5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 1f8657d2-54e7-5923-8c0b-99ef273af93c |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 941946e5-41d4-56da-91ed-f78130dced46 |  | textbox | Print Name:
text | dc149d26-1f8e-5789-aba1-e7770985b24f |  | textbox | Position:
date | 7b3790cc-4f5c-505f-a44e-78a02a807e74 |  | date | Date:
date | 211ff6cc-cf81-5273-9ecc-15970dcb79f8 |  | date | Work Completed On
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification.
select | ea6ba6f0-6088-58af-911b-e2521376a02c |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | da2a95d9-0410-555c-9d36-803f4866e864 |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | be4ab3ed-673d-53e9-99c4-dad81eadbd22 |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | 7e86f849-51c3-5d1f-8067-3a60f759a264 |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | 25dfa9ff-f90d-5687-bfc2-fba10d08e790 |  | textbox | Other:
select | 4d8f824f-9a68-55f0-a65f-755a899bff7d |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | a47583af-7ffe-5672-aa8e-4d1c54142a71 |  | date | Lot Closed On
text | c8cd9bf4-b5d2-5905-b98e-4886ff14908c |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-017-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0017 - Underground Stormwater Drainage | abec4b66-3279-45e0-813f-2db6d5a923a0
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | e92d9a3d-d737-5fbd-bd16-740439e7421f |  | date | Lot Created On
date | 39dce24c-4fb9-54bc-85d6-89d9d217510b |  | date | Lot Opened On
date | 9739a878-9623-5f39-80b7-256487320f5b |  | date | Work Commenced On
select | 41c0d26e-4fc2-52b0-827e-31dad0a986f2 |  | dropdown | Lot Type | CIL-Civil Lot, DRL- Drainage Lot, EAL- Earthworks Lot, ELL- Electrical Lot, UTL- Utility Lot, STL- Structural Lot
text | 55a2dc37-9ed0-53a9-8af4-cc1c028a23ff |  | textbox | From and To Chainage
select | 6a0acfca-16e0-51e7-875f-86344dd27e03 |  | dropdown | Construction Element | STOR - Stormwater
select | b5b7300d-5952-5b36-9a77-8e2bda53ba28 |  | dropdown | Activity | DRAP - Drainage Pit
select | fa4fff0f-3be3-5de3-b7f3-16b4de24af1e |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | d3ffcf41-7e0a-518d-ac32-06266b1a594d |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | 776bfa7b-c5e0-597f-9ef7-417b07f0e2d3 |  | textbox | Engineer Responsible
text | 542e5ac4-4709-5119-b287-c99b551b2f11 |  | textbox | comments
checkpoint-group |  |  | section | 1 - Stormwater Products and Materials
checkpoint-status |  |  | checkpoint | 1.1 - Drainage Pipes
label | 22766316-a1be-5885-979d-45bafabf097b |  | note | Frequency: Prior to Commencing Work
label | b54308d9-e20c-539c-bf9e-41b0416b4bb0 |  | note | - - - - - - - - -
label | f372daaf-e779-5993-b668-d9069b67432f |  | note | Acceptance Criteria: Drainage pipes and culverts supplied in accordance with 701 and AS/NZS 4058.
label | 6e45ba54-42b5-562a-9f1f-c0933975998e |  | note | Documentation as per 701.05 is available in Teambinder Material Approval form
label | ae0bd16d-e2fa-56ca-8a8c-8a3eae69ea69 |  | note | - - - - - - - - -
label | fac613e5-d08f-5ea0-b850-56b8b1c783bc |  | note | Reference Documents: 701.04, 701.05
label | ebf8b2eb-263e-5f9c-9426-ed551c212581 |  | note | - - - - - - - - -
label | 092e4e07-2d01-5cfe-80c2-ad8c7d44f554 |  | note | Inspection / Test Method: Document Review
label | e1b50692-28c0-5273-ae26-726fde286518 |  | note | - - - - - - - - -
label | 34c02cc0-2896-59e4-bd81-4f46169a5bf8 |  | note | Record of Conformity: Insert Teambinder Material Approval Number
label | 33e8cd24-23b0-57ce-97ac-d9434c54960d |  | note | - - - - - - - - -
label | 7c7210ce-4baf-53f0-8961-87db4ee47021 |  | note | IP
label | c52aaf31-a183-5d9d-936e-b729606bd3e3 |  | note | - - - - - - - - -
label | 0d82c38e-8a54-5070-8c7c-88538b11838c |  | note | Responsibility: Engineer
label | 210d810a-52c6-57ae-9948-dc9b0e74d3fd |  | note | - - - - - - - - -
text | e2b2b8e8-56c4-5312-aab0-decfc9a03a88 |  | textbox | Enter: Teambinder Material Approval Number:
checkpoint-status |  |  | checkpoint | 1.2 - Drainage Pits
label | 6636fa73-f3af-5c87-864a-d3febb693c55 |  | note | Frequency: Prior to Commencing Work
label | 2a145988-8cbe-5a49-ac87-29e0f75dd726 |  | note | - - - - - - - - -
label | d6d8d709-7700-5ddd-9387-cac5113e46d1 |  | note | Acceptance Criteria: Drainage Pits are supplied in accordance with 705.07.
label | 3b3d2ff3-a663-5fb1-b864-a4f5258477c8 |  | note | Pits deeper than 1m to be fitted with step irons as shown on the drawings. Step irons to be compliant with AS4680.
label | 5c198d32-b422-5da2-8fcb-315d4ce9d07e |  | note | Suppliers documentation has been submitted via Teambinder Material Approval form
label | a4544659-0383-5248-a0e8-d6706f3b981d |  | note | - - - - - - - - -
label | d8f8bb33-825c-5fc2-b03b-1b506e1364e8 |  | note | Reference Documents: 705.07
label | 746dc524-b537-590a-9ac3-0429fabf3597 |  | note | - - - - - - - - -
label | f6ed58aa-c6ec-5452-9923-55c17c1fe09d |  | note | Inspection / Test Method: Document Review
label | 8b292cfa-280e-5adf-989d-f0be6b7201cd |  | note | - - - - - - - - -
label | 763ba814-9e4e-5a1f-9757-ec0cf9e1c4b9 |  | note | Record of Conformity: Insert Teambinder Material Approval Number
label | 13b313e4-fa1d-547c-a233-cda3203046cb |  | note | - - - - - - - - -
label | 7e7ad66b-5368-5b50-8ec3-cc7afd48831d |  | note | IP
label | 1a1bed6e-f0e1-5adc-a29e-32151c622a55 |  | note | - - - - - - - - -
label | cf44ff47-6a93-566b-98c2-7ed3a978bcfd |  | note | Responsibility: Engineer
label | 256ce6cb-de2c-5b86-8728-9983f3b49cbb |  | note | - - - - - - - - -
text | 4527c2ca-21e1-557e-a923-227ee736c440 |  | textbox | Enter: Teambinder Material Approval Number:
checkpoint-status |  |  | checkpoint | 1.3 - Drainage Bedding Material
label | e19be3b8-ae54-5b8e-9837-0c116580754d |  | note | Frequency: Prior to Commencing Work
label | 5e6d811c-6cdb-5737-994d-54c676eba84b |  | note | - - - - - - - - -
label | ddfdee31-f5af-5f75-a0c9-6930a68b85dc |  | note | Acceptance Criteria: Bedding Materials comply with Table 701.081 and 701.082.
label | 4c522a25-3457-5b0f-8ca4-24aee166dcfb |  | note | Material Approved via Teambinder Material Approval Form.
label | 19782b71-04b3-5cd8-8867-a3ff9f37a4c0 |  | note | - - - - - - - - -
label | 45905e61-c68a-5de9-8d33-cdeea3efeea2 |  | note | Reference Documents: Table 701.081, Table 701.082
label | 96058c52-c5cd-5117-b355-6cb39c6fceeb |  | note | - - - - - - - - -
label | 99c506f2-a8e8-536a-86cc-3cd47867be30 |  | note | Inspection / Test Method: Document Review
label | 8518de3a-917b-5b51-bf93-6d2317a590fb |  | note | - - - - - - - - -
label | 1d4c3696-984b-55d8-b5b7-4b92bbb849c4 |  | note | Record of Conformity: Insert Teambinder Material Approval Number
label | 4bd13b4b-c77c-5b20-982e-8fa00681a547 |  | note | - - - - - - - - -
label | 7727591c-443f-5a3c-84c6-f8b881cabcfd |  | note | IP
label | e5ae0845-7992-54d7-86a7-e8bed2f33b20 |  | note | - - - - - - - - -
label | c4900e5d-585b-52b3-9634-58daadd34ac3 |  | note | Responsibility: Engineer
label | 3ae9cbae-3083-5dff-a0f8-413acad2b83c |  | note | - - - - - - - - -
text | 304e7d5a-386e-522d-9052-db371321adfa |  | textbox | Enter: Teambinder Material Approval Number:
checkpoint-status |  |  | checkpoint | 1.4 - Drainage Backfill Material
label | d7b8f0fe-ca46-54c4-a917-3f20bfb4f44b |  | note | Frequency: Prior to Commencing Work
label | fbab3b21-0376-56e7-bb06-e6e7e464f206 |  | note | - - - - - - - - -
label | 434c63c6-bd99-5aec-8bee-2ba2c1fc3ce6 |  | note | Acceptance Criteria: Select and Ordinary Backfill Materials comply with tables 701.081 and 701.082
label | 57a99c2c-c342-5ae8-a3ba-419e77e9d1c7 |  | note | Material Approved via Teambinder Material Approval form.
label | e11b3697-1ab9-5594-bdf0-093ec4474066 |  | note | - - - - - - - - -
label | ebbfe5b7-fbb5-5ac6-ba5c-8e79aa3452f8 |  | note | Reference Documents: Table 701.081, Table 701.082
label | de4c555e-8917-55cd-a654-e7a9169bcf44 |  | note | - - - - - - - - -
label | 16250bde-ba4b-5aef-af3e-7ff3a26c7929 |  | note | Inspection / Test Method: Document Review
label | ce95e05c-5ee5-57a9-ac79-76da13922ea4 |  | note | - - - - - - - - -
label | e61fc681-5b3c-556b-ae91-2b2d0c91e48f |  | note | Record of Conformity: Insert Teambinder Material Approval Number
label | 60ccb4e6-3e9b-52e2-ae9b-bd03f3509177 |  | note | - - - - - - - - -
label | 7e86c833-d493-538c-a908-d4347641bdc3 |  | note | IP
label | 31646755-481d-5a0c-8764-bfc9efe82736 |  | note | - - - - - - - - -
label | 3e73a08f-fbdd-570c-81c9-15c678614f6f |  | note | Responsibility: Engineer
label | 869f3726-cee7-5a58-89f6-c50d03afb3d0 |  | note | - - - - - - - - -
text | 1b359225-72ea-5c94-b355-3c78ce8f6fa8 |  | textbox | Enter: Teambinder Material Approval Number:
checkpoint-status |  |  | checkpoint | 1.5 - Bedding & Backfill Material Testing
label | bfbd84f4-7379-508c-8ad2-41bf0776d07b |  | note | Frequency: 1 per 1,000 tonnes or part thereof
label | ec0c78df-f9d6-5c98-9ab2-3d6be3f3ddc9 |  | note | - - - - - - - - -
label | 5a16df30-a230-574b-a954-42b1962d6e2f |  | note | Acceptance Criteria: Bedding and backfill material tested at to ensure materials comply with the following:
label | d6c8c507-d87b-5b56-a2f7-772c0f4fc780 |  | note | - - - - - - - - -
label | 0e7c6f47-572b-5a2e-858d-2fa9b1dc2d76 |  | note | Reference Documents: Table 701.091, Table 701.092, Cl. 701.29, Table 701.291
label | 2e1c20b3-214e-551a-bfb7-59b94a1a0a7b |  | note | - - - - - - - - -
label | 625f8ee2-77a4-535a-82e2-582687548cee |  | note | Inspection / Test Method: Grading and Plasticity Index
label | dd8884e7-d708-5853-984b-b49d72c772fe |  | note | - - - - - - - - -
label | 23627a00-5ac2-5892-89b6-fc3d8574db33 |  | note | Record of Conformity: Test Records
label | 5ee6fd00-dc90-5e36-8aa5-eaf237d1acf7 |  | note | - - - - - - - - -
label | d47684ee-1f21-5543-8deb-e7a47cca8760 |  | note | TP
label | 9107009f-346b-5051-9906-4c25f3497ddb |  | note | - - - - - - - - -
label | 0ad3e150-695c-57b4-a8bb-114d93f23d43 |  | note | Responsibility: Engineer
checkpoint-status |  |  | checkpoint | 1.6 - Material Inspection
label | 5a3b3969-0c5a-557c-b122-09d96dd847ce |  | note | Frequency: Each Delivery
label | 3e1a52d3-b4d0-5984-b947-2868e2562565 |  | note | - - - - - - - - -
label | 394bc114-7e0f-528f-b4ce-ad7cbdaf042f |  | note | Acceptance Criteria: Material inspection to be raised on ConQA for all precast pits, pipes and culverts.
label | 334f84c7-1382-5a92-bf3f-b7515920b353 |  | note | - - - - - - - - -
label | b279beb3-ea8f-579d-a028-a8d6192478cb |  | note | Reference Documents: ConQA Order Acceptance Form
label | b7fe6f83-e12c-58b6-94c4-b6ff45f970a0 |  | note | - - - - - - - - -
label | 874b2342-1336-53a4-88ef-c97c6f6ed0bc |  | note | Inspection / Test Method: Document Review
label | 8c1c872c-315e-56ed-8039-94416081c0c8 |  | note | - - - - - - - - -
label | cd60a27e-44be-5b62-b269-50ffcaeb9842 |  | note | Record of Conformity: Insert ConQA Material Inspection Reference
label | 518e5600-e81a-5f1a-9241-28dd1e4cdb42 |  | note | - - - - - - - - -
label | 831c7a85-35c2-5377-88e9-64607b15041f |  | note | IP
label | 6c874eed-65d0-56f4-abca-6aaa7cc18b1b |  | note | - - - - - - - - -
label | 12dafda4-1171-50ad-bf00-ce949a03db5b |  | note | Responsibility: Engineer
label | 327e2395-2359-5eda-aa2e-c4808f1c7cdf |  | note | - - - - - - - - -
text | a4aa4d2e-091a-5616-9d3f-b3fed311c9d5 |  | textbox | Enter: Material Approval Number:
checkpoint-group |  |  | section | 2 - Preliminary Works
checkpoint-status |  |  | checkpoint | 2.1 - Work pack briefing
label | a8acbdec-d91a-5185-936a-7efc88df2f0c |  | note | Frequency: Prior to Commencing Work
label | 028258d9-cda2-5eb9-97e7-7ec94460c63d |  | note | - - - - - - - - -
label | c1529e36-bbb0-5eb6-a208-f81c86737e2b |  | note | Acceptance Criteria: All personnel on site have been briefed on the relevant work park to scope of works.
label | 1a675817-fe7e-5f9b-9e78-947f03d958b2 |  | note | - - - - - - - - -
label | 880ca6e4-5d53-51fc-bf0c-6aa859403085 |  | note | Reference Documents: WP
label | 7a17ba8e-b3c9-580c-b47b-4f35e1f8ff59 |  | note | - - - - - - - - -
label | 3ae53932-aec7-59b6-82d4-4c80e4ab7b5e |  | note | Inspection / Test Method: Document Review
label | 0737e733-df1e-549d-b2af-3b91e34c0e1f |  | note | - - - - - - - - -
label | a4b5b497-f22a-5fe3-8321-1a5710918ab6 |  | note | Record of Conformity: Work pack signed.
label | 594a789a-bcb0-5728-9b12-e38999c67070 |  | note | - - - - - - - - -
label | 105c81f4-c226-57ff-a38c-136ce5b7bbdc |  | note | HP*
label | d0d50934-3345-5def-84c4-b92513058657 |  | note | - - - - - - - - -
label | fb5eba59-5349-54f8-878f-17984d6a5ede |  | note | Responsibility: Engineer / Foreman
checkpoint-status |  |  | checkpoint | 2.2 - Check that current revision drawings are being used
label | f45ef929-b226-52bf-a7b9-70ca429b6b52 |  | note | Frequency: Prior to Commencing Work
label | 55a13f08-e9b4-56d3-bcd5-ae9097ed303a |  | note | - - - - - - - - -
label | a9a61edb-3f5a-5c90-b313-ea11e42fc4d4 |  | note | Acceptance Criteria: Issued For Construction (IFC) and latest available design revision in use.
label | c4abc12d-b064-5c01-bb83-9b1d1c0ac75b |  | note | - - - - - - - - -
label | 62b34db4-a5b1-5394-adba-066342220566 |  | note | Reference Documents: IFC Project Drawings/ Drawing Register
label | 5ba80b95-d6d2-5bda-8c42-dd523b217a94 |  | note | - - - - - - - - -
label | 8c55e6fa-6fd5-5c25-8817-90158b874007 |  | note | Inspection / Test Method: Document review
label | 5a8e1193-f5b4-5498-969f-479291d97b4e |  | note | - - - - - - - - -
label | ab68c7fd-5741-50b0-8297-2b1a0b32e53e |  | note | Record of Conformity: Latest revision IFC drawings
label | e5fff2bf-9098-5e71-ac16-d9b8f5a96615 |  | note | - - - - - - - - -
label | 4c22562b-6431-5b30-b48a-d9024488a917 |  | note | HP*
label | de7b831f-ab66-569f-a8ae-f00247bfa2eb |  | note | - - - - - - - - -
label | 3ea2eb11-ce44-53e0-9f2f-b0f8c84ad76e |  | note | Responsibility: Engineer / Foreman
checkpoint-status |  |  | checkpoint | 2.3 - Ground Penetration Permit (GPP) issued
label | 94de2eb4-02a1-50a7-b364-c255a7b8cbf6 |  | note | Frequency: Prior to Commencing Work
label | a368e8df-ce0f-5005-abc0-b2135e4f84ae |  | note | - - - - - - - - -
label | 45c3db0d-f137-5c15-8cb6-433bd07a1183 |  | note | Acceptance Criteria: Current GPP signed and specific to the area where works will be executed. Including walk through of the work area with the site team and GPP Coordinator prior to works.
label | ab9f9cc2-42d7-52fb-8bf4-88900653a16f |  | note | - - - - - - - - -
label | 5c322aea-cb4c-5aad-a0ad-f3f086db9f41 |  | note | Reference Documents: Excavation Permit
label | 137771d9-603b-5416-8f03-0ad87ecace6e |  | note | - - - - - - - - -
label | c8d1a714-e38e-53da-84ae-83e7c4e50147 |  | note | Inspection / Test Method: Document review & Site inspection
label | 6ceb3459-fe65-5e34-83c8-8906020eeed1 |  | note | - - - - - - - - -
label | e004f708-e529-588f-96aa-f03115060604 |  | note | Record of Conformity: Excavation Permit #
label | 075e8279-17a8-5d83-9cf9-01bfdc1bbe78 |  | note | - - - - - - - - -
label | 6eb524f2-a085-5e50-b295-28a36b17eef1 |  | note | HP*
label | 303f8a7c-4645-54f3-b72e-be3f14270807 |  | note | - - - - - - - - -
label | cf63a968-4186-5105-b2fe-79f5d4106969 |  | note | Responsibility: Engineer / GPP Coordinator
label | dfdf21d5-2430-596f-b5ea-a50500322370 |  | note | - - - - - - - - -
text | 9bf34e0d-7f61-5aa1-8bb7-56bdc0dcf2a0 |  | textbox | Enter: Ground Penetration Permit #:
checkpoint-status |  |  | checkpoint | 2.4 - Usage of HDPE Pipes
label | 8ef4e12f-af74-5223-8dcc-4b1d4fff8d31 |  | note | Frequency: Pre Process Approval
label | d12615ff-862c-5719-b856-0dafdf1ebbd3 |  | note | - - - - - - - - -
label | 87e215b4-0bca-50df-ad92-eea0423db808 |  | note | Acceptance Criteria: HDPE (Stormpro/Blackmax) pipes to be used only under non-paved areas inline with the latest design.
label | f120ce07-2676-53bc-8641-cb3d787a1845 |  | note | - - - - - - - - -
label | 9b9045fd-3a3b-5cee-831e-a08158af0303 |  | note | Reference Documents: VicRoads Spec.
label | 5d3cd34a-3013-5bc7-85b5-585f7f5a8e6f |  | note | Cl.619 Cl. 701.04 Cl. 701.05(a) AS4058 AS4680
label | 83ee5251-ab78-50ed-bec4-47c916392121 |  | note | - - - - - - - - -
label | aab6b5f0-763d-5082-97b1-bd4752a59575 |  | note | Inspection / Test Method: Teambinder Material Approval
label | 2bec9645-aabb-5abd-9376-5b052ec7317b |  | note | - - - - - - - - -
label | c8371cd3-92d8-5fbc-b256-cc7e288e1b75 |  | note | Record of Conformity: Manufacturer certificate or accreditation
label | d2e19300-bcd0-50c2-a361-2ea9664d4c6b |  | note | - - - - - - - - -
label | a488adb0-1b5d-5d01-8421-da4981f63618 |  | note | IP
label | 1c6eefab-e5ac-5cf5-ae6d-a6fc177c800e |  | note | - - - - - - - - -
label | 5ce07cdb-9f2a-5cba-a41e-819c8e844c71 |  | note | Responsibility: Engineer
checkpoint-status |  |  | checkpoint | 2.5 - Backfilling with cement stabilised sand (If required)
label | 29776e93-68b2-5e47-9147-2d6d625739b5 |  | note | Frequency: Each drainage line
label | 53cebda3-41d5-5c18-b088-10286ede4c6d |  | note | - - - - - - - - -
label | cdd44e6f-05dc-558b-9080-2a72a904826e |  | note | Acceptance Criteria: Subject to superintendent approval, underground stormwater drains may be backfilled to half the pipe diameter or box culvert height with 3% stabilised sand. Mixture to have a water content sufficient to ensure penetration beneath the pipe or box culvert invert without leaving free surface water.
label | 76acfa18-2942-5feb-9489-4efbc556e96d |  | note | - - - - - - - - -
label | 4e2f545e-c015-512e-9cdb-d8ae2b682673 |  | note | Reference Documents: VicRoads Spec. Cl. 701.19(c)
label | 9883674a-8f72-5a96-92f4-eb4ebc5da40b |  | note | - - - - - - - - -
label | 8cacde7e-0755-55a9-8c53-ff198a1703e4 |  | note | Inspection / Test Method: Site Inspection
label | c219bb60-0a6d-5173-832c-fd7c306a6be6 |  | note | - - - - - - - - -
label | afffd0b2-32e6-53ab-8609-105f0e5124f4 |  | note | Record of Conformity: Superintendents Correspondence, ITP signed
label | c81f28da-fbc3-5ded-aeda-dc7ad8e4324e |  | note | - - - - - - - - -
label | 7aa05297-eab8-50c3-b938-742070eaf962 |  | note | AP
label | 9fc582e4-e3e0-56a6-964e-97516db04dcb |  | note | - - - - - - - - -
label | c2e3f42d-61e9-5f53-9232-b59dc261b63c |  | note | Responsibility: Engineer / Superintendent
checkpoint-group |  |  | section | 3 - Installation of Drainage
checkpoint-status |  |  | checkpoint | 3.1 - Confirm position of culverts
label | 9ee2a89c-f3eb-5db8-9937-a6d0be968c2d |  | note | Frequency: Prior to commencing drainage line
label | 3dbdd9f6-4eb2-50d7-a7aa-6d7fe3ed9cb2 |  | note | - - - - - - - - -
label | 8a3bd790-7a80-511f-aaa1-97e2b855eb16 |  | note | Acceptance Criteria: Prior to commencement of excavation for the culverts and stormwater drainage, confirm the position with the Superintendent.
label | 9e118bba-ad56-5a5e-9f41-c884a2aa35fc |  | note | - - - - - - - - -
label | 5beaeeb3-2ae0-5344-a6f8-41c453d00c39 |  | note | Reference Documents: VicRoads Spec. Cl. 701.10 IFC Drawing
label | 96250516-10ea-5cba-9cc3-a31f1f7a91d8 |  | note | - - - - - - - - -
label | aa53abe5-a50a-5039-9442-da65fbec4b4e |  | note | Inspection / Test Method: Site Inspection
label | c0dfa639-3ce6-596f-9662-c9f29a6e509d |  | note | - - - - - - - - -
label | a2411991-dd64-549e-b4fb-8fdc8cf2c492 |  | note | Record of Conformity: Design and survey setout position confirmed with Superintendent.
label | 89119578-1458-5be3-90c9-c4967e3884f8 |  | note | - - - - - - - - -
label | f93d3c67-71db-56c1-8da5-cfc8be8bf41a |  | note | HP*
label | 6bda32d5-d223-5a59-ac84-e486091dc660 |  | note | - - - - - - - - -
label | f4ac0245-ec6a-5046-b4c9-12cbc7d8b663 |  | note | Responsibility: Engineer / Superintendent
checkpoint-status |  |  | checkpoint | 3.2 - Excavation
label | 36148099-df8b-5d9c-bba1-08cc85ad2181 |  | note | Frequency: Each trench
label | c103f49c-cf96-5e8e-9344-7b9bb2f56174 |  | note | - - - - - - - - -
label | 10fb66cd-f844-5ecc-afb2-9e36b54ef55e |  | note | Acceptance Criteria: Ensure trench is excavated to prepare culvert foundation and specified depth of bedding.
label | f4d52b59-dacb-5b3a-9105-30ca64a25c9d |  | note | - - - - - - - - -
label | eef52e53-0a79-54d1-a803-9340738160d6 |  | note | Box culverts:
label | 1673022e-bc5e-5244-960a-4474c54d48ac |  | note | distance between culvert wall and trench wall is between 0.5 - 1.0 x the overall height of the culvert.
label | 2c9e6087-4212-5d77-ace4-d5e86827ab8e |  | note | Pipe culverts:
label | 78f395fd-1107-5935-b385-e5e7cd8cc000 |  | note | the width of trench at and below the level of the top of the pipe shall be such that the horizontal clearance from the outside of the pipe to the wall of the trench is greater than >300mm, less than <600mmm.
label | 5e466ff0-8d47-588a-8af6-e0d7a262ded9 |  | note | Pits:
label | 22a6f86f-d0e1-5094-9164-619a3fdc5f62 |  | note | Clearance from external faces of the pit to each face of the excavation to be not less than 400mm
label | 2cb6ec2b-a8ed-5dc6-ae30-dbdad4ea033e |  | note | - - - - - - - - -
label | 36bdd09d-4200-5417-b883-654e48483784 |  | note | Reference Documents: VicRoads Spec. Cl. 701.15 Table 701.151 Cl. 705.05(b)
label | 1fa5abef-2420-55f5-b289-0cc75a45e272 |  | note | - - - - - - - - -
label | 897911e0-71bd-5924-b777-0f8488749c7c |  | note | Inspection / Test Method: Site Inspection , Measurements of trench
label | d4cf18a0-06cb-54be-95b5-39e9d5f3c33e |  | note | - - - - - - - - -
label | e4316447-a934-591a-8e00-e3644059c7eb |  | note | Record of Conformity: ITP signed
label | 209ea601-7793-5279-8feb-c12e54a6c76f |  | note | - - - - - - - - -
label | a5364d71-664a-5885-ad71-b541bc26e0f7 |  | note | IP
label | 5c600d41-6378-5cfc-9f51-1db95bf5a755 |  | note | - - - - - - - - -
label | f7c9f120-b634-5d16-92a7-d0c53561c3e1 |  | note | Responsibility: Engineer
checkpoint-status |  |  | checkpoint | 3.3 - Bedding
label | dd9634cf-70cb-558a-91c6-7d338e023f85 |  | note | Frequency: Each trench
label | 4b455957-d207-5ff0-bf80-598e6886558e |  | note | - - - - - - - - -
label | 9c2a37ce-cac8-536f-bd24-1caae9442952 |  | note | Acceptance Criteria: Bedding material shall be provided and placed for the full width of the trench. The compacted thickness of bedding material following any shaping necessary shall be:
label | cae25a3d-3ebf-5355-844a-5a86a91eec43 |  | note | minimum 100mm for pipes of D< 1500mm
label | 354e2ac3-ec46-5412-b006-72466fdb824e |  | note | minimum 200mm for pipes with D ≥ 1500 mm
label | e559d7a1-a60c-5a9c-bc0c-07b79af8896a |  | note | D' is the nominal pipe diameter or culvert width.
label | 062bee77-ecc9-5314-aab0-2db2f0a13b0b |  | note | Bedding and backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
label | 4977577a-5bb2-5e0d-ac7c-2f562302a044 |  | note | Once culvert sections are in position, an additional layer of bedding material is placed to a height equal to 30% of the nominal pipe diameter or culvert height.
label | 903cf725-4460-530c-97cc-6a790b39cc3a |  | note | Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | dcd6e9e0-cfc9-59cf-a5be-26e730335a2f |  | note | - - - - - - - - -
label | 2007bcbd-1e52-5bb8-961f-1d1932173411 |  | note | Reference Documents: VicRoads Spec. Cl. 701.16 Cl. 701.20(a)
label | 1ef49b35-5967-5f69-b88a-6f5e41ce6434 |  | note | - - - - - - - - -
label | 9316dc76-5570-596d-a9c6-5270622e953a |  | note | Inspection / Test Method: Site Inspection
label | 1993da49-394e-5dfc-bebd-d4d4767cf4c3 |  | note | - - - - - - - - -
label | 645dec44-4e98-55cd-86bd-36431ec640ea |  | note | Record of Conformity: Test Report
label | 3a4b66bd-04a5-5bba-82fd-67f9dbd21438 |  | note | - - - - - - - - -
label | 3397ec67-e122-590f-aa56-361ec6dc0d33 |  | note | IP
label | db2b83f1-f6d1-5fd3-a858-35457fe2f07c |  | note | - - - - - - - - -
label | efe089a9-557d-5e80-b09f-f88372f5cee4 |  | note | Responsibility: Engineer
checkpoint-status |  |  | checkpoint | 3.4 - Laying - Circular Pipe
label | 861af292-7ddb-5c17-bf4f-832ed94e2f4d |  | note | Frequency: Each culvert
label | cbdde34f-cb41-5d25-b462-c5cee32938b2 |  | note | - - - - - - - - -
label | 55daf26a-e6ad-5534-a655-0abaae3d2bea |  | note | Acceptance Criteria: Rebate and socket ends of pipe sections are positioned facing upstream and are to be fully entered. (Laying from downstream)
label | 0c1d7f87-ecbe-584f-9baa-0fb32e6eae60 |  | note | The lower portion of the pipe shall be in contact with the bedding for the full length of each section. The compacted bedding shall be shaped to accommodate the joint collar and ensure that the pipe is supported along its full length.
label | 2bcfa05c-d689-51b3-845b-3af3ff392463 |  | note | Where applicable, the top of the pipe as marked shall be within five degrees of the vertical axis of the culvert.
label | bfe60ec3-7ecb-51b5-9ab1-29e89ecacbc5 |  | note | Spacing of multiple rows of culverts to reflect Table 701.171.
label | 717603e1-945e-5980-9a64-dc3bec66f521 |  | note | - - - - - - - - -
label | 614ea54e-3297-566f-9ffe-d9c0b292c5db |  | note | Reference Documents: VicRoads Spec. Cl. 701.17(b)
label | 791dd23c-ddec-59a5-b1d5-cd4e41a27667 |  | note | - - - - - - - - -
label | 6f18e841-3531-5c0c-a639-08cc6a1cf72c |  | note | Inspection / Test Method: Site Inspection
label | cc894041-b182-5929-93f1-047a0b9d6de7 |  | note | - - - - - - - - -
label | b3f3dfd0-d516-5ed2-8151-ad56f04edb5e |  | note | Record of Conformity: ITP signed
label | 752eef06-34f8-5cbf-8df4-4100cbea5414 |  | note | - - - - - - - - -
label | fa0faf4a-eefa-5a56-8489-a913e9bc40b6 |  | note | IP
label | 1b28d492-a011-514e-ae6b-30211ba64ab1 |  | note | - - - - - - - - -
label | d7fae9b4-3c2d-5b9e-9706-2249a2d6e597 |  | note | Responsibility: Engineer
checkpoint-status |  |  | checkpoint | 3.5 - Laying - Box Culverts
label | 48167bd3-ace5-5229-b8ce-05c33ace306f |  | note | Frequency: Each culvert
label | 11bc4c24-a994-5e77-b928-58bbf2e854d3 |  | note | - - - - - - - - -
label | 3f907d36-7611-5ee0-b225-6332797ff326 |  | note | Acceptance Criteria: Rebate and socket ends of pipe sections are positioned facing upstream and are to be fully entered. (Laying from downstream)
label | bd9375f6-3ed6-5588-a259-b0af3221ae9d |  | note | Consecutive sections of box culverts are firmly placed butted together. The top section matched to the bottom section and no lips over adjoining bottom sections.
label | 105ac6f0-b746-58df-949f-4d19a2f09857 |  | note | Contact areas between the top and bottom sections mortared.
label | 41c433e8-3007-5e4e-b73e-8666f5ce35de |  | note | Multi‑row box culverts laid with sections in each row in contact with the sections in the adjacent rows.
label | 14fb23fc-a179-5a25-94f0-dfd591d7695d |  | note | - - - - - - - - -
label | af19db28-47da-518a-8f29-2d9e44fa3721 |  | note | Reference Documents: VicRoads Spec. Cl. 701.17(c)
label | feae7603-fea9-5004-b58d-7fbf5c0ff514 |  | note | - - - - - - - - -
label | 5546184e-7e44-5352-8c53-0793238a916f |  | note | Inspection / Test Method: Site Inspection
label | 8f76d0ba-0768-5993-a1bc-387c2ed4ece0 |  | note | - - - - - - - - -
label | 0a775130-397c-536a-9b85-1e0b20b6b155 |  | note | Record of Conformity: ITP signed
label | d0ea86e3-2dd4-51ab-9cb4-5237c669602d |  | note | - - - - - - - - -
label | 7d044ffb-8711-5a47-9045-8b45eadf8189 |  | note | IP
label | dd0628c4-79a7-5ddd-b856-c3b2a35c5ff4 |  | note | - - - - - - - - -
label | 0a90e154-80f0-5289-86d7-acbd0dffb5a5 |  | note | Responsibility: Engineer
checkpoint-status |  |  | checkpoint | 3.6 - Laying - Cutting of Culverts (If applicable)
label | 9c05749c-327d-5ea3-ba3d-c8aef4840f55 |  | note | Frequency: Each culvert
label | a33db21f-e3c3-5886-ba2a-b06db808e6b6 |  | note | - - - - - - - - -
label | 8c6fe6c5-066c-5436-8143-2473a199dcbd |  | note | Acceptance Criteria: Rebate and socket ends of pipe sections are positioned facing upstream and are to be fully entered. (Laying from downstream)
label | a9fd6999-9444-5f0c-bbcf-d454f71ed818 |  | note | When cutting culvert section to length or to create a penetration, cuts to be done by machine to achieve a clean vertical face.
label | 1ee3c813-958e-50fa-8af1-abbb176f5e14 |  | note | Any exposed reinforcement shall be coated with an approved epoxy treatment to prevent corrosion.
label | 01a8e2fe-f4cd-5e5d-9da2-cd2147d973db |  | note | - - - - - - - - -
label | 48cf8cbd-3185-54bf-86b1-e721b0a595fa |  | note | Reference Documents: VicRoads Spec. Cl. 701.17(d)
label | 0bf74926-f864-57f3-903c-e2fa6d891f58 |  | note | - - - - - - - - -
label | 36e83c36-1771-5902-bd5e-9210555b10a1 |  | note | Inspection / Test Method: Site Inspection
label | 4ae8acf0-2f7e-52ef-842a-25fa68fff70b |  | note | - - - - - - - - -
label | a12ac862-48e6-587e-b68c-f3cb77fd9c62 |  | note | Record of Conformity: ITP signed
label | 9464de87-eb14-555c-9d99-e604aa23bf35 |  | note | - - - - - - - - -
label | f97a431d-66c0-5f8d-9912-fbdd6df7b819 |  | note | IP
label | 2ae72326-4258-5943-a8bb-3e890c3c7567 |  | note | - - - - - - - - -
label | 7c652262-cb92-5b21-bbf1-9b76906531ce |  | note | Responsibility: Engineer
checkpoint-status |  |  | checkpoint | 3.7 - Jointing
label | 1e8649f7-002e-5fe5-bcc8-d8ea4a15b942 |  | note | Reference Documents: VicRoads Spec. Cl. 701.18
label | c5babfbd-e335-593e-ba00-f032c985f44c |  | note | - - - - - - - - -
label | ddd64629-5e3a-520a-ad44-45b3a62e4a3d |  | note | Inspection / Test Method: Document review/ Site Inspection
label | 04a6d560-5b1e-521f-aca8-cc437f2208aa |  | note | - - - - - - - - -
label | 7fbbbe22-8f13-58f3-8d3d-cea71d69d541 |  | note | Record of Conformity: Manufacturer’s recommendations, ITP signed
label | c8459a0b-33db-5489-ad64-ccbe2210924d |  | note | - - - - - - - - -
label | 2d9be0dc-a409-50c2-86a9-4a4b1dcfe24f |  | note | IP
label | 46676cd1-496d-57bb-9250-56b29a40e5ff |  | note | - - - - - - - - -
label | 01cdbccb-c649-5c5e-a6aa-5981525cfa69 |  | note | Responsibility: Engineer
checkpoint-status |  |  | checkpoint | 3.8 - Survey
label | d9b6b30c-7083-508c-876e-01693e408d2a |  | note | Frequency: Each Lot
label | a2a57663-56aa-5783-86ec-438effc07e2d |  | note | - - - - - - - - -
label | afbafebb-2d00-501c-a89c-09a7c2ba2ddb |  | note | Acceptance Criteria: The location of each run of underground drainage has been verified by a survey pickup prior to backfill and form the as constructed survey.
label | c7d74d69-ee8e-5616-b82e-88401fefdcaa |  | note | RRJs assembled and prepared in accordance with the manufacturer’s recommendations.
label | 5d438766-0564-514b-9501-a481e39a452c |  | note | Tolerances that apply:
label | 1424841f-531d-5350-a946-68b4476be8a8 |  | note | (a) offset of entry pits required to match lines of kerbs or barriers +/-20mm
label | efae8d45-46bf-5091-81de-b6dd3d7ad06c |  | note | (b) plan location of pits other than offsets to kerb lines or barriers +/-100mm
label | 7c749712-7eae-5360-b8d6-52f78f550a82 |  | note | (c) Invert leve of pipes at pits +/-50mm whilst maintaining required drainage grade.
label | dffcb84d-e87f-519f-9098-886589114b62 |  | note | (d) Departure from design grade of pipe runs +/-10mm in 10m provided minimum grade is not less than 1:250
label | 328aa5e0-a5a0-5a89-b569-6d7752cc087b |  | note | - - - - - - - - -
label | 0c670a37-91f4-556f-af72-63d408514d97 |  | note | Inspection / Test Method: Survey
label | f8443cce-3433-59be-bec2-de3426a2c69e |  | note | - - - - - - - - -
label | 9d4cef3f-4ebb-53c1-a049-1c72b1509e54 |  | note | Record of Conformity: Survey Report
label | 6b970984-93cb-5554-be07-4454e6cbba44 |  | note | - - - - - - - - -
label | e7e89d94-a38c-5770-8dbd-1e390a816176 |  | note | SCP
label | 2f990337-12d0-5284-8ad9-7fc8e4454043 |  | note | - - - - - - - - -
label | 5dde7880-45f8-573d-bcd3-10d801bfe02f |  | note | Responsibility: Engineer / Surveyor
checkpoint-status |  |  | checkpoint | 3.9 - Backfilling
label | 28a369be-8ef8-5b61-a22e-1c171ab5effb |  | note | Frequency: Each culvert
label | 4e8c7e8e-5bcd-5647-adc2-19780c011c8a |  | note | - - - - - - - - -
label | 40f200f1-7135-52a1-82b1-19662f47d39b |  | note | Acceptance Criteria: Culvert Under Area to be Paved:
label | f0daab41-fb61-5e17-a5ed-926e347f582f |  | note | Where the trench has been excavated from design subgrade level or above, the trench is backfilled to design subgrade level with selected backfill material, and above that level with appropriate pavement material.
label | 16815c6b-b191-5cf0-8f45-fe670feb8bd7 |  | note | Where the trench is excavated from below design subgrade level the trench is filled with selected backfill material.
label | edcfad0a-4158-5b82-9ac7-6d4b3f1f41a1 |  | note | Culvert Under Area not to be Paved:
label | 8fe27fb0-caad-5414-9f80-876804f77ad4 |  | note | The trench is backfilled with selected backfill material to a level 300mm above the top of the culvert and with ordinary backfill material above that level.
label | d51ddf54-b3b1-5f5e-a8ba-dc8c7f333851 |  | note | - - - - - - - - -
label | 4120dfbf-2159-5c73-9242-f54f8a69bf36 |  | note | Reference Documents: VicRoads Spec. Cl. 701.19(a)
label | 4e7aa35e-d3c0-5801-b805-eb7b2e937828 |  | note | - - - - - - - - -
label | b42acd1e-de29-5ef2-9cf0-3cc73f6a68a5 |  | note | Inspection / Test Method: Site Inspection
label | f5decc14-dd8c-5e60-84bd-2b052c5e49a0 |  | note | - - - - - - - - -
label | 44cf7428-af74-5f6e-8e46-0a3de2708118 |  | note | Record of Conformity: ITP signed
label | e9531b1b-e136-58a2-ac1f-1e04da8fc11b |  | note | - - - - - - - - -
label | 46183100-c427-5328-b5e3-a6b556a03849 |  | note | IP
label | d3a37890-a725-5597-81ec-60ccf86ffcc9 |  | note | - - - - - - - - -
label | 7abc6312-b999-5ca8-b9e9-d4046e9c3674 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3.10 - Inlet/Outlet Structures
label | b896bea0-e610-5c93-8c58-7adc0701bb61 |  | note | Frequency: Each headwall
label | 92b8c896-b473-5d9d-84a1-e836f9ff8dc3 |  | note | - - - - - - - - -
label | bb7d74d4-d45b-5fdc-8e97-bc59ac5386a9 |  | note | Acceptance Criteria: Inlet and outlet structures constructed in accordance with the drawings and specification. Concrete used for the construction of inlet and outlet structures shall comply with the requirements of Section 610.
label | b85dab98-e501-5915-b9e8-3784d734e638 |  | note | Where the trench has been excavated from design subgrade level or above, the trench is backfilled to design subgrade level with selected backfill material, and above that level with appropriate pavement material.
label | b2a05ae7-c8ff-5ca1-bd18-7800d443dc38 |  | note | Footings extended to the depths shown on the drawings or as necessary to achieve a satisfactory foundation.
label | 72db4ace-5b02-5440-a541-ef13b8edeb26 |  | note | If backfilling to the required level, select backfill material is used.
label | 32d991fe-1ead-5506-8024-0f8a63977a4f |  | note | - - - - - - - - -
label | ad9993e2-a53e-57f4-be45-0da3a3620f0c |  | note | Reference Documents: VicRoads Spec. Cl. 701.25 Cl.610
label | 0644ca9f-ac80-5060-a567-29bc0fa278b5 |  | note | - - - - - - - - -
label | 901b2016-83ad-5845-b4f5-6603f05a7bbc |  | note | Inspection / Test Method: Document Review/ Site Inspection
label | e6d56a90-325b-5d33-8469-1cfe7bd188a9 |  | note | - - - - - - - - -
label | 35857230-9087-5c10-ade0-f7c996d11a12 |  | note | Record of Conformity: Latest IFC Drawing ITP signed
label | 419c81b9-5422-5860-b6fd-ff881f63620d |  | note | - - - - - - - - -
label | 3f009e9a-d7b0-5967-934e-9e16ea9b9bbd |  | note | IP
label | f6e93ff1-d8cd-5b91-a63c-1c5ba730dd6a |  | note | - - - - - - - - -
label | 5dd4db97-b4df-5d94-a616-b0fa46584399 |  | note | Responsibility: Engineer
checkpoint-group |  |  | section | 4 - Testing and Inspection
checkpoint-status |  |  | checkpoint | 4.1 - Inspection of drainage lines
label | 1bbf56bd-a56f-5e2a-a340-7966fb1f3a01 |  | note | Record of Conformity: Inspection Organisation, Inspection report, ITP signed
label | 47c23104-c208-5782-b5cd-e476e0f52670 |  | note | - - - - - - - - -
label | 9e94b0a5-49c1-57cc-8a2c-78d1e04d1d8e |  | note | HP
label | 3d5790ad-a99c-5356-8042-ea7e7071b1a9 |  | note | - - - - - - - - -
label | d1370bda-d7d3-59bc-964c-bb9fd0a4c0ba |  | note | Responsibility: Engineer / Superintendent
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.2 - Bedding Compaction Requirements
label | 5fbb9599-1d1b-546d-b5e3-6b32cf904c8a |  | note | Frequency: 3 test per lot. , (1 lot consists of one layer of bedding for a culvert length between pits or endwalls) , Min. 20% of all lots for each culvert shall be tested.
label | c6da021f-c26b-5d26-bcd8-cb29930ea938 |  | note | - - - - - - - - -
label | 721d2ac1-d4c0-524a-b32b-ca2c697b869b |  | note | Acceptance Criteria: Bedding assessed for compaction and /or moisture in lots.
label | a564e5e0-8f4e-5521-996f-3ac9d5daa0a2 |  | note | Bedding compacted to refusal with handheld mechanical equipment with a mean moisture ratio of 92%.
label | 0a6cc8e5-12f6-551e-9541-9405f8d9721c |  | note | - - - - - - - - -
label | a3496649-c2a0-5b29-b24f-2b97183444b2 |  | note | Reference Documents: VicRoads Spec. Cl. 701.20 (a)
label | 58da5776-422a-56d2-ae25-7c0c7de3fd3f |  | note | - - - - - - - - -
label | f11f5896-244c-5918-a6df-ab2fd2275541 |  | note | Inspection / Test Method: Site Inspection
label | 6952818c-e926-54aa-8a9f-49a4ff7214c0 |  | note | - - - - - - - - -
label | e9e2db77-3ecf-5427-b5de-b2583852de17 |  | note | Record of Conformity: Compaction and moisture Test Records , ITP signed
label | ded8086c-286c-5cbb-a8a3-d0bafe370446 |  | note | - - - - - - - - -
label | d608e5ae-c386-5800-b048-8d2041c3e11c |  | note | TP
label | 261ab013-bac9-5a62-b126-670b4518dfaa |  | note | - - - - - - - - -
label | dbab308e-4add-51b7-bdbc-d6540e1955f0 |  | note | Responsibility: Engineer
checkpoint-status |  |  | checkpoint | 4.3 - Backfill Compaction and Moisture requirements
label | de5634cd-b4ab-5a8a-ac1d-641b3b3724fd |  | note | Frequency: 3 test per lot. , (1 lot consists of one layer of bedding for a culvert length between pits or endwalls) , Min. 20% of all lots for each culvert shall be tested.
label | 51a2a5f4-225f-554d-a05b-ca2d09ad25a0 |  | note | - - - - - - - - -
label | 405923ec-6195-53be-914f-9bc4a3754bb0 |  | note | Acceptance Criteria: Backfill assessed for compaction and or moisture in lots.
label | 87d7335e-126b-5293-aaf4-316586342b1e |  | note | Backfill material which will have a nominal size after compaction of 40mm or < less compacted to a mean value of density ratio of not less than 97%.
label | 390310bb-76ce-56a4-ac2d-c1ee7a1db610 |  | note | Backfill material which has a swell equal to or greater > than 2.5% maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | a505d97f-114b-58df-90ba-12fc9ac0707b |  | note | - - - - - - - - -
label | c70bde2c-d681-5910-a8ae-8549202551ed |  | note | Reference Documents: VicRoads Spec. 701.20 (b)
label | 4442d854-3998-598d-89d4-c6567d4c26c9 |  | note | - - - - - - - - -
label | 9bbfb490-a04d-5fa5-a55c-de3dad67e9bc |  | note | Inspection / Test Method: Site Inspection
label | 7ac70a84-2e82-5eda-8bdf-7ab8db6de739 |  | note | - - - - - - - - -
label | c0da15db-00a5-56e2-b56a-817037f25841 |  | note | Record of Conformity: Compaction and moisture Test Records ITP signed
label | edaa78a3-e25a-5c9f-8e3b-348b31237d04 |  | note | - - - - - - - - -
label | bcf56000-16b7-59d0-bd0f-112d145f9ee0 |  | note | TP
label | bcee79ac-a4cc-5fe9-adba-32637ae40da9 |  | note | - - - - - - - - -
label | 9f581b20-56a1-54b5-a7ff-70187cc6db6d |  | note | Responsibility: Engineer
checkpoint-status |  |  | checkpoint | 4.4 - Flushing System
label | f8148d37-cb46-555d-8577-45fa07b0687e |  | note | Frequency: Each culvert
label | c8785619-fe8e-5036-b42f-cddc926f4ad0 |  | note | - - - - - - - - -
label | bbe0b511-2e2f-532c-ab87-a8dac48ba96f |  | note | Acceptance Criteria: Each culvert flushed clean from end to end on completion and maintained in proper working order.
label | 675d48b5-5fff-5fe3-8120-7fab613403c8 |  | note | - - - - - - - - -
label | 290423a9-6ca6-5e64-99c9-223dcab60996 |  | note | Reference Documents: VicRoads Spec. Cl. 701.28
label | 1f69dad1-984d-5ed8-a623-47c105216da3 |  | note | - - - - - - - - -
label | 0f5497c7-095c-52f5-aa4a-a81e5f0c56c6 |  | note | Inspection / Test Method: Site Inspection
label | e6545784-7c08-5c1f-8423-0b456883ba87 |  | note | - - - - - - - - -
label | 0285da57-90b5-5560-b1fd-cd2f90df9e8b |  | note | Record of Conformity: ITP signed
label | 680dee2b-4c32-5747-aa5d-ecca92bdff78 |  | note | - - - - - - - - -
label | 6a944d47-3c4a-59a6-b3ae-3a0aeab260a0 |  | note | IP
label | 6d566074-1f56-5d58-ae9c-89e13c2942e3 |  | note | - - - - - - - - -
label | 5373f07a-d457-5c8b-b5d1-6263389d95dc |  | note | Responsibility: Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
label | 3c4e4258-9770-53d5-a4ef-2ec89a95bd33 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | d0ad0eb7-42c5-5b45-8fbc-07270948a175 |  | textbox | Print Name:
text | ca2f2663-09d9-5c50-b93e-a3c52a509af4 |  | textbox | Position:
date | a370e83c-e92e-507f-9906-d286b5e5027a |  | date | Date:
date | ef638545-f411-5d96-966a-d2f228a342f8 |  | date | Work Completed On
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification.
select | b6e9e78d-a1d4-572e-8625-c11f5b0c1698 |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | 2198b652-5e60-5715-b667-4a45c95769ea |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | 2f23f6d9-a033-54f2-988b-77eb5af3b309 |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | 2087589d-2edd-51f9-a364-c413b6477bc8 |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | ff8ebc17-5cba-5341-bb1c-241c589c9f37 |  | textbox | Other:
select | 79f6b725-075e-5068-99a6-41d13fefc5b5 |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | 0f0bbfc8-7c7c-520d-8862-d27920ed5dfe |  | date | Lot Closed On
text | b20f6795-fc4f-5535-84c9-d5e64876f307 |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-078-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0078 - Insitu Pit Construction | be851287-66f1-4f8a-9ca3-a43cadd72550
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | b82cd022-aa1d-5086-ae43-751ba19750c3 |  | date | Lot Created On
date | bd1d4563-8ec5-528b-b4f3-2253441c019d |  | date | Lot Opened On
date | 742c3b16-b425-5964-a55e-a378109ed73e |  | date | Work Commenced On
select | 9b153335-1249-548c-9321-ad8069c3242c |  | dropdown | Lot Type | CIL-Civil Lot, DRL- Drainage Lot, EAL- Earthworks Lot, ELL- Electrical Lot, UTL- Utility Lot, STL- Structural Lot
text | 9f967845-ab6e-53b6-924d-e0703be216f2 |  | textbox | From and To Chainage
select | e8c9d42d-8a15-5ab2-a1bf-100cbd09641d |  | dropdown | Construction Element | STOR - Stormwater
select | 2e72b29f-d9c8-590f-8df1-90a141d04e92 |  | dropdown | Activity | DRAP - Drainage Pit
select | a592b92a-69cc-5f44-be0a-fb36c0929826 |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | 59ba875b-a661-56bf-b179-a6d0f2e19431 |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | 651407f4-c66c-50a5-8571-8a2d79ed3700 |  | textbox | Engineer Responsible
text | 670fb026-51c2-5aec-9525-d9a03bf14a61 |  | textbox | comments
checkpoint-group |  |  | section | 1 - Preliminary Activities
checkpoint-status |  |  | checkpoint | 1.1 Check for correct documentation
label | da4561b3-93b8-55a1-b566-9186a992c1c7 |  | note | Frequency: Prior to commencing any activity
label | e8910e2c-0cd8-5389-8234-c50b86964991 |  | note | - - - - - - - - -
label | 349f50c3-fda3-5660-bb1a-30cc6342bded |  | note | Acceptance Criteria: Ensure that all employees and subcontractors are:
label | eb6888db-d91f-5d2b-bd7b-689885c1e64b |  | note | using the correct and complete set of drawings all drawings are the latest revision
label | 72673838-7b92-5d36-8e76-0ceba07212ff |  | note | - - - - - - - - -
label | 6f263a52-4f8f-5ca5-8650-116b298c0880 |  | note | Reference Documents: Drawings and drawing registers
label | 8d4173ec-635c-5c18-ba5c-ce2e1937eede |  | note | - - - - - - - - -
label | dddd3163-9b27-5bef-89e1-1354f6c76dd8 |  | note | Inspection / Test Method: Visual inspection
label | 71553964-030a-5561-9a7a-6c56ca11e956 |  | note | - - - - - - - - -
label | 6e7bccaa-62fb-5407-be34-c085b2654a02 |  | note | Record of Conformity: ITP signed
label | 360144cc-78ff-5398-a341-6b2a939577f6 |  | note | - - - - - - - - -
label | 1eed8be1-0aa7-5002-83a0-f5b99559ab7d |  | note | HP*
label | 228d1c07-2a5b-597f-bb93-987678416b18 |  | note | - - - - - - - - -
text | cbec7aff-e1aa-5514-a24f-fb09b1ac8780 |  | textbox | Responsibility: Site Engineer/ Supervisor
checkpoint-status |  |  | checkpoint | 1.2 Implementation of all measures and controls
label | 1219bcfc-3dac-53fa-b5f8-02da64c9bd56 |  | note | Frequency: Prior to commencing any activity
label | 8455c975-dc9a-51b8-bc76-ebac9bd3adc3 |  | note | - - - - - - - - -
label | 05e21734-8bdb-5cb6-a87e-8a9b9ae8e9b4 |  | note | Acceptance Criteria: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | 4e29b9e6-b730-5157-8f3d-3ae3c32c9bd0 |  | note | - - - - - - - - -
label | 3c87d162-5151-5563-ba11-c08a09ea7234 |  | note | Reference Documents: PSP, EMP, TMP, JSEA, SWMS, WP
label | 7416a898-895f-569c-95b6-abea292f905e |  | note | - - - - - - - - -
label | 452d8423-4a70-5b40-8559-4fa54eebb328 |  | note | Inspection / Test Method: Visual Inspection
label | 2a2fe3d5-1d62-5668-9391-615351cc537d |  | note | - - - - - - - - -
label | 96b22bcc-1956-528e-adf6-2f19b92ac47f |  | note | Record of Conformity: ITP signed
label | d4b7837a-e85b-5c56-8496-074a4e0b57dc |  | note | - - - - - - - - -
label | b8e573f3-67cc-51a1-b737-576eb9beb345 |  | note | HP*
label | 0e45b82e-e6d1-5583-8b77-10b0d94a3c2e |  | note | - - - - - - - - -
text | 0fdd45b8-4cce-5b68-909b-a9aba78d5ddc |  | textbox | Responsibility: Site Engineer/ Supervisor
checkpoint-status |  |  | checkpoint | 1.3 Use of approved mix design
label | 89e48fa3-7441-5a87-936a-64d5358f9308 |  | note | Frequency: Prior to commencing any activity
label | 2d0489f2-1442-5f59-bf61-4221979f5fe1 |  | note | - - - - - - - - -
label | ea772bf3-373a-5a09-9b55-b5c5c222041c |  | note | Acceptance Criteria: The Contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete. Concrete shall not be placed until the mix design has been reviewed by the Superintendent, and allocated a registration number on the Register of VicRoads approved concrete mixes.
label | 844ba840-1607-5a0b-808b-af7af70fe31c |  | note | - - - - - - - - -
label | 5779e28e-7200-5933-94fe-9f7ba0999643 |  | note | Reference Documents: Cl 610.07
label | 25ac793d-07f5-5eb3-b757-909308ff9ecc |  | note | - - - - - - - - -
label | 018a5934-c061-5dd3-b282-9c405b7e668a |  | note | Inspection / Test Method: Verify
label | c2862fe6-ecb3-5518-a1a6-9fa9e54d3c3e |  | note | - - - - - - - - -
label | 6b415eea-3e15-5159-acea-8f9906665516 |  | note | Record of Conformity: ITP signed
label | dbb0c830-9947-5cca-8122-cc2eb4d2f2ac |  | note | - - - - - - - - -
label | a0de4e72-89fe-58f7-8021-9ec0b8c26584 |  | note | HP
label | f17930f7-61d0-5bb6-97db-8136445a0756 |  | note | - - - - - - - - -
text | 01ca96a3-b4a7-50b3-b1af-bfc9dd2a2799 |  | textbox | Responsibility: Site Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.4 Correct materials are being used
label | 3b8864b4-bca1-5dff-b118-bf4907c0018d |  | note | Frequency: Prior to commencing any activity
label | 862b9cb2-5173-545a-90c3-9774263c03aa |  | note | - - - - - - - - -
label | 7adb7342-f4de-50c8-a6f9-41c8b9288e10 |  | note | Acceptance Criteria: Falsework shall comply with the requirements of Section 613 and AS 3610 Formwork shall comply with the requirements of Section 614 and AS 3610 Void formers shall comply with the requirements of Cl 614.07 Reinforcement shall comply with the requirements of Section 611, contract drawings and standard drawings
label | 8c7581f1-032f-581d-965a-0dd58114e260 |  | note | - - - - - - - - -
label | 01c45d1f-b823-5ac9-9478-fe0a3816d0e4 |  | note | Reference Documents: VR Spec 611 VR Spec 613 VR Spec 614 Cl 614.07
label | 9a19f05d-b405-51ba-af23-626b78271576 |  | note | - - - - - - - - -
label | f975efaa-c93d-5fc7-baab-b56fe2b30842 |  | note | Inspection / Test Method: Verify
label | 5259f0fe-17a0-58c6-bd0d-ff4502d0323d |  | note | - - - - - - - - -
label | 0e28cdb8-7a25-5944-be53-ab56e6c011a8 |  | note | Record of Conformity: ITP signed
label | b2798bf2-0105-5a22-8bc0-d4b039e75e03 |  | note | - - - - - - - - -
label | 78b80836-f848-5afa-8a31-fba6bc7c5927 |  | note | IP
label | 7cf579e7-a5ce-5c7c-8e4e-36c2f8c37854 |  | note | - - - - - - - - -
text | ed900e39-edd0-51a0-9dae-5fcb58c6ccfb |  | textbox | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 1.5 Excavation Permit
label | 6d41bdba-b2e1-5dd0-9b44-72d82a935d5f |  | note | Frequency: Each lot
label | c9975810-8fb7-57d4-8f93-89b58e0390c4 |  | note | - - - - - - - - -
label | 7ebc6b64-cd8a-5c95-bcd4-41a626b07617 |  | note | Acceptance Criteria: An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
label | 2ed11c50-9803-5f45-b514-f6df490fbfed |  | note | - - - - - - - - -
label | 99c25f99-7b00-5cb0-9285-0a9570cd1219 |  | note | Reference Documents: Excavation permit
label | 4499864e-516a-5f2d-9115-83eba2221153 |  | note | - - - - - - - - -
label | b25f03a6-3525-55c0-96cf-0237dd4106ab |  | note | Inspection / Test Method: Verify
label | 3062b51d-6287-5ac2-ad9d-fdcaf72aca9e |  | note | - - - - - - - - -
label | dda2ff5d-e740-552b-8986-38731044008c |  | note | Record of Conformity: This ITP Signed Off
label | 1213998f-356f-51ac-89c7-099a47af9835 |  | note | - - - - - - - - -
label | 884863ca-261c-5e1f-be65-cd7386ebe7cf |  | note | HP*
label | d314bf33-9c4d-5814-b2ec-d9bc09eaaf02 |  | note | - - - - - - - - -
text | efea2048-654a-56b9-9800-d10785bc472d |  | textbox | Responsibility: Site Engineer
checkpoint-group |  |  | section | 2 - Excavation and erection of falsework/formwork
checkpoint-status |  |  | checkpoint | 2.1 Excavation
label | f147a853-08ad-5671-b4c7-0cef43d7bf79 |  | note | Frequency: Prior to concrete pour
label | bb2caa7b-e5b5-5bc5-b26b-e900b6f3610a |  | note | - - - - - - - - -
label | 23abb43f-af67-5ca5-93b8-50a7801246a2 |  | note | Acceptance Criteria: Excavations shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation
label | b60d4eaa-9b77-521f-8d01-9c3c8a847ea1 |  | note | - - - - - - - - -
label | 143a0db8-b26e-50d0-a8a8-5b79d24bfc33 |  | note | Reference Documents: Cl 705.05
label | 55a2c583-815c-5316-b74c-3deae4275208 |  | note | - - - - - - - - -
label | aff3ff37-72be-5a08-b97c-b15e8f61e91b |  | note | Inspection / Test Method: Visual inspection
label | 4def822e-9579-58e6-aa67-84305b37a583 |  | note | - - - - - - - - -
label | d0b95ab9-06d0-521d-9e66-06fd8bfbf8c9 |  | note | Record of Conformity: ITP signed
label | 6e2e7fa2-739a-5d88-bf4c-5a7bfbe8478d |  | note | - - - - - - - - -
label | d70b3dcd-b74f-553c-b0b9-8aa85cf40248 |  | note | IP
label | 0b19f3da-33a2-5d8f-a292-ef15a0ac32a8 |  | note | - - - - - - - - -
text | fdd4d632-677d-5307-b13d-92ce0de31fb7 |  | textbox | Responsibility: Site Engineer/ Site Supervisor
checkpoint-status |  |  | checkpoint | 2.2 Construction Methodology
label | c0e493fd-2e80-5878-ae7d-3b9e756a3fb5 |  | note | Frequency: Prior to erection
label | f8246b87-02b9-54c4-b8ef-fc751719a271 |  | note | - - - - - - - - -
label | 0b0dcd9c-4b80-50ec-abb5-d5df7009c56f |  | note | Acceptance Criteria: Formwork shall be used in such a manner that it can be removed without damage to the concrete. Formwork shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to to confine freshly placed concrete and maintain position and shape during construction.
label | 2966e664-8746-5a65-ba6f-c2cc06693957 |  | note | - - - - - - - - -
label | 96466afc-ccec-5f15-a114-cf240f2fb9a5 |  | note | Reference Documents: Cl 614.04 Cl 614.06
label | ead50410-710a-5789-b018-bd8840623f80 |  | note | - - - - - - - - -
label | c0a9330e-a455-5787-ac3a-94a1f74d6d7f |  | note | Inspection / Test Method: Verify
label | 2e08b15f-8dd6-539f-8c70-774d244566be |  | note | - - - - - - - - -
label | ef7836ff-d83d-5479-82e9-1d298734f235 |  | note | Record of Conformity: ITP signed
label | a04c50ba-9577-5b48-9ee0-42a1d5d747ab |  | note | - - - - - - - - -
label | 4d8ba919-b2d0-5f3b-8b53-20be29d85743 |  | note | IP
label | 33b649f8-3a35-584d-b71c-dd6cc4f695cb |  | note | - - - - - - - - -
text | 122b690d-f705-5a82-901c-237d4b6d54ce |  | textbox | Responsibility: Site Engineer/ Site Supervisor
checkpoint-status |  |  | checkpoint | 2.3 Formwork levels and position
label | 37e2ab53-0cf7-5ddf-ae57-70772f98cee4 |  | note | Frequency: Prior to concrete pour
label | 9e1f5ff4-f0d0-50d2-82bc-c975d785fb6c |  | note | - - - - - - - - -
label | 40d20c1a-aa13-5836-8113-7169f5906748 |  | note | Acceptance Criteria: A pre-pour survey carried out by a surveyor. Surveyor report obtained prior to concrete pour. Erected formwork within the tolerance (as per Table 610.461 and Table 610.462). Any errors in the level or positioning of formwork is to be corrected prior to placing concrete
label | 480704c0-8c15-52e3-bac9-de7d3b4481c6 |  | note | - - - - - - - - -
label | f1be7f87-4c9f-504c-8116-59d339c53b14 |  | note | Reference Documents: Cl 614.06 Table 610.461 Table 610.462
label | e18f58bb-aa45-51cd-850d-a1a45943b0cf |  | note | - - - - - - - - -
label | 1b5db0a7-beec-510d-beed-ff6a8cc8dd70 |  | note | Inspection / Test Method: Visual inspection
label | a8ee9932-3661-5f76-9665-f43a52b341c3 |  | note | - - - - - - - - -
label | bfdb8170-927c-53fc-b466-6c68c25a70ec |  | note | Record of Conformity: ITP signed
label | 7688466f-5826-5efd-b406-6d9e88d8ae1e |  | note | - - - - - - - - -
label | 26c39169-9fd5-5c34-bc1d-e7ecb6438100 |  | note | SCP HP*
label | cd79c428-ec82-56db-8d7a-5e9e27894063 |  | note | - - - - - - - - -
text | 689aacfd-4891-5a40-8d24-95b9c64ea066 |  | textbox | Responsibility: Site Engineer/ Surveyor
checkpoint-group |  |  | section | 3 - Steel reinforcing
checkpoint-status |  |  | checkpoint | 3.1 Placement methodology
label | 7d1d352d-6d5e-56b0-8a9b-2320d86e121c |  | note | Frequency: At all times
label | 80eacf55-c6e2-5e3a-9156-717eb962d072 |  | note | - - - - - - - - -
label | ac3b3615-82e3-5d3b-89d8-77b894e97c3e |  | note | Acceptance Criteria: All steel reinforcement to be securely held during placing and compacting of concrete Supports shall be of a material durable to impose loads without movement of the reinforcement The placement method shall not allow the reinforcement to become contaminated by contact with other steel
label | b62f2f1a-f522-53d1-8736-0d1c5509462b |  | note | - - - - - - - - -
label | 5234924c-765f-5ffc-94e8-118d34d1ed38 |  | note | Reference Documents: Cl 611.10
label | 50350abd-d55c-595d-98e6-4825dbb62e49 |  | note | - - - - - - - - -
label | a4f1e51c-59e5-53d4-b409-f2bb0dfda1eb |  | note | Inspection / Test Method: Verify
label | 7a559f86-4527-58c6-be4d-f996f04fabb4 |  | note | - - - - - - - - -
label | bac3bfc7-c320-599d-acc6-11ffec3bbb33 |  | note | Record of Conformity: ITP signed
label | ec124365-f53c-565e-b8f4-d5f3a7ad74c1 |  | note | - - - - - - - - -
label | 3c1f2cfa-c1ff-5340-92c5-c59862dbd10b |  | note | IP
label | 04f3dd64-ddf7-515a-8bce-cf41011a3826 |  | note | - - - - - - - - -
text | 1e35f7fb-fe27-50d0-a149-fc8b7dafa8be |  | textbox | Responsibility: Site Engineer/ Site Supervisor
checkpoint-status |  |  | checkpoint | 3.2 Minimum Cover
label | c4e60fe1-3270-5e04-937e-34135a6406ea |  | note | Frequency: At all times
label | 79c4bf62-ac3b-5683-9519-41b5c2d83796 |  | note | - - - - - - - - -
label | 4e05c56d-eaf5-5d55-a615-4d5bae707eb3 |  | note | Acceptance Criteria: The specified minimum cover must be maintained at all tire wire positions. A tolerance of 0 to +5mm is allowed.
label | cb25120f-6f81-539e-8c8a-7b4e72262523 |  | note | - - - - - - - - -
label | 3fe81cce-4822-5023-841a-52ecb0c6c574 |  | note | Reference Documents: Cl 611.10
label | ea951e75-7334-52c0-aa29-10af1794594d |  | note | - - - - - - - - -
label | b89f0015-e52f-520c-a75c-20982f86cb1e |  | note | Inspection / Test Method: Visual Inspection
label | ef122699-5219-56c5-bee7-9191f8794321 |  | note | - - - - - - - - -
label | e86ae757-62d7-594e-be85-3187b6913b40 |  | note | Record of Conformity: ITP signed
label | 50b5274f-3786-5a67-87eb-c487ba3c8ca5 |  | note | - - - - - - - - -
label | d8975268-5bac-54b2-97c6-9a37a5ad411c |  | note | IP
label | a2c8eab5-240e-5e54-8d39-92a9f59bb248 |  | note | - - - - - - - - -
text | eb9d2960-59a2-5353-a53b-b78772243e29 |  | textbox | Responsibility: Site Engineer/ Site Supervisor
checkpoint-group |  |  | section | 4 - Pre-pour Planning and Inspection
checkpoint-status |  |  | checkpoint | 4.1 Pre-pour Checklist
label | 0eb4ff55-dde6-5b62-a629-6e66f61a565e |  | note | Frequency: Prior to concrete pour
label | 40c99853-b585-5db6-b683-b6c343e9afd5 |  | note | - - - - - - - - -
label | e35db7e0-8bc7-59f6-a329-ab68eaf43dae |  | note | Acceptance Criteria: Pre-pour Checklist (CLA) completed and signed.
label | 3d0e84a0-d51f-5280-bc52-c0177870850b |  | note | - - - - - - - - -
label | 01e1af31-a87c-537d-b256-a52f13d85b5e |  | note | Reference Documents: CLA
label | 3f037b6f-92f0-57e9-80a6-9a228798c5f1 |  | note | - - - - - - - - -
label | de9cdb11-a6fd-53de-948a-396c0e809f15 |  | note | Inspection / Test Method: Verify
label | 07f6cddc-fa04-536d-8fb3-2b221915e7d8 |  | note | - - - - - - - - -
label | 10c2c73b-b9e9-5162-ac7b-bcfc149735bc |  | note | Record of Conformity: CLA
label | b1ad5c76-6793-5540-8fba-d1321750af0b |  | note | - - - - - - - - -
label | a0a1c6c0-2d31-51a9-8181-f8c153aacffe |  | note | HP*
label | 147e4f6a-6989-5802-8ca7-62d7b71bdd7c |  | note | - - - - - - - - -
text | 2821f6e5-49db-5cdd-9b4a-87a789c41622 |  | textbox | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 4.2 Pre-pour inspection
label | 3dcef586-00e2-5b8a-86cb-939d87c52663 |  | note | Frequency: Prior to concrete pour
label | 4b4bd10d-2414-5772-9322-39bb79d05964 |  | note | - - - - - - - - -
label | a2bb86fe-12ab-57fa-8b58-e6c6e390fe59 |  | note | Acceptance Criteria: Superintendent confirms that the inspected formwork, reinforcement and embedments comply with the project drawings and specifications. Hold Point released by the Superintendent.
label | ccac26ba-cbb2-506a-995e-30d2faed487f |  | note | - - - - - - - - -
label | 094ad2c0-425d-5a72-8ca1-cde0b7ac9810 |  | note | Reference Documents: Cl 610.18 (a)
label | 25ee1fce-76fa-5906-9fbc-be13bff228f5 |  | note | - - - - - - - - -
label | 65a0dbf2-bbc3-508f-be1e-ed02bc306ad7 |  | note | Inspection / Test Method: Verify
label | 56436b23-97a9-591b-a508-236e3dc3511e |  | note | - - - - - - - - -
label | 490d2494-662e-5c39-9a03-a0ab121398b4 |  | note | Record of Conformity: ITP signed
label | 87670014-b87d-5198-a30b-6d8c8bdc8b05 |  | note | - - - - - - - - -
label | 4abe49cb-83c6-5c00-ab34-ca2789f1ebaa |  | note | HP
label | c7e009b0-974a-5e23-a5da-dd2eae7aaef1 |  | note | - - - - - - - - -
text | f7dec5c0-7f36-53fa-abc8-36fd4d317769 |  | textbox | Responsibility: Site Engineer/ Superintendent
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.3 Temperature
label | 63764210-d98b-52b0-abc3-631d087112a9 |  | note | Frequency: Prior to concrete pour
label | 34d80346-3bf8-5edc-b91d-0ce2e9d37d27 |  | note | - - - - - - - - -
label | 29a05ac5-2a19-5b67-a0f6-e60536fa7e90 |  | note | Acceptance Criteria: Concrete shall not be place when temperature is <5°C or > 35°C. All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
label | 7165d6c2-ce4b-5034-8d50-820c190f19a6 |  | note | - - - - - - - - -
label | c0f6450d-d3c9-58f1-989c-5fbbeb086c08 |  | note | Reference Documents: Cl 610.17 (b),( c), (d)
label | c3024c11-3483-5208-a944-99b86bb972b0 |  | note | - - - - - - - - -
label | bad33b4c-3249-5d1f-92fc-6a32444589ef |  | note | Inspection / Test Method: Verify
label | 2b2142ed-9f51-52c3-aa72-6a64fe5147b7 |  | note | - - - - - - - - -
label | 9e749198-4c15-5c33-a490-52a3464ccbe5 |  | note | Record of Conformity: ITP signed
label | 7d0af27b-1476-5f2a-88b0-f5208bad7222 |  | note | - - - - - - - - -
label | d8929e63-2881-57a9-b229-b5b9e6000058 |  | note | IP
label | 45d2f951-3c80-5da0-b9fe-38c88e197f60 |  | note | - - - - - - - - -
text | b913c7e2-ffca-5ad3-980d-075327c5356b |  | textbox | Responsibility: Site Engineer/ Site Supervisor
checkpoint-group |  |  | section | 5 - Placing Concrete
checkpoint-status |  |  | checkpoint | 5.1 Carry out sampling of concrete
label | c3303099-5800-5864-b264-b82f6fcc99f3 |  | note | Frequency: Each concrete pour
label | cba7c8b1-d813-5ca1-b99e-f7a94b69587c |  | note | - - - - - - - - -
label | 82723d60-b2f7-5a37-bf29-9ed9e3f36cec |  | note | Acceptance Criteria: Compressive and slump sampled to be completed in accordance 610.16 No. of Samples: 0 to 10m3 - 1 No. 10 to 25m3 - 2 No 25m3 + refer to specification
label | 05182662-75fa-550e-9c21-9bd027556d8e |  | note | - - - - - - - - -
label | cb1ad91b-cbfc-5e89-8761-27305752288f |  | note | Reference Documents: Cl 610.16 CL 001B CL 001C
label | 90ac208c-b214-541e-8fb2-d38235cc9b14 |  | note | - - - - - - - - -
label | 7d94b6db-ab5f-55b4-805a-539c2b29cd8a |  | note | Inspection / Test Method: Checklist
label | 8d2c382f-8cf6-547a-8b01-c9fdd8168670 |  | note | - - - - - - - - -
label | dce1b94b-ae60-5b43-b3bd-22d2cd884d1a |  | note | Record of Conformity: CLB CLC
label | 9d38b445-b09f-5005-8ba7-c8b08d50c738 |  | note | - - - - - - - - -
label | c49493ae-fff5-548f-bd3c-fbd298f57888 |  | note | TP
label | 1390b934-29df-5f36-a58a-c37859d67394 |  | note | - - - - - - - - -
text | 8891acc5-69f3-5045-b875-d580710f9ac3 |  | textbox | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 5.2 Slump Testing
label | 2c43e179-d882-5ccb-b49d-f83010d7bbea |  | note | Frequency: Each concrete pour as per 6.1
label | f5eefcc9-cee5-5e85-ad7c-4ac2dd2089e8 |  | note | - - - - - - - - -
label | 7c6530d6-ae1f-59e8-a096-4f4bf8d1ffc3 |  | note | Acceptance Criteria: Slump testing to be within the tolerances specified in Table 610.162. <60mm = + or - 10mm 60mm to 80mm = + or - 15mm 81mm to 110mm = + or - 20mm 111mm to 150mm = + or - 30mm 151mm+ = + or - 40mm
label | 38310d56-63ff-5038-9ec9-1e55840307a4 |  | note | - - - - - - - - -
label | ebf2e4a7-8ebb-53ed-8e7f-306400b8e263 |  | note | Reference Documents: Cl 610.16 Table 610.162
label | 2ac6d363-bcdf-5044-9d52-b9ecd22bfbd9 |  | note | - - - - - - - - -
label | 9118a81f-3083-5690-b441-f76a652ef469 |  | note | Inspection / Test Method: Verify
label | bc2b04ac-db77-5bcb-a9ed-20367573d9e5 |  | note | - - - - - - - - -
label | dd6a9293-74f8-59d7-80d9-c35d45610b4c |  | note | Record of Conformity: Concrete test records
label | 6d20c279-42d7-56ae-b947-6e3b61777efe |  | note | - - - - - - - - -
label | 8314e131-8845-5441-8211-e4cd09bbfb54 |  | note | TP
label | b3758d16-e5c1-5d99-9553-4fe2f26352c7 |  | note | - - - - - - - - -
text | d527ef1b-43d0-5de6-b514-6b7c1eaeaa4b |  | textbox | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 5.3 Compressive testing
label | 8c3f1ebb-569e-556d-86ee-9d452963d45e |  | note | Frequency: Each concrete pour as per 6.1
label | 86ae3ead-8168-5e21-8999-b9f0ede94ba4 |  | note | - - - - - - - - -
label | 6a6387ef-3d4b-5a8f-9eaf-4f9d5750ace6 |  | note | Acceptance Criteria: A minimum of one cylinder shall be tested at 7 days and a minimum of 2 cylinders at 28 days. The average compressive strength at 28 days shall not be lower than the specified minimum compressive strength. Additionally, the compressive strength of each individual cylinder shall be no less than 90% of that at 28 days.
label | 4fd8b6db-3593-57a9-a40f-a28764616e33 |  | note | - - - - - - - - -
label | ef5ca710-443f-5e27-a00a-d800963422c7 |  | note | Reference Documents: Cl 610.16
label | 049a4378-579e-542d-b829-96dd04061f02 |  | note | - - - - - - - - -
label | db3e0621-64b0-5b68-9e4f-04da5e46818b |  | note | Inspection / Test Method: Verify
label | 8e43652d-cbae-531b-a8ea-b304be1faa16 |  | note | - - - - - - - - -
label | cbe7d77f-b193-5f8d-8f0b-5518148b981a |  | note | Record of Conformity: Concrete test records
label | 810866b4-8b90-5ae5-b516-d52b95395d6d |  | note | - - - - - - - - -
label | 7a393d99-edd4-51b1-8c9c-400c7aa1b2ea |  | note | TP
label | e6321a4f-e69a-5eeb-8354-7eb46eeed518 |  | note | - - - - - - - - -
text | 2d5b1152-2b5c-5e10-979b-ce686272eb9e |  | textbox | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 5.4 Cleaning formwork
label | 509ece41-bc54-5fdc-8b83-69380bea6124 |  | note | Frequency: Each concrete pour
label | 2e090620-19b6-5a29-8327-1d2bb4159288 |  | note | - - - - - - - - -
label | 2fa06318-71ac-5b6d-841d-a123f2651be2 |  | note | Acceptance Criteria: Concrete shall not be placed until all foreign material has been completely removed from the forms
label | 7f2b91b1-4a56-5f14-a16f-f75efc86d772 |  | note | - - - - - - - - -
label | ca3d4b45-20e0-5838-925a-573079c328e2 |  | note | Reference Documents: Cl 610.18 (a) (iii)
label | 1de966d5-efe7-5ff8-b123-4070bf3e0022 |  | note | - - - - - - - - -
label | a68aaea3-0cd7-5aaf-b137-bbab92411701 |  | note | Inspection / Test Method: Verify
label | 414e7692-cae9-55da-852d-03cd6896f5cd |  | note | - - - - - - - - -
label | d043cc49-8420-5f9c-af2f-2f744aef941e |  | note | Record of Conformity: ITP signed
label | c3e7834f-a581-56b1-b4d8-bb43043de1e0 |  | note | - - - - - - - - -
label | 17836d7b-f36b-50a1-ad33-7672c3d03396 |  | note | HP
label | 15cb02c3-67f9-5bde-854e-0989f16069a0 |  | note | - - - - - - - - -
text | d5825b1f-b9a3-53eb-9414-8164b0b716e9 |  | textbox | Responsibility: Site Engineer/ Superintendent
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5.5 Discharge time
label | dbe8e9b7-0f94-5928-b5ee-2f59f26fa465 |  | note | Frequency: Each concrete pour
label | faf53587-0a1c-5412-928d-5790d6458081 |  | note | - - - - - - - - -
label | edfe2ba8-1093-561d-ad77-456f55778689 |  | note | Acceptance Criteria: Discharge time (concrete placed and compacted) < 60 minutes from batch time unless approved otherwise.
label | f41fa240-1b26-55e4-b8f2-8aa40001889b |  | note | - - - - - - - - -
label | ce1931da-a7dc-59c4-85a7-7b9861d54c98 |  | note | Reference Documents: Cl 610.13(f) CLD
label | 53c22cc2-1322-595d-88f5-3987cc20000f |  | note | - - - - - - - - -
label | e1bc90e1-13de-5abd-89ec-53973cc65d09 |  | note | Inspection / Test Method: Checklist
label | b93ac630-c2da-5b18-be64-d8bb14d56cae |  | note | - - - - - - - - -
label | f1c66d17-53ae-5f28-90ed-6d0f3318b326 |  | note | Record of Conformity: CLD
label | f68f9ec1-97a0-506b-9c02-6f5ffa52899a |  | note | - - - - - - - - -
label | efda79d0-d423-585b-ab65-1a27e55f81a4 |  | note | IP
label | cf582696-e27c-5f86-b1c8-cfb43b2aa19a |  | note | - - - - - - - - -
text | 9609408d-cfee-5e93-b150-caa6e6ed647d |  | textbox | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 5.6 Placement methodology
label | d484509b-c933-5703-85bc-c22b946b65da |  | note | Frequency: Each concrete pour
label | c79c220b-05b2-5331-a7c8-53de15d54236 |  | note | - - - - - - - - -
label | 7a3d57e5-df0d-5255-85ed-3746867c8550 |  | note | Acceptance Criteria: Concrete shall be transported, handled and placed in a manner that will prevent segregation or loss of materials. Concrete shall not be freely dropped from height >2m. Concrete shall not be moved horizontally by vibrators
label | 2a1d3d6b-06d0-5dc2-a3e6-1543ff6d02b7 |  | note | - - - - - - - - -
label | 80df1af2-b8ff-567f-a15f-dc54899a0014 |  | note | Reference Documents: Cl 610.18 (a)
label | 2accb996-3982-5784-96a7-e8d4bb1fa898 |  | note | - - - - - - - - -
label | 16d30335-50a2-548c-b5ef-49f437570956 |  | note | Inspection / Test Method: Verify
label | 45ca8c1a-99bf-514a-b3d5-3040f6c12cd0 |  | note | - - - - - - - - -
label | bbc70f59-c378-566f-a1f6-38396c477bb8 |  | note | Record of Conformity: ITP signed
label | e369c3a0-aa23-573d-825b-40233751fa89 |  | note | - - - - - - - - -
label | 0224030a-e4e1-5826-9c6c-5eeaea8fd23f |  | note | IP
label | 4eb5439b-962e-5631-8d04-79aba533bf80 |  | note | - - - - - - - - -
text | bf8f4df5-5669-501d-b26d-96267c2d9889 |  | textbox | Responsibility: Site Engineer/ Site Supervisor
checkpoint-status |  |  | checkpoint | 5.7 Load Spacing
label | f1582dcb-d8fa-519e-92c7-d65a7c2de946 |  | note | Frequency: Each load
label | e2800fd3-4ef7-58eb-ab49-964d0d8f3494 |  | note | - - - - - - - - -
label | 02efb41c-3d3f-57a4-a980-cd52d0259d0c |  | note | Acceptance Criteria: During continuous pours their shall be no more than 25 minutes lag time between truck loads (From Finish to Start)
label | 1c8414bb-56c3-5d0b-9171-a817eea0c3fb |  | note | - - - - - - - - -
label | 7ed6676c-0938-5b54-bfc5-70114207c2b3 |  | note | Reference Documents: Cl 610.18 (a)
label | 2a33a8fb-f735-55af-b0ef-ee3a05f9b8eb |  | note | - - - - - - - - -
label | 33fc1c4a-a1a8-5363-802d-a7b77f885b6e |  | note | Inspection / Test Method: Verify
label | 31027459-df21-56e0-8b5e-99c2b19aefa3 |  | note | - - - - - - - - -
label | 623e766f-79ad-52d9-a92e-0cc564330699 |  | note | Record of Conformity: ITP signed
label | 00f2dbdb-06f7-5cc4-88d4-d2bfcd08858a |  | note | - - - - - - - - -
label | 9105de8e-2b71-54a8-b149-6d7378380f19 |  | note | IP
label | 252a61c2-a6ef-5652-9f67-cb9c1fc9c6d9 |  | note | - - - - - - - - -
text | 8c15556e-f8ce-59d9-8768-bdc8afcd0fa1 |  | textbox | Responsibility: Site Engineer/ Site Supervisor
checkpoint-status |  |  | checkpoint | 5.8 Compaction
label | d9697fc7-7fba-5fae-a378-a8ed71f7e00f |  | note | Frequency: Each concrete pour
label | 030b7628-e430-5560-ad2e-8247021f917d |  | note | - - - - - - - - -
label | 09b3a4e5-bcd1-523d-97db-e707eac3be39 |  | note | Acceptance Criteria: Vibration shall be applied to the full depth of each layer and extended into the top 100 mm of the underlying layer. Vibration shall continue at each point until air bubbles cease to emerge from the concrete, then withdrawn slowly. Concrete shall not be vibrated to the point where segregation of the ingredients occurs.
label | 157dbf88-80f1-5618-a7f6-fe298dc2e628 |  | note | - - - - - - - - -
label | e83029be-ed1f-598c-8d02-8778d0f2c915 |  | note | Reference Documents: Cl 610.18 (d)(i)
label | 7da3f974-0d2d-50b2-aa7f-88c26f438f91 |  | note | - - - - - - - - -
label | c8bce364-a346-5f7b-b202-db186486fd7c |  | note | Inspection / Test Method: Verify
label | b489e632-dcf3-5dab-913a-ba4c595a8fd0 |  | note | - - - - - - - - -
label | 3c0bf596-b68e-57aa-b9db-60b612f57fbc |  | note | Record of Conformity: ITP signed
label | dcf75f1a-0381-51d5-b61c-c54d90b010d1 |  | note | - - - - - - - - -
label | c687b235-7cba-53a2-8723-9c1800ed507b |  | note | IP
label | 52f95276-2676-5a8c-aeca-03f37d6730c2 |  | note | - - - - - - - - -
text | f06ca4d1-864e-5224-8c6f-557fce841873 |  | textbox | Responsibility: Site Engineer/ Site Supervisor
checkpoint-status |  |  | checkpoint | 5.9 Construction Joints
label | a79e1472-1c9a-5938-8ae4-402d290e5664 |  | note | Frequency: Each pour involving construction joint
label | 809a2675-f211-534b-9270-3cf91cb0b3bd |  | note | - - - - - - - - -
label | fce8acad-9484-5256-978e-67bd67f29c93 |  | note | Acceptance Criteria: The location and details of construction joints shall be as shown on the drawings. The placing of concrete shall proceed continuously from joint to joint. Any point at which the placing of concrete has stopped and the concrete has taken its initial set shall be treated as a construction joint. Before placing new concrete against concrete which has set, the forms shall be re tightened.
label | 0ea14356-0a57-5581-b4a8-44842d8f4541 |  | note | - - - - - - - - -
label | bfde2f98-4de3-5b3d-a83b-a88163823fcf |  | note | Reference Documents: Cl 610.20
label | 63c207a0-4998-5de6-9798-338619088839 |  | note | - - - - - - - - -
label | 5e644f60-92f2-54e4-87f1-aa5db7b74969 |  | note | Inspection / Test Method: Verify
label | 1fded164-7afc-5b6c-897d-d074d7928825 |  | note | - - - - - - - - -
label | f3420e92-629b-56d6-9b33-815c789160f0 |  | note | Record of Conformity: ITP signed
label | 3159a8a8-0dd2-5e15-89d2-e99aeb951cca |  | note | - - - - - - - - -
label | 93c9da00-f168-5940-8322-ca0b7a2b66b3 |  | note | IP
label | aefe2be3-4192-5085-b45c-1e62d21a5558 |  | note | - - - - - - - - -
text | 429defd6-c3f0-5585-b20e-e5aab788eb59 |  | textbox | Responsibility: Site Engineer/ Site Supervisor
checkpoint-group |  |  | section | 6 - Post-pour Details and Inspection
checkpoint-status |  |  | checkpoint | 6.1 Formwork removal
label | 7007dcfd-f729-533c-a9ba-cb3d8561b8a0 |  | note | Frequency: Each concrete pour
label | 6c821d3e-861a-5189-b8d7-7f01f7e37000 |  | note | - - - - - - - - -
label | 6e2746d7-e06c-5bdf-9a06-4adeca3c6b34 |  | note | Acceptance Criteria: Formwork not removed/disturbed for the duration of the minimum removal time specified in the Table 610.251. Walls <2m = 2 Days Side of slabs and piles = 1 Day
label | 4f819a1e-1c95-556a-96a3-d76465037eeb |  | note | - - - - - - - - -
label | f73a8eb3-51a1-5b6a-8897-faadb9b1ac65 |  | note | Reference Documents: 610.25 Table 610.251 CL 001F
label | 4f651e55-028b-5139-a345-48a3b7aacb83 |  | note | - - - - - - - - -
label | 9dceffa0-3c38-5607-bc8b-61df3b6abaca |  | note | Inspection / Test Method: Verify
label | 0705b109-70d1-5261-bac7-5621f599102a |  | note | - - - - - - - - -
label | 67ccdb57-4ed3-502b-9342-352f356642f0 |  | note | Record of Conformity: ITP signed
label | b8aba89f-14a2-5641-9806-e5e12d28b20f |  | note | - - - - - - - - -
label | fc1aa67a-3558-5528-b88a-08cbcfe0a773 |  | note | IP
label | 04ef504b-664e-5179-a482-0bd2ee58b8ae |  | note | - - - - - - - - -
text | 5dfebd3b-772f-5cfd-8654-9b9e33a5101e |  | textbox | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 6.2 Post-pour Checklist
label | 3e98bf4c-a1ec-59d0-9d64-b9144fe97651 |  | note | Frequency: Each concrete pour
label | 12c351d3-2091-5294-9461-f6c0fb3d022c |  | note | - - - - - - - - -
label | 1ff1690d-4d75-5249-94c1-4fe885091ed0 |  | note | Acceptance Criteria: CL 001F – Post-pour Checklist completed and signed.
label | a08f86b9-95db-5cb0-a398-e93ddbd862c6 |  | note | - - - - - - - - -
label | 9eac6e64-245c-543a-bedc-f3a2c69eb834 |  | note | Reference Documents: CL 001F
label | f9d1e7b8-1faa-5bad-806d-f50637804b5e |  | note | - - - - - - - - -
label | 5c5bb561-c520-559c-b11d-25124818c648 |  | note | Inspection / Test Method: Verify
label | ca2b1a57-a514-5508-89d0-8f0e75d310f3 |  | note | - - - - - - - - -
label | 8fe06190-538d-5c7e-8366-bf32787df10a |  | note | Record of Conformity: CL 004F
label | 7935c12c-946a-57c8-8877-b82b2f28e967 |  | note | - - - - - - - - -
label | 875d3b26-3539-556c-842a-07115ec6b6c3 |  | note | HP*
label | 8f5af7ae-cc69-5ca5-91d2-eb3e3786b082 |  | note | - - - - - - - - -
text | 3d068369-a92c-583f-818a-5f7c55cf1788 |  | textbox | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
label | e3d095d5-c315-582a-8e85-f90beb2cf941 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 056b37dc-3fbc-5396-a9f3-5f39b339750d |  | textbox | Print Name:
text | 087bc97c-e809-52ea-afdc-ac969edeb93e |  | textbox | Position:
date | 9b409934-5daf-5b59-b265-51db28aad275 |  | date | Date:
date | cc6e42eb-c499-57c7-a439-673aadbe35cc |  | date | Work Completed On
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification.
select | 77c9912d-ae8d-5cf4-a117-dbcbf4b08c22 |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | 28946c8c-b329-5c82-aa23-f0ab6fb99f86 |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | e0284b07-a805-54ed-9792-fef6fd5510d3 |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | 99c85f56-59b2-5457-b667-73fbd0a249d7 |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | c11660c8-15f2-5582-a82e-80cb7ebe50e9 |  | textbox | Other:
select | ebb303b8-6c6f-5063-8d42-c55f8716ba60 |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | 18852dae-4972-577d-84a0-05c47d9f6f6d |  | date | Lot Closed On
text | 3d7b1369-def8-571e-8d89-cd1d4b83a27b |  | textbox | comments
checklist-flat |  |  | checklist | ITP-001-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0001 - Clearing & Grubbing | ca1dc026-f34c-4536-b6d3-7bba87ca97dc
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | 59718c11-00c6-5626-928f-340371cdd1f6 |  | date | Lot Created On
date | 3cb0ceda-d001-59b6-8e28-9659f9072ad9 |  | date | Lot Opened On
date | 6fcc25a6-d419-588e-813d-73a401881155 |  | date | Work Commenced On
select | 53f4bb91-3f5f-5cba-9f1b-ba46735bff2b |  | dropdown | Lot Type | CIL-Civil Lot, DRL- Drainage Lot, EAL- Earthworks Lot, ELL- Electrical Lot, UTL- Utility Lot, STL- Structural Lot
text | 2d3a33af-c0cd-5f18-bfde-a1406a0df405 |  | textbox | From and To Chainage
select | c2ca6056-2c54-532f-b8ca-4d7ff7010821 |  | dropdown | Construction Element | EART - Earthwork
select | 696785e0-1126-5e97-9db1-d3579373eb84 |  | dropdown | Activity | CLGR - Clearing and Grubbing
select | 98cc1584-6271-5dd3-80f2-b5146a0c5c55 |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | 1c4b5cd5-c59e-5630-84b9-9f880e6f88ed |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | 8b125ab0-a43d-5858-927b-e7dd0441785b |  | textbox | Engineer Responsible | OPEN FIELD
text | 38d3feec-c97b-5185-946f-4d1b505ca31b |  | textbox | comments | OPEN FIELD
checkpoint-status |  |  | checkpoint | 1.1 Induction
label | c4f11de1-919e-5738-b7fb-4e069e1ba368 |  | note | FREQUENCY: Prior to Commencing Work
label | 989d9817-4ff9-5791-b10f-2a862f4d2c44 |  | note | - - - - - - - - -
label | 061f7494-bb92-5976-b354-f01fe478bcc8 |  | note | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the CRG site
label | 1800820d-f9bd-5805-9aee-589f9ec614e8 |  | note | - - - - - - - - -
label | c4d0fe11-f5d0-5361-a306-03ca9e265802 |  | note | REFERENCE DOCUMENTS: PMP, Inductions Register
label | f2e2104f-bf86-5ada-86a8-62f7c4d52ba4 |  | note | - - - - - - - - -
label | bf8fcd7e-0a8b-5d3f-9b7e-756c314006ca |  | note | INSPECTION/TEST METHOD: Document review
label | 32e4a27f-7d80-55ef-88a4-ceb0cbec71d0 |  | note | - - - - - - - - -
label | c890c341-db19-565a-aac7-5f5b967251bb |  | note | RECORD OF CONFORMITY: Site induction signed
label | c360107d-1a4a-521c-8e5f-54056a7fbd66 |  | note | - - - - - - - - -
label | 12570bba-1865-5002-b36c-e6b3c4fb90ff |  | note | AP
label | 47b1f726-f242-5c9d-b2d7-9e2039495680 |  | note | - - - - - - - - -
label | e79daeae-313c-544b-a5df-b4d7adad0c66 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | 1f6dd113-58a4-52e6-927b-461c283e069a |  | note | - - - - - - - - -
date | 90e7438f-5835-5aba-abd7-b8259691a644 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Safety measures are in place, SWMS undertaken
label | 47df3d5b-98fd-5e9a-bf26-08531d7cf43b |  | note | FREQUENCY: Prior to Commencing Work
label | 685caeac-f3dc-5bcd-acdb-4dd7fc616c1e |  | note | - - - - - - - - -
label | 1a8d7886-d830-56b0-ade8-4c232faa5a23 |  | note | ACCEPTANCE CRITERIA: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
label | 087397d0-7176-535a-be3c-81cd88867fce |  | note | - - - - - - - - -
label | 5dddf8f5-4215-59cf-a67c-da20fa8b6fd5 |  | note | REFERENCE DOCUMENTS: Health and Safety Coordination Plan
label | 81302791-f2a8-53ba-8fe3-5dc081fc6409 |  | note | - - - - - - - - -
label | ba942d99-8f86-5149-ad49-cf494e618bce |  | note | INSPECTION/TEST METHOD: Document Review
label | 61a6bb37-b542-5c4b-b8d8-36022d502898 |  | note | - - - - - - - - -
label | fb210188-ce6d-50dc-88f3-a91d22abd646 |  | note | RECORD OF CONFORMITY: SWMS(s) signed
label | 2343c97b-e517-5536-9d38-f6dae99cdbe1 |  | note | - - - - - - - - -
label | 5652b807-de81-5ee0-9d02-e4b3381c3ecd |  | note | HP
label | b5b87b88-4290-521c-b848-75ec07a122a0 |  | note | - - - - - - - - -
label | 33f72896-8ed1-582e-bcab-b1cd088e6f51 |  | note | RESPONSIBILITY: Site Engineer, Site Foreman & Superintendent
label | 63007c6f-6c9b-54ef-8e75-84a609505f43 |  | note | - - - - - - - - -
date | d6146ef8-8ab9-5bec-adb3-c5dc7cba7489 |  | date | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 1.3 Check that current revision drawings are being used
label | 37e470fe-d009-5111-9a0b-648f54756fa3 |  | note | FREQUENCY: Prior to Commencing Work
label | 5513b31f-6561-5645-8895-67d0b341b6c3 |  | note | - - - - - - - - -
label | 2b23fad8-dc35-53dd-b89c-fa96634dc0ac |  | note | ACCEPTANCE CRITERIA: refer to latest drawings and latest available revision used
label | 2bfb413c-14c1-5491-82ee-768288f3a913 |  | note | - - - - - - - - -
label | f93a756b-3708-5bc5-bbb2-6f69a506f375 |  | note | REFERENCE DOCUMENTS: IFC Project Drawings/ Drawing Register
label | e785fa76-69ff-50bb-982e-053a599efdaf |  | note | - - - - - - - - -
label | c187c187-cb7b-5259-90c3-8233fe436adc |  | note | INSPECTION/TEST METHOD: Document review
label | 721ce7bc-365e-5efe-b6c2-1b76669e6628 |  | note | - - - - - - - - -
label | 82e1927b-2b8f-5e25-b810-e97c469bdd40 |  | note | RECORD OF CONFORMITY: Latest revision drawings
label | 05ddbc4c-5a81-59bd-8617-ea16c9e3eee1 |  | note | - - - - - - - - -
label | 1f2c3898-05f1-5f01-a9f2-c0f650515c06 |  | note | AP
label | b92d8e93-41dc-54c4-a112-7c635c3e2bbd |  | note | - - - - - - - - -
label | abd7f221-dc24-5815-acb2-94d830ff54c7 |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | 2d20c03e-cec9-5901-bf6f-356a0cddc3c7 |  | note | - - - - - - - - -
date | 00e7297f-3a9b-506f-b8f6-34f5816442ed |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
label | 18cf5d74-567d-5492-b751-871f18d48047 |  | note | FREQUENCY: Prior to Commencing Work
label | 78e06ef4-1909-5916-916c-af6134132896 |  | note | - - - - - - - - -
label | b1f7bfee-71cd-52d3-9b02-6a5e2b1f5708 |  | note | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | f8d5a5f3-2beb-5a7a-a720-61e42f186239 |  | note | - - - - - - - - -
label | 826a33ca-ff17-566a-a5f6-e3f3e4bff93e |  | note | REFERENCE DOCUMENTS: EMP, induction register Project Spec. Cl.1200.03
label | b514523e-4fb1-5c8a-ba8f-e82603eceac8 |  | note | - - - - - - - - -
label | 09c689de-a22b-5f96-871a-588d5c735552 |  | note | INSPECTION/TEST METHOD: Document review & Site inspection
label | 9a5ea761-5f76-514b-89b2-a0cc79cf14e6 |  | note | - - - - - - - - -
label | 26716aa4-0851-5d76-90d4-f11c50eae7a3 |  | note | RECORD OF CONFORMITY: Site induction signed This ITP signed
label | 270b9aec-5c75-5a84-b162-6bc3f7d0d9b3 |  | note | - - - - - - - - -
label | a38b4977-9b9a-50d4-b962-60ddd06dc154 |  | note | IP
label | a6a69ee7-5913-5341-9891-95f540123ae2 |  | note | - - - - - - - - -
label | 10061cd0-dbba-587a-bba3-9102b092a864 |  | note | RESPONSIBILITY: Site Engineer
label | 4f1277ba-402b-535d-82cb-a60d59f0901a |  | note | - - - - - - - - -
date | e5278eb5-7b55-5b9f-9adf-8a6950ac1689 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 Excavation Permit issued
label | f7d7d07b-f9c5-5899-97d6-967c15cd3051 |  | note | FREQUENCY: Prior to Commencing Work
label | 09eb9ad8-ff7b-5eeb-b83f-d16895aa2eb6 |  | note | - - - - - - - - -
label | 752078b5-ed78-5dc7-8d32-d4e4d36b5cb0 |  | note | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | bc62f9df-a5b7-5e55-b0b6-d07b3d554513 |  | note | - - - - - - - - -
label | 05fe117f-4851-5c65-92e6-e0cba36b3559 |  | note | REFERENCE DOCUMENTS: Excavation Permit
label | 9c345cd7-1a95-5a3d-91b2-2bd25b9c32f0 |  | note | - - - - - - - - -
label | a094d286-cfc5-5e6f-804e-95615a980f8d |  | note | INSPECTION/TEST METHOD: Document review & Site inspection
label | 84775944-5117-5552-8480-28112c2d7508 |  | note | - - - - - - - - -
label | 4a4a8a5f-a3d2-51cf-9171-ff956500b4fc |  | note | RECORD OF CONFORMITY: Excavation Permit #
label | 5d4ed0b0-aacc-5eb4-bab6-0a64ea60f6c3 |  | note | - - - - - - - - -
label | a0c4d8e7-65fe-5879-b470-43dc503856a3 |  | note | HP*
label | dae1258e-4094-56f5-80a2-b937d78055f3 |  | note | - - - - - - - - -
label | 5b092f42-9b06-5c89-b235-98f0602a62a5 |  | note | RESPONSIBILITY: Site Engineer
label | 2656c47a-5e80-5dc8-9a7c-6237fbe4a117 |  | note | - - - - - - - - -
date | 7883f666-6c4a-5262-8b63-76d1a4be44d2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.6 Traffic Management (When required)
label | b6d74629-784e-5e95-a1ea-68b079e61b80 |  | note | FREQUENCY: Prior to Commencing Work
label | 6b5ce27e-449d-59c3-89f8-d2df76dd9040 |  | note | - - - - - - - - -
label | ff49fe57-1bc5-5cc8-a877-54cff0a9f44e |  | note | ACCEPTANCE CRITERIA: Approved TMP and MOA
label | a87507da-f0b8-5326-ae3c-e15222cb28bd |  | note | - - - - - - - - -
label | 6a32c59d-3ff4-53c8-9744-35e9f9499442 |  | note | REFERENCE DOCUMENTS: TMP
label | e59afad9-a6f6-5c92-ba51-eb1877e588ed |  | note | - - - - - - - - -
label | 4f465fd1-d16f-506a-a0b2-b1611f5f91f9 |  | note | INSPECTION/TEST METHOD: Document review & Site inspection
label | 2686112d-1e53-526a-ba4b-82fefd1072cb |  | note | - - - - - - - - -
label | b5c50cb8-d2d8-5163-892b-2828aab37dcb |  | note | RECORD OF CONFORMITY: Approved TMP & MOA
label | 2876205b-3b57-52be-ad21-fa77a5b755bd |  | note | - - - - - - - - -
label | 924835f6-3272-50cd-ba48-4f65c939eea1 |  | note | AP
label | 3cbfdf08-2865-5522-9ea9-4c19d012ab26 |  | note | - - - - - - - - -
label | 5d71ba2f-2a42-5d18-908d-44382428c7f4 |  | note | RESPONSIBILITY: Site Engineer
label | 54e42a1a-ea64-57f6-856b-54f319165e95 |  | note | - - - - - - - - -
date | 3c6b3ec8-f2b3-5063-ab34-7c15b37ab196 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.7 Vegetation Removal Permit (if required)
label | 1372731c-169d-5055-b816-0ff1686eb591 |  | note | FREQUENCY: Prior to Commencing
label | ecc1df76-3aad-5a1d-a4dc-65a68e655ba0 |  | note | - - - - - - - - -
label | eb27eefa-1d9f-547b-b672-cb7e9b839efd |  | note | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat, FH shall: (a) arrange an on-site inspection with the Superintendent relevant authorities to confirm and clearly identify and mark trees, vegetation or habitat to be removed, consistent with the Design Documents and any relevant permits. (b) fence and sign all sites nominated as No-Go Zones.
label | fec6596c-6bd2-5f53-a26a-201dd5cf3921 |  | note | - - - - - - - - -
label | 11b066a7-a7ac-5093-ae41-851fa38a1eb8 |  | note | REFERENCE DOCUMENTS: Project Specs. Cl.1200.15
label | 873db04e-1ea5-5681-af80-4610b82bdbf1 |  | note | - - - - - - - - -
label | 783df4a5-b3ba-5bb0-8af8-90b7a9bad6c4 |  | note | INSPECTION/TEST METHOD: Document Review
label | 7b23e025-3a75-5fec-a25c-8148a16e9441 |  | note | - - - - - - - - -
label | a5747482-704e-5ce5-a185-71f144213ce8 |  | note | RECORD OF CONFORMITY: Approved Veg Removal permit received.
label | 4052daa1-f465-55e9-903e-7c35376a671b |  | note | - - - - - - - - -
label | f34f2277-9ad1-56d3-8529-e26b7023762b |  | note | HP
label | 8489f418-8606-5f15-9f89-28b784fb7ef9 |  | note | - - - - - - - - -
label | 2beff777-b4d5-5875-b922-921204d750b6 |  | note | RESPONSIBILITY: Site Engineer & Superintendent
label | 2970bd85-5d99-5b18-8aa2-820b9977cc3a |  | note | - - - - - - - - -
date | dd3fcc3e-1874-58b1-9846-af5f51b652ab |  | date | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 1.8 Extent of Clearing and Grubbing
label | 7b8bff1d-690d-5e9d-a289-08c414da1476 |  | note | FREQUENCY: Prior to Commencing Work
label | a1a2c34f-87e6-5552-8d10-fb8b6d4da9de |  | note | - - - - - - - - -
label | d8afd6c5-ccb6-530c-af46-4ee5b891f8b4 |  | note | ACCEPTANCE CRITERIA: Extent of Clearing and Grubbing shall be reviewed jointly by Superintendent and FH representative prior commencement of the Works
label | 883d394f-eda1-5c47-93ad-ae4ef93c2e97 |  | note | - - - - - - - - -
label | 1dd65c93-24c2-5e7b-ba53-0ff88be02975 |  | note | REFERENCE DOCUMENTS: Project Spec. Cl.3020.07(a)(ii)
label | 59f1477b-9b46-531f-9876-6ca16575aa41 |  | note | - - - - - - - - -
label | 70653a42-eefe-5a2b-8356-fb77212c79fa |  | note | INSPECTION/TEST METHOD: Site Inspection
label | d06a847a-e39e-5eba-ae57-cc8b8b25794f |  | note | - - - - - - - - -
label | 1824ad63-c8d6-526a-a91e-d115c6168fd5 |  | note | RECORD OF CONFORMITY: Extent of Clearing and Grubbing reviewed by Superintendent
label | 22e412fb-1fe5-50be-937e-6e86a626ff8c |  | note | - - - - - - - - -
label | 9a007bda-d1b2-5f0d-8fd5-aad386637a5c |  | note | HP*
label | ce20a235-f25b-586f-aea3-e6777167edbc |  | note | - - - - - - - - -
label | b06a3bdd-ee35-51ce-9bfc-2c80af93ad3d |  | note | RESPONSIBILITY: Site Engineer
label | 0d7fe5bf-1645-55ef-aaff-fd1eb9b8d90c |  | note | - - - - - - - - -
date | b85a6ba6-9d3f-5a93-ab2a-6a48f2408b76 |  | date | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 2.1 Identification of Cultural Heritage sites and areas of Cultural Significance
label | b7316e43-e415-530f-9c31-9f73ff528d51 |  | note | FREQUENCY: Prior to Excavation
label | 4ca83726-11bc-5839-977a-c373d777e5ca |  | note | - - - - - - - - -
label | 1b918ad0-0d0f-5062-b429-d80a5e0ab730 |  | note | ACCEPTANCE CRITERIA: Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing. Immediately notify the Superintendent if any Cultural Heritage is discovered or identified during construction and work to be suspended. Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage.
label | 3a30983d-f4d8-5a38-8630-bf2e78324eac |  | note | - - - - - - - - -
label | e8b7c9e3-dedf-5e44-9ca5-96ecb3ca5eea |  | note | REFERENCE DOCUMENTS: Relevant EMP Project Spec. Cl.1200.17 VicRoads Spec. Cl.201.10
label | 886d5357-3153-5e80-8041-1e50397b6bd8 |  | note | - - - - - - - - -
label | c96e6f0b-20da-51c7-949c-e02ee6ea5eba |  | note | INSPECTION/TEST METHOD: Document review & Site inspection
label | 1913d147-dc3c-5fe2-be33-f0e80894804e |  | note | - - - - - - - - -
label | 3302f5f5-5dae-582a-b3cf-9cb48f9fb138 |  | note | RECORD OF CONFORMITY: Cultural Heritage approval (when required) Signed ITP
label | 806015ca-587c-569e-92ef-e50d04ec70d5 |  | note | - - - - - - - - -
label | 836ccce4-9658-506d-90ce-7d278c29a3ff |  | note | IP
label | 9b40422d-256a-5009-ab35-0574ecb08081 |  | note | - - - - - - - - -
label | 4d339ef6-91e1-51e1-83a4-6324e80894fe |  | note | RESPONSIBILITY: Site Engineer
label | bc450f20-e576-5824-a5b7-0d8f21ea2a91 |  | note | - - - - - - - - -
date | 9e23c3e3-c627-5b8c-8bc6-dc0311293a70 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Stockpiling
label | 943cb1b7-eb5f-5968-8a56-4de356908b53 |  | note | FREQUENCY: Prior to Excavation
label | 8480272d-e3b5-5906-bdc3-518781313eac |  | note | - - - - - - - - -
label | 843858e1-3c47-56d3-ad6c-78d9fe60420b |  | note | ACCEPTANCE CRITERIA: Where soil is stockpiled on Site, such stockpiles shall be located, where possible, to provide a clearance of not less than 10 metres from waterways. If this clearance is not possible, additional protection shall be provided. An area for stockpiling of topsoil has been designated and marked according Work Procedure WP-0009
label | 56f653db-2e24-5cd6-b42a-20aa263a17c5 |  | note | - - - - - - - - -
label | 5a023889-0b7a-584a-ba41-4843f1a607eb |  | note | REFERENCE DOCUMENTS: Project Spec. Cl.1200.09 (b)(i)(4)
label | 4fd431c5-910d-5a3a-abae-5fdd23cdd00a |  | note | - - - - - - - - -
label | 5e9490d9-9cdd-50a6-ac8c-736cf1c0c363 |  | note | INSPECTION/TEST METHOD: Document review & Site inspection
label | e0b5aa05-a4fa-51c8-bc64-79591408b82c |  | note | - - - - - - - - -
label | caae3ba3-f798-5c9c-ad68-81b037ab8ef7 |  | note | RECORD OF CONFORMITY: Signed ITP
label | ae67607b-7822-50cc-a7d5-b3aba034dfd8 |  | note | - - - - - - - - -
label | b7f016a7-475c-5877-aad1-b470a3c30fe9 |  | note | IP
label | 5550a08b-e2a5-5014-b0ed-f3504fbda60e |  | note | - - - - - - - - -
label | 8b4db1d9-bb76-5b73-89ba-399849d55bb3 |  | note | RESPONSIBILITY: Site Engineer
label | 9d5ac07c-9024-549e-9378-fe83d2bd3bca |  | note | - - - - - - - - -
date | 5d87a512-b0fa-5b1b-9700-99ef7e3e4d11 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Stripping of topsoil
label | ebb0bbfb-a83c-5a29-8a0d-a0e53c7f1af7 |  | note | FREQUENCY: Prior and after commencement of any ground disturbing activities
label | 81fb18a0-89ae-5d1b-b91a-484eed9d577a |  | note | - - - - - - - - -
label | 8820c0a2-8350-5150-878f-c97c36d3574d |  | note | ACCEPTANCE CRITERIA: Topsoil shall be stripped for the full width of the formation. Declared noxious weeds, pests and pathogens shall be treated and monitored before stripping of topsoil, and after spreading, to prevent and/or minimise the spread of weeds and other pathogens throughout the site. Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re spread as soon as practicable.
label | 22c3a156-385f-55b8-b2b3-1f2cd948ff0f |  | note | - - - - - - - - -
label | 20b6f318-f750-5760-972c-3cd486d72be7 |  | note | REFERENCE DOCUMENTS: Relevant EMP Project Spec. Cl.1200.16 VicRoads Spec. Cl.204.05
label | f2c64cd0-477d-5199-a94e-5e2945959ed1 |  | note | - - - - - - - - -
label | 516d9dd8-d683-5d65-b73d-9414a0aa8e3b |  | note | INSPECTION/TEST METHOD: Site Inspection
label | 00b47367-5d9c-57f1-83f9-adf5880a7d15 |  | note | - - - - - - - - -
label | b7fd8d14-ac8d-588a-9e7c-3fe337986b0f |  | note | RECORD OF CONFORMITY: Signed ITP
label | edf8350d-964c-51a9-862e-d5a684f36ab4 |  | note | - - - - - - - - -
label | cbb3a0f0-f8fc-52b3-8c06-74dee4c92232 |  | note | IP
label | 36749fd2-9f24-5790-9aed-66f0011a0e90 |  | note | - - - - - - - - -
label | 7212fa20-eb70-57ee-908e-7ad3d8987b5f |  | note | RESPONSIBILITY: Site Engineer
label | bb744305-c06d-5eb8-a206-8b5c92aaa76c |  | note | - - - - - - - - -
date | 59d889f0-8970-5cbc-a424-7c92d3bf0d49 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Removal of abandoned services
label | ce3ae9eb-acc3-5885-ba62-fe58bbad778f |  | note | FREQUENCY: Prior to commencing this work
label | e4b0d4d5-af36-5678-a888-d29425f5d158 |  | note | - - - - - - - - -
label | 30207abe-9bd6-5d45-8e66-76a726a58c90 |  | note | ACCEPTANCE CRITERIA: Removal and disposal of abandoned services and obsolete underground drainage lines which interfere with the execution of works has been done. Verify service is not likely to contain a hazardous material (sewage, asbestos pipe) Decommissioned services to be disposed of in a suitable manner. Decommissioned pits have been broken back to 0.3 metres below subgrade level.
label | a6e32f48-10ab-5152-97e6-9ed2d80e3757 |  | note | - - - - - - - - -
label | 017009ad-e2bc-521f-b9f7-eaa1047a2df2 |  | note | REFERENCE DOCUMENTS: Project Spec. Cl.3020.07(a)(i) VicRoads Spec. Cl.201.05 Excavation Permit # IFC Drawings
label | 3f6dc261-592d-519a-8c04-e8d81889ca7c |  | note | - - - - - - - - -
label | 16078674-6c51-5d3e-bd8e-a4330b253026 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | 16170594-d091-5376-aab8-6c77016a17c7 |  | note | - - - - - - - - -
label | 40e0927d-e3bc-54f5-8e32-8e30aab3d5cd |  | note | RECORD OF CONFORMITY: Signed ITP
label | fbc37c5a-7b41-5ba7-834f-31df9ed1d3e2 |  | note | - - - - - - - - -
label | 3811d690-6319-5e49-82da-e37e78953e83 |  | note | HP*
label | ed25b0d4-e133-5853-be63-991e274b158f |  | note | - - - - - - - - -
label | e38da777-5652-5678-ab6b-951da417335c |  | note | RESPONSIBILITY: Site Engineer
label | d382151b-4bac-50cd-b356-42764954dd95 |  | note | - - - - - - - - -
date | a8f08116-3a85-5845-9e5d-b61f505a9bf0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Clearing of Trees and Vegetation
label | c95587a4-b326-5867-b6e5-24083370216a |  | note | FREQUENCY: During clearing works
label | 7dd369c2-dca0-5fe4-b448-f7602a6918bf |  | note | - - - - - - - - -
label | 3329a53d-2bb6-5d27-bdcf-9bf7ac90cb8f |  | note | ACCEPTANCE CRITERIA: Clearing work shall not be undertake outside of the specified limits of work. Tree branches extending over the carriageway shall be trimmed to provide a clearance of at least 6 m above the carriageway surface.
label | 8ca7c65a-f225-5787-9ea3-7cbbe7a1a114 |  | note | Where whole branches are to be removed, the three cut method shall be used.
label | 0bc3edaf-ada1-582e-be8e-f3f4faf98a18 |  | note | - - - - - - - - -
label | deeea810-2d78-5e01-af2b-33c67aa3ee48 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.201.04
label | 2978e412-784c-5812-8327-3204fb70e267 |  | note | - - - - - - - - -
label | 469adcb1-65da-5afe-bf6d-a9f2be6e0c9e |  | note | INSPECTION/TEST METHOD: Site Inspection
label | 69feb279-d6ef-5ce5-86d5-5ce78eb8cf37 |  | note | - - - - - - - - -
label | 809baaf1-fe20-596d-a67b-49d46af3acd1 |  | note | RECORD OF CONFORMITY: Signed ITP
label | fcb8623e-1ecc-59fa-aa35-7fd8e07af77e |  | note | - - - - - - - - -
label | 809a917e-d69c-5525-9b94-517c3efec1ab |  | note | HP*
label | 5fd3e582-3440-56c2-849a-7af2323512cb |  | note | - - - - - - - - -
label | 9d7206e7-87ad-5c4c-b7ed-5e3af089d8f5 |  | note | RESPONSIBILITY: Site Engineer
label | 67a2d126-720a-53a9-9886-23c3cfb83efe |  | note | - - - - - - - - -
date | 51830072-baa1-5d44-88a3-ede8d54d40cc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 Clearing Process
label | 3bed75e7-72fc-5c7e-9892-6104b9f8ef84 |  | note | FREQUENCY: During clearing works
label | baeed6c5-9e06-5324-acef-0660e99b0190 |  | note | - - - - - - - - -
label | a3df9aef-3f53-50b0-a090-ea34cb3e6c81 |  | note | ACCEPTANCE CRITERIA: Tree Clearing shall be done in a 2 stages:
label | 232d22e2-0fca-508e-b153-eebb46002066 |  | note | 1. only non-habitat trees as identified by the the ecologist are to be removed
label | 323c331d-c352-5038-bf4b-9b1a5b35d3fc |  | note | 2. the removal of habitat trees must occur not less than 24 hours after the removal of non-habitat trees in the area
label | 51bccd5c-0f1d-5b63-a66f-a959a781b4b9 |  | note | - - - - - - - - -
label | cbb45d85-4ebc-58cf-9002-94fc763471c9 |  | note | REFERENCE DOCUMENTS: Project Spec Cl. 1200.15.5.a
label | f6489a21-9797-5914-9fb5-c457c1ca5dce |  | note | - - - - - - - - -
label | 5acb6a64-23a7-5b1d-ab42-ad981b0b3d96 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | 3b1df3ef-8dca-5965-8ecf-54ddef6ad866 |  | note | - - - - - - - - -
label | ed1cdb67-530b-5bb8-8520-15d7201bd6a5 |  | note | RECORD OF CONFORMITY: Signed ITP
label | cd99b396-150b-521c-82ef-ef75d7800857 |  | note | - - - - - - - - -
label | 4d12be88-d991-5b10-b266-58071b1a925b |  | note | HP*
label | c3fdbe49-2217-53e7-9c8a-37ab6de8e428 |  | note | - - - - - - - - -
label | 0a56b407-ca03-5a1b-89e6-97cf9b6b837e |  | note | RESPONSIBILITY: Site Engineer
label | 20484fbe-4392-55ff-8aae-4dd4d7dcde81 |  | note | - - - - - - - - -
date | c6e2f4f3-2fd5-5129-a5c2-e235778fa196 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 Grubbing of vegetation
label | e0d9af69-2cbc-5af8-82d6-ca4c7167f5ba |  | note | FREQUENCY: Prior to commencing excavation
label | baf6a228-1f03-5c9e-9788-a447fd6b24cb |  | note | - - - - - - - - -
label | 166c0d3d-895e-5dce-85bf-689bd394600f |  | note | ACCEPTANCE CRITERIA: In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3 m below the subgrade and batters, whichever is the lesser treatment.
label | 9f613617-f954-523c-a27d-dd098d3556ff |  | note | In areas to be covered by embankments, to a depth of not less than 0.3 m below the stripped surface or not less than 0.6 m below the finished surface of the subgrade, whichever is the lesser treatment. Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material
label | 82b4d7c7-2a65-5313-b7f0-adcebc8be536 |  | note | - - - - - - - - -
label | ccded32a-2df3-5e00-bc62-52860088e4c0 |  | note | REFERENCE DOCUMENTS: Project Spec. Cl.3020.07(a) VicRoads Spec. Cl.201.05
label | adc6bec1-dd77-5ed5-92b6-9cb81ff1b484 |  | note | - - - - - - - - -
label | 7ca51f69-a8a8-54f4-aada-09898deda17c |  | note | INSPECTION/TEST METHOD: Site Inspection
label | 78f3b2fb-ee23-52e8-b4a7-9eb226bdc955 |  | note | - - - - - - - - -
label | 6dbd7725-72fb-58ce-a75a-d677086fe828 |  | note | RECORD OF CONFORMITY: Signed ITP
label | de8d15e2-4ba6-587d-9f9d-fad8b1a90de4 |  | note | - - - - - - - - -
label | 48346c78-ffda-5c81-b25c-cb4f37edf7db |  | note | IP
label | 29418c49-89b3-5e1f-bb2a-8cd15aae731d |  | note | - - - - - - - - -
label | 5b753012-8b3c-59b0-b3a4-b4057c638953 |  | note | RESPONSIBILITY: Site Engineer
label | 47d5a813-fd0b-5338-ab8a-ba0f8354dca8 |  | note | - - - - - - - - -
date | dc896368-51dc-571d-a7ac-85e52b3d3d17 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 Disposal of vegetation
label | c12bd6c6-5b36-5df9-a373-c942601b4364 |  | note | FREQUENCY: At completion of works
label | c822cc3f-2322-5503-adfc-49249ee4abd0 |  | note | - - - - - - - - -
label | ae304dba-704c-5e7e-979b-3280d4fee8d5 |  | note | ACCEPTANCE CRITERIA: Tree trunks and large branches shall be removed from the site. Small tree branches, shrubs and leaves, excluding noxious weeds, shall be disposed of by chipping and mulching to form mulch.
label | bc10d970-710c-5699-8cec-9dcb4e56fee5 |  | note | - - - - - - - - -
label | f06f4e84-d904-5369-85ad-61eb878f812b |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.201.07
label | 6a373dd6-823c-5391-87f1-9b0b47df993c |  | note | - - - - - - - - -
label | 25f0c274-fc5b-5158-9afa-03718d5a91c7 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | c46ee826-28e3-5790-b065-6acf116d434f |  | note | - - - - - - - - -
label | 6eaa9842-8349-5f4e-b40a-239e721b4ae1 |  | note | RECORD OF CONFORMITY: Delivery docket
label | 76e0aa96-7186-58a9-b3fd-2c0f2a58c79f |  | note | - - - - - - - - -
label | b39dc6e4-2b4c-5638-8ebb-f757f80ad4cd |  | note | IP
label | 23457e9f-911d-5547-af81-0b11a48046a9 |  | note | - - - - - - - - -
label | 3dc88ecd-b765-5d79-b47a-e4e8fa197edd |  | note | RESPONSIBILITY: Site Engineer
label | ea860c3b-7f72-5cd7-b66c-5c8923fff701 |  | note | - - - - - - - - -
date | e464903b-0950-5f16-b470-a7d80f9dbe8d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Topsoil Placement
label | 720d905f-8bf1-535f-9d36-d01fb5f523c9 |  | note | FREQUENCY: At completion of works
label | 66e07792-4e31-5b94-9bff-8de25ca22627 |  | note | - - - - - - - - -
label | 162b2b5b-bb53-5add-bf51-af7f2d00c07b |  | note | ACCEPTANCE CRITERIA: All disturbed and/or not paved areas shall be topsoiled according to Section 204 of VicRoads Standard for Roadworks and Bridge works, to the following minimum depths - Batter slopes > 2:1 = 50mm -tree and shrub plantation bed areas= 100mm - Verge, 50mm outer edge / 20mm when within 100mm of the edge of seal or asphalt surface treatment - All other areas - 75mm Topsoil should be levelled and spread, but not compacted, except for verge areas.
label | 6e01c51f-f8ae-5ef3-bd40-c3570342f546 |  | note | - - - - - - - - -
label | 778be8a5-532f-54fb-883d-eb8da2c52dab |  | note | REFERENCE DOCUMENTS: Project Spec. Cl.3020.07(k), VicRoads Specification Cl.204.17
label | cc0271e9-f3e5-529d-856a-27b6c3a37e9e |  | note | - - - - - - - - -
label | 1f5c2247-2112-5dfd-b2d7-89298cfc9f06 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | b9fece64-432b-5de3-a496-6ad1b8d4f765 |  | note | - - - - - - - - -
label | e06f53d6-5767-5dea-afb0-159c6ba2b21b |  | note | RECORD OF CONFORMITY: Signed ITP
label | b5b26862-7082-5c39-b53a-1da2cb17c491 |  | note | - - - - - - - - -
label | 428abe4e-759d-56a9-b49a-8953fe991b88 |  | note | IP
label | 78a50f9e-d5d2-5d30-8a80-27cbdf43173d |  | note | - - - - - - - - -
label | c7963d1a-36c4-52dc-b734-e77c2325516e |  | note | RESPONSIBILITY: Site Engineer
label | 1f60c2f6-7510-59df-abbc-7e0e3a45b5e0 |  | note | - - - - - - - - -
date | 07ee862b-17f5-5aa3-a3f6-7d82fbc8ca40 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 28159cb7-5603-5ecf-a7b0-d2abd7d348a1 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | c616d978-c9a7-5f23-b804-091411a3b0ac |  | textbox | Print Name:
text | 1ac82e1d-5894-537c-a9f7-5933de128122 |  | textbox | Position:
date | b2274fe4-bbc5-5b8e-8156-f20bce166ce4 |  | date | Date:
date | bfc7516d-93cf-5719-b2ef-b8cb2460dbd5 |  | date | Work Completed On
checkpoint-status |  |  | checkpoint | Lot Verification.
select | be1485f5-474e-5390-99de-3252d37aed32 |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | 51b0fb6a-0313-5597-a7d1-1277171fe704 |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | fde20705-a959-5bc4-92c9-ed3856117318 |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | 24f93442-c160-55fe-b68f-e4e593465ac4 |  | dropdown | Lot Plan or “Highlighted” IFC drawings (mud maps) attached to the Lot? | Yes,No,N/A
select | 4bc165fe-b104-53bf-a1fb-f8283c86b69a |  | dropdown | Survey conformance records attached to the Lot? | Yes,No,N/A
select | 28246055-83c0-5ca4-975f-f6d70152a3a0 |  | dropdown | Subcontractor/ Supplier records attached to the Lot? | Yes,No,N/A
select | 236cbfdf-0498-5ce5-a920-86e6ac2bdaeb |  | dropdown | Conforming Test Results attached to the Lot? | Yes,No,N/A
select | 2c8dc7ba-1e2e-5677-af86-97ccd5d0d8d1 |  | dropdown | As built records attached to the Lot? | Yes,No,N/A
select | 484f1afe-3b01-530d-a401-6267a03443a3 |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | 54eac100-5261-5986-bbbb-a5dfc7158a54 |  | textbox | Other:
select | 4035f1e3-4bd2-5630-b861-707d39d9ac24 |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | 217b0bf4-1ab7-51de-9fd1-75d0a7664784 |  | date | Lot Closed On
text | 63878963-1419-5384-a0d1-d8f58f22f1db |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-086-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0086 - WELDING CARBON REINFORCEMENT | d310740b-eb65-4974-8ccd-4ebb0ae11172
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | 7646c54d-8c51-50c0-b8bf-2bdded5306e3 |  | date | Lot Created On
date | 23400d49-72de-5d98-96ac-e0db22cedb22 |  | date | Lot Opened On
date | be319c7c-12e1-59a1-892b-f00fb2c09ad1 |  | date | Work Commenced On
select | ab366031-6ce9-5bbb-bd6e-bdc9c88e954b |  | dropdown | Lot Type | CIL - Civil Lot
text | 7eebfc05-43d3-52d0-aa94-3d569973b53e |  | textbox | From and To Chainage
select | 016ef632-2ad8-53f1-8568-5931217ae119 |  | dropdown | Construction Element | SITE - Site General
select | b9f15b4e-3472-5e20-a54f-6a25e7723394 |  | dropdown | Activity | OTH - Other
select | a7e6526b-5f96-5da1-8e4a-5fad77be39bb |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | 0f220279-249b-54fd-ba25-d65f3d8be17a |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | 28c7f51c-a1f5-5adc-979e-0b8ed8342294 |  | textbox | Engineer Responsible
text | 3a533ae1-fb48-5959-bb58-48cf260db415 |  | textbox | comments
checkpoint-group |  |  | section | 1 - Preliminaries - Permits
checkpoint-status |  |  | checkpoint | 1.1 - Induction
label | 5c6a7777-a85d-56e6-afe5-d22b803c237f |  | note | Frequency: Prior to Commencing
label | ed25a299-d7cc-5ec5-a3f7-feeafce0bf4b |  | note | - - - - - - - - -
label | 0f8ea686-1182-54f0-b73a-a4c69eda7be7 |  | note | Acceptance Criteria: All personnel on site have been inducted to the CRG site
label | de18049b-27cd-5a5e-bf20-3a1fd2c77667 |  | note | - - - - - - - - -
label | 1a24e628-ab1c-5b9f-a568-a6fcfb8ef2df |  | note | Reference Documents: PMP Inductions Register
label | 799cb019-77d8-5a7d-b917-29817b8dba1b |  | note | - - - - - - - - -
label | 34f61721-1ebc-51a7-8221-b65d880dbe82 |  | note | Inspection / Test Method: Document review
label | bac30f01-e851-5986-ad65-fba326499538 |  | note | - - - - - - - - -
label | 087cfa11-4cb1-525e-adc8-d89ccd27eb89 |  | note | Record of conformity: Site induction signed.
label | 8c9f2380-6923-5117-bd89-fb72d49b14cb |  | note | - - - - - - - - -
label | e7616030-52f3-5f28-9254-22d8fdd250b7 |  | note | AP
label | 40e27565-4ab7-5634-9ee3-2176454804ee |  | note | - - - - - - - - -
label | c1fc6fdf-ceb3-5ae3-a688-fa8d49345332 |  | note | Responsibility: Site Engineer / Site Foreman
checkpoint-status |  |  | checkpoint | 1.2 - Check that current revision drawings are being used
label | f4dfafad-fd79-508f-8063-db3b73707dbb |  | note | Frequency: Prior to Commencing
label | b049ebb0-590d-5038-a483-9175557dd032 |  | note | - - - - - - - - -
label | 8ff1fe59-d51a-58b8-89d3-123a5957d768 |  | note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
label | 60d413ce-d5d5-548b-94b5-a631b7b07f19 |  | note | - - - - - - - - -
label | 3f327730-6243-5b99-bef1-7cf404c5d166 |  | note | Reference Documents: Project Drawings / Drawing Register
label | 652e222e-a634-5e29-87c3-db0b5c0c0462 |  | note | - - - - - - - - -
label | 20e86d11-ea5f-59dc-9eef-57725ea83c72 |  | note | Inspection / Test Method: Document review
label | f96c21ff-b312-511d-a07d-baba717a81ae |  | note | - - - - - - - - -
label | 68ccbcbf-f9ad-5947-82e5-dd027618b5e0 |  | note | Record of conformity: Latest Revision Drawings
label | 098439b8-890c-5a78-bf8c-eefa37b79b39 |  | note | - - - - - - - - -
label | 4b30358c-e994-583e-8bdd-d233c2910f1f |  | note | AP
label | 184c3392-2555-5db2-98e1-821dac94c903 |  | note | - - - - - - - - -
label | 7f7b1952-4dbe-5535-9d84-9696bd8f47d0 |  | note | Responsibility: Site Engineer / Site Foreman
checkpoint-status |  |  | checkpoint | 1.3 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken
label | b95cdad2-1281-59b9-a10c-d459bdf7843a |  | note | Frequency: Prior to commencing
label | 51e311c0-c54a-567c-91bc-37a6fe325fdd |  | note | - - - - - - - - -
label | d0b7df0a-9c2f-58da-bb9e-1fdd8da0b914 |  | note | Acceptance Criteria: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
label | e95c92ca-ab54-53ff-8101-3a3cf57cb230 |  | note | - - - - - - - - -
label | 407f27a5-16d1-53ce-95b4-192c9169e214 |  | note | Reference Documents:
label | e2d06647-fae4-5149-b201-0e8c81d755c3 |  | note | Project Specs. Cl.1125.02 Cl.1125.07
label | 2fd15f93-065b-5ecc-b5e1-7e29bb84cd64 |  | note | Health and Safety Co-Ordination Plan
label | 4e24ccff-f8bf-5fc4-a42f-9b6b245ef20a |  | note | - - - - - - - - -
label | 41215b31-a1b7-56d5-b78b-b955d68e5294 |  | note | Inspection / Test Method: Document Review
label | 713120e1-c40c-59c4-8547-c72cdaf12372 |  | note | - - - - - - - - -
label | fc49e317-8e0c-52b5-8443-a8e01bf80ed3 |  | note | Record of conformity: SWMS(s) signed
label | 1a92273d-4fc2-5150-b44c-5950def10ec5 |  | note | - - - - - - - - -
label | 00f741da-d3f0-5d44-8df5-4dbbfcfe58d3 |  | note | HP*
label | 6a11ba5e-ec7e-52eb-9edf-4a709dd5924a |  | note | - - - - - - - - -
label | 88562653-22b9-594d-af7d-7c42b4a936d0 |  | note | Responsibility: Site Engineer
checkpoint-group |  |  | section | 2 - Preliminary Works
checkpoint-status |  |  | checkpoint | 2.1 - Welding Procedure Qualification
label | c5b261b3-196d-53e5-9c59-ff17102b9a95 |  | note | Frequency: Prior to commencing
label | 1ccdc6a4-6ccf-5b32-8a08-ddd20301d265 |  | note | - - - - - - - - -
label | 478b6cee-a159-5981-b127-eea92cf4312c |  | note | Acceptance Criteria:
label | 439eace4-337e-518c-8d74-8da40ab0abb7 |  | note | Welding of splices in steel reinforcement, including to other steelwork and to continuity bar reinforcement, shall not commence until the welding procedure has been qualified and reviewed by the Superintendent.
label | 79c33943-ab9c-5d9d-909e-724053f9918a |  | note | Submit the following documents:
label | 7697cdcf-18b8-56be-9940-c19f00c01836 |  | note | • Qualified welding procedure
label | 3cc7bb6b-4984-5a05-af84-464c428076fe |  | note | • Qualified welders record
label | 9a22f0e1-510e-51e2-b546-919aedf07084 |  | note | • Welding supervisor qualifications
label | bce0ffc8-6eac-5e21-acb2-611a163b7e21 |  | note | • Welding Test Plan
label | 8b7c93e2-ae0f-51d7-bb77-f52dbb296c68 |  | note | • Welding test certificates
label | 6e65bebc-eef4-578a-a06c-a9045e872b1e |  | note | - - - - - - - - -
label | 018ed06f-7ad3-5ec3-8026-1e93950db88e |  | note | Reference Documents: VicRoads CL611.14 AS1554.3 Section 4
label | 9684978c-b74e-5795-ab9b-262814089d21 |  | note | - - - - - - - - -
label | 2d67e604-f476-5904-acdc-2208c4cab6d8 |  | note | Inspection / Test Method: Document Review
label | c5636a77-62d7-5eee-9e9a-e0bd312b9f5e |  | note | - - - - - - - - -
label | 139aafd4-9367-58ad-8cfe-17dd469a6a05 |  | note | Record of conformity: Signed ITP
label | 5f99db47-221b-5534-90b0-756fe29e4996 |  | note | - - - - - - - - -
label | 3b305e34-22b3-5f16-81b6-cab434c89fdf |  | note | HP
label | b012662c-0c4b-5a0f-ba57-19f85f7abb68 |  | note | - - - - - - - - -
label | be6c28ff-7de6-5db1-a2c2-b6a6b957e0ba |  | note | Responsibility: Site Engineer & Superintendent
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Construction Activities
checkpoint-status |  |  | checkpoint | 3.1 - Surface Preparation
label | 1d8e3166-bba9-5263-8bec-dbb6b8adc2fc |  | note | Frequency: Prior to Welding
label | 8a16486b-3c1e-555a-b614-68ce70756782 |  | note | - - - - - - - - -
label | 882f49ff-33a3-54f7-9c52-fb0f5105792e |  | note | Acceptance Criteria: Surfaces to be welded are free of corrosion & paint or any other foreign material that may affect the quality of the weld
label | ed9f49dc-9c67-5a19-8f84-2d564092683e |  | note | - - - - - - - - -
label | 126b39b1-73a9-549c-81bf-c9d0937beb44 |  | note | Reference Documents: AS1554.3 CL5.1
label | 51e69a8b-dd39-541e-ac2f-94db9e030da3 |  | note | - - - - - - - - -
label | f1028ff1-cfc2-5471-9549-59517451f9bd |  | note | Inspection / Test Method: Onsite Inspection
label | 89b75d1f-5b36-5c12-be85-cc0d6b00a81f |  | note | - - - - - - - - -
label | 3cc6f9c2-a067-5b25-bbb3-67b01952b291 |  | note | Record of conformity: Signed ITP
label | 94429516-ff35-56b3-a4be-c2801f8cedb9 |  | note | - - - - - - - - -
label | 8ba1790d-36b2-5a31-8f50-b8801bdee5b8 |  | note | IP
label | 2a9f0332-d203-5d4b-91bf-a7a7c5cec1f4 |  | note | - - - - - - - - -
label | 6c0210e5-2ebb-53e3-bc5a-406e0d82eef6 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3.2 - Assembly
label | de31d9b4-e2b4-5f56-b63f-eb1fcb01c588 |  | note | Frequency: Ongoing
label | f7053806-9a1a-50b1-8ca9-987217648dba |  | note | - - - - - - - - -
label | 59504494-c329-5a6a-a325-65dc1c328846 |  | note | Acceptance Criteria:
label | 58f83325-11b0-5863-91eb-020f884cc1fb |  | note | Where reinforcing steel is to be assembled prior to welding, it shall
label | 2d0f6ac0-5a11-5c86-94cb-5226c29ffff8 |  | note | a) Bars are to be in the correct location
label | 4791e4e7-e44f-5530-9b44-a45d5a8968ff |  | note | b) Before welding a butt splice, bars shall be not out of alignment by more than 0.1 times the diameter up to a max misalignment of 3mm
label | bd004619-71a1-51d5-9645-ce82da24135f |  | note | c) Parts to be spliced shall be into as close a contact as practical but not more than 0.25 times the diameter of the smaller bar but not more than 3mm
label | e80f8972-0c12-5493-b15f-dd4ea95a60e3 |  | note | d) Tack weld, shall be subject to the same initial treatment (preheating). Tack weld that will be consumed in the final weld shall be cleaned. Defective tac weld shall be removed before final weld
label | e0fcbbb1-e82c-513c-863d-317f6614efff |  | note | - - - - - - - - -
label | 798c2792-7388-5c4b-a4ef-a1d26fa09d4a |  | note | Reference Documents: AS1554.3 CL5.2
label | 266c14e7-62ae-56b1-9f7f-6950c8a6e188 |  | note | - - - - - - - - -
label | 4c462f2e-36f4-5f2a-b894-c1ef592363e7 |  | note | Inspection / Test Method: Onsite Inspection
label | d2d27a32-71a2-5874-8a62-8c4f1ce04820 |  | note | - - - - - - - - -
label | c9082733-7631-5bdf-bae9-96bc0e3978c3 |  | note | Record of conformity: Signed ITP
label | efa356c5-590b-57b8-b0d1-c5c223f6c809 |  | note | - - - - - - - - -
label | cee32148-d54c-52eb-8677-58ef3c0ac7b5 |  | note | IP
label | fc593338-798c-572d-8f35-1caf0cdf8414 |  | note | - - - - - - - - -
label | b4a3138c-b050-510f-9400-7efc333d5436 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3.3 - Preheating
label | 94806dde-2388-5151-99a9-6bfdd553b621 |  | note | Frequency: Ongoing
label | 65ee1dc4-8125-5883-80c7-bb41bf4c0be9 |  | note | - - - - - - - - -
label | 682f0fad-34c8-5fd8-93ee-a4cf077a3f05 |  | note | Acceptance Criteria:
label | f435c8b2-238a-5a4d-84fc-9527a7f79f35 |  | note | Please refer to table 5.3 to determine if preheating is required
label | 34b5f033-a0d3-533d-b8bf-f81aee90eeb3 |  | note | Grade 500N, bar size less than 40mm pre heating is NOT required
label | f64707f5-55c2-5acc-a2fd-b3084b2e3701 |  | note | - - - - - - - - -
label | dba33ff6-31b9-5cb5-97da-601b2ae5f78e |  | note | Reference Documents: AS1554.3 CL5.3 Table 5.3
label | d2d15eb3-d36c-57d7-9369-4938c9c50645 |  | note | - - - - - - - - -
label | 3d6c18a8-78a9-518e-b74e-04152ee70960 |  | note | Inspection / Test Method: Onsite Inspection
label | 3c155d27-fe45-5713-8dbb-b9527b03c3d6 |  | note | - - - - - - - - -
label | 72092f03-7b63-5b35-8abc-5f06eb042c4f |  | note | Record of conformity: Signed ITP
label | 946a2adc-d1da-51a9-b938-0fb6340df635 |  | note | - - - - - - - - -
label | aea1d238-028a-5016-ab67-c3d227ccf8fb |  | note | IP
label | a7c89f36-c339-5a20-97a7-f7015dd18b8a |  | note | - - - - - - - - -
label | 1a163e37-6aa7-5701-ad2a-74cc9a368ca3 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3.4 - Weather Conditions
label | d3584d8a-3eca-57ec-9c24-daf1d7d0d8c2 |  | note | Frequency: Ongoing
label | 650be565-fbb3-5549-83f4-25dda23921f3 |  | note | - - - - - - - - -
label | 5e67bbd0-6fb0-5892-b478-b8d48f48b491 |  | note | Acceptance Criteria:
label | 8f551892-c6ac-5b7b-a304-7ffcec2ca074 |  | note | Welds shall not happen when:
label | 22188c59-bf0a-51b2-b6c9-a607b281e3d2 |  | note | a) Temperature of the metal is colder than 0 degrees
label | edd47938-331d-51ee-b219-3d6cbb244e4b |  | note | b) Surfaces are wet. If surface can be dried pre heating is required to 20 degrees
label | ffba5e07-6187-5f11-a790-8ba06390d39b |  | note | c) During periods of high winds
label | 4e17e553-8771-5226-9cfb-e29c81ebf6f3 |  | note | - - - - - - - - -
label | b8731209-fea4-5517-9bb3-bf10d6916910 |  | note | Reference Documents: AS1554.3 CL5.5
label | 5fde583a-c98a-59ed-bedc-e6c86cfe6354 |  | note | - - - - - - - - -
label | 78265d05-4fd5-50da-b8c7-0fe3ae56e7c2 |  | note | Inspection / Test Method: Onsite Inspection
label | f85ed06a-d0ea-52b0-82ec-ecbc651f64c3 |  | note | - - - - - - - - -
label | c2197cc7-67e8-5808-a6a0-e88b60e6ed0b |  | note | Record of conformity: Signed ITP
label | 42602167-31bb-5964-82af-1def4c85ea9c |  | note | - - - - - - - - -
label | ccc9b0be-0280-54b3-9457-f74df08ebd0b |  | note | IP
label | b0d3fa7b-2595-5d12-8fad-6e7a59623512 |  | note | - - - - - - - - -
label | 0f394a8a-9dd1-595d-8391-06014864f02c |  | note | Responsibility: Site Engineer
checkpoint-group |  |  | section | 4 - Testing
checkpoint-status |  |  | checkpoint | 4.1 - Inspection and Quality of Welds
label | e2a3f6f0-68f8-539a-addd-899bdb553896 |  | note | Frequency: As per table 611.141
label | 1c0ec940-b9f9-5424-bc34-0c84e6c26903 |  | note | - - - - - - - - -
label | 22893580-711f-58d8-9a2f-991344b30ff2 |  | note | Acceptance Criteria: Testing shall not be less than what is shown in Table 611.141
label | a4a6ff4c-40f9-594f-b1d3-9eaa0cefcbef |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
label | b207fbf4-bf7e-5efa-911c-9114b8ef0e8b |  | note | Table 611.141 Inspection and Quality of Direct Butt Splice Welds
label | 23fbd8a7-a7a0-5d37-87e8-5ecc5cb2d7a0 |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
label | b263cf13-7e74-539a-b0f5-00c2bda8af20 |  | note | Inspection Process ¦¦ Minimum extent of inspection (% of welds, as no.) ¦¦ Detail of inspection of direct butt splice welds ¦¦ Quality requirements
label | f405dd0f-976c-5e68-a855-5c6fd31b8d02 |  | note | Visual inspection ¦¦ 100 ¦¦ Each full weld circumference ¦¦ AS/NSZ 1554.3, Table 6.2
label | 65bf6977-607a-5867-ad2a-0ff70e42cf5f |  | note | Non-destructive internal inspection by Radiography ¦¦ First two inspection lots :: 20 ¦¦ with a minimum of 12 bars inspected per lot, and at least 6 of these 12 bars to be examined at two directions, at least 60 degrees apart ¦¦ AS/NZS 1554.1, Table 6.2.1
label | 0e5cbef0-b6fa-567a-ab9e-38c134512427 |  | note | Non-destructive internal inspection by Radiography ¦¦ Subsequent inspection lots after first two :: 10 ¦¦ If more than one weld in an inspection lot does not comply with the quality requirements, revert to extent of inspection as for the first two inspection lots ¦¦ AS/NZS 1554.1, Table 6.2.1
label | 1e189ceb-eb88-5c12-842f-abc95a14ae4e |  | note | Non-destructive surface inspection by Magnetic particle, or Liquid penetrant ¦¦ 5 ¦¦ Each full weld circumference ¦¦ AS/NZS 1554.3, Table 6.2
label | 3cd2ed55-6de4-566c-a635-beea37baf3b4 |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
label | 9ad93c50-616f-5230-aa62-d87f5124b87c |  | note | - - - - - - - - -
label | 88d7fdf8-00e7-5122-bae8-f5e8120f9f6d |  | note | Reference Documents: VicRoads 611.14 AS1554.3
label | c614f815-b27d-5bbe-8479-e2d17ebb042f |  | note | - - - - - - - - -
label | 3d4c051b-ad32-58ce-ad3a-fa1c32cde051 |  | note | Inspection / Test Method: Test Reports
label | 2cd822ad-b107-54e0-9957-e0ad26cf1106 |  | note | - - - - - - - - -
label | 9b4aeb1b-5376-5102-8ae8-565a1145eedb |  | note | Record of conformity: Signed ITP, Test Reports
label | 55aa86c0-837f-5588-87a1-0300b9890c71 |  | note | - - - - - - - - -
label | 8da4a912-9566-59a0-802b-00be881ba614 |  | note | IP
label | 510b7e28-1039-5f21-a209-ca90389cf406 |  | note | - - - - - - - - -
label | af7c74f4-250f-52ea-b2b9-22014e6e3c8b |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
label | 17636bf7-9129-5ff6-89d3-b1d2a27d3ec1 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 091b60b2-909c-5ad2-8081-313cf3df84c3 |  | textbox | Print Name:
text | 2890f111-051f-523d-adf5-e35526daf37b |  | textbox | Position:
date | 587950a8-a2e6-5396-b72a-cfc65b6b2c51 |  | date | Date:
date | 66f1ac2e-8fdd-5bbd-893d-300dbf557031 |  | date | Work Completed On
checkpoint-status |  |  | checkpoint | Lot Verification.
select | 44003b29-8ad8-5b6d-a2c8-e1b7ef07fb47 |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | 533741ae-ee3b-5be2-bceb-9c2c15b70762 |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | a0434e9d-5c09-5534-9172-45b18e707237 |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | b5d0680f-867f-57a3-9cbe-562710c33425 |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | fbf506b6-977d-5d0b-84ff-ae4561195822 |  | textbox | Other:
select | f2bf7463-cd4a-5aa1-92bc-b56e8674015d |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | 0ddfe032-3757-5a93-8f28-7cec98dc5944 |  | date | Lot Closed On
text | 67bddf58-0b02-5543-9e7a-cecf4e86b689 |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-041-UT-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0041 - Water Protection Works | d40a78c4-a119-4ac5-9937-293b64db9f84
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | 69c7587a-6434-5123-a72b-d5b5cfeff659 |  | date | Lot Created On
date | d77fd1c7-992d-59d8-a2d8-274558dc69a4 |  | date | Lot Opened On
date | a7a1b4fd-4a66-52f1-bebf-c8b10f447246 |  | date | Work Commenced On
select | 8f7b0199-f020-5b90-b66a-34a27b071eb7 |  | dropdown | Lot Type | CIL-Civil Lot, DRL- Drainage Lot, EAL- Earthworks Lot, ELL- Electrical Lot, UTL- Utility Lot, STL- Structural Lot
text | 7f3174f5-98b2-5163-b49b-8c98737469d0 |  | textbox | From and To Chainage
select | 7cd1d73d-4eba-5e18-bee8-49046b21aeaa |  | dropdown | Construction Element | UTIL - Utility
select | 1f17ad80-acf6-5679-b79a-31441b253cbe |  | dropdown | Activity | WATE - Water
select | e66feaf8-f19f-5ba6-aad1-1d912b91aa30 |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | b886f52a-8a54-5a89-a79c-fc58f7d1b332 |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | a7be5c83-89f8-5d96-b2c8-9b55d9ebb206 |  | textbox | Engineer Responsible
text | 8dbf8040-76a1-51e3-b9a0-33e8bc946ab7 |  | textbox | comments
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Induction
label | b131dea4-7060-5337-98d8-4b67c840291d |  | note | Frequency: Prior to Commencing
label | 7c4873a4-ce18-5cb8-b9a7-380074d0f034 |  | note | - - - - - - - - -
label | 848cc756-3d16-5bfe-ac42-90098376bfee |  | note | Acceptance Criteria: All personnel on site have been inducted to the CRU site
label | c9eb1708-59fd-5f21-b194-7f0bb7009249 |  | note | - - - - - - - - -
label | 87953ca6-70b7-5092-b0bb-160653b2c137 |  | note | Reference Documents: PMP Inductions Register
label | 239a1e60-238c-5355-838f-3b538b212ea1 |  | note | - - - - - - - - -
label | d06d58c7-25d8-5102-a8c2-46f54ed363b6 |  | note | Inspection / Test Method: Document review
label | 44f7be6c-6313-59d2-8216-bd23dc56f83b |  | note | - - - - - - - - -
label | d9ba6d2a-3fc1-59db-8787-f76c152873a9 |  | note | Record of conformity: Site induction signed.
label | 8532b302-5b6b-58c0-85b7-56fb972ca8fd |  | note | - - - - - - - - -
label | b7679fd8-3831-5359-bbb6-ca3b2833723f |  | note | AP
label | c30e3075-f19d-5a97-be22-165b57d80551 |  | note | - - - - - - - - -
label | 3eb12b3d-04f4-5c77-9e88-4ece6c133d8a |  | note | Responsibility: Site Engineer / Site Foreman
checkpoint-status |  |  | checkpoint | 1.2 - Safety measures are in place, SWMS undertaken
label | c2030f98-d6c9-5300-a2b1-700cb9b94dc4 |  | note | Frequency: Prior to commencing
label | f2f894ee-7937-5f1b-9368-b8001a37f4ac |  | note | - - - - - - - - -
label | 107f9853-ceef-5470-b3d4-a983bb6137db |  | note | Acceptance Criteria: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
label | da66f60c-d68a-52bd-9b01-e48d7c256e9a |  | note | - - - - - - - - -
label | 004c547d-6d50-53dd-87a3-d61bc2a42b19 |  | note | Reference Documents: Health and Safety Coordination Plan
label | 3ac7ff09-4547-5710-b5fa-6a984d1de5bd |  | note | - - - - - - - - -
label | fe39fb7a-2f51-54d1-89a9-58b73794cc6a |  | note | Inspection / Test Method: Document Review
label | 70f114fb-fcd4-5d3b-8072-f959b0f7d9a6 |  | note | - - - - - - - - -
label | 354c8067-279e-5adc-87b8-bf0b25032f5f |  | note | Record of conformity: SWMS(s) signed
label | d490e1c5-ccae-5ebf-af1a-a1ef318d3b3f |  | note | - - - - - - - - -
label | 37b76164-b4bd-59b5-86dd-1fa369e35f77 |  | note | HP*
label | 5834c914-9ba7-514b-a0de-28a96db39f64 |  | note | - - - - - - - - -
label | 26d33566-d643-5672-afa2-52459f099b83 |  | note | Responsibility: Site Engineer, Site Foreman
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Check that current revision drawings are being used
label | a276e0e0-310f-54c8-9586-ff7c3e398d48 |  | note | Frequency: Prior to Commencing
label | 39805658-cad1-5759-98b4-e86f8b678c56 |  | note | - - - - - - - - -
label | 613c2cb6-389f-5bba-af70-3f9bd7356b87 |  | note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
label | fa938320-2733-54e9-af82-5568154488ea |  | note | - - - - - - - - -
label | 21a9d48b-5794-5ce5-8287-0e5007dc69b7 |  | note | Reference Documents: Project Drawings / Drawing Register
label | 2a25e717-0990-5330-b819-95bf7645eca1 |  | note | - - - - - - - - -
label | dbe40d67-03e6-5db6-ad98-bc5746351b45 |  | note | Inspection / Test Method: Document review
label | 4dcd6a3d-b8dc-5e4f-b9f4-1090d4ffcfa4 |  | note | - - - - - - - - -
label | 6aced582-44b7-59f8-93c2-f3a629ce1fb8 |  | note | Record of conformity: Latest Revision Drawings
label | a678ddb3-2636-57cb-85e1-343251b636cf |  | note | - - - - - - - - -
label | fbdd7b92-2341-5567-815f-21b3e8d2db11 |  | note | AP
label | e83a9a7e-0344-5cee-954b-51a02ec422e0 |  | note | - - - - - - - - -
label | d8f21a3c-ab02-556d-84f0-6cca6de7fb97 |  | note | Responsibility: Site Engineer / Site Foreman
checkpoint-status |  |  | checkpoint | 1.4 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
label | 73b8bbbd-29ec-5e68-a05e-e7c0469fe856 |  | note | Frequency: Prior to Commencing
label | 80ce3c16-54d1-5912-b8c6-2c993b139321 |  | note | - - - - - - - - -
label | adc95aa2-c068-5413-b104-cc5f6f9948e3 |  | note | Acceptance Criteria: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | 9fab5559-31cc-5a51-bd1a-cedac28d586a |  | note | - - - - - - - - -
label | fac8a329-20e7-5781-ba7d-8b59821904fb |  | note | Reference Documents: EMP, Site induction
label | cf47c0bb-66a1-5e85-8c85-329456277613 |  | note | - - - - - - - - -
label | c1dc0939-65c7-5a80-b54f-93fa4aae9e3a |  | note | Inspection / Test Method: Document review & Site inspection
label | 85ef5699-5f2a-5b82-b2f3-63bec9904bf4 |  | note | - - - - - - - - -
label | 1d7ee3ae-fe70-5ea7-8cfb-d3a47f7e554f |  | note | Record of conformity: Signed ITP
label | b042e3e6-8471-5ea1-acbd-3a0911dc4ee8 |  | note | - - - - - - - - -
label | 5bdc7729-0732-583c-b7e2-e3a160c19e9b |  | note | IP
label | cab7d17d-43e5-51d4-8c7f-d7b9f0e6291b |  | note | - - - - - - - - -
label | a13019b5-9a37-5490-a968-197212cb3d20 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 1.5 - Confirm suggested Asset treatment has been approved by Utility provider
label | 30142dbf-6d59-5c98-9f7c-99cf7fe20b25 |  | note | Frequency: Prior to Commencing
label | ce9037e5-6c6f-530c-b651-df11fb0bf57f |  | note | - - - - - - - - -
label | e68c9351-b054-515f-9dd7-68f660259b21 |  | note | Acceptance Criteria: Ensure that adequate notice is given to the Utility Service provider and Superintendent prior to utility asset protection as per PS3120.06 part C Date of Notification: Date of Utility Provider approval:
label | b9b4a1fa-8b0e-50a7-a832-7d67497787d9 |  | note | - - - - - - - - -
label | fdb2a064-fbff-5e7e-8696-e11c93e1720a |  | note | Reference Documents: MRPV- ITC Delivery Contract
label | fbff81eb-ebec-51aa-b0bb-bb88b1b90d1c |  | note | - - - - - - - - -
label | 7c16f6ce-6783-51e6-a5f1-eae210303325 |  | note | Inspection / Test Method: Document review
label | 00a512df-2bab-54b1-875a-44db52c7a002 |  | note | - - - - - - - - -
label | f94f3ca1-16d9-536b-aa32-5afd5fa04c52 |  | note | Record of conformity: Signed ITP
label | be76156d-5956-58d6-80cc-73c906bf5df6 |  | note | - - - - - - - - -
label | eafbe0c4-018e-5dff-9734-7fdb85d29b7b |  | note | AP
label | 474d299c-63be-5452-9e21-d38247d503e9 |  | note | - - - - - - - - -
label | 9b5beade-4908-51b9-a497-bbd74ac0001c |  | note | Responsibility: Site Engineer
checkpoint-group |  |  | section | 2 - Procurement
checkpoint-status |  |  | checkpoint | 2.1 - Approved materials ordered.
label | 14ba5a61-4632-5fd8-a338-8dc34f670578 |  | note | Frequency: Prior to excavate
label | 18570bed-fc1e-5e2d-b7dc-1e550737c32d |  | note | - - - - - - - - -
label | 90093e68-4e08-52f5-9a88-24d31fee10f6 |  | note | Acceptance Criteria: Complying with AECOM Utility Protection Detail Drawings
label | 101a6313-2152-547b-94ef-a48d98d6b806 |  | note | - - - - - - - - -
label | 125e5073-80cc-5804-904b-38e661cbb2c1 |  | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2126
label | 8ad04686-f7bd-5f57-9509-4bebedf90d38 |  | note | - - - - - - - - -
label | c5ee146d-fcba-5908-a4bd-d74edd8f12fe |  | note | Inspection / Test Method: Site Inspection
label | dadf2e38-86a1-5261-9a14-d3399b532b82 |  | note | - - - - - - - - -
label | e1ff4913-d227-5453-a4ce-e91775cc90f1 |  | note | Record of conformity: Supplier's Declaration of Conformance.
label | 53482e43-8bb5-5253-9812-08c82a538d2d |  | note | - - - - - - - - -
label | 93cba574-974d-5dd9-96d8-7c5e4530e166 |  | note | SCP
label | b38b2531-edc6-5a26-9bc6-69d6e5a64863 |  | note | - - - - - - - - -
label | c2f0166b-9f34-5060-a9da-06e9e335c032 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 2.2 - Receival and Inspection of products.
label | 1694c1c1-88d2-53c2-97cd-0273424dbaec |  | note | Frequency: Upon receival
label | cd8ad6dc-1cb4-5f56-b028-323cf999377b |  | note | - - - - - - - - -
label | 27a66c63-dd88-53ab-91e2-9963de9e836d |  | note | Acceptance Criteria: Approved Product and supplier. Right dimensions / specifications. Defect Free.
label | 5c3d373c-8b4d-5dc8-9e70-bd45a50aecec |  | note | - - - - - - - - -
label | 742ce207-47a1-565b-9bb2-fee6ece0fd40 |  | note | Reference Documents: Receival & Inspection Checklist
label | 909d9a52-6ae8-50b1-b167-cb0135657748 |  | note | - - - - - - - - -
label | 462ecfc7-ea4f-5583-bce7-13356c17da94 |  | note | Inspection / Test Method: Site Inspection
label | 690b3046-8efa-540c-a44c-154c752a1149 |  | note | - - - - - - - - -
label | 5d54c6ed-699f-5678-a0f6-2f58b1526654 |  | note | Record of conformity: Completed Receival & Inspection Checklist
label | 0ce47b38-2e7d-5298-9fde-076cd2ceea8c |  | note | - - - - - - - - -
label | d50c3d74-ec25-5c12-a757-bc1438d12586 |  | note | WP
label | 7b3fa231-67d1-55c8-8ff7-5edea6242afd |  | note | - - - - - - - - -
label | 1cea5b82-5148-5907-bf20-815614e4fb23 |  | note | Responsibility: Site Engineer
checkpoint-group |  |  | section | 3 - Construction Works - Detail 1 - Stabilised Sand Encasement
checkpoint-status |  |  | checkpoint | 3A.1 - Survey set-out
label | a5ef31ef-19d7-566e-ad9d-72cef54474fd |  | note | Frequency: Prior to Commencing
label | 985ade2a-749c-5470-a897-919ac6b4304b |  | note | - - - - - - - - -
label | d38e9765-30a8-5fdf-88b3-8f53e721534f |  | note | Acceptance Criteria: Latest available revision used
label | b17ed2b6-8424-5d19-928b-c45c41300dd7 |  | note | - - - - - - - - -
label | c6083a2c-a273-57f5-a4f2-eb5ec529784a |  | note | Reference Documents: Drawings
label | 4988efe9-8c01-5b8a-93eb-07ff82c4f8c7 |  | note | - - - - - - - - -
label | 1f901470-9e81-5b43-8911-804d0e837b2b |  | note | Inspection / Test Method: Site Inspection
label | 55aabb69-a250-5a35-af17-68832f8371e5 |  | note | - - - - - - - - -
label | 77f49ccf-4a8d-5b1a-b254-2c4763cec6da |  | note | Record of conformity: Survey records & pegs on the ground
label | afc08682-5fe2-552b-95b4-a8236c86b6e6 |  | note | - - - - - - - - -
label | b21c913f-1095-5f81-8406-ecf8c950bf8f |  | note | SCP
label | c8e5e502-fa24-5513-b431-2ccae3dff28e |  | note | - - - - - - - - -
label | 2eedaa38-f387-5142-95d0-b4c0d6f20c06 |  | note | Responsibility: Site Engineer & Surveyor
checkpoint-status |  |  | checkpoint | 3A.2 - Excavate and expose Pipeline
label | d51f8a1d-bc5f-5758-9e46-9cd32145c418 |  | note | Frequency: During construction.
label | 6f45a9f6-ab85-5c6f-b6b0-92adabed0cb1 |  | note | - - - - - - - - -
label | 2c25dfe3-1a6a-5500-8b64-26b960d11a53 |  | note | Acceptance Criteria: Ensure that the minimum cover requirements, horizontal and vertical alignments are within tolerances.
label | 77be4f5a-9276-5678-b5db-b39956887d24 |  | note | - - - - - - - - -
label | 535a1b50-0c66-5746-adb8-5bc31480a8bf |  | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2126
label | 032ab50e-1822-53be-a027-96de302c0854 |  | note | - - - - - - - - -
label | 2259abf7-82e6-5c89-a189-93df61bec77f |  | note | Inspection / Test Method: Document review & Site inspection
label | e7fa64db-e6ae-56d0-a558-6f451613cda8 |  | note | - - - - - - - - -
label | 94ddb1cd-3be7-5032-bc2e-ee7242e48a6d |  | note | Record of conformity: Signed ITP
label | d75433b2-b3fc-5d7c-a45e-b9c7cbe1f377 |  | note | - - - - - - - - -
label | 94edf095-4d0a-5e87-89f3-52268e5331fc |  | note | AP
label | 8ede8405-9f8c-5601-9b1f-e6295c8d7d58 |  | note | - - - - - - - - -
label | 0e21b44e-13f4-5c1b-8572-94ebecdd34fa |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3A.3 - Survey Pick up
label | f1a19da7-68f1-50c7-8e2f-f4bdcc256c17 |  | note | Frequency: During construction.
label | 552afe6d-fa82-5e56-a187-b8e2eb187e54 |  | note | - - - - - - - - -
label | 382ef7d7-384e-5730-8b1d-5005b132e904 |  | note | Acceptance Criteria: Once asset has been completely exposed surveyor is to complete a survey pick up at multiple points across exposed asset.
label | 93b208b2-7c92-504d-b335-503952aba26b |  | note | - - - - - - - - -
label | 89f4bc79-ee20-545f-a5c4-be02845a9c47 |  | note | Reference Documents: As Built documentation
label | 273e39ac-4228-522e-820c-164c6936e06d |  | note | - - - - - - - - -
label | 2f168490-3d53-5af1-8555-82ca29c5abf9 |  | note | Inspection / Test Method: Site Inspection
label | 05b93908-c67a-59c9-874a-45d1473d9e04 |  | note | - - - - - - - - -
label | 7e5b951b-3945-5d52-b32d-ffb26eea9b19 |  | note | Record of conformity: Survey records
label | 60228357-e11c-5c77-80db-467734fffcbb |  | note | - - - - - - - - -
label | 2559a74c-95f4-5d05-8fd2-507e2d4a1a8d |  | note | HP*
label | 1fe152f2-3626-5858-afb7-d23c953d4534 |  | note | - - - - - - - - -
label | eb7c8171-fe45-58c6-b732-907e692b92f4 |  | note | Responsibility: Site Engineer & Surveyor
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3A.4 - Place pipe protection material
label | 484e9129-5d1e-5d77-a6cd-411d5b254492 |  | note | Frequency: During construction.
label | b2f3df9f-4625-5407-b087-4134b3e08f79 |  | note | - - - - - - - - -
label | 793ca166-ac69-576c-bf7e-45a4f364b933 |  | note | Acceptance Criteria: Detail 1 - Place 5% stabilised sand uniformly along length of pipe, work into place under pipe haunches. Min cover requirements - as per MRWA-W-202. Marker tape to be placed above protection.
label | 1c23f4ef-40f3-5c42-941b-75468424680d |  | note | - - - - - - - - -
label | ffac7ccd-effe-5f44-9ba2-dd88933e3fc5 |  | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2116; MRWA-W-202
label | 3e496bc4-9843-5e22-8d0d-a1a2b8bc08ad |  | note | - - - - - - - - -
label | 7e512442-99f3-5354-9c9d-41b1943ea229 |  | note | Inspection / Test Method: Visual
label | f25751d7-97a0-59f0-8894-ab626207ee0b |  | note | - - - - - - - - -
label | 9aa3083f-94eb-5130-ad08-5a84726bfe9f |  | note | Record of conformity: Signed ITP
label | 51cfbad9-69f9-5fb4-b18d-0d72f38b2a68 |  | note | - - - - - - - - -
label | c14f02f6-f891-5109-a8af-8ae37e8a2d3a |  | note | WP
label | 08a3e2ae-cf6d-5d44-819e-a6fa2d951599 |  | note | - - - - - - - - -
label | d5c7157b-4dfc-52c1-9a02-502b4ebd6f7e |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3A.5 - Survey pick up- Encasement of Asset
label | 94ce0cd8-c686-54f6-a5ae-39c6858fea8d |  | note | Frequency: During construction.
label | 1e67e70c-5962-5935-8e1f-5cd79fa9ecd7 |  | note | - - - - - - - - -
label | 01ae5f67-2cbe-5eaf-98eb-f6f809772e8d |  | note | Acceptance Criteria: Once encasement of stabilised sand has been completed the surveyor is to complete a survey pick up across multiple points on top of asset protection
label | a4f2d7d6-637d-54c6-af4b-afaeca66d856 |  | note | - - - - - - - - -
label | 829017af-9b65-5ae6-9375-ac56d86d9a8f |  | note | Reference Documents: As Built documentation
label | 5f29a8fb-0385-503b-81f8-61a052f09bd3 |  | note | - - - - - - - - -
label | 4231f972-cd47-5d3b-b8e9-44e156063660 |  | note | Inspection / Test Method: Site Inspection
label | 8cf2a5bf-b755-53b7-a53f-47c1646d0099 |  | note | - - - - - - - - -
label | 5b2e77f1-afee-540e-b9e9-88ff646e2393 |  | note | Record of conformity: survey records
label | cecaca83-5b6a-50e7-865f-29ea58c9e3dc |  | note | - - - - - - - - -
label | 025ee293-4439-5375-9629-2e82eaeaf78e |  | note | HP*
label | ff7adbb4-fe22-5cd1-90ae-1bf81bb23fb9 |  | note | - - - - - - - - -
label | 99d5cf02-e36e-5696-a677-641e8d9e421d |  | note | Responsibility: Site Engineer & Surveyor
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3A.6 - Compaction Testing (where granular material forms part of permanent pavement)
label | 95d9649d-85d5-5470-aa81-945965335d85 |  | note | Frequency: Each Lot
label | 880c287b-d3c5-5df7-a91a-2327669b2bce |  | note | - - - - - - - - -
label | 5ecb6feb-5e9e-5dd6-9750-343704b8ee00 |  | note | Acceptance Criteria: Material during compaction shall have a moisture content of not less than 85% Compaction Scale A requirements apply Lower & Upper Subbase layer-Not less than 98% Compaction Layer directly beneath bituminous surfacing 100% Compaction
label | 116db504-a0eb-5b02-917e-ab85b20e39b4 |  | note | - - - - - - - - -
label | c33939e7-ad61-5313-8a2a-d100118fef52 |  | note | Reference Documents: VR304 Table 304.08
label | ec4595f1-dee4-556a-9860-ccb91017276f |  | note | - - - - - - - - -
label | b37c80b1-1f25-5fa0-8175-6a9844ea1f39 |  | note | Inspection / Test Method: Compaction Test
label | 5a97c601-41a3-5272-8c90-f0fc5db131d3 |  | note | - - - - - - - - -
label | 1cfef7b2-5c80-587c-9024-7bbacf79836e |  | note | Record of conformity: Test Results
label | 48609c30-6bba-5608-9a2f-d400bc0a082f |  | note | - - - - - - - - -
label | e29c7f47-b466-5598-a8a5-b180b6a6357d |  | note | TP
label | bc7cd0df-e147-5d7b-9921-1d729514138a |  | note | - - - - - - - - -
label | 9d51ef5d-f769-5f3e-b0ea-bf5105e216ce |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3A.7 - Post Compaction Grading (where granular material forms part of permanent pavement)
label | 046473c4-2de1-5626-80ae-b3a968a8565b |  | note | Frequency: Refer to table 304.111 for various minimum frequency or testing for Grading or PL
label | 12d6e8e6-747b-5b23-9d95-e4d92456b0f1 |  | note | - - - - - - - - -
label | ea07254f-8bc9-51e8-a591-be34db9208d6 |  | note | Acceptance Criteria: Grading and Plasticity testing to be conducted post compaction
label | 053be9db-9e55-5072-abd1-c9168b56a1df |  | note | - - - - - - - - -
label | 1c567e74-4091-5c4b-9a1d-e91d528e724c |  | note | Reference Documents: VR304 Table 304.08
label | 863d0aac-7c2d-5318-9f36-6cd50e8bc908 |  | note | - - - - - - - - -
label | 1af50f57-6068-5a45-84ee-f06a13f929d9 |  | note | Inspection / Test Method: Compaction Test
label | 0032af5d-bc91-5738-a655-237620cf10d3 |  | note | - - - - - - - - -
label | 25fefca3-d31f-5dd6-89d0-51e95a117985 |  | note | Record of conformity: Test Results
label | 8ba0e943-cac0-5c64-b66c-266e5c66a7fd |  | note | - - - - - - - - -
label | d309f0f6-4133-5ad1-8086-928386a21343 |  | note | TP
label | 9c3a786e-fd79-5a14-a9ee-e5e7f2526f67 |  | note | - - - - - - - - -
label | ed6b01a6-f3d1-5f02-a595-323636267f83 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3A.8 - Backfill Trench (where material forms part of permanent works)
label | 3ef0ab8d-f0e0-55ed-b1a0-55cfe2df2673 |  | note | Frequency: During construction.
label | ff46147e-d28c-5f89-a29a-de7ca7c3774f |  | note | - - - - - - - - -
label | 687beda9-2255-5712-bed6-9bba27aa1fd8 |  | note | Acceptance Criteria: Superintendent approved backfill material is to be used for backfill asp 1145-C201-ACM-CVP-DRG2126 Backfill is to be compacted in layers to achieve specified density uniformly throughout the depth of each layer. Material: Inorganic fill material with 75mm max. stone size (non trafficable) 95% Dry Density Ratio @ 1 test in each 900mm of fill & each 100Lm
label | 2a0199bd-f863-5954-a246-8ab5e1d3fcf5 |  | note | - - - - - - - - -
label | 35982683-0ea9-55e6-afab-c7f262e7a70e |  | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2126
label | cb718750-81d5-5a96-bec2-ed32c4616476 |  | note | - - - - - - - - -
label | f12b09c5-0d9a-50ff-9b09-9cbada80280b |  | note | Inspection / Test Method: Visual & Test Reports
label | 97e1bdbe-3372-5583-9a47-e2e50c084a3a |  | note | - - - - - - - - -
label | e7509ffd-cade-51af-99b1-28cf3b1d6750 |  | note | Record of conformity: Signed ITP
label | fda1f66b-5260-5eca-a87b-56cf8f8e2a2c |  | note | - - - - - - - - -
label | a47048a7-0c51-55f6-b538-565070da5dbc |  | note | IP
label | 025b10a9-4a23-5482-9ac8-a226a35a5f5b |  | note | - - - - - - - - -
label | bd5ab417-3adf-5ffe-9f28-6c75f5c1e7b1 |  | note | Responsibility: Site Engineer & Superintendent
checkpoint-group |  |  | section | 4 - Completion
checkpoint-status |  |  | checkpoint | Test Requisition
text | ab7a4528-397f-5ca3-ba82-9c25b8e109be |  | textbox | Test Requested on
text | 228c5303-1906-5eba-9bdb-9dfd871b15b0 |  | textbox | Location
select | b3155c65-8237-5964-8867-a0ce8640bc21 |  | dropdown | Material Type | Type A,Type B,See comments
select | adfaea73-3976-518b-a0a1-01dcb118b376 |  | dropdown | Material Source | Holcim,Boral,See comments
boolean | 71718492-a3d2-5942-871b-87cf83009219 |  | tickbox | Compaction Test (Standard)
boolean | 3db1803a-8f22-547b-8067-b21a7e942a36 |  | tickbox | Compaction Test (Modified)
boolean | 6184f0ba-0bae-500e-a64f-2129285638da |  | tickbox | Maximum Particle Test
boolean | 8e8412ae-acae-58bd-aaac-deb5faab995d |  | tickbox | CBR/Swell Test
boolean | 4b00e7ae-9cff-5851-8d14-1d0d408d6537 |  | tickbox | PI Test
boolean | 92baaa1b-6433-5979-9220-40d0fba59a2a |  | tickbox | Permeability Test
boolean | b9033816-69ff-5482-9987-9763a24bbc27 |  | tickbox | Grading
boolean | 7f28e43c-54ac-56b8-a9a5-9a644c6f9b0a |  | tickbox | Moisture
boolean | 85f09edd-75d1-5b52-8501-0023dc3c76f8 |  | tickbox | See comments
text | bc6faa3f-bae3-5715-a239-c5195d559acc |  | textbox | Test Level/ Layer
holdpoint |  |  | signoff | Test Requisition
checkpoint-status |  |  | checkpoint | 4.1 - Surface Reinstatement
label | be65d777-2412-5ade-96a2-a590c8415649 |  | note | Frequency: Completion of works
label | 73ec6e5f-bdf8-5145-8f3b-5826422e9247 |  | note | - - - - - - - - -
label | 4e69b5d2-0bf7-549e-84ea-4b98ed508cd2 |  | note | Acceptance Criteria: Surface reinstatement similar to adjacent undisturbed materials, visually accepted by Superintendent's Represented
label | c5ca1a06-de98-5481-933d-f650bd0a145f |  | note | - - - - - - - - -
label | a5cae9e4-fff6-5eaa-a194-c8001a0db9fc |  | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2126
label | e3bf20e1-1df3-5fda-937d-5900590c87b4 |  | note | - - - - - - - - -
label | dcf082c4-3f47-518e-93a4-40d60a1f15df |  | note | Inspection / Test Method: Visual
label | fa134e9e-7c77-5c1a-9d29-892d504e1ce2 |  | note | - - - - - - - - -
label | 2a3c3584-90e9-5f03-a7c2-ebc730f89f82 |  | note | Record of conformity: Site Inspection
label | db6a4cb4-87a9-5153-9cda-b22ff89d8d33 |  | note | - - - - - - - - -
label | 01b43f49-5de3-5508-8274-aa04c3d7a797 |  | note | IP
label | dc9c7ca0-f255-57fa-9b01-1fb36a242092 |  | note | - - - - - - - - -
label | 45fe2137-8919-5c4b-9068-121f4e6e330f |  | note | Responsibility: Site Engineer & Superintendent
checkpoint-status |  |  | checkpoint | 4.2 - Survey data captured for as-built purposes
label | 4c892123-ee62-5e90-a9be-a17035da1f27 |  | note | Frequency: Completion of works
label | c2e4b60d-e212-579e-a331-aed8a3f5010f |  | note | - - - - - - - - -
label | 6dc817a6-f1c8-5fa4-9b66-c86bc4dfd0fd |  | note | Acceptance Criteria: As-built Drawings Tolerances as per WSA 02 - 2014-3.1
label | 4bfca2c7-e388-5a95-bfc2-2200530a29c5 |  | note | - - - - - - - - -
label | f6a83e8b-e65f-5659-98ec-f7e8fbef3237 |  | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2126
label | 7b6b202c-9bac-50cd-abb1-e9091b9fe5f6 |  | note | - - - - - - - - -
label | 98d46d56-a99d-5182-aaa3-cb9fac095819 |  | note | Inspection / Test Method: Document review
label | 6d21ab52-d565-5ecc-8d5f-44aa383ed1e9 |  | note | - - - - - - - - -
label | 3c937135-65ba-5745-bd34-2c6fc9d65d23 |  | note | Record of conformity: As-built survey records
label | 45c64c5c-6722-5078-ab80-a02c01b2380c |  | note | - - - - - - - - -
label | a04d4bbc-5544-5350-b888-c58143854c14 |  | note | AP
label | 98f461c4-3999-559d-a923-c205162e580d |  | note | - - - - - - - - -
label | f663a37e-2c86-586b-b400-78a0908b1502 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
label | 4dde93dc-608f-55ec-bc61-45624228c1cf |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 771a6864-2481-5908-b5d5-702e763e4762 |  | textbox | Print Name:
text | 859a7ec7-3878-5da0-a602-b06f2168a343 |  | textbox | Position:
date | fd010bf4-0ca9-5689-9f69-bd65fcd8e040 |  | date | Date:
date | a7012071-a1a6-534a-82cc-70e91b97a431 |  | date | Work Completed On
checkpoint-status |  |  | checkpoint | Lot Verification.
select | 603f5047-3bd6-5da2-83c1-743341990100 |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | 836d52e6-803e-5d7b-a70f-216e31836944 |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | 9d357a54-8e71-5306-872a-82c073eab8fc |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | 6577664d-1ed7-502d-a8ec-d99d08ef196c |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | 8ec963c3-de09-5c38-85a0-fb00932e29c8 |  | textbox | Other:
select | 69579fbb-b141-5362-af3d-1b62c53b6709 |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | 65cb42b9-282b-5b63-b3e4-1dd1bc0387ae |  | date | Lot Closed On
text | a005cab4-5e49-51f0-993c-6b862d1c9908 |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-082-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0082 - Structural Patch Repair | d71c343f-e523-4e3a-8a98-3116a55cd569
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 00c397ca-b117-585a-9418-16059c7cddb6 |  | note | Document Title: ITP-082-AX-LOT-XXX - Description
label | 41761891-4650-5f6c-8151-61e077c83f7d |  | note | ITP Description: Structural Patch Repair
label | 36824288-5536-5459-8a18-b9c927f99918 |  | note | Document Number (in Teambinder): 1145-C200-FUL-QAC-ITP-0082
label | e2084857-067a-5b77-ad06-fa2ef0b9d6e5 |  | note | Revision Number: 00
label | 90640134-67e1-58e2-9bfa-6fcc1d42b8ce |  | note | Revision Date: 09/05/2022
label | 307a0ae5-3c9f-5ed5-8ac0-5623f24545ef |  | note | ITP created by: Omar El-Khub
label | 3beedde7-2ef2-53b7-94c5-a74e9c9cde56 |  | note | ITP approved for use by: Babak Rudd
label | 4827feb8-6836-5168-82e7-7ee3d5f85457 |  | note | 1.1 VicRoads Section 689 (Dec 2017)
label | 3ab25ba2-17a1-52f9-b7b9-9f3dc3974e71 |  | note | 1.2 AS1012
checkpoint-group |  |  | section | 1 - Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | 5d792849-2c71-5972-b57f-e41907b0ed54 |  | date | Lot Created On
date | ca714714-6223-5211-8ec1-be8f52439512 |  | date | Lot Opened On
date | c7cb9c55-5d76-5290-a837-4146552d2333 |  | date | Work Commenced On
select | 6623e577-5556-547d-a6fe-d962526da4f8 |  | dropdown | Lot Type | STL- Structural Lot
text | 699752e6-4b8b-5733-8ddb-231950e13d59 |  | textbox | From and To Chainage
select | 6db8f428-625d-50ce-a1e6-7818f9f01db5 |  | dropdown | Construction Element | SITE - Site General
select | 914445a8-ea16-528e-9f79-a4251f23000f |  | dropdown | Activity | OTH - Other
select | 3ea03e19-6fca-57ea-8293-b8d024352ac4 |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | 07ce336f-c1c4-52d6-a93f-c468c7deec6f |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | 8af61da1-705e-51a9-9ebf-7f7f19b87c4a |  | textbox | Engineer Responsible
text | 651ce4cb-ce72-5710-b618-0136b89d9203 |  | textbox | comments
checkpoint-group |  |  | section | 2 - Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 2.1 - Assessment of Affected Concrete
label | c4e225ff-1dd3-56be-893c-86f6e0b08d7d |  | note | Frequency: For each element, prior to Works commencing
label | 725c55ac-7dc3-528d-882d-4209ed15fd40 |  | note | - - - - - - - - -
label | 4b8e8f48-66ca-563c-b162-df5b8f50159b |  | note | Acceptance Criteria: Contractor shall assess the affected concrete to determine influence of spalling, deterioration, and honeycombing on the load bearing capacity, serviceability and durability of the structure.
label | a5646d73-2f88-5c71-a6e3-b596240abab1 |  | note | - - - - - - - - -
label | 1750b062-0e3c-582b-af58-39d91f50ddd5 |  | note | Reference Documents: VicRoads Spec. Cl.689.02
label | 84cf7d92-cb25-54bf-8d30-e89d1608a4c7 |  | note | - - - - - - - - -
label | 72fc3cfa-1fba-5362-8544-d3194990e386 |  | note | Inspection / Test Method: Visual Inspection
label | 5291f6b8-f316-5f06-8c55-6559e254d2bb |  | note | - - - - - - - - -
label | 4e59b39c-be55-5ec0-a1c3-5a975e5192d0 |  | note | Record of Conformity: Hold point released
label | f881dd99-b715-58c8-8ed6-783ab251c0ef |  | note | - - - - - - - - -
label | 98b601d4-d1d5-5ebf-958c-c5b5a024e1a1 |  | note | HP
label | b3a8f3a7-33fb-571b-acba-8a5db2c29a2f |  | note | - - - - - - - - -
label | 26de7a39-a6c4-53a0-932b-491f507b2429 |  | note | Responsibility: SE/PE and Superintendent
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.2 - Deviations from Manufacturer's TDS and/or Specification
label | 835a1137-480c-511b-ac22-f156b6e7ea10 |  | note | Frequency: For each element, prior to Works commencing
label | 92254b42-3a26-5081-bd26-cd1d26d8712f |  | note | - - - - - - - - -
label | d9e2ce12-8024-5fcf-b14b-6687d8787e8e |  | note | Acceptance Criteria: The contractor shall perform concrete repair work in conformity with the manufacturers specifications. Any deviations from manufacturers specification must be submitted for approval as an updated WMS and/or ITP.
label | fdf0dcca-8d48-581f-b168-a8a35aecfdc2 |  | note | - - - - - - - - -
label | 8a1eac11-109a-58d7-b092-64ac678b30a2 |  | note | Reference Documents: VicRoads Spec. Cl.689.08 Product TDS
label | d933c7c3-c89b-52f6-a8fb-e66db0926180 |  | note | - - - - - - - - -
label | 755c6f09-1a09-5cd2-9259-431d129de9ba |  | note | Inspection / Test Method: Visual Inspection
label | 064e58c4-7c03-54ff-b066-214144ffca95 |  | note | - - - - - - - - -
label | 8fc4dab9-2a2e-5f3a-b631-7b672b9b74cd |  | note | Record of Conformity: Hold point released
label | 90ad157f-52fa-5437-9f16-8dcb2c55e355 |  | note | - - - - - - - - -
label | 9b34d773-9f29-581d-9791-442b3eb1ad6e |  | note | HP
label | ac118c67-841b-5aac-ba61-2213f3fd1ce4 |  | note | - - - - - - - - -
label | e2c45bb6-43db-521e-9614-9353b9f05770 |  | note | Responsibility: SE/PE and Superintendent
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.3 - Work Method Statement and Inspection and Test Plans
label | baeb1e1f-52b5-5655-9e13-ba745e95326c |  | note | Frequency: Prior to commencing repair
label | 74ec7761-cc7e-593f-800b-3c1797fbfdcc |  | note | - - - - - - - - -
label | 5468294a-181c-57ce-8432-4009a997184f |  | note | Acceptance Criteria: WMS and ITPs completed by FH should be reviewed and approved by the Superintendent
label | ed311e93-f2c0-550a-bd9e-ffbc77f03214 |  | note | - - - - - - - - -
label | 16c713a4-a387-54b1-b6c2-b5974b1d0809 |  | note | Reference Documents: VicRoads Spec. Cl.689.13
label | 34d4a833-03fb-5f5c-a5ad-f399f77af37a |  | note | - - - - - - - - -
label | 838d9607-9573-533b-b571-948085af2e0d |  | note | Inspection / Test Method: Document Review
label | dacbb8d4-01d0-5876-ae2f-82e226422ee6 |  | note | - - - - - - - - -
label | 9792db99-072c-55cb-97c3-dfb98d25e5cf |  | note | Record of Conformity: Hold point released
label | 5b612aae-1e61-5574-bca5-c39fea50ce7b |  | note | - - - - - - - - -
label | 3596630a-830a-5b9f-95b5-3d47aa180c0e |  | note | HP
label | 44b62041-cea3-59cc-bc98-32ded36fb82d |  | note | - - - - - - - - -
label | b65e3eb4-b310-575b-8f20-2d3197dba72b |  | note | Responsibility: SE/PE and Superintendent
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | 3 - Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 3.1 - Material approval and Reference
label | 65ce6e79-0bfa-56da-b864-92ffbc0481bd |  | note | Frequency: For each product, prior to Works commencing
label | ece3c4a4-682a-5976-81ac-24a4cbd3f40a |  | note | - - - - - - - - -
label | ea390678-c204-51a4-9107-aa105e766598 |  | note | Acceptance Criteria: Is the selected repair mortar material capable of:
label | 57c28646-1b8b-5747-9274-ad7aa11e3dc1 |  | note | being hand applied in vertical and overhead sections up to 30 mm thick in one application with no slumping;
label | 750c34a5-c333-5cd5-8852-763ddeebad53 |  | note | achieving a drying shrinkage ≤600 microstrain;
label | 47b2f89c-e05d-510f-9a69-8b2fc9ac7ef1 |  | note | achieving a minimum wet density of 1600kg/m³;
label | bb01630c-e9c3-5aa0-af88-198c3cdc6d2b |  | note | achieving the strengths and bonds conforming to the requirements in Table 689.061.
label | 72af5fe5-845c-585f-98fd-03e059694db3 |  | note | Is the selected fairing coat material capable of:
label | 12c7ed76-2e29-5b08-a9d3-2041142fe36b |  | note | application to 0-3mm thick;
label | 0213b3f6-0c2d-5ddf-bdae-959d38eebadf |  | note | covering a large area without shrinkage cracking.
label | 6d867d83-9709-5cbd-a407-f88ee1f0772b |  | note | The following information shall be provided with each batch:
label | 81a5ec39-94a8-5daa-a694-dc2ddf7537db |  | note | Manufacturer's name and address
label | 0b79dcc0-a185-5e50-9244-a38c827be6e5 |  | note | Product reference
label | 2eea2df6-b4f7-5b56-a42b-bb12d46278f2 |  | note | Batch number of identification
label | 6a839731-f6e2-58e1-9af2-791dc1164e37 |  | note | Quantity manufactured in the batch
label | 522891f1-2cbb-5006-9231-d8cba59149d7 |  | note | Certificate of date of manufacture
text | 0364299a-d777-583c-9aad-5b8b2cd3f151 |  | textbox | TeamBinder Material Approval Number:
label | 89e37b5a-4d07-5f0f-b4cb-a999c47610b0 |  | note | - - - - - - - - -
label | 5cada697-c60b-57f8-b53f-d2c676c85f17 |  | note | Reference Documents: VicRoads Spec. Cl.689.08 (a)
label | 6e2aa6e8-612d-5ba8-9176-69c6322a58be |  | note | - - - - - - - - -
label | 70f8867f-e8c4-576c-9549-9f339049da32 |  | note | Inspection / Test Method: Document Review
label | daa19242-99cb-596e-aa96-db26a39e1de9 |  | note | - - - - - - - - -
label | 437236f7-c743-5adc-b37a-5459f76c30a0 |  | note | Record of Conformity: Attach repair mortar product TDS, Attach fairing coat product TDS, Signed ITP
label | e96b1945-3997-5e1f-af67-4bbcc3be7d47 |  | note | - - - - - - - - -
label | 51dab150-4520-5b04-8d3c-16fb39bea959 |  | note | IP
label | aa277bbe-e56f-5264-9010-36bc58783c6e |  | note | - - - - - - - - -
label | 779b705c-e609-5069-b361-ecff7ac6ebed |  | note | Responsibility: SE/PE
checkpoint-group |  |  | section | 4 - Structural Concrete - Cementitious Patch Repair - Application
checkpoint-status |  |  | checkpoint | 4.1 - Surface Preparation
label | a279ee33-3899-5b6e-aa8c-a8010648020f |  | note | Frequency: Each element
label | 3a50a311-ce9f-55c5-9052-5d162f36ea44 |  | note | - - - - - - - - -
label | 32aa3ca6-4545-5989-bec6-8486aec64af1 |  | note | Acceptance Criteria: For all types of patch repair all defective and delaminated concrete and existing repair materials shall be broken back to a sound and dense concrete surface. Defective concrete shall be removed using light hand held percussive equipment or high pressure water jetting
label | 68cab0ea-1e61-527f-86df-f8439749d520 |  | note | Resulting cover allowance:
label | 7311d360-6ee4-5245-bfc6-f4f6be3e3d95 |  | note | Exposure classification A and B1 = 20mm minimum
label | 605998d2-1903-5e03-b18d-7fa1f99980bb |  | note | Exposure classification B2, C1 and C2 = 50mm minimum
label | e392abd6-87fc-5347-8b36-57ee082217f5 |  | note | All concrete surfaces and mortar substrates shall be sound, clean and free from dust, oils, and grease and surface contaminants. All loose and unsound materials and surface laitance shall be removed
label | 4eac9847-e6c7-5b6c-a7a9-bd52f27fbf12 |  | note | The concrete substrate and any exposed steel reinforcement shall be cleaned by a final wash down or by blowing down with oil free compressed air to ensure removal of all residual contamination. The prepared concrete substrate shall be thoroughly pre-wetted with clean fresh water and shall be surface dry prior to application of repair material
label | 64f537dd-f974-57bb-9b98-eeff6007bdee |  | note | - - - - - - - - -
label | d186c296-487b-5e34-9e7d-88cacbb628a4 |  | note | Reference Documents: VicRoads Spec. Cl.689.08 (b) and (c)
label | 48825f0f-92d8-5ace-bdbe-8f5ff48cbad9 |  | note | - - - - - - - - -
label | c3392059-a4c5-5b25-9aaf-9a910e24cc7f |  | note | Inspection / Test Method: Visual Inspection
label | b7d0f548-56e8-5a6a-9b41-d29753e35ab9 |  | note | - - - - - - - - -
label | 00b472e3-2b10-581b-b98b-6e63f41a7c1f |  | note | Record of Conformity: Hold point released Signed ITP
label | 0a0bfbe5-e04d-5a7e-96ff-eef37a20d936 |  | note | - - - - - - - - -
label | 6e858867-065c-5a58-b4d1-fa4990f0bff7 |  | note | HP
label | c4ef4d14-ac09-5295-99cd-15172affc304 |  | note | - - - - - - - - -
label | f5f53ee6-d276-5673-ad54-a6e6e840f557 |  | note | Responsibility: SE/PE
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.2 - Pre Application of Repair Mortar
label | 4ae9cee8-8c63-59a8-82bc-c1c48150ce43 |  | note | Frequency: Prior to each repair
label | 1143e5d6-651a-55c7-beb5-df1c04279a18 |  | note | - - - - - - - - -
label | d681c27c-089d-5c3c-a66b-70f85a9ed0c5 |  | note | Acceptance Criteria: Reinstatement of prepared areas shall not commence until:
label | 1d0d8346-4a31-5955-9c80-561806c9d514 |  | note | (i) a joint measurement of the repair area by superintendent and Contractor
label | 39a91894-4176-5b2c-9bbd-5237abdee70d |  | note | (ii) evidence the area conforms with specifications
label | eb136af2-5282-5730-912e-14fe81d09fc7 |  | note | (iii) Contractors quality procedures have been sighted by superintendent
label | e347d272-4f67-517b-985d-04274d8954c8 |  | note | The repair mortar shall be thoroughly mixed in whole bags with potable water prior to commencement of application.
label | e027fab0-152b-59d9-aab6-e7e5f0f5607a |  | note | All materials shall be applied in accordance with the manufacturer’s specifications or instructions for use in a continuous process.
label | 9050a67f-038a-5c34-9774-fa71153b7aa7 |  | note | - - - - - - - - -
label | 2374a9cf-0dae-5497-a3d8-1ff05a644a9e |  | note | Reference Documents: VicRoads Spec. Cl.689.08 (e)
label | 1d72f71c-2455-5342-baff-447eb2642770 |  | note | - - - - - - - - -
label | dc424bc2-506a-581f-8648-a46742c8f011 |  | note | Inspection / Test Method: Visual/ Measure
label | f4b81d5f-f619-529d-b005-9363e2d338a4 |  | note | - - - - - - - - -
label | 6ed1970f-ccac-50dc-8621-7c9322686fcf |  | note | Record of Conformity: Hold point released
label | f3289cd6-c9bb-5ee6-aede-1aad702ee033 |  | note | - - - - - - - - -
label | 67d1386f-7a45-5c43-8549-b2cae6b0bc1e |  | note | HP
label | f195cd9c-2e12-5500-9fe4-7406a806bcde |  | note | - - - - - - - - -
label | 4ff59b32-f6db-5a53-a827-100827f60a4b |  | note | Responsibility: SE/PE
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.3 - Application of Repair Mortar
label | 4e0ae27e-6b34-52ae-9add-b9a7fb4bfa59 |  | note | Frequency: Each Repair
label | 8dbd8b49-4683-5f07-a8a5-bc6e7e9338b9 |  | note | - - - - - - - - -
label | 4326493b-4754-5c7e-b3e0-0135e4f7bd1b |  | note | Acceptance Criteria: Temperature at time of application:
label | 4c0f22a0-fa17-5cda-b66c-31880c6c6e65 |  | note | below 5°C or above 35°C
label | 415e49f1-eba6-544a-bde0-be51ab0b3f91 |  | note | Repair material shall be applied while the substrate bonding coat is still tacky
label | 9bfb13ff-c796-5aba-a38b-2b7e7f501538 |  | note | Where formwork is used to facilitate the patch repair, it shall be pre-treated such that it prevents moisture absorption from the repair mortar and positioned such that it does not inhibit effective compaction of the repair material.
label | c24c6ecd-6ef6-59af-aa11-daa50bb0b300 |  | note | Concrete shall be rebuilt to the original surface profile using a cementitious repair material. Where the existing concrete cover to the steel reinforcement is less than the design requirements, the new repair shall be profiled as required to ensure that a minimum cover of polymer modified repair material to the steel reinforcement is achieved as specified in clause 689.08(b).
label | 53543066-1c0c-50eb-bb8b-9a8b698de23f |  | note | - - - - - - - - -
label | 1c0c6369-c951-5262-a7c7-0db6056e3b4e |  | note | Reference Documents: VicRoads Spec. Cl.689.08 (e)
label | 34f10dfe-9302-51ca-b63d-daef5de0f75b |  | note | - - - - - - - - -
label | 7c5672cb-c143-5793-9b4d-3f6aef7ff067 |  | note | Inspection / Test Method: Visual
label | 56cc2207-ae19-54ca-b922-57b492ee4e10 |  | note | - - - - - - - - -
label | a9c638a0-ad27-50e6-b15b-e72a2047134e |  | note | Record of Conformity: Signed ITP
label | b2c0851c-ef38-5a1d-89fa-0cc782c9a1fc |  | note | - - - - - - - - -
label | d7009457-d1cc-5ab5-9b25-8528d3e2ec00 |  | note | IP
label | 002b3780-2e26-5219-9ffd-e53b91646df0 |  | note | - - - - - - - - -
label | a60a39bc-8e28-5263-ba3f-259778a15821 |  | note | Responsibility: SE/PE
checkpoint-status |  |  | checkpoint | 4.4 - Measuring Tolerances
label | 0b0bce7f-578d-5c2c-82f5-6d1b9a5ae013 |  | note | Frequency: Each Repair
label | f0717e0c-d5d5-5216-87ca-4d47e2389d21 |  | note | - - - - - - - - -
label | 396b6c11-bb57-5b40-902b-03eeb9bb9b94 |  | note | Acceptance Criteria: Tolerances applicable are:
label | 599a6e24-020b-5c51-a230-1f152e65d050 |  | note | Edges and Surfaces: ±3mm
label | 0ac6655d-5797-517c-a3bb-68f1e5a58af5 |  | note | Maximum allowance for irregularities: 3 mm with a 2 m straightedge
label | 71e44aad-32f8-53c7-92d4-b3dce7de8c4d |  | note | Maximum allowance for unevenness: 1 mm with a 300 mm straightedge
label | c9cc49cb-9fa3-5455-b1ab-178c5d505055 |  | note | - - - - - - - - -
label | 2034a10c-3dcd-50f1-99d6-52ce450bb0e4 |  | note | Reference Documents: VicRoads Spec. Cl.689.11
label | bc3864ac-fd03-55f2-ba52-f4fadad9a3bc |  | note | - - - - - - - - -
label | 52da5db3-2a57-5514-8394-728cd81e3fb1 |  | note | Inspection / Test Method: Visual/ Measure
label | d3a56ff4-9c8a-5703-98ce-320d1d0eeb2c |  | note | - - - - - - - - -
label | b54f5c30-72d5-512f-ba4a-b876170c89c5 |  | note | Record of Conformity: Signed ITP
label | 6b20d70d-542e-5f4e-8515-c7532d458f99 |  | note | - - - - - - - - -
label | 16674a7b-728f-5fa8-b99e-d0a668787a10 |  | note | WP
label | 3b223433-85e3-5b6e-9ed1-ce77c36b1712 |  | note | - - - - - - - - -
label | 4d3b0f98-338e-5ddb-acd0-6e3f34238ea7 |  | note | Responsibility: SE/PE
checkpoint-status |  |  | checkpoint | 4.5 - Cementitious Repair Mortar Test Cubes
label | 389ede12-21c9-55a6-a0b3-d8c82ee7dd70 |  | note | Frequency: Test Specimens
label | 959fdf92-44ec-5f29-8be5-c5bec69a8cbc |  | note | - - - - - - - - -
label | 57746050-5f14-54a7-9ebf-6cc9938fbc53 |  | note | Acceptance Criteria: Three 75 mm test cubes shall be taken from the first batch of material mixed, then three 75 mm cubes for every 100 kg of material used thereafter to test for compressive strength. Test cubes shall be made of steel or polystyrene and shall be fully sealed.
label | 7b8ae619-681f-54cb-aea4-67378dd6c73c |  | note | Cubes:
label | 03a71fc6-79b3-55b2-ae4d-df67322de4b0 |  | note | 2 specimens tested at 7 day strength
label | 86c347b5-f325-51eb-b24c-6cb7fdf62a76 |  | note | 1 specimen tested at 28 day strength
label | bc7a60f7-68df-517e-ad94-5cc25ff7ff30 |  | note | - - - - - - - - -
label | 56191b92-0b57-5f26-a3d2-8be5a7ec17d4 |  | note | Reference Documents: VicRoads Spec. Cl.689.12 (a) Table 689.061 AS1012.8.3 AS1012.9
label | 69ad23dd-da0c-57d7-bfb5-27ea75f29f8d |  | note | - - - - - - - - -
label | b5573200-da0e-5512-9853-574f24a3ef86 |  | note | Inspection / Test Method: Test
label | 03d02fb1-209b-5088-8c4a-726ba7e29b34 |  | note | - - - - - - - - -
label | 477c4641-3875-573a-b4b1-2d4d6921d4a2 |  | note | Record of Conformity: Test Results Signed ITP
label | 8cea5c59-2deb-5f59-987d-aca2e604de8c |  | note | - - - - - - - - -
label | 40c915dd-7732-5e28-b749-48a9b805cd56 |  | note | TP
label | 1886666c-528c-542e-b474-df2f1efb0ccd |  | note | - - - - - - - - -
label | d33ebbc9-b92e-5492-b804-430aa283d38d |  | note | Responsibility: SE/PE
checkpoint-status |  |  | checkpoint | Final Inspection
label | d36d167c-2eb5-5582-891c-cf4f89c96f1c |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | a2dd93d5-bb9e-5b3f-be92-469c4197adae |  | textbox | Print Name:
text | 7a05fc52-f359-5773-b144-98f4343d3c06 |  | textbox | Position:
date | 7a71f668-9f01-5d2d-8bc9-00a7aa81946d |  | date | Date:
date | 911f687e-b2dc-5bdf-ab03-779e90af4646 |  | date | Work Completed On
holdpoint |  |  | signoff | Sign ITP
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification.
select | f70875bc-9887-57b8-9e20-b482f393a5ed |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | ebb625f3-37e9-551e-adc8-7f97a0bb24c0 |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | 5cc9788c-7521-50f8-837a-22618de1f082 |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | 39cb4efc-2d35-5aa8-832c-c5b90da7c5d9 |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | ab57edd6-dbc8-521e-a51f-81d6e9e39684 |  | textbox | Other:
select | b9c98425-2497-5f7f-a26b-ef16ef65b930 |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | 5d48e787-57cf-5923-ad11-0647cc3b173a |  | date | Lot Closed On
text | 6b870370-8372-5838-950e-9b81048ca36b |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-074-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0074 - Installation of Fencing | d7f927f7-508a-4e63-b7bd-b65ce0a0c1b2
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | 0a668bb8-c8cb-5c0d-881c-43940e7cc13a |  | date | Lot Created On
date | 1af896a6-e222-597a-bbdd-9fdf7fcdf372 |  | date | Lot Opened On
date | 8615010b-6a98-5fd0-b7b7-0c7cc7047a6e |  | date | Work Commenced On
select | e5f43a5d-67fe-5d87-8e00-1b4d46dfa5b3 |  | dropdown | Lot Type | CIL-Civil Lot, DRL- Drainage Lot, EAL- Earthworks Lot, ELL- Electrical Lot, UTL- Utility Lot, STL- Structural Lot
text | 32589c78-1617-53e5-9107-13cda8c96648 |  | textbox | From and To Chainage
select | b4773811-904a-57a3-a454-d69aa48ca51d |  | dropdown | Construction Element | ROAD - Road Furniture
select | c9eb4534-5360-58be-b456-ead31d27a057 |  | dropdown | Activity | FENC - Fencing
select | 4074ed9b-0086-502d-936a-62836f78e592 |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | 15caf064-c384-54a7-b419-aea0a02db0ec |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | 151616a5-893e-5256-a2fe-03fd0228521c |  | textbox | Engineer Responsible
text | d876187f-939e-5e6b-b614-0f95564cc0b8 |  | textbox | comments
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Check that current revision drawings are being used
label | 8272ed9c-f676-51bf-b9f4-cad2aefda2a8 |  | note | Frequency:
label | f6e73758-70f2-57e4-b3df-aefa6b6d0372 |  | note | - - - - - - - - -
label | 1d603eac-98fb-50cd-8a65-6d03027a785d |  | note | Acceptance Criteria: Prior to Commencing
label | 44ef205f-ee3f-5e75-8cfd-0145d7792234 |  | note | - - - - - - - - -
label | 4d8ff7a4-aa0a-5f2b-a1bd-11a5d6f8fd24 |  | note | Reference Documents: Issued For Construction (IFC) and latest available revision used.
label | e4542977-fe01-568f-b20e-6752966595c2 |  | note | - - - - - - - - -
label | 7b4c65ae-1da7-5500-a2c1-7c9589f2accd |  | note | Inspection / Test Method: Project Drawings / Drawing Register
label | 1f8a719e-12f1-5b88-a26f-1bc849dc011a |  | note | - - - - - - - - -
label | 5b5cabf8-60b4-533f-b34d-3cdac8aa529b |  | note | Record of Conformity: Document review
label | fe961f74-b692-5a66-8033-b17378e685cc |  | note | - - - - - - - - -
label | 5310bcb6-c926-5ffa-8087-7b328eb4e0ac |  | note | Latest Revision Drawings
label | ac140c3b-0763-588e-88e0-4b89497f8c03 |  | note | - - - - - - - - -
label | 4d3655b5-2633-5e10-a20b-2373a9d0f768 |  | note | Responsibility: AP
checkpoint-status |  |  | checkpoint | 1.2 - Confirm understanding of current Environment Management Plan (EMP) related to the work area and that all prescribed environmental controls are in place
label | 77c199b9-8975-51c4-8a04-7b23ab72ce33 |  | note | Frequency:
label | 614619a3-8e5d-5574-aee4-15a9b1b2cbd4 |  | note | - - - - - - - - -
label | 98bb8caa-e7eb-554d-b74d-e524df237e5e |  | note | Acceptance Criteria: Prior to Commencing
label | 3e60a630-8782-572a-a854-ff58b68a7e2b |  | note | - - - - - - - - -
label | 2f3dc5fa-50a9-5202-adfa-79655f84ccc7 |  | note | Reference Documents: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified .
label | a9de1f7b-6e0a-579c-883e-3ae248392109 |  | note | - - - - - - - - -
label | 8d8adf0a-af1a-5a36-8d88-25bc68ad8135 |  | note | Inspection / Test Method: EMP, Site induction, Project Specification Cl. 1200.03
label | 07d26f75-eee3-5d41-b4ab-daeaaa5b0f07 |  | note | - - - - - - - - -
label | d97bc0b2-2df9-5a1e-b58f-076c4e3499be |  | note | Record of Conformity: Document review & Site inspection
label | 3ac20a9a-487a-5bdf-b261-29c02ef3fcef |  | note | Signed ITP
label | 8ec23993-0218-5dd2-8a99-ac8d9798bb78 |  | note | - - - - - - - - -
label | 14c873c2-9cf8-5934-b099-78d93c6c459e |  | note | Responsibility: IP
checkpoint-status |  |  | checkpoint | 1.3 - Excavation Permit Issued
label | 38a7b493-c5fe-572a-b9b5-e501aad9c750 |  | note | Frequency:
label | 223ac2dd-1d1b-5780-896c-16448427166e |  | note | - - - - - - - - -
label | c99e1abb-0acd-5139-9675-d4f6455c668e |  | note | Acceptance Criteria: Prior to commencing work
label | 1252db41-e30b-58c5-a8ee-f6091b539923 |  | note | - - - - - - - - -
label | e854adfa-647e-58e7-8277-26dcbd6aca4f |  | note | Reference Documents: Current Excavation Permit (GPP) signed and specific for the area where works will be executed.
label | 83fb636c-df1b-56a8-abb5-7da987a4381c |  | note | - - - - - - - - -
label | b4a81e3b-c887-559b-83c3-6edb6e7aef5a |  | note | Inspection / Test Method: Excavation Permit
label | f8d540bd-f8b9-500e-b10d-b92cf2ef0695 |  | note | - - - - - - - - -
label | 848414e4-6be5-5f2c-9eba-719f2a6825f2 |  | note | Record of Conformity: Document review & Site inspection
label | 45722479-fa10-59ee-a685-282d3dc3fdaa |  | note | Excavation Permit #
label | b9a6078a-ee60-5c6a-8d65-5cbe9ba92517 |  | note | - - - - - - - - -
label | 89a358cd-e3b6-566d-b6b4-c72ca754681a |  | note | Responsibility: HP*
checkpoint-status |  |  | checkpoint | 1.4 - Traffic Management (When required)
label | a42e5742-ef42-5988-ac0c-0d67891d4c97 |  | note | Frequency:
label | c0ed39e9-073f-537b-8a26-b879009fd105 |  | note | - - - - - - - - -
label | e4a34764-a9d9-50c9-a0a8-8c4c1bb8e002 |  | note | Acceptance Criteria: Prior to Commencing Work
label | 67162e0b-31da-5999-95c8-c6110700ddf0 |  | note | - - - - - - - - -
label | 97e9e497-080b-5c4a-9c7f-e14bafaa822f |  | note | Reference Documents: Approved Traffic Management Plans and Permits: TMP and MoA.
label | 1e811a65-e4d3-5c54-9bf1-de5bf2b91fc8 |  | note | - - - - - - - - -
label | f4c0f02c-8a88-552e-ba54-59571f10de05 |  | note | Inspection / Test Method: TMP, MoA
label | c5a9123a-f7dc-5d88-902f-7b667275673a |  | note | - - - - - - - - -
label | d7a668fd-a35e-5218-8382-0cb18a59ca62 |  | note | Record of Conformity: Document review & Site inspection
label | 129462c4-a82a-5559-ab11-58b0440ddd98 |  | note | Approved TMP & MOA
label | 039473cd-dfdb-546f-b43b-66ebe711593b |  | note | - - - - - - - - -
label | c52c6dab-ee70-5e7e-bf29-40ad56103ae3 |  | note | Responsibility: AP
checkpoint-status |  |  | checkpoint | 1.5 - Material Conformance
label | 2c305bf0-f4ab-5d78-864f-8171ec6ba174 |  | note | Frequency:
label | 81ee646d-4317-5a94-89ea-afd38798a999 |  | note | - - - - - - - - -
label | d8f63120-b167-5999-97f2-f1c7635d2ac9 |  | note | Acceptance Criteria: Prior to commencing
label | cf475b3b-422b-5f10-9b89-3b7b467539ce |  | note | - - - - - - - - -
label | 6af016b9-f873-5c29-9e7b-f3f1b32efa7e |  | note | Reference Documents: The Contractor shall submit for review by the Superintendent prior to the proposed use of fencing materials, gates and connections to existing fencing, a signed certificate including relevant test reports demonstrating the compliance of the materials and components required for the construction of each type of fencing, gates and connections to existing fencing, comply with the requirements of this specifications.
label | 85b2f397-3fcf-591f-9433-e58f7ffcbaa7 |  | note | - - - - - - - - -
label | 593ee99b-58b3-5b9e-965e-284c2f41672b |  | note | Inspection / Test Method: VicRoads Sec 707.03
label | e0263d32-85f6-5977-8117-2bc4694a956f |  | note | - - - - - - - - -
label | de3d582d-31f5-5955-ad14-96995b4eb820 |  | note | Record of Conformity: Document Review
label | 23368ac8-46c8-5290-9a82-fcd3e1362fd9 |  | note | Certificate of Conformance Relevant Standard Drawings
label | f74067de-b5a6-5d24-b6dd-63bdaa1f7a0a |  | note | - - - - - - - - -
label | 568d8d62-9ba5-5cd6-b5d0-c700b2da7fc2 |  | note | Responsibility: AP
checkpoint-group |  |  | section | 2 - Construction
checkpoint-status |  |  | checkpoint | 2.1 - Site preparation
label | 02423719-7ba2-58d4-9fd3-299cd249622b |  | note | Frequency:
label | 13b61703-c336-5507-9734-1effc5d19d36 |  | note | - - - - - - - - -
label | b6d1f9d5-5c71-5e53-9e9f-64b43d2bdfa8 |  | note | Acceptance Criteria: Each Lot
label | 58646f98-0492-5fe7-90f2-57cf8167143e |  | note | - - - - - - - - -
label | 6f40beae-8a83-5f88-b471-989b666e508d |  | note | Reference Documents: All logs, stumps, saplings and undergrowth within 1 m of the fence line and all trees which will interfere with the proper construction of the fence shall be removed and disposed of. Any high points which interfere with the placing of wire or wire netting shall be cut down to provide the clearance shown on the detailed drawings, and any low spots shall be filled with surplus earth from holes and trimming
label | 4fc26244-c8d6-5d45-a26a-90daa9441ce8 |  | note | - - - - - - - - -
label | d4c71fbe-c4af-56de-90ff-c2152d0ed2cd |  | note | Inspection / Test Method: VicRoads Sec 707.04
label | d3bbf3c7-bef9-5e6a-9981-9234acaefe59 |  | note | - - - - - - - - -
label | 6476e4d8-fcc1-550d-a2fe-22b5a04612b5 |  | note | Record of Conformity: Site Inspection
label | 3dfb01ff-a9e6-53e9-bdfd-ac366d6245d8 |  | note | Photos
label | 7c2d4f1f-be3c-57bf-a8a5-c4c1ff61aed2 |  | note | - - - - - - - - -
label | 21bee1be-c8d1-58fe-8b58-34b144333a8b |  | note | Responsibility: IP
checkpoint-status |  |  | checkpoint | 2.2 - Fencing Set Out
label | 9200e95c-4d0f-5bbf-9628-b33c403af564 |  | note | Frequency:
label | 7a5b5ca6-68e6-5459-ae8a-c09aa9fdf553 |  | note | - - - - - - - - -
label | bccce6c7-a235-5cf2-bb46-887d8750224c |  | note | Acceptance Criteria: Each Lot
label | b4af4590-926a-53ec-9eb5-e1e29c75dc77 |  | note | - - - - - - - - -
label | cbbc50db-34b4-5d5e-bcf3-3120e9a11549 |  | note | Reference Documents: Surveyor to set out fenceline as per drawings and set out posts as per drawings if required. Cadastral Boundary Surveyor when in related to property boundaries, Right of Ways, and Titles.
label | 8e176d98-f9d7-584c-8e0e-8ab314a01466 |  | note | - - - - - - - - -
label | b4d573b4-b2a5-5269-8b96-79b84188ff1b |  | note | Inspection / Test Method: Drawings
label | 43a4e3ed-398e-5c87-ac53-32f62ce47c04 |  | note | - - - - - - - - -
label | d55fe73c-b39e-5a2c-96e9-ea8b1ee9750f |  | note | Record of Conformity: Site Inspection
label | 6759745c-1344-5776-bc93-17e67b41052b |  | note | Drawings/ Survey Set Out
checkpoint-status |  |  | checkpoint | 2.3 - Install Fence
label | dab0f6ca-b728-5afe-9b91-fa92be00870b |  | note | Frequency:
label | 8259db89-3a67-5bce-9b60-111a310f7d27 |  | note | - - - - - - - - -
label | e3ebb72f-52d6-5a03-966d-7cc7964d89f9 |  | note | Acceptance Criteria: Each Lot
label | 0acbe477-ae2e-502e-b70d-35bbe7db0dfa |  | note | - - - - - - - - -
label | 14e458c7-7ad6-5b8a-a389-d74be8dc15f8 |  | note | Reference Documents: Install fence as per VicRoads Sec 707.04
label | b218dbcf-fb6a-5d59-a812-6845d31e5fb6 |  | note | - - - - - - - - -
label | 3e06c7dc-26eb-56af-86a2-5d4ec5d3835c |  | note | Inspection / Test Method: VicRoads Sec 707.04
label | 692d905c-5b30-5390-8266-9d2b500b71cf |  | note | - - - - - - - - -
label | 8be0bbce-5c62-5f10-a8e1-96c78d78cbeb |  | note | Record of Conformity: Site Inspection
label | c781705a-c2bb-5e20-af87-c13cc86da694 |  | note | Signed ITP
label | ba763a5c-e016-5970-ac84-2ba1974669e2 |  | note | - - - - - - - - -
label | 3b66e3ac-524e-53ee-9331-0987168bcf99 |  | note | Responsibility: IP
checkpoint-group |  |  | section | 3 - Conformance
checkpoint-status |  |  | checkpoint | 3.1 - Asbuilt Survey
label | edc50b88-7262-589d-8ea9-8f14edf25f57 |  | note | Frequency:
label | 75b11437-4910-5c60-93bc-afbbc00e3a13 |  | note | - - - - - - - - -
label | ca9d236d-50ea-5125-bcda-fd01ddc20be6 |  | note | Acceptance Criteria: After installation
label | ecd643f9-00d5-55d1-9883-55a241c39a8d |  | note | - - - - - - - - -
label | ff1329a6-713c-5508-a71b-ab1ac44150a9 |  | note | Reference Documents: Construction Tolerances: the vertical tolerance on the height of the fencing shall be Â± 20mm from the design line. ( b ) the longitudinal line tolerance for the fencing shall be Â± 20mm in plan view; and ( c ) the tolerance on the verticality of fencing shall be 1 in 50.
label | 04185027-2f60-55b8-bb32-d752bd16383e |  | note | - - - - - - - - -
label | 98604e73-e159-5a71-ba06-b17eacc57db5 |  | note | Inspection / Test Method: VicRoads Sec 707.08 Asbuilts Survey Report
label | 3b57d127-ef93-5d3e-9482-054940aa050e |  | note | - - - - - - - - -
label | 33c00b19-73b7-5b25-9a7f-b8f574cd1783 |  | note | Record of Conformity: Document Review/ Site Inspection
label | f4c19a67-988c-584b-97e0-d1224686aa99 |  | note | Asbuilt Survey
label | 395fe021-965b-512d-966a-f9ea10ec2ec3 |  | note | - - - - - - - - -
label | b8c01086-83ba-54cb-9a9e-b71627cf48bd |  | note | Responsibility: SCP
checkpoint-status |  |  | checkpoint | Final Inspection
label | cec1b81d-c94c-57d2-b3ea-a368785084aa |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 27edbaa1-bb58-5753-8d0b-0a66809aebbb |  | textbox | Print Name:
text | 5a2576fc-de2e-5f80-a4d7-be3aef7b5977 |  | textbox | Position:
date | edda6458-e4c4-58b8-9fb5-5b0ee06d4737 |  | date | Date:
date | 85c2f737-dd83-5331-80f4-80bcfd361cca |  | date | Work Completed On
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification.
select | 4074b9b0-f932-5e2e-aa9d-348bb60878f1 |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | ffee9704-168d-59d7-9988-67d6b412bbce |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | e3582bd4-8bf7-523c-9c08-e79e8b95ce50 |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | 58d93512-6a2a-57ba-8e6e-994863b0e094 |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | f73d026e-4b06-5bf5-aa09-5ec8ec2f0d14 |  | textbox | Other:
select | c3bde03a-90a4-53b9-b037-261e1a580ea2 |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | 51d9ef94-4c68-5f3d-827b-2ac6a7c23c60 |  | date | Lot Closed On
text | 88ab1046-7743-5fae-a138-f757ef383835 |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-009-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0009 - Unbound Pavements | e44afadc-bff3-4d47-8ccd-48323eccced5
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | 3203799c-e2e9-5c66-a9fc-0141c33222ef |  | date | Lot Created On
date | 9466a943-feb8-5e3c-a059-276baab75055 |  | date | Lot Opened On
date | ef3fed68-ac76-5bc5-9f20-fa727d261616 |  | date | Work Commenced On
select | 6e9080f5-c3ab-5e30-83cb-68d8807a033b |  | dropdown | Lot Type | CIL-Civil Lot, DRL- Drainage Lot, EAL- Earthworks Lot, ELL- Electrical Lot, UTL- Utility Lot, STL- Structural Lot
text | 36b9b679-3c20-596e-964c-c6a75190f575 |  | textbox | From and To Chainage
select | 72889075-b113-55b8-a55d-12dbd39d0ce6 |  | dropdown | Construction Element | PAVE - Pavement
select | c84bbe51-d415-5c41-8d93-fdbceb552f0c |  | dropdown | Activity | BAC1 - Base - Class 1, BAC2 - Base - Class 2, BASA - Base - Asphalt, INAS - Intermediate - Asphalt, IPSC - Insitu Pavmnt Stab-Cement, IPSF - Insitu Pav Stab-Foam Bitu, SCTCC - Subbase CTCC, SCTCR - Subbase - CTCR, SUC3 - Subbase - Class 3, SUC4 - Subbase - Class 4
select | 84145787-143e-5443-94d1-880e802f7a8c |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | 66beb392-8324-55ba-a122-ac1ea9849db0 |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | 41ba38ab-3d9f-578e-9742-e8445abd223f |  | textbox | Engineer Responsible
text | 0950effe-dd48-53a0-af9c-00c6858acc88 |  | textbox | comments
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Induction
label | 155fecea-b516-51a3-bff5-c857e0687a31 |  | note | Frequency: Prior to Commencing
label | 0cd76498-d71d-5adb-ad11-37880d18a3da |  | note | - - - - - - - - -
label | 3305cc29-bb8f-5fa5-bcd7-83cf6c5bd537 |  | note | Acceptance Criteria: All personnel on site have been inducted to the CRU site
label | b0e57b3b-1228-5560-a1c0-7efc5ab8f668 |  | note | - - - - - - - - -
label | 93b1b75a-fc43-55d7-b91f-4edf8217e8fa |  | note | Reference Documents: PMP Inductions Register
label | fe92ced2-a032-581e-a84a-cf74d83694a1 |  | note | - - - - - - - - -
label | 754b62c5-597e-56db-85b9-41e3eaa6b034 |  | note | Inspection / Test Method: Document review
label | 5d1456eb-5246-5ba3-81c1-b704901efb31 |  | note | - - - - - - - - -
label | 234a4a93-4321-591e-ab48-485345714764 |  | note | Record of conformity: Site induction signed.
label | 8a3eac3c-c7cd-5c8a-aa2e-3451c7801ee4 |  | note | - - - - - - - - -
label | ee89da63-37f3-5895-aa34-43218a9462bd |  | note | AP
label | 1239ba0c-54f2-56f9-8f53-be191f0e193d |  | note | - - - - - - - - -
label | f93d0ed2-402d-5c56-b5e2-9f94b9d87fbf |  | note | Responsibility: Site Engineer / Site Foreman
checkpoint-status |  |  | checkpoint | 1.2 - Check that current revision drawings are being used
label | 7275c377-46f5-5c59-8a6f-6ce6074a49f3 |  | note | Frequency: Prior to Commencing
label | bdf806b2-0cbb-5754-87ab-89d4b6383098 |  | note | - - - - - - - - -
label | 13f151f2-0c8e-557a-a036-e77de3310c6d |  | note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
label | e9f39d34-9020-5aaf-9f71-72a0338911e9 |  | note | - - - - - - - - -
label | ab9d4ebe-7764-574a-8110-2e96db93ad5f |  | note | Reference Documents: Project Drawings / Drawing Register
label | 27cb3298-2c0f-5f1a-8767-8d5832cbdf92 |  | note | - - - - - - - - -
label | 504f68e7-3f08-5f03-b7e9-3813f1b88161 |  | note | Inspection / Test Method: Document review
label | 13707d7d-1c26-5c9c-841a-be6eae5ebaf4 |  | note | - - - - - - - - -
label | e4c9adc3-deb0-503b-85e6-0dace6098e7c |  | note | Record of conformity: Latest Revision Drawings
label | 2afac19b-9f6a-512d-ac95-48d0df890357 |  | note | - - - - - - - - -
label | 169b6ac1-e76e-5812-8740-3c03481a8016 |  | note | AP
label | b79dcbe8-13db-5789-aaa9-863810a58b2c |  | note | - - - - - - - - -
label | 2da345af-cc08-54da-9d78-ec26ffdadc36 |  | note | Responsibility: Site Engineer / Site Foreman
checkpoint-status |  |  | checkpoint | 1.3 - Confirm understanding of current Environment Management Plan (EMP) related to the work area and that all prescribed environmental controls are in place
label | f9510fd9-d8a3-51cb-86f7-a94844ef3bc5 |  | note | Frequency: Prior to Commencing
label | 38222f77-248c-5c31-b008-49766ad68164 |  | note | - - - - - - - - -
label | 177541fe-4697-53c6-ac6b-4a989cb9511f |  | note | Acceptance Criteria: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | ad7c4292-4ff5-5005-bcfb-74b0a1150e11 |  | note | - - - - - - - - -
label | cf111375-3936-577f-89aa-2ab39db3e02a |  | note | Reference Documents: EMP, Site induction, Project Specification Cl. 1200.03
label | 8a6cad2e-f902-5cf9-9e45-f1c1dc00089c |  | note | - - - - - - - - -
label | a768a14c-62f1-5f70-92aa-46ccf9388411 |  | note | Inspection / Test Method: Document review & Site inspection
label | 61e2704e-2c8b-5f2d-a61b-43272e434c6b |  | note | - - - - - - - - -
label | 7360990f-0b31-5ec2-8bbc-8d5c6689fd36 |  | note | Record of conformity: Signed ITP
label | 9d6395c1-d146-50db-85ed-19b74994b75f |  | note | - - - - - - - - -
label | 0e8471a6-0ea6-535f-8793-af4d84aebee2 |  | note | IP
label | c1055175-995d-5c63-bf5c-e61058b1956b |  | note | - - - - - - - - -
label | a72b719d-4a1b-5243-ad95-e35a82bb7a62 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 1.4 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken
label | 3a6b08ca-dea7-5387-a19a-d0084eb9d5da |  | note | Frequency: Prior to commencing
label | 2b7ed412-119f-57c0-aa13-3373b08b0dff |  | note | - - - - - - - - -
label | f5ea5692-35b8-5b58-a72e-c3763413ee08 |  | note | Acceptance Criteria: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
label | c58bd600-d51f-5747-90f3-fb809d5d335c |  | note | - - - - - - - - -
label | de05973e-a1ae-58d6-8733-e0fd598329a6 |  | note | Reference Documents: Project General Specification Cl.1125.07 Health and Safety Coordination Plan
label | 5bab0d7d-3f04-5d7a-b581-512ec20d488c |  | note | - - - - - - - - -
label | c559ed95-fe1e-5c64-9cea-a5b22ca34c53 |  | note | Inspection / Test Method: Document Review
label | 0a499822-1673-5663-b360-5917ea507332 |  | note | - - - - - - - - -
label | a6b20431-0bd1-589f-a188-ebbc47eed4a6 |  | note | Record of conformity: SWMS(s) signed
label | 0a2a935b-1a34-5080-b1e8-9961c072f903 |  | note | - - - - - - - - -
label | 9176df7f-8086-5e58-8368-20b8ec6008ef |  | note | HP*
label | 0f7d056a-494d-5396-aeb8-40541d21bac0 |  | note | - - - - - - - - -
label | d4cfd172-fcbe-592c-831a-af1b892eaa8b |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 1.5 - Crushed Rock Mix design
label | ba9d7dec-41ed-54ff-a99c-72eacfe1f9fa |  | note | Frequency: Prior to Commencing Work
label | fe5bd6d9-c5e7-561b-8f4a-2493c388c3f5 |  | note | - - - - - - - - -
label | 4cd8e562-40a0-5ab8-97e8-cf18a42d3de8 |  | note | Acceptance Criteria: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175.
label | 21bb1c18-01db-586c-b20f-1313ac31a18e |  | note | - - - - - - - - -
label | c35675c1-5f0a-55ee-9375-3c75f870432f |  | note | Reference Documents: VicRoads Specification Cl.812.04
label | 6dff1c43-da97-5853-b856-357e16db30c0 |  | note | - - - - - - - - -
label | d016fcde-748b-56a0-86fc-d94177738e8d |  | note | Inspection / Test Method: Document Review
label | 0ffd2867-3591-5ce7-8e05-81335564ac14 |  | note | - - - - - - - - -
label | acebac35-e25e-57a1-83b3-7fc2469b9011 |  | note | Record of conformity: Mix Design VicRoads Approval
label | f7a924fa-64f6-536f-86c7-a7045c776cbb |  | note | - - - - - - - - -
label | aecd8dad-ce23-55be-a7a6-1079010dddf9 |  | note | HP
label | cdc89a5c-33ae-5206-b961-3c36498e8417 |  | note | - - - - - - - - -
label | 1da7f209-cc8d-5e9b-8263-20955b18437f |  | note | Responsibility: Superintendent
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-status |  |  | checkpoint | 1.6 - Excavation Permit issued
label | 461436a5-a44b-5f68-9d4b-81f4edd5d086 |  | note | Frequency: Prior to Commencing Work
label | 8d61249e-f2eb-5afe-b216-e7de23fa53d0 |  | note | - - - - - - - - -
label | 404309d4-03f2-5131-afa1-e26d15385b21 |  | note | Acceptance Criteria: Current Excavation Permit signed and specific for the area where works will be executed.
label | 212fae2b-f96a-598e-b4e0-09bd221e6feb |  | note | - - - - - - - - -
label | 7866ced4-df1a-5299-80ce-5bff610a2519 |  | note | Reference Documents: Excavation Permit
label | 7f06400a-280a-5689-ab01-78668d22b7a9 |  | note | - - - - - - - - -
label | c96503e7-1e2c-5275-9daa-e966e4fe9180 |  | note | Inspection / Test Method: Document review & Site inspection
label | ad0af753-955e-530c-b083-2dc7b6a1c4a6 |  | note | - - - - - - - - -
label | c02eddf0-71a8-5c3c-b81e-c30b65a528cd |  | note | Record of conformity: Excavation Permit #
label | d897fe5b-1ef5-5393-ac70-39f2a1d48fe9 |  | note | - - - - - - - - -
label | ee0624db-aeb3-5448-b8cf-3538d88ddd6f |  | note | HP*
label | 10c5c365-e24f-5b67-b60c-13ff02c3f7fd |  | note | - - - - - - - - -
label | 0f189fe0-7923-584a-be41-e4301b1da09f |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 1.7 - Traffic Management (When required)
label | 421df136-1fd8-53ec-b56f-abce9705086a |  | note | Frequency: Prior to Commencing Work
label | 59815c68-619f-5fa4-b307-b63ff6d1be7a |  | note | - - - - - - - - -
label | 30615eda-f483-5343-86fe-5b9374a9dcb4 |  | note | Acceptance Criteria: Approved TMP and MOA
label | 823ce0c4-7bf1-54c2-9189-feb34f0db5a8 |  | note | - - - - - - - - -
label | 23679220-32e1-5f10-8a31-0fd4be8592dd |  | note | Reference Documents: TMP
label | 96fc4f24-b5fd-5f33-98bf-c59a5b363e99 |  | note | - - - - - - - - -
label | 4eb478a4-13c9-5e98-8e49-2d7f5ffb0d95 |  | note | Inspection / Test Method: Document review & Site inspection
label | 61199d88-023d-5771-99c4-db511c426d1d |  | note | - - - - - - - - -
label | f5e2272e-79c3-5af3-834c-78d450df5558 |  | note | Record of conformity: Approved TMP & MOA
label | 990e3c78-7b4e-52a6-9400-132ef6dbf9d5 |  | note | - - - - - - - - -
label | 7811c2e1-880a-509b-9db8-b1cc0815f7ab |  | note | AP
label | 0b8d8413-3273-53c5-8f64-b2f07f168879 |  | note | - - - - - - - - -
label | f90965a0-f920-5dc2-9bb9-d7359c7e0dad |  | note | Responsibility: Site Engineer
checkpoint-group |  |  | section | 2 - Placing Fill
checkpoint-status |  |  | checkpoint | 2.1 - Transverse Joints
label | 33ac20bf-00f8-5bef-a992-f626fb4974f9 |  | note | Frequency: Check prior to placing material
label | fd805a08-b2f1-5c5e-ab69-f71955b24715 |  | note | - - - - - - - - -
label | ca0214fd-12ab-5130-8231-ae9fc4481b63 |  | note | Acceptance Criteria: * Material should be spread to minimize number of joints. * Transverse joints shall be offset from one layer to next by not less than 2 metres * Transverse joints shall be offset from one layer to the next by not less than 2 m.
label | 9c6f39ca-7fd7-5597-8fb1-093988a5ecf4 |  | note | - - - - - - - - -
label | b28ffcda-a74a-52f0-83c7-cb31d9689980 |  | note | Reference Documents: VicRoads Specification Cl.304.07 (a, b & c)
label | ec81b593-fffb-5cbb-ae3c-a8fb5198e30a |  | note | - - - - - - - - -
label | 2d0afae8-08a3-55d1-9c25-fe90e6be6fb7 |  | note | Inspection / Test Method: Site Inspection
label | 3a12e153-d23b-5cd1-a2bc-31c9ba9c589e |  | note | - - - - - - - - -
label | 33770eae-73ac-522e-9bae-2cb46fef7a8d |  | note | Record of conformity: Signed ITP
label | 5b9c46a5-9202-5485-9b32-aceec9ec822a |  | note | - - - - - - - - -
label | 16df53f7-1a11-5b70-af85-6be5ef5fa5ff |  | note | IP
label | 705ec533-5651-5697-8e32-bbe238364d21 |  | note | - - - - - - - - -
label | 3bd88636-8974-54ae-b557-cf53ef24af09 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 2.2 - Longitudinal Joints
label | 1e403ea1-a9aa-5f54-9d4c-faee0585e0c4 |  | note | Frequency: Check prior to placing material
label | e8ee5c60-97e8-57df-b66e-9b75a45b233b |  | note | - - - - - - - - -
label | 204f4747-18c4-585c-8a92-644ebe220245 |  | note | Acceptance Criteria: * Material should be spread to minimize number of joints. * longitudinal joints shall be offset from one layer to the next by not less than 150 mm. * longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
label | d765c6e9-32d5-5dcb-9f5c-c3cc7351ca4a |  | note | - - - - - - - - -
label | eabc172c-1821-5f50-a1f3-f265388cb2e1 |  | note | Reference Documents: VicRoads Specification Cl.304.07 (a, d & e)
label | cdee0f9f-b1df-522e-a58b-53f78c371f3f |  | note | - - - - - - - - -
label | 8dbcb750-aac8-5cc8-b301-11fd634803c2 |  | note | Inspection / Test Method: Site Inspection
label | b8652e51-4547-5215-959b-396cf3c187cd |  | note | - - - - - - - - -
label | 36ad6514-df90-5c88-9c6f-cb741dd06053 |  | note | Record of conformity: Signed ITP
label | ef770102-8070-5b68-a7be-1295a080d307 |  | note | - - - - - - - - -
label | 3aa10ef3-f332-51a2-a154-51a9e9a661b0 |  | note | IP
label | b9df3a3f-b6c0-5c44-bee6-d9f313fff857 |  | note | - - - - - - - - -
label | ef60c3ae-4fcf-582e-bf83-30c4f8924ecc |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 2.3 - Lot Size
label | 647bb5db-6f21-5118-bd80-41ff0eb4e9df |  | note | Frequency: Check prior to placing material
label | 21b8b527-1c31-5d9a-99b1-68ff74a8b7df |  | note | - - - - - - - - -
label | 2577976a-b5e0-5887-82b8-60b593340f16 |  | note | Acceptance Criteria: A single lot shall be considered a single layer of 4000m2 or one day's production in a single layer, whichever is lesser. For pavement construction, any lot that has a surface area less than 500 m2 may be treated as a small area and tested in accordance with Section 173.
label | fffdf6c0-1429-50ac-8a29-52dc6917723c |  | note | - - - - - - - - -
label | ec2da191-16c3-5087-96bd-ebe02654a096 |  | note | Reference Documents: VicRoads Specification Cl.304.08 (b)(ii & iv) Table 304.111
label | 76ddaddb-45f6-5586-8bd8-8e71a2833c20 |  | note | - - - - - - - - -
label | e38230a3-1a13-56be-9a03-028ab69d591c |  | note | Inspection / Test Method: Site Inspection
label | 98afb2d8-82f0-5586-a210-5d2ce33a1f7f |  | note | - - - - - - - - -
label | a18c1899-4aef-587f-85c7-f28de257ea91 |  | note | Record of conformity: Signed ITP
label | 9fffd593-8058-55e6-93ec-a0aafd139415 |  | note | - - - - - - - - -
label | 37bbb6fa-7655-578b-8322-deaa81f976a7 |  | note | IP
label | d3446d84-e10b-5010-a553-b54ddc51fcee |  | note | - - - - - - - - -
label | 588cb4b5-2b96-579d-ae15-5de01f510a4a |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 2.4 - Proof Roll
label | 2f7ac211-1969-5356-983c-53ceb410b081 |  | note | Frequency: After placing material
label | 909a1957-73ff-5651-bef7-276d22785b57 |  | note | - - - - - - - - -
label | 6725b2c7-9f6b-556c-ad4a-f57ed95f5009 |  | note | Acceptance Criteria: Pavement lots should be subject to proof roll as outlined in VicRoads Section 173, under supervision of Superintendent
label | bfd11b81-5db5-5029-bf0a-227e80acb895 |  | note | - - - - - - - - -
label | cd39026d-0a0e-5795-a90b-b1960611e83e |  | note | Reference Documents: VicRoads Specification Cl.304.08(b)(iv) Cl. 173
label | 908a0f1f-6e7b-5549-954a-154b3fc16945 |  | note | - - - - - - - - -
label | 127f2c4e-c0b3-514c-9f9c-81bee237c562 |  | note | Inspection / Test Method: Site Inspection
label | 893ca0ef-3f5b-56ce-96cf-bad2cc7d949f |  | note | - - - - - - - - -
label | 0c9a0d1f-cc18-54c9-878d-025a291cb006 |  | note | Record of conformity: Signed ITP
label | 1a84cb47-fa2c-5928-a170-a9b86a0c4141 |  | note | - - - - - - - - -
label | 722fbaa4-cb3e-5df2-9a61-41938b35a3aa |  | note | HP
label | f99f382f-bde5-58b4-ab77-039f65e2030b |  | note | - - - - - - - - -
label | 76735ce6-2f0b-5fb2-af7f-246210e743e0 |  | note | Responsibility: Site Engineer & Superintendent
holdpoint |  |  | signoff | HOLD POINT AUTHORITY
checkpoint-group |  |  | section | 3 - Testing and Inspection
checkpoint-status |  |  | checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
label | 6370529b-b36d-506d-9653-5f3f915f5944 |  | note | Frequency: Prior to Testing
label | b2958d79-5644-516c-bc6c-62fbfd7decf3 |  | note | - - - - - - - - -
label | d8b95bd6-60d0-51cb-93c2-b8edeab6f81e |  | note | Acceptance Criteria: Table 204.161 from VicRoads Standard nominates the level of testing required for acceptance of Surface Level Measurement. Scale A - Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.08. and 304.10. If no failures, Reduced Frequency applies as specified in Table 304.111.
label | cb6af634-f1c0-5439-9ac2-b0db254fa61d |  | note | - - - - - - - - -
label | c4393f96-557c-5320-8284-913b043875bc |  | note | Reference Documents: VicRoads Specification Table 204.161 VicRoads Specification Cl.304.08 (a) Cl.304.11 (b) Cl.304.11 (c)(i) Table 304.111
label | 7c08629d-afa8-5035-a44c-9897cfa701f6 |  | note | - - - - - - - - -
label | 54757904-703c-5603-a889-c94d285bda76 |  | note | Inspection / Test Method: Document Review/ Site Inspection
label | e3a3d8a7-870e-5ed0-b27f-c250821923a0 |  | note | - - - - - - - - -
label | 01d962e2-6d02-548b-8195-a932658fbd6f |  | note | Record of conformity: Signed ITP
label | 27f4a0ec-f0f5-5b17-81db-124909d51ba5 |  | note | - - - - - - - - -
label | 49961fb8-37ad-5307-9271-516c5c4a97bf |  | note | IP
label | 120a5220-7fab-5a19-b04d-4b464ed3125b |  | note | - - - - - - - - -
label | 4e92d719-2ca1-524b-8255-18554655afc8 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3.2 - Modified Compactive Effort
label | a6c0fe8a-ba91-5ae5-adc3-6a1207757aad |  | note | Frequency: As per 3.1
label | bdcd6862-f0ec-511f-8c75-2e38b3975b67 |  | note | - - - - - - - - -
label | 32a8a68a-e469-5622-a83e-17ab9f3727d1 |  | note | Acceptance Criteria: Characteristic Value of Density Ratio for Subbase:- > 98.0% for Scale A and >97.0% for Scale B. For work to be tested for compliance with Scale A or Scale B requirements, the number of tests per lot shall be six.
label | 0d743980-f1f8-504d-bee6-2b64b8d41d43 |  | note | - - - - - - - - -
label | 1967ea68-7b83-5ddc-9664-9ed99aedec31 |  | note | Reference Documents: VicRoads Specification Cl. 304.08 (b) (iii) Table 304.081
label | bae0172e-200f-57c5-bf56-f136431182a2 |  | note | - - - - - - - - -
label | c14867ef-43df-52be-8967-0f4d6fd6f91d |  | note | Inspection / Test Method: Site Inspection
label | 3c5ef7cf-5e4b-59be-a72c-58928f7dff67 |  | note | - - - - - - - - -
label | 278145e6-b6a0-5b3f-abc2-f559006b6c37 |  | note | Record of conformity: Test Records
label | 0b7c5031-add6-544d-a54e-50167cf7cafb |  | note | - - - - - - - - -
label | f162b18f-d539-5ad5-a9d7-377845be74ae |  | note | TP
label | 5f0d8cce-77d6-53a2-a8bc-9577edb49c2d |  | note | - - - - - - - - -
label | f38c6829-34fa-5898-9d12-11ae8ed0c6b8 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3.3 - Permeability Testing
label | 6c82eaf9-3cfd-5b7c-9c7b-430cfa56bb76 |  | note | Frequency: As per 3.1
label | 3820f209-76df-5998-b2eb-5fb3f8dab27d |  | note | - - - - - - - - -
label | 9c6540ec-4b61-5121-94ec-4e09df64653d |  | note | Acceptance Criteria: Class 4 Crushed rock max 5x10^-9 m/sec. Class 3 Crushed rock max 5x10^-7 m/sec Where the Class 4 material is used as a levelling layer in a deep strength asphalt pavement, the Superintendent grants dispensation from 5x10-9 m/s Max permeability requirement in clause 3040.05(a) and table 3040.051
label | d71be7ce-212f-55f6-9e6a-55729d7833ae |  | note | - - - - - - - - -
label | 3772cc15-aa7c-5e9b-8ebd-73c1787417a6 |  | note | Reference Documents: Project Specification Cl.3040.05(a) Table 3040.051
label | 61106585-161d-5d3d-99db-71d26f37141b |  | note | - - - - - - - - -
label | 3059fcf5-16f6-5e43-bb1b-a65909f5f89e |  | note | Inspection / Test Method: Site Inspection
label | ec6e66bf-205c-57b8-a549-ab24b1d9ce5d |  | note | - - - - - - - - -
label | f05c8a15-4b19-529f-a277-ac898f930c79 |  | note | Record of conformity: Test Records from Supplier
label | c498a16f-96e5-58b1-82c9-2a8c44e9c92f |  | note | - - - - - - - - -
label | 714ab1c5-fb56-5a1a-83a0-3625b0ea2379 |  | note | TP
label | 3118d2fb-fc2b-5439-8748-ac05618a37dc |  | note | - - - - - - - - -
label | c353710f-ea44-5cf7-bddd-d9f157187b75 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3.4 - Post-compaction Plasticity Index
label | c859a818-b139-572e-932f-b084c02fe965 |  | note | Frequency: After compaction
label | 9a291c0a-cc5f-51b9-bfb3-23e2aacac614 |  | note | - - - - - - - - -
label | 466e3895-576d-5611-92ca-ee6126372736 |  | note | Acceptance Criteria: Post-compaction Plasticity Index must comply with the requirement of table 3040.053. Class 3: 0 < PI < 10.
label | a1b5e19c-7e08-583d-b3b6-1e8f31e1b86a |  | note | - - - - - - - - -
label | b9872f3e-fa31-504e-9e6a-b9b970ab584b |  | note | Reference Documents: Project Specification Cl.3040.05(a) Table 3040.053
label | 675c3278-28e8-5b38-b3ed-e93cc9acf0fa |  | note | - - - - - - - - -
label | 4e00828a-8f3c-5a38-ba54-ce6c9e550a56 |  | note | Inspection / Test Method: Site Inspection
label | af38b70e-835b-5fca-a4b4-bd3a43dd049b |  | note | - - - - - - - - -
label | 272fe470-a46f-5873-910d-660b4c9b6184 |  | note | Record of conformity: Test Records from Supplier
label | 85f1cc34-3272-5381-9687-ebd5c0b79b8c |  | note | - - - - - - - - -
label | db6b2f16-eb1c-5831-a209-943ce1169947 |  | note | TP
label | 5ff0b0d8-10c4-5ef8-8f58-5ea8f39775ae |  | note | - - - - - - - - -
label | bde3282a-51f1-517f-bd66-2d727effca0c |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3.5 - Post- compaction Grading
label | 46a968b1-9e63-5926-bb21-38859894733d |  | note | Frequency: After compaction
label | cf943c01-47a0-507f-96eb-dff60e2d5e01 |  | note | - - - - - - - - -
label | cd2b3281-b071-5500-bba5-3155d2f3e3ad |  | note | Acceptance Criteria: The post compaction grading shall comply with the requirements of table 304.101
label | 082d3f41-f08e-52d0-b67e-dd5fd063cd6e |  | note | - - - - - - - - -
label | b9eaa437-3546-5c34-8582-73b7efb10b9f |  | note | Reference Documents: VicRoads Specification Cl. 304.10 Table 304.101
label | 3f70b5c7-1793-5f42-9ed2-9201ff9e455e |  | note | - - - - - - - - -
label | ddb3f2e1-f0c9-55a8-8898-ae0e8b7b6c80 |  | note | Inspection / Test Method: Site Inspection
label | ff93ceaa-a7b1-5175-90f4-619438fea743 |  | note | - - - - - - - - -
label | eceac276-fb32-56bd-b735-b9ec5bb04675 |  | note | Record of conformity: Test Records from Supplier
label | 1eaf23d2-340e-5d72-8dc8-c814708b1ab2 |  | note | - - - - - - - - -
label | 0c52a960-af40-5601-9b35-9619592c2f72 |  | note | TP
label | 96103029-f5ab-5574-8b95-80f39ece84fa |  | note | - - - - - - - - -
label | 57099d31-1008-5836-9ee5-40f3612b2d49 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3.6 - Test Requisition
text | 94a12814-65f6-5f85-bf27-fc2967cca595 |  | textbox | Test Requested on
text | b5643e16-4224-5d77-ae46-b4240dd80b6b |  | textbox | Location
select | de5b94ee-e995-5c20-bcc9-cda6970fd3d5 |  | dropdown | Material Type | Type A,Type B,See comments
select | ea7c54cf-16d8-51cb-a82b-d9a7b74c7ec9 |  | dropdown | Material Source | Holcim,Boral,See comments
boolean | b5781ddb-a10e-56ce-b512-465c967ca6ce |  | tickbox | Compaction Test (Standard)
boolean | 36be0681-74be-5e8b-9e7b-b94d63f08560 |  | tickbox | Compaction Test (Modified)
boolean | 9ea1746c-5227-5e3b-897c-a4862dadac41 |  | tickbox | Maximum Particle Test
boolean | 19ed1d2e-427c-54d4-97af-f82f4e2f3c4e |  | tickbox | CBR/Swell Test
boolean | 4cd2cc1a-591e-509b-987b-29bad9c5de79 |  | tickbox | PI Test
boolean | ef86e3c2-989b-5554-87c5-6ce87f752aa3 |  | tickbox | Permeability Test
boolean | 2eb994e1-5b80-5152-ad72-f6cbc992d677 |  | tickbox | Grading
boolean | 83470543-fe9a-523c-aa7d-f59ec116f1ef |  | tickbox | Moisture
boolean | f12fdd96-1051-5817-80b2-cc5922b2473a |  | tickbox | See comments
text | 1d313a6d-0618-5a6a-b27b-21820218a078 |  | textbox | Test Level/ Layer
holdpoint |  |  | signoff | Test Requisition
checkpoint-status |  |  | checkpoint | 3.7 - Survey Level
label | ad70f33d-7c3b-52bc-bf27-c40d0d268f5d |  | note | Frequency: At completion
label | 408fe277-2b75-57f6-b9df-54564fa50fe2 |  | note | - - - - - - - - -
label | c81570b0-892c-565e-94f0-7aacfae30b41 |  | note | Acceptance Criteria: Scale A: Minimum number of measurements per lot: 80 for Upper — Upper Subbase: Mean + 4mm to -8mm wit a maximum Standard Deviation of 8mm — Lower Subbase: Mean +6mm to -10mm with a maximum Standard Deviation of 10mm — Base: Mean +- 5 with a maximum Standard Deviation of 8mm
label | bf2cfa25-79ab-51c8-9a9f-a8a4eee468dc |  | note | - - - - - - - - -
label | 7b8d9ae9-e8b3-51c0-80a8-4fe5baaebb59 |  | note | Reference Documents: VicRoads Specification Table 304.061 Table 304.062
label | f756fe28-edff-5ef2-b8fc-f90ea7f58231 |  | note | - - - - - - - - -
label | e1f34062-4882-570f-b520-7ba8f65732ca |  | note | Inspection / Test Method: Site Inspection
label | 79f910da-cb04-5de7-b6cf-2d13b5d8a3c8 |  | note | - - - - - - - - -
label | a473e8b0-50e0-5b3c-8b06-bad0b4124d59 |  | note | Record of conformity: Test Records
label | 91070437-2af0-576e-b366-4654ff977066 |  | note | - - - - - - - - -
label | c5ca17bf-b554-5cbd-b917-776b86562d10 |  | note | TP
label | db6e5a01-0e5f-5ba7-8f72-cb93cd3cc243 |  | note | - - - - - - - - -
label | 73094a2f-7fe3-5f73-9f26-ca7094f1a537 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
label | 5f349af8-c657-5484-9509-62d42b2260ed |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | c1aa4edd-d0c4-52bb-ae04-bed247f439e6 |  | textbox | Name:
text | 25ddc6ba-86d6-57c3-b4eb-b81d4bcb3e3f |  | textbox | Position:
date | fe92a357-f912-503b-964e-6cd4f968b966 |  | date | Date:
date | c3d1e3b6-1264-5114-844e-842e6b5a7f1f |  | date | Work Completed On
holdpoint |  |  | signoff | Add Signature
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification.
select | e72f41af-00b9-559f-a0ed-83ce1d17fc2d |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | 46afce78-2f0e-5ea8-8ea3-9a13ac61ff47 |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | 61d7c231-746d-5244-befa-fd22f6767018 |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | 73c7986b-3496-525f-8bf0-e589f4442c84 |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | 1d9f32f5-14ac-57d9-a510-12bd5368edc2 |  | textbox | Other:
select | b052ed30-258e-5004-8791-d55a462ee54a |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | df828d99-7ef0-5e46-b553-824eebb02525 |  | date | Lot Closed On
text | dffee8cc-b348-5ab5-97b0-85dd62bd649e |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-042-UT-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0042 - Comms Protection Works | e5db8193-8a06-4551-9a35-1904855a0c9e
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | 851e92ae-b723-560b-9b83-058a56439a26 |  | date | Lot Created On
date | 60723e24-f69d-5343-bea5-2563871224b1 |  | date | Lot Opened On
date | 7d3a8bc2-0efa-5056-8fcf-9f943479d0e5 |  | date | Work Commenced On
select | 13703b05-fb66-5c9a-9025-1bb3c74f508a |  | dropdown | Lot Type | CIL-Civil Lot, DRL- Drainage Lot, EAL- Earthworks Lot, ELL- Electrical Lot, UTL- Utility Lot, STL- Structural Lot
text | 04169a95-200c-5884-8f0f-57db10ec7740 |  | textbox | From and To Chainage
select | f58fb162-d182-5082-b84a-447de6983015 |  | dropdown | Construction Element | UTIL - Utility
select | e9fa275a-0956-507b-82ae-06a0569e6f16 |  | dropdown | Activity | TELE - Telecommunication
select | d96ee1e9-c09b-5210-8f1e-47161ff02972 |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | a35e593e-584f-5bc9-b576-711217f51e9a |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | 6da9954d-e843-52aa-8545-08a209ae2952 |  | textbox | Engineer Responsible
text | 2c25fbfd-2eee-5ca7-920b-d12596f42e25 |  | textbox | comments
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Induction
label | 5977cf84-dce4-56e8-87f0-bfab13417a07 |  | note | Frequency: Prior to Commencing
label | 670760aa-13e7-531c-9dbb-2461d27fc374 |  | note | - - - - - - - - -
label | 3137f51e-81c4-5e15-87e7-9e029ed65e6d |  | note | Acceptance Criteria: All personnel on site have been inducted to the CRU site
label | c79dd234-932e-5b75-aaf2-1517ee83dbcb |  | note | - - - - - - - - -
label | da078658-4991-596e-9012-d72cfbaa7e6f |  | note | Reference Documents: PMP Inductions Register
label | 1d72a602-7afc-5ad2-ac89-dcf38c8d7fca |  | note | - - - - - - - - -
label | 3c6781ff-f523-5d39-adf1-ed4a8bee80ef |  | note | Inspection / Test Method: Document review
label | 76cf415d-8442-589e-b623-028cb57cfe62 |  | note | - - - - - - - - -
label | 0b723ec2-1263-5ada-b265-e51be24c0efb |  | note | Record of conformity: Site induction signed.
label | 6e39e2a3-e694-5ebe-8011-9419ed390b37 |  | note | - - - - - - - - -
label | c69ec5a4-5907-579a-8a01-a074247f3ad5 |  | note | AP
label | b3434831-37f1-5048-a19b-067b64f3e54a |  | note | - - - - - - - - -
label | 42966574-3a63-5c30-afc1-02bde4591822 |  | note | Responsibility: Site Engineer / Site Foreman
checkpoint-status |  |  | checkpoint | 1.2 - Safety measures are in place, SWMS undertaken
label | bc46a152-9c65-5ec3-af03-09d5a4313e4a |  | note | Frequency: Prior to commencing
label | c7b1886c-3595-5188-92bf-ba3976b5e202 |  | note | - - - - - - - - -
label | 05d9dbe8-3861-53d9-8c08-cf69fe2e110e |  | note | Acceptance Criteria: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
label | a0970032-2ecf-54b8-8730-a70fc1f0d9bd |  | note | - - - - - - - - -
label | 7d7bd8c3-ebd7-528e-ba7f-c8374b4bce7d |  | note | Reference Documents: Health and Safety Coordination Plan
label | 51283858-92b5-5e03-93de-5e7f5af58f08 |  | note | - - - - - - - - -
label | 1a4a4699-804b-5bf4-917b-f6731d0fa54b |  | note | Inspection / Test Method: Document Review
label | 35799286-d031-50c1-80e4-d5a4a6feab28 |  | note | - - - - - - - - -
label | 58f1d730-38f4-5dc0-babc-a785dd042637 |  | note | Record of conformity: SWMS(s) signed
label | 6defb39a-ca66-59ec-95d2-6ab610444b18 |  | note | - - - - - - - - -
label | 1d8a6b16-e859-5ac2-92e4-18c8618bfa88 |  | note | HP*
label | ee6f01be-718c-5ad1-87f7-3cb7d228679d |  | note | - - - - - - - - -
label | 431e6f42-7390-5f66-b054-7326fc4c9802 |  | note | Responsibility: Site Engineer, Site Foreman & Superintendent
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Check that current revision drawings are being used
label | e374e500-a088-5793-a849-2949549d5390 |  | note | Frequency: Prior to Commencing
label | 00fffbde-729d-54d2-a247-5af4344fcf23 |  | note | - - - - - - - - -
label | c851d363-7392-5262-af1b-6b0e28723bb6 |  | note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
label | e90045e6-546d-58dd-b6b6-3ba06d780648 |  | note | - - - - - - - - -
label | eb63eb73-968e-50af-91a6-f8c3e81165a5 |  | note | Reference Documents: Project Drawings / Drawing Register
label | 5acb574b-b713-54a8-b1ff-b81c5f0adf12 |  | note | - - - - - - - - -
label | a11d4cdf-5cd5-519c-b461-9c2bcf4ddc40 |  | note | Inspection / Test Method: Document review
label | 1b1dcd92-11ba-58c2-88ab-a0364955f6d0 |  | note | - - - - - - - - -
label | 1a883298-f4d7-56d7-a357-8b9ee906d876 |  | note | Record of conformity: Latest Revision Drawings
label | dfb031ab-49c5-5b70-be55-6925d60b2245 |  | note | - - - - - - - - -
label | a63a303f-4c10-53aa-a901-f516503ca42a |  | note | AP
label | 9d2c5855-adcf-588a-84d2-daad42ee41b6 |  | note | - - - - - - - - -
label | b3e7885e-249d-594d-bef9-4fdcf7143ad3 |  | note | Responsibility: Site Engineer / Site Foreman
checkpoint-status |  |  | checkpoint | 1.4 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
label | 0ebf17a5-e0ec-5fae-b3c1-f9b3e1321c9e |  | note | Frequency: Prior to Commencing
label | 6c8ef3b4-bec3-50a2-a6f8-3d179210d9f2 |  | note | - - - - - - - - -
label | dc06ae9a-2797-5e5e-9562-4ecc12ad702e |  | note | Acceptance Criteria: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | 765b7b85-c7a0-5fa6-95b1-ba61af0a7ff9 |  | note | - - - - - - - - -
label | f95e9182-ec0d-5fc2-86c0-95d27dfb8848 |  | note | Reference Documents: EMP, Site induction
label | 75b43f9f-cc1d-5686-a2f6-48e0a21a8ebf |  | note | - - - - - - - - -
label | c29a2c57-e26a-5289-b312-acc65d6d5155 |  | note | Inspection / Test Method: Document review & Site inspection
label | ad245197-1ba9-590e-abcd-ab86bfcf7038 |  | note | - - - - - - - - -
label | 9b951d62-fa7e-5913-a203-8d9239ccf28e |  | note | Record of conformity: Signed ITP
label | 22d64889-9fd1-588c-99e2-fc82c07e9f63 |  | note | - - - - - - - - -
label | 6c0047a7-c3b2-5967-ac65-477eedacbb12 |  | note | IP
label | e2c21fac-614e-580c-8a20-6c7005b55007 |  | note | - - - - - - - - -
label | b153fee5-8379-5861-b593-ee00a4fe2548 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 1.5 - Confirm suggested Asset treatment has been approved by Utility provider
label | 706a884c-810e-51fa-aac8-5770bfff11a1 |  | note | Frequency: Prior to Commencing
label | 84ffb983-08bf-5076-99ce-f0398f41eabe |  | note | - - - - - - - - -
label | 1e089061-c50a-5c21-ab43-757d76eaab18 |  | note | Acceptance Criteria: Ensure that adequate notice is given to the Utility Service provider and Superintendent prior to utility asset protection as per PS3120.06 part C Date of Notification: Date of Utility Provider approval:
label | 7032bf04-7d77-528d-a083-9229f7ae5920 |  | note | - - - - - - - - -
label | c102965e-e1cc-5e3e-9540-5fe84ab89295 |  | note | Reference Documents: MRPV- ITC Delivery Contract
label | 1f18ddcd-e911-5321-a8ca-e357cef68380 |  | note | - - - - - - - - -
label | 693e5770-d527-57e8-b9fb-33be15e8784e |  | note | Inspection / Test Method: Document review
label | d3a7dd75-38a4-551c-ad88-b6a1fafeece5 |  | note | - - - - - - - - -
label | 6c58eca1-6f95-52bd-ac49-6e95b2ac7465 |  | note | Record of conformity: Signed ITP
label | cd3de8d0-7003-5ecc-9ff0-963c55adccbe |  | note | - - - - - - - - -
label | c68c2580-9fcf-5afa-8b4d-afdd9659ebab |  | note | AP
label | 3d8f2e08-0454-575c-9af1-5206defc787e |  | note | - - - - - - - - -
label | 51ce1732-6aad-5481-8562-b1c603a3cb4c |  | note | Responsibility: Site Engineer
checkpoint-group |  |  | section | 2 - Procurement
checkpoint-status |  |  | checkpoint | 2.1 - Approved materials ordered.
label | 1fb9b6c9-a798-550d-a0a5-a6a53296bab7 |  | note | Frequency: Prior to excavate
label | b6ddde2e-cce8-571d-8629-92be6493c4ed |  | note | - - - - - - - - -
label | ca456894-85c6-5c6a-812c-c60fb36ac88e |  | note | Acceptance Criteria: Complying with AECOM Utility Protection Detail Drawings
label | 2ab20825-16cd-524d-b920-be66c3aa4b70 |  | note | - - - - - - - - -
label | e0943827-fb19-54c7-bf95-2d78025c1cc7 |  | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2127 & 1145-C201-ACM-CVP-DRG-2128
label | 5ef088bb-c8a7-58ae-bd59-542001e5e871 |  | note | - - - - - - - - -
label | a45d152d-b23d-5686-8704-bfc8c6281d6f |  | note | Inspection / Test Method: Site Inspection
label | b53548ad-06d1-52aa-ac8c-e3e7ed015dec |  | note | - - - - - - - - -
label | d48ec6fc-fdfa-505b-b622-58e779379c3a |  | note | Record of conformity: Supplier's Declaration of Conformance.
label | ce9992e1-928d-58fc-a837-0501387094d1 |  | note | - - - - - - - - -
label | 76eeafd7-5a3c-51a7-b421-0cd5119c17b9 |  | note | SCP
label | 85a995d0-4a30-5259-9a22-74574a85ff1e |  | note | - - - - - - - - -
label | ba7c4b5e-6cc1-5e14-bb1f-ca673f949558 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 2.2 - Receival and Inspection of products.
label | 48a1a722-d2d6-5d49-9925-862ee761e642 |  | note | Frequency: Upon receival
label | f2eb6cec-a96d-50e2-8693-cf45129f6968 |  | note | - - - - - - - - -
label | c542ca21-749a-5db6-99fd-ecfa711059ef |  | note | Acceptance Criteria: Approved Product and supplier. Right dimensions / specifications. Defect Free.
label | e5174b7b-c2c0-5017-a42d-7e082af7a6c5 |  | note | - - - - - - - - -
label | 151797ca-1211-5fd3-82d3-bbd0353c371a |  | note | Reference Documents: Receival & Inspection Checklist
label | 5e9bd0eb-0c7c-5a41-ba70-b67a3ce3e8a8 |  | note | - - - - - - - - -
label | 315c4f6c-f065-5375-93ff-97bbf876bb2a |  | note | Inspection / Test Method: Site Inspection
label | 25768a1e-f09c-549c-b1eb-53d4e5caf24c |  | note | - - - - - - - - -
label | 3ab8406b-e74a-54cb-a5ab-808640053786 |  | note | Record of conformity: Completed Receival & Inspection Checklist
label | ec67d1c1-a370-5a70-9e52-53a8d8f83b62 |  | note | - - - - - - - - -
label | f5d56d67-7597-56ce-85ca-41e5467468ce |  | note | WP
label | 80c8850e-75be-5386-b51d-eed368d3ea3f |  | note | - - - - - - - - -
label | 2a500b45-dcd3-5f2e-99fd-2cda5152f093 |  | note | Responsibility: Site Engineer
checkpoint-group |  |  | section | 3 - Construction Works - Detail 1 - Stabilised Sand Encasement
checkpoint-status |  |  | checkpoint | 3A.1 - Survey set-out
label | 7c9e934a-9f05-5c24-af5a-bcf34c6b45d7 |  | note | Frequency: Prior to Commencing
label | 56de8085-d095-5be8-9265-22476aff5792 |  | note | - - - - - - - - -
label | 016545ee-1808-5598-b309-bf3383ae1638 |  | note | Acceptance Criteria: Latest available revision used
label | eba82a16-e2b2-52cd-b7bc-46223bc5e3a6 |  | note | - - - - - - - - -
label | 666653e0-da28-5bcd-bedd-6c7ad0c3654f |  | note | Reference Documents: Drawings
label | 0f844480-2673-5a6d-b6cb-1e1b80d851a2 |  | note | - - - - - - - - -
label | aad9c085-9598-5b36-a436-b8df448ebc34 |  | note | Inspection / Test Method: Site Inspection
label | 6d7b9c33-1490-55c1-ae3c-b9660d65d1be |  | note | - - - - - - - - -
label | 1ae611ff-b284-56a6-b310-a1bfdd7ad189 |  | note | Record of conformity: Survey records & pegs on the ground
label | fdd2b56e-132b-5ef5-b36a-e366017d0fbc |  | note | - - - - - - - - -
label | 53ef4247-e1ae-5232-bfc2-107cea9c3305 |  | note | SCP
label | a839bd97-cfd8-58fc-8f39-f58cb46b57e4 |  | note | - - - - - - - - -
label | 9815253c-0ff2-5cb7-84ca-819fdab3cdcc |  | note | Responsibility: Site Engineer & Surveyor
checkpoint-status |  |  | checkpoint | 3A.2 - Excavate and expose Pipeline
label | c8535b14-778f-5e3f-9986-dbc5602d3366 |  | note | Frequency: During construction.
label | 9efccc9d-9eab-5e0a-ad1d-16084e692e80 |  | note | - - - - - - - - -
label | b057d594-a65b-5662-989c-d35cd23ea5ee |  | note | Acceptance Criteria: Ensure that the minimum cover requirements, horizontal and vertical alignments are within tolerances.
label | 2a1bf6c6-392d-59fe-b26e-f85add183ada |  | note | - - - - - - - - -
label | 3d0cbab4-1dac-5ac7-8e6b-4ddf2843fdc6 |  | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2127 & 1145-C201-ACM-CVP-DRG-2128
label | 6d5150e3-4ed3-5c53-9e89-3aeccc44ef98 |  | note | - - - - - - - - -
label | d6b721a8-171f-5a4d-aaf6-40ecf32c2410 |  | note | Inspection / Test Method: Document review & Site inspection
label | 7872029c-06b0-5175-abe8-9926e9e7d7c4 |  | note | - - - - - - - - -
label | a6ab2a08-25cf-5e15-b0b5-268879df82f8 |  | note | Record of conformity: Signed ITP
label | a42365c3-58fe-505c-8718-c30c34ae460f |  | note | - - - - - - - - -
label | d1f8b06a-5627-54e9-a009-2075576b929b |  | note | AP
label | b78b9c59-2b9f-55fe-9635-dbbb8b850326 |  | note | - - - - - - - - -
label | ba751286-d56a-5fcf-9523-61a42cb435da |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3A.3 - Survey pick up
label | 40de84c8-ca8c-5ba6-8b80-aec3c770ac79 |  | note | Frequency: During construction.
label | af6bfa2b-9afe-5211-8e2c-c50a6ea2ee7c |  | note | - - - - - - - - -
label | 96716668-44af-56c1-bbc2-161280448b52 |  | note | Acceptance Criteria: Once asset has been completely exposed surveyor is to complete a survey pick up at multiple points across exposed asset
label | 2e9a8c06-8efc-5796-9179-f0bcd8783cb7 |  | note | - - - - - - - - -
label | beb4e512-658a-54b3-afbb-64d11c3cc284 |  | note | Reference Documents: As Built documentation
label | bc80da29-6c61-545f-bf77-3f091af6ca42 |  | note | - - - - - - - - -
label | 9d62b863-5ca5-57d2-a716-cba7b97390e5 |  | note | Inspection / Test Method: Site Inspection
label | c87a3330-369e-5961-a4e3-859e6babada7 |  | note | - - - - - - - - -
label | fdfd7069-ed29-515a-b8ab-3352dacef40a |  | note | Record of conformity: Survey records
label | 6a2265f2-8886-57d6-87be-54dfc5b72c20 |  | note | - - - - - - - - -
label | 46aa8961-7bff-5b4d-803a-fa76f173357e |  | note | HP*
label | 946ef9b3-ed61-555a-b5e2-3a764547057f |  | note | - - - - - - - - -
label | 64ef5084-9d18-5b1f-9539-9302353428c9 |  | note | Responsibility: Site Engineer & Surveyor
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3A.4 - Place pipe protection material
label | 074fe982-20d8-5dd5-b108-f0954a6574de |  | note | Frequency: During construction.
label | 5fdd29a6-f9c8-56bc-a7ea-d792d450eaab |  | note | - - - - - - - - -
label | baf0e076-fbb8-5986-8680-7ec1173e7f62 |  | note | Acceptance Criteria: Detail 1 - Place 5% stabilised sand uniformly along length of pipe, work into place under pipe haunches. Min cover requirements - 400mm width of trench, 100mm below pipe and 150mm above pipe. Marker tape to be placed above protection.
label | d93158a2-4f1b-5cfb-bc2f-daeb2b4019e3 |  | note | - - - - - - - - -
label | 27b31d53-b96f-5db6-92de-3c53932801e3 |  | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2127 & 1145-C201-ACM-CVP-DRG-2128
label | f2005665-0ee6-5356-b10e-c93a4cc5ac72 |  | note | - - - - - - - - -
label | 7c89e5f7-d455-5077-af91-56b63cd8c98f |  | note | Inspection / Test Method: Visual
label | 1f9562cf-04c5-564f-a881-c39fac5e6739 |  | note | - - - - - - - - -
label | 62fe6b83-430e-52cb-abf5-7059ed5ec9dc |  | note | Record of conformity: Signed ITP
label | 879fd5b9-bfdc-53d2-8019-266b52f2beae |  | note | - - - - - - - - -
label | 661e228e-210c-5f2d-a56d-f06274eef279 |  | note | WP
label | 0afc664f-468e-5b35-97fe-fce83ffa7c3f |  | note | - - - - - - - - -
label | bbc8aa04-f9fb-5ca8-af47-0ae511406189 |  | note | Responsibility: Site Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3A.5 - Survey Pick up - Encasement of Asset
label | 9a473809-a83b-5533-b1f2-64b76d8dbe80 |  | note | Frequency: During construction.
label | 6447f683-8094-53f4-b20e-7d7465e644c2 |  | note | - - - - - - - - -
label | 4dd8fc17-1484-569c-af3a-36d6fa4b1c9d |  | note | Acceptance Criteria: Once encasement of stabilised sand has been completed the surveyor is to complete a survey pick up across multiple points on top of asset protection
label | 39f091e8-b42f-59e8-9c21-e7919dc3787f |  | note | - - - - - - - - -
label | 2187bd65-a15c-5480-9e5e-dba8d956b552 |  | note | Reference Documents: As Built documentation
label | eaf5f6d4-44ae-5824-8ddb-b350574bdb8c |  | note | - - - - - - - - -
label | 00719488-2850-597d-aead-a27c630daf25 |  | note | Inspection / Test Method: Site Inspection
label | 1d07d78d-4a13-54d4-bd2d-69a1e17506b6 |  | note | - - - - - - - - -
label | f5004f8f-adf8-5aa5-a80d-c9c0adde60fb |  | note | Record of conformity: Survey records
label | e21f262d-d8ce-57d6-8118-6761e2e3bc03 |  | note | - - - - - - - - -
label | 49fadb75-9e87-597e-a629-6f3934a5ffc8 |  | note | HP*
label | 61422b0d-1db5-5287-9fd8-1e50cb0fbbd5 |  | note | - - - - - - - - -
label | e744dddd-37a0-5cb5-a16d-d18d66f30d45 |  | note | Responsibility: Site Engineer & Surveyor
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3A.6 - Compaction Testing (where granular material forms part of permanent pavement)
label | 6f0fae11-2d15-5436-ba5d-2bf8f5a3f817 |  | note | Frequency: Each Lot
label | 291643e7-9c44-5444-b59c-de0f87f7f8db |  | note | - - - - - - - - -
label | c363da58-1359-53f1-bc2f-20a82c0d5f82 |  | note | Acceptance Criteria: Material during compaction shall have a moisture content of not less than 85% Compaction Scale A requirements apply Lower & Upper Subbase Layer - Not less than 98% compaction Layer directly beneath bituminous surfacing 100% Compaction
label | a544175e-5f0b-5185-880a-4243669d07d4 |  | note | - - - - - - - - -
label | f7521fe3-ac46-51dd-8401-014ba6f245fe |  | note | Reference Documents: VR 304 Table 304.08
label | 29c653c9-09df-5ca0-9a57-992a15fbea1f |  | note | - - - - - - - - -
label | 51c9e4e2-1026-523d-8cf0-6117b256bcf8 |  | note | Inspection / Test Method: Compaction Test
label | 86b49d45-d48d-5daf-9e29-ac0fcb4b735c |  | note | - - - - - - - - -
label | 4c006092-b579-5f13-af64-3b0758098c84 |  | note | Record of conformity: Test Results
label | 5cd8f058-7785-55c5-b95e-ff0e1bb0236e |  | note | - - - - - - - - -
label | 12dd382e-6eee-5181-a0c3-a33d0de1a355 |  | note | TP
label | bee673e3-16df-57fc-8f12-975411781847 |  | note | - - - - - - - - -
label | 57db4a25-3bce-5fcb-aa02-00affc7e01f5 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3A.7 - Post Compaction Grading (where granular material forms part of permanent pavement)
label | 5bb9c051-644b-5f41-b2a4-ec55fb35466f |  | note | Frequency: Refer to table 304.111 for various minimum frequency or testing for Grading and PL
label | ef51d2ad-67cd-54e1-8404-494cf4770d8b |  | note | - - - - - - - - -
label | 7a05cec9-b908-5e27-8b6f-62f396b9ed55 |  | note | Acceptance Criteria: Grading and Plasticity testing to be conducted post compaction
label | e5591b25-fe77-50d1-b659-adfdeb23ec3c |  | note | - - - - - - - - -
label | b041f36e-2a33-59cf-a25a-1d5338203137 |  | note | Reference Documents: VR 304 Table 304.09
label | b34950c4-ef55-53db-a9c1-c71e24e26895 |  | note | - - - - - - - - -
label | afa484d3-8b9c-546a-8273-b837c91f7819 |  | note | Inspection / Test Method: Compaction Test
label | 80633d37-210f-53a6-abee-722755b883db |  | note | - - - - - - - - -
label | b71b7adc-dbdb-54df-a841-0ddebc48f06f |  | note | Record of conformity: Test Results
label | 1b352756-dd32-5e15-a694-bb7fbb512e55 |  | note | - - - - - - - - -
label | 654ce7f3-7478-522e-9be7-01c53468637d |  | note | TP
label | acb17cd5-05f5-5395-ac3b-4f3b3301aea1 |  | note | - - - - - - - - -
label | 7d25528f-d956-5851-af27-57dc537750e3 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3A.8 - Backfill Trench (where material forms part of permanent works)
label | 458ab3aa-8a62-5094-a0bd-502a10638809 |  | note | Frequency: During construction.
label | 43debd91-4d73-5a34-a5f3-23685575876e |  | note | - - - - - - - - -
label | 17bd523f-7a7d-5f66-b639-60b842d9b798 |  | note | Acceptance Criteria: Superintendent approved backfill material is to be used for backfill asp 1145-C201-ACM-CVP-DRG2127 Backfill is to be compacted in layers to achieve specified density uniformly throughout the depth of each layer. Material: Inorganic fill material with 75mm max. stone size (non trafficable) 95% Dry Density Ratio @ 1 test in each 900mm of fill & each 100Lm
label | 819b8d05-ffb5-5d8f-b61a-6858e92e070d |  | note | - - - - - - - - -
label | 8c288616-a2c1-503b-a981-56970e6fbaa3 |  | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2127 & 1145-C201-ACM-CVP-DRG-2128
label | d8353374-21d1-5ae0-a0e3-8ac5e09d23da |  | note | - - - - - - - - -
label | 92aacbbc-c378-5a20-ab6e-8a1628f88e25 |  | note | Inspection / Test Method: Visual & Test Reports
label | e0ef76d9-ff97-506f-95a3-e6607d05e06f |  | note | - - - - - - - - -
label | 196a3ff8-b008-545c-ab4d-700aaf9ccbdd |  | note | Record of conformity: Signed ITP
label | b0fa81f0-cdab-57ed-b878-daa483bb26ee |  | note | - - - - - - - - -
label | 7e6a0f68-49f5-5994-956c-f4ea5b818218 |  | note | IP
label | 173cfcce-58ce-5237-b965-59e89d076547 |  | note | - - - - - - - - -
label | 69f43c81-f03f-5745-800f-dd8463ddff3e |  | note | Responsibility: Site Engineer & Superintendent
checkpoint-group |  |  | section | 4 - Completion
checkpoint-status |  |  | checkpoint | Test Requisition
text | 1c653c2e-fe2d-569b-bc1e-c1ffde3e7008 |  | textbox | Test Requested on
text | 781a74b7-37ac-56b9-a484-55f06e6dbf14 |  | textbox | Location
select | 6a4c37e8-b6a1-5e31-9dcf-6c2b90d4ccdf |  | dropdown | Material Type | Type A,Type B,See comments
select | 58cd4984-6e7f-5ac7-a692-7f128a3e6b5c |  | dropdown | Material Source | Holcim,Boral,See comments
boolean | 1fcd9df5-7582-5e74-a8aa-523a8d3952a3 |  | tickbox | Compaction Test (Standard)
boolean | 9e8aaea0-f42d-58de-b7d9-616492c4f571 |  | tickbox | Compaction Test (Modified)
boolean | b6146fa3-bdf7-588c-aa01-c6e4cf2df9c4 |  | tickbox | Maximum Particle Test
boolean | c4f8b4c8-3b15-5ebe-bb56-bf250b0d1f43 |  | tickbox | CBR/Swell Test
boolean | a08711a4-4228-5c1f-a572-9d78381e74e8 |  | tickbox | PI Test
boolean | 5f9acdd1-803a-5fba-bd19-91fa409e1b65 |  | tickbox | Permeability Test
boolean | 2c263634-9f57-5ece-af95-04851578b1d8 |  | tickbox | Grading
boolean | 732c7523-b8c6-5cf8-8496-3f7bd8467e9a |  | tickbox | Moisture
boolean | 7b640d10-7ead-5187-b140-f813e1630654 |  | tickbox | See comments
text | dd02c81f-8dda-52ec-ba35-0f737534031b |  | textbox | Test Level/ Layer
holdpoint |  |  | signoff | Test Requisition
checkpoint-status |  |  | checkpoint | 4.1 - Surface Reinstatement
label | 100a6ef3-a2fe-527c-ba7a-5fa8d4c36246 |  | note | Frequency: Completion of works
label | ad2743e8-99be-5d36-9ec1-fee177666110 |  | note | - - - - - - - - -
label | cc75a14d-a347-5e04-8d70-d1ac5cbc9eb3 |  | note | Acceptance Criteria: Surface reinstatement similar to adjacent undisturbed materials, visually accepted by Superintendent's Represented
label | c0bb68a3-aeff-53e9-8193-83b03f93e3f9 |  | note | - - - - - - - - -
label | f3d0e375-d37f-5b71-945b-202fef7d54b7 |  | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2127 & 1145-C201-ACM-CVP-DRG-2128
label | 773868aa-07d1-5a4b-a31f-143a7f703246 |  | note | - - - - - - - - -
label | e550f153-17bb-584b-8d97-370dd1198ffc |  | note | Inspection / Test Method: Visual
label | d2e5b5f9-bbf3-5857-be62-5dd2777ede52 |  | note | - - - - - - - - -
label | b51380c3-fb57-570e-8cf3-b02a9c381d7e |  | note | Record of conformity: Site Inspection
label | 357992a0-8f5d-5f87-8271-07d97d64b35c |  | note | - - - - - - - - -
label | 9413b4d3-631b-5b50-aa94-01797bfe2ea1 |  | note | IP
label | 17b7fade-f6fe-58b5-bf1e-68590f8a8fb7 |  | note | - - - - - - - - -
label | 748d5d9e-ad10-5631-a47d-2f8298ac91c3 |  | note | Responsibility: Site Engineer & Superintendent
checkpoint-status |  |  | checkpoint | 4.2 - Survey data captured for as-built purposes
label | d13448c7-d29e-5693-b421-04b1b3835aa3 |  | note | Frequency: Completion of works
label | d7a7ddc7-3135-57eb-a799-7fe0fac74072 |  | note | - - - - - - - - -
label | e3e39824-0ff4-5bd8-8c51-12cabab13da0 |  | note | Acceptance Criteria: As-built Drawings Tolerances as per WSA 02 - 2014-3.1
label | 3b6e6cf6-95bc-50fa-ae9b-3d04c0a8339d |  | note | - - - - - - - - -
label | 4607a97e-3df2-5936-bc6a-0f8002fdb419 |  | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2127 & 1145-C201-ACM-CVP-DRG-2128
label | 6ef3ca9f-e432-566c-be38-8f01f5884df1 |  | note | - - - - - - - - -
label | 1337af9d-4fae-5c39-97be-7f385e015f5d |  | note | Inspection / Test Method: Document review
label | ab7ce194-80f9-5467-ba14-1472e2cfd7e3 |  | note | - - - - - - - - -
label | 4cdeb118-19f3-50fa-a799-cfc5bb0e4d10 |  | note | Record of conformity: As-built survey records
label | d08655f8-abd7-5638-a604-c24e18b79df2 |  | note | - - - - - - - - -
label | 53f69d7e-cfee-5c70-93a9-644a6bdbd83a |  | note | AP
label | 50c1b415-a1fa-5a18-b30e-8b688ac701c5 |  | note | - - - - - - - - -
label | 42206ceb-6273-5653-8f52-fc023b8f7799 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
label | 2123716e-b93f-593c-9929-23c2738e408d |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 07ad2f77-97b3-5164-9b35-ff1001a945de |  | textbox | Print Name:
text | 5f44e8a7-2040-5134-b1ac-0c9120bd4182 |  | textbox | Position:
date | 8c5070e9-7f84-5708-b180-37bc39e4d9f6 |  | date | Date:
date | ba84cd9f-31dd-5fde-911a-59955b4d5dcd |  | date | Work Completed On
checkpoint-status |  |  | checkpoint | Lot Verification.
select | 6a2abbaf-4e78-5ed8-9685-9a477a87ab09 |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | 8a0aad77-c9a6-509b-a405-5c9411e8e577 |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | 1441bd51-1827-5fce-83f2-42ee415329ad |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | 796ef165-1d35-5362-a31c-d69379f1f974 |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | 58fe69b4-0b9a-5569-b12a-aad604b75f80 |  | textbox | Other:
select | bfda56a7-11f5-5f6d-a6de-02f79f378eeb |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | c775b3fd-1c90-56d6-937c-a653d9e5954f |  | date | Lot Closed On
text | 32570278-a7b9-5145-a4ed-936de46cadbd |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-043-UT-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0043 - Electrical Protection Works | e616592a-16ca-430e-9462-0e1d32a621b6
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | e8d49e45-4f3e-544c-814a-fe41b47611fd |  | date | Lot Created On
date | 32744003-9830-5f3a-8170-fb7a9e1fe7d6 |  | date | Lot Opened On
date | e42d6ff8-1407-5a9a-859e-f4469a30f8fd |  | date | Work Commenced On
select | 227fd173-c25d-53b4-85ce-7f75cae614ae |  | dropdown | Lot Type | CIL-Civil Lot, DRL- Drainage Lot, EAL- Earthworks Lot, ELL- Electrical Lot, UTL- Utility Lot, STL- Structural Lot
text | 9c27c68b-7fc6-5d93-b715-57a731eace25 |  | textbox | From and To Chainage
select | 84efc297-7c4d-5c84-bb8e-d69663d2b6ce |  | dropdown | Construction Element | UTIL - Utility
select | 46944887-1a29-506e-8375-f90185fdd7ef |  | dropdown | Activity | POWE - Power
select | a04b954b-02be-50e4-9bb4-3416ccb027fc |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | 95886dc8-3f06-5d11-8652-3347615908b4 |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | e267260c-fd41-5008-9131-9ac6e11f495c |  | textbox | Engineer Responsible
text | 853e1f7d-7f44-5159-a800-e6676b1e67d0 |  | textbox | comments
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Induction
label | 3c5cd2e2-b943-5e31-bdce-278c045f54d0 |  | note | Frequency: Prior to Commencing
label | e1afeafe-3bf6-5c8f-be08-fb4d1e5e6854 |  | note | - - - - - - - - -
label | 2572c78e-aae0-5816-a6a5-073a9a3449f8 |  | note | Acceptance Criteria: All personnel on site have been inducted to the CRU site
label | a9470fe2-b5d5-5928-b3e1-085affd928d1 |  | note | - - - - - - - - -
label | bd745d6c-d2fd-5e60-8d10-12adf4b98c7b |  | note | Reference Documents: PMP Inductions Register
label | 09290c6f-e1cd-5882-9ed3-46894b79133e |  | note | - - - - - - - - -
label | e5e9b89e-ef78-5b03-9824-d39ee6bb4e9b |  | note | Inspection / Test Method: Document review
label | 0bd20f42-1f85-57b5-834f-4781b09bbfd8 |  | note | - - - - - - - - -
label | e2098667-e227-50f1-a850-61b5f50744a3 |  | note | Record of conformity: Site induction signed.
label | 3dad20fc-63b8-5223-857e-92bd0e8ab9b6 |  | note | - - - - - - - - -
label | 1bf39ea5-2c15-5dfc-9c56-fc3204d3ac0d |  | note | AP
label | 4a5ccee2-5a90-5be6-9a31-b730fa4f4349 |  | note | - - - - - - - - -
label | 3e310d01-ff5e-590f-beb3-e94b573f5528 |  | note | Responsibility: Site Engineer / Site Foreman
checkpoint-status |  |  | checkpoint | 1.2 - Safety measures are in place, SWMS undertaken
label | 7b84c6f4-b303-5376-bd4c-fdea304752eb |  | note | Frequency: Prior to commencing
label | 5f941eca-e37f-55f2-a541-a713cb2288aa |  | note | - - - - - - - - -
label | 5278d7fa-c0a2-53c8-834e-e06b6256f958 |  | note | Acceptance Criteria: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
label | 6bebbc9b-57fe-5a07-b308-421af305567d |  | note | - - - - - - - - -
label | d6f782ba-71b5-537d-89bb-d047dff96c5b |  | note | Reference Documents: Health and Safety Coordination Plan
label | 4ddb996a-e870-5cb4-9f71-2f838c9e2411 |  | note | - - - - - - - - -
label | db2a8640-147c-5d60-b82f-3ac836d87218 |  | note | Inspection / Test Method: Document Review
label | 7c3c138c-4cc9-59ba-9016-92abab7fbf69 |  | note | - - - - - - - - -
label | 5f9b2ec6-48fb-5443-980d-b11c90f46511 |  | note | Record of conformity: SWMS(s) signed
label | ca6d773d-efa0-5652-b969-9bed1fba2438 |  | note | - - - - - - - - -
label | 64eacdb7-886a-5bd0-bd01-b884406e7130 |  | note | HP*
label | dec5a761-51b0-5914-ad12-2820c1cfabb1 |  | note | - - - - - - - - -
label | e27fd96f-3fb2-5af1-ab82-fc9dbbf41d42 |  | note | Responsibility: Site Engineer, Site Foreman & Superintendent
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Check that current revision drawings are being used
label | e93845c7-c6b7-5c01-ac3c-7c0d242cfa2b |  | note | Frequency: Prior to Commencing
label | 919afead-410e-5828-9f40-4bc6141410b8 |  | note | - - - - - - - - -
label | c0eae80c-e880-525f-a125-9e69f0a0941a |  | note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
label | 1bf96c28-ff34-5411-b4e7-b529acee190d |  | note | - - - - - - - - -
label | 18929d8e-87f9-56c1-af15-9544d137685e |  | note | Reference Documents: Project Drawings / Drawing Register
label | 5bb16add-5bd7-5dce-912c-7705d232044c |  | note | - - - - - - - - -
label | 6ef65277-cb92-55c8-aa0c-3467362ff799 |  | note | Inspection / Test Method: Document review
label | 9c660ff3-1717-5f0f-8951-a6af20665476 |  | note | - - - - - - - - -
label | fe42d3f8-01a9-5329-9401-be4bcca0275d |  | note | Record of conformity: Latest Revision Drawings
label | 9343788a-dd13-5402-a25b-852f85c86bb4 |  | note | - - - - - - - - -
label | 9388387e-d68d-579d-bf22-949f7ed427d3 |  | note | AP
label | 91daefc7-99fb-5d66-b5fb-c17578501171 |  | note | - - - - - - - - -
label | dd7e5440-f066-5cd5-a8ae-005cb18a7acc |  | note | Responsibility: Site Engineer / Site Foreman
checkpoint-status |  |  | checkpoint | 1.4 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
label | c6e759da-2a38-5d72-ae6e-747a9c14baa4 |  | note | Frequency: Prior to Commencing
label | e1cf0a87-a393-5517-ada4-aa555a8d1a60 |  | note | - - - - - - - - -
label | 6ce92a7c-02c0-51f1-b417-3da8e5075bec |  | note | Acceptance Criteria: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | a7dd1a36-1a00-556d-9567-b22e5d091bf8 |  | note | - - - - - - - - -
label | 4a15287d-13d9-53b3-a59c-dd396b6ade7b |  | note | Reference Documents: EMP, Site induction
label | cc5b17a9-ceee-5b56-9c4d-cc07a4922265 |  | note | - - - - - - - - -
label | e74162e0-7f21-5afd-8d64-682a4a643853 |  | note | Inspection / Test Method: Document review & Site inspection
label | 873c707e-7c79-5953-afae-ee4d162217ab |  | note | - - - - - - - - -
label | 5ed94c16-3770-5e46-9026-58f7da401016 |  | note | Record of conformity: Signed ITP
label | 058d97ce-146d-52bf-abd2-9f277188cc58 |  | note | - - - - - - - - -
label | e41628db-783e-5df6-a242-a28799c92cef |  | note | IP
label | ea8356e7-9eec-5b38-b9e6-2cacf58b0411 |  | note | - - - - - - - - -
label | 1a435091-2afa-513e-9d73-aa4eb2c89225 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 1.5 - Confirm suggested Asset treatment has been approved by Utility provider
label | fc586b9a-463c-5ce2-acc4-73e04a6d273f |  | note | Frequency: Prior to Commencing
label | ffc8d62c-c5db-5617-a019-f33ac0003248 |  | note | - - - - - - - - -
label | 03d81051-02ea-5db6-a3e3-29de7d4f971e |  | note | Acceptance Criteria: Ensure that adequate notice is given to the Utility Service provider and Superintendent prior to utility asset protection as per PS3120.06 part C Date of Notification: Date of Utility Provider approval:
label | 6370794d-81b0-5469-a9d7-9bfe600ae02d |  | note | - - - - - - - - -
label | a788e5e4-0fbb-5cbb-9419-2dce09b55d9d |  | note | Reference Documents: MRPV- ITC Delivery Contract
label | a68cea63-efd4-57a5-9fb3-cb5ec8d03ef3 |  | note | - - - - - - - - -
label | e80b5c35-0c0e-5b2b-a62c-fcfae9be66c1 |  | note | Inspection / Test Method: Document review
label | 0c52205d-4aea-5e4a-9f7b-8fb39762f0f6 |  | note | - - - - - - - - -
label | 9afdc400-baab-53b2-ace8-ae22299ccf8e |  | note | Record of conformity: Signed ITP
label | 7bceefba-4295-523b-bb78-74dc903bb4f6 |  | note | - - - - - - - - -
label | a8195e4d-8873-5997-b513-7ea531c41634 |  | note | AP
label | 9f96dab2-d0c8-5e55-9fd5-59223939ec2d |  | note | - - - - - - - - -
label | a8fdd5b8-d94c-5604-a3d5-c6cd654809be |  | note | Responsibility: Site Engineer
checkpoint-group |  |  | section | 2 - Procurement
checkpoint-status |  |  | checkpoint | 2.1 - Approved materials ordered.
label | 34a943a4-bd4d-554b-b766-87735eee4ef1 |  | note | Frequency: Prior to excavate
label | cfbc2953-e4ed-5377-9c23-3f632230ba65 |  | note | - - - - - - - - -
label | 159c6527-e718-5432-b1e3-faac83175243 |  | note | Acceptance Criteria: Complying with AECOM Utility Protection Detail Drawings
label | aa0f15e4-2890-57b8-b22c-9f3de9ccd046 |  | note | - - - - - - - - -
label | 16a9dcd7-e8a3-558f-8e10-6ac5ad4d92fd |  | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2127 & 1145-C201-ACM-CVP-DRG-2128
label | b637ec2c-9b67-55ed-81c2-e733a3fdffee |  | note | - - - - - - - - -
label | 6da0006a-e963-5195-962f-4f1d798a65f0 |  | note | Inspection / Test Method: Site Inspection
label | bb855ee5-aadd-5658-b9af-ae414b180c1f |  | note | - - - - - - - - -
label | 8f5da69b-bcef-5ca1-926c-e0f38157df91 |  | note | Record of conformity: Supplier's Declaration of Conformance.
label | 4c048ac4-c80c-528b-a019-d631a8a6fd6e |  | note | - - - - - - - - -
label | 1860259d-cc68-551a-a1fb-aa63eeb08149 |  | note | SCP
label | abd006c4-b7b2-574a-ae8d-a35f3595e197 |  | note | - - - - - - - - -
label | a3a21b83-fa20-50d0-a4ee-256229e34007 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 2.2 - Receival and Inspection of products.
label | 82c6cacd-d6f9-5efa-a42a-3e089a44d72b |  | note | Frequency: Upon receival
label | a4bedfd2-decd-5cdb-9671-93b4f89c43b9 |  | note | - - - - - - - - -
label | 80ebfb47-8448-5f44-b26e-9d421b82c3fc |  | note | Acceptance Criteria: Approved Product and supplier. Right dimensions / specifications. Defect Free.
label | acb881d3-d70e-5303-9718-1fb043891a0f |  | note | - - - - - - - - -
label | b505033e-4bd6-53d6-a4ce-ae52635c6bd0 |  | note | Reference Documents: Receival & Inspection Checklist
label | 23f6d482-c52b-5599-b475-b4a57c3dfa89 |  | note | - - - - - - - - -
label | cf04672f-742c-57d8-bb7d-4b9c5f07ebdf |  | note | Inspection / Test Method: Site Inspection
label | 42d97771-45d0-5afa-9c78-16c2b4be39a1 |  | note | - - - - - - - - -
label | 6046c804-1eab-5f33-9fdf-d9a7ec6db430 |  | note | Record of conformity: Completed Receival & Inspection Checklist
label | b8872a3d-9aff-584c-a756-eeaffe4f1912 |  | note | - - - - - - - - -
label | 60600cca-f191-5e2b-9e02-f213ba1ff3c7 |  | note | WP
label | 53c8630f-2e64-5084-b45f-7b8d7ea19324 |  | note | - - - - - - - - -
label | ae1bba8c-a7ee-58f1-8a3a-17631f0c83d7 |  | note | Responsibility: Site Engineer
checkpoint-group |  |  | section | 3 - Construction Works - Detail 1 - Stabilised Sand Encasement
checkpoint-status |  |  | checkpoint | 3A.1 - Survey set-out
label | a08726ca-14c0-5024-95f5-1212c3c16d99 |  | note | Frequency: Prior to Commencing
label | 8ca67e1c-ae6e-5869-af2e-c0ceff2063ae |  | note | - - - - - - - - -
label | bd367a66-07f9-50a0-b720-a6265b4a3c2a |  | note | Acceptance Criteria: Latest available revision used
label | 30076c6a-e913-51e5-92ec-698f86fe6708 |  | note | - - - - - - - - -
label | 46253555-281c-5f26-83bb-88444c63f78b |  | note | Reference Documents: Drawings
label | da3cd963-aaca-56ac-9c83-ea94a5532b9c |  | note | - - - - - - - - -
label | 542148fd-a916-5e81-97dd-d5ea545432b8 |  | note | Inspection / Test Method: Site Inspection
label | 6e4ea93c-3932-5824-acaa-16c95504d34b |  | note | - - - - - - - - -
label | 03713635-77fd-5256-822a-88fe72fa042e |  | note | Record of conformity: Survey records & pegs on the ground
label | 604beaa9-552e-560f-b359-1bebb3f772e7 |  | note | - - - - - - - - -
label | 7518ac04-ce0c-5953-acd9-2e33d49e3b54 |  | note | SCP
label | 96cbf395-028b-5b18-850a-aa63ed9c6d00 |  | note | - - - - - - - - -
label | 28400af7-e6a5-5917-bdb4-c46ff3eccf6b |  | note | Responsibility: Site Engineer & Surveyor
checkpoint-status |  |  | checkpoint | 3A.2 - Excavate and expose Pipeline
label | 37156a63-4b5c-5fe5-a35b-c2e26d172b3c |  | note | Frequency: During construction.
label | d05ef5f2-0fdc-5d47-bd35-c745e191001d |  | note | - - - - - - - - -
label | 2e2c79dd-f263-5e63-a2aa-72156771864f |  | note | Acceptance Criteria: Ensure that the minimum cover requirements, horizontal and vertical alignments are within tolerances.
label | e6a106f9-ebba-5753-85d8-976479c7efe5 |  | note | - - - - - - - - -
label | 250ba29d-ab3c-52e1-aec7-41a3136ad7dd |  | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2116
label | 694c8ddf-d91e-5ae2-aa15-c174ce673092 |  | note | - - - - - - - - -
label | 5cd44e13-e1b5-56e1-8ef2-079fe6dbc437 |  | note | Inspection / Test Method: Document review & Site inspection
label | 929d7bff-5f42-5b38-b20b-f9b56b6d4e62 |  | note | - - - - - - - - -
label | afb4278e-db80-5dee-aa48-da048e8ee2e0 |  | note | Record of conformity: Signed ITP
label | 96d6d8d5-296e-5cdc-bae3-01b0efc5a84e |  | note | - - - - - - - - -
label | 3b5e492b-2f24-5302-91c7-b0a37ffe8301 |  | note | AP
label | b97b1a75-f8c3-53e9-88cf-1ee49d20a8ea |  | note | - - - - - - - - -
label | a376ec13-ddb7-58bf-a972-98be3c2db4f7 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3A.3 - Survey pick up
label | 4273c463-362d-52ad-8e15-b0482938b84c |  | note | Frequency: During construction.
label | b8c929c5-23da-5d6f-b044-113809e0829b |  | note | - - - - - - - - -
label | 9042e5e8-147b-591f-a110-1e8b37c8a79b |  | note | Acceptance Criteria: once asset has been completely exposed surveyor is to complete a survey pick up at multiple points across exposed asset
label | f6a4b923-b2e5-5238-b460-a9e7ec0110d9 |  | note | - - - - - - - - -
label | b95770dd-0120-56ed-8ba3-5149c7f4c15c |  | note | Reference Documents: As Built documentation
label | 2828c87c-4674-574e-8f97-d8802f92163d |  | note | - - - - - - - - -
label | 7a8923a1-7051-5e38-887b-9c3a9ba71c7b |  | note | Inspection / Test Method: Site Inspection
label | 90edb35f-7e44-53c9-8ea8-51d62844792c |  | note | - - - - - - - - -
label | a33444f4-7559-5dbe-bd4a-1eea80baff94 |  | note | Record of conformity: Survey records
label | d3ed15d2-ec0a-506b-a28c-32390574356e |  | note | - - - - - - - - -
label | 135a8f05-5aa8-555e-b8dc-bce19ab66bfb |  | note | HP*
label | 8d052b6b-cbc5-5613-b6fa-bb962ab49566 |  | note | - - - - - - - - -
label | 619f14b1-d7ef-5855-acdd-4792044ae565 |  | note | Responsibility: Site Engineer & Surveyor
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3A.4 - Place pipe protection material
label | 12523a05-51ce-5eb3-b114-43508694abf3 |  | note | Frequency: During construction.
label | 28a9e8d6-8112-52a2-8c52-739a5b4c530e |  | note | - - - - - - - - -
label | 4f237f75-a1a7-552a-933e-ee519326b358 |  | note | Acceptance Criteria: Detail 1 - Place 5% stabilised sand uniformly along length of pipe, work into place under pipe haunches. Min cover requirements - 400mm width of trench, 100mm below pipe and 150mm above pipe. Marker tape to be placed above protection.
label | 65923cf3-7ea9-5204-a5cb-86f24e5c0b36 |  | note | - - - - - - - - -
label | a2fbc8ad-b70b-5839-871b-5a907dff4359 |  | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2127 & 1145-C201-ACM-CVP-DRG-2128
label | 28a1b9a2-83cf-5a92-b12c-ed0855838593 |  | note | - - - - - - - - -
label | 2bb705a9-323f-56ed-b6f0-804c5f578fe7 |  | note | Inspection / Test Method: Visual
label | 714faa8f-b7a6-573c-bebd-b991f0256e2d |  | note | - - - - - - - - -
label | 60c2a1fb-6b38-58fe-85d3-f3779415e485 |  | note | Record of conformity: Signed ITP
label | c5b74cbf-5982-5a52-9f26-eebf13133342 |  | note | - - - - - - - - -
label | f00af42a-e4b7-58cf-b2f0-f405616f54ba |  | note | WP
label | 4219e952-3e32-593e-aac6-c1ac451a8c24 |  | note | - - - - - - - - -
label | cdc4989b-90d5-52b8-b193-a74e66fb0442 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3A.5 - Survey pick up- Encasement of Asset
label | 07a7e374-fc76-5dd7-b6cf-063073961dc2 |  | note | Frequency: During construction.
label | ea8ca1e0-6ae3-5244-a66a-2a74697fb3b8 |  | note | - - - - - - - - -
label | 88909c0a-6bf1-5384-af9f-84eb9467ace0 |  | note | Acceptance Criteria: Once encasement of stabilised sand has been completed the surveyor is to complete a survey pick up across multiple points on top of asset protection
label | ad167363-8c6f-5138-8a3f-b27d6d49e86d |  | note | - - - - - - - - -
label | 483bfa8c-9b3e-56c1-ae41-8f82fb821a1a |  | note | Reference Documents: As Built documentation
label | 8f713892-b40e-59ae-a3f3-c6a28cb2e980 |  | note | - - - - - - - - -
label | e7820c10-4060-515b-bf36-c37496ffdc72 |  | note | Inspection / Test Method: Site Inspection
label | 5e2f5b75-b5da-582d-b327-820a4dc4df01 |  | note | - - - - - - - - -
label | b6c9c7ea-d35f-5e57-b761-92c909ab5b27 |  | note | Record of conformity: Survey records
label | 429b0306-5cd9-5e39-b16a-67c29d93ac7e |  | note | - - - - - - - - -
label | 4f61612c-577c-57e3-8200-bd83b3f4ab45 |  | note | HP*
label | 8e8e5361-9413-5b2c-9c13-f9797d6401e5 |  | note | - - - - - - - - -
label | fabdd7b3-74cc-54a9-a8de-98e565234157 |  | note | Responsibility: Site Engineer & Surveyor
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3A.6 - Compaction Testing (where granular material forms part of permanent pavement)
label | 1192b1e9-5516-5e2b-b8db-f442ca1cf290 |  | note | Frequency: Each Lot
label | a9c3b1f7-f7a9-5f71-9d4f-b7bb3df81c3a |  | note | - - - - - - - - -
label | 1187234c-eadb-5460-930c-e5e2d39db100 |  | note | Acceptance Criteria: Material during compaction shall have a moisture content of not less than 85% Compaction Scale A requirements apply Lower & Upper Subbase Layer- Not less than 98% compaction Layer directly beneath bituminous surfacing 100% compaction
label | f4410983-19f8-545e-96be-648ebffa5d6a |  | note | - - - - - - - - -
label | 8b69d0a1-09b9-5b77-8ad6-c9121cce073b |  | note | Reference Documents: VR 304 Table 304.08
label | cdf8eb44-4b30-53f1-9468-5ec07a830740 |  | note | - - - - - - - - -
label | 55a54a17-947a-5ade-9352-169c9fc9372c |  | note | Inspection / Test Method: Compaction Test
label | 366d0322-84c0-53a6-a053-029be336d326 |  | note | - - - - - - - - -
label | ab346c01-25b6-5c2a-9b83-f3b8b2b5dc20 |  | note | Record of conformity: Test Result
label | 4a6b740c-36e3-5448-8cf9-bdccbaefb9e1 |  | note | - - - - - - - - -
label | 2654b83f-cf1c-5bfb-bea4-7efe97c463c4 |  | note | TP
label | bbf3fdde-e008-5d8a-84c9-cd211828f3b3 |  | note | - - - - - - - - -
label | 0dedc6de-bbf6-50ad-924b-89a8d14b053a |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3A.7 - Post Compaction Grading (where granular material forms part of permanent pavement)
label | 9095431d-c047-50d2-86c9-1b2535626f6f |  | note | Frequency: Refer to table 304.111for various minimum frequency or testing for Grading and PL
label | 9890646e-fe63-56c4-83e0-f40668d7c4e1 |  | note | - - - - - - - - -
label | 9bb462aa-e82d-5541-af36-f9cdbdbdf0a6 |  | note | Acceptance Criteria: Grading and Plasticity testing to be conducted post compaction
label | 9a0c74b4-afce-5e7b-a699-69ec39a523ea |  | note | - - - - - - - - -
label | 4d8cdbaa-64ab-5023-9c68-11595014740d |  | note | Reference Documents: VR 304 Table 304.09
label | d8b0696f-7f37-54ea-b642-84bdcfe8c642 |  | note | - - - - - - - - -
label | f3ee235e-ea04-5a18-9a49-8b79579afef4 |  | note | Inspection / Test Method: Compaction Test
label | b558fd64-5d53-5448-a538-13828ca10322 |  | note | - - - - - - - - -
label | ffd08bbc-f889-545b-8a68-0153a97698bd |  | note | Record of conformity: Test Result
label | aa62d190-5651-56b0-851e-a5f61264593b |  | note | - - - - - - - - -
label | df177034-63b9-5c5c-933b-b83fa1e7ab81 |  | note | TP
label | 181024d0-2890-56eb-b8cd-cfa1e520f1f8 |  | note | - - - - - - - - -
label | ed650d21-ffe1-54f5-b15f-bc7f0c3a419d |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3A.8 - Backfill Trench (where material forms part of permanent works)
label | f0ceb052-652f-51b7-baae-5eee55b478cb |  | note | Frequency: During construction.
label | 6951b08b-d1d3-5e6f-86ac-7222e751bddc |  | note | - - - - - - - - -
label | 2bde47bd-d7bb-5d41-afc2-d15d68869dd7 |  | note | Acceptance Criteria: Superintendent approved backfill material is to be used for backfill asp 1145-C201-ACM-CVP-DRG2127 Backfill is to be compacted in layers to achieve specified density uniformly throughout the depth of each layer. Material: Inorganic fill material with 75mm max. stone size (non trafficable) 95% Dry Density Ratio @ 1 test in each 900mm of fill & each 100Lm
label | 7296b91e-e037-5b87-9162-9e1cb4fef8cc |  | note | - - - - - - - - -
label | 6cdae927-f084-5297-bc3a-24c57971df1e |  | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2127 & 1145-C201-ACM-CVP-DRG-2128
label | d16a3635-da19-5f57-b0b9-2f6d31f1e821 |  | note | - - - - - - - - -
label | 4c7566ac-ad68-5967-90e1-e79ae6ff1398 |  | note | Inspection / Test Method: Visual & Test Reports
label | 8f995ed3-9297-571a-9a20-b7893d6d2784 |  | note | - - - - - - - - -
label | 34d60867-d851-50c8-97e0-52e40d670442 |  | note | Record of conformity: Signed ITP
label | e3cfaa09-6145-566b-a380-38b43d1dc1b0 |  | note | - - - - - - - - -
label | 6ba5bf41-e890-5010-a6d3-279fb4b96174 |  | note | IP
label | 037b43a2-0944-5921-9262-8ad4771b942f |  | note | - - - - - - - - -
label | 208954ae-147a-5605-a6f8-b85e3606387d |  | note | Responsibility: Site Engineer & Superintendent
checkpoint-group |  |  | section | 4 - Completion
checkpoint-status |  |  | checkpoint | Test Requisition
text | 3d053ce1-8cfd-5a7b-bd3d-4fb190767abe |  | textbox | Test Requested on
text | 286a0826-84a2-5b5e-b059-2863a46bea1b |  | textbox | Location
select | 37317299-cb66-5832-9c20-da4e874a10bf |  | dropdown | Material Type | Type A,Type B,See comments
select | 14958777-f1d1-5779-8ecf-92f1e4af4405 |  | dropdown | Material Source | Holcim,Boral,See comments
boolean | 02d10ed8-3def-5343-8f3e-7a704462d823 |  | tickbox | Compaction Test (Standard)
boolean | 75d6318f-bb56-5046-a3ed-64ffafd9899a |  | tickbox | Compaction Test (Modified)
boolean | b9e85009-e44a-5bc3-afb5-a6bdfedd4610 |  | tickbox | Maximum Particle Test
boolean | f6a18e84-1da3-531f-bfb2-7cf8e913c34a |  | tickbox | CBR/Swell Test
boolean | c54a83b9-d453-51f6-9309-84d64a6fddcc |  | tickbox | PI Test
boolean | b1aa6fad-1be8-515a-bedd-5cb959170e70 |  | tickbox | Permeability Test
boolean | 65716a32-f6f1-58d2-99ff-e9be35a26111 |  | tickbox | Grading
boolean | da2fb165-dd90-5831-9e0c-10e51669325e |  | tickbox | Moisture
boolean | 9242f0dc-afae-53ca-99e2-667963a4ef09 |  | tickbox | See comments
text | 44d39716-ccfb-5a52-8846-29161cfc2214 |  | textbox | Test Level/ Layer
holdpoint |  |  | signoff | Test Requisition
checkpoint-status |  |  | checkpoint | 4.1 - Surface Reinstatement
label | 398bc2ee-2bc9-5dae-9211-c6266b076d05 |  | note | Frequency: Completion of works
label | 052b5f7a-14d4-56e8-a2b6-da3c02c86cf9 |  | note | - - - - - - - - -
label | a5c1d861-6017-52ff-b413-a1001826c6cd |  | note | Acceptance Criteria: Surface reinstatement similar to adjacent undisturbed materials, visually accepted by Superintendent's Represented
label | cef8f171-58c2-57bd-ba0b-a097b0815dc8 |  | note | - - - - - - - - -
label | c1c500b0-3f99-522c-8183-d56480ddf713 |  | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2127 & 1145-C201-ACM-CVP-DRG-2128
label | ffa0997b-4ad9-5b17-8f44-0c30aa61c58d |  | note | - - - - - - - - -
label | 3ad62202-657b-5baf-89d6-5ad726a6b042 |  | note | Inspection / Test Method: Visual
label | ab1cfd2c-539f-55c4-a7ba-b5ecc089a97c |  | note | - - - - - - - - -
label | 24d4112a-c845-5f63-b795-7303dee17a4a |  | note | Record of conformity: Site Inspection
label | 304331b0-0d8c-54d2-ae7f-9fae389ab5bd |  | note | - - - - - - - - -
label | 4fbb7756-daea-5234-92b8-d884df2ad65c |  | note | IP
label | fbff98a1-b149-54b4-8097-c83865ad1eeb |  | note | - - - - - - - - -
label | c7bee3b8-f14c-59da-8c22-8554855db667 |  | note | Responsibility: Site Engineer & Superintendent
checkpoint-status |  |  | checkpoint | 4.2 - Survey data captured for as-built purposes
label | bf1c2d81-a1e2-5d4a-87e8-cbace83c905b |  | note | Frequency: Completion of works
label | 5f90a1c8-a07c-5825-b7f3-c0cc80fc99ce |  | note | - - - - - - - - -
label | 08c62764-7174-5a81-89de-bec2fedfb3bd |  | note | Acceptance Criteria: As-built Drawings Tolerances as per WSA 02 - 2014-3.1
label | f041b7a0-fe55-52f8-800b-907c9cb9aab2 |  | note | - - - - - - - - -
label | 93e57511-e67e-512c-a027-791f5af4c78b |  | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2127 & 1145-C201-ACM-CVP-DRG-2128
label | fa771e30-b913-54a3-8e22-fbf2dd4cbb6b |  | note | - - - - - - - - -
label | 1425a8ef-b5e8-5768-9100-ef64bc7f836c |  | note | Inspection / Test Method: Document review
label | a79e9412-38e8-5ef7-a79d-59f0769907d6 |  | note | - - - - - - - - -
label | 95dce106-0c2d-5585-912d-2fb7bc995bd7 |  | note | Record of conformity: As-built survey records
label | 3cb897e1-d61e-5381-9998-aa2d55a18f37 |  | note | - - - - - - - - -
label | d1f9db6f-b2cc-540d-bc15-43356db5057c |  | note | AP
label | 77bcc053-2afd-5781-9f31-2fdbd182798c |  | note | - - - - - - - - -
label | bb732d2f-48d2-5bb1-8bc4-c80a07b0ba49 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
label | d9aa975b-4aff-5775-85e8-05249143c20e |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 9b0ddb46-075b-5a24-bad9-174229bcd99d |  | textbox | Print Name:
text | 8f919253-1a5b-5138-8e4d-45973cd741e3 |  | textbox | Position:
date | ec5ee3a0-991f-5e0d-afaa-6aedef0985f4 |  | date | Date:
date | ab832dba-b536-5d85-8a06-1e3094c19973 |  | date | Work Completed On
checkpoint-status |  |  | checkpoint | Lot Verification.
select | 0beaadbd-80c3-57b6-9b0d-e67a46c85b0e |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | 345d2cd5-2f35-5ffd-8a75-c9a21eeef663 |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | 55a8a561-e6f0-5bfb-9ae0-09395729187f |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | 15a60c33-2156-5c10-ace1-d1bd5361d9fa |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | 66789288-c32a-5ace-b6a5-e5841892a68f |  | textbox | Other:
select | 98509ac4-f3b1-569d-b8b8-f0512650041e |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | a1675822-7435-5bad-88cc-3411e17a8029 |  | date | Lot Closed On
text | 55772375-7012-5491-91cf-0d26da182012 |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-077-UT-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0077 - Electrical and Communications Conduit Installation | e6a95f20-1300-418d-af74-06386e5c1bff
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | 71bef4c8-7d89-5a15-9e0e-1a6cf68f50c6 |  | date | Lot Created On
date | 7fc0af89-53fd-567d-ac9c-5bb6fae8b531 |  | date | Lot Opened On
date | 0a94eae5-44cd-512a-a03c-519d62be015e |  | date | Work Commenced On
select | 386da6bf-3e14-527d-81c0-efb60709bf89 |  | dropdown | Lot Type | CIL-Civil Lot, DRL- Drainage Lot, EAL- Earthworks Lot, ELL- Electrical Lot, UTL- Utility Lot, STL- Structural Lot
text | c679dea7-a005-5426-a319-d218b72a950c |  | textbox | From and To Chainage
select | 5fb7c8ef-abeb-56f0-937f-9ea2d816f04e |  | dropdown | Construction Element | ITS - ITS
select | c1f6c6a9-f93a-599d-87c5-9d6b5a310410 |  | dropdown | Activity | COND - Conduits / Pits
select | 82176665-5bee-5e57-89f8-b79747fda63f |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | 70aa361d-3f9c-51a3-a1c8-18bbe15176db |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | 07f58591-15b6-5386-95e1-8e98fa4cc185 |  | textbox | Engineer Responsible
text | d7e066c9-3692-541b-9276-b161aa224cc0 |  | textbox | comments
checkpoint-group |  |  | section | 1 - Preliminaries / Pre- commencement activities
checkpoint-status |  |  | checkpoint | 1.1 - IFC / Shop Drawings Submission & Approval.
label | c79f3fae-5974-5ff0-846b-5df2f85f3dc6 |  | note | Frequency - Prior to Commencing
label | 5392dc4b-bca2-5114-9a8d-ecec30178417 |  | note | - - - - - - - - -
label | 5c6e57ce-ad11-56b4-89e3-4e97462125ab |  | note | Acceptance Criteria - IFC Construction Drawings & Most Current Revision.
label | 442d6b5f-c80a-583f-a230-39603cf07999 |  | note | - - - - - - - - -
label | 4c06c083-090e-5a65-a8da-a725962afdae |  | note | Reference Documents - IFC Drawings
label | e1c9d0bd-fc0e-5c71-9e8c-2f551983f2f9 |  | note | - - - - - - - - -
label | a4578401-881b-51ed-abc8-589f49f348b8 |  | note | Inspection / Test Method - Document review
label | b52a2d27-7f03-56a3-b5b2-e14fcfed160c |  | note | - - - - - - - - -
label | 83a711bc-61ad-55c7-a0f5-78efeb0220a4 |  | note | Record of conformity - IFC Dwgs
label | ac2a65de-d5f1-5849-b7ad-66432f180811 |  | note | - - - - - - - - -
label | 820d59b4-1928-50a8-abab-f31052340f9b |  | note | HP*
label | 53cbac5c-54e1-59e6-a1dc-d7e8ac382153 |  | note | - - - - - - - - -
label | 9846a6aa-96cf-583b-aef4-9be1c5b4fbd4 |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Project Engineer
label | 9129abe1-5acd-5378-bc39-f7efcde3d0d1 |  | note | - - - - - - - - -
date | 58e09ca1-87fe-5f56-9b50-f4c7ff856dfd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Survey Set-Out
label | f2176854-83fc-5ff5-b36b-153e85d6c55b |  | note | Frequency - Where Required
label | 937be4e6-31e6-5a35-8df8-18195dbb7ab2 |  | note | - - - - - - - - -
label | 599386b1-8070-577c-9045-1480c18ee877 |  | note | Acceptance Criteria - Qualified Surveyor to set out extent of works on ground
label | b6e225ae-4518-583f-8c82-8fc97f59232f |  | note | - - - - - - - - -
label | b8d56710-02e2-5a76-ac50-d80d6ce3cd0f |  | note | Reference Documents - IFC Drawings
label | e393b250-e05b-5548-873c-7499df076208 |  | note | - - - - - - - - -
label | 6207e2df-313b-5737-b237-6eec21545b26 |  | note | Inspection / Test Method - Survey
label | d33c8941-c60a-5777-b432-0ae81db30f48 |  | note | - - - - - - - - -
label | 7efbbb59-e2be-58f8-b983-2b3396d31fd9 |  | note | Record of conformity - Survey Calibration Certificates
label | bc133a8e-1fa9-53f5-bb99-0caf1a1512a2 |  | note | - - - - - - - - -
label | 6eaecdf5-3d9f-56b2-9a7c-6ec7d0964185 |  | note | WP
label | 66926059-cc7c-56ed-9438-8c95bd7aae92 |  | note | - - - - - - - - -
label | c7860635-18a8-5f3e-a597-e6e9a175a1fd |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Foreman
label | e76142c3-2cd2-59ef-bdfb-b4b399ac39a5 |  | note | - - - - - - - - -
date | 1ccdf3c6-9ce4-52eb-92a3-6a4362a5e520 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Excavation Permit/ Service Location
label | 741c7bc9-ff21-55c4-b305-ddc0b57e93bb |  | note | Frequency - Prior to Commencing
label | 57ffbe00-6bc4-5d48-9c58-665fc3ae7cd3 |  | note | - - - - - - - - -
label | dd93fbbc-77a4-53af-9119-a5ab63fb62ae |  | note | Acceptance Criteria - Identify underground services NDD/hand dig as necessary.
label | 3d6214d4-f017-5343-a54e-249dd55b750e |  | note | DYBD documents
label | 80cd77d5-ddd8-57d3-9fe0-ab831228cd4f |  | note | - - - - - - - - -
label | dddabf27-e0fe-5e91-98e1-530e50e74081 |  | note | Reference Documents - Dial Before You Dig
label | 692add77-6c64-5f68-896e-dbe94f9cae7f |  | note | - - - - - - - - -
label | 9deb2aa4-fb73-5684-bad3-1e88489de3e2 |  | note | Inspection / Test Method - Survey
label | e7696428-feb0-54ef-89a4-bd3817cae345 |  | note | - - - - - - - - -
label | c159d8a3-e045-5cb3-a667-65fa6d953b5d |  | note | Record of conformity - Excavation Permit
label | 2d5c8a2c-344e-5c45-ae0c-dc94101461a0 |  | note | - - - - - - - - -
label | 2bdc3cc7-2906-5b41-a8b8-3530e51720f6 |  | note | HP*
label | 5973d9e0-da08-5847-880f-7a21e41c90ea |  | note | - - - - - - - - -
label | eba269c2-8ff8-5cd9-9e20-99d29171a26e |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Foreman
label | e70ca3b6-8f0e-5429-8f17-01a49e0d6f2a |  | note | - - - - - - - - -
date | f45aeba0-3f6f-5585-9ae5-eba547591398 |  | date | Date Completed:
checkpoint-group |  |  | section | 2 - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Conduit Sizing
label | abb25a5b-6de4-571a-a40b-9cd874c017cc |  | note | Frequency - Prior to Commencing
label | 4fd897ad-fbbb-5449-889b-f85b006359c8 |  | note | - - - - - - - - -
label | 8e05a705-f5af-5762-8686-b96d134b400a |  | note | Acceptance Criteria - Conduit sizing to comply with VR table 733.021
label | 9cfd3091-de74-5d2b-9ced-02ff48442efb |  | note | Excludes utility providers designs and requirements
label | 4272a7c2-7dd6-57c5-a42f-21899006bc35 |  | note | - - - - - - - - -
label | 7021c8dd-005f-5228-a477-b084d1dee49a |  | note | Reference Documents - VR SS
label | b35f6fc4-db8d-517b-9d51-0654962f9f4b |  | note | Table
label | f73a2f94-73a5-5b14-afb4-97768b71d7d6 |  | note | 733.021
label | d9eecf3c-60be-5723-9141-ce6cc906da35 |  | note | - - - - - - - - -
label | d1bb6e10-7105-516d-804f-0896e0c3149f |  | note | Inspection / Test Method - Site Inspection
label | b299ae34-7be6-5445-b136-7890fdde9444 |  | note | - - - - - - - - -
label | 88755103-49ee-5aee-972b-8da4000110bf |  | note | Record of conformity - This Checklist
label | 299d9f1e-958f-56bd-bf10-7fe81a445b53 |  | note | - - - - - - - - -
label | 1a97cfce-0454-5cc6-ba8d-2356a28de4bd |  | note | IP
label | 5bd28cf8-4914-55c8-9009-68aeefc819b0 |  | note | - - - - - - - - -
label | b033dbc3-3535-56c6-ad27-8441dc1bd262 |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Foreman
label | 9514f07d-71ba-578e-a874-bc34a52547aa |  | note | - - - - - - - - -
date | 75d59d7e-e6a2-5879-8dff-ac2147dc7637 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Material Backfill
label | c7cc4db7-33b4-534d-9d83-1f846a1740ac |  | note | Frequency - Prior to Commencing
label | c10f5423-149c-5071-9a86-98baec196e87 |  | note | - - - - - - - - -
label | 2b1db58c-90b8-5e88-b862-3f22b3241752 |  | note | Acceptance Criteria - Unless otherwise specified, materials used for bedding and backfilling shall be uniform in composition and free from perishable matter and shall comply with the requirements specified in Table 706.061.
label | 241fd3a7-5b6f-59e5-bf71-b46b3256bb00 |  | note | - - - - - - - - -
label | e3284bb3-41ec-5fe8-bb53-3abcbc0490b9 |  | note | Reference Documents - VRSS 706.03
label | 97aa54b1-0cfe-5784-a8f4-be5d8c9f7e2c |  | note | - - - - - - - - -
label | 79ef9c45-93a3-5f1b-892a-ea4f5d730fbe |  | note | Inspection / Test Method - Site Inspection
label | 090ccac0-5dc7-50b5-b072-7ac9a579962d |  | note | - - - - - - - - -
label | b4c16a55-878e-5afe-8a5e-e39666f951b1 |  | note | Record of conformity - This Checklist
label | 8cdd3738-7ac2-5136-abc6-5c8448815c95 |  | note | - - - - - - - - -
label | 464fc88d-f591-5a54-83d5-add2070aaf6e |  | note | IP
label | 66257eab-0f37-595e-95d5-4a36dcc96696 |  | note | - - - - - - - - -
label | 3d0c5dc8-9f35-5ef2-90ca-b725679ddce7 |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Foreman
label | 759ee671-35c7-5786-9427-dab5a08ac69c |  | note | - - - - - - - - -
date | 622e3b80-a01d-5300-8209-f97b8a44ccf6 |  | date | Date Completed:
checkpoint-group |  |  | section | 3 - Excavation
checkpoint-status |  |  | checkpoint | 3.1 - Entry/ Exit Points
label | 48c1cf06-ecf0-571d-92c5-1514b69d9b6c |  | note | Frequency - Prior to Excavation
label | c8a82891-cd6a-56e6-8556-d89097598836 |  | note | - - - - - - - - -
label | 811048bd-104f-5318-9ccd-ad7db0214a77 |  | note | Acceptance Criteria - Entry/Exit points to be established
label | febb4034-dd6e-54e3-9e12-9b05d0530ec7 |  | note | - - - - - - - - -
label | e2439fe4-32d9-5ba9-8aad-0a505d7793d6 |  | note | Reference Documents -
label | 344d49bd-9700-55dc-9faa-c655ca64fbfe |  | note | - - - - - - - - -
label | 5358b53e-6e48-5289-97f4-6080cd5d2979 |  | note | Inspection / Test Method - Review
label | 62070dae-a893-5273-9cd0-d1de2775b9a4 |  | note | - - - - - - - - -
label | fea1ed07-19b1-5cc3-8dec-34f6f76bb760 |  | note | Record of conformity - This ITP
label | 72cb1922-16fa-5cbb-a5ca-0805bdf2941a |  | note | - - - - - - - - -
label | 92aeb10e-a31b-5fdc-ab48-353a4f8f8628 |  | note | HP*
label | 0ff0909b-5c72-5f79-8c3c-20c36c4a5f21 |  | note | - - - - - - - - -
label | de1a147d-06ba-5f6b-b27e-542fb1fb3dbd |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Project Engineer
label | db7c301c-d169-5f90-b4dd-089678b9f117 |  | note | - - - - - - - - -
date | 3abcf085-6004-54fd-807f-6714573886c6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Minimum Cover
label | 051a7baa-0df7-52f9-88f8-bfdfe2e43c78 |  | note | Frequency - Ongoing
label | df3cbbb8-fe75-57ad-b11f-5cc37ab4e4b7 |  | note | - - - - - - - - -
label | 55e94d2c-1dfe-56c3-8fc9-20e3bcfa92ee |  | note | Acceptance Criteria - Minimum conduit cover shall apply as per table 733.031
label | 0d4a158e-5443-5ea9-b378-2ba29ad87a7d |  | note | Under Freeway Pavement – 1200mm
label | 179eb480-66f6-5694-bbb6-2d0736f8e128 |  | note | Under Arterial Road Pavement – 1200mm
label | fec3bb11-f133-5d58-8853-d7937a04f32f |  | note | Under Local Road Pavement –600mm-800mm
label | 34817a83-1bea-5048-a26c-7ad13b4156d7 |  | note | Under Open Drains – 750mm
label | 6a3f20de-9e66-570a-985a-e4464bfdfd48 |  | note | Under footpath or unpaved areas (LV Circuits only) – 600mm
label | 48a600f5-357c-5896-a5cf-d0e54a74c205 |  | note | Under footpath or unpaved areas (Extra LV or Comms conduits only) – 300mm
label | 15c0809b-5715-576e-a40c-6e8034b1f8a0 |  | note | - - - - - - - - -
label | 304a8a53-bfb5-576e-973e-089ba24f0f8e |  | note | Reference Documents - VR SS
label | 5f4ff1f0-a47f-5a86-9bd9-67bde6307c36 |  | note | 733.031
label | ea5430ee-75fd-525e-9b98-48e886e40820 |  | note | Refer Individual asset owners specifications
label | 2aa91eab-cb3c-537b-9eca-74a2a7619c75 |  | note | - - - - - - - - -
label | b97d51b3-c102-5b28-8607-64374b56cd0c |  | note | Inspection / Test Method - Survey
label | 4141367c-02e5-501e-8e63-b9279816d133 |  | note | - - - - - - - - -
label | 9ca2980b-b8f1-5f2f-a259-4c4a24db1160 |  | note | Record of conformity - AS Builts
label | f54d930f-ff3c-5cbc-a869-8872fbfbd164 |  | note | - - - - - - - - -
label | 950a630e-01ec-5eb0-a65a-c9de606bdb28 |  | note | SCP
label | bc8717b5-d6bd-5661-a004-0cb1e26c512e |  | note | - - - - - - - - -
label | b1d99370-6ab5-57d1-b83f-b0a62cc446f6 |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Project Engineer
label | bc000201-763f-5dee-b536-918ab76bf096 |  | note | - - - - - - - - -
date | 65e89a6b-f36a-513e-8198-3d1909460f6e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - Backfilling
label | b9d57fc4-eb97-51f7-bbbd-f90c1ae64a06 |  | note | Frequency - Prior to backfilling conduits
label | 7929dad2-1947-500e-9948-e6374f93c45c |  | note | - - - - - - - - -
label | 31080601-d252-56ce-b602-fedf07560a54 |  | note | Acceptance Criteria - Once the bedding material has been laid and the conduits put in place, works shall not proceed prior to inspection by superintendent or representative.
label | 6903fb91-ff84-5015-b829-818a570b15ce |  | note | For Vicroads assets only. Not applicable to Utility providers
label | 2a932dc7-ac4c-51d2-b851-1a31a7ef4b17 |  | note | - - - - - - - - -
label | bee86efa-feeb-5dd9-b123-5537fa328b55 |  | note | Reference Documents - VR 733.06
label | 4bd8e217-06fc-5b49-bb54-7dfae8722d3d |  | note | - - - - - - - - -
label | c37e7e2a-6bad-5d7f-bc8f-2a2b23ca3342 |  | note | Inspection / Test Method - Inspection
label | 1ebc79ab-8ca7-520f-bf57-f5c6e21e89b4 |  | note | - - - - - - - - -
label | 284a8453-54c5-57d0-b081-0340c56a57d6 |  | note | Record of conformity - This ITP
label | 4f1d1d88-3509-5f7f-a13e-30a9f93d6d7f |  | note | - - - - - - - - -
label | 3cd1e62f-9843-58cf-98ff-2e3e018ca7b1 |  | note | HP
label | 820523c6-042b-5c62-aa82-cfe23e160a53 |  | note | - - - - - - - - -
label | aad57de7-2c1f-555c-a235-ed6c3c61bacf |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Superintendent or Representative
label | d64d645b-3387-5e8e-9286-1c363aa751d7 |  | note | - - - - - - - - -
date | c0a80673-01f0-5799-8db9-5d141809ffb7 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Compaction Requirements
label | 73ffdad8-43f1-56dc-8d2f-92e1d3ca1a4d |  | note | Frequency - During excavation
label | 24bb9075-b851-5469-8bd0-e3ea2c0f9a6b |  | note | - - - - - - - - -
label | 3367cfe5-382f-5d0e-be1e-d40b4133ae86 |  | note | Acceptance Criteria - Under Paved Areas - 98% Modified Compaction
label | be111cf2-30ee-56e8-933d-220c4d794c9e |  | note | Unless otherwise specified, pavement material shall have during compaction a uniform moisture content within the range 85% to 115% of the optimum moisture content as determined in the Modified compactive effort.
label | e2281386-8bf3-5bd6-b362-267ad09c7745 |  | note | Bedding and Backfill (except pavement)
label | c18067ec-4471-5b9d-a3bd-dfd29b9ee95a |  | note | Backfilling beneath areas to be paved shall be assessed for compaction in lots as defined in Section 173. The number of tests per lot shall be three. Backfill, the whole of which passes the 37.5 mm AS sieve, shall be compacted to a mean value of density ratio of not less than 97%. The calculation of density ratio shall be based on Standard compactive effort. A lot shall consist of a single layer of work. A minimum of 20% of all lots constructed shall be tested.
label | 3fde6a0a-a64f-5626-ad41-cc0f84c16b1b |  | note | - - - - - - - - -
label | ce8df9ed-9a10-5397-8f88-2da4a2b8bb5a |  | note | Reference Documents - Test Results
label | 820dae3c-7a13-5699-b839-df0c338ece03 |  | note | - - - - - - - - -
label | 7bafd51a-03e3-5aa0-be4f-d359dfc2d02f |  | note | Inspection / Test Method - Compaction Test
label | 87de43e2-1b6c-5f21-bb03-ed533b898e04 |  | note | - - - - - - - - -
label | 39a6c8be-0ed5-5966-8e32-ad6aab675f60 |  | note | Record of conformity - Test Result
label | 623650b9-5d03-5ce4-b73e-dd1a22efd50c |  | note | - - - - - - - - -
label | 953aa849-e3c8-5d17-8d08-254933682c77 |  | note | TP
label | 4ddae27c-e154-5a21-9ef7-9f22698a93a8 |  | note | - - - - - - - - -
label | 6eca88d3-c3cb-58d3-85e6-083c773a76da |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman -
label | a57cc047-d164-5a63-b16d-6e5bff011165 |  | note | - - - - - - - - -
date | 0c810fd6-f3be-5736-a36c-18af7651eaa3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 - Survey pick up / Bore Mark Out
label | 68172a6d-1ebd-5985-9066-82dbacefea86 |  | note | Frequency - During Bore
label | 9c889f62-f20e-5658-bf45-cb10a7734b82 |  | note | - - - - - - - - -
label | 2c08cda6-b3f9-5094-a0d7-8c6165180c45 |  | note | Acceptance Criteria - Survey to pick up as record of conformity on top of laid conduit prior to backfill.
label | e249433b-2165-50be-b170-fe2a896831a1 |  | note | - - - - - - - - -
label | 2a716089-0fc8-5efd-9155-6a1603a0a618 |  | note | Reference Documents - Survey
label | 19a82845-e080-5eed-8e95-364742af7666 |  | note | - - - - - - - - -
label | ce827300-a2df-5a82-a562-a1dc025633de |  | note | Inspection / Test Method - Survey
label | 341d63b2-4f84-5ac5-a016-b82a1e67bb29 |  | note | - - - - - - - - -
label | 93d3e3be-71e0-5e4a-8211-6e75f71488af |  | note | Record of conformity - AS Builts.
label | 209b4c5d-ff98-5eee-b68a-3384b90f6f7f |  | note | SCP
label | e2633fa5-4e82-5a05-a6e4-a82d4f489d65 |  | note | - - - - - - - - -
label | 59cc5071-a40c-52e8-bfbe-67d753a0e130 |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Foreman
label | b107f589-21ce-5a01-b019-2aa1fd972db4 |  | note | - - - - - - - - -
date | 42fd5551-f69b-522b-aa6e-c1991da34ee0 |  | date | Date Completed:
checkpoint-group |  |  | section | 4 - Completion
checkpoint-status |  |  | checkpoint | 4.1 - Entry/ Exit Points
label | 4c389474-e37a-5fe3-8992-4cc5f5bc153b |  | note | Frequency - On Completion
label | fe82a626-29fd-5153-867a-8c151b234efa |  | note | - - - - - - - - -
label | e5334ccd-5aa5-5365-b58d-659e0c6ec123 |  | note | Acceptance Criteria - Ensure clean fills is used to fill in Entry/ Exit points
label | 95a541a4-7f5a-5a2d-91c6-e528081343c5 |  | note | - - - - - - - - -
label | 013ecfe5-be2d-516d-ba8c-53e6429f3558 |  | note | Reference Documents -
label | b6cccf72-f80b-506f-82f1-eddc67dfbc63 |  | note | - - - - - - - - -
label | bf030900-c3f4-586e-af77-c422da21b0b1 |  | note | Inspection / Test Method - Review
label | 38be73a4-16f9-59c9-a256-48609fd9040e |  | note | - - - - - - - - -
label | 6ec49f1d-a783-5f8c-9a80-f77de87b6cd5 |  | note | Record of conformity - This ITP
label | c856313c-df79-5d84-a896-15346a5f6028 |  | note | - - - - - - - - -
label | 1a68d3c6-2a77-5c54-9a68-0f72e6b09686 |  | note | IP
label | c4dbe53d-4b63-5642-9a45-4143242e554c |  | note | - - - - - - - - -
label | ce7f4330-471b-5d26-acc3-87ff9cb56e43 |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Foreman
label | dbb4cde9-9c88-552d-9b4e-febf300ee6ef |  | note | - - - - - - - - -
date | d7b88314-7f9d-54a5-b7c2-35924d946d58 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Conduit Layout
label | cbfab4a7-d64c-54da-825c-5478c7a75978 |  | note | Frequency - Each Lot
label | fb2a5be3-38f7-51fb-bd0a-6ea128ad0e01 |  | note | - - - - - - - - -
label | a708ffe8-29a5-5001-ba44-155e8265912f |  | note | Acceptance Criteria - Conduit arrangement to suit trench detail;
label | b6ac4ec3-5fd6-518d-afe0-78a57ea60e3c |  | note | Conduit to slope towards pit for drainage purposes;
label | 86ca988c-5ff9-59cf-9653-c11b6ed986ef |  | note | Quantity of conduits to be confirmed and entered w/ each lot.
label | 559bfdfc-c511-55bc-bb28-a213e84d7fa9 |  | note | - - - - - - - - -
label | 910c7e72-d4f1-544e-b6a7-103c79781c2c |  | note | Reference Documents - Utility Provider Drawings/ Project Plans
label | 904cd85d-91a5-52b3-a7c7-881a84c6d077 |  | note | - - - - - - - - -
label | 3ed14428-1cfb-5543-a195-10f3709bd1bf |  | note | Inspection / Test Method - Project Engineer
label | f9522652-9c06-551a-af0a-8000e45c9eed |  | note | - - - - - - - - -
label | 7365baf2-e1d0-5d9b-89e8-3cf2a2f7a3ca |  | note | Record of conformity - Inspection
label | fdddea35-227c-599c-b4dc-60e4a1114e7c |  | note | - - - - - - - - -
label | 0681350f-1190-58d2-b810-b25bb0a0a219 |  | note | IP
label | 7a13eca0-2e6d-5395-9a54-f9e823c0556a |  | note | - - - - - - - - -
label | 6b49a2fc-ee1c-5140-aaec-33068c125905 |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Foreman
label | 0b40f4a6-492e-50ba-859e-092577a5fd01 |  | note | - - - - - - - - -
date | f94fbcb0-b317-5bb8-8d82-b34efc138a12 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Draw Cord
label | e2a14e28-a836-59c4-94e4-e7f75bfad3c9 |  | note | Frequency - On Completion
label | 631e826f-b971-5420-83f1-e03726b354a1 |  | note | - - - - - - - - -
label | a03c6ebf-7a00-59f8-a3fd-02616d2d7818 |  | note | Acceptance Criteria - Each conduit for electrical wiring an communications cables shall be provided one synthetic draw cord not less than 3mm diameter and a minimum breaking strain of 1.6kN
label | 2b094b74-56f8-5d79-ba42-a5f1d412b94d |  | note | - - - - - - - - -
label | ebcff86d-fbf2-5b77-8127-22db83b47d5c |  | note | Reference Documents - VR SS
label | d1996381-6235-50c5-a0d6-084c879bc9f6 |  | note | 733.05
label | b660fdd6-e762-5c13-9c24-11f0f0f1eb6c |  | note | - - - - - - - - -
label | 64cb7629-3327-5ce4-b1e1-512cb9e1d11c |  | note | Inspection / Test Method - Inspection
label | a5f87334-989f-55e3-8c06-dc80a78c8747 |  | note | - - - - - - - - -
label | 40c21961-2d08-5638-a8cc-900f9b32b504 |  | note | Record of conformity - This ITP
label | 0d44cdb4-b458-5bbc-8a70-4ad1e7b7522a |  | note | - - - - - - - - -
label | 56b2d236-19bc-5f5a-b547-a1579f82f691 |  | note | IP
label | 83f52dfa-105f-5b53-8be2-4f2a781289ea |  | note | - - - - - - - - -
label | e97ecee0-5551-5da1-94a0-536e338a9aac |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Foreman
label | 0be40d70-4470-56bf-baea-522bb5e1da53 |  | note | - - - - - - - - -
date | 3e767b45-cc21-5af2-8978-98afea7a5b59 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 - Site clean up
label | 89ff9475-a015-58ef-b406-57a1dd7f6bff |  | note | Frequency - On Completion
label | cf50975a-3144-5e8b-b297-f94c5b6743ee |  | note | - - - - - - - - -
label | 9684756e-7857-5fe4-9b71-7d7e1eb81fd1 |  | note | Acceptance Criteria - Ensure site is clean and all garbage has been removed
label | 62a86219-834b-50e4-9189-2b5aa8506969 |  | note | - - - - - - - - -
label | 05c105aa-fe7d-5db3-940a-8e680b7c50ed |  | note | Reference Documents - VR 733.09
label | d386d929-fb8a-5228-bb64-55360b2b8ab5 |  | note | - - - - - - - - -
label | 672c20b5-a07a-5dd4-8a02-13f4636b9309 |  | note | Inspection / Test Method - Inspection
label | f8694096-b997-5e7b-8b12-297b3b193e40 |  | note | - - - - - - - - -
label | 73356a16-1d26-58db-85d2-28e32a484eb1 |  | note | Record of conformity - This ITP
label | bee79ae0-f4f7-5660-9911-3cd5feea1e7e |  | note | - - - - - - - - -
label | 2fa6c357-82e5-588b-bb9b-03a3bd66d3cd |  | note | IP
label | 055a7ea9-1c91-599c-8fe3-977aea0aa778 |  | note | - - - - - - - - -
label | d3525125-5748-5c09-9bc2-334955b4b983 |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Foreman
label | bab187e6-c1b5-59c0-8554-48a5e964b51e |  | note | - - - - - - - - -
date | 1ae78df4-b53c-5a7a-a507-e27faf6bee01 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 - Maintenance of Pavement
label | 964200bf-5b41-5dee-a5ab-18ada208b1b1 |  | note | Frequency - On Completion
label | 0324547d-af30-51ab-abe9-7951a9bada85 |  | note | - - - - - - - - -
label | 28a8fde7-b7d1-5c8f-8945-4925b774fffd |  | note | Acceptance Criteria - The reinstated surface shall be maintained in a trafficable condition after the completion of backfilling. Additional pavement material shall be placed in the trench and compacted as specified where in paved areas settlement or loss of material from the surface exceeds 20 mm measured from a straight edge laid across the top of the trench.
label | 67905f50-0494-5efe-ad5b-5632a1474981 |  | note | - - - - - - - - -
label | 4a1d83de-338e-59f3-b5a8-18f956b16c9c |  | note | Reference Documents - VR 706.11
label | 353566c1-a4e4-59ed-a8b4-aed6c44920f0 |  | note | - - - - - - - - -
label | bb7cb7d4-7410-5c2d-923d-ca97f08d2a6f |  | note | Inspection / Test Method - Inspection
label | e15c04dc-0d5f-5203-bd3c-4c0fb534c82f |  | note | - - - - - - - - -
label | 164ae65e-1790-5476-975e-fefd8d81fa16 |  | note | Record of conformity - This ITP
label | 990bbf04-a11e-5ba2-b095-fa1816b6db1b |  | note | - - - - - - - - -
label | cc033f35-6151-5db8-bb5a-af6b1034667f |  | note | IP
label | 8983b42c-c54e-505b-af6d-4d4111ec5886 |  | note | - - - - - - - - -
label | 724f0e87-d1d2-50e9-a9fb-a83a87eeb306 |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Foreman
label | 2f0be1c6-2cf7-52f1-a2e9-60e53148fcc4 |  | note | - - - - - - - - -
date | 3e649396-3e4d-5562-a54b-3026a295526e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 - Records
label | c3ef2df7-88c5-5f59-b890-047b2a0a569f |  | note | Frequency - On Completion
label | f260ba28-b219-54be-9c60-92678e1b2b50 |  | note | - - - - - - - - -
label | b13fdbcc-e8ee-50ae-b230-285a76353f71 |  | note | Acceptance Criteria - Bore Logs of the works to be supplied from subcontractor
label | b39209a1-6345-5b4e-8535-2c616dc84127 |  | note | - - - - - - - - -
label | 697923c0-48ce-5885-b1dc-b5b010b12406 |  | note | Reference Documents - Bore Logs
label | 72a4227d-1630-56be-b1e3-2ba2fd87e6da |  | note | - - - - - - - - -
label | a45f6451-27ee-50ae-8007-5bf73d7bfb8d |  | note | Inspection / Test Method - Document review
label | a486fbee-5dd7-5e56-9841-bb9ee4f26f89 |  | note | - - - - - - - - -
label | 21ae63c9-6d5a-5008-b9b7-119c17146a14 |  | note | Record of conformity - This ITP
label | 2881aa47-e5e1-54fb-9354-3b93a65017bb |  | note | - - - - - - - - -
label | d78fb87a-fc82-5645-b49f-229f718c1da0 |  | note | HP*
label | a5c73c81-a75f-5151-8398-d0e2187833e9 |  | note | - - - - - - - - -
label | 614b3f87-e61d-54d8-8443-c5c81801ef76 |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Project Engineer
label | 4bcc92ca-b753-5a11-b857-774e6a7775d3 |  | note | - - - - - - - - -
date | ea7740a8-1c2d-5e85-ad98-61704605e765 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 1897ac67-c3c1-5519-a587-2a232191dd21 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 8f499b02-fb37-564b-956e-69713417acf8 |  | textbox | Print Name:
text | 363b4956-b3e4-5915-aa71-96de60748d3b |  | textbox | Position:
date | 96fffba3-d489-57a1-a837-5ffe39a8b300 |  | date | Date:
date | f0672d4e-1fae-5e28-892e-87b3eef296e1 |  | date | Work Completed On
checkpoint-status |  |  | checkpoint | Lot Verification.
select | b93c3e5a-c4f9-5480-9b33-9107b95044d8 |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | b5d5b9ee-6dbf-5ec6-9f4d-c16a607aa03b |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | ffd1ccf3-db76-561b-bf23-6010ec3634ef |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | 959e618f-d3fe-5142-b14d-3aa690679f72 |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | 2adf714b-7245-5c2e-bf5b-e2dcb0853321 |  | textbox | Other:
select | d253c105-e17f-5787-9bb7-8ba948d9e9e4 |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | 6db02d74-0d2f-58e5-8224-0fea15f510b7 |  | date | Lot Closed On
text | c307c3d6-e802-50a6-8123-a921f9553d12 |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-085-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0085 - SUP INSTALLATION (HCC) | ed7cffb0-19d5-497c-84b5-1359ac943fbf
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | 2e570b9a-e401-5130-a8d9-d616c6c0590a |  | date | Lot Created On
date | 0e1d4fe5-7427-5ca9-8f07-ed182b34ea25 |  | date | Lot Opened On
date | fd6e935c-d04b-5331-80f5-3134356ee7c8 |  | date | Work Commenced On
select | 86a0ac61-821b-5512-b393-6c9eccbcc257 |  | dropdown | Lot Type | CIL - Civil Lot
text | 585c6a70-c332-5380-b616-4eba986dd93b |  | textbox | From and To Chainage
select | 4c29aa2c-6084-5831-8b56-3f6a76fe219e |  | dropdown | Construction Element | PAVI - Paving
select | b78abdc2-208f-5026-a96e-3f17ab1a4080 |  | dropdown | Activity | SHUP – Shared User Path
select | eaa678c7-e2c3-5050-a351-6bec6606dcdd |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | f363959e-c14a-51fa-b923-92a585a163d1 |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | 7e8d79d3-7eaf-575e-a5f3-02616361dfe0 |  | textbox | Engineer Responsible
text | 77b21e18-7b9f-5e60-ae1c-bc4377700cae |  | textbox | comments
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Check that current revision drawings are being used
label | 03ba854b-b32a-5c0b-a053-cc7e39b82987 |  | note | Frequency: Prior to Commencing
label | 47ee0802-6b91-5ac5-93de-232b3e34548d |  | note | - - - - - - - - -
label | a218be83-ea64-5b4b-9383-1a18181153b4 |  | note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
label | a3f3449a-8a82-5a7d-95a1-860d96056389 |  | note | - - - - - - - - -
label | ad1b6bc5-bbc0-5b8c-8a3e-d828a731a920 |  | note | Reference Documents: Project Drawings / Drawing Register
label | 9567aab5-175c-56c2-8678-d1511d6f3dee |  | note | - - - - - - - - -
label | c6f44a6e-c9c1-5668-8834-79ddbd9f63a1 |  | note | Inspection / Test Method: Document review
label | d007f70b-f3c1-5cd0-8bdb-1f075f3cc1c0 |  | note | - - - - - - - - -
label | 8b8dc6c4-bb64-51ed-bf13-6107d85e88f8 |  | note | Record of conformity: Latest Revision Drawings
label | 41ec0ccd-ba91-58e6-88c4-365ce08153ae |  | note | - - - - - - - - -
label | 4737f95a-cac4-5aa7-b8bf-1bbfbbdc33c7 |  | note | AP
label | cd8fd411-bf35-56fd-9836-11d57d9c6a29 |  | note | - - - - - - - - -
label | eda3a119-53c6-56e6-b3a9-ea4308f7353b |  | note | Responsibility: Site Engineer / Site Foreman
checkpoint-status |  |  | checkpoint | 1.2 - Bedding Material / Base Layer
label | d7a15792-a48a-5b18-b9d5-68c7f47d0133 |  | note | Frequency: Once, for each mix design, prior to placement of material
label | ffdecb39-3427-5063-8bb4-3b1424d529e9 |  | note | - - - - - - - - -
label | 6a7980d8-eb97-5eb5-81d8-e630a96663e5 |  | note | Acceptance Criteria: 20mm Class 3 bedding material conforms to specified requirements applicable to the class of product as detailed on the drawings.
label | c9a7c89a-134c-5dfc-ab54-8219b2d0bebc |  | note | • Material is registered with VicRoads in accordance with Code of Practice RC500.02.
text | 477ad267-e765-52c9-96cd-812d885f3d56 |  | textbox | Enter: Teambinder Material Approval number
label | 22ee4344-ffba-5228-b826-41c01afc9a0e |  | note | - - - - - - - - -
label | 7c5b5029-93b6-5f41-9cc7-f85365bd2037 |  | note | Reference Documents: IFC Drawings 703.21 812.04
label | bc656808-5c3e-5df5-b018-19b90a582312 |  | note | - - - - - - - - -
label | 1eb0c545-0904-5b3d-a2c4-b6b61045d68a |  | note | Inspection / Test Method: Document Review
label | 8b8b0713-b4ee-5146-a1cd-8cca3a96334b |  | note | - - - - - - - - -
label | b1a0e9db-b0b2-5115-8787-cc497249296b |  | note | Record of conformity: Teambinder reference number
label | ce416f03-ee4e-5e98-8eeb-cf9a6d1d9b78 |  | note | - - - - - - - - -
label | 0ff38acf-f232-5b89-903b-c0c1e8ac277a |  | note | IP
label | 30357104-658a-5215-91a3-6bfd4e4e66f4 |  | note | - - - - - - - - -
label | 8f407237-8144-5354-a9b2-666727d74bc3 |  | note | Responsibility: Site Engineer Superintendent
checkpoint-status |  |  | checkpoint | 1.3 - Concrete Mix
label | da06a36d-d3b8-588c-90da-747127492591 |  | note | Frequency: Once, for each mix design, prior to placement of concrete
label | 71a03480-8fff-5bf7-905b-1e99875d09b3 |  | note | - - - - - - - - -
label | 9a8eb31c-c5d7-5411-9245-e5a7ab1d1a62 |  | note | Acceptance Criteria: Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings.
label | 0277912c-3d52-5789-bd76-2b3906d5e4e2 |  | note | • Paving concrete mix conforms to AS1379. SUP concrete mix is registered with VicRoads.
label | 79606b8c-0a6d-5938-a972-274ccb9a3659 |  | note | • No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
label | 022a1a03-dd8f-5c89-90de-850cd1ed47bd |  | note | • Concrete mix designs shall remain valid for 12 months from the date of registration, unless constituent materials and material proportions cease to comply with the specified requirements.
text | 5c75723a-37bd-5515-9177-ee98240e37c2 |  | textbox | Enter: Teambinder Material Approval number
label | 9116eeaf-701b-5aaa-880b-5cd158aba87e |  | note | - - - - - - - - -
label | d9106ef7-f1fa-536b-bc02-98e6cf214c7a |  | note | Reference Documents: IFC Drawings 703.05 (a) 703.07
label | e77803af-2a87-5cd1-8d99-2898ebcb4c32 |  | note | - - - - - - - - -
label | a65fe421-1113-5abc-b3de-91d21aafc04c |  | note | Inspection / Test Method: Document Review
label | b5d3de90-ea03-5907-a4ec-5bcd24d9a785 |  | note | - - - - - - - - -
label | 5ad3f1d4-a0ef-576f-9d67-1461c01acd19 |  | note | Record of conformity: Teambinder reference number
label | 75ee7403-9c29-5fe4-96be-d1b64994b213 |  | note | - - - - - - - - -
label | ef2f99f7-9def-5ad3-a617-347f2777fabf |  | note | IP
label | 77fd491a-d9cb-55d6-8690-32c605c234f8 |  | note | - - - - - - - - -
label | 850c6cca-b84c-52bd-84dd-25363af4d9e0 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 1.4 - Evaporative Retardant
label | d9f3b64e-d607-5c7d-bbd9-6c2595dbde77 |  | note | Frequency: Once, for each product, prior to placement of concrete
label | 07b515af-115f-5ee3-982c-84a6a022a68d |  | note | - - - - - - - - -
label | ea97d5af-bd02-5ba6-bb27-b64b5d57a61d |  | note | Acceptance Criteria: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
text | 01587371-86e1-5287-a8b3-78a818b657f0 |  | textbox | Enter: Teambinder Material Approval number
label | 7b6c002f-3e35-59d5-b01c-3d4c25913173 |  | note | - - - - - - - - -
label | 6a96cb4a-7f6b-52cd-858f-17b6333a2e3d |  | note | Reference Documents: 703.09
label | 78ea67fb-422f-5dea-8a6f-82c6c357e2e4 |  | note | - - - - - - - - -
label | 0b2a7192-f246-53b4-8d03-9abe064bce9c |  | note | Inspection / Test Method: Document Review
label | be8da57c-1885-5114-bf05-3d89eb92ad56 |  | note | - - - - - - - - -
label | c8f2d46b-6d90-5d93-b980-ff3b43b181a3 |  | note | Record of conformity: Teambinder reference number
label | 81c0ad6e-0806-5f23-ac93-cdbd19f0f9d7 |  | note | - - - - - - - - -
label | f65c2ac1-020a-5805-92aa-25d1976f1f8b |  | note | IP
label | 7bbc87a8-bdc4-55f2-b8a1-1d310407128c |  | note | - - - - - - - - -
label | 48b08975-edca-52ef-9ef1-2463ddec3f13 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 1.5 - Curing Compound
label | 1de96a0f-06bf-5de3-8e0c-dc283b92d9f6 |  | note | Frequency: Once, for each product, prior to placement of concrete
label | e8f09c26-fccf-5e6c-9aa9-deb30c226394 |  | note | - - - - - - - - -
label | 3916b31a-341d-585d-9539-81888c4c1552 |  | note | Acceptance Criteria: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
text | 5b13f73c-eed5-5f11-9265-b1fda4da6d1d |  | textbox | Enter: Teambinder Material Approval number
label | a23e027a-3f71-587a-89e8-6e1128725482 |  | note | - - - - - - - - -
label | 6e15d972-851e-504b-9278-92ee00620943 |  | note | Reference Documents: 703.10 (a)
label | 0b44f637-8a2c-5c7c-86c4-e970e72a8361 |  | note | - - - - - - - - -
label | 1cc5b3ee-8093-54c9-aa4c-7c4f56e698e4 |  | note | Inspection / Test Method: Document Review
label | 97588777-32a5-5da4-849b-5e516b9ae987 |  | note | - - - - - - - - -
label | f3c53191-3e2b-5d4d-8f83-7fffb2634b94 |  | note | Record of conformity: Teambinder reference number
label | 7c01548a-0fa1-55d7-96ee-6931298f881b |  | note | - - - - - - - - -
label | bbae6927-b4dd-5a20-a493-493c9de5b41e |  | note | IP
label | 61b3e519-d6e2-50d5-b7c4-180879855c36 |  | note | - - - - - - - - -
label | 65a5c324-15af-5a3b-8fc8-da33d04ed22c |  | note | Responsibility: Site Engineer
checkpoint-group |  |  | section | 2 - Construction Works
checkpoint-status |  |  | checkpoint | 2.2 - Temporary Drainage Provisions (if required)
label | d417ac57-e860-5e34-96b3-9a1896509f2a |  | note | Frequency: Prior to Commencing
label | bd1b96eb-1eb7-538b-bf88-f9a79302460b |  | note | - - - - - - - - -
label | 8ae64aeb-d2f0-533c-a5da-69046d0d043f |  | note | Acceptance Criteria: Before obstructing any waterway, channel or culvert, the Contractor shall make appropriate provision for its temporary diversion, and obtain prior written approval from the relevant waterway authority.
label | 825d2e34-802f-5cc0-83a2-3f0902b95093 |  | note | • The Contractor shall make provision for the safe discharge of drainage and stormwater at all times during construction.
label | cb4c477b-635f-54a3-bdbf-5451dfdd5844 |  | note | - - - - - - - - -
label | a111c4bd-70a3-5ecf-a8db-b7cb67665471 |  | note | Reference Documents: IFC Drawings, VicRoads Spec Cl.703.18
label | be520e0a-c6c2-55c0-83a7-6240136bb292 |  | note | - - - - - - - - -
label | cf243149-5c57-52bb-9472-4f2b4474ad29 |  | note | Inspection / Test Method: Site Inspection
label | 72fd8e00-2b81-5912-ad8e-d14b687935a7 |  | note | - - - - - - - - -
label | e23289b6-f8bf-579e-812b-33bd6039c095 |  | note | Record of conformity: Written approval from relevant waterway authority, ITP Signed
label | b523b06b-e005-53ca-b553-f1d892452abb |  | note | - - - - - - - - -
label | 7ed8032c-775d-52ee-9644-82165d515c3b |  | note | AP
label | 96f9af6b-404d-567b-8dba-d3a76fa25220 |  | note | - - - - - - - - -
label | 5008eb22-9294-503f-b0cb-0fa455d92eb5 |  | note | Responsibility: Supervisor / Site Engineer
checkpoint-status |  |  | checkpoint | 2.3 - Pavement Thickness Increases for Crossings
label | 43a8ca59-5bd5-533f-8e3f-b8c7be0b8818 |  | note | Frequency: Prior to Commencing
label | 2de765d8-c46f-5dec-8176-b4f634de8810 |  | note | - - - - - - - - -
label | 36ba0123-857b-52b3-94aa-0609afc072ff |  | note | Acceptance Criteria: Where applicable, excavation to allow for increase in the bedding and slab thicknesses at:
label | 9036ad8c-c582-58f7-8358-b384fbdd134e |  | note | i. Pram crossings
label | cde8086d-82a4-577b-afc1-1c10234e8a6f |  | note | ii. Vehicle crossings (residential and/or commercial)
label | 1559ac49-1bc2-5a28-976e-52d009034bab |  | note | iii. Established / existing mature trees
label | 9b9f562a-071c-516c-9dc5-651b34672142 |  | note | • Consult the Relevant Council drawings for dimensional tolerances for thicknesses, grades and ramp lengths.
label | 54db333a-02d2-5051-81b6-9f39065d74e3 |  | note | - - - - - - - - -
label | 2e61c20c-4baa-5363-99ae-adbcc5b216e4 |  | note | Reference Documents: IFC Drawings
label | b37c639d-91d4-5f05-8885-bcc961d9b03f |  | note | • VicRoads Spec 703.16 703.24 EDCM 401
label | bb4ddcaf-1822-5bf4-92dc-bf74b6544069 |  | note | - - - - - - - - -
label | ee33397e-677f-5d1e-af6c-ec2657a2d601 |  | note | Inspection / Test Method: Site Inspection
label | e78aba38-5652-5ecf-8622-a7ff22199fd4 |  | note | - - - - - - - - -
label | cd3b5de0-f55a-52b1-bd7f-4f6de83c9c4f |  | note | Record of conformity: ITP Signed
label | 446050c9-da3b-5d76-80af-b793fd3ecdba |  | note | - - - - - - - - -
label | 3b6c2b03-268a-5571-a123-1046eac86982 |  | note | IP
label | 78161c5a-30f5-527a-89f4-f7abdf712ec3 |  | note | - - - - - - - - -
label | 8fea581a-8a8e-5478-8020-782e659b5bb2 |  | note | Responsibility: Superintendent/ Supervisor / Site Engineer
checkpoint-status |  |  | checkpoint | 2.4 - Subgrade Preparation
label | 64e5b9bd-d6ad-5398-bc84-9b95081ec395 |  | note | Frequency: Each Lot
label | 7fd7a672-68b7-59ec-8a00-5a331c5fef97 |  | note | - - - - - - - - -
label | c54bd4d7-eaef-58a9-8b1d-4b8407615185 |  | note | Acceptance Criteria: Subgrade to be test rolled to ensure the substrate is adequate for bedding and concrete placement
label | 57e2cff4-02ae-51df-8704-6c49f19c3d41 |  | note | - - - - - - - - -
label | ec6c0569-5a3c-5402-9e59-0898c669b42b |  | note | Reference Documents: WP 011
label | 7623639e-02a0-5a48-9a40-5f9a3623b71c |  | note | - - - - - - - - -
label | 69e52aff-d7be-5386-9167-e31e9ce3437a |  | note | Inspection / Test Method: Site Inspection
label | 056135b0-a533-59f8-bebf-41cf56d50765 |  | note | - - - - - - - - -
label | 211a7b62-383f-5413-9d1b-61abba8c58d8 |  | note | Record of conformity: ITP Signed
label | c797a135-67a9-5238-a3c2-cef5f7528b59 |  | note | - - - - - - - - -
label | 0d692ccd-6683-5513-aafd-1454d2975d2e |  | note | HP*
label | 6d3cf941-32a5-55a4-acc1-7ce5b390d67c |  | note | - - - - - - - - -
label | a5cf9a95-080b-5ec3-9245-0fe64cda7768 |  | note | Responsibility: Supervisor / Site Engineer
checkpoint-status |  |  | checkpoint | 2.5 - Bedding Preparation
label | 797a6674-0891-5f84-8551-a8dc769e3152 |  | note | Frequency: Each Lot
label | e1dbcee8-9447-55e3-af52-62d51cc743e1 |  | note | - - - - - - - - -
label | 9f4aef2c-4a2a-5366-a641-ccfe9324a085 |  | note | Acceptance Criteria: All bedding material shall be as specified on design drawings.
label | c20c5a68-46ce-5d36-ae16-f6d14bb0f31f |  | note | • Where not specified, bedding material used for cast in place concrete paving works shall be compacted size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
label | 75c9e80b-ef79-55f3-bee3-da8affce1f3f |  | note | • Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface. Bedding to be compacted to 98% standard.
label | 8de39cbc-5818-57b5-9e05-e710c37060e2 |  | note | - - - - - - - - -
label | ee33a454-6a35-5849-addf-66c86bf70e9e |  | note | Reference Documents: VicRoads Spec Cl.703.21 812, 820
label | ec7db30b-e5f6-570c-9970-4122edbdbac7 |  | note | • IFC Drawings
label | 9932223b-4da2-53ad-9901-586955e06eda |  | note | - - - - - - - - -
label | 40fce6a7-0408-525f-9f02-7879542c673c |  | note | Inspection / Test Method: Site Inspection
label | 32b8172e-ba90-5819-8176-803557cc77c7 |  | note | - - - - - - - - -
label | 4e9ea9e1-ba13-544e-9246-dc0d60db8cc9 |  | note | Record of conformity: ITP Signed
label | 3630a1e3-f55d-5a10-b978-eb56a124927e |  | note | - - - - - - - - -
label | c9432e25-67c0-564b-b6e7-330397016dfa |  | note | IP
label | 6947c32c-bf7a-5e7d-afcd-5beee32f7d87 |  | note | - - - - - - - - -
label | dbe3aed5-9505-5ed8-88eb-1fdac88ac71e |  | note | Responsibility: Supervisor / Site Engineer
checkpoint-status |  |  | checkpoint | 2.6 - Formwork
label | 720db574-d1fa-5ef1-8f96-104014d42558 |  | note | Frequency: Prior to Commencing
label | 68ffc86f-2454-5658-925a-7ad086c6bca6 |  | note | - - - - - - - - -
label | ccc8d395-6e6d-569b-80b1-d43a1f5653b4 |  | note | Acceptance Criteria: Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
label | 09b173fd-475d-58b1-9fe6-6e76c12a0d47 |  | note | - - - - - - - - -
label | 14a6daaf-539a-567b-a62a-39ba37a95ab4 |  | note | Reference Documents: VicRoads Spec Cl.703.12
label | 9911084b-2f15-56c1-a547-7419025f20f6 |  | note | - - - - - - - - -
label | aaa3946f-4153-5af9-a69a-acc484a30efc |  | note | Inspection / Test Method: Site Inspection
label | be9e9181-d9f6-5d25-a14b-88e89c5a658e |  | note | - - - - - - - - -
label | d4acbd00-60d6-5e0e-95f0-b978e2ae7be7 |  | note | Record of conformity: ITP Signed
label | d9301a4f-4e25-56ef-b997-adf709f9161d |  | note | - - - - - - - - -
label | aee9a29e-1fa8-5ba6-b36b-ec76bfa5ef6b |  | note | IP
label | 65b007dd-a158-5461-b50f-db10291367ac |  | note | - - - - - - - - -
label | ae46a071-5bec-5cbc-81bd-8055c13f0756 |  | note | Responsibility: Supervisor / Site Engineer
checkpoint-status |  |  | checkpoint | 2.7 - Steel Reinforcement
label | a19484f8-58ac-5cda-967f-4542cb5c898f |  | note | Frequency: Prior to Commencing
label | 0e02a311-5206-5ffb-83f7-52200d0431f7 |  | note | - - - - - - - - -
label | 1bc23a12-a99e-5b1b-989f-8d59f024875b |  | note | Acceptance Criteria: Steel reinforcement shall be placed in accordance with drawings and AS/NZS 4671. If not specified, mesh shall be placed as per VicRoads Spec Cl. 703.16.
label | 4d69c18d-7812-5a71-9954-6ed1c571b104 |  | note | • The minimum cover of any steel reinforcement to the nearest concrete surface shall be 50 mm unless shown on the drawings.
label | f0d21b07-9369-5a28-a153-17be6c86bd0d |  | note | • Reinforcement shall be supported using either concrete or plastic chairs.
label | 9841d848-dd26-580c-b817-1882693ea8ed |  | note | - - - - - - - - -
label | 7b760cb7-dba8-5dba-a23f-84c6da11501f |  | note | Reference Documents: VicRoads Spec Cl.703.13 & Cl.703.13 AS/NZS 4671
label | 2c65f66d-2f33-53b2-a7dd-fc327ddca017 |  | note | - - - - - - - - -
label | dd1ee7f1-3028-5419-a20e-703506bbebf8 |  | note | Inspection / Test Method: Site Inspection
label | 00a202f6-fb21-5165-bd0f-0c44963558fa |  | note | - - - - - - - - -
label | accbfdd0-cf3e-5497-bc77-ab0078d665d8 |  | note | Record of conformity: ITP Signed
label | 13548bc3-b98d-5fad-95ff-9bd5174526a3 |  | note | - - - - - - - - -
label | 61f43437-ca20-546a-9eb0-833e74fa4e9b |  | note | IP
label | 4282b0c4-a5ea-5876-80ec-7c5e69450eef |  | note | - - - - - - - - -
label | 8cc0b8fb-4841-545a-92fd-64f94e097058 |  | note | Responsibility: Supervisor / Site Engineer
checkpoint-status |  |  | checkpoint | 2.8 - Pre-pour inspection
label | d77832c5-55d9-5b97-8f87-7cee6ebf6271 |  | note | Frequency: Each Lot
label | ae031f47-c9b8-56de-ace8-300ffcc26897 |  | note | - - - - - - - - -
label | 71d7391e-bbc8-55fd-857b-dac9e47ba582 |  | note | Acceptance Criteria: Inspection to ensure that forms, reinforcement dowels and other embedments conform to the requirements of the specifications and drawings.
label | fe104258-9f40-5765-a45a-443ba8cf50cd |  | note | - - - - - - - - -
label | 3a988b75-6e56-55a5-b59f-ffdcdc5fb193 |  | note | Reference Documents: VicRoads Spec Cl.703.05, Cl.703.09, Cl.610.17 (a)(b)(c)(d), AS 1379
label | e3964374-c89f-5dc5-b869-121c81588669 |  | note | - - - - - - - - -
label | a26539f6-29e7-5e98-95f5-f385c51c3937 |  | note | Inspection / Test Method: Site Inspection
label | fd6fea9e-4ebf-5ae4-9ec3-410f00b1acd1 |  | note | - - - - - - - - -
label | 44728309-138c-57be-ad98-5a1edc1f49f8 |  | note | Record of conformity: ITP Signed
label | 52d4b115-9a58-5aab-839f-3ae7fb56d19b |  | note | - - - - - - - - -
label | 78051ad9-5b9a-5fcb-a962-1ccd430f3447 |  | note | HP
label | 02f6ced4-3726-5699-8c68-1ff123d17027 |  | note | - - - - - - - - -
label | d9ea4fef-6f8a-5023-8709-6183d9e05fda |  | note | Responsibility: Project Engineer, Superintendent/Council & Surveyor
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.9 - Concrete Testing
label | 75adc7ba-bb70-56c6-920d-7c9ff50ed4c2 |  | note | Frequency: Each Lot
label | 694a0728-8c96-598a-9721-61bd455f3ef9 |  | note | - - - - - - - - -
label | 7212d104-0425-55c5-870f-3a8e4ad0c7eb |  | note | Acceptance Criteria:
label | e9e44750-a172-5db2-9303-206f473534b7 |  | note | ○ Concrete Testing Frequency:
label | 23973c37-6173-5bf8-897d-f62c3600227d |  | note | • 0m³ to 50m³ = 1 sample
label | 70bd7ebe-d691-5497-815e-cd45bef38927 |  | note | • Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum.
label | a00fd68d-ef8e-51ce-a5cf-74121d682a71 |  | note | • Compressive strength cylinders = 2 no. 28 day strength.
label | 45f32bb3-bc04-55be-bece-86e86b919894 |  | note | ○ Slump Testing Tolerances:
label | 9bf9121e-e24c-58f7-a5dd-323e6d73f6aa |  | note | • <60mm = ±10mm
label | 62f7fb59-93f5-5c21-82ee-b3ad7acebb63 |  | note | • ≥60mm to ≤80mm = ±15mm
label | b3f2f322-c7bf-511d-9120-5064c37ea97a |  | note | • >80mm to ≤110mm = ±20mm
label | 9a464dd2-66fc-5150-9428-0040771e712e |  | note | • >110mm to ≤150mm = ±30mm
label | 5ecc9baf-41eb-565e-949b-671a13bebf72 |  | note | • >150mm = ±40mm
label | 7016646f-9793-56b3-8375-6d518691faed |  | note | - - - - - - - - -
label | 7500100d-518a-5388-81ee-a1d5f7740264 |  | note | Reference Documents: VicRoads Spec 703.11
label | 0c9a26bc-7994-5109-be83-192059450c46 |  | note | - - - - - - - - -
label | e6bb22c3-35aa-54ff-922b-1967645a1ef8 |  | note | Inspection / Test Method: Site Inspection
label | a94ff21b-3484-55a7-9736-59b421aecd4d |  | note | - - - - - - - - -
label | bff58cc1-0ca0-56d5-9b93-5f1b4514988d |  | note | Record of conformity: Concrete Pour Record, ITP Signed
label | 4cb43fe9-671f-5158-8c4c-fe473875aa83 |  | note | - - - - - - - - -
label | 7540bb29-8d83-5eaa-9c43-78773331c80b |  | note | IP
label | e315771f-76d2-5411-a693-ab6160695049 |  | note | - - - - - - - - -
label | e5587377-54f3-5d16-9a86-ef0f3108fb32 |  | note | Responsibility: Supervisor / Site Engineer
checkpoint-status |  |  | checkpoint | 2.10 - Curing
label | 855f6610-543e-54a6-9dd7-b3a15eb27a1a |  | note | Frequency: Each Lot
label | a62314cb-297a-52b0-b6c4-4d85f5918a2a |  | note | - - - - - - - - -
label | c7bec2df-5b60-5c8b-b68c-2a44717f7ecc |  | note | Acceptance Criteria: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed and shall continue uninterrupted for a period of not less than 7 days after placing the concrete
label | 4a35ed38-f179-5b23-a3fe-96ee2bae4c20 |  | note | • Concrete shall be cured either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these
label | ac55d0c1-1653-5d14-be85-9bdbee911a37 |  | note | - - - - - - - - -
label | 76c36c46-7bf6-592c-a755-768dbec5ae49 |  | note | Reference Documents: VicRoads Spec Cl. 703.10
label | 671fce9f-1ee5-5bac-873e-cbdf54923834 |  | note | - - - - - - - - -
label | 29321499-9552-5827-b0a6-4dd8af9cf632 |  | note | Inspection / Test Method: Site Inspection
label | efbfa684-de87-5cfb-b779-4b90bbff7d9d |  | note | - - - - - - - - -
label | 1d7e76f5-2528-53c4-ab92-2bab88490823 |  | note | Record of conformity: ITP Signed
label | 88b6f185-a8c2-5529-b567-ab5208eccf22 |  | note | - - - - - - - - -
label | 59e5ebb2-4a42-5079-bd10-7eae5d25a731 |  | note | IP
label | be3fd892-47bf-5c7d-b666-058dbf1a8602 |  | note | - - - - - - - - -
label | ef2ecad0-26d0-5b71-aef8-0a686233df62 |  | note | Responsibility: Supervisor / Site Engineer
checkpoint-status |  |  | checkpoint | 2.11 - Tolerances
label | c366887a-2e05-5c2d-89c3-d711531351c9 |  | note | Frequency: Each Lot
label | b671cd5d-3f7b-5b97-9c14-8544dc4af575 |  | note | - - - - - - - - -
label | 79cf5380-cdca-55ec-93a6-6f31f49e386f |  | note | Acceptance Criteria: Concrete paving to match existing fixtures (e.g. pit covers, edgings and vehicle crossings) within 5mm.
label | 1d2055e7-9291-5506-a076-51a0bd518c98 |  | note | • Deviation of finished work shall not exceed; 10mm from line or level; or 5mm from a 3m straightedge for curves and shaped areas.
label | 31c4fba5-c796-58e3-9a62-c09d66b146c2 |  | note | • Deviation of section dimensions shall not exceed 5mm (except for overall width); 25mm for the overall width; and +/- 3mm for dimensions less than 25mm.
label | 4d9cef40-554b-504e-9d69-b5c04d03c008 |  | note | - - - - - - - - -
label | a0233f58-4dda-50bd-b2d8-7774b754219e |  | note | Reference Documents: VicRoads Spec. Cl 703.15
label | bb4033ef-5327-5821-af06-c1afa1228504 |  | note | - - - - - - - - -
label | 4392b5ef-9cca-5b5a-b38f-bc63b2a5b596 |  | note | Inspection / Test Method: Site Inspection
label | dd2655cc-cc56-5f5f-a5cc-fa02458090a5 |  | note | - - - - - - - - -
label | ac6c00a8-c118-5043-9a24-51ecd6d6fc21 |  | note | Record of conformity: ITP Signed
label | aee03a08-7ab3-5431-986a-e61d70edf531 |  | note | - - - - - - - - -
label | 1371d305-96d1-5acf-a8c8-2b59630e1094 |  | note | IP
label | 614740e6-1516-5643-a8b4-0c054e01e82b |  | note | - - - - - - - - -
label | bf381db7-acbd-5dc6-a463-d33a927ffdc5 |  | note | Responsibility: Supervisor / Site Engineer
checkpoint-status |  |  | checkpoint | 2.12 - Joints
label | 311fad84-98d2-598c-983f-e4feee1f560a |  | note | Frequency: Each Lot
label | 34cf4ab9-8409-5ac4-9961-9483cc84aa8d |  | note | - - - - - - - - -
label | 9e8c7f23-a312-5a20-a861-4f62d8667692 |  | note | Acceptance Criteria: Expansion Joints: shall be placed at intervals as specified by the drawings.
label | 0bc675b7-ff69-5a9a-b5b2-ec79bf368b2d |  | note | • Control Joints: at least 25% of the paving thickness deep and 5 mm wide shall be formed with a cutting tool at 2.5 m intervals along the full width of footpaths, other surfacings and shared use paths.
label | 3cbfb09f-fa91-5ae9-ab24-384b3e0630b1 |  | note | • Between Concrete Paving and Shared Use Path: Except for medians <2.0m wide, bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt (ableflex).
label | 9cbf7f9c-2ffa-5d52-be55-3e79876581b5 |  | note | - - - - - - - - -
label | d11a5f9b-18bb-53f6-8a46-ba0b649af821 |  | note | Reference Documents: VicRoads Spec Cl. 703.26 (b)
label | 35f19ae0-6129-54d4-b8b8-e7cba5e2ffd4 |  | note | - - - - - - - - -
label | 1e3f27e6-d7fb-536b-b6fe-8a5f0f503a02 |  | note | Inspection / Test Method: Site Inspection
label | 91e58e28-d2a2-59f8-819b-c770ff9acbea |  | note | - - - - - - - - -
label | b4db6cea-0074-55da-8be3-467fb5c2ae61 |  | note | Record of conformity: ITP Signed
label | 033b4157-48db-5f99-b87f-82322d64fe20 |  | note | - - - - - - - - -
label | 7e876d85-c786-52d6-acec-81a15967a7e4 |  | note | IP
label | bb4ba5d6-737b-5b4e-bf74-90e8c1af6851 |  | note | - - - - - - - - -
label | 9838584d-e82a-5891-8eb8-650e9d7098be |  | note | Responsibility: Supervisor / Site Engineer
checkpoint-status |  |  | checkpoint | 2.13 - Stripping Formwork
label | 1d61756b-940f-547a-8388-dafa2febca6b |  | note | Frequency: Each Lot
label | 85fef905-2687-57d7-98b0-370cb00b7ec1 |  | note | - - - - - - - - -
label | 0a733d20-7673-55bb-ae65-046511399041 |  | note | Acceptance Criteria: Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
label | dee02d83-1166-5408-92b4-dcaaafbaefa4 |  | note | i. 2 days for vertical formwork on external surfaces; and
label | 23d4bc26-e258-5188-b0f6-86f59a791d01 |  | note | ii. 1 day for vertical forms on permanently hidden surfaces
label | a6652543-003b-59bd-b27e-10831489c387 |  | note | - - - - - - - - -
label | b52adc98-5e8e-5ef9-81fa-4381b677bf55 |  | note | Reference Documents: VicRoads Spec 703.12, AS3610 Table C2
label | e5badc1c-d953-5c17-ba1d-016a52d36435 |  | note | - - - - - - - - -
label | 6520901c-5d12-5c84-be7f-76bc223d80b6 |  | note | Inspection / Test Method: Site Inspection
label | b205bdb5-59b2-56d4-9ba6-8bc395fa55a5 |  | note | - - - - - - - - -
label | 81f7e58d-cdbb-5a48-bc36-db490a7815a3 |  | note | Record of conformity: ITP Signed
label | 40454dcf-c358-5041-b04a-39bd82fcb04f |  | note | - - - - - - - - -
label | acc6f36e-cbb7-5c20-ba98-3b76d5d6f1c6 |  | note | IP
label | 02b95ad8-8942-5d7c-8c18-0a6ce363d03d |  | note | - - - - - - - - -
label | 8b1b670d-0081-54ed-9917-057686da4d25 |  | note | Responsibility: Supervisor / Site Engineer
checkpoint-status |  |  | checkpoint | 2.14 - Protection of Newly Poured Concrete
label | 3c66bc04-7450-5c5d-803c-8bd750ded3d5 |  | note | Frequency: Each Lot
label | 634172b8-eaaf-517f-ac07-d0bd5cf1e8bd |  | note | - - - - - - - - -
label | 515df587-dd1e-544a-aaa7-64e1b7b7b21c |  | note | Acceptance Criteria: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
label | 38c0d659-96f4-5b3f-8df4-a0dd7bfc43c8 |  | note | • Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
label | 097ccfa4-7b54-562b-af70-f7934ac360ce |  | note | - - - - - - - - -
label | ce50c730-e35d-5759-8c02-d80290a439d3 |  | note | Reference Documents: VicRoads Spec 703.27
label | 3edbe754-6596-5b4b-978d-0e55705f2db5 |  | note | - - - - - - - - -
label | 626eaeba-6741-5de3-83c7-a5b27af6e832 |  | note | Inspection / Test Method: Site Inspection
label | b6259f68-b48e-5a0e-937d-e3a26d56ca19 |  | note | - - - - - - - - -
label | f3ac16de-88a4-5357-99e7-30a9e9e14dcd |  | note | Record of conformity: ITP Signed
label | 9c31e9e3-6b91-5f1d-8528-802815f61f4c |  | note | - - - - - - - - -
label | fe2f345f-bbb5-5935-9ffe-85f7f512505b |  | note | IP
label | 3ad24805-bf2c-5e24-a0f0-b393a50c8ec8 |  | note | - - - - - - - - -
label | 62321f86-07a1-55a7-bb09-276c2ecbc486 |  | note | Responsibility: Supervisor / Site Engineer
checkpoint-group |  |  | section | 3 - Post-Construction
checkpoint-status |  |  | checkpoint | 3.1 - Survey data captured for as-built purposes
label | 27052ef7-6ed0-59a4-80ef-2fb5eb3aef5f |  | note | Frequency: Completion of each lot
label | 603d23ad-8e52-5670-9159-d7da91e68bf5 |  | note | - - - - - - - - -
label | 1d5bd2d3-9fca-5c73-86a8-3da68d1575dc |  | note | Acceptance Criteria: Survey to ensure and validate that all works meet level and location requirements.
label | 487aa9fe-7639-5235-ace5-553cb92862fa |  | note | • Review of existing survey control marks and any additional control marks providing verification of conformity of as constructed features with design.
label | e1d6623d-cefe-549b-bc53-4fb7cd928807 |  | note | • As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
label | 724443b0-34d7-5064-8c69-c3f1da4e3ff2 |  | note | - - - - - - - - -
label | 12b619b8-a78d-52a5-a415-1c66cd396182 |  | note | Reference Documents: IFC Drawings / survey records
label | c24e033b-bea9-599f-beb4-17084bfeab33 |  | note | - - - - - - - - -
label | ca853635-4ea2-54cd-a770-c6a3a35a9e76 |  | note | Inspection / Test Method: Document review
label | 397e293f-af65-5c79-a0aa-26027c04f2c8 |  | note | - - - - - - - - -
label | 38a2c532-83e4-58bf-8849-405ebce661e7 |  | note | Record of conformity: As-built survey records
label | 63cf10ee-383a-54e3-9614-5a40f8c5145d |  | note | - - - - - - - - -
label | a4bffba9-7714-531a-9154-87392fbd6a27 |  | note | SCP
label | 3b3119d7-f9b0-5db4-bae8-e51f8fa410f0 |  | note | - - - - - - - - -
label | 822e1dda-60ef-5e27-ad43-a55d55913543 |  | note | Responsibility: Project Engineer
checkpoint-status |  |  | checkpoint | 3.2 - Cracking of Concrete
label | d90ecc67-f4c1-5ff5-8d0f-3b37da3eb7b4 |  | note | Frequency: Each Lot
label | 78806adb-1cb6-597b-b0e2-5a076834efc2 |  | note | - - - - - - - - -
label | 34181c44-6dbb-548d-98ad-41c3224318ce |  | note | Acceptance Criteria: The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm.
label | a5a67ae3-04c9-5a02-9d87-16c0f5471760 |  | note | • Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
label | 4e1e77c7-5944-54b8-add6-689f528505e3 |  | note | - - - - - - - - -
label | 5465394a-fc06-5d3b-b95c-0e9a9483c901 |  | note | Reference Documents: VicRoads Spec. Cl. 703.30 687
label | bcda19e5-3e03-5f0d-8656-87b717c26ebd |  | note | - - - - - - - - -
label | eb740f0f-a8d9-5d10-9364-95fa3c62bf5d |  | note | Inspection / Test Method: Site Inspection
label | 79eba09b-140b-5cff-b380-a9402be46d24 |  | note | - - - - - - - - -
label | 253d0431-745a-5d47-ada0-c9b554d3bf80 |  | note | Record of conformity: ITP Signed
label | 341ba66d-fa69-51b8-b93c-6a3aef9fd1d2 |  | note | - - - - - - - - -
label | f8119a01-fbad-567c-b2a7-1cc708d353a4 |  | note | IP
label | 06ede263-5026-5f78-8e34-9f8cf070f1da |  | note | - - - - - - - - -
label | a8a97725-7308-5bab-a943-5a270791e03b |  | note | Responsibility: Supervisor / Site Engineer
checkpoint-status |  |  | checkpoint | 3.2 - Compressive Strength Test Results
label | 590fc6b9-1789-55a1-a24f-d9ed68c23f0b |  | note | Frequency: Completion of each lot
label | ce95fabf-3846-54bf-af02-ddf0400a5c92 |  | note | - - - - - - - - -
label | 395b87eb-a092-525d-90cf-996be51805c0 |  | note | Acceptance Criteria: 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | 5576493a-8004-51b0-93c5-02fae38f99ee |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | 3b3dfc5c-a997-5388-9abd-0edd3ba0bae8 |  | note | - - - - - - - - -
label | ea857fc7-80a3-59db-9917-5bc31bac9c40 |  | note | Reference Documents: IFC Drawings, Relevant Council Drawings 703.11, Table 703.111
label | d2769744-2b10-5c6b-9a6f-b9e7a7d2a5a4 |  | note | - - - - - - - - -
label | 57da2188-21e6-5b25-a621-8200acad75e8 |  | note | Inspection / Test Method: Site Inspection
label | e0a13b38-f4d1-5eaa-bc80-ba6bc6b05012 |  | note | - - - - - - - - -
label | bf426bb7-3d34-5eaa-b9fc-554ea98a669b |  | note | Record of conformity: Attach: Compressive Strength Test Results
label | c980960b-8ed7-5dd6-bd6d-765c11c5d364 |  | note | - - - - - - - - -
label | 0941626f-42d6-56dc-9f88-141bf10c75e1 |  | note | IP
label | 3fb343f8-1876-5090-afd5-da891fd48c11 |  | note | - - - - - - - - -
label | 18820e57-455c-593e-9082-ad4606c79af9 |  | note | Responsibility: Supervisor / Site Engineer
checkpoint-status |  |  | checkpoint | 3.3 - Backfilling
label | e4b9dbad-9577-5a02-95c9-3d80830df664 |  | note | Frequency: Completion of each lot
label | 4d228298-322f-5995-99af-2b2226d0c293 |  | note | - - - - - - - - -
label | 37dfdafe-34d0-56a7-ad6d-c2367adb9c84 |  | note | Acceptance Criteria: Where required, as soon as concrete has cured sufficiently and not earlier than three days after placing, topsoil shall be placed and firmly compacted in layers not exceeding 150mm and to a width not less than 300mm behind the edging to the top of the edging.
label | 27cac322-cc4c-57c2-a889-c2ad11b2e464 |  | note | - - - - - - - - -
label | 86f37c64-9e07-56b7-b5c3-9c636a62a6c8 |  | note | Reference Documents: VicRoads Spec. Cl 703.29
label | 78f7973e-fc41-50fd-bfff-e2516b940613 |  | note | - - - - - - - - -
label | 71356e09-63e4-55e1-ae54-f9d1620f3f40 |  | note | Inspection / Test Method: Site Inspection
label | 79db8794-b43f-5943-aac0-3a37a219e1fc |  | note | - - - - - - - - -
label | ba6f7120-d309-589f-8550-b1fcaa56fd2c |  | note | Record of conformity: ITP Signed
label | 7ec71a18-632f-57d3-8677-f2471898af79 |  | note | - - - - - - - - -
label | 703b6938-0ea4-5959-903d-1e8b4d6e974f |  | note | IP
label | b35ac524-520c-5f54-9240-b8e43123680c |  | note | - - - - - - - - -
label | 1e10b170-b54e-5ffb-860d-23e28a0a8ffc |  | note | Responsibility: Supervisor / Site Engineer
checkpoint-group |  |  | section | 4 - Completion
checkpoint-status |  |  | checkpoint | 4.1 - As-built Survey
label | 6e95023a-b2e6-5d71-83dd-8ff5abad8767 |  | note | Frequency: Completion of each lot
label | 936c1ff6-8bfb-5c99-8a09-929cd05e2327 |  | note | - - - - - - - - -
label | 508ffa0b-f46b-5972-92e2-80550900c99b |  | note | Acceptance Criteria: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
label | 3018657e-50bc-57aa-bf8e-44e3703f4b76 |  | note | • Departure from RL = ±10mm
label | 8c487d4d-0ec9-528d-aae8-974c410d9138 |  | note | • Departure from alignment = ±10mm
label | 18cd95f2-5932-54c4-b315-528b08653b18 |  | note | • Rate of change of deviation from RL or alignment = 10mm in 10m
label | 3feabb21-6029-5203-a648-d004bb3458be |  | note | • Irregularities in alignment = 5mm in 3m
label | b91c80a8-4413-5f5d-aa7a-ad03ce59db59 |  | note | • Section dimensions = ±5mm
label | 63bd660f-1ce7-5e80-8d3e-6cd31a37646a |  | note | • Section dimensions (less than 25mm) = ±3mm
label | 0ecf98e6-3fc9-5f46-a28f-972ee3997576 |  | note | • Width of pavement = -5mm, +15mm
label | 57f8beaa-55f3-5492-a10f-b741d4c6d0e5 |  | note | • Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a crossfall between 1% and 3% towards the edges.
label | fe3a9a69-863e-5ec5-9069-f110777dd555 |  | note | Attach: Survey As-builts / Survey Report
label | 4b176fb4-429e-5998-ae0f-b71c79b4457c |  | note | - - - - - - - - -
label | 57a161f1-35ce-5a57-9b01-07e08083302c |  | note | Reference Documents: IFC Drawings, VicRoads Spec 703.15
label | f7cfccb1-227f-5b44-ae66-40b1a2af0579 |  | note | - - - - - - - - -
label | 1a6e2f0e-b6f7-56b7-8338-e6970ae54780 |  | note | Inspection / Test Method: Document Review
label | 251a41c5-a272-5557-b8aa-6b9897073756 |  | note | - - - - - - - - -
label | 4ef3d4d9-f70b-554a-8f5b-b1065de5d905 |  | note | Record of conformity: ITP Signed
label | 9bd1cd65-bce1-5340-a120-d0c529128fc2 |  | note | - - - - - - - - -
label | d6f07da4-0972-500b-a216-4c19804f172d |  | note | IP
label | 8575fd9d-2e30-5e23-a8e0-d9f83058edbc |  | note | - - - - - - - - -
label | aa8b75c9-d015-569d-87ce-4b36f29325ff |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 4.2 - Red-Line Markup
label | a2236011-65fc-55cf-a3f8-e61eed4beb8f |  | note | Frequency: Completion of each lot
label | 66764df0-e996-5ee9-be66-115ab0db0edf |  | note | - - - - - - - - -
label | e1b9319e-1396-5a0b-825e-3395d96c304c |  | note | Acceptance Criteria: Capture any changes in design or RFI's as per approved red-line markup procedure
label | 3b1a9e0a-c379-50b4-ab1c-2f5cb7d67895 |  | note | - - - - - - - - -
label | af1cdd70-752c-5847-ac9c-0156868f13c4 |  | note | Reference Documents: Quality Management Plan
label | f121c69e-9a43-5c7f-8442-7c7996529832 |  | note | - - - - - - - - -
label | 63a618fd-b845-5f78-b932-d95b05b64d8f |  | note | Inspection / Test Method: Document Review
label | 7d7ba3be-79fb-59aa-a496-1a3544caece9 |  | note | - - - - - - - - -
label | b6a349c4-5012-58da-90f6-79eb71e59308 |  | note | Record of conformity: ITP Signed
label | 9f9a2261-a1c5-53dc-8a5e-73228bea2c5a |  | note | - - - - - - - - -
label | 34c579c8-9151-59f4-aede-3554ee5da675 |  | note | IP
label | 32a0908e-cc56-582a-96fe-370ade1b3bcb |  | note | - - - - - - - - -
label | c9012f92-1693-5010-808d-4cb9f782f262 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 4.3 - Non-conformance Report (NCR) Closure
label | f2e73706-27f8-548f-9f9d-dfe66ce16df6 |  | note | Frequency: Completion of each lot
label | ae102f42-43a2-58cf-b50a-1bbd42648e67 |  | note | - - - - - - - - -
label | 328d5e9a-b766-545f-9149-460a5fb8c66c |  | note | Acceptance Criteria: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 2f4422c8-06fa-5b8f-ac5c-88622433cad3 |  | note | - - - - - - - - -
label | f77214bf-495f-5a70-a6d5-fcfe1c7264bd |  | note | Reference Documents: Quality Management Plan
label | f4b253d9-6515-5236-b0b7-eb8865b90a7e |  | note | - - - - - - - - -
label | a87f6fdc-86cc-5d59-84a5-f5e94e079220 |  | note | Inspection / Test Method: Document Review
label | 2779e04e-b5d2-5693-ba14-de350c25beec |  | note | - - - - - - - - -
label | 9ecb401a-78fe-585a-a938-e8bf8a968709 |  | note | Record of conformity: ITP Signed
label | 2bfe4b42-6b66-5725-acb5-abff25031941 |  | note | - - - - - - - - -
label | bbe6e287-5a91-5a47-9277-719522c48763 |  | note | IP
label | cc99dbe1-b2ff-5619-a62b-7a12b3890d01 |  | note | - - - - - - - - -
label | 4699245a-206a-5eb2-91e4-2e48568a0f7d |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
label | a90a4b3b-7a67-58e9-97dd-51cdb1f08e83 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | a6b5f8ad-f262-563e-bae4-49f3fd31fdc5 |  | textbox | Name:
text | 1bd4fe32-6509-54de-b24a-da4947a2da7e |  | textbox | Position:
date | 7357d833-089d-53c6-a24e-e6dc8f6f24bb |  | date | Date:
date | dece111a-2149-5168-9aa4-da46e1dc8815 |  | date | Work Completed On
holdpoint |  |  | signoff | Add Signature
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification.
select | 41ef9a07-8c10-5ba8-b45d-98605709e6e0 |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | f7224814-d788-5dc9-9f3b-054aa91d1d1c |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | 09903ef5-7779-56eb-9c1d-2ca5f3442f0e |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | 529ad8e9-bc1c-555e-99e5-4610a8c33a50 |  | dropdown | Lot verified By | Babak Rudd (Quality Manager),Abid Hameed (Area 1 Manager),Nicola Lodo (Area 2 Manager),Nicholas Terpstra (Delivery Manager),Other:
text | 0076f82c-6acb-50dc-a2ee-745026f0e166 |  | textbox | Other:
select | f5846d7f-2234-5451-b862-1883aa8710c1 |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | f88c82fe-633a-5223-805e-64c7fb50e22d |  | date | Lot Closed On
text | 0dc2df05-4d69-551d-a816-177623ceb8d9 |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-063-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0063 - PERMANENT LINE MARKING | ef4e3052-d979-4368-98c5-f3636ee15c58
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | 07e410e8-6cbf-53ab-8e6e-2f09845997c3 |  | date | Lot Created On
date | 670140b7-a44e-58a8-837d-0af50d34e36b |  | date | Lot Opened On
date | ea46a9ee-a8bf-51f2-a45d-16da1138f0bc |  | date | Work Commenced On
select | 1d676cd6-d000-5df9-9476-31802e9cbac4 |  | dropdown | Lot Type | CIL - Civil Lot
text | 09e7484d-1594-5e69-b167-e8304a691dd1 |  | textbox | From and To Chainage
select | 333801fd-4e44-5db0-9d2c-7fea91b0539f |  | dropdown | Construction Element | SIGN - Signage and Pavement Marking
select | 51c5a0c7-7c16-58ef-bf65-1f268c5442c2 |  | dropdown | Activity | LINE - Line Marking
select | a8df422b-867d-597e-9b5d-b2219fef6c2e |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | fd48bbb7-985d-55b1-a688-5024b690b58a |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | 0ce645ef-0e85-545e-a148-971a2970a0eb |  | textbox | Engineer Responsible
text | d273752e-7284-56c0-8589-47063da38533 |  | textbox | comments
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 Inductions
label | e74dd060-62b8-5f45-8700-ce88d7a78d70 |  | note | Frequency: Prior to Commencing linemarking works
label | 99f75bac-81c9-5515-a0b3-62445801bbcb |  | note | - - - - - - - - -
label | 4a9efcbe-acd8-5d57-acd2-1bc5a890ed12 |  | note | Acceptance Criteria: All personnel on site have been inducted to the CRU Site.
label | 154b32b7-e2f3-53ce-87b9-3db335a43d4a |  | note | - - - - - - - - -
label | 144e2ccd-8487-528b-983a-5f9d72aaa2c4 |  | note | Reference Documents: Inductions Register
label | f3afdfad-8818-5944-a4e5-ef4bfc7289f1 |  | note | - - - - - - - - -
label | 8c4b6fbb-90be-50f2-98d5-51bd0223cd2c |  | note | Inspection / Test Method: Document review
label | 403909a0-a9bc-5c43-a83a-f0e0570b7656 |  | note | - - - - - - - - -
label | 0b6f107e-6c14-5dc7-bb1a-0d4b652886c4 |  | note | Record of Conformity: ITP signed, Site induction signed.
label | 654ae767-d932-5497-ac98-2b62dfbbf1cb |  | note | - - - - - - - - -
label | 162a86f7-5aee-56e9-9e00-fb14843c1831 |  | note | IP
label | e1687f23-6575-5224-b1ad-aefcf39d6309 |  | note | - - - - - - - - -
label | 6b3c125d-b62c-5d7c-9079-20abbe9733be |  | note | Responsibility: Site Engineer / Site Foreman
checkpoint-status |  |  | checkpoint | 1.2 Safety measures are in place, SWMS undertaken
label | c765cfc4-9009-59b1-90f9-e7fe6f619cc9 |  | note | Frequency: Prior to Commencing linemarking works
label | ce51ee83-26d0-5918-bfe9-45534f295c3f |  | note | - - - - - - - - -
label | bf618fee-336d-5962-81c0-00b646b881f0 |  | note | Acceptance Criteria: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
label | 7e13eeb4-37aa-5fe4-86ed-7e213111ca69 |  | note | - - - - - - - - -
label | 5edd80f2-1844-517c-801b-99737ab2d784 |  | note | Reference Documents: Health and Safety Co-Ordination Plan
label | 5a4214d2-e1da-50b5-a83a-2a100c30ff8d |  | note | - - - - - - - - -
label | 83017589-cba6-5789-bdd3-f938713b1628 |  | note | Inspection / Test Method: Document Review
label | 0fea00ed-3a9f-5c83-a49b-5773909284ea |  | note | - - - - - - - - -
label | aa18529c-ff19-5400-ac37-6cedbfec44f0 |  | note | Record of Conformity: ITP signed, SWMS(s) signed
label | 027333f3-e18d-540b-ba45-6c68d5154b6d |  | note | - - - - - - - - -
label | 5bfc0219-19af-520c-ab4c-27e3af2386f2 |  | note | IP
label | 24711503-b767-51a5-8d0b-35541c5a4a97 |  | note | - - - - - - - - -
label | 7efdaf0f-fd9f-573c-81a1-513550d11691 |  | note | Responsibility: Site Engineer / Site Foreman
checkpoint-status |  |  | checkpoint | 1.3 Check that current revision drawings are being used
label | 23301dd8-bf27-5b4b-b1c1-54a871e5dada |  | note | Frequency: Prior to Commencing linemarking works
label | d79011cc-2ca7-58bc-aef0-75ff756c6e86 |  | note | - - - - - - - - -
label | 9d5fe02b-94b0-5d57-9a26-15632cc208cf |  | note | Acceptance Criteria: Issued For Construction (IFC) drawings, & latest available revision used.
label | 0b74e196-1c81-5e5f-b9a1-2e774dc3a815 |  | note | - - - - - - - - -
label | 756d3e7e-3246-5301-8256-dfc413efd461 |  | note | Reference Documents: IFC Project Drawings, PS3070.04, PS3070.06
label | 67c75924-2b8e-5cc6-b660-8a90b0f49b21 |  | note | - - - - - - - - -
label | fff9f221-eb89-50ad-81bf-2a3d1904b82d |  | note | Inspection / Test Method: Document review
label | 887f20ba-d83c-5f8f-9da4-0ae34085fcd2 |  | note | - - - - - - - - -
label | 1dcfb743-75b7-5947-b65d-1950138af162 |  | note | Record of Conformity: ITP signed, Latest revision IFC drawings
label | edc20b56-26c7-51a5-9f6a-d806b7fcf536 |  | note | - - - - - - - - -
label | c7f52a88-4450-5bce-88ee-bd3c5b86c2a3 |  | note | IP
label | d0cb25b0-03bc-583d-b20a-bea0238ec261 |  | note | - - - - - - - - -
label | 0481b885-f675-538d-9e47-1383699e675b |  | note | Responsibility: Site Engineer / Site Foreman
checkpoint-status |  |  | checkpoint | 1.4 Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
label | 20339aad-2e1b-5cf5-aad5-e13f97a8cc95 |  | note | Frequency: Prior to Commencing linemarking works
label | 3dd23bf5-8694-5803-b4fa-560da1a2f7ef |  | note | - - - - - - - - -
label | aec4bf5c-0eb5-5956-a999-e6eaa3a351f8 |  | note | Acceptance Criteria: All environmental measures to be implemented as per construction environmental management plan
label | 6a0384a2-0979-50e8-91ad-90b531a3612f |  | note | - - - - - - - - -
label | 63e8c685-8b69-51f9-837f-33a6873b3b1c |  | note | Reference Documents: CEMP, Site induction, PS1200.03
label | 73ea91bc-be6c-51fe-a8c6-84cbca8fcb83 |  | note | - - - - - - - - -
label | 200c45e9-3486-51d5-a0d0-bb51837ba828 |  | note | Inspection / Test Method: Document review & Site inspection
label | 0c009fa7-4067-5408-a7e4-670a307250a9 |  | note | - - - - - - - - -
label | 7b45fc2d-c58c-5c03-b525-84cde799960d |  | note | Record of Conformity: ITP signed
label | 0dea83ea-1428-50b8-b391-adafddc044ed |  | note | - - - - - - - - -
label | fcd1b6b6-d548-51e4-b48a-43dbf9d9f0b9 |  | note | IP
label | 9aba0f7d-80cd-5e59-8b40-359581ba41ce |  | note | - - - - - - - - -
label | bead2ab8-91ec-5e60-a0ee-384a5f172ca4 |  | note | Responsibility: Site Engineer / Site Foreman
checkpoint-status |  |  | checkpoint | 1.5 Traffic Management (When required)
label | d5a85e83-b97e-5117-9533-0b5880840650 |  | note | Frequency: Prior to Commencing linemarking works
label | 30c0d654-e313-5481-88da-8886c1d1d346 |  | note | - - - - - - - - -
label | 0de79d21-1222-54cf-8b35-c7d500adbfd9 |  | note | Acceptance Criteria: Approved TMP and MOA in use
label | 9e548b65-2830-52bb-8068-1da42eb0e685 |  | note | - - - - - - - - -
label | 1c3e95a3-5436-59c1-b06f-62d18d46a699 |  | note | Reference Documents: Applicable TMP, PS1160.012
label | 2387a6a7-f459-5c9f-956d-ccee4b7fd636 |  | note | - - - - - - - - -
label | 8a59c311-09ee-5b70-bc6a-e5262075ae35 |  | note | Inspection / Test Method: Document review & Site inspection
label | 1981540c-8d1b-5668-88b9-727cd18ea35f |  | note | - - - - - - - - -
label | 78052009-a992-5daf-aaca-b9f34f0cf0a7 |  | note | Record of Conformity: ITP signed, Approved TMP & MOA
label | cdddf0d3-be55-579d-a380-3cae1d2a644b |  | note | - - - - - - - - -
label | 9fe075e4-92b7-516c-996e-8edd6bbbe4b7 |  | note | IP
label | 31e9b8ed-2185-5d1d-afc4-005b9a7a0934 |  | note | - - - - - - - - -
label | 09aacc33-0f58-5377-9b50-761d56c2c2a1 |  | note | Responsibility: Site Engineer / Site Foreman
checkpoint-group |  |  | section | 2 - Linemarking Works
checkpoint-status |  |  | checkpoint | 2.1 Verification of line marking material
label | cd6165de-1da4-53e0-aa06-6e335b5ec8ff |  | note | Frequency: Prior to commencing site preparation
label | 2da26fd0-2d80-53a8-a2c2-548cab8638f8 |  | note | - - - - - - - - -
label | 84fc3360-be3d-5583-b41e-08c352b992f4 |  | note | Acceptance Criteria: Line marking material to comply with minimum requirements as specified in VicRoads Spec 721.A05, VR721.A13, VR721.A14, & PS3070.05
label | de157f38-3119-5e46-9187-af62e6184992 |  | note | - - - - - - - - -
label | 07142f6e-2677-5a50-af43-ebfdde29234f |  | note | Reference Documents: PS3070.05, VR721.A05
label | b0b376cb-8c67-5731-baa3-6b5be90df8a5 |  | note | - - - - - - - - -
label | 0d4bbd8c-5f6c-5c51-9543-b2ef5db5a019 |  | note | Inspection / Test Method: Document review
label | f49fd26d-4ad7-5ca0-b196-648a676d61d0 |  | note | - - - - - - - - -
label | 2c7c5b77-cabd-54b4-9584-10a59702219b |  | note | Record of Conformity: ITP signed, Material compliance
label | a5c9d3be-c645-557f-b9a8-c2ba1da5bfda |  | note | - - - - - - - - -
label | 57d8bc64-f25f-53c4-9332-b3af84e35310 |  | note | IP
label | 616c584c-c1f9-5e79-aa9c-9f2eb237934c |  | note | - - - - - - - - -
label | 9bf3159e-122a-56b4-ace5-6c785b69530b |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 2.2 Site preparation
label | 477b0f27-181b-5122-ad09-d0e774a0fd7d |  | note | Frequency: Per lot
label | 88175f51-a273-5064-bbb8-f5789e8e0553 |  | note | - - - - - - - - -
label | 223226aa-6d5f-56bb-99b0-1faba03acb91 |  | note | Acceptance Criteria: Site to be prepared by removing any foreign materials and debris within reasonable limits.
label | 7bd2000c-ada9-5468-b877-ec11938d319c |  | note | - - - - - - - - -
label | 90733091-a2ac-55db-b052-d746426f5b32 |  | note | Reference Documents: PS3070.07C, VR721.A06, VR721.A08
label | eef74902-eba2-5d17-890c-ac6a18098041 |  | note | - - - - - - - - -
label | 53952b6e-1ac8-52a0-8ac4-5dfcf52c9259 |  | note | Inspection / Test Method: Document review & Site inspection
label | a1f881e9-1695-5f14-a2eb-7be171db808f |  | note | - - - - - - - - -
label | 09fd93dd-4a39-5e4d-96e7-c878eb52cad2 |  | note | Record of Conformity: ITP signed
label | 917d68e1-2b5d-5006-89bd-b5d4ae1d338c |  | note | - - - - - - - - -
label | 87df5a3f-3044-55e1-9951-836a15eb53fc |  | note | IP
label | fd6bb253-e883-56a0-8f81-96f9ab3c50ad |  | note | - - - - - - - - -
label | 3c41a89d-5eb7-5d93-b449-58e46fc75861 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 2.3 Removal of unsuitable/redundant markings (If required)
label | 8cdffc1c-ee18-54ee-ae3b-c2fa05960ad8 |  | note | Frequency: Per lot
label | ebb6c150-7585-5194-8a35-d71f041c5166 |  | note | - - - - - - - - -
label | 97ab563e-c9e6-5105-a239-b9835e69c764 |  | note | Acceptance Criteria: If redundant/unsuitable pavement markings to be removed, removal methodology to be approved by superintendent
label | 2a3f29f6-be8f-50f4-9dc8-02bfcd39cf9f |  | note | - - - - - - - - -
label | 763db3e3-8162-5895-ad3a-e6b93cc4e169 |  | note | Reference Documents: PS3070.07C, VR721.A06, VR721.A08, VR721.A12
label | d79a6971-2bdc-5cc4-81f5-7f7d9d370a62 |  | note | - - - - - - - - -
label | 83c0ca80-a88f-5e36-b446-f37ee9a015a0 |  | note | Inspection / Test Method: Document review & Site inspection
label | fb793eda-1fd5-5ec2-8a82-6c7a90603da4 |  | note | - - - - - - - - -
label | 805ff30e-e2f5-5272-a897-dc6c6276a33f |  | note | Record of Conformity: ITP signed
label | 5416bcaa-e6d8-5979-8526-50704e8f4a53 |  | note | - - - - - - - - -
label | 3afa922f-17eb-5331-84bd-c85190bdcf79 |  | note | HP
label | 5a431e31-2c17-5c40-b2e4-541d3ba78cfc |  | note | - - - - - - - - -
label | 15ed6fd8-cd4f-5c89-8be4-6d376b2c1ef7 |  | note | Responsibility: Site Engineer / Superintendent
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 Set out of line markings; dimensions and spacings
label | dac2b8bc-68aa-5708-a961-f2b62f90f069 |  | note | Frequency: Per lot
label | 4d9df194-9aac-5705-9dbf-bf6d0227eb5f |  | note | - - - - - - - - -
label | 01469810-2b00-5fc9-b9eb-c532ae029baf |  | note | Acceptance Criteria: Painting/application of material shall not commence until the Superintendent has inspected the setout and installation timeframes are adhered to.
label | 2bf757fe-2a2b-52cc-98c9-ba032cf23a58 |  | note | - - - - - - - - -
label | 7c213e11-41ff-5431-b3ba-794e99b64507 |  | note | Reference Documents: IFC Drawings, PS3070.07D, PS3070.07H, PS3070.07J, VR721.A09, VR721.B05, VR721.B04
label | 2d38f142-f0c1-59e1-91d1-3376ea2cd91b |  | note | - - - - - - - - -
label | 0989f873-c951-58da-b567-ae314562678f |  | note | Inspection / Test Method: Document review & Site inspection
label | 097d48f4-bb94-58c9-a805-d10a0b67a71b |  | note | - - - - - - - - -
label | 942e4c35-ab9b-5beb-88b3-428608a3e1bd |  | note | Record of Conformity: ITP signed
label | 42905651-20f0-563b-b8a9-96745d0be350 |  | note | • Consent to proceed by Superintendent OR written exemption granted
label | 27797c17-1398-5ee4-ae29-d1b038da3486 |  | note | - - - - - - - - -
label | 2bb71496-193f-550b-97d1-20350abe84a8 |  | note | HP
label | 8a3ee628-f5b5-59a5-b5cd-c73891fa89bb |  | note | - - - - - - - - -
label | d7fcf39f-d82c-5981-a5db-c02efd1fb747 |  | note | Responsibility: Site Engineer / Superintendent
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 Painted pavement marking application (if required)
label | 46b87c3a-c2c7-5cac-ace2-8e609a6ee99d |  | note | Frequency: Per lot
label | a60636d8-7ef0-557f-8055-e57f2d4fcaae |  | note | - - - - - - - - -
label | 434f1c45-2071-5941-964e-12113b21b60c |  | note | Acceptance Criteria: If required, Council approved painted pavement marking is to be applied by a self propelled machine, with the minimum requirements for paint, glass, and skid resistance to be as per Material TDS
label | 5b265536-deae-5b67-b132-a561521dd7a1 |  | note | - - - - - - - - -
label | 24e9ca75-97c8-5800-9b66-e4271390cb80 |  | note | Reference Documents: Material TDS
label | 902c712a-0e6c-57ab-9575-660897270fcd |  | note | - - - - - - - - -
label | 281445c4-4add-580c-a01e-8b6bacabcb62 |  | note | Inspection / Test Method: Document review & Site inspection
label | ac9ca991-6cc9-50a7-8da6-78d63eec9117 |  | note | - - - - - - - - -
label | 7230bd9f-1d4c-519c-a22f-a5ad906ea9be |  | note | Record of Conformity: ITP signed
label | 4beaccc4-f863-5ebf-9e74-52cadecfe3e6 |  | note | - - - - - - - - -
label | 06ae6b93-a602-541e-9c0f-df8b1ee2c6fd |  | note | IP
label | 3242e410-7b04-570b-bc3d-32895c990f8e |  | note | - - - - - - - - -
label | 7b500b1a-068f-5a35-9440-941fb5e20059 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 2.6 Long life pavement marking application
label | 058577b9-22ca-5b3f-9bde-413823bde937 |  | note | Frequency: Per lot
label | 76ede703-a602-5dfd-8f95-fb2557c7a842 |  | note | - - - - - - - - -
label | ff3ae6bc-26d6-52ab-8054-b9f5a1cd801f |  | note | Acceptance Criteria: all line marking shall be applied using a self propelled ride-on machine including statcon marking unless otherwise approved, with the minimum requirements for long life materials and glass beads to be as per table 721.E021 & Material TDS
label | e1f39727-b40c-51ad-89bb-53c758ea8adc |  | note | - - - - - - - - -
label | 203a9279-04d1-5960-ad87-34fa30c9b7b5 |  | note | Reference Documents: VR721.E01, VR721.E02, Material TDS
label | cfd1eed9-3b5a-5de8-8241-f0921705c222 |  | note | - - - - - - - - -
label | 6d4dbedc-10bf-540e-912d-fc35ff42b555 |  | note | Inspection / Test Method: Document review & Site inspection
label | c306696f-5712-5fad-919f-c6d2e1f03fb5 |  | note | - - - - - - - - -
label | e5ce4cfe-3d24-5558-9ac2-14cc07554a57 |  | note | Record of Conformity: ITP signed
label | c7b4cac2-35ad-56d0-85ed-fa36628f6ed0 |  | note | - - - - - - - - -
label | f84eed37-d7b1-5084-894e-65cd2aa3857e |  | note | IP
label | 144515fa-14f9-5c27-be8c-2aee907ee688 |  | note | - - - - - - - - -
label | 5ed9473e-2f54-59f5-9f22-7faab7959d65 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 2.7 Protection of works
label | 7adae1c7-013b-5c97-815b-91c2224786bd |  | note | Frequency: Per lot
label | 0d8e8fc4-d0da-5ea5-b0ed-23ae42391edc |  | note | - - - - - - - - -
label | 23638c1a-c592-50cd-adad-743f48bded05 |  | note | Acceptance Criteria: Work to be protected by appropriate means until it is trafficable.
label | 24dae342-3369-538b-8355-b8951205b67a |  | note | - - - - - - - - -
label | 5390a4a5-c3b2-5935-8d78-dba71755118d |  | note | Reference Documents: VR721.A11
label | 76ad8005-84c7-544e-8727-0360904231f8 |  | note | - - - - - - - - -
label | 3bd8bf72-f401-5657-beb9-3f5a90091537 |  | note | Inspection / Test Method: Document review & Site inspection
label | 4ec06b21-4b40-56fa-803a-ee109aa454b4 |  | note | - - - - - - - - -
label | b0b88634-c051-5a8e-9d08-10da60413012 |  | note | Record of Conformity: ITP signed
label | a9af7824-6745-57a0-b841-a93e406cfa60 |  | note | - - - - - - - - -
label | 76206ca7-0338-55ed-93ed-5cdafddf0070 |  | note | IP
label | ccb54cf9-711e-57d5-87a8-f8e03c4c0830 |  | note | - - - - - - - - -
label | 3f0a217b-6aa7-5059-8dff-535c7d71cc65 |  | note | Responsibility: Site Engineer
checkpoint-group |  |  | section | 3 - Testing
checkpoint-status |  |  | checkpoint | 3.1 Acceptance of retroflectivity
label | b8aea1b2-5cd8-5512-bbe3-ab8d1285188c |  | note | Frequency: Per lot
label | 61cc30cc-5ba6-5f7b-99d8-5dbb87e8cea7 |  | note | - - - - - - - - -
label | 45e1e8e8-aba4-5d67-b7b4-30761c506f73 |  | note | Acceptance Criteria: Contractor to measure level of retroflectivity, with the average of six test site retroflectivity values for each lot.
label | d4b0f9e5-c48e-55f2-8155-941da60af0e5 |  | note | - - - - - - - - -
label | 1793f1f5-7430-588b-8ce9-648305f04d53 |  | note | Reference Documents: VR721.A13
label | eb3625ce-93d1-5423-90c4-bc7bd28e1724 |  | note | - - - - - - - - -
label | 8747db7a-08a1-533f-ad1a-d9d17c208f89 |  | note | Inspection / Test Method: Document review & Site inspection
label | 53dfdb6c-5c18-5c5c-afe7-a00e0b6a9ae5 |  | note | - - - - - - - - -
label | 2c3cdc86-fea4-55be-bdbf-6d6f490344cf |  | note | Record of Conformity: ITP signed, Test report
label | 89ee0296-529b-5722-a98b-3821cab06eff |  | note | - - - - - - - - -
label | a48dded6-0cea-59ae-b0b4-764e070b5007 |  | note | TP
label | 47e3681d-8088-5b78-9edc-d2ff87b3aa31 |  | note | - - - - - - - - -
label | 816a5af4-72b0-5db8-9b99-eb94a8c8eba9 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3.2 Acceptance of colour
label | d92b050d-0cb2-5a3b-bd13-ec2d2cbfa332 |  | note | Frequency: Per lot
label | d2fb1d3b-04d5-5e47-8bea-bc70e1c204cf |  | note | - - - - - - - - -
label | 806ee5e2-fcd8-5d24-9734-57c234f04f96 |  | note | Acceptance Criteria: Colour match tests for white & yellow markings to be conducted as per 721.A14, with results forwarded to the superintendent no later than 5 days from testing.
label | 92f829f1-ed34-595b-a27c-9550f8d3d189 |  | note | - - - - - - - - -
label | eba52051-7ab2-5bea-9b06-9f36d194209d |  | note | Reference Documents: VR721.A14
label | 386c1892-1463-580f-877f-2aada60ae677 |  | note | - - - - - - - - -
label | 61ea9c01-26e8-5b0b-8628-5f9e2c47b982 |  | note | Inspection / Test Method: Document review & Site inspection
label | acb1bf32-53a4-50b8-be21-71ed4b8fe59d |  | note | - - - - - - - - -
label | 557a076a-7563-5a81-af89-e478c18f14ba |  | note | Record of Conformity: ITP signed, Test report
label | 0ac2fd73-80e5-5491-9d11-47aeea8e3990 |  | note | - - - - - - - - -
label | 1d5f9708-553f-5596-be52-a2c9875cf4ff |  | note | TP
label | 96212a66-eb0d-5c32-b317-8011deed7b61 |  | note | - - - - - - - - -
label | 70d84d10-f545-58c9-b0d9-a8e66e621d5c |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3.3 Acceptance of tolerances
label | c6b3ca7e-c5da-5a8f-9622-8da2fdf16fab |  | note | Frequency: Per lot
label | ea72fe63-3d22-5669-990d-c1ca87b4e586 |  | note | - - - - - - - - -
label | cc8257f8-75f2-5674-8b39-f513aa6309d7 |  | note | Acceptance Criteria: Survey conformance report to show line marking applied as per tolerances shown in table 721.A101.
label | 25acf5b3-67c1-55c0-8aba-4ad42c2b1732 |  | note | - - - - - - - - -
label | 18377abc-8ff1-5854-ba11-4f8ca575e5a2 |  | note | Reference Documents: VR721.A10, VR721.A101
label | 56277e5c-bd28-5121-9a3c-0d750fa46305 |  | note | - - - - - - - - -
label | 2461ad1e-2290-5b27-a61e-702920b5def5 |  | note | Inspection / Test Method: Document review & Site inspection
label | 2bb7089e-9409-5f19-8ee9-455dfa3c076c |  | note | - - - - - - - - -
label | 5e39e663-a12d-501e-b91f-50474747fdc0 |  | note | Record of Conformity: ITP signed, Survey report
label | 80e9660b-8a93-5a49-9969-3de6c25dce92 |  | note | - - - - - - - - -
label | c8a47aaa-a4e0-5b79-b461-3dff60ca50d1 |  | note | SCP
label | 9b23ba12-83fe-52c2-b27d-bbe7be016821 |  | note | - - - - - - - - -
label | 5aafddd7-cf56-59a6-8aae-acaba7a7f1eb |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3.4 Acceptance of work
label | 5a9b9a69-f266-54e9-8140-99f961371323 |  | note | Frequency: Per lot
label | 84761193-c583-5010-baf2-afac5580bc5c |  | note | - - - - - - - - -
label | 526fde7e-44fb-5296-9ee2-3800628b4415 |  | note | Acceptance Criteria: Work to comply with specified requirements as detailed in VR721.A12
label | 5f3a80e6-b53d-5330-8e65-603f89be7521 |  | note | - - - - - - - - -
label | 22ca94f1-21ab-5fa5-abd4-c0a265b4fe1a |  | note | Reference Documents: VR721.A12
label | 8d2c4b44-b9e2-550b-9ec9-f7dfefc50dce |  | note | - - - - - - - - -
label | d2353fbd-8769-5aea-956b-641e156f2466 |  | note | Inspection / Test Method: Document review & Site inspection
label | edaac096-da78-5154-83b1-d07510e3a098 |  | note | - - - - - - - - -
label | 09793a7b-fdf9-50d5-88a9-f1efc0c4f9ac |  | note | Record of Conformity: ITP signed
label | 4e29a21a-86c6-51ea-a889-77ebf125cf43 |  | note | - - - - - - - - -
label | e8c9fd3e-2fb1-5a64-8c71-09613dd3f8d7 |  | note | TP
label | fea19fbf-db83-5156-a78e-b4fe11f9f28d |  | note | - - - - - - - - -
label | f11d5992-b50a-58bb-a919-5a360fa554f7 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3.5 Records & reporting
label | e3c41226-f1a8-511b-943e-9f6a69c0ca50 |  | note | Frequency: Per lot
label | 4d291c80-5ac4-5c0f-a24c-6f152edff298 |  | note | - - - - - - - - -
label | beeb8fcd-3e96-50e7-80fb-e43a85d4737a |  | note | Acceptance Criteria: All new markings to have job completion report forwarded to the superintendent, with a retroflectivity report completed and forwarded to the superintendent showing the retroflectivity for each test lot.
label | 6e97c225-9e7c-521d-93eb-d2bada705fc8 |  | note | - - - - - - - - -
label | c1260daa-2777-5cac-b199-49176189e92e |  | note | Reference Documents: VR721.B06
label | 0d439603-9cce-5f44-be78-0ce8efd71f73 |  | note | - - - - - - - - -
label | 85d70655-10b5-5940-9055-3f1382f6edf0 |  | note | Inspection / Test Method: Document review & Site inspection
label | cd175569-99ff-5bf2-be92-22461c1630a0 |  | note | - - - - - - - - -
label | ff647658-c985-5a91-8b0a-49a884a2a059 |  | note | Record of Conformity: ITP signed, Reports
label | 68b19243-71eb-5dc4-90fa-b9193a3a2b89 |  | note | - - - - - - - - -
label | b8f1cd5f-da45-5d06-83ae-d93b975c41cc |  | note | TP
label | 5ebec07b-b714-5e99-9414-73825278a72f |  | note | - - - - - - - - -
label | 6f17701c-0419-5ade-9f5b-8c09ee1054f0 |  | note | Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
label | 455aaf0f-1aaf-59e0-a042-0d595d554a47 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 90cfbdd7-1296-5a86-bce1-25b857a5d32d |  | textbox | Print Name:
text | ea0465e8-b610-519f-9bdc-695408248bfa |  | textbox | Position:
date | 62e16efb-d9b8-5021-aa3b-8b1b7d670f2a |  | date | Date:
date | 6557a8a2-8976-5955-9884-5e36abbcabc0 |  | date | Work Completed On
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification.
select | a01c3db5-fd31-52aa-80ff-8ab2cdbd1996 |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | 4bd4205c-94fd-522e-9683-8eb595685a64 |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | 5ccddcc4-545d-5900-958c-e2a9a432b706 |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | 8f2c6958-4b03-5a02-94bc-bfd132bfb24a |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | 51997d95-5d65-5e7f-9384-f8dcf10a3d5e |  | textbox | Other:
select | ff54a5c4-1785-5bd8-818c-9a00476b98d9 |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | 72021016-68b1-5fb5-9c4e-a2989951a96d |  | date | Lot Closed On
text | 9eb76a04-b87b-56a4-9f77-b71c0262caea |  | textbox | comments
checklist-sectioned |  |  | checklist | ITP-006-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | fed3260c-d764-4fcc-9bf4-951e27921dd8
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
date | b4782ab8-6ec3-5b21-baa3-16497a12ea65 |  | date | Lot Created On
date | ea61e41f-deb4-547b-bdef-bba441835f2d |  | date | Lot Opened On
date | ba5cf2be-19bd-513d-ba36-55a645dfd8d9 |  | date | Work Commenced On
select | 231ca2df-7dfc-52f0-8075-0e1084912c43 |  | dropdown | Lot Type | EAL - Earthworks Lot
text | a2fd3514-0cb1-5515-9eb1-47b06050a87a |  | textbox | From and To chainage
select | 5403b225-bfcf-5b13-8e99-ed7895887d42 |  | dropdown | Construction Element | EART - Earthwork
select | b0092170-6573-5bb4-b2dc-9b5da56357ef |  | dropdown | Activity | TYPB - Type B
select | ece45015-b866-511d-8d2f-1ba6c8401fe8 |  | dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | fcad6c69-7714-553d-a4b8-81ed60fa8b10 |  | dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | 9a23f1ac-c4a2-5baf-9e2c-7ad486238097 |  | textbox | Engineer Responsible
text | 819eef3e-b59c-5b24-81b5-51d41b635ff1 |  | textbox | comments
checkpoint-group |  |  | section | 1 - Preliminaries
checkpoint-status |  |  | checkpoint | 1.1 - Check that current revision drawings are being used
label | 52b99de2-457b-51b8-a0c0-4ac3f1073cf2 |  | note | Frequency - Prior to Commencing
label | 09a87971-f93d-5d36-8d6d-83d6c0a5b005 |  | note | - - - - - - - - -
label | bff6f962-1921-5e8d-8bb6-0e0222476d3e |  | note | Acceptance Criteria - Issued For Construction (IFC) and latest available revision used
label | b8db71ce-6f4e-5123-8b5f-c7236de26632 |  | note | - - - - - - - - -
label | 5c687d1e-d440-5b34-bbcc-c177a268918d |  | note | Reference Documents - Project Drawings / Drawing Register
label | 6e5ab086-53b0-5f55-9595-c8cf859edd9a |  | note | - - - - - - - - -
label | 93f5d06e-bdd7-57e2-9dea-8786b2a7c306 |  | note | Inspection / Test Method - Document review
label | dcb2467f-a4e4-5db4-9804-3032a508d78e |  | note | - - - - - - - - -
label | 4a812f64-5db6-556c-8952-6b0a96e24af1 |  | note | Record of conformity - Latest Revision Drawings
label | d0f90126-5405-5561-b456-2ddc599d9da3 |  | note | - - - - - - - - -
label | cc08e3c0-1e1b-567c-ad5b-b6b836e9de95 |  | note | AP
label | 74ae7c25-e71d-5846-b318-911e77b4b67f |  | note | - - - - - - - - -
label | feebfb5b-cc84-5a55-9c30-61173d3baa81 |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer / Site Foreman
label | 1410f849-af46-5147-b2d0-669a5a3d6427 |  | note | - - - - - - - - -
date | db55dc1d-264b-5c4f-b159-8bbc446416d9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Excavation Permit issued
label | 20acdecd-c7ee-5cd9-a429-15b48e1609f9 |  | note | Frequency - Prior to Commencing
label | 7fb36c4a-6a63-5444-acaa-1ab86f8e12b2 |  | note | - - - - - - - - -
label | 29f9f26e-1c15-5d9d-8189-9b50ed023363 |  | note | Acceptance Criteria - Current Excavation Permit signed and specific for the area where works will be executed.
label | f2cc3754-c3ff-506b-b644-e343e4daf8f7 |  | note | - - - - - - - - -
label | ba94c1ed-8786-527c-8162-c7b82ed06bb4 |  | note | Reference Documents - Excavation Permit
label | f03bb7d6-8d83-5483-ba04-1619625ef134 |  | note | - - - - - - - - -
label | e4d7ced0-1bc8-5a89-9d60-f86f82b005b6 |  | note | Inspection / Test Method - Document review
label | f9361967-4bac-5145-bcda-cdb55919110d |  | note | - - - - - - - - -
label | 5379c27b-08db-5a07-a204-c0b696a7f4fa |  | note | Record of conformity - Excavation Permit #
label | 64af4fff-5df2-51a5-801b-79d3a721ddc4 |  | note | - - - - - - - - -
label | b69f69ec-519d-5641-b20c-55372798c7f7 |  | note | IP
label | e5422eb9-abed-5b52-afc5-4c76ff7d2404 |  | note | - - - - - - - - -
label | ec87337a-4653-532c-8634-b36b4171d347 |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer
label | 046adec3-1178-50f9-8ed2-6269d655db74 |  | note | - - - - - - - - -
date | 51f3660a-e646-5f12-b703-a2d06fd65ee3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Re-Use of insitu material
label | f91729f6-562a-5abc-8d8c-214c8bad9f53 |  | note | Frequency - Prior to Placing fill
label | 83640849-cf24-5519-ac97-51c660b8da35 |  | note | - - - - - - - - -
label | 8955f478-b17f-558b-9f79-47e25c114d3b |  | note | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with clause 204.04.
label | 2b07192b-db48-5686-8c93-adb0f985329f |  | note | Type B Material shall meet the following requirements:
label | 04237fb5-feec-53d6-9689-8086240511cf |  | note | CBR ≥ 1.5%
label | 1d9bed20-6821-5155-9521-c86bb82de19c |  | note | Swell < 2.5%.
label | 51d45f8c-a25e-5cb6-9a32-452517e15033 |  | note | Attach: Test Certificates
label | 43fb8588-90de-54e0-92ae-47f92801a4d9 |  | note | - - - - - - - - -
label | 7ace1632-e5f6-5664-8378-717bb98d3a86 |  | note | Reference Documents - VicRoads Specification
label | 53f6b62c-ec2a-591d-9489-af70da887fd8 |  | note | Cl. 204.04
label | 09459d68-4005-5749-86e1-fb967950f393 |  | note | Cl. 204.06
label | 4a0e7ece-8f26-5a0d-9342-569447eb5818 |  | note | - - - - - - - - -
label | a4989cb9-c4b9-5cec-8300-a0320b3c33f7 |  | note | Inspection / Test Method - Site Inspection
label | aef017e1-178b-5035-a001-2432744d1f88 |  | note | - - - - - - - - -
label | b2b76cd2-ec97-5b7b-a29e-a063f1f00afd |  | note | Record of conformity - Test Results
label | bebc4673-cc12-5240-a2fc-8f09265151ab |  | note | - - - - - - - - -
label | c26e7f0e-07d3-5eb5-a4b9-7760093e8e5e |  | note | Material Category agreed with Superintendent
label | 23a8f894-06af-505e-a56d-9684bbac6397 |  | note | - - - - - - - - -
label | ab53ebde-d9c1-5348-994e-de5c60157aea |  | note | HP*
label | 9034ebd4-f7db-5074-acba-da7676d53e66 |  | note | - - - - - - - - -
label | a941b528-67c2-58f2-9d90-b0819a8ee741 |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Superintendent
label | 80d4d42a-bef1-5959-8c28-3b0a9f630200 |  | note | - - - - - - - - -
date | e9014003-4f40-5770-992a-14fcd7192c86 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 - Type B Material Approval
label | 771f711c-83a9-52d2-b59a-df5088510ae8 |  | note | Frequency - Prior to Commencing
label | 4eabc439-2c97-5ac0-9ede-cee7e02eb6ed |  | note | - - - - - - - - -
label | 1188112f-3109-526d-9e67-00d4b658bd12 |  | note | Acceptance Criteria - Prior to the import of Type B material, FH to provide the Superintendent, at least 1 week prior to the commencement of cartage, copies of test results to confirm that the proposed Type B material complies with section 204 of the VicRoads Spec.
label | 53be571f-f67d-55ff-9498-3c873110755d |  | note | Type B Material shall meet the following requirements:
label | 618a22e4-1d2a-5f6f-82b4-333429847981 |  | note | CBR ≥ 1.5%
label | 73387661-b40b-5534-894c-ccb9334e5400 |  | note | Swell < 2.5%.
label | 8b216b0a-22fc-5e32-b8b1-d0dd2dbeabe0 |  | note | If parameters are not met, remove 400mm of material mm below Cut Floor Level and replace with conforming Type B material.
label | bee7407c-bcce-5be5-b344-345ef1a6992e |  | note | If removal and replacement of material below the Cut Floor Level is not required, surface shall be loosened to a depth of 150mm and re-compacted to meet the specified requirements.
label | 579e2517-c5b1-5e35-94fa-fb6963cb2759 |  | note | Attach: Test Certificates, Sample Delivery Dockets
text | 86b6c413-fa90-5388-9dbc-9fefb4c1bf03 |  | textbox | Teambinder Approval number
label | 869f490d-1e35-582d-862a-69083e9a887f |  | note | - - - - - - - - -
label | b4af758a-35d8-51fd-b687-577e5a5d76a2 |  | note | Reference Documents - VicRoads Specification
label | d86ad905-bd64-5627-9c80-946ec1dacc50 |  | note | Cl. 204.04(c)
label | 08b7c372-e2b7-592c-8aed-d2ce354f93f9 |  | note | Cl. 204.06(e)
label | 251bb153-26ac-5e36-9848-8641fd46894e |  | note | Project Specification PS3020.05
label | a2116657-0615-5bb8-afd0-81f2914a6b41 |  | note | - - - - - - - - -
label | e6765902-1ce1-5b18-a3ff-0fb8b8c933af |  | note | Inspection / Test Method - Site Inspection/ Document Review
label | b308ce2c-c351-5e37-9acb-e6374a6339cb |  | note | - - - - - - - - -
label | c07a007e-7691-5d14-93cd-86cf518e7dc2 |  | note | Record of conformity - Geotechnical Report
label | 15c0d773-6de1-5aea-a132-19b5d264f6af |  | note | - - - - - - - - -
label | 3717671c-4793-50f8-b5a7-481b978950ec |  | note | HP*
label | 02ccc9ed-ad98-5c41-858e-a0d369138f3b |  | note | - - - - - - - - -
label | 2fbaab4c-954d-5229-aab6-5c71401f4c91 |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer
label | 79524ce6-9992-5578-a080-1a3d49fe2243 |  | note | - - - - - - - - -
date | 45c0a746-32a1-5169-a160-5ac812ab9f03 |  | date | Date Completed:
checkpoint-group |  |  | section | 2 - Cut Activities - 400mm below
checkpoint-status |  |  | checkpoint | 2.1 - Survey set-out
label | aba57e13-bb06-51ba-8688-473a9f463da2 |  | note | Frequency - Prior to Placing fill
label | 79d9404b-d342-509f-9d34-1f67781a8263 |  | note | - - - - - - - - -
label | ba19d8e3-a41c-5c3a-aa5b-fd66e5ec4b85 |  | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used.
label | 35c75e65-e0af-5c4c-b623-8259814015e0 |  | note | The boxing width shall not be less than specified or shown on the drawings and the edges of boxing shall not deviate by more than 50 mm from the designed offset from the centreline or design line.
label | 6c4dc1b3-2a27-55bc-8231-8383b1d5be4a |  | note | - - - - - - - - -
label | 159e304f-b9dc-5e99-9825-8456acf5eb9a |  | note | Reference Documents - Project General Specification Cl.1190.06
label | 5689c8d7-3df6-5830-96bc-373e14ad33fe |  | note | Latest IFC Drawings
label | 9ccc94eb-f45d-52c4-8bbc-334c992c71f7 |  | note | - - - - - - - - -
label | b5e6596f-0c69-56d8-b96a-aa36e345d8e1 |  | note | Inspection / Test Method - Site Inspection
label | f707c908-e108-5fc1-a076-7d73e6743200 |  | note | - - - - - - - - -
label | 75f41cf9-03a1-5768-8634-3fc82f2ef5de |  | note | Record of conformity - Survey records & pegs on the ground
label | ca41de6a-b99e-5395-867b-84edf14aa0c8 |  | note | - - - - - - - - -
label | ff33721d-8a8c-5030-8307-af5de04ac5e2 |  | note | SCP
label | 4243a7e4-e519-57b0-ab3b-25e517006983 |  | note | - - - - - - - - -
label | e1e639d2-50ab-5836-8368-da84d7d72883 |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Surveyor
label | dc1c9c50-5834-5238-b30d-2119c0011874 |  | note | - - - - - - - - -
date | deb9150c-4feb-5423-8d95-c5805cc0c44b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Ground water
label | 3b2b09ee-eee9-533e-a3d2-3fc6f926900b |  | note | Frequency - Prior to Commencing (if required)
label | 4cf63c58-809e-5860-99fd-6ec20ce6d833 |  | note | - - - - - - - - -
label | 2c915a01-feb8-5b87-b409-e97e8eabbb4d |  | note | Acceptance Criteria - Where groundwater or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review.
label | c9c7b02f-edca-5d85-9bf2-b348cafd353a |  | note | The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | 88493277-a0cc-5bcf-92bd-a756c00d8c12 |  | note | - - - - - - - - -
label | 846110b3-32d0-5810-8089-947b3e08bc92 |  | note | Reference Documents - VicRoads Specification
label | 44b1da55-62ff-5007-ad9e-48eb7d568b58 |  | note | Cl. 204.06(h)
label | 2313b230-cb0a-5968-ad91-8f7a5e2b9641 |  | note | - - - - - - - - -
label | daf5e2a8-168c-5dc9-8d5a-d4685c1c59c1 |  | note | Inspection / Test Method - Site Inspection/ Document Review
label | 6d3af875-884c-5584-8286-7c3aeecb32d8 |  | note | - - - - - - - - -
label | 420333ec-c29c-5399-9850-ecaf62bb73ae |  | note | Record of conformity - Area reviewed by Superintendent
label | abacb6f8-3941-5b79-8301-6196a50ed04d |  | note | Signed ITP
label | 9e42d60b-1f11-5523-a566-2e6f7f2eacd9 |  | note | - - - - - - - - -
label | 63bd9c50-e5b5-545b-b0c4-0b065a4c743e |  | note | HP
label | 163aa600-3b5b-545c-a62a-12ca2910af28 |  | note | - - - - - - - - -
label | bc1d881a-457b-5237-ab19-bf899ed97fee |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Superintendent
label | 06c0ce09-f823-5f57-9030-381786a3e66c |  | note | - - - - - - - - -
date | caec21dd-42d4-5172-ac59-6bc1407a2d57 |  | date | Date Completed:
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-status |  |  | checkpoint | 2.3 - Acceptance of Rock Subgrade (when applicable)
label | 4cf0f6b2-569d-52d7-84d8-1e0385085c3a |  | note | Frequency - Prior to construction of the regulating layer
label | 568c36d6-b6a4-5d2c-95c2-21367b4152cf |  | note | - - - - - - - - -
label | f8091a3a-5234-540b-be88-a27f030a060a |  | note | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | 0d81cc44-fac9-5ead-b155-08d0f79d9161 |  | note | Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | ddc9cc2e-7cae-5f63-b0f4-260219d25648 |  | note | - - - - - - - - -
label | 376c637a-f3d9-57bc-99e6-970254e54747 |  | note | Reference Documents - VicRoads Spec. Cl. 204.06(f)
label | f7056eb3-a0fa-5cb1-af81-9b797a3b2a36 |  | note | - - - - - - - - -
label | ff3687c3-8611-5a9e-a2ea-ca9cb6c1d08d |  | note | Inspection / Test Method - Site Inspection/ Document Review
label | 27063950-da6c-529d-be95-358c6a45af29 |  | note | - - - - - - - - -
label | 8925af95-3b59-598c-901a-3e18b9078ee3 |  | note | Record of conformity - Superintendent acceptance
label | 440fc01f-59b3-5a15-b1fb-11b20edd9b3c |  | note | Signed ITP
label | fec0bfa4-314e-5d6f-9003-8e444bcf2862 |  | note | - - - - - - - - -
label | b16df26d-f74b-5e0c-8364-eb6eacb5aaa5 |  | note | HP
label | 66831aa9-3927-5bd3-ba3f-5a124a09de2d |  | note | - - - - - - - - -
label | 53a48862-4e1f-512b-bda0-d92009ae74e2 |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Superintendent
label | e51ff7b0-002c-5b4e-b0e5-5d9fe2cd1627 |  | note | - - - - - - - - -
date | 996dffe6-302b-547e-a53f-bdbfe1dff04a |  | date | Date Completed:
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-status |  |  | checkpoint | 2.4 - Proof Roll - Cut Floor
label | d5a4a052-4af4-5372-8c17-36f7840cc058 |  | note | Frequency - Prior to Placing fill
label | 66a14103-0de7-5fee-af36-6ce2b32ff518 |  | note | - - - - - - - - -
label | d1c3e4a3-88d8-5447-8695-d7ee112c3300 |  | note | Acceptance Criteria - Areas upon which fills are to be constructed, all layers of fill, and material within 150 mm of the cut floor level in cuts, shall be test rolled in accordance with Section 173. Superintendent to be present during all test rolling.
label | 6d05c1ce-0c7f-59e5-b939-22b9a2023a72 |  | note | Fulton Hogan to provide not less than 24hrs notice to the Superintendent of the location and commencement time for test rolling. Superintendent to be present during all test rolling.
label | 848a2827-4ec3-5a99-8952-a9118cd31368 |  | note | No fill is to be placed on the prepared areas until the the area has been reviewed by the Superintendent.
label | 5bb44cf9-cc46-5fd1-b165-562ac3913d62 |  | note | Where unsuitable material is encountered the Contractor shall propose in situ treatment and depth of excavation to the Superintendent for review.
label | f812672a-d552-5da5-81df-bdff960c6004 |  | note | Where <10% of the lot area is deemed unsuitable, material shall be rectified as agreed by the Contractor and Superintendent
label | 71953589-300e-5313-a12b-09365d8cb3c6 |  | note | - - - - - - - - -
label | 2466fef6-39f7-565a-94ed-56b96f8cbd0c |  | note | Reference Documents - VicRoads Spec. Cl. 204.12 Cl.173.03
label | 5630e1d8-2feb-5f76-bc1b-7d1b32b77d44 |  | note | Cl. 204.10(b)
label | db4175c2-7815-547c-8038-d0df8c9d3b0d |  | note | Cl. 204.07(d)
label | 9a3199d9-621f-5dc2-b89f-3b0283a23b3e |  | note | - - - - - - - - -
label | d3e7b214-448a-509c-8e36-3942e1822b30 |  | note | Inspection / Test Method - Site Inspection
label | 00b5f2eb-aea8-5db3-ae0c-615da6c90872 |  | note | - - - - - - - - -
label | 0c29de5e-5789-5122-8ee5-06073994d9ae |  | note | Record of conformity - Area visually reviewed by Superintendent
label | a48942ea-c5fb-5127-bcc4-b4feff630a99 |  | note | Signed ITP
label | 581ce914-b20e-5cac-9dbd-b6c29ce5d983 |  | note | - - - - - - - - -
label | 3f230f05-d3dc-5ebc-8b23-2d8f9af1bd13 |  | note | HP
label | 7391713e-27fd-50c3-9be0-26f17c3d451e |  | note | - - - - - - - - -
label | abfab430-279e-50f1-89c5-a79e410021a0 |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Superintendent
label | 72cd618f-74e6-5d75-9805-9d1953842047 |  | note | - - - - - - - - -
date | 717fbf45-ced7-5e25-bfc4-cd9f6171bfe2 |  | date | Date Completed:
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-status |  |  | checkpoint | 2.5 - Compaction Testing
label | c7ddd09c-f73b-56b3-b9db-b56b54503532 |  | note | Frequency - Each Lot
label | 8f7f3cc2-b8a6-59cd-871e-0784955751bd |  | note | - - - - - - - - -
label | 6aaa477b-0a36-56b5-aa72-ec5bbe5e96cc |  | note | Acceptance Criteria - Frequency = 6 tests per lot
label | 53ffb599-225f-5d1d-afe3-4517cec51f2f |  | note | Min Frequency (subject to approval) = every second lot
label | a9eff641-575c-529e-884b-e37288fd2b6a |  | note | Lot = One day's production or 4,000m2, whichever is the lesser
label | e47c0019-bbcd-58e2-b09b-b5c04a2d208c |  | note | Characteristic Density Ratio =
label | 0459ea83-57ca-53ad-9c85-27d68431adf4 |  | note | 97% minimum when more than 400mm below top of Type B Fill
label | f9046df7-202b-5eee-955f-1d5ae13bc671 |  | note | 99% minimum when within 400mm of top of Type B Fill
label | d4f7bf57-8469-5f14-a435-1568ecf4e3ed |  | note | Attach: NATA Compaction Test Report
label | ce96cca6-7608-5611-8a4e-39aee2764cc8 |  | note | - - - - - - - - -
label | 5cc8106b-3ce6-5295-aa0b-6b6a4eef9d8c |  | note | Reference Documents - Table 204.131
label | 42883e37-e6d9-54c0-95c9-9bc4dab26dd1 |  | note | Section 204.13, 204.14
label | a926276f-d155-5495-a0de-0f35ec81adb6 |  | note | - - - - - - - - -
label | 62bb9e01-b19d-5967-a074-c5d5f981c7bc |  | note | Inspection / Test Method - Document Review
label | 3c1c69e5-5a31-5bd5-95a1-4fc15a9681d6 |  | note | - - - - - - - - -
label | 63fa2302-68c2-5fef-91d2-5c189f68173c |  | note | Record of conformity - Sign ITP
label | 2819ab9f-78b4-5691-a0b9-d7cbb4d1fab4 |  | note | NATA Compaction Test Report
label | 73fae927-6831-547c-a910-5da13aaeb68a |  | note | - - - - - - - - -
label | 2fa99057-60db-526c-be8e-b385acb262f6 |  | note | IP
label | f6a69f53-8b0e-57e8-8a4e-dbfcccfaacb6 |  | note | - - - - - - - - -
label | 83d40932-bb50-5b48-a53b-c3f57bc2c238 |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer
label | 05269e65-4d50-52fa-8b03-21d896f94544 |  | note | - - - - - - - - -
date | 5fbb5439-5ae3-5966-9eae-df1b43871853 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 - Survey Pickup
label | c8a22e93-08c2-56f4-9a0f-76969826cf82 |  | note | Frequency - Prior to Placing fill
label | 2233a407-bc54-507e-b5af-64fa08dd43dd |  | note | - - - - - - - - -
label | ce2c6be3-6dbd-5099-b8b2-78d6e006633e |  | note | Acceptance Criteria - Ensure the Cut Floor Level is recorded by survey
label | c2159531-eddd-5efd-83e2-3533254f7f1e |  | note | - - - - - - - - -
label | 55426932-401f-593c-bc6b-adcf7fed44df |  | note | Reference Documents - VicRoads Specification
label | 8a12981e-bfee-5ed3-81b6-96de52aab01d |  | note | Cl. 204.03(f)
label | 8d2cdf22-fbf2-5f82-adc4-9f270b9dfa8f |  | note | Cl. 204.03(g)
label | c28954c2-bf83-5883-8e1f-43a2dcd9573e |  | note | Table 204.031
label | 7588b61a-3fdb-52de-9239-7fe1008a04f6 |  | note | - - - - - - - - -
label | c347275a-4ac7-5b5c-8501-442b9b61e47a |  | note | Inspection / Test Method - Document Review
label | e28161f9-c222-5561-b27f-ffc57057cdf4 |  | note | - - - - - - - - -
label | 9aa2f345-761a-5c7e-9da7-6420aa2612db |  | note | Record of conformity - Survey As-Built
label | 51f56c63-0508-5220-a595-572b378afddb |  | note | - - - - - - - - -
label | 9588679a-48ac-54f8-bd92-bf12469468d4 |  | note | SCP
label | 0d56d12e-9184-53b6-ab1a-707571be088b |  | note | - - - - - - - - -
label | fc111b0e-5def-548b-855a-7fa0741a1ca5 |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Surveyor
label | 1f21b328-a389-5be0-94c1-a182e259477b |  | note | - - - - - - - - -
date | 3446f74c-1b9e-5373-b0fa-3f5c1093aae9 |  | date | Date Completed:
checkpoint-group |  |  | section | 3 - Fill Activities
checkpoint-status |  |  | checkpoint | 3.1 - Placement of Fill
label | c56354e3-10f3-5d1a-80d1-413f288a642a |  | note | Frequency - Each Lot
label | 5430de97-0e4d-55fd-a5b4-2d616c47c603 |  | note | - - - - - - - - -
label | a7e4b2a6-2d11-55c8-a9af-ab74107e1258 |  | note | Acceptance Criteria - Fill material shall be spread and compacted in layers not exceeding 200mm compacted thickness.
label | 987eaf12-2744-5182-82d8-0e6026bbd1bf |  | note | Each layer shall be keyed in to the layer above by means of a textured surface
label | fb273f4d-180d-5cfb-bc00-7f769950b65a |  | note | Any rocky material present must be uniform throughout the layer.
label | 757f672a-6f04-544c-b68c-269fd1def8d5 |  | note | - - - - - - - - -
label | 7c65c19b-0f52-5cea-a622-1179f2037c6b |  | note | Reference Documents - VicRoads Spec. Cl. 204.10(d)
label | bccbe9e7-d702-56df-8270-7b45addda70b |  | note | - - - - - - - - -
label | e4e57854-9874-5c45-b1c5-2ba2801f3a35 |  | note | Inspection / Test Method - Site Inspection
label | 707202eb-0312-50b4-ad72-395c3b163ea7 |  | note | - - - - - - - - -
label | 5efb8301-0533-53df-8c82-0dfac871962f |  | note | Record of conformity - Signed ITP
label | 76b68889-ac9e-5d6e-8832-20535c373759 |  | note | - - - - - - - - -
label | cf616211-e9f5-5202-9200-605ef28f6a68 |  | note | IP
label | 677bacf8-b32e-5888-9a0f-5c241889abc8 |  | note | - - - - - - - - -
label | 78d7e042-e303-5a26-ac7d-84a5fa8ca2c0 |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer
label | 6945d598-b3dd-5fe6-9069-4984339fc681 |  | note | - - - - - - - - -
date | 79cd9850-6c9e-599e-bedb-654b88a66584 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Preparation of final surface - Subgrade
label | 80eddd33-1283-5973-9964-66bacde29d55 |  | note | Frequency - Prior to construction of subgrade layer
label | 930c2865-1787-55ef-b985-83544d474c59 |  | note | - - - - - - - - -
label | 875f272e-8905-5672-aef0-16154e53a9fb |  | note | Acceptance Criteria - The top of the Type B material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03(g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water)
label | 8af9fa4f-9154-5b63-a27e-7a58b81dc26d |  | note | - - - - - - - - -
label | 5f47e04c-f7d9-5d9c-86b8-20428a74aaa0 |  | note | Reference Documents - VicRoads Spec. Cl. 204.15 Cl. 204.03
label | de24ce5e-efbb-5cee-80de-6c5bf873c321 |  | note | - - - - - - - - -
label | f3eaa212-7615-5596-9da8-01ee2091ad36 |  | note | Inspection / Test Method - Site Inspection
label | a5a20ab9-e2e6-5f93-8b62-75a11e8de4fe |  | note | - - - - - - - - -
label | 6d21799b-e9b3-542c-af78-e7eddd069776 |  | note | Record of conformity - Signed ITP
label | e4687c34-7e5a-5c4c-9ad7-d3342b322a70 |  | note | - - - - - - - - -
label | 1827c5d8-c055-57ea-b808-f3004479e48a |  | note | IP
label | b6002c97-e1f9-5204-acb9-03445b3650f2 |  | note | - - - - - - - - -
label | 2dd54766-242b-567f-99d0-d0c01fcfa1cf |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer
label | ce3c06db-df7d-56bc-9b7f-f476769f727a |  | note | - - - - - - - - -
date | 07d5914c-f570-5fef-a194-a61201c8f28d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - Trimming and level conformity
label | 9d77a097-45d0-5dd6-a07f-fd849e5f23b7 |  | note | Frequency - Each Lot (one day's production) prior to Commencing
label | b6f1f0e0-cb26-5703-9109-1a97dfad06d9 |  | note | - - - - - - - - -
label | b2032647-532c-53f0-8fa3-d9e2451d19bb |  | note | Acceptance Criteria - Ensure that the level at any point on the surface of the Cut Floor Level immediately below capping does not differ by the mean values of more than 5 mm above or 15 mm below the specified level.
label | ce2b6185-9d2f-5185-98f8-2f8f2fd1917a |  | note | The level at any point of the subgrade shall not lie more than 20mm below a 3m straightedge in any direction accepting crowns.
label | 0780eede-ee18-5f31-bf6c-7c68090cfd11 |  | note | - - - - - - - - -
label | 40038282-131c-5789-bc2a-0099c02d5780 |  | note | Reference Documents - VicRoads Specification
label | e8f196cc-a268-5735-b17e-c485f9c98bad |  | note | Cl. 204.03(f)
label | 0f7468c7-3171-5df0-9d5d-2b4615c67fdd |  | note | Cl. 204.03(g)
label | afd23922-98be-5ba2-b715-a02dd4388418 |  | note | Table 204.031
label | 55d09cad-5be8-53ab-9a15-8256b8ab9ce5 |  | note | - - - - - - - - -
label | 71f19095-02a0-5560-8ea5-bfc00f858b09 |  | note | Inspection / Test Method - Survey Report
label | faefbbe9-4109-54be-beb5-1ed26448da31 |  | note | - - - - - - - - -
label | 62f3d6dd-537d-548d-a322-55a2309c01f8 |  | note | Record of conformity - Survey Record
label | 7684bb5a-00e0-5ae7-a988-861dc3df2c82 |  | note | - - - - - - - - -
label | e784891e-9321-5ffc-8140-3d62c784fa92 |  | note | SCP
label | 8a0535b5-c14f-5ab8-b5d0-a5049ffebdef |  | note | - - - - - - - - -
label | 410ab4ad-f503-54a3-a141-af752a0aa8f6 |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Surveyor
label | b032007e-7e47-57e0-89c0-813569154fc4 |  | note | - - - - - - - - -
date | f96522ca-a769-59ea-b062-4a203a02354b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 - Proof Roll - Top of fill layer
label | 96d16c95-9469-5d1b-9741-35a04711a80c |  | note | Frequency - Prior to Placing fill
label | 396454ca-0bf0-503c-a384-c5b53ff559bc |  | note | - - - - - - - - -
label | e6e07111-665b-5237-b8b5-389f2c78b6a3 |  | note | Acceptance Criteria - Areas upon which fills are to be constructed, all layers of fill, and material within 150 mm of the cut floor level in cuts, shall be test rolled in accordance with Section 173. Superintendent to be present during all test rolling.
label | ed5ce5df-b2a1-57af-9623-d01eaed282e7 |  | note | Superintendent to be present during all test rolling.
label | 812f86ec-b699-5dcc-bdbf-e28628ccf50c |  | note | Fulton Hogan to provide not less than 24hrs notice to the Superintendent of the location and commencement time for test rolling. Superintendent to be present during all test rolling.
label | f59d15ac-d014-5f77-be71-90f0c1838816 |  | note | No fill is to be placed on the prepared areas until the the area has been reviewed by the Superintendent.
label | 82589977-d21f-50b6-8e52-5685e2542fd5 |  | note | Where unsuitable material is encountered the Contractor shall propose in situ treatment and depth of excavation to the Superintendent for review.
label | c88cb93c-c615-5a04-aabc-cf8516d0f370 |  | note | Where <10% of the lot area is deemed unsuitable, material shall be rectified as agreed by the Contractor and Superintendent
label | a79430d6-c8ee-519f-9321-be7ed63bc0aa |  | note | - - - - - - - - -
label | 209b9270-9bbc-573b-a996-e7edb504f868 |  | note | Reference Documents - VicRoads Spec. Cl. 204.12 Cl.173.03
label | ccce4a52-0e04-5666-ad5e-c8863fbceca6 |  | note | Cl. 204.10(b)
label | 8db68e1a-d53f-56ab-8a54-546a4067af53 |  | note | Cl. 204.07(d)
label | 0718e3bf-5744-533c-9380-9bb4210ab265 |  | note | - - - - - - - - -
label | 43b180b0-b440-5e7d-b601-04fd3196801a |  | note | Inspection / Test Method - Site Inspection
label | a94a4be8-494b-599f-8f17-f2cdaae35f90 |  | note | - - - - - - - - -
label | c817f07d-a773-54a0-838f-a4ca248debf9 |  | note | Record of conformity - Area visually reviewed by Superintendent
label | b9841437-b0ec-5a12-8c7e-609c03ca7aa2 |  | note | - - - - - - - - -
label | 654fdbb0-794e-57b2-94fb-389f6779470f |  | note | Signed ITP
label | a07f6371-5521-584c-8bfd-95c8aa11aa7e |  | note | - - - - - - - - -
label | c0ec6d33-37cb-5a6b-b6b7-e56b1dac306f |  | note | HP
label | 8f808f5c-09cb-5cb5-b30e-666ac5c0a3f5 |  | note | - - - - - - - - -
label | d6f6c971-3f70-52a1-9d19-31fad2f80b08 |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Superintendent
label | 863a88eb-945d-5e00-9d7b-783fb01b1663 |  | note | - - - - - - - - -
date | 42d30c7a-bfcb-57ae-b682-1528a25c9421 |  | date | Date Completed:
label | c8089d5f-0dcb-5dad-b8a1-6911617fe5ff |  | note | - - - - - - - - -
holdpoint |  |  | signoff | Authority Holdpoint
checkpoint-status |  |  | checkpoint | 3.5 - Post-compaction Testing
label | 834a6fb4-2076-5ab5-be29-f2d3cc63c5f0 |  | note | Frequency - Each Lot
label | 4f46e7f3-1302-571b-a9f4-eadcb9c65a99 |  | note | - - - - - - - - -
label | c156534a-3bd8-59c7-ae4a-7e0cdcb78b68 |  | note | Acceptance Criteria - Post compaction testing shall meet the following requirements:
label | 6d51ca6e-339c-54d7-85f9-d2840a0ff320 |  | note | CBR ≥ 1.5%
label | fe9ebec8-ad67-50da-a2e5-1d48c5491d25 |  | note | Swell ≤ 2.5%
label | 47ae84b6-508f-56ea-a45a-fdc743d8083d |  | note | Characteristic Density Ratio ≥ 99%
label | 1da57883-a6c0-5edc-ba58-0be8a60054a4 |  | note | Moisture Ratio ≥ 70%
label | 2f380aa7-8e03-578a-b1cc-9071c8540477 |  | note | Subject to approval min frequency testing as follows:
label | 0f835d6b-85a4-59b0-9a08-11a40b08c619 |  | note | Compaction & Moisture: 1 test per 2 lots
label | e1fe78d8-01c7-5607-aed3-851dd9ea4901 |  | note | CBR & Swell: 1 test per 8 lots
label | 916c9b1a-fa08-5d43-9ff5-626409e58856 |  | note | Attach: NATA Compaction Test Report
label | 71a22cae-ecf3-5e4b-bab1-6e5516dc97b4 |  | note | - - - - - - - - -
label | 2daba4a2-1365-5c73-b7ff-27e40d09e7b8 |  | note | Reference Documents - VicRoads Spec. Table 204.142
label | 1e92706c-ceba-5891-89fd-91c18751d28a |  | note | - - - - - - - - -
label | 83e8824c-62d1-5471-bf94-7b637af9eb19 |  | note | Inspection / Test Method - Site Inspection
label | d0f3ae4b-ee84-51f8-890d-2682ab976e18 |  | note | - - - - - - - - -
label | 33a52401-7a06-5bf0-9584-32fb47934b28 |  | note | Record of conformity - Signed ITP
label | d09f226a-c979-52aa-be24-677334ef55ce |  | note | - - - - - - - - -
label | 342d5442-ff8a-5855-b6a2-013805e246a1 |  | note | TP
label | 56fab060-9635-59e7-867b-62c82d4b6174 |  | note | - - - - - - - - -
label | 9995f9bb-a45e-527a-a7d8-1260fc63c6de |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer
label | d9c73c51-715c-504e-a57f-7a711666bf46 |  | note | - - - - - - - - -
date | 1424cd1c-c95c-5185-ad7d-d4a59fb5ec16 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 - Survey Pickup - Top of subgrade
label | 64eb7af3-d263-5319-8536-dc5dcb56c152 |  | note | Frequency - Prior to Placing fill
label | abaf37c8-25ee-5543-b3f7-a845f9f8edd5 |  | note | - - - - - - - - -
label | db25d4ab-8f8b-5542-9ec1-fdbc8dde87d5 |  | note | Acceptance Criteria - Ensure the Top of subgrade is recorded by survey
label | ffc8b469-db35-510d-bafd-dce60f273252 |  | note | - - - - - - - - -
label | f76062a8-86a2-5e09-85b9-19da18de8769 |  | note | Reference Documents - VicRoads Specification
label | 09eb2d03-4185-5a2e-b091-37471baab476 |  | note | Cl. 204.03(f)
label | 66461e11-f145-502a-8607-15c451d10ef6 |  | note | Cl. 204.03(g)
label | c15caadb-5d4e-5093-a969-c5c13f84c3e1 |  | note | Table 204.031
label | 27737314-4a50-571b-94aa-f2dcb4ced092 |  | note | - - - - - - - - -
label | 771f2249-cb05-57f1-a9a2-aa38ce3691d5 |  | note | Inspection / Test Method - Document Review
label | 4d384ffd-388e-5f9f-ae6b-17cddcff09ff |  | note | - - - - - - - - -
label | e6e7a052-35b0-5335-a743-58451fe84825 |  | note | Record of conformity - Survey As-Built
label | 31d55730-9828-58d2-b25b-3c274b496f3e |  | note | - - - - - - - - -
label | 93282110-e5f5-5243-922e-b68fdf88e04b |  | note | SCP
label | 20138c37-9913-5a2c-84c5-793625130504 |  | note | - - - - - - - - -
label | cdd8ecd2-06f6-5262-b662-ede16dfc0350 |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Surveyor
label | 962b089d-4237-5ca9-8f1b-e6b63fcf1b9b |  | note | - - - - - - - - -
date | 6ace37aa-35cc-51df-a720-5406ecc51861 |  | date | Date Completed:
checkpoint-group |  |  | section | 4 - LOT Closeout
checkpoint-status |  |  | checkpoint | 4.1 - Survey As-Built
label | 5a0b5f58-955d-5fbb-af35-ea9c7c67711c |  | note | Frequency - Each lot
label | 9ffd5723-0926-5310-a7a7-15a5ba4c6262 |  | note | - - - - - - - - -
label | b97ad782-d2c7-594c-ab17-174682a74fce |  | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | e1cd0073-6d11-5ee9-a7e7-158ff25a6566 |  | note | Scale A:
label | e5926adc-a4aa-5385-a8d0-58ffa084a5d4 |  | note | Min. No. of Measurements Per Lot: 80
label | 3679a4bb-5036-5d4c-bbcc-61e063b23d9d |  | note | Range x (mean) = +5, -15mm
label | fdd285a9-d843-5507-a525-d3715334928e |  | note | Max S (Standard Deviation) = 12 mm
label | f02cde2f-de49-5bb4-b9a3-ed67dbff6a38 |  | note | Attach: Survey As-builts / Survey Report
label | 3578546d-cb5c-501e-8ec8-2013f99d3721 |  | note | - - - - - - - - -
label | 5d2df183-bfb6-5472-a44e-bbd6c78c457d |  | note | Reference Documents - Section 204.03 (h), 204.16
label | e399f01d-0edd-50e0-a706-765a5a65d04c |  | note | - - - - - - - - -
label | 89e21945-1204-5f8a-85b2-a226161dbe14 |  | note | Inspection / Test Method - Review Document
label | 3051a3a3-c64c-57c6-b8df-fe011f62b883 |  | note | - - - - - - - - -
label | 3f35654c-3fd8-550d-adff-67955d9d1301 |  | note | Record of conformity - Attach As-Built Report
label | d7676cb4-c7cd-5c4c-b034-5388fad9b67f |  | note | - - - - - - - - -
label | 303878d4-ea38-5a40-9b99-da69eefef779 |  | note | SCP
label | ce7f51e3-1f71-5438-8b34-0b4ceec8bd85 |  | note | - - - - - - - - -
label | de63bd74-2c26-5e2f-b3fc-c458cd866e55 |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Surveyor
label | b57088af-d42d-5e8a-b24a-aef244f742a8 |  | note | - - - - - - - - -
date | f36ee153-ddc3-5122-acf6-47da1cfec4da |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Non-conformance Closure
label | 5b21be91-940b-573d-82a0-1f87fe989c76 |  | note | Frequency - Each Lot
label | f87e2b7b-ab57-5722-8269-404e0d64a87e |  | note | - - - - - - - - -
label | 894a8b16-51c1-5a6c-a731-e0052e84dd9f |  | note | Acceptance Criteria - Ensure All related Non-conformances are recorded and closed out.
text | a6e7c4bc-1de3-5940-ba7a-28a3ee6d05a1 |  | textbox | CAMS Case Number(s)
label | 7f155554-3d69-5c08-bbe6-7cd51b7ff9a6 |  | note | Attach: Closed NCR Report
label | 9fb4c979-ecf9-5ab1-a225-8a41abdff916 |  | note | - - - - - - - - -
label | 603be8ab-d1d9-5256-b26d-a0f7237e01de |  | note | Reference Documents - Quality Management Plan
label | 07db8abd-c166-524d-b427-3be0823a9767 |  | note | - - - - - - - - -
label | 0a235093-3aab-52fc-8e90-281f95352d27 |  | note | Inspection / Test Method - Review Document
label | c3979d62-03e4-5e08-94ae-e0dc3e72dd62 |  | note | - - - - - - - - -
label | 1030d54a-93f6-5e63-8fb2-503c9788820e |  | note | Record of conformity - This ITP
label | e3b36146-605d-5d64-87c3-af99de9cef02 |  | note | - - - - - - - - -
label | 5e50a320-5698-5309-83c3-51fa92a7ae4d |  | note | IP
label | 3b8613fb-42d3-5280-8a7b-d00ed240843d |  | note | - - - - - - - - -
label | 937c10c0-252a-5a44-9a6c-64dcb553e7e9 |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer
label | 8778b8b6-1769-5b5c-b3f4-6a59a77e0f8b |  | note | - - - - - - - - -
date | 0e42983f-733a-5897-b8f9-35f73f1d99a7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Red Line Markups
label | a091fad8-0ab1-5cc0-bbf2-59a5de7f5a79 |  | note | Frequency - Each Lot
label | 3035acc9-e690-5a0c-a191-f348711935f6 |  | note | - - - - - - - - -
label | 5c71e29c-5e28-5f9d-8678-98bd0aa46db5 |  | note | Acceptance Criteria - Ensure any changes from design are captured in red-line markup drawings
text | 96370d39-15d3-5cbf-94a1-0ac773b469b9 |  | textbox | RFI References
label | 517efae1-aaac-5ef8-aa15-769cc296f585 |  | note | - - - - - - - - -
label | eb53f2cd-a604-503b-9b81-0b31ab28e030 |  | note | Reference Documents - Quality Management Plan
label | e890054a-de99-5790-ba37-32aec96f139e |  | note | - - - - - - - - -
label | 68a8fc13-7541-512a-963b-e326ea40beeb |  | note | Inspection / Test Method - Review Document
label | 9cd372c8-6a1b-5718-9d05-811150a87d39 |  | note | - - - - - - - - -
label | 078734c3-225a-5836-b525-21c3c1568398 |  | note | Record of conformity - This ITP
label | 84fc9754-d0ee-526b-ba44-2a466151e8bc |  | note | - - - - - - - - -
label | a7f4a4d6-a83b-517b-be3c-4a7e6f02b837 |  | note | IP
label | 6f7da54d-5cc6-5cda-b189-463130f53d04 |  | note | - - - - - - - - -
label | 9c4b2538-8a26-5638-abab-5f07177e1b96 |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer
label | 72fefe9e-daad-5f26-86c9-28fced0165ff |  | note | - - - - - - - - -
date | 4892300d-1075-5530-8866-22eda6aa6ffb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 - Final Inspection
label | 7ba7bc26-6e12-5266-806c-d5eecee9ed35 |  | note | Frequency - Each Lot
label | ad62c266-95e2-598a-ae4d-c0a91a765a0e |  | note | - - - - - - - - -
label | 99670eb6-ec21-592f-9ea7-21169656007e |  | note | Acceptance Criteria - It is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
label | ce71067b-aeef-5d02-abe6-721678b57fb2 |  | note | - - - - - - - - -
label | 7fa0a4bc-6df1-5db0-af54-bedc795e4a6c |  | note | Reference Documents - Quality Management Plan
label | a69ecc9d-4d70-509e-a77d-2fe2def47c78 |  | note | - - - - - - - - -
label | 07f8b19d-94b0-549e-8512-9c74d1bc8ce5 |  | note | Inspection / Test Method - Review Document
label | 9eaf0010-a2d5-52c1-a812-29c08f84d632 |  | note | - - - - - - - - -
label | 91626aca-9c5e-5c60-9db7-a1afa0bccb8c |  | note | Record of conformity - This ITP
label | 25e2d672-6338-5e6b-a6b9-dbd131649de8 |  | note | - - - - - - - - -
label | e2f2e85f-02ed-56b8-b56f-c0a00ee93540 |  | note | IP
label | 5a514f55-90ce-5600-a441-6ae45a1d02e9 |  | note | - - - - - - - - -
label | 353f185b-7809-5995-9eab-a8fdaad25b62 |  | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Quality Manager
label | dad5bc38-cb82-574e-b9ec-6f84a4879845 |  | note | - - - - - - - - -
date | 4441f733-fcbb-53cd-a65c-82ae1256dde8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | fe45d8e1-bec9-5370-8296-123382a0c468 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | beb1187a-76dd-54f6-9a44-f4a8b0603d76 |  | textbox | Print Name:
text | 9db0e91d-c423-5f26-b2e1-511ade7aa5b0 |  | textbox | Position:
date | 982a105a-35df-59d5-84d5-9c588405e8dd |  | date | Date:
date | 208ff665-d1c9-52f7-8d80-0c4d9c1fa5ac |  | date | Work Completed On
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification.
date | a830ad51-576f-55e6-9a32-83c1a92d4d35 |  | date | Work Commenced On
select | fcff1708-c595-5008-a4f0-fdd2b60138ce |  | dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | 3edba94f-2506-5535-b24b-8d39c3db3472 |  | dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | f5ff53c6-2565-5c1a-9981-0d5b70ab139d |  | dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | a5f0bdc7-2506-5ac8-bbf8-137121ad574d |  | dropdown | Lot Plan or “Highlighted” IFC drawings (mud maps) attached to the Lot? | YES, NO, N/A
select | 378e89ce-bf12-518a-8394-ac6a9ff6e4c9 |  | dropdown | Survey conformance records attached to the Lot? | YES, NO, N/A
select | 5d676944-6e02-5b48-8ddd-a198440302f7 |  | dropdown | Subcontractor/ Supplier records attached to the Lot? | YES, NO, N/A
select | b3e540a6-d4bb-5e60-88ef-5e50851816a2 |  | dropdown | Conforming Test Results attached to the Lot? | YES, NO, N/A
select | 7c2c7bbf-4b4e-5d69-9807-b445c40aff63 |  | dropdown | As built records attached to the Lot? | YES, NO, N/A
select | b72e2c20-747e-5f13-ba8f-6f3fb907d1bf |  | dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | a00093ab-f787-54fd-8180-7647eed1ccde |  | textbox | Other:
select | 3be21c63-a9b1-58ff-ac70-25d8ed8f1cca |  | dropdown | Lot Status | OUTSTANDING, CLOSED
date | d9464837-6038-55ed-a9cf-ed405bcb6f5a |  | date | Lot Closed On
text | cd47d41e-ddf0-592c-9d85-70fc9fa34bbb |  | textbox | comments