## QA Folder Structure
QA
A40 Structure
level B2 - Tunnel
Foundations
Lift pit
Walls
Slab
Level B1 - Lower isolation
Foundations
Lift pit
Columns
Walls
Slab
Tunnel
Other
Level 00 - Upper isolation
Insitu beams
Slab
Columns
Walls
Precast wall stitch
Precast beam stich
Other
Level 01
Insitu beams
Slab
Columns
Walls
Precast wall stitch
Precast beam stich
Other
Level 02
Insitu beams
Slab
Columns
Walls
Precast wall stitch
Precast beam stich
Other
Level 03
Insitu beams
Slab
Columns
Walls
Precast wall stitch
Precast beam stich
Other
Level 04
Insitu beams
Slab
Columns
Walls
Precast wall stitch
Precast beam stich
Other
Level 05
Insitu beams
Slab
Columns
Walls
Precast wall stitch
Precast beam stich
Other
Level 06
Insitu beams
Slab
Columns
Walls
Precast wall stitch
Precast beam stich
Other
Tunnel
Zone TF
Capping beam
Base slab
Roof slab
Walls
Other
Zone TD
Capping beam
Base slab
Roof slab
Walls
Other
Zone TC
Capping beam
Base slab
Roof slab
Walls
Other
Zone TB
Capping beam
Base slab
Roof slab
Walls
Other
Zone TA
Capping beam
Base slab
Roof slab
Walls
Other

## Tools Inventory
Tools & Equipment
| Section | Stihl Cut-Off Petrol Saw
| Checkpoint |  | CR Number
| Checkpoint |  | Photo
| Section | Electric (7") Angle Grinder
| Checkpoint |  | CR Number
| Checkpoint |  | Tag Tested Date
| Checkpoint |  | Photo
| Section | Electric (5") Angle Grinder
| Checkpoint |  | CR Number
| Checkpoint |  | Tag Tested Date
| Checkpoint |  | Photo
| Section | Electric (5") Angle Grinder Cordless
| Checkpoint |  | CR Number
| Checkpoint |  | Photo
| Section | Cordless Impact Driver
| Checkpoint |  | CR Number
| Checkpoint |  | Photo
| Section | Portable Stick Welder
| Checkpoint |  | CR Number
| Checkpoint |  | Welding Gloves
| Checkpoint |  | Welding Helmet
| Checkpoint |  | Photo
| Section | Electrical Leads
| Checkpoint |  | Tag Tested Date
| Checkpoint |  | Photo
| Section | Bolt Cutter
| Checkpoint |  | Photo
| Section | Dog Bars
| Checkpoint |  | Quantity
| Checkpoint |  | Photo
| Section | Cutter Bender
| Checkpoint |  | Photo
| Section | Ramset Epoxy Gun Electric
| Checkpoint |  | CR Number
| Checkpoint |  | Photo
| Section | Ramset Epoxy Gun Manual
| Checkpoint |  | Photo
| Section | Pipe Wrench
| Checkpoint |  | Quantity
| Checkpoint |  | Photo
| Section | Sledge Hammer
| Checkpoint |  | Photo
| Section | Spirit Level
| Checkpoint |  | Photo
| Section | 25/30m Measure Tape
| Checkpoint |  | Photo
| Section | Face Shield
| Checkpoint |  | Photo
| Section | Fire Extinguisher 3kg
| Checkpoint |  | Photo
| Section | Bar Stands
| Checkpoint |  | Photo

## Pile Caps
ADHB
Reinforcing Installation
Pile Caps
| Section | Delivery/material check
| Checkpoint |  | Detail sheet & drawing reference
| Section | Workface acceptance
| Checkpoint |  | Safe
| Checkpoint |  | Waterproofing
| Section | Pile caps
| Checkpoint |  | Pile cap reference
| Checkpoint |  | Pile starter orientation is correct
| Checkpoint |  | Welded hoops
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Stirrups/links diameter/spacing
| Section | Starter bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | IMBMS
| Checkpoint |  | Set out
| Checkpoint |  | Sufficient protruding lap
| Checkpoint |  | Starters perpendicular
| Checkpoint |  | Cover NF/FF CRITICAL
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | Reinforcing secure
| Checkpoint |  | All reinforcing steel adequately tied
| Section | Miscellaneous
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| Checkpoint |  | Penetration detail
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Checkpoint |  | Area left clean & tidy

## Ground Beams
ADHB
Reinforcing Installation
Ground Beams
| Section | Delivery/material check
| Checkpoint |  | Detail sheet & drawing reference
| Section | Prestart/area acceptance
| Checkpoint |  | Safe
| Checkpoint |  | Blinding level surveyed
| Checkpoint |  | Setout
| Section | Top bars
| Checkpoint |  | T1 Bar diameter/grade/spacing
| Checkpoint |  | T2 Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | Development length into pile cap
| Checkpoint |  | Returns 90 degrees
| Checkpoint |  | Cover to perimeter
| Checkpoint |  | All bars adequately tied
| Section | Bottom Bars
| Checkpoint |  | B1 Bar diameter/grade/spacing
| Checkpoint |  | B2 Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | Development length into pile cap
| Checkpoint |  | Returns 90 degrees
| Checkpoint |  | Cover to perimeter
| Checkpoint |  | All bars adequately tied
| Section | Stirrups/links
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct dimensions
| Checkpoint |  | Trimmers to penetrations/openings & additional stirrups
| Checkpoint |  | All bars adequately tied
| Section | Column starters
| Checkpoint |  | Bar diameter/quantity/correct protruding lap
| Checkpoint |  | Couplers in lieu of starters
| Section | Starters beam/wall/panel/floor
| Checkpoint |  | Template
| Checkpoint |  | Bar diameter/quantity/correct protruding lap
| Checkpoint |  | Couplers in lieu of starters
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | Miscellaneous
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| Checkpoint |  | Penetration detail
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Checkpoint |  | Area left clean & tidy

## Lift Pit
ADHB
Reinforcing Installation
Lift Pit
| Section | Delivery/material check
| Checkpoint |  | Detail sheet & drawing reference
| Section | Workface acceptance
| Checkpoint |  | Safe
| Checkpoint |  | Blinding levels correct/waterproofing/setout
| Section | Base slab top & bottom
| Checkpoint |  | Bar diameter/grade/spacing
Links diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | Staggered laps
| Section | Ground beams
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Section |  | Stirrup diameter/grade/spacing
| Checkpoint |  | Correct dimensions
| Section | Sump
| Checkpoint |  | Location
| Checkpoint |  | Trimmers
| Section | Starter bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Sufficient protruding lap
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | Reinforcing secure
| Checkpoint |  | All reinforcing steel adequately tied
| Section | Miscellaneous
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Checkpoint |  | Area left clean & tidy

## Slab on Ground
ADHB
Reinforcing Installation
Slab Ground
| Section | Delivery/material check
| Checkpoint |  | Detail sheet & drawing reference
| Checkpoint |  | Blinding RL surveyed and correct
| Section | Slab reinforcing
| Checkpoint |  | Mesh SE82
| Checkpoint |  | Mesh laps
| Checkpoint |  | H12 perimeter bars
| Checkpoint |  | H16 edge bar
| Checkpoint |  | D12 bend down starters
| Checkpoint |  | Epoxy starter bars
| Checkpoint |  | Strip drain reinforcing
| Checkpoint |  | Insitu around tunnel/openings
| Checkpoint |  | Trimmers to penetrations/openings
| Section | Starters vertical/horizontal
| Checkpoint |  | Template
| Checkpoint |  | Bar diameter/quantity/correct protruding lap
| Checkpoint |  | Couplers in lieu of starters
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | Reinforcing secure
| Checkpoint |  | All reinforcing steel adequately tied
| Section | Miscellaneous
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Checkpoint |  | Area left clean & tidy

## Column Insitu
ADHB
Reinforcing Installation
Columns
| Section | Delivery/material check
| Checkpoint |  | Detail sheet & drawing reference
| Section | Workface acceptance
| Checkpoint |  | Safe
| Checkpoint |  | Set out
| Checkpoint |  | Starters perpendicular (not bent by other trades)
| Section | Column
| Checkpoint |  | Bar diameter/quantity/correct protruding lap
| Checkpoint |  | Couplers in lieu of starters. TYPE?
| Checkpoint |  | Stirrups/links diameter/grade/spacing
| Checkpoint |  | Stirrups/links to top of concrete pour
| Checkpoint |  | Holding stirrup at top of column
| Checkpoint |  | All bars and stirrups adequately tied
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Checkpoint |  | Area left clean & tidy

## Suspended Slab
ADHB
Reinforcing Installation
Suspended Slab
| Section | Delivery/material check
| Checkpoint |  | Detail sheet & drawing reference
| Section | Workface acceptance
| Checkpoint |  | Safe
| Section | Slab
| Checkpoint |  | Typical slab bar diameter/grade/spacing
| Checkpoint |  | Alternating perimeter L-bars-300CRS & 150CRS at K-frame locations
| Checkpoint |  | Alternating L-bars-300CRS on internal GL's
| Checkpoint |  | Drag bar diameter/grade/quantity/spacing
| Checkpoint |  | Trimmer bar diameter/grade/quantity/spacing/45 degree at corners
| Checkpoint |  | Restraint bars into columns
| Checkpoint |  | H16-150-EW-T&B in hatched locations
| Checkpoint |  | Other
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | Miscellaneous
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Checkpoint |  | Area left clean & tidy

## PC Beam & Stitch
ADHB
Reinforcing Installation
PC Beam Stitch
| Section | Delivery/material check
| Checkpoint |  | Detail sheet & drawing reference
| Section | Workface acceptance
| Checkpoint |  | Safe
| Checkpoint |  | Starters from protruding from PC Beams as per drawings/no re-bending
| Section | Longitudinal T/B & sides
| Checkpoint |  | Correct laps
| Section | Stirrups/links
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct dimensions
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | Reinforcing secure
| Checkpoint |  | All reinforcing steel adequately tied
| Section | Miscellaneous
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| section | Review & Handover
| checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint |  | Area left clean & tidy

## Panel Stitches
TH-01
Reinforcing Installation
Panel Stitches
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Checkpoint |  | Detail sheet #
| Section | Workface acceptance
| Checkpoint |  | Safe
| Checkpoint |  | Starters from protruding from panels as per drawings/no re-bending
| Section | Verticals NF/FF
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct level at base
| Checkpoint |  | Correct length
| Checkpoint |  | Correct laps
| Checkpoint |  | Sufficient protruding lap
| Checkpoint |  | Top cover where returns terminate
| Checkpoint |  | Trimmers to penetrations/openings
| Section | Horizontals/stirrups/links
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct dimensions
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | Reinforcing secure
| Checkpoint |  | All reinforcing steel adequately tied
| Section | Miscellaneous
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| section | Review & Handover
| checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint |  | Area left clean & tidy

## Shear Wall
TH-01
Reinforcing Installation
Shear Wall
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Checkpoint |  | Detail sheet #
| Section | Workface acceptance
| Checkpoint |  | Safe
| Section | Wall verticals
| Checkpoint |  | Starter height, bar diameter
| Checkpoint |  | Main bar diameter/grade, quantity, and lap
| Checkpoint |  | Correct laps & staggered
| Checkpoint |  | Staggered laps
√ | Checkpoint |  | All bars adequately tied
| Section | Wall horizontals
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | All bars adequately tied
| Section | Stirrups/Links
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Adequately tied
| Section | Cage
| Checkpoint |  | Cage Correct Overall Length
| Checkpoint |  | Cage Correct Overall Width
| Checkpoint |  | Cage Correct Overall Height
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | 1st handover for cast-ins
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Checkpoint |  | Area left clean & tidy
| Section | Final review
| Checkpoint |  | All reinforcing tied back correctly
| Checkpoint |  | All starters postioned correctly
| Checkpoint |  | Cover blocks/chairs/spacers

## Crane Base Insitu
Job
Reinforcing Installation
Crane Base
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Section | Workface acceptance
| Checkpoint |  | Safe
| Checkpoint |  | Blinding levels correct/waterproofing/setout
| Section | Piles
| Checkpoint |  | Starters perpendicular
| Checkpoint |  | Piles - Cut off height & linished
| Checkpoint |  | Flange nuts fixed and epoxied
| Checkpoint |  | Hoops/spiral installed with correct diameter/grade/spacing
| Section | Bottom bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | Staggered laps
| Checkpoint |  | All bars adequately tied
| Section | Top bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | Staggered laps
| Checkpoint |  | All bars adequately tied
| Section | Side bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | All bars adequately tied
| Section | Stirrups/links
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | All bars adequately tied
| Section | Starter bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Sufficient protruding lap
| Section | Miscellaneous
| Checkpoint |  | Cast-ins/Crane legs
| Section | Housekeeping
| Checkpoint |  | All loose items removed off workface
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Holdpoint |  | Request Review
| Checkpoint |  | Area left clean & tidy

## Foundations
TH-01
Reinforcing Installation
Foundations
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Checkpoint |  | Detail sheet #
| Section | Workface acceptance
| Checkpoint |  | Safe
| Section | Pile cap
| Checkpoint |  | Stirrups/links diameter/spacing
| Checkpoint |  | U-bars diameter/spacing
| Section | GB top bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Section | GB bottom Bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Section | GB Stirrups/links
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct dimensions
| Checkpoint |  | Penetration thickening
| Section | GB Side bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Section | Starter bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Set out
| Checkpoint |  | Sufficient protruding lap
| Checkpoint |  | Drossbach template installed for panel starters
| Checkpoint |  | Starters braced and perpendicular
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | Reinforcing secure
| Checkpoint |  | All reinforcing steel adequately tied
| Section | Miscellaneous
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Checkpoint |  | Area left clean & tidy

## Slab Comflor
Totara Haumaru
Reinforcing Installation
Slab Comflor
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Section | Workface acceptance
| Checkpoint |  | Safe
| Section | Slab Comflor
| Checkpoint | C80/250 | H16-200 CRS-EW and SE62 Mesh
| Checkpoint | C80/180 | H12-200 CRS-EW and SE62 Mesh
| Checkpoint | C80/200 | H16-200 CRS-EW
| Checkpoint |  | Trough bars 30mm bottom cover
| Checkpoint |  | Typical trimmers at slab edge and openings
| Checkpoint |  | Diaphragm/Drag bar reo
| Checkpoint |  | Saddle bars running E-W
| Checkpoint |  | Edge hairpins and nosing bar
| Checkpoint |  | T1 Connections
| Checkpoint |  | Bar laps
| Checkpoint |  | Mesh laps
| Checkpoint |  | Correct laps at step
| Checkpoint |  | Nibs - note location
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | Miscellaneous
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Checkpoint |  | Area left clean & tidy

## Capping Beam
Job
Reinforcing Installation
Capping Beam
| Section | Delivery/Material Check
| Checkpoint |  | Material delivered to site correct
| Section | Workface Acceptance
| Checkpoint |  | Safe
| Checkpoint |  | Blinding levels correct/waterproofing/setout
| Section | Piles
| Checkpoint |  | Orientation
| Checkpoint |  | Correct height
| Checkpoint |  | Hoops bar diameter/grade/spacing
| Checkpoint |  | Hoops welded laps
| Section | Top Bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | All bars adequately tied
| Section | Bottom Bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | Staggered laps
| Checkpoint |  | All bars adequately tied
| Section | Side Bars
| Checkpoint |  | NF/FF Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | 40mm IMBMS couplers fitted and aligned
| Section | Stirrups/Links
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct dimensions
| Section | Footpath Starters
| Checkpoint |  | Setout correct
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct dimensions
| Section | Miscellaneous
| Checkpoint |  | Penetrations/trimmers
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Holdpoint |  | Request Review
| Checkpoint |  | Area left clean & tidy

## Stair Landing
Job
Reinforcing Installation
Location
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Checkpoint |  | Material at a minimum 1 level above or below
| Section | Prestart/area acceptance
| Checkpoint |  | Workface ready and clear
| Checkpoint |  | Setout
| Checkpoint |  | Safe access
| Checkpoint |  | Edge protection
| Checkpoint |  | Starters from panel/slab/wall pre-bent & straight
| Checkpoint |  | Panel/slab/wall coupler inserts have are clean and at correct levels
| Section | Cover blocks
| Checkpoint |  | Correct type/size
| Section | Stair landing reinforcing
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Starters screwed in & epoxied
| Checkpoint |  | Correct laps
| Checkpoint |  | Trimmers to penetrations/openings
| Checkpoint |  | Cover top, bottom and sides
| Section | Housekeeping
| Checkpoint |  | All loose items removed off workface
| section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Holdpoint |  | Request review
| Checkpoint |  | Area left clean & tidy

## Slab Mesh
Job
Reinforcing Installation
Slab Level 1
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Section | Prestart/area acceptance
| Checkpoint |  | Workface ready and clear
| Checkpoint |  | Level correct
| Checkpoint |  | Setout
| Checkpoint |  | Safe access
| Checkpoint |  | Edge protection
| Section | Cover blocks
| Checkpoint |  | Correct type/size
| Checkpoint |  | Sufficient spacing to avoid sagging
| Section | Slab reinforcing
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Perimeter slab starters
| Checkpoint |  | Perimeter longitudinal. Positioned correctly either side of studs
| Checkpoint |  | Saddle bars over beams and walls
| Checkpoint |  | Cantilever steel
| Checkpoint |  | Drag bars
| Checkpoint |  | Column additional steel
| Checkpoint |  | Insitu slabs HD12-125EW
| Checkpoint |  | Correct laps
| Checkpoint |  | Correct mesh type SE62
| Checkpoint |  | Correct laps SE62
| Checkpoint |  | Insitu around openings and stairs
| Checkpoint |  | Trimmers to penetrations/openings
| Checkpoint |  | Cover top, bottom and sides
| Section | Housekeeping
| Checkpoint |  | All loose items removed off workface
| section | Review & Handover
| checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| holdpoint |  | Request Review
| checkpoint |  | Area left clean & tidy