## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | FC - S - Soffits |  |  |  |  | Yes | FC - S - Soffits | 0049b72e-380b-497e-9afc-55c0c6ae4e21
checkpoint-group |  |  | section | Pre-Installation Checks
checkpoint-status |  |  | checkpoint | Wiring in and anchored down for downlights, checked and accurate
checkpoint-status |  |  | checkpoint | Air Conditioning pre wire and pipe completed and acceptable
checkpoint-status |  |  | checkpoint | Fire sprinklers droppers installed and acceptable
checkpoint-group |  |  | section | Soffits works checks
checkpoint-status |  |  | checkpoint | Framing completed, checked and accurate including sheet joins/blocking
checkpoint-status |  |  | checkpoint | Framing centre correct at 600mm centres, including set out to allow all sheets joints to be fully supported
checkpoint-status |  |  | checkpoint | Villaboard installed, stopped and painted, checked and acceptable
checkpoint-status |  |  | checkpoint | Plaster installed as per spec and painted and acceptable
checkpoint-status |  |  | checkpoint | All soffits completed and acceptable
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | FC - S - External Plaster - Nibs & Beams |  |  |  |  | Yes | FC - S - External Plaster - Nibs & Beams | 01b4cdda-8074-4419-86b9-15ff176c36ac
checkpoint-status |  |  | checkpoint | All nibs/ beams prepared for plaster checked and acceptable
checkpoint-status |  |  | checkpoint | Saddle flashing installed to deck ends, checked and accurate
checkpoint-status |  |  | checkpoint | Falls set to 5 degrees as per plan - 20mm Fall over 200mm checked and accurate
checkpoint-status |  |  | checkpoint | Corner and drip edge flashings installed correctly and acceptable
checkpoint-status |  |  | checkpoint | Plaster installed as per spec and painted, checked and acceptable
checkpoint-status |  |  | checkpoint | All cladding works completed and acceptable
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | Soffits QA |  |  |  |  | Yes | Soffits QA | 3581f1e7-6eed-4254-acd8-c6a7f95cdcd3
checkpoint-group |  |  | section | Preinstall QA
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Substrate acceptable and ok to begin work
holdpoint |  |  | signoff | Request Review/ Raise Remedial
checkpoint-group |  |  | section | Install QA
checkpoint-status |  |  | checkpoint | All framing installed, true and level
checkpoint-status |  |  | checkpoint | Framing centre correct at 600mm centres, including set out to allow all sheets joints to be fully supported
checkpoint-status |  |  | checkpoint | Wiring in and anchored down for downlights
checkpoint-status |  |  | checkpoint | Air Conditioning pre wire and pipe completed
checkpoint-status |  |  | checkpoint | Fire sprinklers droppers installed
checkpoint-status |  |  | checkpoint | Villaboard installed, stopped and painted
checkpoint-status |  |  | checkpoint | Plaster installed as per spec and painted
holdpoint |  |  | signoff | Request Trade Contractor QA & Sign Off Sign Off
checkpoint-status |  |  | checkpoint | All soffits completed correctly
checkpoint-group |  |  | section | Handover QA
checkpoint-status |  |  | checkpoint | All works completed as per spec
holdpoint |  |  | signoff | Raise Remedial / Request Sign Off
checklist-flat |  |  | checklist | Pre Commencement Checks |  |  |  |  | Yes | Pre Commencement Checks | 4d15ec47-c34d-47f2-a6ae-5cd52417ed44
checkpoint-status |  |  | checkpoint | Quality Management Plan Completed, Agreed & Attached
checkpoint-status |  |  | checkpoint | Inspection & Test Plan Completed, Agreed & Attached
checkpoint-status |  |  | checkpoint | Relevant Breakdown & Checklists Setup on Conqa & Reviewed by Main Contractor
checkpoint-status |  |  | checkpoint | Conqa Setup & Project Team Trained & Given Access
checkpoint-status |  |  | checkpoint | Review Access Granted to Main Contractor & Relevant Parties
checkpoint-status |  |  | checkpoint | Matrix/insights Setup (if required)
checklist-flat |  |  | checklist | Handover checklist |  |  |  |  | Yes | Handover checklist | 4eecf34b-ce4d-401b-8ec7-2dfb04cddc00
checkpoint-status |  |  | checkpoint | PS3s, warranties, user manuals and any other documents attached
checklist-sectioned |  |  | checklist | Sto Poly Plaster QA |  |  |  |  | Yes | Sto Poly Plaster QA | 556ce35c-08d1-47d0-94ba-231f70723e83
checkpoint-group |  |  | section | Preinstall QA
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Substrate acceptable and ok to begin work
holdpoint |  |  | signoff | Request Review/ Raise Remedial
checkpoint-group |  |  | section | Install QA
checkpoint-status |  |  | checkpoint | Moisture Barrier
select | e23be043-4916-5947-a9af-431ff7559f18 |  | dropdown | Type: | Paper,RAB
checkpoint-status |  |  | checkpoint | All joints/penetrations/openings taped as per specs
checkpoint-status |  |  | checkpoint | All windows installed, with air barrier sealant applied
checkpoint-status |  |  | checkpoint | All head flashings are installed 3mm past end of window
checkpoint-status |  |  | checkpoint | Installation of foot tray, windows flashings and battens
checkpoint-status |  |  | checkpoint | Appropriate fixings used at correct centres for poly cladding
checkpoint-status |  |  | checkpoint | All cladding completed correctly
checkpoint-status |  |  | checkpoint | Meshcoat to plaster, banding installed, true and flat
checkpoint-status |  |  | checkpoint | Topcoat k and painted
checkpoint-group |  |  | section | Handover QA
checkpoint-status |  |  | checkpoint | All works completed as per spec
holdpoint |  |  | signoff | Raise Remedial / Request Sign Off
checklist-sectioned |  |  | checklist | Plastered Nibs & Beams QA |  |  |  |  | Yes | Plastered Nibs & Beams QA | 80885645-ca54-4df5-b607-0fab648514be
checkpoint-group |  |  | section | Preinstall QA
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Substrate acceptable and ok to begin work
holdpoint |  |  | signoff | Request Review/ Raise Remedial
checkpoint-group |  |  | section | Install QA
checkpoint-status |  |  | checkpoint | All nibs/ beams prepared for plaster
checkpoint-status |  |  | checkpoint | Saddle flashing installed to deck ends
checkpoint-status |  |  | checkpoint | Falls set to 5 degrees as per plan - 20mm Fall over 200mm
checkpoint-status |  |  | checkpoint | Corner and drip edge flashings installed correctly
checkpoint-status |  |  | checkpoint | Plaster installed as per spec and painted
holdpoint |  |  | signoff | Request Trade Contractor QA & Sign Off Sign Off
checkpoint-status |  |  | checkpoint | All cladding completed correctly
checkpoint-group |  |  | section | Handover QA
checkpoint-status |  |  | checkpoint | All works completed as per spec
holdpoint |  |  | signoff | Raise Remedial / Request Sign Off
checklist-flat |  |  | checklist | FC - S - STO Poly Plaster |  |  |  |  | Yes | FC - S - STO Poly Plaster | ba88807e-dc2b-4f51-a43f-434e85d3803a
checkpoint-status |  |  | checkpoint | Moisture Barrier installed with correct fixings & fixing pattern, checked and acceptable
checkpoint-status |  |  | checkpoint | All joints/penetrations/openings taped as per specs, checked and accurate
checkpoint-status |  |  | checkpoint | All windows installed, with air barrier sealant applied, checked and accurate
checkpoint-status |  |  | checkpoint | All head flashings are installed 3mm past end of window and acceptable
checkpoint-status |  |  | checkpoint | Foot tray, windows flashings and battens installed, checked and acceptable
checkpoint-status |  |  | checkpoint | Appropriate fixings used at correct centres for poly cladding, checked and acceptable
checkpoint-status |  |  | checkpoint | All cladding works completed and acceptable
checkpoint-status |  |  | checkpoint | Mesh Coat to plaster, banding installed, true and flat and acceptable
checkpoint-status |  |  | checkpoint | Topcoat and paint works completed and acceptable
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | Completion Documents |  |  |  |  | Yes | Completion Documents | ce44d876-5ec0-40d0-bc3f-ae9516a61710
checkpoint-status |  |  | checkpoint | PS3 (STO Plaster Systems)
checkpoint-status |  |  | checkpoint | Manufacturer's Product warranty
checkpoint-status |  |  | checkpoint | PS3 (STOTHERM Cavity & Insulation System)
checkpoint-status |  |  | checkpoint | Product Warranty - ‘STO Plaster System’
checkpoint-status |  |  | checkpoint | Maintenance manuals
checkpoint-status |  |  | checkpoint | James Hardie, Villaboard Installation - (PS3)
checkpoint-status |  |  | checkpoint | James Hardie, Villa board product warranty
checklist-sectioned |  |  | checklist | Sto Poren Panel Plaster QA |  |  |  |  | Yes | Sto Poren Panel Plaster QA | e60c1477-1329-4a31-b08f-0aa3ca9cf4aa
checkpoint-group |  |  | section | Preinstall QA
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Substrate acceptable and ok to begin work
holdpoint |  |  | signoff | Request Review/ Raise Remedial
checkpoint-group |  |  | section | Install QA
checkpoint-status |  |  | checkpoint | Moisture Barrier
select | cdb3afe6-a10f-5c8c-9032-58fc491b48f2 |  | dropdown | Type: | Paper,RAB
checkpoint-status |  |  | checkpoint | All joints/penetrations/openings taped as per specs
checkpoint-status |  |  | checkpoint | All windows installed, with air barrier sealant applied
checkpoint-status |  |  | checkpoint | All head flashings are installed 3mm past end of window
checkpoint-status |  |  | checkpoint | Installation of foot tray, windows flashings and battens
checkpoint-status |  |  | checkpoint | Appropriate fixings used at correct centres for Poren Panel cladding
checkpoint-status |  |  | checkpoint | All cladding completed correctly
checkpoint-status |  |  | checkpoint | Meshcoat to plaster, banding installed, true and flat
checkpoint-status |  |  | checkpoint | Topcoat k and painted
checkpoint-group |  |  | section | Handover QA
checkpoint-status |  |  | checkpoint | All works completed as per spec
holdpoint |  |  | signoff | Raise Remedial / Request Sign Off