## Project Breakdown
INSERT PROJECT NAME HERE |  |  | Checklists
QA / ITP's
Kingspan Roof
|  | Box Gutter | Box Gutter Installation checklist
|  | Kingspan Roof | Kingspan Installation checklist
|  | Flashing/Capping | Flashing/Capping Installation Checklist
Wall Cladding - East, West Elevation
|  | Kingspan Wall Cladding | Kingspan Wall Cladding checklist
|  | Askin Wall Cladding | Askin Wall Cladding checklist
|  | Flashing/Capping | Flashing/Capping Installation Checklist
Wall Cladding - North Elevation
|  | Kingspan Wall Cladding | Kingspan Wall Cladding checklist
|  | Askin Wall Cladding | Askin Wall Cladding checklist
|  | Flashing/Capping | Flashing/Capping Installation Checklist
Variations
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
OH&S
Daily Prestart Toolbox Forms
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Weekly Toolbox Forms
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
SWMS
Onsite Material Install Form1
Foremans Diary Reports
COVID Tracking Reports
Delivery Dockets | Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Checklist Library | Add Delivery Docket
Add Non Conformance Corrective Action Report
Add Offhire Information
Add Onsite Material Install Form
Add Pre-Start Tool Box
Add Tool Box Training
Add Variation
Inspection Reports | Wire Mesh Install
Handrail Install

## Example Project Area
INSERT PROJECT AREA NAME HERE
type | name | values
checklist | Insulation checklist
section | Material Inspection
checkpoint | Insulation: Roof sarking on medium weight paper
100mm glasswool on medium sarking
checkpoint | Thermal spacer: 80mm thermal spacer
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation checklist
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Monoclad
checkpoint | Coating Type: Standard Colorbond
checkpoint | Insulation Type: Roof sarking on medium weight paper
checkpoint | 100mm glasswool on medium sarking
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: Monoclad screws
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations checklist
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Roof Ventilator: Ventlite 410mm Roof with Colorbond base
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | to fit the purpose.
checkpoint | Adequate support around penetration to prevent roof
checkpoint | sheet from buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Soffit Cladding checklist
section | Material Inspection
checkpoint | Soffit Cladding type: 0.42mm Colorbond Matt Mini Corry
checkpoint | Top hat support: 0.75mm tophat
checkpoint | Flashing Material: 0.61mm Colorbond
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Wall Cladding checklist
section | Material Inspection
checkpoint | Wall Cladding type: 0.48mm Kliplok Colorbond Matt
checkpoint | Top hat support: 0.75mm x 25mm Top Hat
checkpoint | Flashing Material: 0.61mm Colorbond Matt
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation checklist
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Insulation under gutter: Sisalation
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Box Gutter: 0.61mm Colorbond
checkpoint | Gutter Flashing: Colorbond to match
checkpoint | Sumps / Outlets: 0.61mm Colorbond
checkpoint | Overflows:
section | Installation
checkpoint | Sump Depth adheres with AS3500:3 p.38
checkpoint | Box Gutter depth adheres with AS 3500:3 p.37
checkpoint | Gutter Brackets installed with fall as per Specification (no less than 1:200)
checkpoint | Gutter Brackets installed no greater than 750mm Centre to Centre
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | lower most part of Gutter flashing are at least 100mm off from sole of the box gutter
checkpoint | pops are installed from underside of the sump
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Quad Gutter Installation Checklist
section | Material Inspection
checkpoint | Metal fascia: 0.61mm Colorbond
checkpoint | Quad Gutter: Quad gutter 115
checkpoint | Half round 200mm
checkpoint | Quad Gutter Brackets: Quad gutter 115
checkpoint | Half round 200mm
checkpoint | Gutter Flashing:
checkpoint | Stop ends: 115mm Quad stop ends
checkpoint | Downpipes:
checkpoint | Pops: 0.61mm Colorbond
section | Installation
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Downpipe installed as shown on drawings and correct
checkpoint | size and connected to stormwater
checkpoint | Downpipe installed straight and bolted to downpipe clip
checkpoint | Downpipe spreader installed as shown on drawing
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Ortech Installation Checklist
section | Material Inspection
checkpoint | Ortech Material: S50 Plain Durra Board
checkpoint | S50 Cement Sheet Faced Durra Boards
checkpoint | Durra Panel - S50 Soundsorb Fabric Finish
checkpoint | Powdercoating Durra Beams and T-Units
checkpoint | Ortech Beams: Durra Beam (Lowder)
checkpoint | Ortech T-Units: T- Unit (lower)
checkpoint | Ortech Accessories: Aluminium Angles (Bottom & Top of Panels)
checkpoint | Caulking to Precast
checkpoint | Caulking to Stub Colums
checkpoint | Durra Panel Wedges - Lower
checkpoint | Aluminium Sealing Tape - Lower
checkpoint | Ortech Screw/Fixings: Durra Beam Bolts
T-Unit Fixings
section | Installation
checkpoint | Select correct beam type and length
checkpoint | Layout beams in correct alignment
checkpoint | Select correct Tee units
checkpoint | Ensure Tee units screw fitted securely in grid
checkpoint | Durra panels installed fitted firmly into beams/tees
checkpoint | Wedge cleats installed locking Durra panel securely in place
checkpoint | Inspection durra panel for perforation
checkpoint | Repair and perforations with aluminium sealing tape.
checkpoint | Review tightness of all bolts and prior to lifting
checkpoint | Attach Ortech lifting jig
checkpoint | Elevate and visually inspect underneath for defects or misalignment
checkpoint | Confirm finsihed ceiling is free from defects
checkpoint | Place module in position and complete connections to cleats
checkpoint | Review connections prior to dis-engaging lifting frame
checkpoint | Ortech and Durra panel not exposed to weather for long periods prior to installation.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Parapet Wall Cladding checklist
section | Material Inspection
checkpoint | Parapet Wall Cladding type: 0.48mm Kliplok Colorbond Matt
checkpoint | Top hat support: 0.75mm Top Hat
checkpoint | Flashing Material: 0.61mm Colorbond Matt
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Ampelite Polycarbonate Installation checklist
section | Material Inspection
checkpoint | Material Item: Ampelite Cool lite GC 2400gsm Kliplok Profile
checkpoint | Purlin Strips for Fibreglass
checkpoint | Screws and Washers for Fibreglass
checkpoint | Other: Dual Fibreglass Roof System?
section | Installation
checkpoint | Are the oversize holes up to 15mm diameter and drilled at all fixing points
checkpoint | Are the side lap perimeters sealed with thick sealing foam strips
checkpoint | Material installed as per Ampelites recommendations.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Fascia Gutter checklist
section | Material Inspection
checkpoint | Fascia Gutter Brackets: Standard Colorbond
checkpoint | Fascia Gutter: Standard Colorbond
checkpoint | Gutter Flashing: 0.55mm Standard Colorbond
checkpoint | Fascia Board Accessories: Junction stud/top hat to support Fascia
section | Installation
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Kingspan Installation checklist
section | Material Inspection
checkpoint | Panel:
checkpoint | Internal liner colour:
checkpoint | External liner colour
checkpoint | Buildex fixings 14 x 95mm SDS - bonded washer
checkpoint | buildex type 17 12 x 20mm stitching screws
checkpoint | 6mm Kingspan Butyl tape
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Kingspan Spec
checkpoint | Panels located correctly
checkpoint | Fixings as per Kingspan Spec
checkpoint | Stitching screws 350mm centres
checkpoint | Four way lapped joins installed correctly
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Ampelite EEFAS Installation checklist
section | Material Inspection
checkpoint
checkpoint
checkpoint
checkpoint
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Ampelite EEFAS system spec
checkpoint | Panels located correctly
checkpoint | Fixings as per EEFAS system Spec
checkpoint | Stitching screws 350mm centres
checkpoint | Four way lapped joins installed correctly
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Eurobond Installation checklist
section | Material Inspection
checkpoint | Wall Cladding - 150mm Insulated Panel - Eurobond Rainspan
checkpoint | Insulated Panel Wall Cladding - Butyl Tape to Side Laps
checkpoint | RS1 - Base Support to bottom of panels (Rainscreen 150mm)
checkpoint | Insulated Panel Wall Cladding - Airseal tape to Panel Top & Bottom
checkpoint | Insulated Panel Wall Cladding - 150mm Panel Screws
checkpoint | Wall Cladding Top Hat - 1.6mm - Ledger Angle to base of panels
checkpoint | Wall Flashing - 0.61mm Colorbond - Wall Trim - 200mm - Internal
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Top Trim - 200mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Internal Trim - 200mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Wall Trim - 400mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Foot Flashing 400mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Louvre Trim - 400mm
checkpoint | Wall Penetration - 1000mm x 1000mm
checkpoint | Wall Penetration - Downpipe penetrations
checkpoint | Wall Penetration - Outrigger screen penetrations
checkpoint | Wall Penetration - Overflows through facade
checkpoint | Butyl tape to wall flashings
section | Installation
checkpoint | Eurobond Firemaster panel to span between floor levels
checkpoint | Fireban caulking inserted to all panel joins
checkpoint | Gal support angles installed with masonry fixings
checkpoint | 300mm centres and caulked to concrete
checkpoint | 3mm top movement angle with slotted holes to allow minus 10mm + 25mm movement as per project engineer
checkpoint | All flashings installed with fireban caulking and compliant fixings
checkpoint | Panel fixed at base with stainless steel 197mm screws x 4 in each panel
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Dridesign - Zone 3 - Section C - Wall
checklist | Dridesign Installation checklist
checkpoint | Dri Design Panels - Aluminium panels - non perforated
checkpoint | Dri Design Panels - Aluminium panels - 80m2 only perforated to bleacher area
checkpoint | Insulation - Wall - Acoustic Black Perforated - 50mm
checkpoint | Metal Wall Cladding - Custom On Site Panel
checkpoint | PVC Tape to the rear of the Cassette Top Flanges
section | Installation
checkpoint | Aluminium - Small face extrusion
checkpoint | Aluminium - Wall Trim - 400mm
checkpoint | Aluminium - Window Trim - 400mm
checkpoint | Aluminium - Foot Flashing - stepped to stairs
checkpoint | Wall Penetration - Overflow slots through facade
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Rosanna Strips
section | Material Inspection
checkpoint | Insulated Panel Wall Cladding - Rosanna External Top Hats
section | Installation
checkpoint | Rosanna Strips: Straight and in correct plane.
checkpoint | Plumbness
checkpoint | Adequate Fixings according to Manufacturer's Specification
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Kingspan Roof
Kingspan Roof
type | name | values
checklist | Box Gutter Installation checklist
section | Material Inspection
checkpoint | Box Gutter Brackets: Size #2
checkpoint | Insulation under gutter: White Sarking
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Kingspan Gutterboard
checkpoint | Box Gutter: 0.61mm Colorbond
checkpoint | Box Gutter: Kingspan K10 x 60mm
checkpoint | Gutter Flashing: Colorbond to match
checkpoint | Sumps / Outlets: 0.61mm Colorbond
checkpoint | Overflows:
section | Installation
checkpoint | Sump Depth adheres with AS3500:3 p.38
checkpoint | Box Gutter depth adheres with AS 3500:3 p.37
checkpoint | Gutter Brackets installed with fall as per Specification (no less than 1:200)
checkpoint | Gutter Brackets installed no greater than 750mm Centre to Centre
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | lower most part of Gutter flashing are at least 100mm off from sole of the box gutter
checkpoint | pops are installed from underside of the sump
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Kingspan Installation checklist
section | Material Inspection
checkpoint | Panel: 100mm Kingspan PIR Insulated Panel
checkpoint | Internal liner colour: TBC
checkpoint | External liner colour: TBC
checkpoint | Buildex fixings 14 x 95mm SDS - bonded washer
checkpoint | buildex type 17 12 x 20mm stitching screws
checkpoint | 6mm Kingspan Butyl tape
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Kingspan Spec
checkpoint | Panels located correctly
checkpoint | Fixings as per Kingspan Spec
checkpoint | Stitching screws 350mm centres
checkpoint | Four way lapped joins installed correctly
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Wall Cladding - East, West
Wall Cladding - East and West Elevation
type | name | values
checklist | Kingspan Wall Cladding checklist
section | Material Inspection
checkpoint | Wall Cladding type: 100mm Kingspan with standard liner PIR
checkpoint | Flashing Material: 0.61mm Colorbond to suit
section | Installation
checkpoint | Butyl Tape to panel
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Askin Wall Cladding checklist
section | Material Inspection
checkpoint | Wall Cladding type: 100mm Askin Xflam with Standard Liner
checkpoint | Flashing Material: 0.61mm Colorbond to suit
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Wall Cladding - North
Wall Cladding - North Elevation
type | name | values
checklist | Kingspan Wall Cladding checklist
section | Material Inspection
checkpoint | Wall Cladding type: 100mm Kingspan with standard liner PIR
checkpoint | Flashing Material: 0.61mm Colorbond to suit
section | Installation
checkpoint | Butyl Tape to panel
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Askin Wall Cladding checklist
section | Material Inspection
checkpoint | Wall Cladding type: 100mm Askin Xflam with Standard Liner
checkpoint | Flashing Material: 0.61mm Colorbond to suit
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative: