## Types (hidden)
Building 1 |  |  |  | Building 2 |  |  | Building 3 |  |  | Building 4 |  |  | Out Buildings
Ground Floor |  |  |  | Ground Floor |  |  | Ground Floor |  |  | Ground Floor |  |  | Ground Floor
Qty | Type | m2 |  | Qty | Type | m2 | Qty | Type | m2 | Qty | Type | m2 | Type
3 | Care A | 24 |  | 1 | Lounge | 67 |  | Cinema | 56 | 3 | Care A | 25 | Circulations to Building 1 & 2
4 | Care B | 24 |  | 1 | Dining | 81 |  | Staff Room | 23 | 1 | Care A | 24 | Circulations to Building 1 & 4
5 | Care C | 23 |  | 1 | Office | 13 |  | Staff Room WC 1 | 12 | 3 | Care C | 25 | Bar Lounge, Café & Store
1 | Store 1 | 10 |  | 1 | Café | 31 |  | Staff Room WC 2 | 11 | 5 | Care C | 24 | Circulation to Building 3 & 4
1 | Store 2 | 4 |  | 1 | Sales Office | 23 |  | Store | 17 |  | Dirty Utiliy | 11 | Pool, Spa, WC's, Plant Room
1 | Store 3 | 5 |  | 1 | Wind Lobby | 16 |  | Circulation | 47 |  | Circulation | 12 | Dining Room | LOT 67 DP52152
1 | Circulation 1 | 48 |  | 1 | Lounge Snug | 37 |  | Male WC | 5 |  | Circulation | 121 |  | LOT 2 DP73994
1 | Circulation 2 | 73 |  | 1 | Circulation | 125 |  | Female WC | 3 |  | Cleaners | 5 |  | Lot 1 DP73994
1 | Wind Lobby | 16 |  | 1 | Admin | 14 |  | Circulation | 13 |  | Store 1 | 6 |  | Lot 1 DP175800
1 | Whanau Room | 9 |  | 1 | Reception |  |  | Wellness | 11 |  | Store 2 | 7
1 | Quiet Room | 23 |  | 1 | Care Reception |  |  | Salon | 12
1 | Clean Utility | 14 | [5 empty] | Kitchen | 100 | NOTE: | Basement Carpark
[8 empty] | Gym | 39
1st Floor
two bed | 11.01 | 86 |  |  | Circulation | 139 |  | Circulation | 40 |  | Circulation
two bed | 11.02 | 84 |  | two bed | 12.05 | 84 | two bed | 13.03 | 89 | one bed | 14.05 | 64
two bed | 11.03 | 86 |  | two bed | 12.06 | 91 | two bed | 13.04 | 87 | one bed | 14.06 | 52
two bed | 11.04 | 84 |  | two bed | 12.07 | 106 | one bed | 13.05 | 62 | one bed | 14.07 | 52
two bed | 11.05 | 84 |  |  |  |  | two bed | 13.06 | 86 | one bed | 14.08 | 53
two bed | 11.06 | 83 |  |  |  |  | two bed | 13.07 | ??? | one bed | 14.09 | 53
[10 empty] | one bed | 14.1 | ???
2nd Floor
two bed | 21.01 | 86 |  |  | Circulation | 101 |  | Circulation | 40 |  | Circulation | 52
two bed | 21.02 | 85 |  | one bed | 22.05 | 63 | two bed | 23.03 | 88 |  | Circulation | 11
two bed | 21.03 | 85 |  | two bed | 22.06 | 85 | two bed | 23.04 | 87 | one bed | 24.05 | 64
two bed | 21.04 | 86 |  | two bed | 22.07 | 91 | one bed | 23.05 | 62 | one bed | 24.06 | 52
two bed | 21.05 | 85 |  | two bed | 22.08 | ??? | two bed | 23.06 | 85 | one bed | 24.07 | 52
two bed | 21.06 | 86 |  |  |  |  | two bed | 23.07 | ??? | one bed | 24.08 | 53
[10 empty] | one bed | 24.09 | ???
[10 empty] | one bed | 24.1 | ???
3rd Floor
[7 empty] | two bed | 33.03 | 88
[7 empty] | two bed | 33.04 | 89
[7 empty] | one bed | 33.05 | 63
[7 empty] | two bed | 33.06 | 85
[7 empty] | two bed | 33.07 | ???
Total No of Apartment types
| Care Rooms | ILU | Serviced Apartments
Grd Floor | 24 | - | -
First Floor | - | 14 | 6
Second Floor | - | 15 | 6
Third Floor | - | 5 | -
Totals | 24 | 34 | 12

## Ground Level
Ground Floor
Type | Name |  | 1st Fix | 2nd Fix
G.01 | Semi Covered Outdoor Space | Common | Common Areas | Common Areas
G.02 | Lounge | Common | Nogs Marked | Lights Cut Out
G.03 | Circulation | Common | Nogs Installed | Light Fitted Off
G.04 | Stairwell | Common | Power Loops Run | Power Cut Out
G.05 | Store | Common | Power Feeds Run | Power Fitted Off
G.06 | WC | Common | Lighting Loops Run | Dali Sensors Fitted Off
G.07 | Comms | Common | Lighting Feeds Run | Emergencies and Exits
G.08 | Lift | Common | Dali Circuits | DB Installed
G.09 | Circulation | Common | Sensors Run | Tested and Commissioned
G.10 | Waiting | Common | Pipes Bonded
G.11 | SVR | Common | Submain DB
G.12 | Wind Lobby | Common | Tray Installed
G.13 | Café | Common | Tray Bonded
G.14 | Nurse Manager | Common | Emergency Lighting Feeds Run
G.15 | Admin | Common | Lights Marked on Floor
G.16 | Waiting | Common | Lights Lasered for Clashes
G.17 | Circulation | Common | Ceiling Nogs Marked
G.18 | Care Suite - Type CS-1 | Care Suite
G.19 | Care Suite - Type CS-1 | Care Suite | Care Suites | Care Suites
G.20 | Care Suite - Type CS-1 | Care Suite | Nogs Marked | Power Outlets Fitted Off
G.21 | Care Suite - Type CS-1 | Care Suite | Nogs Installed | Light Switches Fitted Off
G.22 | Circulation | Common | Power Loops Run | Downlights Cut Out
G.23 | Care Suite - Type CS-1 | Care Suite | Power Feeds Run | Downlights Installed
G.24 | Care Suite - Type CS-1 | Care Suite | Lighting Loops Run | Night Light Installed
G.25 | DLY CON 1 | Common | Lighting Feeds Run | Nurse Call Relay Installed
G.26 | Service Room | Common | Feeds for Pod Run | Tested And Commissioned
G.27 | DB CBD | Common | Night Light Run
G.28 | Comms | Common | Flush Boxes Installed
G.29 | Nurse Station | Common | Nurse Call Relay Cables Run
G.30 | Circulation | Common | Lights Marked on Floor
G.31 | Care Suite - Type CS-1 | Care Suite | Lights Lasered for Clashes
G.32 | Care Suite - Type CS-1 | Care Suite
G.33 | Care Suite - Type CS-1 | Care Suite
G.34 | Circulation | Common | Memory | Memory
G.35 | Care Suite - Type CS-1 | Care Suite | Nogs Marked | Power Outlets Fitted Off
G.36 | Care Suite - Type CS-1 | Care Suite | Nogs Installed | Light Switches Fitted Off
G.37 | Care Suite - Type CS-1 | Care Suite | Power Loops Run | Downlights Cut Out
G.38 | MSR | Common | Power Feeds Run | Downlights Installed
G.39 | DB CBD | Common | Lighting Loops Run | Night Light Installed
G.40 | Circulation | Common | Lighting Feeds Run | Nurse Call Relay Installed
G.41 | Care Suite - Type CS - 2.2 | Care Suite | Feeds for Pod Run | Tested And Commissioned
G.42 | Care Suite - Type CS - 2.2 | Care Suite | Night Light Run
G.43 | Care Suite - Type CS-1 | Care Suite | Flush Boxes Installed
G.44 | Care Suite - Type CS-1 | Care Suite | Nurse Call Relay Cables Run
G.45 | Care Suite - Type CS-1 | Care Suite | Lights Marked on Floor
G.46 | Circulation | Common | Lights Lasered for Clashes
G.47 | Care Suite - Type CS-1 | Care Suite
G.48 | Care Suite - Type CS-1 | Care Suite
G.49 | Dining/Lounge | Common
G.50 | Circulation | Common
G.51 | CM Kit | Common
G.52 | Riser | Common
G.53 | Riser | Common
G.54 | Lift | Common
G.55 | Stairwell | Common
G.56 | Store | Common
G.57 | Circulation | Common
G.58 | Dirty Linen/ Sluice | Common
G.59 | Cleaners | Common
G.60 | Wind Lobby | Common
G.61 | Waiting | Common
G.62 | Circulation | Common
G.63 | Riser | Common
G.64 | Quiet | Common
G.65 | Memory | Memory
G.66 | Memory | Memory
G.67 | Memory | Memory
G.68 | Equipment 1 | Common
G.69 | Drug | Common
G.70 | Clean Linen | Common
G.71 | DB CBD | Common
G.72 | Memory | Memory
G.73 | Memory | Memory
G.74 | Circulation | Common
G.75 | Memory | Memory
G.76 | Memory | Memory
G.77 | Memory | Memory
G.78 | Memory | Memory
G.79 | Memory | Memory
G.80 | Memory | Memory
G.81 | Circulation | Common
G.82 | Memory | Memory
G.83 | Stairwell | Common
G.84 | DLY CON 2 | Common
G.85 | DB CBD | Common
G.86 | Comms | Common
G.87 | Memory | Memory
G.88 | Memory | Memory
G.89 | Memory | Memory
G.90 | Memory Pod | Common
G.91 | Kitch/Scullery | Common
G.92 | WC | Common

## Level 1
Level 1
Type | Name |  | 1st Fix | 2nd Fix
1.01 | Care Suite - Type CS - 2.2 | Care Suite | Common Areas | Common Areas
1.02 | Care Suite - Type CS - 2.2 | Care Suite | Nogs Marked | Lights Cut Out
1.03 | Care Suite - Type CS - 2.1B | Care Suite | Nogs Installed | Light Fitted Off
1.04 | Circulation | Common | Power Loops Run | Power Cut Out
1.05 | Lift | Common | Power Feeds Run | Power Fitted Off
1.06 | Stairwell | Common | Lighting Loops Run | Dali Sensors Fitted Off
1.07 | Store | Common | Lighting Feeds Run | Emergencies and Exits
1.08 | DB CBD | Common | Dali Circuits | DB Installed
1.09 | Comms | Common | Sensors Run | Tested and Commissioned
1.1 | Circulation | Common | Pipes Bonded
1.11 | Care Suite - Type CS - 2.1A | Care Suite | Submain DB
1.12 | Care Suite - Type CS - 2.1A | Care Suite | Tray Installed
1.13 | Care Suite - Type CS - 2.1A | Care Suite | Tray Bonded
1.14 | Care Suite - Type CS - 2.1A | Care Suite | Emergency Lighting Feeds Run
1.15 | Care Suite - Type CS - 2.1B | Care Suite | Lights Marked on Floor
1.16 | Care Suite - Type CS-1 | Care Suite | Lights Lasered for Clashes
1.17 | Staff Room | Common | Ceiling Nogs Marked
1.18 | Lockers | Common
1.19 | Nurse Station | Common | Care Suites | Care Suites
1.2 | MDR | Common | Nogs Marked | Power Outlets Fitted Off
1.21 | Store | Common | Nogs Installed | Light Switches Fitted Off
1.22 | Riser | Common | Power Loops Run | Downlights Cut Out
1.23 | DB CBD | Common | Power Feeds Run | Downlights Installed
1.24 | Riser | Common | Lighting Loops Run | Night Light Installed
1.25 | Circulation | Common | Lighting Feeds Run | Nurse Call Relay Installed
1.26 | Dining/Lounge | Common | Feeds for Pod Run | Tested And Commissioned
1.27 | Private Din | Common | Night Light Run
1.28 | Kitch | Common | Flush Boxes Installed
1.29 | Circulation | Common | Nurse Call Relay Cables Run
1.3 | Care Suite - Type CS - 2.1A | Care Suite | Lights Marked on Floor
1.31 | Care Suite - Type CS - 2.1A | Care Suite | Lights Lasered for Clashes
1.32 | DLY CON 3 | Common
1.33 | DB CBD | Common
1.34 | Care Suite - Type CS - 2.2 | Care Suite | Memory | Memory
1.35 | Care Suite - Type CS - 2.2 | Care Suite | Nogs Marked | Power Outlets Fitted Off
1.36 | Care Suite - Type CS-1 | Care Suite | Nogs Installed | Light Switches Fitted Off
1.37 |  |  | Power Loops Run | Downlights Cut Out
1.38 | Care Suite - Type CS - 2.1A | Care Suite | Power Feeds Run | Downlights Installed
1.39 | Care Suite - Type CS - 2.1A | Care Suite | Lighting Loops Run | Night Light Installed
1.4 | Care Suite - Type CS - 2.1A | Care Suite | Lighting Feeds Run | Nurse Call Relay Installed
1.41 | Care Suite - Type CS - 2.1A | Care Suite | Feeds for Pod Run | Tested And Commissioned
1.42 | Care Suite - Type CS-1 | Care Suite | Night Light Run
1.43 | Care Suite - Type CS-1 | Care Suite | Flush Boxes Installed
1.44 | Circulation | Common | Nurse Call Relay Cables Run
1.45 | Riser | Common | Lights Marked on Floor
1.46 | Cleaners | Common | Lights Lasered for Clashes
1.47 | Store | Common
1.48 | Data Room | Common
1.49 | MSB | Common
1.5 | MSR | Common
1.51 | Riser | Common
1.52 | Lift | Common
1.53 | Stairwell | Common
1.54 | Sluice | Common
1.55 | Circulation | Common
1.56 | Library | Common
1.57 | Snug | Common
1.58 | Flexi | Common
1.59 | Comms | Common
1.6 | Circulation | Common
1.61 | Equipment 2 | Common
1.62 | Care Suite - Type CS - 2.1A | Care Suite
1.63 | Care Suite - Type CS-1 | Care Suite
1.64 | DLY Con 4 | Common
1.65 | DB CBD | Common
1.66 | Care Suite - Type CS - 2.1A | Care Suite
1.67 | Care Suite - Type CS - 2.1A | Care Suite
1.68 | Care Suite - Type CS - 2.1A | Care Suite
1.69 | Care Suite - Type CS - 2.1A | Care Suite
1.7 | Circulation | Common
1.71 | Care Suite - Type CS-1 | Care Suite
1.72 | Care Suite - Type CS-1 | Care Suite
1.73 | Care Suite - Type CS - 2.1B | Care Suite
1.74 | Stairwell | Common
1.75 | Store | Common
1.76 | Comms | Common
1.77 | DB CBD | Common
1.78 | Care Suite - Type CS - 2.2 | Care Suite
1.79 | Care Suite - Type CS - 2.2 | Care Suite

## Exterior
Exterior
| 1st Fix | 2nd Fix
| Mains Ducts Installed | Pads made for Bollards
| Lighting Ducts Installed | Bollards Installed
| Power Ducts Installed | Tested and Commissioned
Cables Run For Bollards
Mains Run in Ducts
Data Ducts Installed
Draw Tape Installed

## Facade (hidden)
Façade
Block 1 | Basement | Ground Floor | 1st Floor | 2nd Floor | 3rd Floor
| N/A | North | North | North | North
| N/A | South | South | South | South
| N/A | East | East | East | East
| N/A | West | West | West | West
Block 2 | Basement | Ground Floor | 1st Floor | 2nd Floor | 3rd Floor
| N/A | North | North | North | N/A
| N/A | South | South | South | N/A
| N/A | East | East | East | N/A
| N/A | West | West | West | N/A
Block 3 | Basement | Ground Floor | 1st Floor | 2nd Floor | 3rd Floor
| N/A | North | North | North | N/A
| N/A | South | South | South | N/A
| N/A | East | East | East | N/A
| N/A | West | West | West | N/A
Block 4 | Basement | Ground Floor | 1st Floor | 2nd Floor | 3rd Floor
| North | North | North | North | N/A
| South | South | South | South | N/A
| East | East | East | East | N/A
| West | West | West | West | N/A
Swimming Pool | Basement | Ground Floor | 1st Floor | 2nd Floor | 3rd Floor
| N/A | N/A | N/A | N/A | N/A
| N/A | South | N/A | N/A | N/A
| N/A | East | N/A | N/A | N/A
| N/A | West | N/A | N/A | N/A
Link 2 -3 | Basement | Ground Floor | 1st Floor | 2nd Floor | 3rd Floor
| N/A | North | N/A | N/A | N/A
| N/A | South | N/A | N/A | N/A
| N/A | N/A | N/A | N/A | N/A
| N/A | N/A | N/A | N/A | N/A
Link 3-4 | Basement | Ground Floor | 1st Floor | 2nd Floor | 3rd Floor
| N/A | North | N/A | N/A | N/A
| N/A | South | N/A | N/A | N/A
| N/A | N/A | N/A | N/A | N/A
| N/A | N/A | N/A | N/A | N/A
Link 2-4 | Basement | Ground Floor | 1st Floor | 2nd Floor | 3rd Floor
| N/A | North | N/A | N/A | N/A
| N/A | South | N/A | N/A | N/A
| N/A | N/A | N/A | N/A | N/A
| N/A | N/A | N/A | N/A | N/A
Link 1-4 | Basement | Ground Floor | 1st Floor | 2nd Floor | 3rd Floor
| N/A | North | N/A | N/A | N/A
| N/A | South | N/A | N/A | N/A
| N/A | East | N/A | N/A | N/A
| N/A | West | N/A | N/A | N/A