## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | ST - S - Insitu Beams Installation |  |  |  |  | Yes | ST - S - Insitu Beams Installation | 033b3d0b-c29c-4667-8763-d1daa3e405cc
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Insitu Beams Installation completed (checked location & level) and no damages
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | SYS - Compliance / Completion Documentation Checklist |  |  |  |  | Yes | SYS - Compliance / Completion Documentation Checklist | 1c393693-7c0c-4246-9ea5-95388405c79e
checkpoint-status |  |  | checkpoint | All Compliance / Completion Documentation - Completed & Attached
button | 596285f6-31e3-561b-a3a0-eef10e634209 |  | button | PS3 - Completed and Attached | Yes, N/A
button | 3f8c2795-80cc-5869-88c8-de875f773266 |  | button | LBP Memorandum/ Record of works | Yes, N/A
button | ab485e20-923d-5b06-9834-86151f7d161f |  | button | Concrete Test Results & Mill Certs | Yes, N/A
button | fcdc1d9d-ec37-5f8d-b69a-b82fd48a119a |  | button | Any Additional Compliance Documentation - Completed and Attached | Yes, N/A
label | e1bf47d0-def1-5bf6-b30b-230d7fbff8e4 |  | note | Do not select "Pass" HERE until all above requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Signoff
checklist-sectioned |  |  | checklist | ST - S - Insitu Stitch Joints |  |  |  |  | Yes | ST - S - Insitu Stitch Joints | 206d2b9e-bd2c-4c3e-b059-8a2bef46dbb4
checkpoint-group |  |  | section | Pour Details
checkpoint-status |  |  | checkpoint | Pour Details:
text | c648f439-7799-5d18-b8f5-596e964a43e7 |  | textbox | Area to be poured:
text | b7faedd1-7755-5f11-98a1-9633d6ae6d1e |  | textbox | Date of pour:
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group |  |  | section | Formwork
checkpoint-status |  |  | checkpoint | Formwork braced & fixed correctly
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g joints to exisiting concrete, release agent to formwork etc)
checkpoint-group |  |  | section | Reinforcing
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All relevant inspections completed and attached
checkpoint-status |  |  | checkpoint | Ryman inspection completed - Approval given to pour concrete
checkpoint-group |  |  | section | Concrete Supplier Specifics
checkpoint-status |  |  | checkpoint | Test blocks booked
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | ST - S - Concrete Pour - Without Reo |  |  |  |  | Yes | SYS - ST - S - Concrete Pour - Without Reo (old version 2) | 20bd4059-8b0d-4bf8-b381-65d47c500ecc
checkpoint-group |  |  | section | Pour Details
checkpoint-status |  |  | checkpoint | Pour details entered
text | 041edeb6-a065-5590-99ce-2c1ceb34ff61 |  | textbox | Area to be poured:
text | a3972770-b61d-56be-b398-e96fe3949df1 |  | textbox | Date of pour:
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group |  |  | section | Formwork and Embedded Items
checkpoint-status |  |  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint-status |  |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g joints to existing concrete, release agent to formwork etc)
checkpoint-status |  |  | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Waterproofing elements have been correctly installed and checked
checkpoint-status |  |  | checkpoint | Relevant service requirements completed (locations checked and accurate)
checkpoint-status |  |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint-status |  |  | checkpoint | Ryman inspection completed - Approval given to pour concrete
checkpoint-group |  |  | section | Concrete Supplier Specifics
checkpoint-status |  |  | checkpoint | Concrete Supplier details entered
text | 7eac6ad2-e8ce-5fc8-ab9b-7823a557b18d |  | textbox | Supplier Name:
text | e721835b-b0d4-53f5-b233-88663c14c5cc |  | textbox | Specified concrete strength:
text | b56f6f78-1c48-5502-9ca4-0b62ae92c9cd |  | textbox | Concrete strength ordered:
text | 13aac0b6-f778-5630-9393-45a7bd375de6 |  | textbox | Concrete quantity ordered:
button | b085aa56-943e-5bda-80af-ba1fe3c4d833 |  | button | Test blocks booked | Yes, No, N/A
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-group |  |  | section | Placement Method
checkpoint-status |  |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint-status |  |  | checkpoint | Heights and falls checked/confirmed before placement
button | 4033443b-0638-5afa-8b5a-f96b8718e561 |  | button | Is the cover correct to specification | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Heights and falls checked/ confirmed after placement
checkpoint-status |  |  | checkpoint | Any curing compound applied correctly
checkpoint-status |  |  | checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
holdpoint |  |  | signoff | Raise remedial/ Request Signoff
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checklist-flat |  |  | checklist | ST - S - Precast Beam Installation |  |  |  |  | Yes | ST - S - Precast Beam Installation | 342ccb4a-0825-4318-b979-5080499422aa
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Precast Beam Installation completed (checked location & level) and no damages
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | ST - S -Panel Starter bars Installation |  |  |  |  | Yes | SYS - ST - S - Panel Starter bars Installation (old version) | 392d3baf-1438-4d56-8bd6-f787879e17fc
checkpoint-status |  |  | checkpoint | Correct drawings referenced and attached
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/ correct
checkpoint-status |  |  | checkpoint | Any additional items installed/completed (trimmer bars etc.) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Panel starter bars installed correctly to specifications (locaion, size, length and spacing) and ready to place the precast panels
checklist-flat |  |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | CST - S - Completion Documents | 52868e77-e429-4193-bfe1-71c1dcfe5fce
checkpoint-status |  |  | checkpoint | All relevant Compliance Documentation completed and attached above
boolean | 5601d439-d44b-5e7b-972d-9592faa17eb4 |  | tickbox | Any additional Compliance Documentation (Required under Section C and by consultants) - Completed and Attached
label | 6009e841-ccd4-5a35-9c63-53132a55325f |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Sign off
checklist-flat |  |  | checklist | ST - S - Precast Wall Panel Installation |  |  |  |  | Yes | SYS - ST - S - Precast Wall Panel Installation (old version) | 674f8c42-a60d-40d4-bba9-8336d407d82a
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Appointment with the engineers confirmed (Enter date & time of the appointment)
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and Braces to be tagged
checkpoint-status |  |  | checkpoint | Grout sleeves correctly grouted
checkpoint-status |  |  | checkpoint | Precast Wall Panel Installation completed correctly (checked location & level) and damage free
checklist-flat |  |  | checklist | ST - S - Insitu Beams Installation |  |  |  |  | Yes | SYS - ST - S - Insitu Beams Installation (old version) | 7293fbbe-1d44-48d7-9718-f95dc41e9636
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Insitu Beams Installation completed (checked location & level) and no damages
checklist-sectioned |  |  | checklist | ST - S - Rib & Infill Installation |  |  |  |  | Yes | ST - S - Rib & Infill Installation | 7a091437-9935-4764-bee9-9b3da84652e7
checkpoint-group |  |  | section | Pre-commencement
checkpoint-status |  |  | checkpoint | Infill Panel SWMS compiled and provided to Ryman for review prior to work starting on site
checkpoint-status |  |  | checkpoint | Ribs inspected on arrival and correct (length, width, size/shape) as per design/shop drawings and damage free
checkpoint-status |  |  | checkpoint | Rib lifting plan confirmed, correct chains and hooks verified.
checkpoint-status |  |  | checkpoint | Infill boards inspected on arrival. No knots, no cracks or other weaknesses across 25% of the width.
checkpoint-status |  |  | checkpoint | Propping layout confirmed as "issued for construction" and attached.
checkpoint-status |  |  | checkpoint | Area cleared for propping to be erected in place.
checkpoint-status |  |  | checkpoint | Structural Steel Brackets fitted and fixed (correct height and as per design)
checkpoint-group |  |  | section | Propping/Falseworks
checkpoint-status |  |  | checkpoint | Floor area cleared for propping to be erected.
checkpoint-status |  |  | checkpoint | Props tagged and fixings as per approved design.
checkpoint-status |  |  | checkpoint | U Head brackets rotated to support bearers, bearers clipped to U head brackets.
checkpoint-status |  |  | checkpoint | All back propping completed, checked and approved as per design
checkpoint-group |  |  | section | Rib Installation
checkpoint-status |  |  | checkpoint | Inspect against rib install and propping layout drawings. Mark up hard copy drawings accordingly and upload to this checkpoint to verify the specification has been met.
checkpoint-status |  |  | checkpoint | No visual damage to ribs
checkpoint-status |  |  | checkpoint | SWMS implemented and followed.
checkpoint-status |  |  | checkpoint | Ryman Foreman Sign off to receive Rib Installation inspection results. Pass this checkpoint after sending the email.
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO RYMAN FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checkpoint-group |  |  | section | Infill Panel Installation
checkpoint-status |  |  | checkpoint | Infill boards tightly constructed as panels, including 'backbone', 6 to 10 boards in length.
checkpoint-status |  |  | checkpoint | Infill panels fitted tightly between ribs.
checkpoint-status |  |  | checkpoint | Infill panel adjacent ends are joined.
checkpoint-status |  |  | checkpoint | Infill panels locked with timber blocks to prevent lateral movement.
checkpoint-status |  |  | checkpoint | Infill boards secured to wall supports
checkpoint-status |  |  | checkpoint | No obvious visual defects on infill boards, no knots, no cracks or other weakness across 25% of the width.
checkpoint-status |  |  | checkpoint | All gaps filled, infills installed, PF rod/expanding foam installed (No gaps)
checkpoint-status |  |  | checkpoint | Ryman Foreman Sign off to receive Rib Installation inspection results. Pass this checkpoint after sending the email.
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO RYMAN FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | ST - S - Precast Beam Installation |  |  |  |  | Yes | SYS - ST - S - Precast Beam Installation (old version) | 82136a52-db6c-4ad6-b7eb-f8d38e5a8966
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Precast Beam Installation completed (checked location & level) and no damages
checklist-flat |  |  | checklist | ST - S - Panel Starter bars Installation |  |  |  |  | Yes | ST - S - Panel Starter bars Installation | 8a12205e-6538-4f14-b253-3d549b73beaa
checkpoint-status |  |  | checkpoint | Correct drawings referenced and attached
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/ correct
checkpoint-status |  |  | checkpoint | Any additional items installed/completed (trimmer bars etc.) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Panel starter bars installed correctly to specifications (locaion, size, length and spacing) and ready to place the precast panels
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | Rib & Infill Installation |  |  |  |  | Yes | SYS - ST - S - Rib & Infill Installation (old version) | 8bd84ed0-b65c-400c-911f-9c513d5ffd38
checkpoint-group |  |  | section | Pre-commencement
checkpoint-status |  |  | checkpoint | Ribs inspected on arrival and correct (length, width, size/shape) as per design/shop drawings and damage free
checkpoint-status |  |  | checkpoint | Rib lifting plan confirmed, correct chains and hooks verified.
checkpoint-status |  |  | checkpoint | Infill boards inspected on arrival. No knots, no cracks or other weaknesses across 25% of the width.
checkpoint-status |  |  | checkpoint | Propping layout confirmed as "issued for construction" and attached.
checkpoint-status |  |  | checkpoint | Area cleared for propping to be
checkpoint-status |  |  | checkpoint | Structural Steel Brackets fitted and fixed (correct height and as per design)
checkpoint-group |  |  | section | Propping/Falseworks
checkpoint-status |  |  | checkpoint | Floor area cleared for propping to be erected.
checkpoint-status |  |  | checkpoint | Props tagged and fixings as per approved design.
checkpoint-status |  |  | checkpoint | U Head brackets rotated to support bearers, bearers clipped to U head brackets.
checkpoint-status |  |  | checkpoint | All back propping completed, checked and approved as per design
checkpoint-group |  |  | section | Rib Installation
checkpoint-status |  |  | checkpoint | Inspect against rib install and propping layout drawings. Mark up hard copy drawings accordingly and upload to this checkpoint to verify the specification has been met.
checkpoint-status |  |  | checkpoint | No visual damage to ribs
checkpoint-status |  |  | checkpoint | Foreman Sign off to receive Rib Installation inspection results. Pass this checkpoint after sending the email.
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checkpoint-group |  |  | section | Infill Panel Installation
checkpoint-status |  |  | checkpoint | Infill boards tightly constructed as panels, including 'backbone', 6 to 10 boards in length.
checkpoint-status |  |  | checkpoint | Infill panels fitted tightly between ribs.
checkpoint-status |  |  | checkpoint | Infill panel adjacent ends are joined.
checkpoint-status |  |  | checkpoint | Infill panels locked with timber blocks to prevent lateral movement.
checkpoint-status |  |  | checkpoint | Infill boards secured to wall supports
checkpoint-status |  |  | checkpoint | No obvious visual defects on infill boards, no knots, no cracks or other weakness across 25% of the width.
checkpoint-status |  |  | checkpoint | All gaps filled, infills installed, PF rod/expanding foam installed (No gaps)
checkpoint-status |  |  | checkpoint | Foreman Sign off to receive Infill Panel Installation inspection results. Pass this checkpoint after sending the email.
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | ST - S - Stair Installation |  |  |  |  | Yes | ST - S - Stair Installation | 9748b2bc-c36a-429b-9783-e7f508b81816
checkpoint-status |  |  | checkpoint | Items inspected on arrival and correct (length, width, size/shape) as per design/shop drawings and damage free
checkpoint-status |  |  | checkpoint | Grid Set-out offset and level correct
checkpoint-status |  |  | checkpoint | Joints scabbled and acceptable
checkpoint-status |  |  | checkpoint | All setout completed correctly and approved
checkpoint-status |  |  | checkpoint | Temporary support installed and approved
checkpoint-status |  |  | checkpoint | Stairs placed, locations, heights and orientation approved. No damage during installation
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | ST - S - Concrete Pour |  |  |  |  | Yes | SYS - ST - S - Concrete Pour (old version 2) | 9ddaa41f-922a-4495-a5e1-fdb131f44a8d
checkpoint-group |  |  | section | Pour Details
checkpoint-status |  |  | checkpoint | Pour details entered
text | 90a414fd-0d59-567a-bcf5-64ae4eea94a7 |  | textbox | Area to be poured:
text | d01295ea-16fa-575f-a723-799f4e950715 |  | textbox | Date of pour:
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group |  |  | section | Formwork and Embedded Items
checkpoint-status |  |  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint-status |  |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g joints to existing concrete, release agent to formwork etc)
checkpoint-status |  |  | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
checkpoint-group |  |  | section | Reinforcing
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Splice laps checked/correct
checkpoint-status |  |  | checkpoint | All couplers installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
boolean | 7412bfad-11df-581b-a39a-99523acfec54 |  | tickbox | Appointment with the engineers confirmed (Enter date & time of the appointment)
boolean | dcda11e4-eb4f-59cf-9a48-459a4a26386f |  | tickbox | Reidbar – coupler and flange nut installations are inspected by the MV Engineer
checkpoint-status |  |  | checkpoint | IMBMS couplers testing carried out for Village Podiums in the form of tensile testing in accordance with NZS3101.1.2006 and results acceptable
checkpoint-status |  |  | checkpoint | All starter bars are installed correctly (location, size and spacing )
checkpoint-status |  |  | checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Welding certificates sited and attached
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Waterproofing elements have been correctly installed and checked
checkpoint-status |  |  | checkpoint | Relevant service requirements completed (locations checked and accurate)
checkpoint-status |  |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint-status |  |  | checkpoint | Ryman inspection completed - Approval given to pour concrete
checkpoint-group |  |  | section | Concrete Supplier Specifics
checkpoint-status |  |  | checkpoint | Concrete Supplier details entered
text | 724ddbfc-c4c7-53d7-91c1-647a22e716df |  | textbox | Supplier Name:
text | 5bf35054-f5ab-58fd-aa73-ce7cab652547 |  | textbox | Specified concrete strength: |  |  | mPA
text | c1ddfbf8-1cdc-561d-a298-ffcdaa63f094 |  | textbox | Concrete strength ordered: |  |  | mPA
text | a9c0c99f-19f9-5f24-98d1-f033c68ae6e3 |  | textbox | Concrete quantity ordered: |  |  | m3
button | 42b9de94-742a-5fe0-948a-bcb45525785e |  | button | Test blocks booked | Yes, No, N/A
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-group |  |  | section | Placement Method
checkpoint-status |  |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint-status |  |  | checkpoint | Heights and falls checked/confirmed before placement
button | 96a365cb-fd50-5837-b7ac-dccd943c7b3e |  | button | Is the cover correct to specification | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Heights and falls checked/ confirmed after placement
checkpoint-status |  |  | checkpoint | Any curing compound applied correctly
checkpoint-status |  |  | checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
holdpoint |  |  | signoff | Raise remedial/ Request Signoff
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checklist-flat |  |  | checklist | ST - S - Blockwork |  |  |  |  | Yes | ST - S - Blockwork | a378452b-91d0-4ad1-920c-56915258b00a
checkpoint-status |  |  | checkpoint | Grids available for reference and base of wall marked accurately, RL reference/top of wall (TOW) confirmed
checkpoint-status |  |  | checkpoint | Base of wall in correct location
checkpoint-status |  |  | checkpoint | Horizontal reinforcing installed correctly (centres/ size / splicing etc)
checkpoint-status |  |  | checkpoint | Ties / Controll joints installed as required
checkpoint-status |  |  | checkpoint | Vertical reinforcing installed as required with appropriate splice
checkpoint-status |  |  | checkpoint | Openings checked and correct - location, height and width
checkpoint-status |  |  | checkpoint | Washouts correct/openings covered correctly and wall braced adequately (if required)
checkpoint-status |  |  | checkpoint | Wall built within tolerance - straight, level and to the correct height (Approval to pour)
checkpoint-status |  |  | checkpoint | Concrete specifications checked and correct
checkpoint-status |  |  | checkpoint | All blocks filled to correct height
checkpoint-status |  |  | checkpoint | Starter bars in centre of block if applicable
checkpoint-status |  |  | checkpoint | Blockwork wall(s) complete to required specification
checklist-flat |  |  | checklist | FC - S - Exterior Timber Framing |  |  |  |  | Yes | FC - S - Exterior Timber Framing | a37a5793-f5db-4048-9dc6-19ba62dae19e
checkpoint-status |  |  | checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint-status |  |  | checkpoint | Framing Dimensions / locations checked & accurate
checkpoint-status |  |  | checkpoint | All frames have been installed square, straight and plumb
checkpoint-status |  |  | checkpoint | DPC installed (if required) correctly
checkpoint-status |  |  | checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint-status |  |  | checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (ensure acoustic & fire rating requirements)
checkpoint-status |  |  | checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s)
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | ST - S - Concrete Pour - Without Reo |  |  |  |  | Yes | SYS - ST - S - Concrete Pour - Without Reo (old version) | a44dac2b-b74c-4bbe-9a10-7d2d6779f3e8
checkpoint-group |  |  | section | Pour Details
checkpoint-status |  |  | checkpoint | Pour details entered
text | 0ef0a806-89f5-5ec6-885a-b62768f8982e |  | textbox | Area to be poured:
text | cb91cdde-edc8-5f03-b33e-e9e1c62a1b96 |  | textbox | Date of pour:
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group |  |  | section | Formwork and Embedded Items
checkpoint-status |  |  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint-status |  |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g joints to existing concrete, release agent to formwork etc)
checkpoint-status |  |  | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Waterproofing elements have been correctly installed and checked
checkpoint-status |  |  | checkpoint | Relevant service requirements completed (locations checked and accurate)
checkpoint-status |  |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint-status |  |  | checkpoint | Ryman inspection completed - Approval given to pour concrete
checkpoint-group |  |  | section | Concrete Supplier Specifics
checkpoint-status |  |  | checkpoint | Concrete Supplier details entered
text | c62ee215-3e89-5890-ac7f-2b3a697aa32e |  | textbox | Supplier Name:
text | a4e2b25f-19aa-5af9-98cc-8676e2e4d729 |  | textbox | Specified concrete strength:
text | 070aec7b-9a74-5499-946a-6c38f6b8b82e |  | textbox | Concrete strength ordered:
text | 4b78bb0a-bc0a-56ad-a40d-5522ca6d5ef4 |  | textbox | Concrete quantity ordered:
button | 01c5abd2-bf42-5783-a239-feb4475741f9 | DataPoint is missing 'button' values | button | Test blocks booked
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-group |  |  | section | Placement Method
checkpoint-status |  |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint-status |  |  | checkpoint | Heights and falls checked/confirmed before placement
button | 9b1aa151-7464-5c40-9d0a-e6249d1506a9 | DataPoint is missing 'button' values | button | Is the cover correct to specification
checkpoint-status |  |  | checkpoint | Heights and falls checked/ confirmed after placement
checkpoint-status |  |  | checkpoint | Any curing compound applied correctly
checkpoint-status |  |  | checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
holdpoint |  |  | signoff | Raise remedial/ Request Signoff
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checklist-flat |  |  | checklist | ST - S - Precast Wall Panel Installation |  |  |  |  | Yes | ST - S - Precast Wall Panel Installation | aa795143-0647-49f1-b6c8-20c3265bd7f3
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Appointment with the engineers confirmed (Enter date & time of the appointment)
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and Braces to be tagged
checkpoint-status |  |  | checkpoint | Grout sleeves correctly grouted
checkpoint-status |  |  | checkpoint | Precast Wall Panel Installation completed correctly (checked location & level) and damage free
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | ST - S - Precast Spandrel Panel Installation |  |  |  |  | Yes | ST - S - Precast Spandrel Panel Installation | acbcced7-d07d-4fe1-8841-dedca789fa25
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Precast Spandrel Panel Installation completed (checked location & level) and no damages
checklist-flat |  |  | checklist | ST - S - Precast Flat Slab Installation |  |  |  |  | Yes | SYS - ST - S - Precast Flat Slab Installation (old version) | afbfa185-000c-45f5-818e-fce5637eac45
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Precast Flat Slab Installation completed (checked location & level) and no damages
checklist-sectioned |  |  | checklist | ST - S - Insitu Pour |  |  |  |  | Yes | ST - S - Insitu Pour | c8bcaa18-8e06-4d1a-b4d3-91fd77265380
checkpoint-group |  |  | section | Pour Details
checkpoint-status |  |  | checkpoint | Pour Details:
text | d2eda102-12ad-5028-b6d0-ea18d172533a |  | textbox | Area to be poured:
text | 845a3ffd-ebd1-5904-8079-7dcd914ccf31 |  | textbox | Date of pour:
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group |  |  | section | Formwork
checkpoint-status |  |  | checkpoint | Formwork braced & fixed correctly
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork etc)
checkpoint-status |  |  | checkpoint | Cover as specified
checkpoint-group |  |  | section | Reinforcing
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Adjacent construction joints roughened and clean (7mm amplitude min)
checkpoint-status |  |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All relevant inspections completed and attached
checkpoint-status |  |  | checkpoint | Ryman inspection completed - Approval given to pour concrete
checkpoint-group |  |  | section | Concrete Supplier Specifics
checkpoint-status |  |  | checkpoint | Test blocks booked
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO RYMAN FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | ST - S - Concrete Pour |  |  |  |  | Yes | SYS - ST - S - Concrete Pour (old version) | c928e3cf-172e-445b-8152-eeb32e0f717a
checkpoint-group |  |  | section | Pour Details
checkpoint-status |  |  | checkpoint | Pour details entered
text | 6a72724e-ec1e-5682-bb04-bc4d4b623d5a |  | textbox | Area to be poured:
text | e3357ad8-0ed9-58f2-b5cb-8c7abd947298 |  | textbox | Date of pour:
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group |  |  | section | Formwork and Embedded Items
checkpoint-status |  |  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint-status |  |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g joints to existing concrete, release agent to formwork etc)
checkpoint-status |  |  | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
checkpoint-group |  |  | section | Reinforcing
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Splice laps checked/correct
checkpoint-status |  |  | checkpoint | All couplers installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
boolean | dbc00060-3410-59d3-981a-b5d4299265c0 |  | tickbox | Appointment with the engineers confirmed (Enter date & time of the appointment)
boolean | af4acce9-37cc-59b6-b516-093addf06a0f |  | tickbox | Reidbar – coupler and flange nut installations are inspected by the MV Engineer
checkpoint-status |  |  | checkpoint | IMBMS couplers testing carried out for Village Podiums in the form of tensile testing in accordance with NZS3101.1.2006 and results acceptable
checkpoint-status |  |  | checkpoint | All starter bars are installed correctly (location, size and spacing )
checkpoint-status |  |  | checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Welding certificates sited and attached
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Waterproofing elements have been correctly installed and checked
checkpoint-status |  |  | checkpoint | Relevant service requirements completed (locations checked and accurate)
checkpoint-status |  |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint-status |  |  | checkpoint | Ryman inspection completed - Approval given to pour concrete
checkpoint-group |  |  | section | Concrete Supplier Specifics
checkpoint-status |  |  | checkpoint | Concrete Supplier details entered
text | 8de5271d-393a-50e0-87f8-a8b777866555 |  | textbox | Supplier Name:
text | d709f5da-f687-596f-80d4-0d704b3e985a |  | textbox | Specified concrete strength: | mPA
text | cf86850c-51c2-56b2-930b-1ad63914d8ad |  | textbox | Concrete strength ordered: | mPA
text | 42329b3f-551b-5db1-8b2c-9e8347dc1550 |  | textbox | Concrete quantity ordered: | m3
button | d76e69d0-7998-5f12-96df-dbdd726536f0 | DataPoint is missing 'button' values | button | Test blocks booked
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-group |  |  | section | Placement Method
checkpoint-status |  |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint-status |  |  | checkpoint | Heights and falls checked/confirmed before placement
button | 4387be48-79d9-52fa-be9b-854cc9333add | DataPoint is missing 'button' values | button | Is the cover correct to specification
checkpoint-status |  |  | checkpoint | Heights and falls checked/ confirmed after placement
checkpoint-status |  |  | checkpoint | Any curing compound applied correctly
checkpoint-status |  |  | checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
holdpoint |  |  | signoff | Raise remedial/ Request Signoff
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checklist-flat |  |  | checklist | ST - S - Precast Shell Beam Lintel Installation |  |  |  |  | Yes | ST - S - Precast Shell Beam Lintel Installation | cb65a347-d7f0-4da7-a1f4-271acec2eb6a
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Precast Shell Beam Lintel Installation completed (checked location & level) and no damages
checklist-flat |  |  | checklist | C - S - Detailed Excavation |  |  |  |  | Yes | C - S - Detailed Excavation | ce6c3db1-4463-47e4-ae12-6a052a3ad33a
checkpoint-status |  |  | checkpoint | Grids/profiles/set out completed, clearly marked and accurate
checkpoint-status |  |  | checkpoint | Excavation depths and locations confirmed prior to detailed excavation commencing
checkpoint-status |  |  | checkpoint | Services (overhead / below ground) considered and isolated where required before excavation commences
checkpoint-status |  |  | checkpoint | Approval given to commence detailed excavation
checkpoint-status |  |  | checkpoint | Excavation checked, correct and approved
boolean | f404f5d7-31db-5a14-8416-12f67587bdf1 |  | tickbox | Location accurate
boolean | 3aa8352f-426d-512a-9b97-a28f3304ca19 |  | tickbox | Depth correct (allow for site concrete if required)
boolean | 9f58ec30-ccb9-5ae8-8def-0e83047d11ed |  | tickbox | Width correct (allow for boxing if required)
checkpoint-status |  |  | checkpoint | Excavation for services is completed and accurate
checkpoint-status |  |  | checkpoint | Excess material cleaned up and removed as required
checkpoint-status |  |  | checkpoint | Detailed excavation completed, reviewed and approved
checklist-sectioned |  |  | checklist | ST - S - Concrete Pour - Without Reo |  |  |  |  | Yes | ST - S - Concrete Pour - Without Reo | d9b7023b-4a79-4630-b705-44156189282c
checkpoint-group |  |  | section | Pour Details
checkpoint-status |  |  | checkpoint | Pour details entered
text | b8ba2ea4-5034-560c-a42c-a35c66f032ec |  | textbox | Area to be poured:
text | 6afde208-63f2-503e-a9de-76a5d957d7bc |  | textbox | Date of pour:
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group |  |  | section | Formwork and Embedded Items
checkpoint-status |  |  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint-status |  |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g joints to existing concrete, release agent to formwork etc)
checkpoint-status |  |  | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Waterproofing elements have been correctly installed and checked
checkpoint-status |  |  | checkpoint | Relevant service requirements completed (locations checked and accurate)
checkpoint-status |  |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint-status |  |  | checkpoint | Ryman inspection completed - Approval given to pour concrete
checkpoint-group |  |  | section | Concrete Supplier Specifics
checkpoint-status |  |  | checkpoint | Concrete Supplier details entered
text | 55e46753-c578-595f-a84e-4f58a34efc3c |  | textbox | Supplier Name:
text | 3ae0ac2c-fbb5-5437-8e54-a138c3996fa5 |  | textbox | Specified concrete strength:
text | bad8f536-8ba1-579b-b14f-4caa709e1bca |  | textbox | Concrete strength ordered:
text | 4f98e636-e4b1-55b6-9968-98143e0178c8 |  | textbox | Concrete quantity ordered:
button | 7df66a4f-cd85-5ad1-9112-edd92cbc5d33 |  | button | Test blocks booked | Yes, No, N/A
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-group |  |  | section | Placement Method
checkpoint-status |  |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint-status |  |  | checkpoint | Heights and falls checked/confirmed before placement
button | e66e00b8-e02d-5cf1-b40a-a6b261038d05 |  | button | Is the cover correct to specification | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Heights and falls checked/ confirmed after placement
checkpoint-status |  |  | checkpoint | Any curing compound applied correctly
checkpoint-status |  |  | checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
holdpoint |  |  | signoff | Raise remedial/ Request Signoff
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | ST - S - Precast Flat Slab Installation |  |  |  |  | Yes | ST - S - Precast Flat Slab Installation | e859d523-1fa9-42f9-b1b5-b1e6c79a1de9
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Precast Flat Slab Installation completed (checked location & level) and no damages
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | ST - S - Insitu Stitch Joints |  |  |  |  | Yes | SYS - ST - S - Insitu Stitch Joints (old version) | f4c5c2e6-7aa1-43a7-b574-32c04c5822bd
checkpoint-group |  |  | section | Pour Details
checkpoint-status |  |  | checkpoint | Pour Details:
text | bd813693-fefe-5d4c-baf3-1d432d18d69d |  | textbox | Area to be poured:
text | 8981cb99-45f6-52a5-b0ce-d1f88d379a57 |  | textbox | Date of pour:
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group |  |  | section | Formwork
checkpoint-status |  |  | checkpoint | Formwork braced & fixed correctly
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g joints to exisiting concrete, release agent to formwork etc)
checkpoint-group |  |  | section | Reinforcing
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All relevant inspections completed and attached
checkpoint-status |  |  | checkpoint | Ryman inspection completed - Approval given to pour concrete
checkpoint-group |  |  | section | Concrete Supplier Specifics
checkpoint-status |  |  | checkpoint | Test blocks booked
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checklist-sectioned |  |  | checklist | ST - S - Concrete Pour |  |  |  |  | Yes | ST - S - Concrete Pour | f5e7cdbc-d1e0-4761-95d8-879f61025d0c
checkpoint-group |  |  | section | Pour Details
checkpoint-status |  |  | checkpoint | Pour details entered
text | 97dd3b5c-a129-5362-94c6-4f3970995285 |  | textbox | Area to be poured:
text | 58ebe3ec-7af3-5f98-9db0-f7d93fc07463 |  | textbox | Date of pour:
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group |  |  | section | Formwork and Embedded Items
checkpoint-status |  |  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint-status |  |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g joints to existing concrete, release agent to formwork etc)
checkpoint-status |  |  | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
checkpoint-group |  |  | section | Reinforcing
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Splice laps checked/correct
checkpoint-status |  |  | checkpoint | All couplers installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
boolean | f4509a3e-9e66-5c7a-998c-c28cf3313fa7 |  | tickbox | Appointment with the engineers confirmed (Enter date & time of the appointment)
boolean | 6e2bfc77-8545-5bda-ad6c-16e8f91502f0 |  | tickbox | Reidbar – coupler and flange nut installations are inspected by the MV Engineer
checkpoint-status |  |  | checkpoint | IMBMS couplers testing carried out for Village Podiums in the form of tensile testing in accordance with NZS3101.1.2006 and results acceptable
checkpoint-status |  |  | checkpoint | All starter bars are installed correctly (location, size and spacing )
checkpoint-status |  |  | checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Welding certificates sited and attached
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Waterproofing elements have been correctly installed and checked
checkpoint-status |  |  | checkpoint | Relevant service requirements completed (locations checked and accurate)
checkpoint-status |  |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint-status |  |  | checkpoint | Ryman inspection completed - Approval given to pour concrete
checkpoint-group |  |  | section | Concrete Supplier Specifics
checkpoint-status |  |  | checkpoint | Concrete Supplier details entered
text | b10a066b-88f6-5c01-b1c1-601385549aea |  | textbox | Supplier Name:
text | 73fa34fe-0ac4-51b8-8f72-2601a5143a3e |  | textbox | Specified concrete strength: |  |  | mPA
text | 92ea16fa-a8a7-590b-91f7-0829dfc3ce93 |  | textbox | Concrete strength ordered: |  |  | mPA
text | 62bb87a9-1a1e-50e8-b5c1-0a6ad0952076 |  | textbox | Concrete quantity ordered: |  |  | m3
button | 3e4e2047-e0ab-58bc-b9ab-31e446396c41 |  | button | Test blocks booked | Yes, No, N/A
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-group |  |  | section | Placement Method
checkpoint-status |  |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint-status |  |  | checkpoint | Heights and falls checked/confirmed before placement
button | 0cb26f56-1d5d-5060-b605-f2dcc0acd633 |  | button | Is the cover correct to specification | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Heights and falls checked/ confirmed after placement
checkpoint-status |  |  | checkpoint | Any curing compound applied correctly
checkpoint-status |  |  | checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
holdpoint |  |  | signoff | Raise remedial/ Request Signoff
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | ST - S - Stair Installation |  |  |  |  | Yes | SYS - ST - S - Stair Installation (old version) | ffff4fc7-7edc-477d-b9df-afe7b9da51c6
checkpoint-status |  |  | checkpoint | Items inspected on arrival and correct (length, width, size/shape) as per design/shop drawings and damage free
checkpoint-status |  |  | checkpoint | Grid Set-out offset and level correct
checkpoint-status |  |  | checkpoint | Joints scabbled and acceptable
checkpoint-status |  |  | checkpoint | All setout completed correctly and approved
checkpoint-status |  |  | checkpoint | Temporary support installed and approved
checkpoint-status |  |  | checkpoint | Stairs placed, locations, heights and orientation approved. No damage during installation