## zres_siteapp
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | AE-ITCX-009 - Mains Cabling Reticulation Test Sheet (Rev 1 +Names) |  |  |  |  | Yes | AE-ITCX-009 - Mains Cabling Reticulation Test Sheet (Rev 1 +Names) | fef72688-e49f-475e-aa08-daba6955a5ca
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Latest consented drawings checked & referenced
text | 465d386c-9e2f-5f5d-ae32-49ab228b3172 |  | textbox | Drawing & Revision #
checkpoint-status |  |  | checkpoint | Pass Once Clear Readable Photo Has Been Attached
checkpoint-group |  |  | section | Test No.1
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | 4c316c2a-b0e9-56a9-badd-d4a5cf40515d |  | textbox | Cable No
text | 5f8d2706-38b8-5446-b6d7-f114135edc6f |  | textbox | Cable Origin
text | 24c5e7b3-0a7b-5b7e-b362-2c227bda27a2 |  | textbox | Cable Destination
text | 3fc1cd4b-7e97-58be-88ac-a2127dfbccd0 |  | textbox | Upstream Circuit Breaker Size
select | 13cc02cb-8933-518a-80c3-1468a47c796d |  | dropdown | Type of Cable | X = XLPE, O = Orange Circ, M = MIMS
button | 07cf5deb-b618-51b2-bcb4-21247c64b76a |  | button | Fire Rated | Yes, No
text | 73160e3e-2ad8-5ac9-81d5-4485e22498c0 |  | textbox | Cable Size (mm²)
text | e7946318-9c39-5c08-9649-362300ca2b9f |  | textbox | Earth Conductor Size (mm²)
select | ed2d36c0-7325-5895-9961-f02befc83bee |  | dropdown | Support Method | Tray, Catenary, Duct, Other (Specify Below)
text | e0f32da3-bb4b-5b29-bdce-be0ca630f9a4 |  | textbox | Other (Specify here)
select | 302c7f8f-68db-529c-84a8-ef3d7075b0d4 |  | dropdown | Tie in Method | Nylon, Steel, Cleats
button | 7543a04c-0900-58f0-9a88-3b6a300ab377 |  | button | Line & Load Side Termination Checked & torque (ITCX-010) | Yes, No
select | 4c496d35-31ee-57b0-b4e3-e0f8e2c94216 |  | dropdown | Cable Grouping | Trefoil, Flat, Quad
select | ad22374d-0d35-5e3e-8b5e-9786b61e0369 |  | dropdown | Cable Spacing on tray required | Yes - Minimum 1D, Not required
text | cd1a6ff0-7f7a-52cd-9cf0-c1101d2e53d9 |  | textbox | Cable Earth Resistance
checkpoint-status |  |  | checkpoint | Insulation Resistance - Pass Once below details are completed
text | 0a2fa70c-a31a-5ca3-a918-7a2e4affa069 |  | textbox | Red / White
text | 76fe93eb-9b84-5e57-a5c5-4e3f38da1931 |  | textbox | Red / Blue
text | 2562f6c8-f19c-5943-b214-a78963e0eb2e |  | textbox | Red / Earth
text | 2088d5cc-7fea-55eb-b07b-de380629a2b0 |  | textbox | Blue / White
text | c6fac328-c8c5-51af-a70d-c674e3d6c803 |  | textbox | Blue / Earth
text | 3f922196-bc52-5c32-8738-82f32c462cb0 |  | textbox | White / Earth
text | 61db16ef-2ceb-58b1-bbb8-0b5ffe6f3cd4 |  | textbox | White / Neutral
text | fac9bb6b-277a-501e-8ab3-9c1810782a62 |  | textbox | Red / Neutral
text | 4a2fd860-fc19-5e06-9c0f-d9c4eb3fc43b |  | textbox | Blue / Neutral
text | 30c4c9a2-980d-56e3-ad72-fb699358a29c |  | textbox | Neutral / Earth (MEN Disconnected)
text | e8157a34-3471-5f71-8b49-999ab20c6225 |  | textbox | Earth Loop Impedance
text | 08569a8b-b05f-561d-9f82-bba066f8a96c |  | textbox | Name
label | 91a8d02d-06e5-530c-949c-d97b201ee1ab |  | note | Signature added below
checkpoint-status |  |  | checkpoint | Photo
button | a5b544ac-b8ad-5c16-949e-a11c778fbc13 |  | button | Photo of Completed Cable in Chamber | Yes, No
checkpoint-group |  |  | section | Test No.2
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | 65bca6b3-c87a-5f28-bfed-c5aca7000282 |  | textbox | Cable No
text | d28db0a7-cfd4-5394-9f29-03eedcde4fd0 |  | textbox | Cable Origin
text | c7af2f42-6980-54a2-96f9-1af70edc23f5 |  | textbox | Cable Destination
text | 2f4469bb-220a-5c4b-a478-38d3089d3802 |  | textbox | Upstream Circuit Breaker Size
select | 0e51e91a-9a75-5e04-9ab3-b3e94aa812fb |  | dropdown | Type of Cable | X = XLPE, O = Orange Circ, M = MIMS
button | c23af699-447b-53e0-a802-03b6fe21540a |  | button | Fire Rated | Yes, No
text | 95d2361c-4d7e-5f78-a535-c8294ad78683 |  | textbox | Cable Size (mm²)
text | ac06c643-20ff-5ce0-a3ec-99cc208f3c19 |  | textbox | Earth Conductor Size (mm²)
select | 3bffa79e-e1d6-58f3-b227-d2ad3acbbe55 |  | dropdown | Support Method | Tray, Catenary, Duct, Other (Specify Below)
text | 7e8b036b-5725-5097-b8aa-58031c3c5490 |  | textbox | Other (Specify here)
select | 3da3a402-060f-5aad-91ce-6909c4b132e7 |  | dropdown | Tie in Method | Nylon, Steel, Cleats
button | 4ecceb71-dc2e-5864-a5d9-206ed730b162 |  | button | Line & Load Side Termination Checked & torque (ITCX-010) | Yes, No
select | 0a6c5b8e-13e3-542a-b6fa-5a0adf2f1ed2 |  | dropdown | Cable Grouping | Trefoil, Flat, Quad
select | c1ed5066-cb4d-5307-a5ab-833e20637b61 |  | dropdown | Cable Spacing on tray required | Yes - Minimum 1D, Not required
text | c0c0ac8f-2b45-5dba-a1cf-df1467dd12eb |  | textbox | Cable Earth Resistance
checkpoint-status |  |  | checkpoint | Insulation Resistance - Pass Once below details are completed
text | cabef32f-b309-58f0-9781-c837ba4809bd |  | textbox | Red / White
text | e24cfab5-2c84-5aa5-8a84-5b16cc2d9249 |  | textbox | Red / Blue
text | 442413eb-19d6-5a48-9ee1-0c6bafff7b92 |  | textbox | Red / Earth
text | f924caa2-bb2e-5e69-8fac-a91581e17680 |  | textbox | Blue / White
text | 4c10f9d1-07d4-5908-83bd-bdd91ef1f8d1 |  | textbox | Blue / Earth
text | 8c435ce2-e567-5d08-856c-52fffb06c524 |  | textbox | White / Earth
text | a5dcefe2-e141-5b97-94cf-22bc091a1d8f |  | textbox | White / Neutral
text | 054dd426-750e-5df6-8a19-5085c7683978 |  | textbox | Red / Neutral
text | 9dbc6156-561d-5be9-91fc-7fbe3cbe2fa3 |  | textbox | Blue / Neutral
text | 48166cbd-e3b0-5dae-9baa-d6396755d1ab |  | textbox | Neutral / Earth (MEN Disconnected)
text | bdf45df6-4879-5ec4-b55a-93c4f1f73327 |  | textbox | Earth Loop Impedance
text | 0b2114bc-d38c-5e91-aabb-4b6d52509893 |  | textbox | Name
label | c7f10f57-8ea7-5910-ab9b-cba2dc2eda1d |  | note | Signature added below
checkpoint-status |  |  | checkpoint | Photo
button | 9edd4429-a8d7-5cda-98c8-76824a0cd5fe |  | button | Photo of Completed Cable in Chamber | Yes, No
checkpoint-group |  |  | section | Test No.3
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | 90cc0cc4-591d-511c-b774-b34cfc97f3a1 |  | textbox | Cable No
text | 393e413c-9d21-5ab4-bf28-2e5a7a2e471f |  | textbox | Cable Origin
text | 2819c361-4539-536e-a718-cc10c77e9d7c |  | textbox | Cable Destination
text | a8f7ab93-be18-5c32-907f-699985d7054a |  | textbox | Upstream Circuit Breaker Size
select | 5abecfad-1d4a-5dcc-9130-8d11f1e56fac |  | dropdown | Type of Cable | X = XLPE, O = Orange Circ, M = MIMS
button | 52cc7c41-5ae8-519e-81ba-d3f19eb0f972 |  | button | Fire Rated | Yes, No
text | 901ce4e3-bac5-5d3e-95c5-e50c825e5a53 |  | textbox | Cable Size (mm²)
text | 0bf5672b-9e8d-5b65-8d0f-0e06f078b03e |  | textbox | Earth Conductor Size (mm²)
select | 80d37511-cb3c-5f58-bafd-6169a062ddd6 |  | dropdown | Support Method | Tray, Catenary, Duct, Other (Specify Below)
text | 130b472f-974b-557e-85ed-cda8048887ea |  | textbox | Other (Specify here)
select | 98487f9e-b593-559f-abe2-714fe75f732b |  | dropdown | Tie in Method | Nylon, Steel, Cleats
button | 874837b3-3437-5400-88ef-202cfaf330cb |  | button | Line & Load Side Termination Checked & torque (ITCX-010) | Yes, No
select | b9ccb4a7-ee73-52a5-b142-d2b76b6a720c |  | dropdown | Cable Grouping | Trefoil, Flat, Quad
select | 58942221-a642-5988-a567-c11c9de0225e |  | dropdown | Cable Spacing on tray required | Yes - Minimum 1D, Not required
text | 996fd414-e90f-5d80-b305-7a2b6cd52023 |  | textbox | Cable Earth Resistance
checkpoint-status |  |  | checkpoint | Insulation Resistance - Pass Once below details are completed
text | defec24a-24fc-54e3-abb7-f0f53dd1ed79 |  | textbox | Red / White
text | 4e098d04-6473-56e1-922f-3f1bc2056257 |  | textbox | Red / Blue
text | 4cf2afa8-ff32-5842-9a82-6d99c227184e |  | textbox | Red / Earth
text | a2adb45d-b138-57a0-b43f-2a4282716635 |  | textbox | Blue / White
text | 67b48fc3-8127-5f67-aa04-244758155239 |  | textbox | Blue / Earth
text | 13b97996-36ff-5109-b864-1d52f7aaa32a |  | textbox | White / Earth
text | bd4cc809-7325-572c-b22b-9e15dfb05613 |  | textbox | White / Neutral
text | a363e0e9-793a-5c8d-9c2a-394e05468ea7 |  | textbox | Red / Neutral
text | 4447e868-a760-54ef-8f84-b919d757cc21 |  | textbox | Blue / Neutral
text | 1a4ea965-e76c-5c31-80f0-35e6fd98f1b0 |  | textbox | Neutral / Earth (MEN Disconnected)
text | d092d5a2-e129-5ff4-ae91-56899fef135f |  | textbox | Earth Loop Impedance
text | 4e0e6735-9875-5228-921c-4b930b9d005f |  | textbox | Name
label | ba7c6718-6243-54c4-8813-5307c0457eb8 |  | note | Signature added below
checkpoint-status |  |  | checkpoint | Photo
button | 60ef51f0-0539-5f94-b28b-404dcb76b68c |  | button | Photo of Completed Cable in Chamber | Yes, No
checkpoint-group |  |  | section | Test No.4
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | 01c732ed-140d-5435-818e-dc36fb6d9d65 |  | textbox | Cable No
text | b8139838-6962-5de1-bc5c-3f8d4fe750b5 |  | textbox | Cable Origin
text | efc7e44d-b1b1-51e0-b447-1512b0572477 |  | textbox | Cable Destination
text | fdbfdbee-6f13-5609-980f-e235f7e03f72 |  | textbox | Upstream Circuit Breaker Size
select | faf01eb2-572b-5ba5-ae18-e63a725db58b |  | dropdown | Type of Cable | X = XLPE, O = Orange Circ, M = MIMS
button | aff51ec7-2063-525e-8920-6397406c3ab4 |  | button | Fire Rated | Yes, No
text | 36c6daec-d33a-5327-9292-6b5007be6e2e |  | textbox | Cable Size (mm²)
text | 1fd1111f-7aa7-547c-a9c8-17b99c7a0ca0 |  | textbox | Earth Conductor Size (mm²)
select | 4b33a6b9-d637-5044-b867-81162153916c |  | dropdown | Support Method | Tray, Catenary, Duct, Other (Specify Below)
text | a10a7080-0a80-54b1-8098-f2cf397ea3c6 |  | textbox | Other (Specify here)
select | 528be823-ddd5-5901-a98b-a432a25dbe18 |  | dropdown | Tie in Method | Nylon, Steel, Cleats
button | aeb4368c-1257-5727-9282-c376333e4a7e |  | button | Line & Load Side Termination Checked & torque (ITCX-010) | Yes, No
select | c38142b5-b7eb-5cd1-a9da-3d4af17cda3f |  | dropdown | Cable Grouping | Trefoil, Flat, Quad
select | 4f8e97f4-6996-5f4b-bf5a-eb596986d089 |  | dropdown | Cable Spacing on tray required | Yes - Minimum 1D, Not required
text | 0c37537c-b1d5-51bf-9c23-7eace62c6262 |  | textbox | Cable Earth Resistance
checkpoint-status |  |  | checkpoint | Insulation Resistance - Pass Once below details are completed
text | 3b3f91de-9577-5e12-b463-f898843bed54 |  | textbox | Red / White
text | 0605cee0-0295-5189-ba50-20c162ce7afe |  | textbox | Red / Blue
text | bc82ce26-9b92-5755-8c76-5368cf1e190b |  | textbox | Red / Earth
text | 4a4317f7-a61c-5ff3-a1d0-7ff559d3098e |  | textbox | Blue / White
text | 0839bff1-ef8f-5334-98f5-2ef7714f8289 |  | textbox | Blue / Earth
text | ace55ef0-1d1a-52dd-9141-bd570efa7ee8 |  | textbox | White / Earth
text | ee0789a3-8261-5e45-90f0-84a59cfcb954 |  | textbox | White / Neutral
text | 7e28fe32-b11f-5ff9-82f4-89f0e04dbc3b |  | textbox | Red / Neutral
text | 44c57a58-48e4-52df-9823-f36b36da74c1 |  | textbox | Blue / Neutral
text | e6f004f7-51e6-589f-a8f6-103a92b5ad70 |  | textbox | Neutral / Earth (MEN Disconnected)
text | 6aad6b28-aa17-5ae4-87b9-2194e2dcdf06 |  | textbox | Earth Loop Impedance
text | ca496ce8-e4d1-5b1b-9072-b53ab5a25668 |  | textbox | Name
label | 6618a710-e69d-5d80-aa7e-87c44b4b5b71 |  | note | Signature added below
checkpoint-status |  |  | checkpoint | Photo
button | 5e13f0dd-81d6-5de9-9b94-248f1d09de5c |  | button | Photo of Completed Cable in Chamber | Yes, No
checkpoint-group |  |  | section | Test No.5
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | b1b5e357-080f-510d-9e84-c33ec4d90290 |  | textbox | Cable No
text | 43d95075-ca81-5d8d-9352-271f97647305 |  | textbox | Cable Origin
text | ebde8e5d-15f1-5975-bbfd-8502369a3bb4 |  | textbox | Cable Destination
text | 4ba38b26-f280-51d2-8885-37d5dd3b64bc |  | textbox | Upstream Circuit Breaker Size
select | 8ed72115-eacf-57cc-9132-de3415944de5 |  | dropdown | Type of Cable | X = XLPE, O = Orange Circ, M = MIMS
button | c8c06ada-79d5-591c-a1fe-293af92ac105 |  | button | Fire Rated | Yes, No
text | 486bd43c-f601-506f-9933-50708e96204a |  | textbox | Cable Size (mm²)
text | e4b6327b-f4cd-5372-8e49-8cc6795c42df |  | textbox | Earth Conductor Size (mm²)
select | 2b645fa2-baab-5402-b762-175003cf1b7f |  | dropdown | Support Method | Tray, Catenary, Duct, Other (Specify Below)
text | 494cbaca-1182-5c96-a6c9-658c809619d5 |  | textbox | Other (Specify here)
select | 99d9775c-66ca-5e58-8b29-e9f396ae75ec |  | dropdown | Tie in Method | Nylon, Steel, Cleats
button | 00625959-d0ad-5509-9814-ce0071e865c3 |  | button | Line & Load Side Termination Checked & torque (ITCX-010) | Yes, No
select | 8ecf7419-826b-5d87-872c-c114993f2c24 |  | dropdown | Cable Grouping | Trefoil, Flat, Quad
select | d76ec3d3-3d28-501f-a4b6-74c41de139a0 |  | dropdown | Cable Spacing on tray required | Yes - Minimum 1D, Not required
text | 6c2a0be4-8dc1-593f-9f08-1f31bff761c8 |  | textbox | Cable Earth Resistance
checkpoint-status |  |  | checkpoint | Insulation Resistance - Pass Once below details are completed
text | 5e6cec30-fb71-5487-80c8-ffbc88bbe08b |  | textbox | Red / White
text | 64e54b4e-46ae-55af-bd72-50b89b1c13a7 |  | textbox | Red / Blue
text | b44ce913-1361-53ec-b9c4-ed09339276eb |  | textbox | Red / Earth
text | b1b9d1f4-ad95-5334-8a6d-6af6066647ee |  | textbox | Blue / White
text | b14db7d4-7958-585e-a78b-7cb21d14087f |  | textbox | Blue / Earth
text | 552ca841-ccea-5fc6-bb06-9a5db1c409dc |  | textbox | White / Earth
text | ee0b36b4-7c6e-5a76-be70-7f7d71d3e8a5 |  | textbox | White / Neutral
text | 4c3026de-264a-59be-ab07-24fbea3d8663 |  | textbox | Red / Neutral
text | 26971cea-b500-5a23-84e3-9a9ea352287c |  | textbox | Blue / Neutral
text | 031ce801-f170-52e4-be0b-bb89e96162d4 |  | textbox | Neutral / Earth (MEN Disconnected)
text | 3aec9cc5-e293-598b-950a-a07f1dae9f3e |  | textbox | Earth Loop Impedance
text | cf389c03-134f-5a0b-9364-ea1d7f175195 |  | textbox | Name
label | 03e1edc5-2479-5b86-8d19-6ce0aeb8e841 |  | note | Signature added below
checkpoint-status |  |  | checkpoint | Photo
button | 9507fd38-4dae-5264-bc2f-12dcfbeba9de |  | button | Photo of Completed Cable in Chamber | Yes, No
checkpoint-group |  |  | section | Test No.6
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | dccb7636-9b99-5364-ab08-67ef6d4f6daa |  | textbox | Cable No
text | a714f6e2-a994-5693-9b35-9ffcc1e75b05 |  | textbox | Cable Origin
text | d9ed7538-ca1f-5d77-aa86-d1901b395d6d |  | textbox | Cable Destination
text | f98c9150-cc76-5c66-8e16-6f595a3c98fc |  | textbox | Upstream Circuit Breaker Size
select | 9f4bc26a-501d-59ff-b7f1-dbf0a3388e43 |  | dropdown | Type of Cable | X = XLPE, O = Orange Circ, M = MIMS
button | 10269147-f25c-5e02-8233-b26dc996319c |  | button | Fire Rated | Yes, No
text | f7c41b95-c796-5ec6-b928-e2efe4ce283c |  | textbox | Cable Size (mm²)
text | 9de26b1b-809f-5e43-9685-40f1d3beaa37 |  | textbox | Earth Conductor Size (mm²)
select | debc48ec-2b80-53b0-b573-b2c59948dec1 |  | dropdown | Support Method | Tray, Catenary, Duct, Other (Specify Below)
text | 10c41a59-c38c-5802-802c-f3d9b0373264 |  | textbox | Other (Specify here)
select | 9b831d44-b7aa-5f2f-b9a8-c735e4105d65 |  | dropdown | Tie in Method | Nylon, Steel, Cleats
button | c1ae7b29-2a47-5a71-bcf8-732dfc09c5eb |  | button | Line & Load Side Termination Checked & torque (ITCX-010) | Yes, No
select | b0b75a80-4246-50e9-9fa7-3045d61acd16 |  | dropdown | Cable Grouping | Trefoil, Flat, Quad
select | 3f3ba77a-cd4b-5816-b90e-4e106a96ad68 |  | dropdown | Cable Spacing on tray required | Yes - Minimum 1D, Not required
text | eb53acb4-d929-57dc-886a-d790c5414c65 |  | textbox | Cable Earth Resistance
checkpoint-status |  |  | checkpoint | Insulation Resistance - Pass Once below details are completed
text | b94e647e-de5b-5de0-ad5d-50ec3182b584 |  | textbox | Red / White
text | d3a58544-2e03-571f-9232-7b0821642e6d |  | textbox | Red / Blue
text | 99b8b51f-8e2e-5a57-8bfb-80180a926f15 |  | textbox | Red / Earth
text | 3595edf7-0d7c-5d59-a0d9-9157ab0a2f47 |  | textbox | Blue / White
text | 15fa5c19-25bf-5af5-91bd-1cad182aea02 |  | textbox | Blue / Earth
text | b10adb9b-be57-5be3-9f98-bd5268fb9928 |  | textbox | White / Earth
text | 880ba6df-9b5d-56f5-8795-b891543fc3fa |  | textbox | White / Neutral
text | 835faf47-05f2-55ff-b4dd-7ae7f13f603f |  | textbox | Red / Neutral
text | bfdf2f01-3b5c-5d7d-b2e7-f31c0a8d782e |  | textbox | Blue / Neutral
text | 8aacc9d8-a561-5c47-85ed-93884debd171 |  | textbox | Neutral / Earth (MEN Disconnected)
text | c297e31d-9e1f-5a19-8c1a-414cd25c78ff |  | textbox | Earth Loop Impedance
text | e567d0e8-8d22-5e1c-b2fa-1f982e042351 |  | textbox | Name
label | bfb571af-5e9f-56e4-a309-eb229aa42f8c |  | note | Signature added below
checkpoint-status |  |  | checkpoint | Photo
button | 2d211282-b8d5-5626-ac1a-0f9415094bce |  | button | Photo of Completed Cable in Chamber | Yes, No
checkpoint-group |  |  | section | Test No.7
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | 0ebc4cdf-d279-559f-b0fb-236173307478 |  | textbox | Cable No
text | 30808aa9-0314-559e-8e8f-d22c818fb224 |  | textbox | Cable Origin
text | 872d5222-599f-5c16-8869-2a6da6233362 |  | textbox | Cable Destination
text | 0a368710-91f1-5179-a069-b08cf7f850f0 |  | textbox | Upstream Circuit Breaker Size
select | cca1b35d-d3d7-5eef-93d6-d99fb004f058 |  | dropdown | Type of Cable | X = XLPE, O = Orange Circ, M = MIMS
button | 72b2a33e-1817-548c-8295-4679581f3207 |  | button | Fire Rated | Yes, No
text | 99e1a8ff-452d-5d16-b368-3b9cccffa337 |  | textbox | Cable Size (mm²)
text | 48e2681b-dac2-5333-bda2-dfa6810efdc8 |  | textbox | Earth Conductor Size (mm²)
select | e13b465c-7790-5ed0-a407-edcb33a3e37e |  | dropdown | Support Method | Tray, Catenary, Duct, Other (Specify Below)
text | 2478c497-4c1b-5b5f-99ef-ae631c50ba5f |  | textbox | Other (Specify here)
select | 3784acf6-12ac-52c6-9b9f-5ec65bf0d4c5 |  | dropdown | Tie in Method | Nylon, Steel, Cleats
button | 76561a99-c9f8-5e5c-a5d1-a35afd14fff6 |  | button | Line & Load Side Termination Checked & torque (ITCX-010) | Yes, No
select | 62edf763-fae2-513e-889a-b901618fb5be |  | dropdown | Cable Grouping | Trefoil, Flat, Quad
select | ed926ea2-9363-5e3f-95e2-1b247b588aa8 |  | dropdown | Cable Spacing on tray required | Yes - Minimum 1D, Not required
text | 5051552a-dd6a-515c-a115-41a9de08e481 |  | textbox | Cable Earth Resistance
checkpoint-status |  |  | checkpoint | Insulation Resistance - Pass Once below details are completed
text | e6345947-4257-5a42-992f-9becc0b26e5f |  | textbox | Red / White
text | 77ca3784-9b27-5382-8834-08a150dda573 |  | textbox | Red / Blue
text | 6a2a210b-54e5-5f24-9b03-89d626180fb5 |  | textbox | Red / Earth
text | d686d81c-eeac-55c5-a0ba-16297cd037c1 |  | textbox | Blue / White
text | 6f32230d-5a39-5d61-8f0a-c56509918c03 |  | textbox | Blue / Earth
text | fbec1372-8ad1-5dd6-b7fa-96e75c4381c5 |  | textbox | White / Earth
text | 92c706df-fc2d-5515-bf79-ccc407dcb32a |  | textbox | White / Neutral
text | 8cd95ac9-037c-54c5-be3b-66821d04abf7 |  | textbox | Red / Neutral
text | c5a6710b-92ed-5896-a9e0-5192fab8e54d |  | textbox | Blue / Neutral
text | 225e7963-3be1-5e94-8a19-43451bc63e96 |  | textbox | Neutral / Earth (MEN Disconnected)
text | 74f09d54-3cea-5a4c-b895-bc475bd4c441 |  | textbox | Earth Loop Impedance
text | 0d4c088a-cb32-5e5a-bb7a-b351c831252c |  | textbox | Name
label | 301b2dd3-e110-5970-b0c5-f9dbedc97f2b |  | note | Signature added below
checkpoint-status |  |  | checkpoint | Photo
button | 8756d3c2-2219-5f0c-9968-92051fe3a84b |  | button | Photo of Completed Cable in Chamber | Yes, No
checkpoint-group |  |  | section | Test No.8
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | 54e69c5b-3e02-5f50-8ebb-4650d7b0a03c |  | textbox | Cable No
text | 57de2331-fcaf-5f95-ac7b-25ab5318e63a |  | textbox | Cable Origin
text | 734df301-1a44-5e46-9319-f32cfa8ce3b1 |  | textbox | Cable Destination
text | cf1050db-fdc1-5330-b872-d1b94e38b1cf |  | textbox | Upstream Circuit Breaker Size
select | 81927e3c-570f-5c7f-9f84-3cc97d9d771d |  | dropdown | Type of Cable | X = XLPE, O = Orange Circ, M = MIMS
button | 0ad2e52c-c2e5-5402-87fa-bc234327aa65 |  | button | Fire Rated | Yes, No
text | a37719db-6f40-59c6-b4ab-16cf4a390a38 |  | textbox | Cable Size (mm²)
text | 2b33a2ad-7d40-5724-b040-eb26175c2b44 |  | textbox | Earth Conductor Size (mm²)
select | d3690a95-ee97-5b9b-a31f-98e2fe1faae9 |  | dropdown | Support Method | Tray, Catenary, Duct, Other (Specify Below)
text | deeb6162-6cb3-507f-932d-6d70e3f58c73 |  | textbox | Other (Specify here)
select | ac3c5359-5a61-550b-9092-1189ea56e219 |  | dropdown | Tie in Method | Nylon, Steel, Cleats
button | 2a6b67b6-9f75-5306-b017-757542f13f62 |  | button | Line & Load Side Termination Checked & torque (ITCX-010) | Yes, No
select | 411ce62b-f5d3-537b-9d49-b136afa934eb |  | dropdown | Cable Grouping | Trefoil, Flat, Quad
select | 0370956e-293a-537a-9a67-5c3b521894bd |  | dropdown | Cable Spacing on tray required | Yes - Minimum 1D, Not required
text | d60db05c-3ea3-524a-9ff1-794835ad815a |  | textbox | Cable Earth Resistance
checkpoint-status |  |  | checkpoint | Insulation Resistance - Pass Once below details are completed
text | 88a580fb-d7e5-5aeb-885b-9fbab3383571 |  | textbox | Red / White
text | 02d32fac-8854-5700-90b6-6616aa3dad30 |  | textbox | Red / Blue
text | d2166087-27c3-5037-a2a4-8b7ba096ff3d |  | textbox | Red / Earth
text | 2e3dc073-ed59-5705-b80f-22ee08d14385 |  | textbox | Blue / White
text | c9154592-b14f-546b-b8f2-bb35d1da4546 |  | textbox | Blue / Earth
text | aa7c9f04-f083-57a3-b9ae-b5646f76c94d |  | textbox | White / Earth
text | 4d7ea7cd-2271-5d02-b936-84947f8a0163 |  | textbox | White / Neutral
text | 99fbce9a-59f3-5067-b910-7d2ecd812ded |  | textbox | Red / Neutral
text | 796c82a5-e6f4-5d4a-83be-8bfbb71cc3ce |  | textbox | Blue / Neutral
text | 76444bf6-2f15-58fe-8688-8869d9fb630c |  | textbox | Neutral / Earth (MEN Disconnected)
text | 5465189b-497f-51c1-8362-cdbe048940fd |  | textbox | Earth Loop Impedance
text | ad9c1035-e047-5bff-8705-1faaec981aae |  | textbox | Name
label | 75725666-794e-53e0-b68b-70ad611df4df |  | note | Signature added below
checkpoint-status |  |  | checkpoint | Photo
button | 784b288b-a841-50d2-8bfd-4bd8595ce051 |  | button | Photo of Completed Cable in Chamber | Yes, No
checkpoint-group |  |  | section | Test No.9
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | 14410788-3d4e-5d22-a949-2b1e8942fe2f |  | textbox | Cable No
text | 501059dc-e762-5af6-88cd-beb106792824 |  | textbox | Cable Origin
text | 555a1193-e169-57e6-83c4-1b8523766d79 |  | textbox | Cable Destination
text | 043f2eb0-ce7f-5031-a3c5-f78522adddc2 |  | textbox | Upstream Circuit Breaker Size
select | 8fb272eb-fcb7-5bfe-bf57-65b7e408cd6d |  | dropdown | Type of Cable | X = XLPE, O = Orange Circ, M = MIMS
button | 68e9eaa1-6022-5aff-a98f-b460d3abf1c5 |  | button | Fire Rated | Yes, No
text | f0316d1c-a32e-5256-8c9a-2fa7b66e24f0 |  | textbox | Cable Size (mm²)
text | f4218e79-ff23-5ea6-a4fe-832be65f0e0a |  | textbox | Earth Conductor Size (mm²)
select | 5e22573a-5c2a-56cd-8c62-73656ca2343c |  | dropdown | Support Method | Tray, Catenary, Duct, Other (Specify Below)
text | bc51a60b-6462-589c-b273-e0f1384f1ae7 |  | textbox | Other (Specify here)
select | 31049dac-17c5-5625-be70-f92d848e9872 |  | dropdown | Tie in Method | Nylon, Steel, Cleats
button | d2dbfc57-6de6-526f-ab97-fc150a166763 |  | button | Line & Load Side Termination Checked & torque (ITCX-010) | Yes, No
select | cfd8b31a-0b7b-54e1-8b1b-eb205c762a46 |  | dropdown | Cable Grouping | Trefoil, Flat, Quad
select | b9d6cf98-1b39-5ca7-b53b-7c0018952ff8 |  | dropdown | Cable Spacing on tray required | Yes - Minimum 1D, Not required
text | ba2bbb94-9ebb-5641-a799-235120eece1f |  | textbox | Cable Earth Resistance
checkpoint-status |  |  | checkpoint | Insulation Resistance - Pass Once below details are completed
text | 76752356-a740-5631-b9bb-22db456015cb |  | textbox | Red / White
text | f879fc27-f6a6-5255-98d7-479e1eaa8c68 |  | textbox | Red / Blue
text | cf465e47-c5d4-5943-859b-df99eb850c35 |  | textbox | Red / Earth
text | 46324fe7-5630-5808-b8a0-f353883c8136 |  | textbox | Blue / White
text | 1e6c6af4-8945-5329-91d7-f6d497879566 |  | textbox | Blue / Earth
text | 8474a0a9-0028-5350-96d8-1ecff6fd1fbc |  | textbox | White / Earth
text | c1e4bb42-f3b6-583c-afa3-b6fcd9ba1e2d |  | textbox | White / Neutral
text | b51f9213-d97b-5349-b357-e13919c56583 |  | textbox | Red / Neutral
text | baf1128f-aa9d-5934-aa4c-0e61c200ac3e |  | textbox | Blue / Neutral
text | 0d33f3fc-5184-51c7-aa20-c9d831234530 |  | textbox | Neutral / Earth (MEN Disconnected)
text | 32cac01b-24a5-5e36-a21b-cd4d67e57ffd |  | textbox | Earth Loop Impedance
text | e8fef62c-b983-5a61-850f-3ea9c1195653 |  | textbox | Name
label | 28c28f7d-a45b-5a5e-becd-2ebfbbf5445f |  | note | Signature added below
checkpoint-status |  |  | checkpoint | Photo
button | 670acc64-8f6d-5c26-a436-9d98fc1aab52 |  | button | Photo of Completed Cable in Chamber | Yes, No
checkpoint-group |  |  | section | Test No.10
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | 86f3c246-309d-5c69-b392-81d0cb26c01f |  | textbox | Cable No
text | b42ea877-9900-5737-a88e-d2b75daeb42b |  | textbox | Cable Origin
text | 83a660f5-36b5-5cfd-bff0-9c99d6a3a214 |  | textbox | Cable Destination
text | 6d5b75cd-30e3-55df-9be6-644f7c1a23fb |  | textbox | Upstream Circuit Breaker Size
select | 9b878113-a442-5b4c-890c-074453d0acf3 |  | dropdown | Type of Cable | X = XLPE, O = Orange Circ, M = MIMS
button | b183fe56-964f-508f-ad06-605451206f8f |  | button | Fire Rated | Yes, No
text | 750af724-ee3d-54c8-b434-befda23fe7a6 |  | textbox | Cable Size (mm²)
text | 23db7835-f457-5429-bb8b-3a72bf9dfede |  | textbox | Earth Conductor Size (mm²)
select | d2f35d7a-d3c6-5dd8-a36e-74540d60d417 |  | dropdown | Support Method | Tray, Catenary, Duct, Other (Specify Below)
text | fe1881ea-c345-519d-8b1b-61108967a772 |  | textbox | Other (Specify here)
select | fdfbce69-7dac-567e-b8a2-4e43f473f39a |  | dropdown | Tie in Method | Nylon, Steel, Cleats
button | eefa69e1-eb22-50ea-a496-688791fc6d29 |  | button | Line & Load Side Termination Checked & torque (ITCX-010) | Yes, No
select | 0b4282cb-1cbc-504d-8684-8728eb7e41e7 |  | dropdown | Cable Grouping | Trefoil, Flat, Quad
select | 067a5d7c-6421-5083-acb0-0f9094fa7e09 |  | dropdown | Cable Spacing on tray required | Yes - Minimum 1D, Not required
text | 234d5383-ce11-5061-bdc6-8d71e2841469 |  | textbox | Cable Earth Resistance
checkpoint-status |  |  | checkpoint | Insulation Resistance - Pass Once below details are completed
text | e3b9f9c2-9bad-50b2-a2b2-14c5e1548639 |  | textbox | Red / White
text | 7842bc11-9d56-5ed5-84b8-6e1de493b533 |  | textbox | Red / Blue
text | 9ab20a8d-753e-5b0c-9f13-c94b04cf0071 |  | textbox | Red / Earth
text | 42d1aab4-ba6b-5347-aabc-06f5577c8b38 |  | textbox | Blue / White
text | 535000df-c844-5024-9f00-2e1b9bc8e355 |  | textbox | Blue / Earth
text | 7f8bc8ca-f963-5987-9965-46c233ff4aa7 |  | textbox | White / Earth
text | b01b2e4a-6abc-5485-86cc-f6104860dac1 |  | textbox | White / Neutral
text | e5889362-ff92-53eb-919c-afa5c4748f59 |  | textbox | Red / Neutral
text | 61c14d90-7f6b-5fa1-94fc-a92726e6f6fb |  | textbox | Blue / Neutral
text | 7c3622b1-553d-5e4f-adfe-d72c5c59d70f |  | textbox | Neutral / Earth (MEN Disconnected)
text | d1f3fa85-84d3-5bd3-899b-412a334efef8 |  | textbox | Earth Loop Impedance
text | 2c029133-585f-5ec5-a4c2-b30f03968a3c |  | textbox | Name
label | 245965fc-0bd6-5dcf-bfc3-650f7e674766 |  | note | Signature added below
checkpoint-status |  |  | checkpoint | Photo
button | 52f328ca-d01c-5ef7-854f-75f94a434239 |  | button | Photo of Completed Cable in Chamber | Yes, No
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Relevant works completed to specification/drawings - Area left clean & tidy
label | 8e793363-caf7-5e53-949c-e6ca7453aa66 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | eec7fb88-d23a-525c-89a2-3ca8449aeb5f |  | note | Any Corrective Actions to be Photographed & Commented below
select | 54dedabb-b3ee-597a-a452-2e0410168f73 |  | dropdown | Installed by (Appselec) | FIELD OVERRIDE
text | bd5a981d-ca2b-5053-bc9b-854db30fcff6 |  | textbox | Other (Specify here)
select | 1c7a633f-83df-5e18-9798-c79742870d1f |  | dropdown | Checked by (Appselec) | FIELD OVERRIDE
text | 0e8b4ab0-1c53-5097-bab6-7e801d19096d |  | textbox | Other (Specify here)
text | f9459caa-c6fc-5dc9-b83c-e5f41a0bd833 |  | textbox | Witnessed by (Builder/QAM)
label | 5d7a0397-3b94-5ff5-a233-e03ab93400a9 |  | note | Signature Sign-Offs - Attach signature(s) below
checklist-sectioned |  |  | checklist | AE-ITCX-010 - Torque Settings for Bolts |  |  |  |  | Yes | AE-ITCX-010 - Torque Settings for Bolts (Rev 1 +Names) | 2fdc9567-3389-4bbb-8536-2255c95c1760
checkpoint-group |  |  | section | Reference Tables
checkpoint-status |  |  | checkpoint | Torque Setting Tables - Pass once tables are confirmed/read
label | 8a967b22-f2f3-57ad-9657-2bce129ceb8c |  | note | .. ..
label | cc2bed2d-dd78-5b75-b96f-9cfb9a13ff34 |  | note | Lugged Cables
label | 7fbb377f-5386-54b4-a921-617d49fcb4f5 |  | note | M6 - Class 8.8 Zinc plated - 9 Newton Meters
label | 8925d1c8-88e8-50c4-a5e7-5f065c171f7b |  | note | M8 - Class 8.8 Zinc plated - 22 Newton Meters
label | a647b0ad-4478-5ccd-b869-635980c894de |  | note | M10 - Class 8.8 Zinc plated - 44 Newton Meters
label | d574bd63-43cf-5c91-95c9-1cbfbf08298c |  | note | M12 - Class 8.8 Zinc plated - 77 Newton Meters
label | 6cd67444-e879-55f5-bd9e-7edb051d3bbf |  | note | M16 - Class 8.8 Zinc plated - 190 Newton Meters
label | 037ef6e3-1f21-5ea1-aaf2-173b2e54642b |  | note | .. ..
label | 9517be9b-e942-54f8-bedf-6ce144357760 |  | note | Bus Bars
label | 04db24ea-5a7b-500f-9c3c-13d48a3e0630 |  | note | M8 - Class 8.8 Zinc plated - 35 Newton Meters
label | b1980a8d-bd18-57cf-95b3-a2f0c037ebe0 |  | note | M10 - Class 8.8 Zinc plated - 50 Newton Meters
label | acd12069-0dd2-5913-9c49-8b8138cbf84a |  | note | M12 - Class 8.8 Zinc plated - 75 Newton Meters
label | d757bb09-a2cf-5f01-a812-e5b9453d233d |  | note | M16 - Class 8.8 Zinc plated - 190 Newton Meters
label | 0c69cf16-7028-568a-a6b7-9571b0968f3e |  | note | .. ..
label | 6826000a-e4ef-54d3-a235-7efdbc71a76c |  | note | ALL BOLTS SUPPLIED BY SWITCH BOARD MANUFACTURES, INCLUDING ALINE, ARE GRADE 8.8 BOLTS AND SHOULD NOT BE SUBSTITUTED
label | 7b0b0286-4e26-53e8-8f8a-f06d00f60950 |  | note | .. ..
label | 03ebba39-a848-5fa9-b15c-a6b722ccb787 |  | note | Torque Settings for SAGAME IPCs
label | 95eae9aa-c996-5138-9723-6543847c072a |  | note | TTD051XFA - 16 to 95 (Conductor Size MM2) - 1.5-10 (Branch Cable MM2) - 9 Newton Meters
label | a1359a5b-582e-5565-89ee-7577299aa3fa |  | note | TTD101XFA - 6 to 54 (Conductor Size MM2) - 6 to 35 (Branch Cable MM2) - 9 Newton Meters
label | baa617e4-cbf9-5a2d-9f16-693b1e1e0ac2 |  | note | TTD151XFA - 25 to 95 (Conductor Size MM2) - 6 to 35 (Branch Cable MM2) - 14 Newton Meters
label | 0dd25464-5e87-5fc2-a7f2-b89c14d1c9cc |  | note | TTD201XFA - 35 to 95 (Conductor Size MM2) - 25 to 95 (Branch Cable MM2) - 18 Newton Meters
label | 04e95ec6-7185-53a1-90b6-cf45790b94ef |  | note | TTD241XFA - 50 to 150 (Conductor Size MM2) - 6 to 35 (Branch Cable MM2) - 14 Newton Meters
label | f8291d9f-2f7e-5a89-bec3-8b57ae706b38 |  | note | TTD251XFA - 50 to 150 (Conductor Size MM2) - 35 to 95 (Branch Cable MM2) - 18 Newton Meters
label | a3eb43b4-eacf-550f-966c-ff0c67150e97 |  | note | TTD301XFA - 25 to 95 (Conductor Size MM2) - 25 to 95 (Branch Cable MM2) - 14 Newton Meters
label | 5a310cd8-6ab3-5428-8493-f8dda1462833 |  | note | TTD341F - 50 to 150 (Conductor Size MM2) - 6 to 35 (Branch Cable MM2) - 14 Newton Meters
label | 1ee666f3-1b9b-5301-9031-11b4dfd5c09f |  | note | TTD351XFA - 50 to 150 (Conductor Size MM2) - 35 to 95 (Branch Cable MM2) - 18 Newton Meters
label | 23a8675d-ee89-57c4-ae74-b58587499413 |  | note | TTD401XFA - 50 to 185 (Conductor Size MM2) - 50 to 150 (Branch Cable MM2) - 18 Newton Meters
label | 80298aef-da63-54ad-8a67-91145e372c0a |  | note | TTD431XFA - 70 to 240 (Conductor Size MM2) - 16 to 95 (Branch Cable MM2) - 20 Newton Meters
label | 21ec16ae-69c2-5984-b7c8-69c0aba73d80 |  | note | TTD451XFA - 95 to 240 (Conductor Size MM2) - 95 to 240 (Branch Cable MM2) - 25 Newton Meters
label | 8a661844-bcf2-56b8-91a3-c967ad991bdd |  | note | TTD551FJA - 120 to 380 (Conductor Size MM2) - 95 to 240 (Branch Cable MM2) - 37 Newton Meters
label | 906bf49e-2800-5e3a-a67d-27454b88cc93 |  | note | INSTALLATION NOTES FOR IPC’S: WHEN USING TWO BOLT CONNECTORS EACH BOLT MUST BE TIGHTENED A1/4 T0 1/2 TURN ALTERNATIVELY UNTIL THE SHEAR HEAD OPERATES
label | c8f7e5f0-ee83-5459-b08b-d81aed6a1e8b |  | note | .. ..
label | 4caebdb7-0148-5fec-b44a-eda1a715e509 |  | note | MANUFACTURER'S CIRCUIT BREAKERS - All torque settings must follow manufacturer's recommendations
checkpoint-group |  |  | section | Photo Of Completed Sheet
checkpoint-status |  |  | checkpoint | Pass Once Clear Readable Photo Has Been Attached
checkpoint-group |  |  | section | Test No.1
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | 2b00ef6d-1fb4-5cab-ac5c-141aa491b9ab |  | textbox | Bolt Size
text | ac564197-df5f-5ddd-a344-c973154d2823 |  | textbox | Switch/cable Identification
text | aaae4c23-9009-5feb-9db7-0177aed37001 |  | textbox | Line/Load
text | bd9bd255-fc0f-59de-874d-e05d17cbbb0b |  | textbox | Red Phase Torqued
text | 84087b7f-5afd-5c49-8e9b-48034f66c09f |  | textbox | White Phase Torqued
text | 7dc4dd7d-1b7b-5a5a-8066-5045ce80f61c |  | textbox | Blue Phase Torqued
text | 8772af86-b2e0-5f82-ba8c-e6d57d813eea |  | textbox | Neutral Torqued
text | a626580f-4744-5148-ae97-5f7ec76abee4 |  | textbox | Earth Torqued
text | 63b20da0-d6ca-5d8c-b6f1-ac534098e20f |  | textbox | Bolts Crossed With Black Texta
text | 84e79d7f-dd58-5189-b69b-0dfb4e825802 |  | textbox | Name
label | 3b6b6137-58e8-527f-ad07-59b5975a414f |  | note | Signature added below
checkpoint-group |  |  | section | Test No.2
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | 7d4f2948-f78b-514a-83bc-ad53531fba16 |  | textbox | Bolt Size
text | 9fa5f2bd-2309-5860-8b4c-13cdca0e1eec |  | textbox | Switch/cable Identification
text | 06caa5d0-2710-5696-ab7e-535fac748121 |  | textbox | Line/Load
text | e1e06a7d-a002-5fe1-92af-e35fb2307d99 |  | textbox | Red Phase Torqued
text | abb44c30-5501-5144-86ce-1c6cd92f2aad |  | textbox | White Phase Torqued
text | a4543111-f16e-5429-95ff-88e42fc787b5 |  | textbox | Blue Phase Torqued
text | 54f81341-f35e-58a9-9f18-7ecdbbb8ed0b |  | textbox | Neutral Torqued
text | c5e27ff0-f3f6-5f1e-baf0-6bba27c526d0 |  | textbox | Earth Torqued
text | 2234cdd6-ee92-5274-9f5b-360d58ef6df5 |  | textbox | Bolts Crossed With Black Texta
text | 7f30ea1b-62bd-5ea6-9ecb-704ef4dc46b3 |  | textbox | Name
label | 68da167b-eb44-59f3-9174-9033d49cbe91 |  | note | Signature added below
checkpoint-group |  |  | section | Test No.3
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | 1320a81a-fea6-5fcf-8d37-81f073beb5b7 |  | textbox | Bolt Size
text | 5eff7552-c68b-52bb-a7da-e694ac688f9e |  | textbox | Switch/cable Identification
text | b5ff2b6b-ef9d-5c70-bfc1-0f4373fced93 |  | textbox | Line/Load
text | 2ed09087-9078-50a8-bde3-1847ad86a983 |  | textbox | Red Phase Torqued
text | 0f9a9c4a-289a-5cc4-8808-286d0c3c9337 |  | textbox | White Phase Torqued
text | 71f8e927-8e0d-58fb-8fb4-8ca63561cac1 |  | textbox | Blue Phase Torqued
text | df6adb92-1abd-5b2c-922a-07273ac4487e |  | textbox | Neutral Torqued
text | 960ef68b-6900-5d4f-a230-dadd5918dd5e |  | textbox | Earth Torqued
text | ec98123c-0794-514e-a92e-c0eb68e3bb09 |  | textbox | Bolts Crossed With Black Texta
text | 0cb9b0b0-a565-5f7d-9d2b-2d9bd0a3e245 |  | textbox | Name
label | 5bb66385-e8f5-5589-8567-db332e37cee3 |  | note | Signature added below
checkpoint-group |  |  | section | Test No.4
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | 3ba7b63d-d134-5c58-99c7-d04f88cc0c09 |  | textbox | Bolt Size
text | e914d45d-a315-5750-9789-d6071d41e940 |  | textbox | Switch/cable Identification
text | 137c018f-f559-5960-a304-1fcfec17f1de |  | textbox | Line/Load
text | 471609f5-a811-558e-9ce5-109097ee603f |  | textbox | Red Phase Torqued
text | cb54be6b-a506-58dc-b2f6-c453ed89d292 |  | textbox | White Phase Torqued
text | a31775c2-5f56-597e-88eb-2f30fe5ec671 |  | textbox | Blue Phase Torqued
text | 8b6371c9-a317-5986-b83d-9087dbe63734 |  | textbox | Neutral Torqued
text | 74b094d8-cc25-53ad-9a71-a08b46c28bed |  | textbox | Earth Torqued
text | d72c6279-8b4e-5846-8cc5-f92e6ee4130f |  | textbox | Bolts Crossed With Black Texta
text | d701596f-0310-50a1-88c9-cc918b64445e |  | textbox | Name
label | 0eafbb8f-80b6-57ab-9eef-4bad911f1eb1 |  | note | Signature added below
checkpoint-group |  |  | section | Test No.5
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | 42ee5876-1948-57e7-9db9-112a062fc58e |  | textbox | Bolt Size
text | 58c0eee5-d429-5c0d-b663-e5de909fe8e2 |  | textbox | Switch/cable Identification
text | 95fc9705-aa99-5931-9b08-4595e54c3caa |  | textbox | Line/Load
text | a360f376-b150-5f55-b5da-3c58f069dc5b |  | textbox | Red Phase Torqued
text | 53aa3322-bac5-5984-bab0-58c6504720cd |  | textbox | White Phase Torqued
text | 7fddadd5-10e9-5371-99b3-c18e8be05aa4 |  | textbox | Blue Phase Torqued
text | 34439c65-47c3-5d0e-be46-b495d48fdc71 |  | textbox | Neutral Torqued
text | dd1f05d9-992d-5637-99cb-84712039378b |  | textbox | Earth Torqued
text | 9a993d6b-cb66-5164-a0fc-f83534545ffd |  | textbox | Bolts Crossed With Black Texta
text | d7110cdc-5f5f-50af-9296-1382c4cf9421 |  | textbox | Name
label | d1c0ccb0-7f0a-56c3-bc8e-b666980f61f9 |  | note | Signature added below
checkpoint-group |  |  | section | Test No.6
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | 8c68ba77-80c6-53f7-8fa7-15abfd38c127 |  | textbox | Bolt Size
text | bfe178aa-6d1b-54cd-aeed-9a26b21a0fc3 |  | textbox | Switch/cable Identification
text | 5fafdada-0187-5565-b8c8-398ee5c0546b |  | textbox | Line/Load
text | 202f6b18-2a45-59b3-a46a-34c038b97eef |  | textbox | Red Phase Torqued
text | 283684a3-df27-507e-b711-69a66b07dc06 |  | textbox | White Phase Torqued
text | 880e3382-567e-5468-9076-3b48e5d6d6b1 |  | textbox | Blue Phase Torqued
text | f67138a9-6b7f-5e72-852c-14923a577fe7 |  | textbox | Neutral Torqued
text | 35b5f8c2-72a5-59ca-8bae-88d230777830 |  | textbox | Earth Torqued
text | 9bbb61cd-b1ec-5b2c-b9df-9fcb36466f96 |  | textbox | Bolts Crossed With Black Texta
text | e1c5d2d7-c278-5399-9c19-271cdb5b54a0 |  | textbox | Name
label | 76313174-7fb6-5639-acf2-9b29d694efc5 |  | note | Signature added below
checkpoint-group |  |  | section | Test No.7
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | 8d359e53-14a4-56dd-bf2d-7d2472f7ddc2 |  | textbox | Bolt Size
text | 492224cd-1aac-5612-bafd-891683c061d0 |  | textbox | Switch/cable Identification
text | c4b0c5fe-4be1-5814-881b-911663a930d7 |  | textbox | Line/Load
text | cd7ef64b-b38f-5536-a9e0-6502f0651627 |  | textbox | Red Phase Torqued
text | eba70953-eafe-5c7e-ace5-115a3008b591 |  | textbox | White Phase Torqued
text | 42492f1f-bd0a-5d5d-842f-e51bf6a0b2b7 |  | textbox | Blue Phase Torqued
text | f40c819c-2843-52fb-a405-42e0880196db |  | textbox | Neutral Torqued
text | ca26a59f-8af7-5547-bf35-e64a283b2da5 |  | textbox | Earth Torqued
text | 4287330c-5795-53d8-9d98-3541793ea6fc |  | textbox | Bolts Crossed With Black Texta
text | 679ed833-0e7d-51dd-a244-bb12723c6551 |  | textbox | Name
label | a83610cf-220a-5fb7-b705-e2a5a5f5ef95 |  | note | Signature added below
checkpoint-group |  |  | section | Test No.8
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | 1eb35cf0-7c53-5d76-8d2d-7a415e471565 |  | textbox | Bolt Size
text | f0dd1262-d29e-5a35-8a43-6ce10178a678 |  | textbox | Switch/cable Identification
text | 8a82dc3d-91ee-58f2-b4c3-a63866a1b9b8 |  | textbox | Line/Load
text | 31672cd7-2b9e-541e-bc1a-fd9cfbcd65c4 |  | textbox | Red Phase Torqued
text | 3834045a-3417-55fc-ab19-e30a2f0a9bf2 |  | textbox | White Phase Torqued
text | 4cabcf50-a08c-5e5e-a9e0-83d51cf33a34 |  | textbox | Blue Phase Torqued
text | c3109945-4b7a-5260-92dc-e1e29f78ca5c |  | textbox | Neutral Torqued
text | 7831d2c6-2df3-5cc0-88dd-cd9bbad979df |  | textbox | Earth Torqued
text | bca5e6b5-acf3-521c-a936-d64d83efabc0 |  | textbox | Bolts Crossed With Black Texta
text | 02845b57-b25a-5523-9686-e89b3c9cd57d |  | textbox | Name
label | 214225f5-f432-5a9e-8f6b-7e1ad6db25ad |  | note | Signature added below
checkpoint-group |  |  | section | Test No.9
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | a3ad691a-e07f-5e82-b5a6-dc1cc935fb8b |  | textbox | Bolt Size
text | fb0cf73b-c8eb-5b20-bc11-ad6371b71fcf |  | textbox | Switch/cable Identification
text | b19d8bfe-ecea-57be-97e2-6b2d3f9b5a0b |  | textbox | Line/Load
text | 593ada1e-3ef6-598b-ae05-719fb18b4725 |  | textbox | Red Phase Torqued
text | c7382b7d-284c-51dc-92af-cd30de7be6db |  | textbox | White Phase Torqued
text | 0e100183-24f4-5dc5-9e66-d19c409ad21c |  | textbox | Blue Phase Torqued
text | 049e4cce-7dd3-5589-bdc3-b3efa2dd384e |  | textbox | Neutral Torqued
text | 061eb61e-8b2b-5737-a348-5ab9f1cd2d32 |  | textbox | Earth Torqued
text | 53e6b077-1d9f-55a2-9a20-b19251a5c54d |  | textbox | Bolts Crossed With Black Texta
text | 4f96245c-3323-5605-984c-8b4738c3ca5e |  | textbox | Name
label | ecb340cc-b2bf-5a1f-8bc0-a8bb1aa10f51 |  | note | Signature added below
checkpoint-group |  |  | section | Test No.10
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | 7291e8b9-5f5c-5e89-b73d-d51ab98e99b7 |  | textbox | Bolt Size
text | 569ae872-28ed-53b6-9773-10dc5d77e732 |  | textbox | Switch/cable Identification
text | 66e79d55-34ee-5442-80be-43aa010fdd49 |  | textbox | Line/Load
text | 96f868b4-8dc1-5bdd-99fb-e49bf3338c34 |  | textbox | Red Phase Torqued
text | 493d2969-1d86-57a5-9a55-6e096064ee0b |  | textbox | White Phase Torqued
text | 6beef9f2-e534-5791-b3f7-e743892bc6df |  | textbox | Blue Phase Torqued
text | 84710ad9-af02-54c9-b8ee-6c9e6a4d0616 |  | textbox | Neutral Torqued
text | 562731ca-7ac6-59a8-a7d6-38a8e0a3ab1d |  | textbox | Earth Torqued
text | d5bdde17-56d3-5769-9249-8f04789bdde1 |  | textbox | Bolts Crossed With Black Texta
text | 31b3d5e5-6cf8-5204-885d-0cf1640ee8de |  | textbox | Name
label | 3f6261f7-4dd6-5486-ac6f-179bfa20ee5a |  | note | Signature added below
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Relevant works completed to specification/drawings - Area left clean & tidy
label | 4fa687f4-cb70-5dd2-86b9-47384a6b54f2 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | f0317572-19ac-5d39-b5f5-aef7b27b9389 |  | note | Any Corrective Actions to be Photographed & Commented below
select | 25bb0870-d425-5c98-8899-5a3a8d692c18 |  | dropdown | Installed by (Appselec) | FIELD OVERRIDE
text | ce5c0850-347c-5aaa-b5a8-e6eb53afd79c |  | textbox | Other (Specify here)
select | 3384154c-7702-5b7f-becc-81ba2c70613e |  | dropdown | Checked by (Appselec) | FIELD OVERRIDE
text | eee42063-4e49-57a3-8015-f17c16d01ed5 |  | textbox | Other (Specify here)
text | dc90468b-7260-57a9-9b68-3914dc1e414c |  | textbox | Witnessed by (Builder/QAM)
label | 15515473-bce5-566a-817a-ac965e33b36f |  | note | Signature Sign-Offs - Attach signature(s) below