## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Enabling Works - Footpath, Kerb and channel | itp |  |  |  | Yes | Richardson Road, Mount Roskill - ITP - Enabling Works - Footpath, Kerb and channel
section | Site Set Out
checkpoint | 1 - Site Set out
label | VERIFICATION ACTIVITY: Surveyor
label | METHODS OR REFERENCE: Surveyor
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: Onsite records/photos
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | Mandatory HOLD POINT
section | Materials
checkpoint | 1 - Kerb & Channel
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Kerb & Channel to be precast hand-laid. Kerbing laid on 300mm min Gap 65 subbase in roads and 100mm GAP 40 in footpaths. (CBR>5).Concrete 20MPa @28 Days
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 2 - Channel Level
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet
label | ONSITE RESPONSIBILITY: Site Engineer
section | Construction
checkpoint | 3 - Concrete Footpaths
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - FP0003
label | FREQUENCY: 10m Intervals
label | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3)
label | ○ Basecourse - 100mm min. thickness
label | ○ Clegg CIV > 12
label | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
label | HOLD POINT: Inprocess Inspection, HOLD POINT, Prepour inspection
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | HOLD POINT
checkpoint | 4 - Concrete Hardstand
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - FP0001
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Subgrade -(CBR > 3)
label | ○ Basecourse - 100mm min. thickness GAP40
label | ○ Clegg CIV > 15
label | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with exposed finish
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet, Concrete delivery, Dockets kept as record
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 5 - Grass Berms
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
label | FREQUENCY: 10m Intervals
label | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 6 - Tactiles
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impared pedestrians. AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY.
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | Asbuilts
checkpoint | 7 - As built information
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | ITP APPROVAL
checkpoint | ITP Approval
note | Prepared by: Cimyona Vinbi
note | Approving Delegate: Daniel Tat
checklist | ITP - Raised Pedestrian Crossing | itp |  |  |  | Yes | Richardson Road, Mount Roskill - ITP - Raised Pedestrian Crossing
section | Details
checkpoint | 1 - Permits
label | H
label | Detail - Obtain Permits
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | Records - Permit attached or permit number noted
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Pre-construction sign offs
label | H
label | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Signed Subcontractor and Supplier Agreements
label | Records - Subcontract and Supplier Agreements
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1 -
label | H
label | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - TMP is approved by CAR manager for each site and works are only completed within the approved dates..
label | Records - TMP on MyWorksites/On Site
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Design
label | H
label | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - IFC drawings have been received by Contractor
label | Records - Check Drawing Register
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Installation of Erosion and Sediment Controls
label | H
label | Detail - Ensure that Erosion & Sediment Control in place
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
label | Records - Environmental Controls Audit
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Installation of Erosion and Sediment Controls
label | H
label | Detail - Ensure that Erosion & Sediment Control in place
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
label | Records - Environmental Controls Audit
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Survey Setout
label | H
label | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey + Smart Level
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Site Photos post surveying
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Locate Existing Services by Hand Digging
label | H
label | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
label | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
label | Records - Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Material Compliance
label | H
label | Detail - LESA dowels to be used at all construction joints
label | Frequency - Prior to pouring concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | Records - Delivery Dockets / Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.1 -
label | H
label | Detail - 0.25mm polythene layer placed across all surface area at bottom of raised table
label | Frequency - Prior to pouring concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Document Review
label | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | Records - Delivery Dockets / Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.2 -
label | H
label | Detail - 50mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
label | Frequency - Prior to pouring concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - CIV >15
label | Records - Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.3 - (1)
label | H
label | Detail - All concrete delivered to site shall have 40MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder and 13mm aggregate chip size
label | Frequency - Prior to pouring concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Concrete Delivery Dockets
label | Conformance Criteria - Delivery Docket added to QA folder
label | Records - Concrete Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.3 - (2)
label | H
label | Detail - Two layers of 663 steel mesh to be placed in the speed table with 50mm plastic chairs seperating them.
label | Frequency - Prior to pouring concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Delivery Docket added to QA folder
label | Records - Site photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Temporary Works (Formwork)
label | W
label | Detail - Formwork to be set to correct line and level
label | Frequency - Prior to pouring concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Concrete Inspection Record
label | Records - Concrete Formwork Checklist
checkpoint | 8.1 -
label | H
label | Detail - Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry and exit ramps
label | Frequency - Prior to pouring concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Conformance Criteria - Designer to inspect formation level
label | Records - Site photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.2 -
label | H
label | Detail - Raised Table ramps to have 200mm depth at entry point and tie into 300mm depth to meet raised table
label | Frequency - Prior to pouring concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Conformance Criteria - Designer to inspect formation level
label | Records - Site photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.3 -
label | H
label | Detail - Raised Table ramps to be 1m across for entry and 1m for departure ramp.Toe to be 1m across for both entry and departure.
label | Frequency - Prior to pouring concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Conformance Criteria - Designer to inspect formation level
label | Records - Site photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.4 -
label | H
label | Detail - Raised Table ramps to be 1:15 gradient for ramps, with 2 layers of 663 mesh.
label | Frequency - Prior to pouring concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Conformance Criteria - Designer to inspect gradient level
label | Records - Site photos / Concrete Formwork Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.5 -
label | H
label | Detail - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
label | Frequency - Prior to concrete pour
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Concrete Inspection Record
label | Records - Concrete Formwork Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Reinforcing
label | H
label | Detail - All construction joints are to contain 2 rows of LESA dowels or similar approved dowels . Speed basket system 50mm w/ Black 300*50*6mm plates @400 centres placed across the construction joint
label | Frequency - Prior to pouring concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Conformance Criteria - Concrete Inspection Record
label | Records - Site photos/Concrete Formwork Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Concreting
label | H
label | Detail - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
label | Frequency - Prior to concrete pour
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Engineer will be notified via email/SMS at least 24 hours before required for inspection
label | Records - Email / SMS
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10.1 -
label | W
label | Detail - Vibrator to be used throughout concrete pour
label | Frequency - When pouring concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Concrete Inspection Record
label | Records - Concrete Formwork Checklist
checkpoint | 10.2 -
label | H
label | Detail - Concrete surfaces on ramps shall be U5 broomed finish and speed table top to be exposed.
label | Frequency - At completion of pour
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Concrete Inspection Record
label | Records - Concrete Formwork Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Curing
label | M
label | Detail - Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
label | Frequency - Post Pour
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Monitoring the time allowed for curing
label | Conformance Criteria - 48 hours minimum have passed
label | Records - Concrete Formwork Checklist
checkpoint | 12 - Remove formwork
label | W
label | Detail - Remove formwork after 48 hours
label | Frequency - Post Curing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Concrete Inspection Record
label | Records - Concrete Formwork Checklist
checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
label | H
label | Detail - Two rows of Lesa diamond placed mid depth @400 C/C along construction joint as per 2789-C3500
label | Frequency - Prior to pouring concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
label | Records - Site photos,delivery dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.1 -
label | H
label | Detail - 150mm thick 40Mpa Concrete with two layers of 663 mesh
label | Frequency - Prior to pouring concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
label | Records - Site photos,delivery dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.2 -
label | W
label | Detail - Tack Coat between AC and Concrete slab
label | Frequency - Post Curing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | Records - Site photos
checkpoint | 13.3 -
label | W
label | Detail - 50mm thick DG10/Mix 7
label | Frequency - Post Curing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | Records - Site photos,delivery dockets
checkpoint | 14 - Lot Number QA File
label | W
label | Detail - Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - All QA files compiled and sumbitted to client
label | Records - QA records
checkpoint | 14.1 -
label | W
label | Detail - Delivery Dockets to be included in QA file
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Delivery Dockets to be included in QA file
label | Records - QA records
checkpoint | 15 - As-builts
label | H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - Asbuilt Drawing
holdpoint | AUTHORITY HOLDPOINT
checklist | ITP - Stormwater Drainage | itp |  |  |  | Yes | Richardson Road, Mount Roskill - ITP - Stormwater Drainage
section | Details
checkpoint | 1 - Permits & Services (1)
label | H
label | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
label | Frequency - Prior to any construction commencing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority.
label | Records - Permit attached or permit number noted.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1 - Permits & Services (2)
label | H
label | Detail - Locate and mark out all existing services
label | Frequency - Prior to any construction commencing
label | Conformance Criteria - B4u dig procedure - follow utility protocols
label | Records - B4u dig plans & GPR report attached
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Pre-Construction Sign Offs
label | H
label | Detail - Sub-Contract and Supplier Agreements
label | Frequency - Prior to commencement.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
label | Records - Subcontract and Supplier Agreements
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Design
label | H
label | Detail - Design is approved and Drawings are of the latest revision.
label | Frequency - Prior to commencement.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | Records - Drawing Register.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Survey Setout
label | H
label | Detail - Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
label | Frequency - Prior to commencement.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - As per Stellar Engineering Drawings: 2789-C3060 or setout files
label | Records - Survey Receipt.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Pipe and Manhole Material Compliance
label | H
label | Detail - Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
label | Frequency - Prior to commencement.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review, Visual Inspection
label | Conformance Criteria - Pipe shall be
label | ○ Check for freshyly formed pipes and return if required
label | 1). DN225 Class 4 RCRRJ pipes AS/NZS 4058
label | 2). All Concrete RCRRJ pipes to be fitted with Rubber rings
label | 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058
label | ○ Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
label | Records - Manufacturers Data Sheets, Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
label | H
label | Detail - Ensure all services conflicting with the line of trench have been exposed by hand digging.
label | Frequency - Prior to commencement.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing / Survey
label | Conformance Criteria - All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
label | Records - As-built Drawings. Doc. Review
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Trenching & Excavation (1)
label | H
label | Detail - Excavation methodology
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Prestart review
label | Conformance Criteria - The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
label | Records - Prestart RCP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Trenching & Excavation (2)
label | M
label | Detail - Trench Profile - Width
label | Frequency - Daily / as trenching takes place. Different depth methodology
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Excavation methdology
label | Conformance Criteria - Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
label | Records - Construction Photos
checkpoint | 7 - Trenching & Excavation (3)
label | W
label | Detail - Trench Profile - Depth
label | Frequency - Daily / as trenching takes place.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Measurement
label | Conformance Criteria - Trench depth varies according to longsection and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
label | Records - FH Drainage Line Record / Construction Photos
checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
label | W
label | Detail - Placing and compaction of Bedding Material.
label | Frequency - Inspected continuously during placing and compaction of Bedding Material.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
label | Records - FH Drainage Line Record / Construction Photos
checkpoint | 9 - Pipe Position Tolerance
label | M
label | Frequency - At any point of pipe
label | Conformance Criteria - Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
label | Records - FH Drainage Line Record, Survey Data.
checkpoint | 10 - Trench Backfill - Placing & Compacting
label | M
label | Detail - Placing and compacting of Trench Backfill Material
label | Frequency - Throughout Trench Backfilling operation.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
label | Records - Construction Photos
checkpoint | 11 - As-Built Drawings
label | W
label | Detail - Red pen marked-up As-Builts of every 'Issued for Construction' AT drawings
label | Frequency - Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings / Visual Inspection
label | Conformance Criteria - As Built and GIS Data
label | Records - Redline As-Built Drawings, scanned as .pdf files.
checklist | ITP - Traffic Islands | itp |  |  |  | Yes | Richardson Road, Mount Roskill - ITP - Traffic Islands
section | Materials
checkpoint | 1 - Mountable Kerb
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet, photos.
label | ONSITE RESPONSIBILITY: Site Engineer
section | Construction
checkpoint | 2 - Survey Setout
label | VERIFICATION ACTIVITY: Survey
label | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
label | FREQUENCY: Prior to commencement.
label | ACCEPTANCE CRITERIA: Survey
label | HOLD POINT: As per Construction Drawings
label | RECORDS: Survey Receipt.
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Concrete Island (1)
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: Kerbs to be haunced with 20MPa Concrete
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Concrete Island (2)
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0003
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: Basecourse to be 150mm min thickness of GAP65
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 4 - Concrete Infil
label | VERIFICATION ACTIVITY: Concrete Infil
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish unreinforced Concrete with 4 kg/m3 Red oxide. Cross Fall of 2% or max rise in centre of 180mm.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | ONSITE RESPONSIBILITY: Site Engineer
section | Asbuilts
checkpoint | 5 - As built information
label | VERIFICATION ACTIVITY: Drawings
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
checkpoint | 6 - RAMM DATA
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: RAMM SHEET
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | ITP APPROVAL
checkpoint | ITP Approval
note | Prepared by: Yeswanth Vemula
note | Approving Delegate: Sumesh Sharma