## Master List Templates
Id | Type | Name | Values | Prompting Name
f2fde9e7-9c31-4b6a-b1b5-5c987f27409a | checklist | Contract HoldPoint Checklist |  | Contract HoldPoint Checklist
96a78813-95b0-48fa-9a93-357ec9a1b8cb | checkpoint | Holdpoint Release
e37a2a86-d6e9-5a29-aadc-aad1b77ad6c5 | textbox | Enter Name
1a23eb1a-cd8f-5c38-b50b-5bc9b39bbe1b | textbox | Enter Description
60a1eb35-e850-40c9-a4b9-af7b0196da59 | signoff | Contract Holdpoint Release

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Postfix
3015466a-a249-477d-b7a0-7a0dfbbeb031 | checklist | FHC-ITP-001 - Clearing & Grubbing Rev2 | itp | FHC-ITP-001 - Clearing & Grubbing
767fe191-cb0c-4937-8534-d3769a75dd53 | section | Preliminary Works
c0fb8624-5d50-4277-9864-ebe05b703085 | checkpoint | 1.1 Check for correct documentation
8fb811c4-2869-53bf-a070-c278e2172397 | note | FREQUENCY: Prior to commencing any activity
a94384a8-9ac1-5f8a-8769-e7ab53a67be4 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
47c6fcfb-3b5d-53bd-99f1-7108ed4a2c63 | note | — using the correct and complete set of drawings
2a9cb5c5-6454-5ce1-bbb7-8b3649cf5875 | note | — all drawings are the latest revision
871e7ded-b4c5-5241-ba9b-d932b147bffc | note | REFERENCE DOCUMENTS: Drawings and drawing registers
64ec494f-d2e5-50f8-97a9-9534cca2728f | note | INSPECTION/TEST METHOD: Visual inspection
8f7fe470-11c2-52b5-a990-a67cca3e119b | note | RECORD OF CONFORMITY: This ITP signed
b354e50d-6f46-5e4a-a803-77974f53e9e8 | note | HP*
67641680-4b93-558d-8b59-17ec488e8be3 | note | RESPONSIBILITY: Site Engineer / Site Foreman
32d3da79-f3ff-5d26-a372-484c99a26f28 | textbox | Date Completed:
e001c818-196a-4baa-a551-cf13b9eadb81 | checkpoint | 1.2 Implementation of all measures and controls
014361cf-c801-5834-9471-ee6d590b656d | note | FREQUENCY: Prior to commencing any activity
831a11f4-18cb-580f-8ce7-bb08d42f61d4 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
a27482a0-d2de-5225-86c3-19a1f7eebaf9 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
6082b4c6-3e4a-59d6-ac07-c663c347d1d3 | note | INSPECTION/TEST METHOD: Visual Inspection
d8e5b744-34dc-5588-b1d3-b5956d280b83 | note | RECORD OF CONFORMITY: This ITP signed
f7f56f7c-0a43-5c24-b671-049ffcb52d59 | note | HP*
ccd87970-0336-5f95-ba21-c3f18a04330a | note | RESPONSIBILITY: Site Engineer / Site Foreman
873d9e6b-e71a-529b-b66d-c84e5c774b7b | textbox | Date Completed:
11c60fab-8c8b-402d-ad75-fbd5a7f22113 | checkpoint | 1.3 Flora & Fauna
58fa6e69-eee1-5169-8361-d102a106e635 | note | FREQUENCY: Prior to commencing clearing
ffe8064f-1792-5961-9411-0baf7a4525be | note | ACCEPTANCE CRITERIA: A qualified ecologist and/or botanist has examined trees to be removed and/or any fallen logs affected by works and provided written clearance for removal; has provided advice on alternative fauna habitat sites if applicable and be present on the site during any relocation works if required.
0a6dc609-d8fb-53fe-a6e9-39080dfe1965 | note | REFERENCE DOCUMENTS: EMP, ECP
dac48501-59ee-5a74-a29a-bc97d752a7f9 | note | INSPECTION/TEST METHOD: Visual Inspection
183aeef4-3d8d-51c9-a9f6-f2743fe62c59 | note | RECORD OF CONFORMITY: This ITP Signed off
a7661afd-c081-5050-a46e-75ce27789b90 | note | IP
c36607b4-1b0b-5210-9dd4-c0ea541310f6 | note | RESPONSIBILITY: Site Engineer / Site Foreman
ba7e7712-5660-575b-bb2c-028d3d014b0b | textbox | Date Completed:
1df61366-9f53-4e53-98bd-e4d947932db2 | checkpoint | 1.4 Permit to distrurb flora & fauna
5831e730-3c09-5ade-8120-5391a10e584d | note | FREQUENCY: Prior to commencing clearing
2eed017d-18b4-59d8-9f1d-6c1dcaf08d1e | note | ACCEPTANCE CRITERIA: MRPA has already obtained permits and/or approvals to disturb flora/fauna sites. Ensure that a copy of these permits are obtained prior to the commencement of tree removal works.
bfdc4534-b3bf-58b5-8d5c-f7d05e787c8f | note | REFERENCE DOCUMENTS: EMP, ECP
3a6862d4-54a0-5fc8-98b0-28ab5bf2b07c | note | INSPECTION/TEST METHOD: Visual Inspection
8fbf0184-2ccd-5431-a0bb-e969ec5482d1 | note | RECORD OF CONFORMITY: This ITP Signed off
8186eaa0-a266-59dc-b30f-d0e4c54a5c2b | note | IP
54852c0d-9624-5787-a68b-9f60623ca43b | note | RESPONSIBILITY: Project Engineer
e6c80d92-b01f-5097-aef4-557b2ce58868 | textbox | Date Completed:
24ebf4e5-2aeb-4d2c-97b4-6e6fd8317bb3 | section | Clear & Grub
e34444b2-1989-41f0-b525-479f534af21e | checkpoint | 2.1 Define work area
0d1517f2-5177-515a-a40d-e1e905fea017 | note | FREQUENCY: Prior to commencing clearing
143ea048-e0eb-5135-add7-fce21c2ce852 | note | ACCEPTANCE CRITERIA: The work area has been determined, and the extent of clear and grub has been reviewed by Fulton Hogan and the Superintendent. Any trees to be removed have been clearly marked and confirmed on site.
4ea96789-8da5-54e5-b5c0-d6e2a0070df2 | note | REFERENCE DOCUMENTS: 201.03
68e678c1-4484-59bb-a859-6d8c8f91b277 | note | INSPECTION/TEST METHOD: Inspect
aea0f4d0-d5cd-58e0-8b2d-b4d0a1d03bd0 | note | RECORD OF CONFORMITY: This ITP Signed off
4e1d93c7-aa6e-546a-8a3d-2b5feca5d8c0 | note | WP
f1eaf3df-d244-52c9-a12c-bb6bede27b68 | note | RESPONSIBILITY: Project Engineer/ Superintendent
279de12c-4270-5bc3-a869-00e93cfc318a | textbox | Date Completed:
5324274e-45fc-4c0d-b2a2-da36327e2c5c | checkpoint | 2.2 Joint Inspection to Mark vegetation or habitat to be removed
53ac5838-7141-5aca-baeb-5dae391875fe | note | FREQUENCY: Prior to commencing clearing
2a019adb-9675-5f07-9fe3-148d86fb32ae | note | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat, the Contractor shall arrange an on-site inspection with the Superintendent to confirm and clearly identify and mark trees to be removed, consistent with Appendix O Tree Assessment Report.
73516507-83d3-5001-97ce-97fe08aae21f | note | REFERENCE DOCUMENTS: Drawings 201.10
b86b56f8-bcb9-51e4-9e5c-b9eb9295a861 | note | INSPECTION/TEST METHOD: Visual Inspection
91b3d9d2-dba7-5cc3-88aa-de1cedd4c8ff | note | RECORD OF CONFORMITY: This ITP Signed off
948f904b-d700-5963-9ffe-cacc60608ccf | note | HP
d491c0e3-caa5-5e0e-b78a-896008c2361b | note | RESPONSIBILITY: Project Engineer/ Superintendent
95dc9b4c-579c-5f41-85db-a1457e3f8395 | textbox | Date Completed:
dc05ef2c-da88-45ce-af94-c53a55da290d | signoff | AUTHORITY HOLDPOINT
0ecab1c6-6aed-42ed-bc2c-9263243f87fe | checkpoint | 2.3 Identify No-go Zones
b0cdf706-4767-525e-887d-c967b62932a1 | note | FREQUENCY: Prior to commencing clearing
d6bcca6b-e7a1-53d4-918e-4a7518ab61ed | note | ACCEPTANCE CRITERIA: Existing vegetation and native fauna habitat identified in the Contract to be retained, shall be identified as ‘No-Go Zones’ and protected by temporary fencing, consisting of, as a minimum, star pickets,wire support and parawebbing. Signage shall be erected outside the limit of the of the vegetation or the habitat site, at intervals no less than 20 metres apart or as per the SSEMP Prior to any work onsite the contractor shall fence and sign all no go zone sites as per the EMP. Any works required inside TPZ shall be completed under the supervision of an Arborist
444bb5c8-796a-55da-8185-56f4c17ffff8 | note | REFERENCE DOCUMENTS: Drawings 201.10
369bd75f-0140-5dce-b434-dcfeb3ca6693 | note | INSPECTION/TEST METHOD: Visual Inspection
97c4080b-ff74-5203-b6c1-1967edd74e2f | note | RECORD OF CONFORMITY: This ITP Signed off
14a0d407-bbc4-5507-91b2-35fd954bce74 | note | HP
0a1b343c-2e87-5a2c-8819-f765109c7073 | note | RESPONSIBILITY: Project Engineer/ Superintendent
8bcdca34-790a-56f7-b497-80ee2f4e9396 | textbox | Date Completed:
120e909e-27ea-4265-be31-815820001b70 | signoff | AUTHORITY HOLDPOINT
62805654-adc1-4964-b7a3-82149e796b5f | checkpoint | 2.4 Clear felling distances of trees are adequate.
8932bbab-a131-5675-ad61-a882579ee7ac | note | FREQUENCY: Prior to commencing clearing
42fbf73c-5849-5857-a01d-c94e84d38ce5 | note | ACCEPTANCE CRITERIA: Ensure the clear distances are adequate and signage is inplace as planned. Trees shall be brought down in such manner as to avoid danger to personnel and traffic or damage to other trees, shrubs, structures or property outside the area being cleared or designated to be retained within the area being cleared.
cda13088-938b-579d-beb5-9fd8eacd7a1e | note | REFERENCE DOCUMENTS: 201.04
eaf2c95a-eacd-59ff-bb49-74d055b1f80f | note | INSPECTION/TEST METHOD: Visual Inspection
4e47627b-15a2-5397-881a-fc2f8aff56d9 | note | RECORD OF CONFORMITY: This ITP Signed off
d26da049-9a50-5c53-8441-a953ce6702ad | note | IP
677a6fec-062c-5524-b53d-a65c8e830ba0 | note | RESPONSIBILITY: Site Engineer / Site Foreman
93980cb8-b707-59d0-b2f9-320fc4e26204 | textbox | Date Completed:
67300e7d-c427-4210-9bc7-42d05fa3b5be | checkpoint | 2.5 Clear and grub trees and vegetation
3a3c04ba-116c-5ed2-841b-286e588db0e3 | note | FREQUENCY: After clearing
d89c3a5f-affa-5542-8f22-116cb2b16b82 | note | ACCEPTANCE CRITERIA: Vegetation in areas of site excavation have been cleared and grubbed to at least 0.3m below subgrade, all other vegetation and obstructions cleared to natural surface level
6682f023-56ca-5091-9543-1ab41898367f | note | ○ Tree branches extending over the carriageway shall be trimmed to provide minimum clearance of 6m above the carriageway surface.
feb64d51-c414-5d94-b728-1de950346595 | note | REFERENCE DOCUMENTS: 201.04, 201.05, 201.06
bb2f573f-f675-5597-81ce-1de4633aa690 | note | INSPECTION/TEST METHOD: Visual Inspection
07d66494-8181-5c17-b174-affd1a0775dd | note | RECORD OF CONFORMITY: This ITP Signed off
6e7d7c79-01de-5cc9-8bba-55871fbbf285 | note | IP
463cdce7-8da9-5388-877e-f8bb68d4cec4 | note | RESPONSIBILITY: Site Engineer / Site Foreman
85e079c1-ffed-54ad-82ab-4ae0a275e324 | textbox | Date Completed:
8f54f717-a7a2-40a0-bc0a-646641c0e756 | checkpoint | 2.6 Backfill holes
57fd7599-b013-526d-a1fe-ce998cf8de69 | note | FREQUENCY: After clearing
6e3b36a1-c36e-57a9-b006-16113053242b | note | ACCEPTANCE CRITERIA: Any holes produced from grubbing operations have been backfilled with similar material to the sorrounding material and compacted to the same degree to the sorrounding material.
0c907ee5-130d-5a3f-b987-f94b42b07a70 | note | REFERENCE DOCUMENTS: 201.05
5a44533d-ab44-5f61-998b-d34fba106f82 | note | INSPECTION/TEST METHOD: Visual Inspection
fdaaa5a9-3091-5881-bfe4-fc9f19501ebd | note | RECORD OF CONFORMITY: This ITP Signed off
c3acbf05-2296-52d5-947c-c021936db7f2 | note | IP
8ab6be40-13ab-51c0-977b-4f0920912f78 | note | RESPONSIBILITY: Site Engineer / Site Foreman
4b7c2a1d-7c8a-52df-b6ba-71a36c5bcca3 | textbox | Date Completed:
5aa6029b-734d-4a1c-8392-e46f2e3b8119 | checkpoint | 2.7 Dispose of Trees and vegetation
0b3ebca5-6d89-53ca-b550-f6182e7db520 | note | FREQUENCY: After clearing
f7d5cf67-3ddb-5448-b750-302dd460678d | note | ACCEPTANCE CRITERIA: Trees that are to be removed shall be mulched to the extent possible and the mulch retained for use in the Landscaping Works.
19e52f1b-3626-59ad-9311-c647ac626461 | note | ○ Noxious weeds shall not be mulched.
d61313e7-feea-5ed3-a62f-1a34c56daf79 | note | REFERENCE DOCUMENTS: 201.07
20770b60-040f-562d-9201-dc81a87e4f07 | note | INSPECTION/TEST METHOD: Visual Inspection
304f636e-9124-5b9c-8da6-17839f400f7f | note | RECORD OF CONFORMITY: This ITP Signed off
d8d78e0a-6ce3-50b9-809c-c68ebc63e3e6 | note | IP
863ab064-ad59-5bf1-ad96-1325ca734773 | note | RESPONSIBILITY: Site Engineer / Site Foreman
2dde0530-1a40-54b7-bc25-9a8e4d15a8ef | textbox | Date Completed:
a2d7ad59-9749-4193-a497-305f9620bd2e | checkpoint | 2.8 Dispose of concrete, bituminous and other recyclable materials.
538181f8-ba52-53f9-8e5c-26dfc2260595 | note | FREQUENCY: After clearing
718f38e5-59f9-534b-977d-0ef297e08f9c | note | ACCEPTANCE CRITERIA: Salvaged concrete, bituminous materials over 50mm and other recyclable materials have been sent to approved recycling establishments.
eb14fea4-b5e0-5783-92b6-5f7bc3de3614 | note | REFERENCE DOCUMENTS: 201.07
942e40ff-1420-5020-b478-7fd2381268c2 | note | INSPECTION/TEST METHOD: Visual Inspection
ca31afae-e382-56b0-a8cd-30abcc8d0d89 | note | RECORD OF CONFORMITY: This ITP Signed off
e51adf6a-44bb-54a7-b44d-00faaa89b160 | note | IP
31907858-9186-5cb3-9d49-d27e30b59cd6 | note | RESPONSIBILITY: Site Engineer / Site Foreman
079427cd-b05c-5165-a715-815993446e8e | textbox | Date Completed:
559701a4-a560-4afd-b16e-60231e98c970 | checkpoint | Final Inspection
45cbfc5f-9b19-595a-a590-1443574be78d | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
898c49e2-f0e8-572f-9d08-46bb844666aa | textbox | Print Name:
10b2d3f1-318b-54b7-b8d5-4da4e0c3ab93 | textbox | Position:
e505a41d-5ff8-5959-b103-dfa0d410f80e | textbox | Date:
7895616c-53c9-4ef8-af70-bb41b28aed48 | checklist | FHC-ITP-003 - Subgrade Preparation Rev2 | itp | FHC-ITP-003 - Subgrade Preparation
acf54f1b-3386-46b9-8486-6b789d7dd5f1 | section | Preliminary Works
47b2ff6c-2492-4167-9ee7-30607159b3f0 | checkpoint | 1.1 Check for correct documentation
0a64e7ce-7bf3-5a2c-affe-19317e0129dc | note | FREQUENCY: Prior to commencing any activity
8fba5429-450d-53c6-86a3-43ca755aeca6 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
7d837dd9-347a-53b5-a32d-a863598d5e76 | note | — using the correct and complete set of drawings
0e560b7d-d75e-5175-aca1-a4f5f383239b | note | — all drawings are the latest revision
457fc248-a5bd-50a5-a0d0-130a464c30f4 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
57c259dc-30db-5850-a797-897b3049cdb5 | note | INSPECTION/TEST METHOD: Visual inspection
8bbbeaf9-7200-5ca2-a433-a8d3ce40ae67 | note | RECORD OF CONFORMITY: This ITP signed off
4a7b955f-b539-511d-8dcb-afa6190f41e2 | note | HP*
7c679c00-4ab8-5e46-ac00-713865208888 | note | RESPONSIBILITY: Site Engineer / Site Foreman
09060d8d-d19e-5fcb-a849-4880e55c25dd | textbox | Date Completed:
1a51957d-ebe4-4573-b196-ce4e001046c5 | checkpoint | 1.2 Implementation of all measures and controls
0e4bf763-ca6b-5b1f-8c49-6207075d9597 | note | FREQUENCY: Prior to commencing any activity
db72ec46-90ee-5142-a6e0-dc479786abc1 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
c09f3a24-c8c3-54cb-8f43-bbb390ba04ce | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
10150f83-ce77-5f98-9e62-c667ca227445 | note | INSPECTION/TEST METHOD: Visual Inspection
b99402ba-9ffe-560e-bcac-4f39ba9df704 | note | RECORD OF CONFORMITY: This ITP signed off
915f1685-a789-5647-b56a-8baadbffac85 | note | HP*
4f2bd219-614c-5d8f-8069-6ecb7d4d21f1 | note | RESPONSIBILITY: Site Engineer / Site Foreman
3f2a72ee-ba71-56cf-ac4f-51d9b14aa52c | textbox | Date Completed:
6764ab17-87b9-4472-8a03-363f8d2d15de | section | Construction Works
1ae23a54-fb3b-456e-80c4-23811caeaf06 | checkpoint | 2.1 Survey Set-Out
d10888aa-ee3b-5de4-a0b1-c1649d14d3c5 | note | FREQUENCY: Prior to commencement of excavation
9c037a26-08ba-5da4-ae2a-10f8d4e748dc | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
769644d4-e224-53fa-9dfa-e2aca1a4b59d | note | REFERENCE DOCUMENTS: Drawings, Work Procedure
2ca3282d-43b7-5ede-be70-a6ade3cbbdfa | note | INSPECTION/TEST METHOD: Verify
9237f00d-e43b-5a35-b549-2937e5874183 | note | RECORD OF CONFORMITY: This ITP signed
104a2ef7-ead3-57f5-a07b-871643bacb1d | note | IP
8e01b6de-3667-5170-a6d4-0f92920ce2de | note | RESPONSIBILITY: Site Engineer/ Surveyor
8fc4e4c8-d2c1-503c-b45e-1f08bbab73de | textbox | Date Completed:
0fe38bbb-42ce-4d94-91b5-da67511efdd4 | checkpoint | 2.2 Excavation Permit
433a7d96-4ff6-59ae-9caf-617ab905b9eb | note | FREQUENCY: Each lot
dfa787a8-6a11-5335-97f9-2c7d8150adc1 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
f327b894-361d-55e3-8d61-604fd69dcbad | note | ○ Plant and equipment shall be appropriate for the task.
2b576e71-b0ed-5472-8cd5-4b98aa60b583 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
00e70bc0-166d-5fce-835d-164425585fa9 | note | REFERENCE DOCUMENTS: Excavation permit
68cb9627-66aa-58df-9a14-7ef7f507464d | note | INSPECTION/TEST METHOD: Verify
c83ecc3b-f403-5440-b205-94ceba8203b8 | note | RECORD OF CONFORMITY: This ITP Signed Off
266bd3ef-6b1d-5640-9792-375fd40d33f1 | note | HP*
7acbb4a6-ae9c-5e85-8c86-3f3a561e18f9 | note | RESPONSIBILITY: Site Engineer
4fd3021d-9c6a-5b55-bc3e-456820b5b47c | textbox | Date Completed:
04137799-b69d-46a6-b8f5-eac6c58e6d00 | checkpoint | 2.3 Subgrade Material Properties
756e13a7-e215-5e40-ba21-38b74bc11e3b | note | FREQUENCY: Each Lot
822f5be6-44b4-5668-b71c-14cdd331b2e8 | note | ACCEPTANCE CRITERIA: Material at cut floor level to have CBR > 2% as per drawing CRG-0010.
458733f1-c304-5a5b-a979-37b0270f67c2 | note | ○ If parameter met rip and re compact 150mm in line with VicRoads spec. If parameters not met, undertake one of three subgrade improvement options (in cut) as per drawing CRG-0011
5276f776-bd52-5d68-b900-f95a9ee2265e | note | REFERENCE DOCUMENTS: Drawings
112364f3-2f08-5843-9b03-4b4f24086d3c | note | INSPECTION/TEST METHOD: Test Point
98649c7c-c3ec-5a50-a0d7-552db1aeea38 | note | RECORD OF CONFORMITY: Test Reports
2521b89b-f79d-5364-b31e-4eb61c0a6bab | note | TP
aee34aeb-3f88-5823-a765-c8d4820f3b9e | note | RESPONSIBILITY: Site Engineer
8efe4376-ace0-50d8-a2d0-70b67d35afed | textbox | Date Completed:
99638187-9b76-411d-ab5a-355840376282 | checkpoint | 2.4 Inspection of Subgrade Material
23268412-6c3d-5be9-a85d-9f2677e2908a | note | FREQUENCY: Each lot
b6337dd8-cdfd-5e13-94ec-234593f5d611 | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on suitability.
2916d7e8-bdb0-53fe-9b7c-9fd9f6713692 | note | REFERENCE DOCUMENTS: 204.06 (c)
f86e14f3-ecd6-5138-8d0d-7a5008a6ec11 | note | INSPECTION/TEST METHOD: Verify
57bc8cdf-2572-5eb0-befa-f56f80ffe0f6 | note | RECORD OF CONFORMITY: This ITP Signed Off
f2c6b125-c956-50b8-b43d-2e062e62ec71 | note | HP
92c09152-7697-5947-9f70-f7d5597f02b9 | note | RESPONSIBILITY: Site Engineer/ Superintendent
078dda8a-0012-5200-afb1-0b4fda0d3966 | textbox | Date Completed:
1863436a-6fb1-4960-b438-7a3d61a971a4 | signoff | AUTHORITY HOLDPOINT
b5abcb4f-d36d-45b4-832c-7471f13fdb3c | checkpoint | 2.5 Unsuitable Material
4259ecb7-6a06-5574-ab67-9ff19e4eacf4 | note | FREQUENCY: Each Lot
2d5e5db8-ce12-5e6b-9c8f-5511e6d49bc1 | note | ACCEPTANCE CRITERIA: Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review.
56ff4244-cea0-51f5-a9e2-2bee97020fb4 | note | REFERENCE DOCUMENTS: 204.07 (d)
0a38a7ca-75b6-5386-b34e-844b4cfbdafa | note | INSPECTION/TEST METHOD: Visual Inspection
06667174-4a27-5796-8bec-f8a3f4d0ea7b | note | RECORD OF CONFORMITY: This ITP Signed Off
c9565809-4a44-5cee-aab4-f40acde74b91 | note | HP
5878c193-c031-5789-8bec-48cc40671c34 | note | RESPONSIBILITY: Site Engineer/ Superintendent
eccbb237-6e43-5368-ae85-3fd8ddab2afc | textbox | Date Completed:
79b7d4e9-1138-4a07-b16c-66b8ead8e902 | signoff | AUTHORITY HOLDPOINT
a611693d-67e4-418a-b169-21129ddfb56d | checkpoint | 2.6 Groundwater
257ffff8-cda1-556c-95ab-725c5d4c88da | note | FREQUENCY: Each Lot
1ec1c79a-1437-5e5a-84b9-fa7424d8bb02 | note | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
2c295c56-1776-564c-b042-3043665deaf7 | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater
29fc5014-edff-5954-aa02-e2ab78db717c | note | REFERENCE DOCUMENTS: 204.06 (h)
e1183265-3238-5f98-99bc-d36e840948ef | note | INSPECTION/TEST METHOD: Visual inspection
af9ba870-3513-5d59-9ba0-90fcdf16139a | note | RECORD OF CONFORMITY: This ITP signed off
1cfdb51d-419b-53c5-a24f-cd60ed727d40 | note | HP
76502a7b-014f-528f-b7ed-d2abd66ea70a | note | RESPONSIBILITY: Site Engineer/ Superintendent
3b7cf82b-350f-5671-97f2-90d905baed20 | textbox | Date Completed:
c7ab9db9-815b-4653-9ccf-81ab8fd3f0b0 | signoff | AUTHORITY HOLDPOINT
69cf64be-136a-4b8a-828f-f4eb6c5ebd0d | checkpoint | 2.7 Trimming and Level conformity
43de6829-1def-5306-874e-a30a025e3cf8 | note | FREQUENCY: Each Lot
20fef51e-201e-517b-b6ca-6b57910cfc1f | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point. Random level assessments shall not be undertaken in lots not exceeding 4000 m2.
a5047821-e995-55f7-9361-8a3d0d3fa9ae | note | ○ Level tolerances:
a797d5eb-53ed-55da-b13b-895a99d6e0d7 | note | — Range x = +15, -30mm
d01bed67-50c0-5c0a-a76d-6fcca096f8ce | note | — Max S = 12 mm
b0581ba3-c491-588f-bdb3-f6a9d31a28e0 | note | — 40 measurements per lot (Scale B)
956659e7-8765-5338-8e9a-5bad27a65eb2 | note | REFERENCE DOCUMENTS: 204.03(f)(g)(h)
411894d7-e6c3-5c86-9d90-22a2ea131790 | note | INSPECTION/TEST METHOD: Survey Report
656f911c-c276-598d-b62f-e1b426da702c | note | RECORD OF CONFORMITY: Survey Record
0c77d52d-666a-5370-b10a-8bc18579581d | note | SCP
4b1067c2-a5bc-5fc5-bbab-83622f72af9e | note | RESPONSIBILITY: Site Engineer/ Surveyor
bf746ead-a860-5f6b-977b-34c5973934d5 | textbox | Date Completed:
51ba9fcf-ef06-4b0f-b3ac-52c622dfb028 | section | Testing
d1f67cea-067f-44de-8a4f-8d9dd5a559d9 | checkpoint | 3.1 Proof Rolling
3f071602-1380-5253-b3e6-0f3e4d85fb1c | note | FREQUENCY: Each Lot
d86cf3b6-b0f3-5ea4-9196-0aeb1b67b889 | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
977cdff1-c375-5623-996a-7ad614c4a93c | note | REFERENCE DOCUMENTS: Section 173
31efc9be-5f25-586f-af16-a3aa38f33db3 | note | INSPECTION/TEST METHOD: Visual Inspection
32bd3c11-c034-5534-9275-5375f22308dd | note | RECORD OF CONFORMITY: This ITP signed off
5b917658-e616-5bfd-a162-dbec3f2d0699 | note | HP*
6ff1dd25-563c-57cd-b77e-f508bc3d09fe | note | WP
17bce3f8-16b1-5523-83d6-7911c9e9b816 | note | RESPONSIBILITY: Site Engineer/ Superintendent
d5e65e78-a65d-5157-887c-4a5512345e46 | textbox | Date Completed:
dc0d9179-241b-47bc-bfa2-737b0381a54f | checkpoint | 3.2 Minimum Testing
f7a89411-0244-5859-9784-5a752cf5cc85 | note | FREQUENCY: Each Lot
4d2d96c7-4ac3-5595-a795-5a55ad69fa9a | note | ACCEPTANCE CRITERIA: Testing of every lot shall continue until three consecutive lots of like material and work have achieved the specified requirements in the first test. After satisfying this requirement and establishing a compaction procedure to the satisfaction of the Superintendent, the Contractor may seek the Superintendent’s agreement to reduce the frequency of testing of subsequent lots to the minimum requirements specified in Table 204.142
4f030859-7c4f-5cc3-b1ab-8f2c894e5dc0 | note | REFERENCE DOCUMENTS: 204.14 c
296765c1-1f6f-5a56-a4d0-6cd2188d2e25 | note | INSPECTION/TEST METHOD: Test Point
0cfa7988-fd45-5638-be87-3dd7e37f6001 | note | RECORD OF CONFORMITY: This ITP signed off
fc191edc-88e1-5816-87f8-ebe7a377c67d | note | HP*
d67809bb-fbe6-57b0-8404-87a1c6643f40 | note | WP
6d0ccb90-bc20-54eb-b63b-bfedd31c02ea | note | RESPONSIBILITY: Site Engineer/ Superintendent
891fcb11-9a50-5afd-ba82-14a80d90e02b | textbox | Date Completed:
6047bc21-f981-4687-8a4e-7b4f30b3d809 | checkpoint | 3.3 Compaction Testing
be9c0cdf-60b6-5529-a3c4-ed363d33bdd3 | note | FREQUENCY: Each Lot
b3a62ffe-f10f-53d4-86c7-e54b5e564598 | note | ACCEPTANCE CRITERIA: Ripped and re-compacted material below Cut Floor Level = minimum compaction 98% SDD.
1ce5d876-4316-5f5c-865e-b94aad6e1c85 | note | ○ Type B Material placed within 400 mm of top of Type B Material = minimum compaction 95% SDD.
1b48b998-2cf5-544b-9c63-08afdbffa76f | note | ○ Type B material 400mm below the top of Type B material and Top 150mm of where fill is to be constructed = minimum compaction 95% SDD.
33c145a1-a74b-5896-b246-d02b8e9cd512 | note | REFERENCE DOCUMENTS: Table 204.131
9e065506-64e2-58fe-ad26-c04cb240676b | note | INSPECTION/TEST METHOD: Test Point
21c4ee4f-a118-5f43-86ee-2ca309aca948 | note | RECORD OF CONFORMITY: Test Records, Lot Register
08afe728-b028-5443-893c-4fce6d0d5b7b | note | TP
1c28e054-6dbb-5904-a808-8bf816b76e4d | note | RESPONSIBILITY: Site Engineer
47425b59-41ee-5dbb-bb7b-8b74877ffabe | textbox | Date Completed:
58be8ac2-a90e-40dc-ac43-10a1c1e5c4d9 | checkpoint | 3.4 Compaction Testing (Small Lots)
c56b913f-7870-5e73-9432-f3fa2cfa9861 | note | FREQUENCY: Each Lot
2efde009-27b4-5b55-9792-ea8efca2f92c | note | ACCEPTANCE CRITERIA: Any lot which has a surface area less than 500 m2 may be treated as a small area. Acceptance of the lot shall be based on the mean values of 3 individual tests. Minimum Compaction shall be 100% SDD.
ee206fef-3497-56f4-931c-fc246dc8c843 | note | REFERENCE DOCUMENTS: 173.04 d
c0c77d53-f983-59cd-b7a3-8aef6f9c61b6 | note | INSPECTION/TEST METHOD: Test Point
5d5f6cff-7e49-53ae-8e59-e33babb4d14f | note | RECORD OF CONFORMITY: Test Records, Lot Register
212c2e1c-cf8e-5ffc-b135-84e957616ff4 | note | TP
6f979afa-dea4-569a-8957-aeb7f7a0d6cd | note | RESPONSIBILITY: Site Engineer
a3d8d9f3-ec46-5b63-886f-67262fabd770 | textbox | Date Completed:
bc93d893-ffa5-4f04-87af-49158dc9f28a | checkpoint | Final Inspection
c5406b40-2677-5a6c-9165-243646f2a82d | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
735e8bf2-396d-54de-a4b4-4ea05869f232 | textbox | Print Name:
600c08e5-2cfe-567c-b673-8fa4d38e3097 | textbox | Position:
57d656f5-eb42-57b2-869a-850e7698afed | textbox | Date:
64bda82b-d166-4e8b-a072-220db5f68045 | checklist | FHC-ITP-004 - Type A Fill Placement Rev5 | itp | FHC-ITP-004 - Type A Fill Placement
5a32276b-4969-48ca-aa7d-edcbe8d1053a | section | Preliminary Works
ceaaea4b-147e-4968-b3db-ed7e2f59e749 | checkpoint | 1.1 The current revision drawings/documents are being used including subcontractors copy.
8b8454c1-a5df-506a-8777-ffa8a2c91a1d | note | FREQUENCY: Prior to commencing
c196c06c-36ce-57b2-83c6-7385db446d2d | note | ACCEPTANCE CRITERIA: Current revision drawing/documents are being used including the subcontractors copy.
233ba073-fae3-59bf-a9ca-1af104c0df1d | note | REFERENCE DOCUMENTS: Drawings and drawing registers
c5771b73-f614-5188-a320-1c38d7a46aca | note | INSPECTION/TEST METHOD: Visual Inspection
45743be1-b437-5aed-ab7d-2453602f9cf8 | note | RECORD OF CONFORMITY: This ITP Signed Off
3c5ee905-e827-5976-bc71-0fc24a964999 | note | HP*
c0730b77-8288-5c2e-a7c7-aed1913c8e93 | note | RESPONSIBILITY: Site Engineer / Site Foreman
3f08f93e-f950-567a-9ad5-72b0a20c4b97 | textbox | Date Completed:
e7b04800-4b96-46d3-9136-f0c41bedf42f | checkpoint | 1.2 Implementation of all measures and controls
6a824e21-1a31-5130-9569-3fd23d965705 | note | FREQUENCY: Prior to Placement/ Each Lot
d2d84491-1bd5-5027-baa3-889061dc5d3e | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
3acd3901-3c9b-5735-b540-59c3bacad069 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
770aff9f-189a-5d17-8fe7-d98ac9821e7e | note | INSPECTION/TEST METHOD: Visual Inspection
caf14a3f-6248-5cd8-b8b2-be11a1f8444b | note | RECORD OF CONFORMITY: This ITP Signed Off
017d9dbc-aac4-57d0-ae22-7e4f4938addf | note | HP*
3e799fc5-86a8-51b3-8775-f69a79cf30e7 | note | RESPONSIBILITY: Site Engineer / Site Foreman
146a66bf-6ce8-5455-b46d-0ffeca6e79c7 | textbox | Date Completed:
305d2ed0-9b0e-49fe-ba71-213d8ce73523 | checkpoint | 1.3 Material Approval
42b49aad-d04d-5d29-955b-1207f27a52ab | note | FREQUENCY: Prior to Placement
53312bd2-cb46-588b-921f-a0e56e6ca080 | note | ACCEPTANCE CRITERIA: Material intended for use is to be submitted to the client prior to placement to verify it conforms to required specifications.
8afbc2de-b4a5-55eb-bafa-c287864a45f6 | note | REFERENCE DOCUMENTS: Material specification sheets
b4d4ba1d-29f9-5826-84ee-c1116ba3d646 | note | INSPECTION/TEST METHOD: Verfiy
6b902791-8e6d-54a8-a55d-a335027d4e5f | note | RECORD OF CONFORMITY: Teambinder Acceptance
02c1e77f-0f5f-5ee2-9c4a-540140cbc9d5 | note | HP*
cc06c163-c7e0-5734-bca7-9e31ed13dbda | note | RESPONSIBILITY: Site Engineer
35b53923-cb27-5e87-b3b8-d37624b48a85 | textbox | Date Completed:
bfe2254c-694c-4630-a825-222db50ecc33 | checkpoint | 1.4 Verify Material
989cd4e1-7451-5099-a28f-8dcd221cfb02 | note | FREQUENCY: Prior to Placement
937d4579-78b5-591c-bc3e-5af63785e9b8 | note | ACCEPTANCE CRITERIA: Assigned CBR to be greater than 6% (<10%), swell is to be less than 1.5%, unless approved as expansive. Soil is to be graded such that 100% passes through a 75mm sieve, 40-80% passes through 4.75mm and 10-40% passes 0.075. PI between 6 and 25. Permeability of less than 5X10^-9 for capping and verge material
c3bd1966-d6a7-54aa-b8c8-a0e9bbd0d220 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04(b), Cl. 204.06(c) Table 204.041, Table 3020.052
0d1a9e88-7483-53ca-9690-33e7a65afcad | note | INSPECTION/TEST METHOD: Site Inspection
cb3f69c9-304c-55ee-a100-d9150067d873 | note | RECORD OF CONFORMITY: Test Record (If silt is observed)
b3613b01-9c06-51d6-9593-7c838fd5db27 | note | HP
390bd2c8-e37d-5cff-80ce-3c2d8d27836f | note | RESPONSIBILITY: Site Engineer & Superintendent
fa23a526-a344-5fdd-a8f8-6e7ef1e2718f | textbox | Date Completed:
55b12032-3119-442a-b600-36f0a93952da | signoff | AUTHORITY HOLDPOINT
22f963fa-b910-4e3d-b572-09702724d808 | checkpoint | 1.5 Excavation Permit
1b931eec-8145-5fe7-961a-09214378770c | note | FREQUENCY: Each lot
c9499aec-7e1a-5517-83af-dc5c1fe49e79 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material.
2e038e3e-1fc1-52f5-8643-35877dcea3a5 | note | ○ Plant and equipment shall be appropriate for the task.
f95fa10a-0f9e-511c-97a1-82b9f2855d1a | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
bd7f06fc-6242-5525-8c84-e7108c7c18aa | note | REFERENCE DOCUMENTS: Excavation permit
4b6d5813-4002-5ce0-b154-6891f6ab1717 | note | INSPECTION/TEST METHOD: Verify
30a6c4d7-b9e0-57ea-8bfb-65caadd7cb6c | note | RECORD OF CONFORMITY: This ITP Signed Off
6b7cd7e7-2228-5b14-bdd6-d620d9967529 | note | HP*
bec8ab96-5b10-51c5-9f96-ed7ff517d08c | note | RESPONSIBILITY: Site Engineer
2a14ecc4-cbe5-5511-9ea5-05b658bab993 | textbox | Date Completed:
fcaf41cc-aa13-4c37-80db-eb7c286f81ca | section | Construction Works
b0cb4949-f1c9-4531-9094-638c33a8c167 | checkpoint | 2.1 Survey set-out
9933b096-49f8-53bf-bd6f-09ef72139dfb | note | FREQUENCY: Prior to Commencing Excavation
9027507f-b8a8-5261-9e4c-0f1954f572d7 | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used
4474a3ab-2855-508e-ad0d-8cdd12fe3cd7 | note | REFERENCE DOCUMENTS: Latest IFC Drawings
10bea490-8d2c-54c7-a466-8e9ec9149891 | note | INSPECTION/TEST METHOD: Site Inspection
01009886-347b-54f3-a43d-3ec6e0d2e57a | note | RECORD OF CONFORMITY: Survey records & pegs on the ground
3e55f136-f32c-5c96-a32b-7e46e7b65eec | note | SCP
1ac62ccb-410f-51ab-be16-f3e7cfbdd6f1 | note | RESPONSIBILITY: Site Engineer/ Surveyor
62515edd-10f7-549f-b190-f0eef602353d | textbox | Date Completed:
fcb8d4da-81fa-4a4d-a914-c23b015434a0 | checkpoint | 2.2 Inspection of fill area
5d3e14d5-fcae-536e-880c-8158238cf5f8 | note | FREQUENCY: Each lot
379c3adc-6d03-54d6-81c1-788a852daa54 | note | ACCEPTANCE CRITERIA: The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
8ccbe349-1b67-56a0-8f9c-e39472139226 | note | REFERENCE DOCUMENTS: 204.10 (b)
834afe8f-a8be-5847-aa32-45617790c552 | note | INSPECTION/TEST METHOD: Visual Inspection
c8d110e3-32bb-5e8f-b82f-3690ce29290c | note | RECORD OF CONFORMITY: This ITP Signed Off
a3a2a71f-7a43-5817-9725-44ba9c50e665 | note | HP
9cc3a29d-a26c-5d2b-9f29-951d22b408bb | note | RESPONSIBILITY: Site Engineer / Superintendent
1953dec2-2cf3-5430-a360-482636428bf3 | textbox | Date Completed:
7632daf2-af79-450f-a2a9-6e97dd4b24d9 | signoff | AUTHORITY HOLDPOINT
cd79b9cd-d892-448d-b0e1-a999296662c4 | checkpoint | 2.3 Layer Thickness
2e50b614-4798-596d-86d8-9bc67b65534a | note | FREQUENCY: During Excavation
ceef771e-2b8a-5faa-9ba7-f6b0b592f582 | note | ACCEPTANCE CRITERIA: Layers placed and spread in uniform compacted layers not thicker than 200mm.
a29593a3-a265-5778-9cb8-9cb8b9aeef90 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(ii)
3eb5e7a0-cac0-578f-8cad-218444611891 | note | INSPECTION/TEST METHOD: Visual Inspection
7cc8697f-c6c3-517c-bbf1-7f4cc77f3a73 | note | RECORD OF CONFORMITY: This ITP Signed Off
04540c45-3954-50af-b989-752cb0b622a7 | note | IP
f56b34e4-1d28-534c-8393-59ad29085bad | note | RESPONSIBILITY: Site Engineer
ba0f7f73-c4b1-5b7a-8904-fccd4eb6ceca | textbox | Date Completed:
54676ef4-936b-420d-a32a-fd07e9f9c30f | checkpoint | 2.4 Maximum Lot Size
8ed026ce-3b42-5aed-b6d3-84cf62907ec9 | note | FREQUENCY: During Excavation
a3fd1b6e-c205-50a6-ae29-4c8139cc1870 | note | ACCEPTANCE CRITERIA: Lot size for testing is to be one day's production or 5,000m2, whichever is lesser.
f81d1739-8c20-5d6b-a916-fe99cccd1d25 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.142
b862b716-6aa6-50cf-8415-3b37ad06e41c | note | INSPECTION/TEST METHOD: Visual Inspection
43fd6521-8b25-5772-8023-5c737a29bea3 | note | RECORD OF CONFORMITY: This ITP Signed Off
92c46e2e-c276-5bd9-82f5-724c25c720fd | note | IP
fcadea1a-c33a-5b4b-b036-b57dcc8ce4f1 | note | RESPONSIBILITY: Site Engineer
3b393244-0264-5d84-8238-87afde19616b | textbox | Date Completed:
fc11b18c-3f4b-4c34-b11f-92ce438dac13 | checkpoint | 2.6 Proof Roll
598cfea8-9922-5a73-9ce9-f9398a9679c6 | note | FREQUENCY: Prior to placement
69146019-711b-5116-877b-99fc33052676 | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
93a71544-60d2-5fa4-83f6-95b88cd194aa | note | REFERENCE DOCUMENTS: 173.03, 204.12), 204.10 (b)
1f064b12-4cee-5f14-a380-638f2f4619a9 | note | INSPECTION/TEST METHOD: Visual Inspection
a3e00e41-e5af-52ed-a09c-985bb97eecf3 | note | RECORD OF CONFORMITY: This ITP Signed Off
3a52978f-0ea5-5292-a054-b145b742bc47 | note | WP
8a9b3854-b57d-53d4-b393-4e536c116cce | note | RESPONSIBILITY: Site Foreman/ Superintendent
ed01962e-f836-5551-88a2-967f68d98be9 | textbox | Date Completed:
bd273e0c-d3de-4531-8aa3-cd681e9b6d12 | checkpoint | 2.5 Type A Placement
0e5280e3-6276-5381-b0db-5ef1bef8d169 | note | FREQUENCY: Prior to Placement/ Each Lot
e31a5e67-1631-594b-a0d7-6545251099a4 | note | ACCEPTANCE CRITERIA: Top of fill must be shaped and compacted to minimise damage due to wet weather
e97f01ca-5a0e-5ac6-882b-6fac174791de | note | ○ note 12 on Pavement Details 009-0001 "Capping Material can be substituted for (3%) Cement treated Stab Sand in confined areas
1785b8c0-3cd0-5dfc-977f-112f5bd1f22f | note | ○ Any rocky material present must be uniform throughout the layer
6eb4106c-28e8-5b9d-a2a8-cb29936fa4d1 | note | ○ Each layer shall be kept generally parallel to the surface of subgrade
f765b7ee-ff1b-5b85-a6d9-022fbf77a276 | note | REFERENCE DOCUMENTS: 204.10 (d) (i). 204.10 (d) (ii). Table 3020.052
1e4080d4-f278-580b-9d9a-e0d61a969c1b | note | INSPECTION/TEST METHOD: Visual Inspection
9f4b9eae-433c-5544-9361-ba0f2922a6b9 | note | RECORD OF CONFORMITY: This ITP Signed Off
4d403302-a020-5281-8012-74e70bc8017a | note | IP
94b9b4f9-00f1-51f4-93db-037ad420801a | note | RESPONSIBILITY: Site Engineer / Site Foreman
a5bc5f37-8882-5726-abf6-20a543d82fa6 | textbox | Date Completed:
b3f66d90-9e5d-425c-abd8-09642f34eb82 | section | Testing
f977f4c9-068a-4156-9249-5ad27db58cc4 | checkpoint | 3.1 Reduced Test Frequency
8c1c922a-465c-592b-b570-bcb09fb59231 | note | FREQUENCY: Each lot
3ed4b908-0b4e-598f-95de-efb1e4bd7c5e | note | ACCEPTANCE CRITERIA: Initial Testing requirements shall satisfy the full requirements as detailed in the specification. Once three consecutive lots have achieved specified requirement, Superintendent can agree to reduce frequency of testing of subsequent lots to the reduced testing frequency specified in Table 204.141. Reduced frequency resets if one lot fails.
3913950a-89da-5425-afda-d3bd7c7c3f4e | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.131
be02daa9-7883-536c-8495-0e85ed47147c | note | INSPECTION/TEST METHOD: Test Record
edc9572b-60bf-5813-9748-52b76f6e8d3c | note | RECORD OF CONFORMITY: Test Records
6652e761-2d53-594f-a7ee-5c48e3530dcc | note | AP
a4822c79-83d3-58ab-a9f3-b570e7e8fe7e | note | RESPONSIBILITY: Project Engineer
dab3c63e-8db8-5dec-95c4-ac591588a456 | textbox | Date Completed:
2887c1e0-20e9-4aac-a0d1-760bdfc41bd8 | checkpoint | 3.2 Compaction Testing
07333195-a79f-575c-ad50-f5fc64b45fec | note | FREQUENCY: Each Lot
db64d516-3e52-50e4-8328-814cc52fa8b2 | note | ACCEPTANCE CRITERIA: Type A material should be compacted to 98% Characteristic Value of Density Ratio (Scale B).
e3573050-6c5d-50d6-8545-d4a0cccb83a7 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.131
6318d516-5afd-5964-82a1-fe784330f069 | note | INSPECTION/TEST METHOD: Verify
ec908985-f59a-54f0-8311-abbabdcbb127 | note | RECORD OF CONFORMITY: Compaction Test Records
5186dcee-9175-5807-b33b-b8eb868aaa30 | note | TP
14d166d6-6274-56bf-b0bb-d170024f9f74 | note | RESPONSIBILITY: Site Engineer
c1e1976a-2d87-59a1-88c9-e9ef6e3bc358 | textbox | Date Completed:
ff6a9bad-9352-4d2f-9bd5-440fdcf8be95 | checkpoint | 3.3 Compaction Testing (Small Lots)
527d1133-d372-5066-ab9b-4c4521186132 | note | FREQUENCY: Each Lot
67c5a3fe-d0a9-53f8-9d76-b99b6fa356da | note | ACCEPTANCE CRITERIA: Any lot which has a surface area less than 500 m2 may be treated as a small area. Acceptance of the lot shall be based on the mean values of 3 individual tests. Minimum Compaction shall be 100% SDD.
02b04993-a5eb-58d3-b958-0a96229ce9be | note | REFERENCE DOCUMENTS: 173.04 d
e9ab975c-a803-50d0-8cc4-768c1e487a9a | note | INSPECTION/TEST METHOD: Test Point
a270098b-a51b-5789-9039-21cae4ba3574 | note | RECORD OF CONFORMITY: Test Records, Lot Register
cb712f41-b664-500a-b3dd-71c5c5b3b1d2 | note | TP
337c7190-8657-5a0e-8807-1a8388b0d2a1 | note | RESPONSIBILITY: Site Engineer
b9677e21-1277-5473-9faf-7fa538d7395f | textbox | Date Completed:
5d74f538-0b67-43af-b1ce-0cab950749b3 | checkpoint | 3.4 Maximum Particle Size
20062807-d96c-5999-9310-31adc0f4fe49 | note | FREQUENCY: Each lot, unless reduced frequency has been approved
b37d01a6-57dc-592a-964c-f8c7a37d4510 | note | ACCEPTANCE CRITERIA: Material is to be graded such that 100% passes through a 75mm sieve, 40-80% passes through 4.75mm and 10-40% passes 0.075
da7b4955-92f7-5152-80bb-7eaf8f43f53f | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14(a)(ii) Table 204.141, Table 204.041
d0eb2d73-d7f5-52ed-b822-0a99defa755a | note | INSPECTION/TEST METHOD: Verify
9753fdbf-0c01-5d47-9903-273287be04ab | note | RECORD OF CONFORMITY: Maximum Particle Size Test Records
66e0f08f-184e-5fae-a09b-be95b475382c | note | TP
4b029aa4-b5b1-5d0b-baad-005e4722d9dd | note | RESPONSIBILITY: Site Engineer
5b2e4808-1259-57aa-a10c-dd267e78ddd2 | textbox | Date Completed:
62bb7012-dcae-4a6d-bbbe-cbd8c10c0665 | checkpoint | 3.5 CBR/Swell
f84206ab-8d83-5a63-87ae-390d0e7dc60b | note | FREQUENCY: First lot only
ae447e2a-8731-5f54-84ab-93f00427224f | note | ACCEPTANCE CRITERIA: CBR: ≥ 6%, Swell: ≤ 1.5% (Verge material less than 1.0%).
00493013-bf6c-5c50-8b5f-87a5d968d422 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14(a)(i) Table 204.141, Table 204.041
3fb836c5-c8c9-54b5-9931-a81e5d1f3c6e | note | INSPECTION/TEST METHOD: Verify
4461a42d-4e4b-557a-a0d1-d394a7eacf6b | note | RECORD OF CONFORMITY: CBR/Swell Test Records
a6ca8e12-4a0b-58d8-904a-2f70b3f7044b | note | TP
0c209de1-b50a-5528-8186-ba90a1b8932f | note | RESPONSIBILITY: Site Engineer
7ceaa427-569c-57fd-b676-fbbf115259a9 | textbox | Date Completed:
918852d8-5f2e-43ee-bebb-798636491b12 | checkpoint | 3.6 Atterberg Limit Tests
c8ad4748-0c48-5134-8601-28bd96b9946e | note | FREQUENCY: Each lot, unless reduced frequency has been approved
b804037f-8aed-544f-897b-e08498f50a5e | note | ACCEPTANCE CRITERIA: PI between 6 and 25, PI x % passing through 0.425 to be less than 1000
6a86c59e-b68f-51d0-bbf1-d33654d492cf | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14(a)(ii) Table 204.141, Table 204.041
90aa5a68-a082-5168-8996-8a46296c07a0 | note | INSPECTION/TEST METHOD: Verify
5ae53905-8f61-57d6-9ac4-023bf39055c0 | note | RECORD OF CONFORMITY: PI Test Records
2144734c-59a0-5b33-bce4-a589e16deefb | note | TP
d715d56b-86b9-5b80-877b-8e31e8bc1a97 | note | RESPONSIBILITY: Site Engineer
ede4693b-4558-5509-9c40-6ec2241b2cbd | textbox | Date Completed:
95d54a3f-32fe-47c0-9086-0e4ee2d32a8d | checkpoint | 3.7 Permeability
0a513066-1f78-534b-8266-fafacb7e2449 | note | FREQUENCY: Each lot, unless reduced frequency has been approved
b45d5848-c286-5c31-8a49-22b301ede540 | note | ACCEPTANCE CRITERIA: Permeability of less than 5X10^-9 for capping and verge material
35008cc3-c205-52c0-9a77-6d960f5539d6 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14(a)(ii) Table 204.141, Table 204.041
fb634bd0-53fa-5a7c-a991-8c6dba304d9f | note | INSPECTION/TEST METHOD: Verify
7cea199a-4bcb-5a0b-89e2-ff466ae4ae9e | note | RECORD OF CONFORMITY: Permeability Test Records
f2befd73-d1ad-5e9d-b5aa-644bb2443b33 | note | TP
8ed77d60-b86e-54d8-ba12-90698220eb19 | note | RESPONSIBILITY: Site Engineer
d57d795c-de3b-56d3-8761-bb29e3e50da3 | textbox | Date Completed:
2af85cb5-c1b8-4d6e-8171-a6b073a70340 | checkpoint | 3.8 Material Property Testing (Scale B)
4d70ec18-43d9-5230-90fe-a52e5755d298 | note | FREQUENCY: Each lot, unless reduced frequency has been approved
8848738c-6564-556f-b597-0af2a587991d | note | ACCEPTANCE CRITERIA: Obtain production testing ITP from the supplier. Materials shall be tested to show compliance with the requirements of Clause 204.04.
43297ebb-db29-55f9-99f6-8ca8ea6ebf0e | note | REFERENCE DOCUMENTS: Cl 204.04 Cl204.14
b4643a2c-e51d-54dc-babe-df55d04fb554 | note | INSPECTION/TEST METHOD: Verify
86c26aa9-08e3-5ba2-863d-a525e1722aa4 | note | RECORD OF CONFORMITY: NATA test report
f288f3e6-c37b-50e7-8dc9-aeedcc3495a8 | note | TP
84c68fb4-0205-5cd9-a62e-cc8ea83d5f08 | note | RESPONSIBILITY: Site Engineer
a17c79a7-2f96-5120-8d95-05e69f5473c5 | textbox | Date Completed:
3b0d5b17-83e5-4f92-a13b-cb297998ae33 | checkpoint | 3.9 Survey Conformance
b3fa48ad-d7ee-5894-ad3e-ac7afd0206ee | note | FREQUENCY: Each lot
073f018f-903c-59d3-97fe-5397fe57ab5d | note | ACCEPTANCE CRITERIA: The number of measurements and the tolerances of the mean and standard deviation from the theoretical surface level must comply with Table 204.031
aea2aa66-6054-5812-a395-edad516df1f8 | note | ○ Scale B:
9b0e9896-0dd9-57c8-a0bd-e0ff56212f7c | note | — Range x = +5,-25
01514a46-331f-55f0-9b7e-45814a2982ce | note | — Max S = 15mm
669025fb-267c-599f-a2ad-c2b83c96c288 | note | — 40 measurements per lot
6cd150a6-728b-5cd4-9fb2-6acb93dcf67c | note | REFERENCE DOCUMENTS: 204.03
2145a5d1-c252-5c5b-aeac-9aaaf0a4add9 | note | INSPECTION/TEST METHOD: Survey conformance point
85211357-1f0c-51fe-a5d4-b45282a23eaa | note | RECORD OF CONFORMITY: Survey report, Lot Register
b4d4b1e6-0588-536a-b58e-162141f9aa66 | note | WP SCP
c7cb94f4-aff5-5c49-8c43-e572532b460e | note | RESPONSIBILITY: Site Engineer & Surveyor
acbbbc60-7623-5baf-a336-128b4ba17bb6 | textbox | Date Completed:
30eac098-427a-4878-b190-7fbf055f172d | checkpoint | Final Inspection
9018eea1-c500-5bae-af30-129542c1e8ed | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
8ad97b86-9da1-5041-864c-364e1599f276 | textbox | Print Name:
07e25e79-29df-57c6-bcfd-ca2cce5b9a3e | textbox | Position:
c1c8f1f7-cd2e-5790-80d2-9310ea0f3d1e | textbox | Date:
4d475638-69c0-4652-9e2c-2d820e131c7a | checklist | FHC-ITP-005 - Class 2 Crushed Rock Rev4 | itp | FHC-ITP-005 - Class 2 Crushed Rock
d36904fe-d5e2-4ae1-94c5-695574d857b4 | section | Preliminary Works
87e13ab2-a4e4-4b07-bfec-7541e4252e32 | checkpoint | 1.1 Check for correct documentation
387e0d43-cdc3-5546-8387-cc9a5f5d0f6e | note | FREQUENCY: Prior to commencing any activity
977527c5-d54a-595b-b00c-e401fdb13a90 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
b280decc-da99-56da-82a0-012c569bf6fd | note | — Using the correct and complete set of drawings
adf6a9fa-7173-5dc6-9c36-f423b17daca7 | note | — All drawings are the latest revision
2283184a-8656-56c7-ab8f-f468027bc488 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
c9cb3881-1d81-5ab6-8112-433dc8958162 | note | INSPECTION/TEST METHOD: Visual inspection
490d93a1-782b-5258-bdd4-e715a3881e5c | note | RECORD OF CONFORMITY: This ITP signed
ce3ab00a-2af8-5445-b586-d40c22a468e4 | note | HP*
bdad4d3b-d760-5aa5-8374-e34912607c4d | note | RESPONSIBILITY: Site Engineer / Site Foreman
1df14c60-882c-57bd-ae29-52ddb5c707f6 | textbox | Date Completed:
396b08d3-d8c6-4cc4-8f40-609a20ea182d | checkpoint | 1.2 Material Mix Design
4f6ff17f-8c55-58ca-81e3-40fdc9609a8e | note | FREQUENCY: Prior to commencing any activity
90b36b63-583a-5e45-b03e-f50312aec221 | note | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02 as listed in Section 175
8251c2c9-2292-56f5-ac22-a717200f0389 | note | REFERENCE DOCUMENTS: Cl 812.04, RC 500.02
0ef94f99-7996-5125-beeb-653e69a9b56e | note | INSPECTION/TEST METHOD: Document Review
8bc97c95-d20f-50b1-b3b4-2bbba83098e7 | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
27115860-114c-5298-8a14-33c76de9e2c4 | note | HP*
f12464bf-71ab-58a4-b0ce-4d1f0c31d884 | note | RESPONSIBILITY: Site Engineer
450f2fca-8703-56d9-96bd-56cddc4ed91a | textbox | Date Completed:
5c9de00c-b423-4107-84da-a98bf0e20a85 | checkpoint | 1.3 Material Approval
30dd40f8-7885-5f3f-a241-c7c9bc77f07d | note | FREQUENCY: Prior to Placement
b566863e-df17-5859-9140-f8f948e6caa7 | note | ACCEPTANCE CRITERIA: Material intended for use is to be submitted to the client prior to placement to verify it conforms to required specifications.
8da7ef72-1738-5019-8457-5c7d53da1f51 | note | REFERENCE DOCUMENTS: Material specification sheets
6f904e1c-221a-505d-a8c1-ca3a0923544b | note | INSPECTION/TEST METHOD: Verfiy
0d186d5e-c967-5ea5-a898-0dd41a900751 | note | RECORD OF CONFORMITY: Teambinder Acceptance
625ae46c-2b96-5b61-8ba3-fe5302562ae6 | note | HP*
227964da-a719-5e29-a6e5-095877a4b922 | note | RESPONSIBILITY: Site Engineer
952a06ab-32e1-58fb-a5ff-785219bc8c17 | textbox | Date Completed:
2fc5144c-14ed-4866-a56c-4d7afe8047a6 | checkpoint | 1.4 Implementation of all measures and controls
8aaa0d9a-9b33-52fe-b0d3-622e65b70cd2 | note | FREQUENCY: Prior to commencing any activity
9b785427-f977-5168-b7da-05eefe2cadd7 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
53ee7400-f29b-5bc9-8697-e4581b35fd2a | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
0cd226eb-3217-5e56-988e-d3a140ba3401 | note | INSPECTION/TEST METHOD: Visual Inspection
bd3d7859-9b06-5eaf-84e8-d4f02fd4ba5a | note | RECORD OF CONFORMITY: This ITP signed
08a7a6c4-095c-5720-b0d1-3525a37d6877 | note | HP*
4a03329f-6ead-5090-a6c7-d5a3f651bbf4 | note | RESPONSIBILITY: Site Engineer / Site Foreman
86f0913d-0253-5c8a-97dd-05c62db68da0 | textbox | Date Completed:
85632fc5-5512-48ce-9273-e926e2046610 | section | Construction Works
c5e287dd-8528-41dc-8721-732fc46b54c4 | checkpoint | 2.1 Transverse Joints
1109e860-6c02-5941-b7dd-75cf940f5000 | note | FREQUENCY: Check prior to placing material
a4aebd9e-04ce-550c-9ec4-1acc7e1e339c | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres
7b121fa1-6270-53df-a361-b7fc8e973dbf | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.07 (c)
d27a8be2-8285-579e-986c-18a16816da9f | note | INSPECTION/TEST METHOD: Visual Inspection
85fc77d3-a375-5836-8dd3-d2ee6b45ed47 | note | RECORD OF CONFORMITY: This ITP signed off
db2ca1f6-f0b8-5836-813f-3759da99cae4 | note | IP
48bc6bb9-a9ce-5697-ae6b-e7e9b67944b4 | note | RESPONSIBILITY: Site Engineer
929c65ab-54a6-51f3-85cd-f518f59866f1 | textbox | Date Completed:
ecbd8015-b887-47c0-9991-4ae279f217f1 | checkpoint | 2.2 Longitudinal Joints
a7598b5b-6da3-5545-aabc-6ef91fc14215 | note | FREQUENCY: Check prior to placing material
dc9c1057-6114-5b9e-9606-df37bc48ad61 | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Longitudinal joints offset from one layer to next by not less than 150mm. Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
3b0fc5ce-abd4-531a-9bc8-2be732455737 | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.07 (d), Cl.304.07 (e)
0c1430a5-9a78-507d-9671-6c2a1fbd2ba1 | note | INSPECTION/TEST METHOD: Visual Inspection
7087f75e-f77e-5775-8b6c-96fdafe65c29 | note | RECORD OF CONFORMITY: This ITP signed off
ff1244ef-86ec-5f3c-b11f-41b495fe2688 | note | IP
f296bef9-3645-5a19-a78b-3d6169566ca1 | note | RESPONSIBILITY: Site Engineer
335654b7-660a-58cb-9140-5dfabc728a9e | textbox | Date Completed:
3b296254-db9c-4bd7-a92e-3076530572fb | checkpoint | 2.3 Lot Size
58cf3ed1-5f60-5fc2-9f82-2c42fca8d56b | note | FREQUENCY: Check prior to placing material
9e19519b-5ac1-55e8-9426-53bd29c36032 | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
ee8b231b-9c4c-5416-a12f-0125046a58c5 | note | REFERENCE DOCUMENTS: . Cl.304.08 (b)(ii), Table 304.111
3c082589-92c5-59d0-8e92-c1526f811481 | note | INSPECTION/TEST METHOD: Site Inspection
c2a22645-a992-56af-960c-48c2f4831e50 | note | RECORD OF CONFORMITY: Signed ITP, Delivery Dockets
405a2876-89b8-57ba-adc2-a815925c524c | note | IP
9c478e21-1888-56b1-bc6e-6423c2cab883 | note | RESPONSIBILITY: Site Engineer
6c601135-d401-5d36-bd66-c70390d5bcf7 | textbox | Date Completed:
d9313a7f-f41e-41f4-8d14-582bec00bd7e | checkpoint | 2.4 Layer Thickness
9eef7ef3-dc90-578c-b908-dca9237e47eb | note | FREQUENCY: Each Lot
fbb32257-5b5b-529b-a015-bb5bc3c6857e | note | ACCEPTANCE CRITERIA: The maximum thickness of any pavement base layer shall not exceed 150 mm and the maximum thickness of any subbase layer shall not exceed 200 mm. The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
4352e079-2ce7-5da8-aa62-25fefbf7073e | note | REFERENCE DOCUMENTS: Cl 304.08(b)(v), Cl 304.08(b)(vi)
074fd6c6-b676-5ef1-bc26-5934e64b2a91 | note | INSPECTION/TEST METHOD: Site Inspection
0a9be27a-853d-5839-acc1-61451dddc3f4 | note | RECORD OF CONFORMITY: Signed ITP
58ea41e5-53c2-5823-bb0b-d8359dba175c | note | IP
99aa0750-afa9-5d3e-8ed3-a8443089a7fa | note | RESPONSIBILITY: Site Engineer
d67f2b68-029a-5088-b60b-29d2ecfa4877 | textbox | Date Completed:
8f2eff31-d807-4ea4-9040-3a09898c0a63 | checkpoint | 2.5 Proof Rolling
8aae8233-ee0a-5202-8942-bafc3ac0513e | note | FREQUENCY: Proof Roll each layer
3229e0fb-466e-5c7d-8ee1-dab8eb3151d3 | note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
d01a6bda-330e-57d7-85ae-a5ec7405fd16 | note | REFERENCE DOCUMENTS: 173.03
5ed0cb83-8c23-548f-91ae-8943d24773af | note | INSPECTION/TEST METHOD: Visual inspection
e99955db-bc26-5a11-95c6-d4f4d0ae42a5 | note | RECORD OF CONFORMITY: This ITP signed off
2a5ce064-0e08-5fe3-ad6f-c0057019cff4 | note | HP/ WP
7e829574-8d08-50ea-bd25-65cd46f0f8a7 | note | RESPONSIBILITY: Site Engineer & Superintendent
ef9aecc1-a8d2-598a-b2e4-c5a1b121e6c6 | textbox | Date Completed:
21011c91-107e-4146-85c3-ca655693a7fc | signoff | AUTHORITY HOLDPOINT
d3d155c6-acc9-4df8-81fe-5a3d771ed18a | section | Testing Requirements
c4cc142a-195a-4c2a-9f2b-094fa67eff6d | checkpoint | 3.1 Determine Testing Scale & Initial Testing Frequency
a64d5694-e20e-54da-93db-7db857e42091 | note | FREQUENCY: Prior to Testing
74dd645a-41cf-5542-9993-cc55d83ecf40 | note | ACCEPTANCE CRITERIA: The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification. Testing of every lot shall continue until three consecutive lots of like material and/or work have achieved the standards specified.
b3181be2-34c1-5805-b9fb-1c3cb95b98bf | note | ○ Scale B - The first lot of each pavement course shall be tested for post-compaction grading and PI. If the first lot each pavement course satisfies the specified post compaction requirements in Clause 304.10(a) and (b), as applicable, no further post compaction testing will be required for that pavement course.
938585b8-38e6-55b6-83f7-907caceeb61b | note | REFERENCE DOCUMENTS: Table 204.161, Cl.304.08 (a), Cl.304.11 (b), Cl.304.11 (c)(i), Table 304.111
a30f8d76-b134-53b8-b52b-1e55ae03265a | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
84ffb292-0898-5c8f-af9d-21c3dbdd5c4d | note | RECORD OF CONFORMITY: Signed ITP
1f1d215c-1268-5518-b43f-60249c407166 | note | AP
19b690da-3432-5876-80a2-cf071730bd56 | note | RESPONSIBILITY: Project Engineer
23de5e4c-9238-5750-95cd-8561bca03342 | textbox | Date Completed:
8bb9b147-b609-462e-9763-fe51cf8b0fd9 | checkpoint | 3.2 Compaction Testing
967e5e7a-fc30-5746-ae74-e27de913ae7d | note | FREQUENCY: Every Lot
bca05c1c-fe1f-583a-93bc-9ee9f6e86d69 | note | ○ Every second lot (reduced frequency)
6e508a62-46aa-5d4e-a446-d864e2f946ce | note | ACCEPTANCE CRITERIA: Minimum Characteristic Density Ratio (CDR) of not less than 98%, using Modified compaction effort.
cf1658bb-cf08-5533-af2b-6a2c3b95ae73 | note | REFERENCE DOCUMENTS: Cl304.08, Table 3040.061, Cl 304.11 (b), Table 304.111
1bc7e909-56ee-5368-97d6-45fce4dfb7e4 | note | INSPECTION/TEST METHOD: Test point
24c7e04c-01ca-5381-9e5b-5dadc3e42944 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
7dde4e59-0053-5c8f-9ab1-fd22d80e34d4 | note | TP
f0b4dcd1-240e-5f05-a040-b2ad62f64973 | note | RESPONSIBILITY: Site Engineer
0a8775fa-83a7-5500-8a8a-1d539c3a39b7 | textbox | Date Completed:
d81c6f69-8b95-4ef0-86cf-2cb3da596262 | checkpoint | 3.3 Compaction Testing (Small Lots)
8c3ea99d-f571-5d51-81fb-da854ba04bf8 | note | FREQUENCY: Each Lot
859033d7-19cb-5894-934c-a24986458349 | note | ACCEPTANCE CRITERIA: Any lot which has a surface area less than 500 m2 may be treated as a small area. Acceptance of the lot shall be based on the mean values of 3 individual tests. Minimum Compaction shall be 100% modified compaction effort.
3efffc43-7fc7-5c2e-ad20-611a10cd1f44 | note | REFERENCE DOCUMENTS: 173.04 d
63f31622-8e05-506f-905e-1cdbdbaa4c10 | note | INSPECTION/TEST METHOD: Test Point
a628100d-ce6e-55a3-ae5b-f68d94d90b6c | note | RECORD OF CONFORMITY: Test Records, Lot Register
82479e9f-4baa-53dc-bde0-388222ce696a | note | TP
f66e8b43-3c47-5cbf-9207-f16058160b8e | note | RESPONSIBILITY: Site Engineer
2de8667c-f1e2-5359-89b0-dc45e34b44b1 | textbox | Date Completed:
8e87f58e-0025-4bf7-9ffc-5231b9d3ac15 | checkpoint | 3.4 Material Grading - Post Compaction (Class 2 & 3 Only)
f0dcff0c-52fa-5e0b-a6dd-49d63a1c6cc8 | note | FREQUENCY: First Lot Only
1a5182cd-8330-566d-a6dd-379ea98efc3e | note | ACCEPTANCE CRITERIA: Post compaction material grading results must comply with the following:
499c2d2f-f06c-5d25-8c14-fa849dca23ee | note | ○ Class 4 - N/A
d7a2eeda-756f-5440-a387-86eb5b89d6af | note | ○ Class 3 - As per Table 304.101 - VR Spec. 304.10
e5d11b16-efd0-5948-b76e-0990c5046ecc | note | ○ Class 2 - As per Table 304.101 - VR Spec. 304.10
a5a54f2a-8302-536e-9efc-0d2f5adab42b | note | REFERENCE DOCUMENTS: Cl 304.101, Cl 304.111
74be9b0b-f814-5699-903e-8830cf14b1ff | note | INSPECTION/TEST METHOD: Test point
229598a5-547b-53da-be62-a4ed6318aa90 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
fb11995f-e828-5e70-903c-d25c347f2f75 | note | TP
d8863e1c-deee-5d99-a101-2741ea7471ed | note | RESPONSIBILITY: Site Engineer
0f4a2651-1949-5638-b2bf-f01497d6995a | textbox | Date Completed:
152d2ab3-b2c3-446a-baca-d71718866fa9 | checkpoint | 3.5 Plasticity Index - Post Compaction (Class 2 & 3 Only)
d27395aa-5774-5eb0-a5dc-971055289596 | note | FREQUENCY: First Lot Only
e6a5383a-8be7-5fd2-968d-ef84b76a6ae7 | note | ACCEPTANCE CRITERIA: Post compaction PI results must comply with the following:
0ae5e428-85e7-57ed-bf41-22864777077b | note | ○ Class 4 - N/A
56c34d9f-7718-56b5-aab2-072883d64484 | note | ○ Class 3 - 0 to 10
3652ce05-ffa5-58a2-a76c-b6ad69398589 | note | ○ Class 2 - 0 to 6
09c588ef-582f-57b7-8b2e-c8a730d813f7 | note | REFERENCE DOCUMENTS: Cl 304.10, Cl 304.11, Table 304.103
e47e7fd8-7daf-5bdd-963f-1eb27a04683b | note | INSPECTION/TEST METHOD: Test point
106ebbc5-3bae-53e3-b685-8941c3de9286 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
9e3e8671-a485-5ffb-bea8-29440cd22b54 | note | TP
f6353f33-d3c5-54bf-978b-b627740f1a4e | note | RESPONSIBILITY: Site Engineer
59d53044-9502-5e2c-aaea-19b6f056311e | textbox | Date Completed:
0d6fd214-d55e-48db-b44c-b99bf7c50f54 | checkpoint | 3.6 Survey Conformance
1dc4c449-6e12-56f2-9359-d5ecd2ad08b9 | note | FREQUENCY: Each lot
32ee415f-7e91-545d-88d5-8b8077da036f | note | ACCEPTANCE CRITERIA: Layer to be finished to a smooth and uniform surface and after compaction shall conform within the following limits:
06cf55f6-2266-5cf5-a46b-84137b561224 | note | ○ Shape: no point deviation > 8mm from 3m straight edge in any direction
8e7cce0b-1963-5570-9e3a-f76380402c9d | note | Surface level tolerances:
0c8b1567-a4a1-5667-bcc4-b9b31cc53b5d | note | ○ Range x = +6, -16mm
ade2ddbf-12a8-591e-ba06-701c9aec9a74 | note | ○ Max S = 15 mm
03f33bfb-9129-55bb-8322-7ddad584f406 | note | ○ 40 measurements per lot (Minimum)
d79b6201-ba4a-517e-998e-094fbb288ecb | note | REFERENCE DOCUMENTS: Cl 304.06(b, d, i) Drawings, Table 304.062
b1fbc22e-d906-5ac4-bbb2-0c9a65ee0299 | note | INSPECTION/TEST METHOD: Survey
d49491c8-cfa0-52d0-beb8-aca7b92a2e20 | note | RECORD OF CONFORMITY: This ITP signed off; Survey Report, Lot Markup
e670b047-d9a9-50de-9509-43e635a3c9fd | note | SCP
b2a84d9e-b3f5-50cb-ae70-898f2757df12 | note | RESPONSIBILITY: Site Engineer/ Surveyor
cf6c47a7-c9a2-56a3-b914-812b3d91d3f3 | textbox | Date Completed:
91a4bf83-b39f-4c5d-9d2b-c1ad7371888c | checkpoint | Final Inspection
bada7515-3cbf-5ba4-9ff7-9a76641f2570 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
c107da0d-44e3-5910-bf99-571d8b4a1eb8 | textbox | Print Name:
25da0481-24be-57af-8618-0c7de231f3bc | textbox | Position:
9ad99b6c-be5c-569e-a2b3-60bd07ef2fae | textbox | Date:
ddc16ef2-d6c4-4605-8495-5ab59704967f | checklist | FHC-ITP-006 - Class 3 Crushed Rock Rev4 | itp | FHC-ITP-006 - Class 3 Crushed Rock
bff2d31a-ba89-42d7-91bc-ee86f031a8f6 | section | Preliminary Works
9205afb1-4ab9-4ea4-9df0-535180111f6f | checkpoint | 1.1 Check for correct documentation
91c84f75-c849-5a52-8263-e0dca6aaef62 | note | FREQUENCY: Prior to commencing any activity
2a4e8d15-39a5-5544-a1d8-d2c4ef274fdb | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
0e1b707d-93b5-50a7-87ca-218c87195952 | note | — Using the correct and complete set of drawings
ed94f534-00ff-52b4-b952-cba7e8919cd6 | note | — All drawings are the latest revision
e623938a-3291-5a7a-840c-01a40b5befce | note | REFERENCE DOCUMENTS: Drawings and drawing registers
5a77f599-a3b8-5c8b-a991-79ae82bba64c | note | INSPECTION/TEST METHOD: Visual inspection
fd492ecc-ed35-5e7a-94ae-46880c630fb6 | note | RECORD OF CONFORMITY: This ITP signed
a722fdf3-6921-547a-b808-1aeb3b59ee78 | note | HP*
72f811a1-2798-5d8b-a225-5b07d81d58da | note | RESPONSIBILITY: Site Engineer / Site Foreman
a5409c5e-2315-5174-90fc-97fe0f28af99 | textbox | Date Completed:
78f74883-5bf8-4dca-b039-b7bf5d03f9fe | checkpoint | 1.2 Material Mix Design
6ab2c4a6-fc18-55a7-95d6-f312ef053e80 | note | FREQUENCY: Prior to commencing any activity
b45468a5-1351-599a-83c9-9084de77979f | note | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02 as listed in Section 175
b93c8d10-54e3-5cbd-a644-07c061caf9b6 | note | REFERENCE DOCUMENTS: Cl 812.04, RC 500.02
80fdb96b-a998-5c71-b660-fa7d57cf6a9b | note | INSPECTION/TEST METHOD: Document Review
ec456dc1-9211-5cae-b410-2e474d35cbd3 | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
b582c753-be9c-5079-9d30-a6d55c728155 | note | HP*
ba092949-c8ef-5b9a-9c17-1a89f1aa8a51 | note | RESPONSIBILITY: Site Engineer
5db7e08c-c48c-52d6-911f-10d3c3f447ab | textbox | Date Completed:
2deee372-acf3-45db-8224-5490ad624c74 | checkpoint | 1.3 Material Approval
3d80e6a2-ce2a-5830-9193-b78309c745ac | note | FREQUENCY: Prior to Placement
9c17b6ae-aa72-5f90-bf63-4f1d2161b53e | note | ACCEPTANCE CRITERIA: Material intended for use is to be submitted to the client prior to placement to verify it conforms to required specifications.
77be7aaa-5ed6-509a-842a-05c51850978e | note | REFERENCE DOCUMENTS: Material specification sheets
62d5a92d-1829-58a3-bf25-2cfd76f223de | note | INSPECTION/TEST METHOD: Verfiy
de7ec5ff-152d-5c5a-a9e2-25a2823cffd1 | note | RECORD OF CONFORMITY: Teambinder Acceptance
aa06a9fc-89bd-539e-aa8f-6f96fba3b9ef | note | HP*
f6484fe9-a2e7-501f-abc4-4bf8d3605346 | note | RESPONSIBILITY: Site Engineer
d75ae20a-43f5-5fee-9027-97239ee56032 | textbox | Date Completed:
fbb6fa79-489b-498e-9082-90780afaa9a6 | checkpoint | 1.4 Implementation of all measures and controls
d0039a90-0b09-588d-afec-64f5f0576dad | note | FREQUENCY: Prior to commencing any activity
d7937a23-ea9a-50e8-bb2e-531d20f91f63 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
d09ffcfd-3051-58b7-a70a-4af2f426ae46 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
568c33fd-1013-594d-967e-45e1a4fb9ac3 | note | INSPECTION/TEST METHOD: Visual Inspection
435b6d44-c0c7-50ea-8a07-b0fbec34bd95 | note | RECORD OF CONFORMITY: This ITP signed
8c914fd8-202b-5586-9cd2-662c9d957fb0 | note | HP*
526b82fd-d03b-5ed9-9583-bfa2f4b8c576 | note | RESPONSIBILITY: Site Engineer / Site Foreman
a9d92619-39e9-5c11-bfe9-b1fd6e320a8a | textbox | Date Completed:
c7721c98-d913-4e6d-8987-c9989af36e4f | section | Construction Works
49b773ee-62ab-45cd-b387-4578744991ae | checkpoint | 2.1 Transverse Joints
8729ab56-52b9-5e32-99f7-e75a601a713c | note | FREQUENCY: Check prior to placing material
ae50bc58-b57c-5a72-b699-0a40207076ac | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres
6b53fefb-a452-518b-b5cf-438f8dd27ceb | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.07 (c)
43ddf6de-bb76-5a8b-a360-27b95747ad22 | note | INSPECTION/TEST METHOD: Visual Inspection
81ed1860-7103-5d9a-a901-bfddbfd77e1a | note | RECORD OF CONFORMITY: This ITP signed off
b6bf4753-a0b6-55ac-827b-10a93aafb648 | note | IP
f1aef445-88a9-5900-aa30-03b671e5de99 | note | RESPONSIBILITY: Site Engineer
9cca2e4e-80df-581d-a992-cf07da43651c | textbox | Date Completed:
05ee8b79-e788-453c-bf7d-c16a722d60d2 | checkpoint | 2.2 Longitudinal Joints
47eb818b-2c5c-5e8d-8119-315c0397b3c4 | note | FREQUENCY: Check prior to placing material
da82a02c-e12c-5d2f-b928-33d8e3b99833 | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Longitudinal joints offset from one layer to next by not less than 150mm. Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
98d63ea3-4e9c-5bd8-9cfd-d2d31c33959b | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.07 (d), Cl.304.07 (e)
43a9edfb-65f1-5cf0-a3aa-744c192e07cf | note | INSPECTION/TEST METHOD: Visual Inspection
fcd00487-0e85-59e9-a417-55ba2fc877cb | note | RECORD OF CONFORMITY: This ITP signed off
a0a513d0-6786-592b-b311-00da20206515 | note | IP
d91d0728-0d71-5b68-9167-b5ea513bd049 | note | RESPONSIBILITY: Site Engineer
5785a928-482a-5f4c-acb6-8e71eb6b2a86 | textbox | Date Completed:
732570e0-c227-4faf-92f4-81c47a4f5256 | checkpoint | 2.3 Lot Size
6895d77b-e52f-5397-bfd3-85cd46241d6e | note | FREQUENCY: Check prior to placing material
f93df11e-f587-5e14-802d-b25a9085236c | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
359ed4be-b141-5781-a4fb-803fc0d4649c | note | REFERENCE DOCUMENTS: . Cl.304.08 (b)(ii), Table 304.111
db449a3d-08c0-57f1-8aff-a32996a1bb1a | note | INSPECTION/TEST METHOD: Site Inspection
a2b17f3c-55cc-5d3e-85bc-c68e2c0aafc8 | note | RECORD OF CONFORMITY: Signed ITP, Delivery Dockets
2ad7f3d6-2a69-5bac-8945-8efb8833253c | note | IP
e5e6f872-9d1f-590c-b34f-4dc363e4d158 | note | RESPONSIBILITY: Site Engineer
115248c6-ff29-5e60-bc18-1eed1195b6d8 | textbox | Date Completed:
da071c42-9c42-48bf-bf70-395a722689d8 | checkpoint | 2.4 Layer Thickness
bbe7f996-3765-5d01-a5a7-0362f259b410 | note | FREQUENCY: Each Lot
2b9320fe-a07b-5c2f-8365-d061b0d27712 | note | ACCEPTANCE CRITERIA: The maximum thickness of any pavement base layer shall not exceed 150 mm and the maximum thickness of any subbase layer shall not exceed 200 mm. The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
edd6d438-41a7-5bce-9dc4-f1fb7ca4c5a1 | note | REFERENCE DOCUMENTS: Cl 304.08(b)(v), Cl 304.08(b)(vi)
ef94d19e-baf8-5227-a39e-34a15562e122 | note | INSPECTION/TEST METHOD: Site Inspection
0ff53975-b1e0-5863-9f2c-fd23edce4c8a | note | RECORD OF CONFORMITY: Signed ITP
b066a964-f44f-5c42-9f2a-e90571d14c56 | note | IP
a9cfc242-1ce2-5c07-9e27-d1c68a565071 | note | RESPONSIBILITY: Site Engineer
1c34e24b-18ec-5557-9a0b-cc4bb6a652ee | textbox | Date Completed:
48bc5ea0-d7b3-4bc5-a355-98efc6bde36e | checkpoint | 2.5 Proof Rolling
8c60b80f-b382-5aa0-9a77-c7f504ca4db3 | note | FREQUENCY: Proof Roll each layer
bd423bfc-27fa-5358-9876-93cfb21aa810 | note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
6b6fb992-fad1-5ea0-a1dc-f8d8b616c188 | note | REFERENCE DOCUMENTS: 173.03
bc9af1ac-370c-5482-afcb-bcf1a06997bb | note | INSPECTION/TEST METHOD: Visual inspection
dfe5f6b4-cb8a-53e6-8c4a-64407060a55b | note | RECORD OF CONFORMITY: This ITP signed off
b04ea5f5-8ffa-5d7b-bd23-f8671301a610 | note | HP/ WP
808c92f3-8f45-5d6c-aac4-926b505bf46f | note | RESPONSIBILITY: Site Engineer & Superintendent
7850def6-b6d9-572a-8ee8-74ecca3800c0 | textbox | Date Completed:
e409077f-a471-4795-b0d2-5f0c66a1f0e7 | signoff | AUTHORITY HOLDPOINT
9f176b8c-d542-466a-9418-394f1a48bca3 | section | Testing Requirements
a83df950-a200-4314-963f-bf246060555d | checkpoint | 3.1 Determine Testing Scale & Initial Testing Frequency
9e9c365d-1a19-5a5a-a68e-d632e8a8f06c | note | FREQUENCY: Prior to Testing
4d981c16-67ae-594c-a3ac-d1a65b099853 | note | ACCEPTANCE CRITERIA: The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification. Testing of every lot shall continue until three consecutive lots of like material and/or work have achieved the standards specified.
50d5cee6-ad7a-52a4-b730-fd7e913a3a5c | note | ○ Scale B - The first lot of each pavement course shall be tested for post-compaction grading and PI. If the first lot each pavement course satisfies the specified post compaction requirements in Clause 304.10(a) and (b), as applicable, no further post-compaction testing will be required for that pavement course.
c0d48b37-6bbf-5846-ad86-c676702be8bd | note | REFERENCE DOCUMENTS: Table 204.161, Cl.304.08 (a), Cl.304.11 (b), Cl.304.11 (c)(i), Table 304.111
09fb3c50-732a-59b1-a524-f952d2135b6a | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
16d1c4a8-ae88-5d59-b6a0-18856e2123b9 | note | RECORD OF CONFORMITY: Signed ITP
5decf77d-3fbf-5378-ab74-ff6d3477f394 | note | AP
2ad9c79d-f48c-5c69-929e-30e02fa86ac5 | note | RESPONSIBILITY: Project Engineer
777c5746-a805-5e2c-966c-5e5cea7951da | textbox | Date Completed:
429d4c05-40a3-41bd-9281-563c63b88b70 | checkpoint | 3.2 Compaction Testing
ace10d98-9d14-53e5-9659-c5e9ced968e1 | note | FREQUENCY: Every Lot
53ec24de-e5b9-5a69-a4fd-db4cb6c13068 | note | ○ Every second lot (reduced frequency)
6cf02c31-dfb5-52c0-83cd-89b5ccc7cdb2 | note | ACCEPTANCE CRITERIA: Minimum Characteristic Density Ratio (CDR) of not less than 98%, using Modified compaction effort.
e9e012fb-59e9-51c7-a796-b93012dfdafb | note | REFERENCE DOCUMENTS: Cl304.08, Table 3040.061, Cl 304.11 (b), Table 304.111
b56e5291-4668-5b92-b8ee-44adb0041a33 | note | INSPECTION/TEST METHOD: Test point
e4c96cdf-9d93-583a-bb47-06eb86408471 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
56fd5e54-85fb-563a-982c-1d87c20bd4f1 | note | TP
bc9a901d-79e3-5561-9105-f568e2dc8cdc | note | RESPONSIBILITY: Site Engineer
4647a442-8dfc-5a97-8574-22b62e0eae7c | textbox | Date Completed:
3e27632d-8422-4cf1-b7a9-e53e1a327c33 | checkpoint | 3.3 Compaction Testing (Small Lots)
3888b730-7ab0-5285-af47-1d72e09cc155 | note | FREQUENCY: Each Lot
c388d21a-f07a-5e63-9aff-8c10186725f9 | note | ACCEPTANCE CRITERIA: Any lot which has a surface area less than 500 m2 may be treated as a small area. Acceptance of the lot shall be based on the mean values of 3 individual tests. Minimum Compaction shall be 100% modified compaction effort.
08605128-da6b-5e84-8748-959769d665e5 | note | REFERENCE DOCUMENTS: 173.04 d
20fe466e-0637-5ec9-8693-304f72eb6816 | note | INSPECTION/TEST METHOD: Test Point
3d36e1a1-5d07-5c1c-861f-1cd02c594fe0 | note | RECORD OF CONFORMITY: Test Records, Lot Register
282eeb77-36d7-562f-8ebd-04b25fcd4fdc | note | TP
675d84f2-3817-5f08-a632-3ca7213f273c | note | RESPONSIBILITY: Site Engineer
205596a7-8726-56dd-8d39-cc6cca18a756 | textbox | Date Completed:
fe4ba624-2907-48cd-94ca-760bc5bf6244 | checkpoint | 3.4 Material Grading - Post Compaction
74afa116-c7fe-530f-83d5-5df2bd3f87e6 | note | FREQUENCY: First Lot Only
a00ee3c4-4b60-5bab-b1e3-a40c20591628 | note | ACCEPTANCE CRITERIA: Post compaction material grading results must comply with the following:
a1d90346-2c05-56b5-922c-1eb2e7b76705 | note | ○ Class 4 - As per Table 304.101 - VR Spec. 304.10
f2dc558e-0de8-557d-98ea-e75723a2c4af | note | ○ Class 3 - As per Table 304.101 - VR Spec. 304.10
74517ea7-6d0e-5b5f-b3ab-9414ede2f44f | note | ○ Class 2 - As per Table 304.101 - VR Spec. 304.10
f0257e68-bdb6-5151-a14a-cc2351486f41 | note | REFERENCE DOCUMENTS: Cl 304.101, Cl 304.111
13da5502-0d4d-5e6a-b017-44c409646909 | note | INSPECTION/TEST METHOD: Test point
623e87c8-c604-57f0-85f1-92ea4295122d | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
eef84454-fd6a-5cdc-bf70-77aab583cb30 | note | TP
7b117bfd-7ae6-5744-96f3-2403bd3cef80 | note | RESPONSIBILITY: Site Engineer
70cfc13b-02b7-57a0-8fb0-eb42ac01515c | textbox | Date Completed:
8562c8e9-37e2-43f6-960b-76f257954363 | checkpoint | 3.5 Plasticity Index - Post Compaction
9c388a3d-e2d9-5810-8e93-fb58d8c9c109 | note | FREQUENCY: First Lot Only
e55615bb-5720-5758-9e5c-2b84ca8f993b | note | ACCEPTANCE CRITERIA: Post compaction PI results must comply with the following:
8774073d-9468-5957-95df-f4bfe73c2e07 | note | ○ Class 4 - 0 to 10
e8df6685-922e-5876-a749-6f212a8da3f3 | note | ○ Class 3 - 0 to 10
e3533b3c-6a98-5740-bb22-9e424be48af3 | note | ○ Class 2 - 0 to 6
8bc35624-973f-51eb-93f1-16095eadb6fa | note | REFERENCE DOCUMENTS: Cl 304.10, Cl 304.11, Table 304.103
b184257e-b705-50ba-bfa4-8d3f8db90668 | note | INSPECTION/TEST METHOD: Test point
63840935-c65f-588f-8dc3-276a5758ca64 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
e2e6f44b-c4a0-50a8-8069-2f0e1a9f03c5 | note | TP
7d1cb792-d255-5ecc-87f6-b2ee295b473c | note | RESPONSIBILITY: Site Engineer
75db86c2-94be-5874-bc3f-405be8270097 | textbox | Date Completed:
16083033-4fe7-457f-aeec-3ccc82fd69d8 | checkpoint | 3.6 Survey Conformance
f722b0f7-997d-55af-a678-19b1c7780edc | note | FREQUENCY: Each lot
8aee165a-b6c1-5e61-baf5-92b6a52d501c | note | ACCEPTANCE CRITERIA: Layer to be finished to a smooth and uniform surface and after compaction shall conform within the following limits:
ad936f9e-46a6-5e66-96b7-61083519d3e9 | note | ○ Shape: no point deviation > 8mm from 3m straight edge in any direction
62c9e014-60cb-5a2a-9fa2-c4e5599fb632 | note | Surface level tolerances:
872c2233-a9b0-5089-b51e-9a7fc4ef51cd | note | ○ Range x = +6, -16mm
d732faf1-9eec-5e60-a36f-6f9daf059e04 | note | ○ Max S = 15 mm
9da56ab3-ba4c-5a86-9e22-5db72504cde5 | note | ○ 40 measurements per lot (Minimum)
3878dc99-394e-5ec3-a388-3935f90ffe15 | note | REFERENCE DOCUMENTS: Cl 304.06(b, d, i) Drawings, Table 304.062
b187ad19-7e17-57b9-852f-91f0bb9cfe09 | note | INSPECTION/TEST METHOD: Survey
ec671419-a62a-5fa8-87ba-c0959213ed73 | note | RECORD OF CONFORMITY: This ITP signed off; Survey Report, Lot Markup
a0b5a56f-0f26-5bad-a6eb-94c6c683e6c3 | note | SCP
6e9ae91b-83de-544f-a86f-3b27b6991d76 | note | RESPONSIBILITY: Site Engineer/ Surveyor
c61e8645-09a8-5737-8ec1-cc9a8a22b760 | textbox | Date Completed:
12678b72-28c8-4766-af08-b9282333309f | checkpoint | Final Inspection
26d6c64f-ae93-56e4-b8e9-28c8d72e7825 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
03881947-33b9-595b-8a45-45495d17fe92 | textbox | Print Name:
7bf4fb3b-9074-5132-94e3-27633a3ee0e4 | textbox | Position:
bced842a-5dcb-523e-983a-30765c1a570f | textbox | Date:
1ba82ebb-0fff-4b5d-8ab1-9d08b6ea1ce4 | checklist | FHC-ITP-008 - Stormwater Drainage Rev4 | itp | FHC-ITP-008 - Stormwater Drainage
0323b18d-bc0f-4953-821d-b1b34a459d27 | section | Preliminary Works
3206aaa8-ef18-4b33-8794-ce0729789aee | checkpoint | 1.1 Check for correct documentation
12cd034e-b08d-5503-9baa-1be979a7ef17 | note | FREQUENCY: Prior to commencing any activity
ce682ea7-f8e2-59dd-befb-7caa8a389342 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
4bb80004-4f37-5cf4-927c-12b98fd67c66 | note | — using the correct and complete set of drawings
1544e48f-adfa-5eb1-af2d-3b998fbfd6b7 | note | — All drawings are the latest revision
3227f941-f13d-52b1-8234-ab64c3c1e924 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
4b676669-c666-531d-95ca-e53f7b5ba029 | note | INSPECTION/TEST METHOD: Visual inspection
74f1fad9-49aa-57a9-abf1-2e81b7fe471d | note | RECORD OF CONFORMITY: This ITP signed off
fc14e9b2-90e4-5876-a1b4-e59d6b8cf465 | note | HP*
13aac310-88d5-5007-a098-72bf5ac1326a | note | RESPONSIBILITY: Site Engineer / Site Foreman
171c857c-6ebc-51a0-8731-aa07a8bf7108 | textbox | Date Completed:
c1f5950c-ea87-4e3a-a66b-2f48a9a7a726 | checkpoint | 1.2 Implementation of all measures and controls
60a3b871-7d68-5ca7-a9fc-f799350c81d2 | note | FREQUENCY: Prior to commencing any activity
f7f406b8-df80-5143-aa1a-0ba7dc189590 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
3b6a9fd2-ff76-58f1-9b60-3ee6eb45581c | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
4b8bb032-12f3-533a-81de-0ba2806f2a46 | note | INSPECTION/TEST METHOD: Visual Inspection
69a3a1c5-ac41-5ff1-b35d-57a04372cfe6 | note | RECORD OF CONFORMITY: This ITP signed off
38781685-14e4-5bf4-bc14-01bb2a6f3c24 | note | HP*
0d673eff-a953-5d01-9350-ea520adb9a6d | note | RESPONSIBILITY: Site Engineer / Site Foreman
eae3fd66-ee18-580a-ab78-f9f228d301c7 | textbox | Date Completed:
76b40eda-2893-4e71-bc3c-3e5e38eadbbd | checkpoint | 1.3 Material Approval
c79d6d76-b03a-54fd-b620-a332f65271cc | note | FREQUENCY: Prior to Placement
097d0713-c3d9-5720-939c-d7b458f20b55 | note | ACCEPTANCE CRITERIA: Material intended for use is to be submitted to the client prior to placement to verify it conforms to required specifications.
0f017224-456c-527a-a5ad-2f6b21f1f17f | note | REFERENCE DOCUMENTS: Material specification sheets
12ec07aa-f237-57fc-a2c4-af76278995ac | note | INSPECTION/TEST METHOD: Verfiy
6b92121a-9b0b-53b9-a483-bc103c9fab21 | note | RECORD OF CONFORMITY: Teambinder Acceptance
e46b14a3-2698-58f8-bbc2-39e8f5c9236a | note | HP*
70eaf8fd-3ae9-5a8f-b513-47b73672ad50 | note | RESPONSIBILITY: Site Engineer
8ee6d3fb-659e-52ef-8cab-39361f50b30e | textbox | Date Completed:
2b6695fb-1880-45d2-854f-2de6f64f144d | checkpoint | 1.4 Precast Materials acceptance
f621b931-6316-5d22-b3ed-90dc6522d006 | note | FREQUENCY: Each Delivery
f3c62189-c7a8-5c06-87ff-35e1c871fca3 | note | ACCEPTANCE CRITERIA: Precast reinforced concrete pipes shall be accepted on the basis of full compliance with the requirements of this section and AS/NZS 4058.
8d2ac51a-c466-5554-a898-a6c6049b732b | note | REFERENCE DOCUMENTS: Cl. 701.05e
5634b392-a01a-50d8-92b9-c128a747305d | note | INSPECTION/TEST METHOD: Visual Inspection
034981b4-564b-5689-b712-fe8627b2457f | note | RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist
a7353f77-4c98-5e21-adc9-1f7047a99c68 | note | IP
1bd694cb-476a-59f6-8474-df272ef1cc24 | note | RESPONSIBILITY: Site Engineer
3cf11056-76e5-50ba-bd52-57fcb04a50b2 | textbox | Date Completed:
6d3385d5-25d5-46d9-8249-b0ce6882caaf | checkpoint | 1.5 Precast Pipe & Culvert Compliance
26bc120f-f9bf-59b0-8fe4-b571cb73cf51 | note | FREQUENCY: Prior to Commencing
eda80c47-f70b-586c-b185-7dbd4ae18be6 | note | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Box Culverts to comply with requirements of VicRoads Section 619.
94b55935-f135-5abd-8d17-ef99809485eb | note | ○ Precast Reinforced Concrete (Portland) Pipes shall comply with requirements of AS 4058
5c3c52a3-b87e-5894-a90f-f3bac15556a1 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.619, Cl. 701.04, Cl. 701.05(a), AS4058, AS4680
28942996-f117-5931-ab9a-7c04823f2ddc | note | INSPECTION/TEST METHOD: Document review & Site inspection
9717f318-8cdc-56ff-af1c-39add0eadd6d | note | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
d2b9ccca-a46f-5f9c-a94b-b08b08c15d92 | note | IP
d0c9f2e5-94ae-5d01-b533-e97efeb8ac23 | note | RESPONSIBILITY: Site Engineer
ed0b9e28-3a9a-5537-82a2-c7a8162787ed | textbox | Date Completed:
b4629ea2-4a35-491b-b227-eb5954ef79a7 | checkpoint | 1.6 Precast Drainage Pit Compliance
dc10240f-4174-52fa-a766-a8205153f9a1 | note | FREQUENCY: Prior to Commencing
ecb286ca-75d9-5200-a2fc-732a4ab6930e | note | ACCEPTANCE CRITERIA: All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 610.
27c00ff2-f1cf-5c77-931c-ab8feb5acce0 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.610, Cl. 705.04, AS5100
bfa9f059-2fea-5aa1-8360-56aa0e7166e1 | note | INSPECTION/TEST METHOD: Document Review
0f563fc7-ff26-513e-b8fa-1dc1093520ee | note | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
d930973e-1763-55f4-bfbf-3d295f33c0ab | note | IP
b7ce9651-28c6-516b-ac16-22dab2190574 | note | RESPONSIBILITY: Site Engineer
27b214f6-bfd6-5c21-b25a-5a5bc901dfa3 | textbox | Date Completed:
53c8dd9e-9175-46ae-baa2-e26f7a2b4d22 | checkpoint | 1.7 Bedding material classification
3f415a86-8bae-5ec7-af16-3aa356fad477 | note | FREQUENCY: Prior to start
899f7152-d7f2-557f-9331-6a2e2be30ff2 | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the requirements of Table 701.091 and Table 701.092.
120e7d91-1ee9-545c-b4e9-e57f2646a406 | note | REFERENCE DOCUMENTS: 701.09(d), 701.091, 701.092
4a7ed19c-5ce5-5c6e-8d42-91250a695f85 | note | INSPECTION/TEST METHOD: Verify
92098564-faca-5e56-a85e-9dc778fecc32 | note | RECORD OF CONFORMITY: Test Reports from supplier
58049170-9c0e-5f92-a04d-1591cf2408ea | note | TP
6e7df7c3-210d-5401-8d0f-83c863a78766 | note | RESPONSIBILITY: Site Engineer
38b9c519-4573-5086-948d-bda235a7de4f | textbox | Date Completed:
fbbcbb46-23c8-4aea-bea9-aa0672b40205 | checkpoint | 1.8 Backfill material Classification
58ba0c77-d8c7-5ea9-bf02-edbb56f6222b | note | FREQUENCY: Prior to start
c8c00ef3-d8e1-50f4-8035-86960b18cebb | note | ACCEPTANCE CRITERIA: Ordinary backfill shall be free from perishable matter and shall conform with the requirements of Table 701.091.
04974a1c-cc4c-517d-8d1d-ebe757ad2459 | note | REFERENCE DOCUMENTS: 701.09(d), 701.091
ebb35331-da0f-568b-8ba6-ef5b443815b8 | note | INSPECTION/TEST METHOD: Verify
1ed7e048-a8d6-5800-babb-8d66bac26559 | note | RECORD OF CONFORMITY: Test Reports from supplier
88b512ab-8455-537d-aa15-ef91b76cc631 | note | TP
f1a20971-22bf-5421-8a09-ed450c63e7e6 | note | RESPONSIBILITY: Site Engineer
437cac8d-a30a-5154-a8bb-8fea1ed59d11 | textbox | Date Completed:
98b9ee4e-80d0-4ebc-bb99-5c9aac6eee63 | checkpoint | 1.9 Mortar material classification
c8cbeebf-1378-58b9-8f44-97701abc287f | note | FREQUENCY: Prior to start
422fce54-ff14-5aab-9335-9d50d9ce05f0 | note | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
c99d0701-2dc8-5819-becc-ab29a6869c15 | note | REFERENCE DOCUMENTS: 610.33
78bd917a-5279-51ec-9cfe-b9d10d5b162e | note | INSPECTION/TEST METHOD: Verify
e07611f5-87b4-5845-b696-978658d25cbb | note | RECORD OF CONFORMITY: Test Reports from supplier
b81eb81b-504f-5cf1-b5fc-c603b10f7660 | note | TP
a91b771c-e612-5027-832a-82c453fd82e8 | note | RESPONSIBILITY: Site Engineer
81c6c037-f233-5d4b-8b50-7158a7baa86b | textbox | Date Completed:
097384fa-80f7-47f6-a5ce-4cee03b86c78 | section | Construction Works
4b310f09-8334-4716-a875-05349c519a8b | checkpoint | 2.1 Excavation Permit
38d1dada-ccb0-538b-9698-9d177bf5b937 | note | FREQUENCY: Each lot
dd64623b-055c-575c-9789-2b3d5560b07b | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
2c0bc5c0-8087-5308-ab42-d61a70b3869b | note | ○ Plant and equipment shall be appropriate for the task.
5ad1d3bc-06a7-54f5-a5b9-02a6f1579c1d | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
e2382ba7-d290-5203-905c-e6399df95b48 | note | REFERENCE DOCUMENTS: Excavation permit
21decc72-266f-59d0-8ca7-732034411610 | note | INSPECTION/TEST METHOD: Verify
1a871ba5-8f40-5948-a0cb-0948436f9569 | note | RECORD OF CONFORMITY: ITP Signed
b2248766-d816-546d-8a2f-ecbd2a7c4aa7 | note | HP*
089dc62d-eb99-5b01-afbb-e63541cca584 | note | RESPONSIBILITY: Site Engineer
682d0fbf-0e7b-5d45-9a9f-26bb2f670515 | textbox | Date Completed:
aeef387f-ecf9-4018-8020-5b1e9fbf4094 | checkpoint | 2.2 Set out drainage
effa8b41-befd-5569-9b02-7b563db8a37f | note | FREQUENCY: Prior to backfilling
cf7b77c4-9919-545a-824a-5b5beb0de26c | note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
7841df94-3e92-5031-8aa3-8983de4080bd | note | REFERENCE DOCUMENTS: Drawings 701.10
adf4e20e-5026-5b99-ab02-64f5d47415de | note | INSPECTION/TEST METHOD: Visual Inspection
7b580461-453c-5892-97b7-1423a0c5610b | note | RECORD OF CONFORMITY: ITP Signed
25f9afcc-2e71-58d2-be4e-6079a1f3787f | note | HP
5a7f4d15-e7d0-55f0-8a4f-043df282ebc6 | note | RESPONSIBILITY: Site Engineer/ Superintendent
ca535a24-2064-5a42-aca2-709493761e03 | textbox | Date Completed:
0c385601-047e-4dd2-96b3-4fb3210d1b46 | signoff | AUTHORITY HOLDPOINT
786a05b5-e98e-4ce7-a7bf-2878f71b3dbf | checkpoint | 2.3 Excavation (pipes)
ff461ab1-ae55-5715-b888-e81f08de6ca0 | note | FREQUENCY: Each Trench
e1ea99f3-9516-5f9b-a82e-9ca2c07424be | note | ACCEPTANCE CRITERIA: Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical
e49650d1-1937-5fb1-84d7-a464c598446c | note | Depth of trench:
123c1324-b6f6-5a0c-91fe-bf91fc9f9eeb | note | ○ > 100mm below underside of pipe (for pipe width < 1500 mm)
5c4dcbe7-bf1f-5a3e-9f5b-d30e1a2b920a | note | ○ > 200mm below underside of pipe (for pipe width > 1500 mm)
c7aecf4e-8172-53d5-926f-ad6badc06ca6 | note | REFERENCE DOCUMENTS: 701.151, 701.15
4ccf6bc3-8f4c-55ae-982f-e1ed83f44235 | note | INSPECTION/TEST METHOD: Visual Inspection
3afae4e2-d3fe-5f9e-a128-c8108627b85d | note | RECORD OF CONFORMITY: ITP Signed
749aebf1-3b17-53f8-b221-b0d66977cde3 | note | IP
69299373-fc73-51ee-92ce-02b32e7683c8 | note | RESPONSIBILITY: Site Foreman
152cacef-576d-5ac9-a03c-af2e70997cd8 | textbox | Date Completed:
739aaa71-d82b-46fe-addf-d1236c4b8512 | checkpoint | 2.4 Excavation (pits)
d8d4c0d5-3aaa-5710-a461-9efe7914742d | note | FREQUENCY: Each Pit
9bb94559-e1cf-5eb8-a629-2bce4b226a8d | note | ACCEPTANCE CRITERIA: A minimum clearance of 400mm is required around the external faces of precast pits.
5027b298-df37-5773-894c-5900cd4ef21f | note | REFERENCE DOCUMENTS: 705.05b
18e53f72-089c-53e1-b1a3-f1d51d256a1d | note | INSPECTION/TEST METHOD: Visual Inspection
a4ef55a8-cbb2-5e4f-ae4f-168910b6b5f7 | note | RECORD OF CONFORMITY: ITP Signed
1cb1449a-5a3d-5192-9615-1a2093e1c7b2 | note | IP
8dc4663c-2295-5ba3-83ad-9f0c34fcdca2 | note | RESPONSIBILITY: Site Foreman
b8d650c5-e257-566b-9fc0-105543bcfa8c | textbox | Date Completed:
6dec8869-0e2d-491c-902b-99d723fa710c | checkpoint | 2.5 Compact base of trench
fc1e0735-ebcc-5b61-80b2-2a136862294d | note | FREQUENCY: Each Trench
af528aff-f64d-5c38-abb5-36112d23d689 | note | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
81f42a74-eeb0-5193-bcb9-5b5c1f0e67de | note | REFERENCE DOCUMENTS: 701.15
22b849d5-1918-598e-895f-65d973b7f182 | note | INSPECTION/TEST METHOD: Visual Inspection
22eb1a42-44b1-5d36-b161-51ef49001a15 | note | RECORD OF CONFORMITY: ITP Signed
10c4fe29-acce-5a05-bb2f-98ba351236c4 | note | IP
ed9f122e-5d7a-5c9d-b1af-f3f1c061dbc6 | note | RESPONSIBILITY: Site Engineer
e00687d9-8c14-528b-a9fe-7b857e1554a8 | textbox | Date Completed:
ef6475c3-b631-4c17-9f8b-cb0e88c87dad | checkpoint | 2.6 Place bedding material & compact
c1d1e7af-0700-567c-af06-590ae4503782 | note | FREQUENCY: Each Trench
9092b16e-5f25-595c-a9e2-391576f6b735 | note | ACCEPTANCE CRITERIA: Bedding and backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
41008227-09f3-5964-9fe2-8a060cfe3b21 | note | REFERENCE DOCUMENTS: 701.20, 701.20a
6c8705dc-edd4-5c57-b887-b6f3077c5b48 | note | INSPECTION/TEST METHOD: Visual Inspection
7c9ef05c-2a80-5f8b-83c6-5c3addd43f34 | note | RECORD OF CONFORMITY: ITP Signed, Delivery dockets
9efa4b8e-fa3d-5254-be6c-1ca592ee296e | note | IP
286d118e-c399-57c2-96ac-ec6513eb50f8 | note | RESPONSIBILITY: Site Engineer
908a5be7-932f-5e9a-bcf6-9e90db41608d | textbox | Date Completed:
3461b0a2-b446-44cc-9e13-b2fc9c258a51 | checkpoint | 2.7 Place pipes & precast pits
2811d693-bc07-5105-b1d5-ecbadaf797d7 | note | FREQUENCY: Each Line/Pit
698fbff7-cb40-5d80-a122-9db0df706dcf | note | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied
9d46a27e-018c-5b6d-a5de-3fe08ddbfe4c | note | REFERENCE DOCUMENTS: Drawings
46d4fcd6-e6f6-50cf-8b03-0f32ef9effa3 | note | INSPECTION/TEST METHOD: Visual Inspection
935c14f2-3207-5f47-819b-871a131c82bb | note | RECORD OF CONFORMITY: ITP Signed
2aef6faa-ebfd-5cb2-a354-a9eba8eb8bdb | note | IP
d3380ab8-281e-5e22-8fbb-318036bb4904 | note | RESPONSIBILITY: Site Engineer / Site Foreman
cbd1a0fe-debc-5fe3-8782-425ec94b97e5 | textbox | Date Completed:
b499724a-b6b4-43be-850e-afa33f36f861 | checkpoint | 2.8 Jointing pipe sections
5850d371-a1c5-594f-88dd-9297d85b76f2 | note | FREQUENCY: Each Line
d2f8c9a5-5bf8-5b8b-b7f5-4ed885f52991 | note | ACCEPTANCE CRITERIA: All interlocking (flush) joint reinforced concrete pipes shall be mortar jointed, or wrapped with a 200 mm wide external joint rubber band.
191a1162-cc74-5e44-ab91-b3ed2d173acb | note | REFERENCE DOCUMENTS: 701.18
36e6c042-cc98-5f74-9a9d-e6f234dd346d | note | INSPECTION/TEST METHOD: Visual Inspection
00a85497-00cf-556e-97df-aa90a93ab7d5 | note | RECORD OF CONFORMITY: ITP Signed
5556a1a6-7b79-51a1-9ccc-7ed4d88f242d | note | IP
d5d788f2-f613-53d9-8d79-e98287f397f4 | note | RESPONSIBILITY: Site Engineer / Site Foreman
a5fc504d-fffa-5d52-a61e-79946f81c219 | textbox | Date Completed:
5aaa4332-8ac8-468e-ab29-61b9ebf723f1 | checkpoint | 2.9 Sealing - for joining culvert sections and pipe penetrations in pits
1abf485d-67b6-589a-9edb-32dfa3ee45c4 | note | FREQUENCY: Each Pit
f06b6cde-a6a1-53d1-b8b5-e322f62acab3 | note | ACCEPTANCE CRITERIA: Contact areas between top and bottom sections of box culverts to be mortared. The joints between various components such as drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar in accordance with the requirements of Clause 610.32.
0f08ad6e-e6a2-5a8e-b7b0-426f8b0c6b44 | note | REFERENCE DOCUMENTS: 610.32, 701.17c
29e92322-2977-5da3-8ade-2bdaa5fb713b | note | INSPECTION/TEST METHOD: Visual Inspection
9850e30c-8ad0-5e1b-840f-a40bbb697df4 | note | RECORD OF CONFORMITY: ITP Signed
b4927a0d-dcc5-5446-be01-4c4c95963013 | note | WP
0f24e10d-5051-5e67-82c0-70bf7572fecf | note | RESPONSIBILITY: Site Engineer / Site Foreman
6f104f96-ecf2-557a-af66-6fb2e42681d3 | textbox | Date Completed:
a3755060-a98b-4e1a-9c11-64f6ff089883 | checkpoint | 2.10 Survey of laid pipe or pit
b259e010-bc25-5039-820a-9e6d51bea6bf | note | FREQUENCY: Prior to backfilling
d2f97acc-ecbf-5053-a1ba-87f3f4ee4bee | note | ACCEPTANCE CRITERIA: The location of each run of drainage has been verified prior to backfilling and conforms to the following tolerances: (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
604fe57c-c799-536a-968c-899b5d4ef07b | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
27521048-0c0e-538f-b83b-efc39998a4e3 | note | (c) invert level of pipes at pits ±50 mm
df2c51ad-2e65-50a9-a63e-6ddc90fccf2c | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
9f7781ba-bec0-5630-b8f0-0502117aab42 | note | REFERENCE DOCUMENTS: 701.1
85eaf56f-b544-5ffa-9c2e-13138381d702 | note | INSPECTION/TEST METHOD: Survey Conformance Point
078a4da4-8ac9-5345-bf53-cae12d6210c2 | note | RECORD OF CONFORMITY: ITP Signed
153fff7d-2c61-523f-9979-2086e3576b90 | note | SCP
77b74b7b-8415-58b1-8948-60656e051ef7 | note | RESPONSIBILITY: Site Engineer/ Surveyor
555e07ec-9569-5ef2-8a50-da7c2630d31a | textbox | Date Completed:
838cb740-c34f-4581-acab-bbf8cf6203f0 | checkpoint | 2.11 Haunching & compaction of bedding material
9207b57f-c4e6-547f-9b61-cb9488489562 | note | FREQUENCY: each lot
6343ad99-76de-5336-aeb8-19bba9ca5cb0 | note | ACCEPTANCE CRITERIA: Height of additional bedding material = 30% of nominal pipe diameter or culvert height.
9812f5cc-346f-59ee-a4a6-b0799477261b | note | ○ Loose layer thickness <=150mm
91fb1a24-2a22-5333-be51-a1d7ba71321a | note | ○ Compacted to refusal using hand held mechanical equipment.
c3d4c549-1805-51ac-9884-521380da7631 | note | ○ 1 lot = 150mm layer
a9e61df0-30be-5c85-b480-c95411900db7 | note | REFERENCE DOCUMENTS: 701.16, 701.20
ff3be8e2-ce0b-549b-94fd-5870244945c7 | note | INSPECTION/TEST METHOD: Visual Inspection
6313ce58-64b3-5ba5-9c7e-ac920ea27a6a | note | RECORD OF CONFORMITY: ITP Signed
cd89ee86-82f0-5a15-8670-2e29ce019475 | note | WP
ce642508-0fc9-5936-a14f-8614899a0343 | note | RESPONSIBILITY: Site Engineer / Site Foreman
998528ee-f9c6-5ea7-bffa-91cbd7f7c827 | textbox | Date Completed:
8e7716a6-0a4c-4e84-b8cf-ee46b2d1fc32 | checkpoint | 2.12 Place & compact backfill material over pipes
3b99f0fb-f9fa-5453-a84a-38c584f1a973 | note | FREQUENCY: each lot
6e741a82-7bf2-5817-bb70-c834953a24e5 | note | ACCEPTANCE CRITERIA: Backfill under paved area:
39defeda-ddab-5385-a010-10653575f871 | note | ○ fill trench with selected back fill material to subgrade level
b400f190-2026-5c76-b836-ad9e76a9fcf7 | note | Backfill under area not paved:
ef81e81f-8253-5251-98ce-ab633b7eaf96 | note | ○ Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level
8b7939d7-3c9e-5684-aafb-6d3998c40203 | note | ○ Loose layer thickness <= 150mm.
73ca1dba-bf00-524d-b314-9c933f744873 | note | ○ 1 lot = 150mm layer
d6f3c285-42a1-5454-b7c6-1148d00bb47d | note | REFERENCE DOCUMENTS: 701.19, 701.20
338e318b-17cb-5da4-8f73-78c5edd1b868 | note | INSPECTION/TEST METHOD: Visual Inspection
72a1395b-ad8a-5e4d-9e13-efb3b2654f79 | note | RECORD OF CONFORMITY: ITP Signed
37797cbf-d409-5cc5-9ca5-6f0874f5bbd5 | note | IP
54737068-4905-54bd-ba11-1efd57296aba | note | RESPONSIBILITY: Site Engineer / Site Foreman
15f53add-bc50-5826-b2a2-5f5a77acd006 | textbox | Date Completed:
1d1a9bf3-c548-4bcb-88e3-0c5b7dbf6099 | checkpoint | 2.13 Place & compact backfill material around pits
29b7df1c-9839-52c0-b708-946d8d68dc54 | note | FREQUENCY: Each Pit
c9c782b9-87c3-5828-b77e-f5f3b48bbccf | note | ACCEPTANCE CRITERIA: Loose layer thickness <= 300mm.
db5622ef-c9e7-5cda-893e-2cdb47ef4fac | note | ○ Compacted to refusal using hand held mechanical equipment.
caf9f3a4-9704-52bb-92b9-b285c20c182a | note | REFERENCE DOCUMENTS: 705.18
590fad67-36eb-5f0e-963a-7e190f530d84 | note | INSPECTION/TEST METHOD: Visual Inspection
5cf14f8e-cafa-585d-94d2-0f508990104d | note | RECORD OF CONFORMITY: ITP Signed
93b20e50-d847-59fd-9fac-dfcc9ed31e61 | note | IP
0c0d1b59-61b7-551e-be7e-c88f3fc361d8 | note | RESPONSIBILITY: Site Enginer
811d7658-4a5f-561e-9ace-f285a2846fa4 | textbox | Date Completed:
04a7724e-131e-4dcc-bb43-ff5dfced9d41 | checkpoint | 2.14 Backfilling with cement stabilised sand
4aea0452-ed06-5603-a7ba-ffbd63f303bc | note | FREQUENCY: Each culvert
715b29a5-dcad-54f5-8d76-a8eabb8063a5 | note | ACCEPTANCE CRITERIA: Where approval is given from superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% stabilised sand with a water content sufficient to ensure penetration beneath the pipe or box culvert invert without leaving free surface water.
98be991b-d1f3-574a-b616-5bbcb98b91d8 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.19(a)
01b66f6e-283a-58a5-b4a0-d99b17b88da0 | note | INSPECTION/TEST METHOD: Site Inspection
753d1cc2-02fe-54ac-89ad-6f116696798d | note | RECORD OF CONFORMITY: Superintendent approval, ITP signed
f1e02802-ae97-5b48-ba0d-678479d857b9 | note | AP
2a880682-8a11-530f-a54e-ff55996929f7 | note | RESPONSIBILITY: Project Engineer / Superintendent
cd6be0e6-5a5f-5655-bb00-7f7af1367e8f | textbox | Date Completed:
0bf328ac-ab50-41ab-8d10-c6de64bcb725 | checkpoint | 2.15 Install step irons
00c1092a-6004-5790-9605-5a2a3d94dcac | note | FREQUENCY: Each Pit
67da3538-d726-53b4-9c42-539c7b4e8fab | note | ACCEPTANCE CRITERIA: For pits > 1m deep.
fe1b31c9-6620-51ea-8522-fc062d0bda1d | note | REFERENCE DOCUMENTS: 705.12
b57ae776-3569-54da-b96f-b21688fb0a80 | note | INSPECTION/TEST METHOD: Visual Inspection
a533b899-f229-5537-a019-bfd4ad023e0c | note | RECORD OF CONFORMITY: ITP Signed
814ea119-2cc8-5f96-9308-ac817d656db2 | note | IP
a40be612-32ef-55e4-a92b-a03cb98c06fe | note | RESPONSIBILITY: Site Enginer
a6dfe365-9bf2-5fbe-b191-a1316b274ab7 | textbox | Date Completed:
3d0acb72-05df-4f81-9350-3eff01a38cbb | checkpoint | 2.16 Pit base shaped with concrete to match pipe invert
cd3d01c8-0719-5f46-ad23-00b8e1fb4273 | note | FREQUENCY: Each Pit
1852b761-4f95-543c-abae-255c82f64dd6 | note | ACCEPTANCE CRITERIA: As shown on Standard VicRoads drawing - Pit & Pipe Invert levels SD 1002
3f2923f4-a0ca-54c4-bc19-ea0769e56ad3 | note | REFERENCE DOCUMENTS: Standard VicRoads drawing SD 1002
4503f14d-1bdb-5e5c-b650-62b89505313e | note | INSPECTION/TEST METHOD: Visual Inspection
4afba817-5941-5899-bd02-68ff3529db7f | note | RECORD OF CONFORMITY: ITP Signed
abfd95d8-cc29-5328-942d-e1220998b57a | note | IP
c70c008d-623b-55b1-a828-80d5f3dd2e3d | note | RESPONSIBILITY: Site Enginer
8d0eba74-57ea-59bc-974a-700ded585985 | textbox | Date Completed:
39e654d1-7ecc-4b14-ae74-82b49a405300 | checkpoint | 2.17 Place pit covers
29087dc5-344a-5886-ae3f-97a87e5bd378 | note | FREQUENCY: Each Pit
d8873f45-372e-573a-91b1-dab22b4afc04 | note | ACCEPTANCE CRITERIA: Covers must be set to within ±10mm of the design levels shown on the drawings
ccb501d5-b7a8-56cb-b283-2f4ca11f9bd3 | note | REFERENCE DOCUMENTS: 705.17
3ffdb033-8a17-5a56-8d88-01121c900104 | note | INSPECTION/TEST METHOD: Visual Inspection
f6f902c1-ba1b-5208-8daf-486b2e285f30 | note | RECORD OF CONFORMITY: ITP Signed
5d98c23a-b387-521d-8c74-3e25f83695c1 | note | IP
48107849-ec53-58e5-9f5a-c690178f3df0 | note | RESPONSIBILITY: Site Engineer / Site Foreman
a549f82b-efe0-588a-945a-bcfdf63e84e5 | textbox | Date Completed:
953f8b1f-2b2b-4c1d-991e-ec75bdce3dc1 | checkpoint | 2.18 Repairs to damaged pipes and box culverts
354067a4-05dd-5200-94f9-7d6935e78d38 | note | FREQUENCY: Each damaged pipe or culvert
e620e39b-8ec7-5b72-8a36-7a661ff10cc9 | note | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the superintendents approval of the repair materials and procedures
f5ca672e-0962-5cac-8a76-61cc95fd7e6e | note | ○ All repair procedures undertaken in accordance with Cl 701.25
3b02e5cd-3d16-587d-8e6b-2012d492d8bf | note | REFERENCE DOCUMENTS: 701.31a
66e1acc5-c7d6-53a0-9d18-d22cddac00a3 | note | INSPECTION/TEST METHOD: Verify
2eb340a0-a412-5921-9950-8f9c6c7754cd | note | RECORD OF CONFORMITY: ITP Signed
a98f8824-4f83-505c-8e07-1fe6238c0ded | note | HP
af118a65-ad7c-5980-89a4-fe1056777b2e | note | RESPONSIBILITY: Site Engineer/ Superintendent
d50dd29d-a507-5d91-8759-dc8af6bc472a | textbox | Date Completed:
d496303f-2ab2-415c-aaab-bbc81e815718 | signoff | AUTHORITY HOLDPOINT
fd4d12ec-3c27-4f60-baa9-978d88a71807 | section | Testing & Completion
449520be-35ab-4917-bcee-14983a345b2d | checkpoint | 3.1 Compaction and moisture content of backfill & bedding material
4b1b0c29-f665-5469-a774-121dec371d33 | note | FREQUENCY: at least 20% of all lots
a4c93c2b-3c22-5aa7-9426-4cf9c77c2f99 | note | ACCEPTANCE CRITERIA: Backfill material shall be compactied to a mean density ratio of 97% using standard compactive effort.
615cf3f3-91b3-52b2-8e64-25784d5aa2ae | note | ○ Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
a1154b68-e90e-5fec-b8c8-7c43dfec4a4d | note | REFERENCE DOCUMENTS: 701.20a, 701.20b
667fb5db-18db-5844-90df-13b2e58c4dbe | note | INSPECTION/TEST METHOD: Verify
28196f5f-017c-58be-a590-31c870dcd88e | note | RECORD OF CONFORMITY: Test Reports
ecfbb81d-83d6-5b20-9522-468df4a3ff35 | note | TP
45dbeb0e-1195-52dc-aec0-f603ceee1d03 | note | RESPONSIBILITY: Site Engineer
2216bc4d-ff02-5b5a-b4e6-a43b9353bfdc | textbox | Date Completed:
b59ea5b8-ed5f-46af-a01e-1ff6d87a7e41 | checkpoint | 3.2 CCTV inspection
c7bc81f5-6ce5-5322-b42d-60edd36c348d | note | FREQUENCY: each lot
97a85536-3e15-5e11-9b56-b22577e72be4 | note | ACCEPTANCE CRITERIA: All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
e53ba662-51f5-535d-addd-cc82b9d22e0e | note | REFERENCE DOCUMENTS: 701.3
2a4b5e79-2c4f-5d41-982f-3e13290b1fdc | note | INSPECTION/TEST METHOD: Visual inspection
68fc7886-2e98-50f5-8ff9-fad7e07a1be7 | note | RECORD OF CONFORMITY: CCTV Report
b8688f2e-65d6-52a1-ba97-36617d297de0 | note | HP
7fe1f774-4848-5ba4-99ce-26748e8b60be | note | RESPONSIBILITY: Site Engineer/ Superintendent
f4ba17a6-4860-5419-8be5-f864d6524661 | textbox | Date Completed:
8a80f1c3-0455-4f00-80bb-c679e6361abf | signoff | AUTHORITY HOLDPOINT
78592ad3-d626-449c-a448-d9fbb73a2352 | checkpoint | 3.3 Flushing of pipes
30906592-d6f2-54e6-aba0-98d97789f12e | note | FREQUENCY: Each line
62a7cbdc-07b5-5460-9784-9d1154ebfe93 | note | ACCEPTANCE CRITERIA: All pipes to be flushed clean upon completion
7de42450-687d-5986-b824-5c27b2ab2444 | note | REFERENCE DOCUMENTS: 701.28
784db615-2758-5359-8248-ed2105d81b60 | note | INSPECTION/TEST METHOD: Verify
13c10212-a479-597f-be0d-3b209672633b | note | RECORD OF CONFORMITY: ITP Signed
20db72d6-5370-5b97-8096-ccf646bc7cff | note | IP
eac42351-ce28-537b-a1b6-8d8568be8849 | note | RESPONSIBILITY: Site Engineer
0b13f38c-2af0-5b48-9bce-0cf9cd269653 | textbox | Date Completed:
c23d284b-b5ce-428d-a110-270b995637c1 | checkpoint | 3.4 Final inspection
e57edea6-6812-54e1-a2f4-d9ebac2a36b9 | note | FREQUENCY: Each line
864f35f1-d5e9-51ed-9274-9c9ba9613009 | note | ACCEPTANCE CRITERIA: Pit and pipes to be clean suitable for use prior to hand over
b540dbd0-ea18-56b2-bc2f-8c36462da79f | note | REFERENCE DOCUMENTS: 701.28
0cac2199-6caf-5a77-a95e-0d448acbc022 | note | INSPECTION/TEST METHOD: Verify
de4bdd7b-eb77-5185-9656-b0aa32c16997 | note | RECORD OF CONFORMITY: Lot Maps
f60b89d5-f00a-5666-9052-63ed821535fc | note | IP
ca039327-a920-5e5c-bec2-dd1cb55a55bf | note | RESPONSIBILITY: Site Engineer
02ce00f6-a8d2-5f7e-a205-1f8c4a3d6617 | textbox | Date Completed:
9f88f689-07cc-4ab4-bf05-1658ed616b13 | checkpoint | Final Inspection
cc6c7e3c-b937-5c49-8f66-969218df1a80 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
7bea03ee-be53-57e4-a406-45674a840d86 | textbox | Print Name:
bddcb8d4-d7a9-50ba-b37d-345657aefe76 | textbox | Position:
3aaadce2-ec66-5cc8-b6c9-5924ce886959 | textbox | Date:
f31b646a-4a84-4b38-b350-efcdc6074e07 | checklist | FHC-ITP-010 - StormTrap Construction v2 Rev1 | itp | FHC-ITP-010 - StormTrap Construction v2
aafccd0b-fc9c-48d3-8253-2c9f7f36ddd6 | section | Preliminary Works
b6fb6959-2089-40be-9bf5-1c839df92e0f | checkpoint | 1.1 Check for correct documentation
e8aba1b3-3c58-52ac-a87a-30dd4488cef5 | note | FREQUENCY: Prior to commencing any activity
fde2df97-29f3-53d5-8d85-4b1768f43497 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
a409abf1-0732-5399-b4d5-9f6f46b3765f | note | — using the correct and complete set of drawings
0a9e4101-3f8f-524d-aec8-c797dc16fa38 | note | — all drawings are the latest revision
6feaa479-1bc4-52fe-9499-c1fd5168fbb2 | note | REFERENCE DOCUMENTS: IFC Drawings, Approved Shop Drawings
faf1cb10-f593-5ba5-b987-5e0a0e2f1a57 | note | INSPECTION/TEST METHOD: Visual inspection
0381977b-36be-5611-b417-65394c34e84f | note | RECORD OF CONFORMITY: This ITP signed off
a16be100-7a1b-5f5e-949f-19e1473b3654 | note | HP*
b268d5f3-428b-53a8-bf3c-3894139c3a74 | note | RESPONSIBILITY: Site Engineer / Site Foreman
537a1605-17ff-5602-ad4e-16e0bbc8a53c | textbox | Date Completed:
e092d803-4401-44d4-a2e0-46dee9066a9e | checkpoint | 1.2 Implementation of all measures and controls
49554871-7f5d-541b-83b9-b3c776159ef0 | note | FREQUENCY: Prior to commencing any activity
64220795-72d7-5bc0-a8a7-446683ea278e | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
77943a85-705d-525a-b8f1-432ec14e5b96 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
061f1426-5d0f-5e05-ba3d-64d76e49a1a6 | note | INSPECTION/TEST METHOD: Visual Inspection
aa527e42-19f2-55c3-998c-bf9b1c84481b | note | RECORD OF CONFORMITY: This ITP signed off
305b6ce3-fa29-5999-9145-6bafd0be25ec | note | HP*
5e507387-afa9-5599-a490-35408cd2d965 | note | RESPONSIBILITY: Site Engineer / Site Foreman
f7a928e2-4e17-5e0c-9b91-de747d69dfcb | textbox | Date Completed:
66c6f017-0973-4731-84a6-9fc73c7b45a7 | checkpoint | 1.3 Material approvals
84012696-b6dc-5542-b83c-0c8f4fe83fc4 | note | FREQUENCY: Prior to Placement
561800ed-e240-53d8-be4d-07cbe00a11c2 | note | ACCEPTANCE CRITERIA: Material intended for use is to be submitted to the client prior to placement to verify it conforms to required specifications.
9ef66412-6f8a-576d-965d-dd0b312ba724 | note | REFERENCE DOCUMENTS: Material specification sheets
1e164e08-897c-59b1-8fe7-ff702ec84fca | note | INSPECTION/TEST METHOD: Verfiy
0f460038-aa1c-523f-9e7c-e5c524bf9283 | note | RECORD OF CONFORMITY: Teambinder Acceptance
4348e200-b7be-5f2a-9af3-356b6b6be08b | note | HP*
fdc5ec81-8b10-5a02-a731-2850f5a1bf51 | note | RESPONSIBILITY: Site Engineer
259db95e-5525-5cf1-b9c6-bc30e8903af2 | textbox | Date Completed:
2fb55309-d3f3-4a0e-8064-6099eb6d20aa | checkpoint | 1.4 Precast Materials Inspection
89df5558-e9d0-53c2-9f04-e8a6d340259c | note | FREQUENCY: Each Delivery
ccb4d549-ac2e-5dd5-baa5-6d605959e82b | note | ACCEPTANCE CRITERIA: Precast materials have been inspected and fit for purpose and free of defects
3d02ff48-9e1b-56f1-9b47-ed2021dc9217 | note | REFERENCE DOCUMENTS: 619.08
93c89aa4-fffa-5b0a-9ee8-b3126cf5c53b | note | INSPECTION/TEST METHOD: Visual Inspection
d1178ef2-2f4f-5d2d-91dd-1ced78c7f3b8 | note | RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist
e2885f6f-01e5-579e-a897-685faa6f8a9d | note | IP
0b1cc3f7-f0db-54fd-8453-1fb5dc848709 | note | RESPONSIBILITY: Site Engineer
b9ede8ec-1dc9-5739-8cf8-847227636bf5 | textbox | Date Completed:
a4936917-733f-4e9e-a61c-ceee07074ea0 | checkpoint | 1.5 Precast Unit Compliance
074f4bf0-ea88-54e4-8256-1c3d255ea64b | note | FREQUENCY: Prior to Commencing
02c50fc6-b0ad-508f-9628-6c4a9c328521 | note | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Box Culverts to comply with requirements of VicRoads Section 619.
689d81a6-7df2-5e7a-85b5-f3c170fd77d5 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.619, 701.04, 701.05
36e7aa94-ed0b-532a-85b3-237879f4caaa | note | INSPECTION/TEST METHOD: Document review & Site inspection
780cc9fb-29d6-552b-aa03-6e0f4d9ce8e4 | note | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
d2d67261-c012-5d39-9292-a583ba8b3fdb | note | IP
81ed8cd4-67d4-56e3-9967-a9cc6f900dda | note | RESPONSIBILITY: Site Engineer
4b1b4f75-43de-563a-a473-80c77600e38e | textbox | Date Completed:
b9d61cd2-6b85-4188-81ba-cdfb688699b0 | checkpoint | 1.6 Slab Bedding Material
0280e8b1-84c4-53e4-976a-f27f6604479d | note | FREQUENCY: Prior to start
c96d3a7a-210b-54b2-bc30-3d6a74925690 | note | ACCEPTANCE CRITERIA: Stormtrap modules shall be placed on an insitu concrete base supported on a level, 150mm pad of compacted road sub-base material compacted to 95% relative MDD with a minimum allowable bearing capacity of 150kpa that extends 600mm past the outside of the system.
2153c9cc-6ae1-5e75-86e1-c48195537659 | note | REFERENCE DOCUMENTS: IFC Drawings, Supplier Shop Drawings
5d2eb4cd-4e73-5f98-a5a1-324a96b0b71b | note | INSPECTION/TEST METHOD: Verify
6803740e-9b60-5405-8954-08e51bc8e9db | note | RECORD OF CONFORMITY: Test Reports from supplier
067c2c6a-188d-5cd4-ba77-4b0c9d6b304c | note | TP
f1646844-78bd-5999-9c05-d485ff2d3a77 | note | RESPONSIBILITY: Site Engineer
2c2210e0-60c1-5708-9d64-0edb4c90fbe1 | textbox | Date Completed:
1b4febf6-535b-4610-a937-63f1acee329c | checkpoint | 1.7 Backfill Material Classification
5b804a36-ed37-5843-ad74-71803a85b76e | note | FREQUENCY: Prior to start
74691f3d-35c5-5b77-b98e-6115b14884e1 | note | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements of Vicroads section 204. The placement and compaction methodology adjacent to the detention system shall not compromise the stability of the system and be placed in even layers no more than 600mm higher than the fill on the opposite side in accordance with AS1289
78863060-fbe4-527e-ac53-2503cd805e7a | note | REFERENCE DOCUMENTS: FHC-ITP-021, 204.04, AS1289
540e7603-09a8-5d78-a9a5-a45ea29ae862 | note | INSPECTION/TEST METHOD: Verify
71040772-1977-5281-ae8e-9e5b13665958 | note | RECORD OF CONFORMITY: Test Reports from supplier / site
91f18030-7cd2-5b60-953a-6ffed7f06da5 | note | TP
985d5ce4-5af0-55d7-a6c0-20939e970199 | note | RESPONSIBILITY: Site Engineer
f06f982e-f39f-5292-a77b-a4e2ffef6f33 | textbox | Date Completed:
178dd755-32ce-4b93-bebf-fd92fa497598 | checkpoint | 1.8 Grouting Material Classification
9a6e41d5-67ff-5bce-b2d9-8a692f4d549b | note | FREQUENCY: Prior to start
95b4a2e6-ca1e-5d92-9f1d-16410f4f77a6 | note | ACCEPTANCE CRITERIA: Where required for general applications other than those specified elsewhere in this specification, cementitious mortars and grouts shall be shrinkage compensating proprietary products with a consistency appropriate for the required use, and able to be placed and compacted to achieve full encapsulation. Cementitious mortars and grouts shall have a minimum 28 day compressive strength of not less than 40 MPa.
05e4ada0-3a09-52c4-99c0-1ea7bb663e9d | note | ○ Cementitious grouts shall be as a minimum Type C Class dual shrinkage compensating.
a842ad27-dd6f-52ed-815f-6c5fd4c8cc09 | note | ○ Only whole bags of material shall be used. Test certificates, material data sheets and health and safety data sheets shall be available for all materials. The mortar and grout applications shall be cured in accordance with the requirements of clause 610.23.
e46f55f2-bcf9-5577-bef7-93f9e5c027c5 | note | REFERENCE DOCUMENTS: 610.33
8fbfb192-70cf-556d-adae-e15759894531 | note | INSPECTION/TEST METHOD: Verify
d2ac5bfb-a69e-5a67-984d-6e72290db21f | note | RECORD OF CONFORMITY: Test Reports from supplier
a7372bf6-1620-59bd-8133-7149d320790a | note | TP
10861317-7c37-5007-9306-dc70fdd0c4c9 | note | RESPONSIBILITY: Site Engineer
c49068d0-38de-5d2e-b4ef-c9b08826d1c6 | textbox | Date Completed:
a908e71c-d3de-4db3-91d6-06c31104e3f4 | section | Construction Works
7416423c-e424-49a9-a7cb-70d623a5ba19 | checkpoint | 2.1 Excavation Permit
78831e7f-e113-5361-891b-d86f71f02926 | note | FREQUENCY: Each lot
4ec602ce-e311-56cd-8e4d-d6a8511625a0 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
7aaae60a-5bdd-5c2b-bb8f-8a394de28fa8 | note | ○ Plant and equipment shall be appropriate for the task.
d4e2513b-494f-5e74-9ac4-ba8de4d3f831 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation.
7de9d253-1be3-518d-9282-30c2a19a4d65 | note | REFERENCE DOCUMENTS: Excavation Permit
8c540333-79c1-54ae-94e6-7eaf955151f7 | note | INSPECTION/TEST METHOD: Verify
e39d2077-e6ab-548a-b63e-1859cd842fa7 | note | RECORD OF CONFORMITY: ITP Signed
48145781-0739-58f4-9a0f-98558081011c | note | HP*
77fd6c37-ae16-50b1-bfde-6dd9d9ed3539 | note | RESPONSIBILITY: Site Engineer
26bc6bc2-507a-5be7-91d0-1359be3b7cc0 | textbox | Date Completed:
0ea87081-f6fe-4d38-808c-a422efee0f8e | checkpoint | 2.2 Review
ab95cae0-62b9-563d-b326-299d4aa3c458 | note | FREQUENCY: Prior to construction
f59da648-0b25-5a25-9f57-40115bcfe78e | note | ACCEPTANCE CRITERIA: Stormtrap construction shall not commence until the Contractor’s construction quality procedure and inspection and test plan(s) addressing all requirements of this section have been reviewed by the Superintendent. Stormtrap modules shall be manufactured according to shop drawings and approved by the installing contractor and engineer. The shop drawings shall indicate size and location of all roof openings and inlet/outlet pipe openings.
dfac1ad5-90bf-5938-97e3-1f23039216df | note | REFERENCE DOCUMENTS: Shop Drawings 626.02
f2ba4a27-fcb6-5b33-81f6-47847a44248a | note | INSPECTION/TEST METHOD: Visual Inspection
3d12a5e1-0493-5229-9593-1028c2326f5b | note | RECORD OF CONFORMITY: ITP Signed
6c8051c5-6437-5c93-869f-c61f04627740 | note | HP
8266e8f6-7eb0-5ada-87bf-fd7f0e184c77 | note | RESPONSIBILITY: Site Engineer/ Superintendent
8a1573fc-87ec-5872-ac5d-f1615b0a95b5 | textbox | Date Completed:
418e907d-a608-4e35-b102-a2ce07e144a9 | signoff | AUTHORITY HOLDPOINT
36b43d0d-de01-48d2-bdc8-5bbe93dafc38 | checkpoint | 2.3 Diversion of Water
fda2c16c-b884-562b-b765-650c6f410b4d | note | FREQUENCY: Prior to construction
95f899bf-5074-5ea6-a8f5-d3db8398c698 | note | ACCEPTANCE CRITERIA: Stormtrap construction shall not commence until water flow has been diverted to the satisfaction of the Superintendent.
65ce9191-b85b-599f-b372-2e25d0b61734 | note | REFERENCE DOCUMENTS: 626.04
76fcba64-1ccc-5c25-aa79-79704fc3cdb9 | note | INSPECTION/TEST METHOD: Visual Inspection
164d806e-37c5-58a3-9c13-a6c8fe9dda51 | note | RECORD OF CONFORMITY: ITP Signed
ac037260-bc9b-5cf2-9452-a09baec1127c | note | IP
076d938f-fbce-570e-8b2f-3bfa3c567274 | note | RESPONSIBILITY: Site Engineer
ccc69d5a-54d1-54b0-ac7a-da5209513beb | textbox | Date Completed:
9a3a9979-b710-41d6-a819-7b2364b4d98d | checkpoint | 2.4 Conformity with Drawings
fe480132-34e2-5a53-afd1-1750126e49e5 | note | FREQUENCY: Prior to excavation
08f50bc5-b76e-5752-b50e-48d69eca9dd4 | note | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the stormtrap the Contractor shall confirm the position of all stormtrap units with the Superintendent.
0d6e3d82-82b3-57ec-978e-64747fe657ab | note | REFERENCE DOCUMENTS: 701.1
6f11a201-a552-57d5-82b7-5ad6a2722b44 | note | INSPECTION/TEST METHOD: Visual Inspection
c4524298-e593-5b65-8184-7233dcb4c08c | note | RECORD OF CONFORMITY: ITP Signed
1a4c485d-67db-5eaa-9572-8777266003e7 | note | HP
86a99d7b-ddce-5073-ae8a-a5088ba28d10 | note | RESPONSIBILITY: Site Engineer/ Superintendent
e1d17513-28c5-56d3-be11-b0b0514628ee | textbox | Date Completed:
edf2b4d8-a0a6-4d25-a526-dfdc8f880b10 | signoff | AUTHORITY HOLDPOINT
ca7a2350-b8a8-4074-b4e1-fd2d237bb129 | checkpoint | 2.5 Tolerances For Placement
7d04fa64-29d5-5bb8-b0f1-44562e8e597b | note | FREQUENCY: Prior to Backfilling
6c17762e-67c0-581d-806b-33ab1e9e1927 | note | ACCEPTANCE CRITERIA: The stormtrap shall be constructed in the location, to the alignment, cross sectional shape, dimensions and levels shown on the drawings.
05570d78-2253-5a59-a240-d3875939acf3 | note | REFERENCE DOCUMENTS: Shop Drawings
78b4be0d-e9c7-5f1a-9938-e06076f0757e | note | INSPECTION/TEST METHOD: Visual Inspection
40bfb605-1172-559e-bf93-20ee7a2e8a90 | note | RECORD OF CONFORMITY: ITP Signed
c8bff0c4-c34f-59e3-be2e-111e11c43a7e | note | IP
c37bfb23-725b-521a-867d-95ed9a3106c0 | note | RESPONSIBILITY: Site Foreman
83f41417-8afc-53e7-bdd6-b42cd7ef03ac | textbox | Date Completed:
8e62849c-ae66-4917-b812-d32c0aaf8d1a | checkpoint | 2.6 Foundation Inspection
28fc017e-1f3c-51c2-8e96-f08bef2c61db | note | FREQUENCY: Prior to Bedding
f5c749d4-14e0-572e-a721-80621e6431dc | note | ACCEPTANCE CRITERIA: Bedding for the cast-in-place concrete base slab shall consist of a compacted layer of 20 mm Class 3 crushed rock, of not less than 150 mm compacted thickness or as specified by geotechnical engineer. No bedding material shall be placed until the foundation or foundation materials have been inspected and approved by the Superintendent. Per FHC-ITP-006 - Class 3 Crushed Rock
fb77e271-2d54-5692-975c-5f58975bd5b9 | note | REFERENCE DOCUMENTS: IFC Drawings 812, 626.06, FHC-ITP-006
60978349-4556-5f53-aaca-b6ba02b8e69a | note | INSPECTION/TEST METHOD: Visual Inspection
6c9ccd69-d797-57da-91b2-79afc817e7b1 | note | RECORD OF CONFORMITY: ITP Signed
6acb3601-3fb0-5dd1-b3a8-847892c559e4 | note | TP
8b1a569b-cf65-55f2-ab31-5bdc6180d178 | note | RESPONSIBILITY: Site Engineer/ Superintendent
856bd366-8324-547b-838b-b5119c9a4ef7 | textbox | Date Completed:
e96f1ebc-ed19-4671-8b33-07d80187d80f | checkpoint | 2.7 Cast in Place Blinding Concrete
3acfd7e2-ac74-5dbd-a249-f9c81c2f4516 | note | FREQUENCY: Prior to construction of blinding slab
f710fee4-1b20-5840-8582-fab377249e31 | note | ACCEPTANCE CRITERIA: All cast‑in‑place concrete for stormtrap construction shall comply with the drawings and Section 610. Construction of the concrete blinding shall not commence until the bedding has been approved by the Superintendent.
91f60226-9518-5a68-a574-3e8ed9018ec3 | note | REFERENCE DOCUMENTS: IFC Drawings 610, 611, 626.07
d98bb38e-c51f-5c18-8247-8d42ca9f3ff1 | note | INSPECTION/TEST METHOD: Visual Inspection
e180da3d-940c-59a6-8985-427587ca96ec | note | RECORD OF CONFORMITY: ITP Signed
249e1d1f-cefd-5421-a34c-7fe369890db3 | note | HP
8270c7bd-6434-5e03-8f51-1560e038674b | note | RESPONSIBILITY: Site Engineer/ Superintendent
1c3d5759-84b9-59ab-8e58-474e36f7a591 | textbox | Date Completed:
a8e4c7a5-0998-4f03-b542-df4b342cceae | signoff | AUTHORITY HOLDPOINT
b31247d9-2656-4791-9a27-c38ec8e93807 | checkpoint | 2.8 Cast in Place Structural Concrete
0e59bc64-cc3f-51e0-baee-833aa22ce3cd | note | FREQUENCY: Prior to construction of concrete base slab
3ebf8f00-f629-5859-8035-bc6c95aa054e | note | ACCEPTANCE CRITERIA: All cast‑in‑place concrete for culvert construction shall comply with the drawings and Section 610. Steel reinforcement shall comply with the drawings and Section 611. Construction of the concrete base slab shall not commence until the pre-pour checklist and the reinforcement and form levels has been checked and approved by the Superintendent.
796feca3-0bb6-5062-b305-850c2f9329e0 | note | REFERENCE DOCUMENTS: FHC-ITP-025
9b440349-7378-5e51-aebf-f845efcf89bb | note | INSPECTION/TEST METHOD: Visual Inspection
06d0af6e-d037-51ec-83ad-022c9e319f66 | note | RECORD OF CONFORMITY: ITP Signed, Completion of Pre-Pour Checklist & Load Batch Traceability Checklist
2167c1ff-751d-5551-b826-e666b6964d5c | note | HP
57d864d1-475a-5aad-8159-191b16c7e7c4 | note | RESPONSIBILITY: Site Engineer/ Superintendent
c9e669c7-96f5-50d2-ab22-0b30c55ac226 | textbox | Date Completed:
c382565e-814e-4d91-80ea-2dcc6f2f5a42 | signoff | AUTHORITY HOLDPOINT
efa7f6b5-f1fa-40c9-bb21-7d596057e008 | checkpoint | 2.9 Placement of Precast Units
472f1ce9-70bf-52f2-a4fb-8d8269f0e6e7 | note | FREQUENCY: During Construction
a4856e61-e167-56c4-9203-428a6490a124 | note | ACCEPTANCE CRITERIA: The perimeter horizontal joint of the stormtrap modules, shall be sealed with preformed mastic joint sealer (stormmastic). The stormtrap modules shall be placed such that the maximum space between adjacent modules does not exceed 20mm. If the space exceeds 20mm, the modules shall be laid again with appropriate adjustment made to line and grade to bring the space into specification.
3767201d-e585-5ded-a5dd-9c9b61e058f6 | note | REFERENCE DOCUMENTS: Shop Drawings
ab6cb751-09fa-5a71-aa9f-eddfb9643932 | note | INSPECTION/TEST METHOD: Visual Inspection
54896caa-e9e5-5f7d-8b7d-874f582de010 | note | RECORD OF CONFORMITY: ITP Signed
a54f6fdd-b944-5b4f-9754-79c47052c87e | note | IP
8a8defc6-74fb-56e2-9520-a54561835edc | note | RESPONSIBILITY: Site Engineer / Site Foreman
9b7e87b8-60ae-5f69-b512-4be3bc660615 | textbox | Date Completed:
91f5ba8a-5f6e-4ea0-aef0-65a845d3e76e | checkpoint | 2.10 Covering External Surface of Joints
d301d117-e807-5027-a7c8-6406ec9b460c | note | FREQUENCY: During Construction
802db82e-698a-55a7-8bd1-89ed8b8b288d | note | ACCEPTANCE CRITERIA: All exterior joints between adjacent stormtraps modules shall be sealed with 300mm preformed cold-applied, self-adhering elastometric resin bonded to woven highly punctured resistant polymer wrap and shall be 300mm integrated primer sealant as approved by humes (stormwrap). The adhesive exterior joint wraps shall be prepared/cleaned and installed according to the manufacturers installation instructions.
ca7799ee-11a3-52d6-8a4d-decfffcb7de9 | note | REFERENCE DOCUMENTS: Shop Drawings
c0ebdaec-9955-584f-8741-4f4dbd247dd4 | note | INSPECTION/TEST METHOD: Visual Inspection
77fe5419-1b1f-59e7-9ad0-bfb5afcec147 | note | RECORD OF CONFORMITY: ITP Signed
5439678b-3b89-542c-90fe-eee8100c8082 | note | HP
2c3f0912-0161-59f1-8712-7b9c9bfd069a | note | RESPONSIBILITY: Site Engineer/ Superintendent
1bcf7f36-895a-51fc-a479-a8abc9a82248 | textbox | Date Completed:
d4510cc6-0e90-44b7-8da7-4cfcdeec47bc | signoff | AUTHORITY HOLDPOINT
6d6531f5-7a29-4315-ac5e-4e1fd1299c0d | section | Testing & Completion
cdc4c359-7129-4cff-bcd9-5b3c738acc62 | checkpoint | 3.1 Concrete Sampling and Testing
5c5eeee0-b3a8-5188-b9c7-1449a136b39f | note | FREQUENCY: Each Strucutral Concrete Pour
376cfaab-42c3-5106-abd3-ca31615cd984 | note | ACCEPTANCE CRITERIA: Concrete sampled and tessted for strength and slump as per requirements outlined FHC-ITP-025 - Structural Concrete Construction
512285f0-754d-571c-ad2e-2b5c527decae | note | REFERENCE DOCUMENTS: FHC-ITP-025
1624dc32-903a-5bc2-81db-99228f801fcf | note | INSPECTION/TEST METHOD: Verify
ee08609b-1e71-56eb-92a7-b6486e0816ee | note | RECORD OF CONFORMITY: Test Reports
a23af95a-2fd2-5aaa-b5c2-69c86fdffd60 | note | TP
4239e3ea-1f3c-5083-92b2-896d4d9f2518 | note | RESPONSIBILITY: Site Engineer
2327cd4f-a340-5b4d-a76f-4ae62b499c02 | textbox | Date Completed:
c969fc5b-d518-403a-8b6f-92c596d43611 | checkpoint | 3.2 Final Inspection
32d154d1-7bba-5b9b-84a1-932e00ed9e6d | note | FREQUENCY: Post Construction
714f2ccb-d902-52d0-9d69-989fe28531bb | note | ACCEPTANCE CRITERIA: Units which do not comply with the requirements of clause 619.14 prior to laying and backfilling shall be rejected and removed from the site.
b264d589-4cfb-5ee1-b527-6ede1cc58df6 | note | ○ Where inspections after backfilling identify defects which do not comply with the requirements of clause 619.14, such culverts shall be removed and replaced, unless the Superintendent approves repairs to be undertaken in accordance with the requirements of Section 610, and Section 687 for crack repairs and Section 689 for conventional patch repairs
9d30cdf1-fa26-5e00-bc09-6a2e82faeef1 | note | REFERENCE DOCUMENTS: 701.31 (d)
cd9a5095-5f19-5c49-a4fa-a5845fc4d652 | note | INSPECTION/TEST METHOD: Visual Inspection
31054b5d-2e0d-5375-b1c0-f23871a26d94 | note | RECORD OF CONFORMITY: ITP Signed
bf076a71-e6a0-512d-84d4-6eb47dd5e888 | note | IP
e43002ed-d961-54f0-aaaf-d6dc630a0851 | note | RESPONSIBILITY: Site Engineer / Site Foreman
f5228ad2-4233-5a39-bc6a-d9b855a625e2 | textbox | Date Completed:
94fdbbad-ecca-4314-8f99-6d9595aff868 | checkpoint | 3.3 Lot Mapping
85d6bb59-745a-504f-9eda-709ee4e30880 | note | FREQUENCY: Post Construction
ca1bda30-ef60-53b9-98ad-8f537462833a | note | ACCEPTANCE CRITERIA: Stormtrap to have suitable lot map based on days production for traceability purposes.
0854b106-c1d0-52a5-8d65-dab2160082bb | note | REFERENCE DOCUMENTS: Shop Drawings
91da4b3b-71a9-5539-a58b-e36346772fe0 | note | INSPECTION/TEST METHOD: Visual Inspection
c6769f5d-4b31-5b68-a0b8-b71d71494f45 | note | RECORD OF CONFORMITY: Lot Maps
89b4277a-a9d9-5ef2-bb8e-7911acd4073d | note | TP
e94ce4a2-a6a8-5824-a973-f0fdfb7bebdb | note | RESPONSIBILITY: Site Engineer / Site Foreman
f9afa9d1-a634-55e2-acac-957e7a358bbb | textbox | Date Completed:
d0864abb-f625-4c25-b585-8d1efaec1c23 | checkpoint | Final Inspection
2105e379-cddb-5ef8-9ace-176bc5b8b358 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
51fddb31-7d4b-5dc3-af6a-3ad07f172086 | textbox | Print Name:
f74a9904-cc42-511b-9a60-d48d3cdd46cc | textbox | Position:
0199f481-b654-5f49-9f74-3bd376fd90af | textbox | Date:
b4fda96d-60c3-4838-b64f-a482774ee986 | checklist | FHC-ITP-013 - General Concrete Paving Rev2 | itp | FHC-ITP-013 - General Concrete Paving
1b7b1c10-01c8-472b-a4a2-6ce5a3bc990f | section | Preliminary Works
a36f465d-0702-4b38-a4e7-7af6f9e3afa1 | checkpoint | 1.1 Check for correct documentation
2dcbd069-bf12-5e63-9615-3db734195d23 | note | FREQUENCY: Prior to commencing any activity
f89806cf-8e70-5d0b-afc4-25e58f5dbc2f | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
04fd787e-4b05-5545-b18b-53d9dd3e6f01 | note | — using the correct and complete set of drawings
852293b6-4e2f-5ee3-89c8-085f001814e5 | note | — all drawings are the latest revision
13b59bbf-af34-51ad-9d57-a06a8cb9f141 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
7bb876bd-b078-5ddd-ab4a-0e494b1b0deb | note | INSPECTION/TEST METHOD: Visual inspection
a9fa421a-3626-50f1-85b1-96cf10267f00 | note | RECORD OF CONFORMITY: ITP Signed
80eb417b-5b96-5837-ba28-81a179aa0ee9 | note | HP*
cce1fdbd-11d3-557b-b2f4-caad7989ad2d | note | RESPONSIBILITY: Site Engineer/ Site Foreman
e23d83c0-7ff4-5561-88c5-b75668830daf | textbox | Date Completed:
86662d76-76d9-43e3-acbb-9212a7440c87 | checkpoint | 1.2 Implementation of all measures and controls
5d85aca6-5bf8-5b04-9978-c117a53c8039 | note | FREQUENCY: Prior to commencing any activity
5d1731f0-0c66-5cdb-b33a-7a0dfe5502fb | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
2cb70ea2-385b-5ee4-95a5-003af06f4226 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
eba2589a-bb1f-581a-a152-f63584073faa | note | INSPECTION/TEST METHOD: Visual Inspection
5d5ed609-92fb-5b16-907d-6120d169d88e | note | RECORD OF CONFORMITY: ITP Signed
27ff3b28-96ec-5c46-ad91-b7653a5c4d18 | note | HP*
ec8b9851-fadb-51b9-84b2-34281b9fa326 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
69cadf42-01f5-5464-a5df-f40fbd31274a | textbox | Date Completed:
12ef8603-a5c7-4729-b5ea-539caa12280a | checkpoint | 1.3 Submission & Approval of Concrete Mix Design
eb837ac0-96e0-5510-ba59-cdd05918d2f6 | note | FREQUENCY: Prior to first concrete pour
fe09f397-ef87-5da1-9b64-c68be70765b1 | note | ACCEPTANCE CRITERIA: The Contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete. Concrete shall not be placed until the mix design has been reviewed by the Superintendent, and allocated a registration number on the Register of VicRoads approved concrete mixes.
779c43b5-4cdb-5fb1-a5c8-edb1af230d96 | note | REFERENCE DOCUMENTS: 610.07(b)
22af872c-cd28-54bb-a5f5-d9d13b78cf83 | note | INSPECTION/TEST METHOD: Verify
734a5b0c-ed6d-537f-a2fd-7a7e06abb69f | note | RECORD OF CONFORMITY: ITP Signed, Mix design approval in teambinder
e5fc472e-21a1-551d-a4bd-7ad6a09cc4fd | note | HP
5cd67e0f-4165-5cbd-925c-87bec266fed4 | note | RESPONSIBILITY: Site Engineer/ Superintendent
25e8b0df-87c7-5119-ad68-8b80bfa214fb | textbox | Date Completed:
c668752f-9d6f-422f-a184-364e13ad1e97 | signoff | AUTHORITY HOLDPOINT
0d954133-8776-4f42-a419-46fc5f9588cb | section | Construction Works
b9af6ecf-8da4-4da9-b0b0-76961b792bc2 | checkpoint | 2.1 Setting Out
a6525460-f3e8-5c71-a02b-a99de266ff24 | note | FREQUENCY: Prior to start
5c0105b6-f1f1-5e3c-b6b2-43cb5942d017 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
5b252420-988e-5bfe-8ed8-050d8779a5ef | note | REFERENCE DOCUMENTS: 703.17
ca5e9a9c-7892-5ddf-9065-994e1196e8ab | note | INSPECTION/TEST METHOD: Verify
1c0f6f14-047c-5745-a2ca-7011fdf402d8 | note | RECORD OF CONFORMITY: This ITP Signed
2b1913fd-2731-5198-bbda-ffab5d2ee909 | note | HP
2f785276-5d1c-5b49-999c-c51f639088fa | note | RESPONSIBILITY: Site Engineer/ Superintendent
9a17dc81-07ce-57bd-9858-afe2fa2608cc | textbox | Date Completed:
7da500db-2bcd-4988-838f-c6e8f2082397 | signoff | AUTHORITY HOLDPOINT
4781203d-2632-479c-b288-1bb39a64029a | checkpoint | 2.2 Excavation Permit
dfc8cc4a-9820-5193-b3df-c910dbd23f90 | note | FREQUENCY: Each lot
051cb0e5-8a25-51b9-98bd-25f9f0b31ff7 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
10c0f801-f831-50d0-b04a-cf72c123e246 | note | ○ Plant and equipment shall be appropriate for the task.
cd987adf-32ad-5a80-8456-f7526c3d6348 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
f2e636e1-251d-5cf8-b27d-94ef10d6e913 | note | REFERENCE DOCUMENTS: Excavation permit
e11fcbae-3325-5dd1-a76e-881ae7cf97e7 | note | INSPECTION/TEST METHOD: Verify
b22278dc-e6f6-5449-a2cf-e1feae43b4ec | note | RECORD OF CONFORMITY: ITP Signed
f752ce1a-8b2b-5aec-ba99-2cc87a15f5a0 | note | HP*
f74dc9b9-dde9-562c-884a-c42d68bb0e5e | note | RESPONSIBILITY: Site Engineer
0acdc0f5-8f6e-5957-90ce-5d05873f0738 | textbox | Date Completed:
38f374e3-4b5a-4e8c-bae1-3f575e84317b | checkpoint | 2.3 Excavation
43e9775c-70e6-5beb-b6ea-36daab8d99a2 | note | FREQUENCY: Each Lot
178288fb-91a7-539f-b27e-dc2e8eec8a95 | note | ACCEPTANCE CRITERIA: Excavation completed to required depth to allow placement of the bedding layer
3240296c-5fe7-5f08-8bb1-4400fdd5686c | note | REFERENCE DOCUMENTS: 703.2
c95834fc-c3a9-5a34-bc16-0fc8fa842805 | note | INSPECTION/TEST METHOD: Verify
90b08c5e-c03a-5658-99f9-0e6938ae9066 | note | RECORD OF CONFORMITY: ITP Signed
2889b2ef-b653-5e42-bf67-f7d8513aaeed | note | IP
72ea42ce-aa20-5868-a81e-bcc852c26baf | note | RESPONSIBILITY: Site Engineer
c64a95cc-a0b7-52a2-9c27-00d0831ad1ec | textbox | Date Completed:
c82ddac6-528a-44e9-b2d0-5db66e687b7a | checkpoint | 2.4 Bedding
7dc68e72-cd92-5ffd-8c3e-6d19dfc22ac2 | note | FREQUENCY: Each Lot
517fafba-74e7-510c-a29f-058e78c5ee8c | note | ACCEPTANCE CRITERIA: All bedding material used shall be as follows:
b174cc36-73cb-51f1-b810-778e143c07c8 | note | ○ 100mm thick layer of 20mm Class 3 crushed rock bedding for median infill
0c84a18d-14b0-50a1-9406-f532c35be00b | note | ○ 150mm thick layer of 20mm Class 4 crushed rock bedding for footpath/pram crossing
d29705cb-4e2c-5684-a0cb-ae9cd73bf47a | note | ○ Bedding trimmed, moistened, and compacted as per Section 304
a545494e-fd4e-5f85-ab53-bde4a8f65d65 | note | REFERENCE DOCUMENTS: 703.21 Drawings
d280ad51-7cfe-54c9-8f9b-82e41dd34cb7 | note | INSPECTION/TEST METHOD: Visual Inspection
f2cbc1eb-9605-5ae5-814a-aa354a04bda9 | note | RECORD OF CONFORMITY: ITP Signed
88739c61-58d9-581c-801c-e33132f36f40 | note | IP
9d7ad097-97e6-5a77-9327-1b9e08ad89ef | note | RESPONSIBILITY: Site Foreman
896d354a-c4aa-5d88-867e-144e8e36ea45 | textbox | Date Completed:
3a309a5b-c13e-47ae-abac-33f14ace03ba | checkpoint | 2.5 Formwork
ce7e6de1-a9b4-5be7-92a9-f296efbc08c9 | note | FREQUENCY: Each Lot
6743dd62-9547-59b3-bbe0-d699be2d3496 | note | ACCEPTANCE CRITERIA: Formwork shall comply with the requirements of AS 3610
737b728b-2c15-59a4-84fa-22b7ddac2bca | note | REFERENCE DOCUMENTS: 703.12, AS 3610
7a9deec0-0220-56b3-83c5-6d71ce14ffd7 | note | INSPECTION/TEST METHOD: Verify
83980751-423d-5911-9554-cb0130eca970 | note | RECORD OF CONFORMITY: ITP Signed
0110e60b-0efc-569b-a64d-729e31f93d55 | note | IP
004a4a91-d71c-5598-b3ea-e6a0d641377d | note | RESPONSIBILITY: Site Engineer
26e1d6b4-e66d-509b-8df8-da513b78daaa | textbox | Date Completed:
da3d9cc1-9ee9-4f85-981c-0b8dace13772 | checkpoint | 2.6 Reinforcement
25407003-8103-5663-8aea-ebb327c2de1e | note | FREQUENCY: Each Lot
1f9975ee-450a-57aa-8332-0fc88502c6bc | note | ACCEPTANCE CRITERIA: Reinforment used shall consist of SL82 mesh is to be placed with a minimum cover of 50mm from the top (unless shown otherwise on drawings).
fcc9e520-31ad-5804-bed8-136bd04fb648 | note | ○ Reinforcement must comply with the requirements of AS/NZS 4671.
d35c0e6d-1de9-5b1a-9af2-0ceecdee9cbe | note | REFERENCE DOCUMENTS: 703.13
18427b79-2143-522f-9733-210668ef1d43 | note | INSPECTION/TEST METHOD: Verify
d1e496ce-8507-557a-b05f-77d41b20055f | note | RECORD OF CONFORMITY: ITP Signed
fda67eb7-637e-5d95-b41c-f97185f707f2 | note | IP
301c81cb-b666-5f70-b0b3-e45e78d144f2 | note | RESPONSIBILITY: Site Engineer
5125396d-132e-520a-a0e7-2d3e6d4b32b9 | textbox | Date Completed:
3875fa35-c19a-4a54-b670-bd9f31794004 | checkpoint | 2.7 Concrete Placement
ad999b1f-c3e6-51fb-aae8-7c846f6ff9c6 | note | FREQUENCY: Each Lot
dd02b682-0591-5b09-baf3-3427583a04ba | note | ACCEPTANCE CRITERIA: Concrete shall be thoroughly compaction via contious tamping and internal vibration. Where concrete is unformed it shall be hand tamped to a smooth surface and screeded in accordance with the construction drawings.
6020b558-c865-5478-a7aa-2147911617ca | note | ○ Where fresh concrete is being placed against concrete which has taken initial set a properly formed construction joint must be used.
3bdb220f-9843-5a11-967f-5b3b88dd74e0 | note | REFERENCE DOCUMENTS: 703.05(a), 703.08
f16e011e-9b04-5b50-9541-dcedb80b038e | note | INSPECTION/TEST METHOD: Visual Inspection
20e5c6a1-4fd5-5b47-83c9-385de51ace0f | note | RECORD OF CONFORMITY: ITP Signed
f22da21d-032e-53c6-a98f-1cd0c63806ef | note | IP
b0e099af-084a-5aaa-9707-7a735a425b9c | note | RESPONSIBILITY: Site Engineer/ Site Foreman
154740eb-a2d9-5233-91c7-463525d9283f | textbox | Date Completed:
35f27b7c-16a8-42ec-be9b-0849d3c34c30 | checkpoint | 2.8 Surface Finish
f347ce3d-1292-5d33-bd34-26c52a81bb86 | note | FREQUENCY: Each Lot
4dd3eb0c-3c56-5924-b3bc-9416183528c1 | note | ACCEPTANCE CRITERIA: Concrete elements shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces in accordance with AS 3610.
1d4c9498-0457-509b-a265-cc2cd4fac31c | note | ○ Footpaths and other Surfacing shall be compelted with a wooden float.
c66f9614-df53-5817-b938-70f6025dd9f0 | note | REFERENCE DOCUMENTS: 703.25
52a09cf2-5979-5587-8752-cff1e026757a | note | INSPECTION/TEST METHOD: Visual Inspection
fcda31ea-51a2-5d58-9019-da7de709de02 | note | RECORD OF CONFORMITY: This ITP Signed
00a8baf0-9d45-5f6e-bee6-af24b424b255 | note | IP
2832c71e-89de-5bc7-98ff-ba0c6c94a5a4 | note | RESPONSIBILITY: Fulton Hogan Engineer
25d89474-9779-5377-830a-89b1d3dbe615 | textbox | Date Completed:
0569a563-ff66-46d9-bc70-974d5460f7d9 | checkpoint | 2.9 Pram Crossings
d38031a6-bd71-5fad-8225-1d2477b1a57e | note | FREQUENCY: Each Lot
23407fdb-a54a-5d0c-b782-57696b350da5 | note | ACCEPTANCE CRITERIA: Ensure that pram crossings are constructed in accordance with requirements for access and mobility.
c3bc08bd-d9f3-53a8-8b86-e7a52ccc7b5e | note | — For pram crossings within concrete kerb refer to Figure 24A of AS 1428.1
c84dba2e-326d-52bb-8db6-dd0c0511f92e | note | REFERENCE DOCUMENTS: Figure 24A AS1428.1 Design Drawings
c1c49e32-2c39-5036-be50-91b95f76693e | note | INSPECTION/TEST METHOD: Verify
f0accae9-bd5c-555e-a233-9520eae57257 | note | RECORD OF CONFORMITY: This ITP Signed
5ba55f4c-03da-5129-9300-d69dcb9e0c25 | note | IP
0e524513-f7fb-539c-99af-f51079ceb809 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
680269d8-cc0b-594c-ad7c-62eac99650a2 | textbox | Date Completed:
148aea9d-b753-44ef-b47a-f61c528649b6 | checkpoint | 2.10 Joints
007b187a-4fff-5421-9472-6143bf5191ee | note | FREQUENCY: Each Joint
72b9d5a8-0109-51d6-92d7-26a20e9ccaaa | note | ACCEPTANCE CRITERIA: Expansion joints shall be installated at 10m regular intervals using 15mm wide cork or bituminous imtergrate particle board.
2967d0bb-42d9-586b-8ae2-786fa70d2dfc | note | ○ Control joints at 2.5m regular intervals, 25% of pavement depth and 5mm wide
f8acec69-3aac-5f18-b170-5e3c7e41c49b | note | ○ Prevent bonding between edging and surfacing. Either paint back of edging with bitumen or use a strip of bituminous felt material.
627c0745-e181-58fc-b170-4c95c402be28 | note | REFERENCE DOCUMENTS: 703.26
d498aa21-b83f-59d8-a6f0-8d00a7e452d9 | note | INSPECTION/TEST METHOD: Visual Inspection
24306e15-3c55-5dcf-b0b8-9a810b849110 | note | RECORD OF CONFORMITY: This ITP Signed
ac4b26ff-6a0a-56cc-aa3e-4a3da0150424 | note | IP
c9f65bd1-9aa6-512e-bc02-e55de8e78b13 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
0e893fac-1df6-54ff-95be-f97856a12e91 | textbox | Date Completed:
6f941c7f-a667-44e6-bc75-2c1223b35aad | checkpoint | 2.11 Protection of concrete
fb306610-cc55-559b-bf7c-13bf6a9a2639 | note | FREQUENCY: Each Lot
0b75ed94-59b6-5e3f-96a6-873c22901143 | note | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
d1af1672-1b01-58b5-9dce-9e655e333f9e | note | ○ Vehicles equal to or less than 1.5 tonnes in weight may be permitted to cross after 4 days, vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
127445f0-dd2e-5b03-93ab-00bf97008138 | note | REFERENCE DOCUMENTS: 703.27
033020f8-a745-581e-ba11-4beb0358659d | note | INSPECTION/TEST METHOD: Verify
83668252-4276-55a0-acb9-92490676f522 | note | RECORD OF CONFORMITY: This ITP Signed
1ff204c9-979e-5722-a0f7-0591fa33f10d | note | IP
98744d47-7166-5811-a3f7-60ecff25bfcb | note | RESPONSIBILITY: Site Foreman
0b790eaa-d891-54ec-a2d3-bf7d152f0484 | textbox | Date Completed:
bfb5a6a0-cf65-492a-b8fe-e61ae7036f7b | checkpoint | 2.12 Curing
326fb927-a468-5b52-b347-f6468aab0195 | note | FREQUENCY: Each Lot
e6302d4a-bd1b-5e66-9524-b1804b4e4c93 | note | ACCEPTANCE CRITERIA: Concrete shall be cured immediately either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
441fce6e-bf0f-51f5-9fab-0d30d74f862a | note | ○ Curing compounds shall comply with AS 3799. The curing compound shall be applied in two coats using a fine spray at the rate stated on the certificate of compliance
d2c8718e-e3a0-50b1-b37c-e6e83905e833 | note | REFERENCE DOCUMENTS: 703.1
39f0d687-1fb0-54ec-b7c1-0dd824374a52 | note | INSPECTION/TEST METHOD: Verify
406a5b26-17be-58de-a52b-45cf21373f4b | note | RECORD OF CONFORMITY: This ITP Signed
d87af860-68db-536a-8c57-fc7621f20bde | note | IP
edd31358-a84f-5377-bbb8-7b29c48468ce | note | RESPONSIBILITY: Site Engineer/ Site Foreman
9d87a031-ae3b-5b7b-8856-c8fc364c7699 | textbox | Date Completed:
2a373747-b3b0-4e3f-bf52-6a96c9ccc256 | checkpoint | 2.13 Ambient Weather
1e5da588-d298-5538-8810-8189abd801f5 | note | FREQUENCY: Prior to commencing any activity
4fa03d9c-4d14-55cb-86d1-7604c012377e | note | ACCEPTANCE CRITERIA: Concreting operations shall comply with the requirements of clauses 610.17(a), 610.17(b), 610.17(c) and 610.17(d) for limits, restrictions and treatments to be applied for concreting in hot, cold and wet weather, except that curing shall be in accordance with clause 703.10.
c70499ac-2c84-5466-a05a-78998c9c583c | note | REFERENCE DOCUMENTS: 610.17(a), 610.17(b), 610.17(c), 610.17(d), 703.09
8629c352-f3f7-50d6-93c7-6a7581359fe7 | note | INSPECTION/TEST METHOD: Verify
0970d0ff-3a5c-51ce-85a0-820906e1ebf2 | note | RECORD OF CONFORMITY: This ITP Signed
634b63ae-aa26-5b46-b638-7f99ae334e83 | note | HP*
9238954b-8b46-5b3b-9a96-ba28b807337e | note | RESPONSIBILITY: Site Engineer/ Site Foreman
8d7c1fd0-cce7-5d1f-8fe1-e2b0a7953401 | textbox | Date Completed:
4ca8e1c5-b5f2-4f56-987b-0b365cb1d617 | section | Completion
b9231fd9-bb45-4a31-b046-3dbbfa5a3c30 | checkpoint | 3.1 Carry out sampling of concrete - strength and consistency
dc70daf5-d3c7-594b-bd52-5aa76d0ea441 | note | FREQUENCY: Each 50m3
f5a06941-d029-56f6-8668-5db62bed62da | note | ACCEPTANCE CRITERIA: Sampling and testing of the strength of concrete shall be carried out in accordance with Clause 6.2 of AS 1379.
8dfd3336-56e6-5d3c-9f87-f655d9675429 | note | ○ The consistency of the concrete shall be determined by a slump test of each concrete strength sample in accordance with AS 1012.3 and Clause 5.2 of AS 1379
b5421084-d941-5b28-af32-11d6473f8048 | note | REFERENCE DOCUMENTS: 703.11
189d4822-64bb-59fc-a524-dc80786b41ab | note | INSPECTION/TEST METHOD: Checklist
4e371e47-91d7-5f0e-b564-34fcbf8f3ce5 | note | RECORD OF CONFORMITY: ITP Signed/Test Records
82e5a307-6460-5cf3-b16b-7b464ceef540 | note | TP
fa5b47a6-ca99-59c1-8483-a241b946ebd0 | note | RESPONSIBILITY: Site Engineer
91ed87c6-9a82-5728-ba25-2f5b2c3efcef | textbox | Date Completed:
a2cdcade-6ada-4278-b23c-7c8b257b52bb | checkpoint | 3.2 Tolerances
88f1992d-726c-5789-8af1-51cf009166dd | note | FREQUENCY: Each Lot
7d16de1f-e086-5321-8c8d-861cf34d2226 | note | ACCEPTANCE CRITERIA: Where matching in with existing surface levels, the new surface shall be within ± 5mm existing.
a405c8b0-a38f-5a95-a2bb-31ce45ccdd6c | note | Section dimensions shall be constructed within the following tolerances:
6c77b7ca-06c8-5a45-b757-b14da242358e | note | ○ 5mm and 15mm for width; or
5695fe71-dde0-5688-9616-ef8c86c38a41 | note | ○ ±3mm for dimensions less than 25mm.
63790c8d-e69a-5bc0-9e24-961b8778d98a | note | REFERENCE DOCUMENTS: 703.15 Drawings
86d16d92-0cba-580c-8250-2ccb8f364442 | note | INSPECTION/TEST METHOD: Visual Inspection
dfa87711-5a95-597f-b533-a4fbcecdf512 | note | RECORD OF CONFORMITY: This ITP Signed
cf69e64e-82ed-58a1-bd4c-f9de9d9b69b0 | note | IP
245a17f7-daa9-535e-b683-5d2e27ef185d | note | RESPONSIBILITY: Site Engineer/ Site Foreman
29f8fe31-8807-5f8c-8863-9d34f237ae67 | textbox | Date Completed:
9ba56714-211c-45b1-8240-e3cbd5ed7ddb | checkpoint | 3.3 Backfilling
0eb0a1f2-b113-54f3-9138-b7cb15909d71 | note | FREQUENCY: Each Lot
6ee6df75-00ed-510e-abc4-abeef7071f7d | note | ACCEPTANCE CRITERIA: After curing, no earlier than 3 days, backfilling shall be completed as per the below:
7015f537-7cf7-5f16-836b-0a74553bf7d9 | note | — Topsoil compacted in layers < 150mm
7156ad4e-cd14-5451-be29-76c5609bce71 | note | — Width ≥ 300mm behind edging to top of edging
28e6628b-85c3-51b1-bf4e-3bb8d94dee24 | note | REFERENCE DOCUMENTS: 703.29
fc8aa5fd-8fcc-5ba1-821c-f71fc8f926c9 | note | INSPECTION/TEST METHOD: Verify
291609b1-1e32-5c2c-9479-4a5d6d85bfc1 | note | RECORD OF CONFORMITY: This ITP Signed
4bdaddfb-8f03-5f13-b8a9-eef3c94b5ccb | note | IP
5ae2caea-067d-5697-8316-a7c6d7f6f55b | note | RESPONSIBILITY: Site Foreman
295bad1d-24d1-58a0-b3c7-6e5fab13daf2 | textbox | Date Completed:
ad0670af-4ad1-464e-9111-065a1639410a | checkpoint | Final Inspection
2fae261e-e9b4-54ec-aa98-584363d3bc19 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
fc87e982-ceb1-54b8-b4ab-954cec1de263 | textbox | Print Name:
760883df-f2c6-525e-a6a3-b95a00a238e5 | textbox | Position:
69970178-4e57-51da-82ac-29debca35f59 | textbox | Date:
5fd02cff-2e4d-4c6f-a078-57dc7649ae24 | checklist | FHC-ITP-014 - Subsurface Drainage Rev3 | itp | FHC-ITP-014 - Subsurface Drainage
74d8c181-d680-4d6e-8125-f5ad0c3b9c27 | section | Preliminary Works
8d79f6d4-d628-4214-97c3-d0a66c87a601 | checkpoint | 1.1 Check for correct documentation
5ed02433-836b-56eb-b44d-cab9010b2b68 | note | FREQUENCY: Prior to commencing any activity
e96c2b4b-0dc8-569a-9965-a5f1f169cffd | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
8a552124-ac82-583a-a1f1-7039f6a33e17 | note | — using the correct and complete set of drawings
40df01e2-3910-5ae1-933d-234a771bc20c | note | — all drawings are the latest revision
8d0b8bfd-06e5-53f8-8ed1-b65482bbd594 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
752c80fc-a4f5-5308-9e3a-3183210c8bfe | note | INSPECTION/TEST METHOD: Visual inspection
6780ce11-533a-57f5-a14d-de4bbc4f8e31 | note | RECORD OF CONFORMITY: This ITP signed off
3914148f-6956-5ddc-bad1-62bacc84628d | note | HP*
6cf17bf4-7109-5ce5-95c6-02697593dcfe | note | RESPONSIBILITY: Site Engineer / Site Foreman
bcbd122d-c323-5172-875f-1235a19bb6b0 | textbox | Date Completed:
4f7e1ec5-7a80-403d-9013-536d33e559ba | checkpoint | 1.2 Implementation of all measures and controls
cd9aa97f-0478-51c0-b480-db2b25274043 | note | FREQUENCY: Prior to commencing any activity
2d853aaa-e0dd-50e6-9494-6ba4fc68aa34 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
a8e82f23-6ce0-5687-a6b6-b56e74d3ea48 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
966db815-3664-5d27-bad3-ae865b5170ec | note | INSPECTION/TEST METHOD: Visual Inspection
59474c43-7e06-5bbf-a0c7-aba2a831d16e | note | RECORD OF CONFORMITY: This ITP signed off
48d95f45-1cb5-53c4-8bc1-1fa6248765b2 | note | HP*
ee03fd42-ed7b-5c00-8f9e-113acf859267 | note | RESPONSIBILITY: Site Engineer / Site Foreman
8435812b-feef-5471-b92c-c5fc155cdce3 | textbox | Date Completed:
0ffc68b9-0440-490b-b549-a70e86f0fd87 | checkpoint | 1.3 Placement of no fines concrete
71a42b28-2f70-5f6b-bc23-770b8294344e | note | FREQUENCY: Prior to works commencing
73dc4ece-baed-5593-8b96-6523af9bbee7 | note | ACCEPTANCE CRITERIA: Where no fines concrete is used as filter material the Contractor shall submit quality procedures for review by the Superintendent which detail the method of placing the no-fines concrete. The method of compaction shall be in accordance with the Contractor's quality procedures
ac2234d5-0dab-5392-9e48-ef75d420f892 | note | REFERENCE DOCUMENTS: 702.09(g)
8742c1de-d64b-5c09-9716-88cf9422f964 | note | INSPECTION/TEST METHOD: Verify
d413959c-b51c-530b-8a3a-ab7e4d3292e7 | note | RECORD OF CONFORMITY: This ITP signed off
f5d077f5-695b-585d-9208-b2bdf43acb9b | note | HP
3e586fdb-2cce-50a7-a533-28ca5be34b73 | note | RESPONSIBILITY: Site Engineer/ Superintendent
5c8d711b-9c61-5c15-a5f4-22f5380a7fc6 | textbox | Date Completed:
b983c72a-89c7-46e4-9af0-689ff9c1f249 | signoff | AUTHORITY HOLDPOINT
e9f39395-72c9-4d00-95d7-5e8ddee7f682 | checkpoint | 1.4 Material Classification
bd4b1338-c993-5544-ace6-bf651d86994d | note | FREQUENCY: Each Lot
3d3657be-cba6-53f0-ba4a-137dffd6baae | note | ACCEPTANCE CRITERIA: Subsurface drainage pipes: 100mm DIA Class 1000 corrugated perforated plastic pipe- with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2.
ab9f3b44-1365-5362-a4c1-541f86bed1c1 | note | ○ Granular filter material for bedding and backfill: Trench backfilled and bedded with specified material on drawings
0f6f5dd6-2903-5ee4-8291-1bba44c058bc | note | ○ Geotextiles: Shall comply with Cl 702.06.
bda877d0-7614-5dd2-84f3-10109c037aa1 | note | ○ Subsurface drain pits: All subsurface drain pits shall be Type S1 to the specification of SD 1611
66db865f-87a3-5fb3-b701-f0e393c31159 | note | ○ Pit Lids: Type M3 circular lid (as per SD 1051) for Type S1 pit
e0201722-d59c-5ca0-9815-b0bfe137ab11 | note | ○ Flushout risers: constructed to the detail of SD 1631
4a8e02a0-8aa2-51b1-8109-1bc93940242a | note | REFERENCE DOCUMENTS: 702.04, 702.05, 702.06
6477859c-3037-5c3e-80e1-25e8b764151e | note | INSPECTION/TEST METHOD: Verify
7b1f2d10-fc94-5dac-99f5-34f8d29a3b20 | note | RECORD OF CONFORMITY: This ITP signed off
4c2f705a-4c9a-53e0-8922-859ebacfe7e6 | note | WP
d57c8524-3f44-544d-bc23-318af335a425 | note | RESPONSIBILITY: Site Engineer
6d2ed859-9a81-58cb-a5df-e1219aed425b | textbox | Date Completed:
878fe94a-5cb9-43c6-88c5-2bb261ce3da8 | section | Construction Works
f8a8e235-57a3-4a74-99f7-9169b841cf0c | checkpoint | 2.1 Excavation Permit
3a2e6ebc-2c38-5a39-b303-aaebe37467da | note | FREQUENCY: Each lot
03d5974a-e342-5de9-bd55-2fa298b8ad92 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
7a5b27fe-e990-5a42-9ce4-d84f41a9234b | note | ○ Plant and equipment shall be appropriate for the task.
1716d367-4eba-57e7-b5c0-7e39d16d2825 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
27e65085-0a85-522a-9f85-af65b778fd65 | note | REFERENCE DOCUMENTS: Excavation permit
609f2f65-0ef8-560d-94a6-545139f38052 | note | INSPECTION/TEST METHOD: Verify
d6b8213e-9e35-5b8a-926b-c4561c81d7cf | note | RECORD OF CONFORMITY: This ITP Signed Off
c57d99cd-49cd-50b8-a841-028efe81a4d6 | note | HP*
a6492793-df94-5320-9b26-863052641569 | note | RESPONSIBILITY: Site Engineer
1fa876b7-69d3-54bd-842f-69a79c99f91a | textbox | Date Completed:
94f18aa5-13d5-4dcc-9faa-1a0454a6ed09 | checkpoint | 2.2 Excavation of Trench
9b4abfbc-4c11-5546-acb6-1f84b83b0791 | note | FREQUENCY: Each Lot
43b79965-b294-555a-95e3-fd70fe65a85d | note | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth no more than 50mm below the specified pipe invert. Grade of the base of the trench shall not allow ponding of water Any loose material shall be removed. To be inspected by Superintendent
161ab925-6311-5963-8d86-0c1316fb8967 | note | REFERENCE DOCUMENTS: 702.08
ac79771f-e715-5ef4-bbf4-bb0d40772730 | note | INSPECTION/TEST METHOD: Visual Inspection
83459e49-56a2-5e50-a87e-870b71ed61c6 | note | RECORD OF CONFORMITY: This ITP signed off
24fdbb0d-8854-5ba4-add9-cbee5f94fec3 | note | HP
bcc4a3d8-caa5-5b06-8f2d-6b20b0d19ddd | note | RESPONSIBILITY: Site Engineer/ Superintendent
ba4848c9-7d40-556a-b9e1-352dfdacbf2e | textbox | Date Completed:
63669dab-6b96-486b-8802-af59b3442b57 | signoff | AUTHORITY HOLDPOINT
d1acadba-963f-4e0b-99c1-d6577777ec45 | checkpoint | 2.3 Placement of bedding
52c26f50-8183-513b-abf6-507568896f9b | note | FREQUENCY: Each Lot
0666f915-8129-5d96-8e3d-1233694b4f5e | note | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
681f04e4-b82b-532f-a2dd-75eb7b06511f | note | REFERENCE DOCUMENTS: 702.09 (c)
50438924-b384-50a6-aeaf-a83350088790 | note | INSPECTION/TEST METHOD: Visual Inspection
21bf3cec-0016-579e-b840-e1d7a698dece | note | RECORD OF CONFORMITY: This ITP signed off
a87895f8-f9e7-5b07-ad81-bd5cb8e4adc6 | note | IP
ba4936b2-2954-5796-98bc-c34f2449b162 | note | RESPONSIBILITY: Site Engineer / Site Foreman
c473a25e-8178-50b7-9f35-fabf272cf9ff | textbox | Date Completed:
3f486bdb-8cd3-4014-90b1-e7488e7b240a | checkpoint | 2.4 Placing pipes and geofabric (if required)
34bb3a7d-d04a-5d6d-8b5b-df0939d7e440 | note | FREQUENCY: Each Lot
208da17d-0377-5ba8-ac05-e7c4db3eb814 | note | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe.
e7a629d7-1d60-50de-938d-02258b152d66 | note | ○ If geofabric required as per Cl 3030.07 (subsurface drains installed in expansive materials), minimum width of geotextile used for wrapping is 450 mm
abd6d338-1681-5e2b-9822-e8631ed9d48c | note | REFERENCE DOCUMENTS: 702.09
deb5ddb9-1d1d-5fd5-a1bb-7df90d458923 | note | INSPECTION/TEST METHOD: Visual Inspection
2f67644b-ead7-59e1-8fa1-cf3ebacf4140 | note | RECORD OF CONFORMITY: This ITP signed off
02297778-7b3a-5746-8cc1-0f1cb6e3a689 | note | WP
814d3041-592e-5011-aaa7-eec685c27d31 | note | RESPONSIBILITY: Site Engineer / Site Foreman
784a6770-c96f-54d9-88c8-86cbd2c1f9ff | textbox | Date Completed:
cbb3f0bf-034e-4155-84fe-1c8031564822 | checkpoint | 2.5 Placement of backfill
7abd3104-a5e4-5135-98c4-d9ac648c82b9 | note | FREQUENCY: Each Lot
efd7ca8d-361d-5412-aca2-50ff122794b8 | note | ACCEPTANCE CRITERIA: Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes. Concrete is to be placed and compacted within one hour of mixing
e8050451-cabd-5b32-bda3-cb948a69d78c | note | REFERENCE DOCUMENTS: 702.09 (g)
e7b54331-cfbe-5ac4-9729-871504d5ef8f | note | INSPECTION/TEST METHOD: Visual inspection
390ab2fd-a1a3-558c-bd56-de2caca41387 | note | RECORD OF CONFORMITY: This ITP signed off
3500ebfb-5aea-5027-adcd-d5271dd80ea8 | note | IP
06959605-653c-517d-9f6d-541db5148127 | note | RESPONSIBILITY: Site Engineer / Site Foreman
8cb98137-2cec-505b-9d18-fb38f866daa0 | textbox | Date Completed:
581e4c57-ede1-44c8-882e-f1f81abe6cde | checkpoint | 2.6 Install Pits and Flushouts
9ef37deb-ce30-58e7-89d5-2d555be6b08c | note | FREQUENCY: Each Lot
0d48f6cf-3834-53fc-87fa-6c67d7a9e864 | note | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
8e3bb24c-a0b5-5968-9351-80eb5e66fb5a | note | REFERENCE DOCUMENTS: 702.1
16be2c11-d24a-589a-9ab5-70572ea4ac53 | note | INSPECTION/TEST METHOD: Verify
55468630-58ed-5a83-863f-bb7048a1883e | note | RECORD OF CONFORMITY: This ITP signed off
af80e72d-569c-5ce5-936a-663fcb0155eb | note | WP
71a4406a-6b14-504c-add5-ff087dcefc4f | note | RESPONSIBILITY: Site Engineer / Site Foreman
5622050b-15d7-5809-be56-dd640d2e9044 | textbox | Date Completed:
4c701a43-1100-4d77-ba58-2b115b31a505 | checkpoint | 2.7 Flushing Test
b7d4d4fd-c408-55e0-8ec5-1864b4ba80df | note | FREQUENCY: At completion of stage
32f59de3-90b8-58d0-9390-ba370f290b5d | note | ACCEPTANCE CRITERIA: All subsurface drainage lines constructed shall be inspected, after completion of the flushing test as stated in clause 702.09(h) and prior to placement of asphalt, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
032bf1c7-a80e-5212-a677-4d52503435c7 | note | REFERENCE DOCUMENTS: 702.09(i), 702.09(h)
493ef4f6-a210-5517-84f4-58877f61080f | note | INSPECTION/TEST METHOD: Site inspection
d9c680b3-0d49-568a-8828-ee6b564d029a | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
f5263b15-5938-52e1-8d2b-02d72091db55 | note | WP
6b8b403f-c350-5574-ad3a-5086b40fdc77 | note | RESPONSIBILITY: Superintendent / Site Engineer
f0c1e87f-7669-55d7-a76e-e61108092fbd | textbox | Date Completed:
e7afa08e-f8d2-4322-8375-83ad825d8579 | checkpoint | 2.8 CCTV
6ef6febf-062f-5747-849c-48aaaaedb9c4 | note | FREQUENCY: At completion of stage
7647d8b2-a016-5f86-b92e-b278eb474a5f | note | ACCEPTANCE CRITERIA: Placement of asphalt shall not proceed until the CCTV inspection and flushing test have been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition of subsurface drainage lines has been verified by the Superintendent.
afda4522-3eeb-5fab-977c-a3cc155f21c3 | note | REFERENCE DOCUMENTS: 702.09(i)
a196762e-b41e-5955-b535-1c4862106e60 | note | INSPECTION/TEST METHOD: Site inspection
d7c2042a-3820-5e24-9e20-33167256198e | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
749fb1a3-1c1d-5d55-8ea8-bd84ee4bf2c0 | note | HP
433fdb4a-b83c-5d46-ac77-f69b8f742669 | note | RESPONSIBILITY: Superintendent / Site Engineer
7cfb24f6-4f48-5841-bfab-d9417da0d649 | textbox | Date Completed:
f7c0f759-336f-41b4-b55f-8775577010e1 | signoff | AUTHORITY HOLDPOINT
9389b7ca-8d01-4cae-8964-8b9a59711f16 | checkpoint | Final Inspection
46e2e72b-d855-56d9-9dc1-354f5628ee2a | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
116dc2a0-5a5d-56f2-83a1-0c11896442e7 | textbox | Print Name:
901de5d0-e3ea-50ac-bb40-bbfcfd60305e | textbox | Position:
ff8ff498-a4e1-5fce-99ea-2724d1a072fa | textbox | Date:
664702e2-c4ca-4b09-9f16-7cf3772b2039 | checklist | FHC-ITP-015 - Kerb and Channel Rev4 | itp | FHC-ITP-015 - Kerb and Channel
8aea0a5a-3ebf-489c-a529-a6065cd84d39 | section | Preliminary Works
c7e67f7a-1bbb-4e13-a535-4a817b04cc21 | checkpoint | 1.1 Check for correct documentation
c7f2bcee-75fc-5959-b89f-7010ce9fc024 | note | FREQUENCY: Prior to commencing any activity
2aab3acb-60b3-51dc-bb79-f70b855f276c | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
71753036-4264-5deb-8d0a-3f3d40f56504 | note | — using the correct and complete set of drawings
683fd5ac-9997-587f-b338-00f4622045a0 | note | — all drawings are the latest revision
898c9ef6-74d1-582c-9d63-3715a1d65f8c | note | REFERENCE DOCUMENTS: Drawings and drawing registers
0890a087-4cdd-5c5a-b63e-20af2526b87f | note | INSPECTION/TEST METHOD: Visual inspection
6dd6752a-d2c5-52a8-92cd-f64bb753d025 | note | RECORD OF CONFORMITY: ITP Signed
40fed917-59e6-58f4-a012-493c97e87d67 | note | HP*
7085e523-6a52-56ca-81ee-e0b64f72c5a1 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
6f6c0860-f0b6-5da3-89b4-124394178c52 | textbox | Date Completed:
e22a50b3-ee42-4b38-8fc0-9d5c74884a19 | checkpoint | 1.2 Implementation of all measures and controls
3a194e44-b0bf-5912-9255-4a0e04a35ae3 | note | FREQUENCY: Prior to commencing any activity
799b0d92-9eb3-53af-86e4-78b8c2eb02ae | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
a4f19642-3e78-5fc1-bd68-7d88d5a8ae93 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
4062e8c1-02ea-5a10-8cef-9b2a5812e729 | note | INSPECTION/TEST METHOD: Visual inspection
be00c494-2ea4-517c-9225-69dff05c08f0 | note | RECORD OF CONFORMITY: ITP Signed
7635ca72-7213-54a2-899c-c9cf112d321f | note | HP*
c86e3c2b-a19f-5fb3-b13d-864a13f23b05 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
4285e753-e1f2-5610-8b72-0b85e8ca57c6 | textbox | Date Completed:
2e3038d7-8f66-4e1f-b390-eb3108a5884d | checkpoint | 1.3 Material Approval
bbc91805-2793-567c-9128-9102182bdde8 | note | FREQUENCY: Prior to Placement
3a182faf-8f74-55a1-9913-f88eee55de39 | note | ACCEPTANCE CRITERIA: Material intended for use is to be submitted to the client prior to placement to verify it conforms to required specifications.
d61b973b-5c2c-53e8-b84d-955c0927d163 | note | REFERENCE DOCUMENTS: Material specification sheets
5de38d63-e01e-5404-a1d7-c072b9da6af9 | note | INSPECTION/TEST METHOD: Verfiy
21a65146-436e-55d0-821c-e0317f9c00b1 | note | RECORD OF CONFORMITY: Teambinder Acceptance
5d43e576-5574-5a26-bd0e-fc62e62d77bf | note | HP*
62946435-30f8-50a8-a47e-4f5bac139b5f | note | RESPONSIBILITY: Site Engineer
78fd6bfc-4f52-5db5-97c2-7d71a4fd5aac | textbox | Date Completed:
d1f7fc6e-bef4-454f-a35d-5870f3f02f59 | section | Construction Works
d1e3591c-dc3d-4d46-8bc1-9f0a7771bf08 | checkpoint | 2.1 Setting Out
d53912c5-c5ec-5c5f-82fd-89549311d7fa | note | FREQUENCY: Prior to start
8b5e059d-0494-5bbe-9673-da314afc5e9f | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
0e0e2a22-9230-53dd-8825-a3ae150808e6 | note | REFERENCE DOCUMENTS: 703.17
374c34ab-70c1-518c-858b-d3bef521e893 | note | INSPECTION/TEST METHOD: Verify
2c115ab6-cea3-5b1d-a187-bf2ecd36c951 | note | RECORD OF CONFORMITY: ITP Signed
fae0d02f-db92-5ba8-ba6e-a02dc6e93e9f | note | HP
2dddb20d-c097-5fd7-9cb8-4136b5cf477d | note | RESPONSIBILITY: Site Engineer/ Superintendent
fed66593-74d1-5a0b-9a61-52ce69d5560e | textbox | Date Completed:
9fe27e00-9ea8-4e2e-a154-682ef6b47993 | signoff | AUTHORITY HOLDPOINT
8874e1a9-7e0d-477a-8392-7d5a357fec3a | checkpoint | 2.2 Temporary Drainage Provisions
e4cffafa-697f-576d-99ea-440b63a40fca | note | FREQUENCY: If Required
f3568264-ea97-5ec2-9d68-d687bae3d667 | note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
6dd221a2-5af5-50c2-8c82-88a86f116caf | note | REFERENCE DOCUMENTS: 703.18
080c1406-0fd1-5b69-8d8c-1411baca5b20 | note | INSPECTION/TEST METHOD: Visual inspection
ff7acf78-41e4-5694-bf54-8767f31d61e9 | note | RECORD OF CONFORMITY: ITP Signed
f845531f-5877-5120-98bc-9fb5d474cbfe | note | WP
47b8603e-2275-51e7-a9b6-0a7a083c8960 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
e5422ee3-2fdd-5a83-aaf2-289d50930a7c | textbox | Date Completed:
75686aa2-0605-4428-a65c-bace3eef9df6 | checkpoint | 2.3 Bedding
b226f648-ae1f-5567-9716-d345d17f0674 | note | FREQUENCY: Each lot
692e0b27-1e32-5162-9028-7f6866ba6761 | note | ACCEPTANCE CRITERIA: All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively.
e33edb42-de8f-562e-97ab-804df52fdd84 | note | ○ Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used adn compacted to a thickness of not less than 100mm.
1d4e57cf-1673-5d35-9a04-0aa2e2c1cc2a | note | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
9b39138a-7061-56a3-b982-fd1acc66962c | note | REFERENCE DOCUMENTS: 703.21
049f2f6e-49ed-575c-bae9-d4fb8351a834 | note | INSPECTION/TEST METHOD: Visual inspection
50248906-5f0e-55da-8327-8b88669fa423 | note | RECORD OF CONFORMITY: ITP Signed
03456d75-0909-52d4-9bab-a41f4aff762c | note | WP
a9622080-5de1-5447-bb94-a8f25c4904d0 | note | RESPONSIBILITY: Site Engineer/ Superintendent
26855d3b-2492-53ec-a7b0-7c3c95b10244 | textbox | Date Completed:
f779a935-35ce-43aa-9076-75ca5f14e561 | checkpoint | 2.4 Pre-concrete check
a55c9813-0826-50ec-b012-2d12110aeb76 | note | FREQUENCY: Each lot
0b024c09-bb40-54b5-97f3-d6166b42b61b | note | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
d0a98d90-1f49-55da-a5bc-7e2563cb2bc8 | note | ○ Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C.
f7d3f463-4b0f-593b-b397-3db58b2775a7 | note | ○ Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
cf3e540f-97c8-5d25-8627-8ab5400a3467 | note | REFERENCE DOCUMENTS: 703.08, 610.17(a)(b)(c)
bd78e0a3-e817-532a-ab16-5829fa6ad3b9 | note | INSPECTION/TEST METHOD: Verify
98d79fa5-8168-5041-a9d8-67a4ab44e2f7 | note | RECORD OF CONFORMITY: ITP Signed
d0a75efe-709b-54dc-ae94-316278f0d035 | textbox | Ambient Temperature |  |  | °C
4c41b515-d017-5af7-83fe-21b91e1307c9 | textbox | Concrete Temperature |  |  | °C
b94ea9a4-b72e-531a-add4-bce7059f47b1 | note | HP*/ WP
dc57f17c-7255-5e01-bf02-50ad50cf912a | note | RESPONSIBILITY: Site Engineer/ Superintendent
b5847be9-55c3-5aea-a84e-5b68fe34d06c | textbox | Date Completed:
19e4f9ab-b68a-40be-b60d-fc370402c631 | checkpoint | 2.5 Concrete Placement
90a30e0b-272e-5a4e-9e81-be83b807104b | note | FREQUENCY: Each lot
6eeecb61-44c8-5b5f-af2f-cb3ea85f7609 | note | ACCEPTANCE CRITERIA: Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
9a8348f3-f19d-5e64-b86c-b88e61f7734b | note | REFERENCE DOCUMENTS: VicRoads Spec 703.23
5eeb1416-f328-509a-a5ba-00ee4294713f | note | INSPECTION/TEST METHOD: Site Inspection
81f371df-7b37-5322-a588-e427dccd4b21 | note | RECORD OF CONFORMITY: ITP Signed
ce242f80-e62e-5be5-ace3-6baf5a74bedc | note | IP
62e7c279-767d-5970-a786-247da3940209 | note | RESPONSIBILITY: Site Engineer
b06a04af-a171-52a7-9afb-607be482a769 | textbox | Date Completed:
d75ccad2-e50c-48e4-87f4-af350996cfe0 | checkpoint | 2.6 Finish Surfaces
db5b3f97-d5c5-5d74-b680-26fc8ecc1bea | note | FREQUENCY: Each Lot
7eabd5d7-29e2-5251-93d0-7096a9591c1c | note | ACCEPTANCE CRITERIA: Edgings: rendered to a thickness not exceeding 3mm and trowel finished.
a6614d1c-1544-5b6c-9a05-4db87e99869d | note | ○ Concrete to have a neat appearance and uniform colour.
b6760e61-4041-564b-a923-eec733f4dc23 | note | REFERENCE DOCUMENTS: 703.25
4d1aacc0-c65d-52ff-823c-3792ab7a2687 | note | INSPECTION/TEST METHOD: Visual inspection
bf182804-f5f9-55c8-972e-a4901ed5e045 | note | RECORD OF CONFORMITY: ITP Signed
e0238063-ab9f-547c-863a-c113e328490b | note | IP
0e641a99-4246-5ec1-ade0-a199ea4932ad | note | RESPONSIBILITY: Site Engineer/ Site Foreman
cd9d6d40-603b-56b7-b64c-dc0c3e454ca3 | textbox | Date Completed:
f195cd2d-5226-42b1-8263-dd7f4aae61e3 | checkpoint | 2.7 Tolerances
75a89b25-a70e-5cd5-8e77-7f3f27afdfea | note | FREQUENCY: Each Lot
ababaa58-87d4-5194-9478-1ed29adb3399 | note | ACCEPTANCE CRITERIA: Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of ‑0 to +10 mm. Except on curves or in shaped areas, the deviation of the finished work from a 3 m straightedge shall not exceed 5 mm at any point.
9a0c123b-1a3d-523e-be8d-e5b85323a72d | note | REFERENCE DOCUMENTS: 703.15(b)
d2b88e1b-89e1-5a11-ae29-bec6156b98a7 | note | INSPECTION/TEST METHOD: Verify
c5b04a77-c1af-5710-b181-b2b29bd59e5d | note | RECORD OF CONFORMITY: ITP Signed
88be59fc-d058-5830-9bdd-dadc104d7dff | note | SCP
1562c72f-fc49-5f0c-9db3-9bdb889cb7f4 | note | RESPONSIBILITY: Site Engineer/ Surveyor
7e605ec7-812d-5ee2-864b-e26f2d63931a | textbox | Date Completed:
1b944541-3294-483d-8d24-8bc0fc84c48b | checkpoint | 2.8 Joints
e89c79e1-244f-5762-b572-75fa1c3a510a | note | FREQUENCY: Each joint
9b26306a-78bd-51d4-a229-7593c0147a19 | note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
f38518d7-7e7e-5a41-9bb2-2828898091ef | note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
aab7a418-1784-52c3-912d-a00018adc116 | note | ○ Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
f635ccd6-b34e-59e1-af23-7937153f0290 | note | REFERENCE DOCUMENTS: 703.26
ea8bf413-fc9e-5355-8e7e-6117ef6ceb1e | note | INSPECTION/TEST METHOD: Verify
be4c3d92-1b54-5795-b7ca-5786ee75afcd | note | RECORD OF CONFORMITY: ITP Signed
e28a43df-b36b-507b-81bd-ef943d1a3d98 | note | IP
c70fa927-a9b0-5499-b52e-a3e0d8864e00 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
1c695ca5-aeba-5a23-a11d-ebd0710f08cb | textbox | Date Completed:
ded70c7a-589c-4162-939f-9794f9a16ca4 | checkpoint | 2.9 Backfilling
57341e63-8275-5b3f-b795-34a85bf03f7e | note | FREQUENCY: Each Lot
9b55f4da-1cce-5662-bb46-060bc540c20e | note | ACCEPTANCE CRITERIA: Not earlier than 3 days after casting.
105adaf2-2c6b-5347-aad0-53d65ade40f4 | note | ○ Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified.
baf59462-d3cc-5f46-9773-1201cc7d40d4 | note | ○ Layers shall not exceed 150mm compacted depth.
1ad95f28-135c-5146-ba6f-e249e260db3a | note | REFERENCE DOCUMENTS: 703.29
dcfee2ac-c1c4-5080-b2a3-b71e21d1fca5 | note | INSPECTION/TEST METHOD: Verify
85fcee23-1db3-5e3c-9002-9ce324415579 | note | RECORD OF CONFORMITY: ITP Signed
b574113d-b1c8-5eed-99ff-caa5c13a1cbc | note | IP
e407da86-a7f7-5a27-ae37-496a7b304302 | note | RESPONSIBILITY: Site Engineer
6696d4ea-984a-595d-8a22-07bc8308cf1a | textbox | Date Completed:
4ee3058e-60ca-41af-b4db-2ea44a167ac6 | section | Completion
32b91fb7-3f08-4a6e-831d-15c42029ce8b | checkpoint | 3.1 Survey data captured for as-built purposes
dfa77531-99f7-5fe8-ba36-a3f3a56e8e33 | note | FREQUENCY: Completion of each lot
0bc29356-f171-5c4d-a04d-56a477ae89ff | note | ACCEPTANCE CRITERIA: Survey to ensure and validate that all works meet level requirements. Review of existing survey control marks and any additional control marks providing verification of conformity of as constructed features with design. As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
35d6806c-1cbd-5fa7-be04-a3d343f9e9b4 | note | REFERENCE DOCUMENTS: IFC Drawings / survey records
f7b13099-6fff-50eb-9821-3e8f5423ef28 | note | INSPECTION/TEST METHOD: Document review
139ff524-64bc-56ec-9856-10b515cb82fd | note | RECORD OF CONFORMITY: As-built survey records
47dbe532-2cda-54e3-9e71-a09d32d9c323 | note | SCP
5e6a46d7-ab4b-5b25-9ee3-c40e536eb149 | note | RESPONSIBILITY: Project Engineer/ Surveyor
75670bfd-d31a-57af-8eb8-41bf01d16cd9 | textbox | Date Completed:
6ab18681-5c3a-48df-9218-414df2528a2b | checkpoint | Final Inspection
a02ba8e0-77ad-5577-a7cc-b2fb942929a0 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
7bd00567-603f-5945-899e-82c6419f5710 | textbox | Print Name:
c0d07e13-6bb9-5cd5-bd3e-dbdd4b05276a | textbox | Position:
61e41440-cbbb-52fd-ad73-178cb01b1f3d | textbox | Date:
6f330fdc-4e54-4072-a184-e8da757584bc | checklist | FHC-ITP-016 - Sign Installation Rev2 | itp | FHC-ITP-016 - Sign Installation
44b612ea-d80b-461a-9cb3-b1d84adf4d1a | section | Preliminary Works
7ca78027-86d6-403a-854e-035da2026e02 | checkpoint | 1.1 Check for correct documentation
51c31ffc-99fd-564c-9caf-a468a5d6a806 | note | FREQUENCY: Prior to commencing any activity
ea1653ad-823d-5f75-8e24-7905dabc0f93 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
5e308375-71ff-5580-86b8-9b3082d2539b | note | — using the correct and complete set of drawings
d3cb3dc9-c3c9-5f97-8204-cfcd17c4891f | note | — all drawings are the latest revision
cb2e9ec0-bb05-52d3-b864-bc9450895ea1 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
0f4557af-33f5-5e6e-8899-ddaa88470009 | note | INSPECTION/TEST METHOD: Visual inspection
93607465-0300-59eb-9a71-d1f566513d11 | note | RECORD OF CONFORMITY: This ITP signed off
771dfad7-08da-5089-8b77-baee3631c799 | note | WP
7e9d8c5e-635a-5aee-89de-eb53150d5d47 | note | RESPONSIBILITY: Fulton Hogan Engineer
4270287f-1415-5c9b-b178-b195cb72facc | textbox | Date Completed:
11d6f32f-2285-4e2f-88fc-def63b6c53e3 | checkpoint | 1.2 Implementation of all measures and controls
33de9830-5094-51a0-8cde-8592f8a6149f | note | FREQUENCY: Prior to commencing any activity
fa8d95a6-c4e3-50b7-a627-be7b8bc7014c | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
5c107500-2465-5ab2-bd98-5c1b8cd62949 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
f796be56-6487-5f4a-9810-5824f8f275bf | note | INSPECTION/TEST METHOD: Visual Inspection
01135579-83ee-52bd-a320-01317731b116 | note | RECORD OF CONFORMITY: This ITP signed off
88ce0bda-5641-5c1f-a63f-8dbab47cdb9f | note | WP
c8c346e4-071f-5eea-b1e3-b90fe3d5d913 | note | RESPONSIBILITY: Fulton Hogan Engineer
1bd91493-c7cb-55d0-bb6e-bd38071d02e8 | textbox | Date Completed:
8f1092fb-44c6-4a61-aea9-024e80f14b7f | checkpoint | 1.3 Signage Conformance
e71eea4d-547a-5bf5-a165-0a1a4ce54112 | note | FREQUENCY: Before commencement of activity
b2a93c37-d827-5fba-9c38-d114a2423e1c | note | ACCEPTANCE CRITERIA: Ensure sign size and immage correspond with contract drawings and meets specification
1104f4b8-dff4-5b72-93d7-e34efed54247 | note | REFERENCE DOCUMENTS: Drawings AS 1742
fb4ca6d0-eced-5c34-adf5-fea9415de63a | note | INSPECTION/TEST METHOD: Verify
e62f1860-f449-584f-9ad1-e7b9ea9d1179 | note | RECORD OF CONFORMITY: This ITP signed off
452c76d9-6fd8-5d9d-b102-14b0d824b19d | note | WP
faccadf3-8789-5a31-97a4-7286c027e08d | note | RESPONSIBILITY: Fulton Hogan Engineer
a4032da8-ae28-5168-943a-b334502264f9 | textbox | Date Completed:
ebb7a1f7-b977-4daa-88cf-dce3f76b7185 | checkpoint | 1.4 Service Identification
9dc1f94a-03f3-558f-8fc9-671ab674aa44 | note | FREQUENCY: Prior to start
79bd5d27-2b16-5342-8621-75978207a875 | note | ACCEPTANCE CRITERIA: Check for any services in proximity to points of installation or coring for spigots
f8e07d01-10c5-54ce-b5ad-c1f1db063dc2 | note | REFERENCE DOCUMENTS: DBYD, Service chart
af7d0d74-45ef-58a7-aa88-f06d1b0e18af | note | INSPECTION/TEST METHOD: Verify
d0fedd2e-5ac1-533e-b431-55c1d80151d2 | note | RECORD OF CONFORMITY: This ITP signed off
c07b943b-42f6-5cc8-bc94-eac63eace894 | note | WP
3d1e637f-87c7-5964-a643-a5f5b7878541 | note | RESPONSIBILITY: Fulton Hogan Engineer
27cad07e-a00d-520b-9d6a-8455a457a40f | textbox | Date Completed:
b6566d58-d704-4168-97f2-d6decdfaf4e4 | section | Construction Works
37cd4a1b-f845-4d07-8b26-b3b820070085 | checkpoint | 2.1 Setting Out
4dcf6547-60e5-53da-a0c0-b1c9b5ce8414 | note | FREQUENCY: Prior to start
48ae6280-9533-531b-8f39-256aacc7a112 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections.
15a9e805-0e79-543a-9d12-af36de4321a3 | note | REFERENCE DOCUMENTS: Drawings
5ee57cca-5a74-5570-89f4-3156a879072e | note | INSPECTION/TEST METHOD: Visual Inspection
10aba41a-a4ae-52c1-a2e9-978194886aba | note | RECORD OF CONFORMITY: This ITP signed off
f87d9a1d-b674-5c4b-98a2-5221e8aaddef | note | IP
ceac7250-ee97-58ce-8e56-c805ecd2d966 | note | RESPONSIBILITY: Fulton Hogan Engineer
7f7161c6-df5e-5cb3-a809-ebdc1f27aaba | textbox | Date Completed:
8dd4436f-42db-43d2-9b14-67aed20e3f4c | checkpoint | 2.2 Post & Foundations
a1997444-6e5c-5a73-b85f-8030fa630881 | note | FREQUENCY: Prior to Start
07ae0a25-d20c-5e15-ad85-395ee8b82b1d | note | ACCEPTANCE CRITERIA: The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences.
7b1d3818-f610-5b39-bf25-08ba410b9194 | note | REFERENCE DOCUMENTS: 714.06
88997464-3434-5f33-92f0-dc0b34a0a1fc | note | INSPECTION/TEST METHOD: Visual inspection
3aca9d9b-fb84-5bb8-a4b6-c693421f6e82 | note | RECORD OF CONFORMITY: This ITP signed off
388ea0b3-bffa-5619-9f8c-e3cdda73a48c | note | HP
233e296d-0b89-586d-9683-b685e7fd698a | note | RESPONSIBILITY: Superintendent
d401b2f7-f6e1-562d-a025-9d8ee470d36b | textbox | Date Completed:
6f9d576f-4b86-4ad3-bc4f-e70803156cd5 | signoff | AUTHORITY HOLDPOINT
d264ffb6-08d9-418b-a1ff-f57ca1d18524 | checkpoint | 2.3 Signage Install
3990914f-634b-5d49-a357-ff2c93b11df0 | note | FREQUENCY: Each Sign
d79a1663-2178-50ff-8e26-2542c2d7b339 | note | ACCEPTANCE CRITERIA: Sign to be installed as per most current drawings, local council documentation, and to the correct height and position.
66338e5f-7ab4-5cae-b888-85703548f177 | note | ○ Spigot embedment shall be within +/- 5mm of design horizontal position and +10mm of vertical design position
279b4d2a-7adc-52ed-ad5e-6af1e3605861 | note | ○ Signs specified to be re used are to comply with AS 1742 standards, and must be replaced if deemed in unsatisfactory condition
e791c5bf-abc3-5e11-ae67-7cb2862a9022 | note | REFERENCE DOCUMENTS: AS 1742, TS 1313 Drawings
36c31dbb-cd15-51f6-84ef-e00d960f1a3d | note | INSPECTION/TEST METHOD: Verify
a861c5a0-31ad-59d9-8a07-238d80ec8c65 | note | RECORD OF CONFORMITY: This ITP signed off
5325223c-28d7-55af-97e5-d87384e5454c | note | WP
cd722681-eafa-5e50-b0bc-852ceee6d102 | note | RESPONSIBILITY: Fulton Hogan Engineer
0e1e4a0d-a1e9-56ac-b55b-a8b447ed8f46 | textbox | Date Completed:
ae0529fc-07b8-4920-822c-ef202a84c145 | checkpoint | Final Inspection
7b6429b2-d89f-5617-8d38-4705fe9beed6 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
0201d773-a8aa-5824-b1b7-8b6d143b15a3 | textbox | Print Name:
09a63f4c-9271-5da5-8fc8-4b53cf515854 | textbox | Position:
b934ec71-0870-5682-b8a8-043af8b26e7f | textbox | Date:
687becc0-d63f-4dff-a1db-39f055ee6c7e | checklist | FHC-ITP-021 - Type B Fill Placement Rev4 | itp | FHC-ITP-021 - Type B Fill Placement
094e165f-67a0-45ed-896b-0975d408273e | section | Preliminary Works
bb351037-b7a7-49c8-8518-13364601dc59 | checkpoint | 1.1 The current revision drawings/documents are being used including subcontractors copy.
0543e8db-c60f-546f-b98d-4d78317dba92 | note | FREQUENCY: Prior to commencing
03d0236c-e610-5b1d-b97c-677237efd278 | note | ACCEPTANCE CRITERIA: Current revision drawing/documents are being used including the subcontractors copy.
97c1eb3d-0ab0-5922-9342-25115ea87bea | note | REFERENCE DOCUMENTS: Drawings and drawing registers
feb1af32-c533-5612-b6f0-c1fae74d8f1c | note | INSPECTION/TEST METHOD: Visual Inspection
fb8350cd-a588-50c4-9184-5f736d0169dd | note | RECORD OF CONFORMITY: This ITP Signed Off
85b675b4-ed02-5f6e-9bce-74ec54c6c182 | note | HP*
f395d5d6-f49d-58d8-b323-141796b9d54b | note | RESPONSIBILITY: Site Engineer / Site Foreman
999a4121-82d4-540c-93c7-03dd2e0ff3c4 | textbox | Date Completed:
df976f5f-8df4-4381-9b5e-343846564590 | checkpoint | 1.2 Implementation of all measures and controls
06aa1e78-2a5a-5a02-87ea-a9d37d96928e | note | FREQUENCY: Prior to Placement/ Each Lot
5814c081-2332-5c03-8c6c-9d159055cd43 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
cdd713fe-8aee-596b-8bc6-71cd374af291 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS, WP001.02
f893648a-7f5b-5504-809f-4644fd86655a | note | INSPECTION/TEST METHOD: Visual Inspection
f46833a4-5fd1-54ef-ac87-3218c53e8e4d | note | RECORD OF CONFORMITY: This ITP Signed Off
34f727c9-08a3-5c0d-8be4-0b712c5d35f7 | note | HP*
ab870315-dd08-5f23-be65-458b2d44c2aa | note | RESPONSIBILITY: Site Engineer / Site Foreman
58aa00a9-acd5-5137-8c64-70c1ac9d21a3 | textbox | Date Completed:
d4d58560-50d3-4f0c-a004-6c80523682aa | checkpoint | 1.3 Verify Material
8333516e-1898-5106-8f43-ce5a9261492a | note | FREQUENCY: Prior to Placement/ Each Lot
107561ac-e8d9-5212-a95e-0f95a09ac441 | note | ACCEPTANCE CRITERIA: Type B material shall have a minimum Assigned CBR of 2%, and Assigned Percent Swell less than 2.5% which has been determined in accordance with VicRoads Code of Practice RC 500.20. Materials that exhibit swells greater than or equal to 2.5% shall be classified as expansive and shall only be used as Type B material if approved by the Superintendent. Material within the top 400 mm of top of Type B material shall have a swell less than 2.5%. Materials that exhibit swells of 5% or greater are not permitted.
d82f9a0e-d367-59b4-9ab8-6df7e9b409cd | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04(c)
18a0d131-0c03-558d-891e-d6960c319839 | note | INSPECTION/TEST METHOD: Site Inspection
bd751642-929d-5bb2-86f0-bed11398e87a | note | RECORD OF CONFORMITY: Test Record (If silt is observed)
dc596aa2-fd94-5a95-8ff7-7d325ffcb71c | note | HP*
3c4b5e97-fe70-5b7e-aea1-77222ea63815 | note | RESPONSIBILITY: Site Engineer / Site Foreman
475c49cc-1300-5384-ba43-a0e36584fb7c | textbox | Date Completed:
07a3d3e0-7875-49ab-bd91-53e7ed16efc8 | checkpoint | 1.4 Excavation Permit
bdf47b6f-0c2c-5e14-8e44-532e97a8cd8a | note | FREQUENCY: Each lot
9831fa8e-6482-5142-be87-e1874d492062 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material.
0203eb38-d862-579c-a142-149cd67bcf7f | note | ○ Plant and equipment shall be appropriate for the task.
b088d731-4e32-59c2-a64e-8cc16cb9e525 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
37533979-07d7-58ea-9718-c70f33d04053 | note | REFERENCE DOCUMENTS: Excavation permit
577caaeb-b3a7-5967-b0ed-950f8332385b | note | INSPECTION/TEST METHOD: Verify
6db44326-a79f-54de-b4b9-72ed326235a9 | note | RECORD OF CONFORMITY: This ITP Signed Off
3afeae2b-c63b-5808-a5be-6c72ae6611ea | note | HP*
cbe50c30-8fac-5566-8db7-7275f000a6bd | note | RESPONSIBILITY: Site Engineer
03626489-b9c1-5eb7-8f9b-8dee3a24e4d9 | textbox | Date Completed:
baa7b4e4-7d9c-4f3f-ad88-f19b65c75614 | section | Construction Works
4f4fa2b1-f7ba-4345-8b9d-154b34688cca | checkpoint | 2.1 Survey set-out
5ed0ee41-aa0e-5e90-a77f-b380e8e68860 | note | FREQUENCY: Prior to Commencing Excavation
0df6784a-ec46-5ab3-bcb3-ea86e4a0870a | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used
a380e5e8-ff30-53e8-936e-1d7f162cbb4b | note | REFERENCE DOCUMENTS: Latest IFC Drawings
1549db6f-4a75-587e-9c58-f54e1e571e3d | note | INSPECTION/TEST METHOD: Site Inspection
7e713c4e-04e0-572f-b660-4f1b1691939b | note | RECORD OF CONFORMITY: Survey records & pegs on the ground
e739891c-ca0e-5c74-88d4-e2841903e437 | note | SCP
4ec25298-496c-575b-8552-ca64f5d1a6c2 | note | RESPONSIBILITY: Site Engineer/ Surveyor
1bea4d23-ef40-5114-9573-453b4a251c47 | textbox | Date Completed:
01a3de0b-330e-4d86-9cf6-ad49ff8d9197 | checkpoint | 2.2 Inspection of fill area
232fae52-5191-5d90-ae39-7b495ad05fb7 | note | FREQUENCY: Each lot
6173fd58-e937-5039-a8c7-f01d6d94d15b | note | ACCEPTANCE CRITERIA: The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
532303b2-4f30-5da9-9087-2f22d07bf028 | note | REFERENCE DOCUMENTS: 204.10 (b)
a484d2c7-f6a6-563f-9dde-e7a0a12a9805 | note | INSPECTION/TEST METHOD: Visual Inspection
7bd6e830-b169-57f2-bf26-40ee8bae152a | note | RECORD OF CONFORMITY: This ITP Signed Off
df03f8db-16b1-555e-b942-6b3481900b2c | note | HP
9fc6cc1d-7500-5c87-99bd-6988aefd1890 | note | RESPONSIBILITY: Site Engineer / Superintendent
20ff8908-d7ba-58c4-a53b-cb9b3aa505fd | textbox | Date Completed:
0fa4b2c6-a5ed-4ea0-9552-bb3eb2d82631 | signoff | AUTHORITY HOLDPOINT
217baa5b-2800-49d8-8e08-0142bd824fc8 | checkpoint | 2.3 Keyed fill layer
81d50090-2b28-557b-b5cd-4673881c3348 | note | FREQUENCY: During Excavation
3b1a0cc0-bfd9-5ba1-8d2e-c5093b3032cf | note | ACCEPTANCE CRITERIA: Placement surface textured to ensure layers keyed into each other.
8d3b3a70-ee4a-5bf4-95da-ef953d3bda0d | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(i)
2bb0dbfa-918e-5183-a255-d29bbc271dd9 | note | INSPECTION/TEST METHOD: Visual Inspection
6e9469d3-bec8-55be-94aa-e61ba4574a2c | note | RECORD OF CONFORMITY: This ITP Signed Off
8e741b2d-34fa-5658-9fc1-9aa8d82137bb | note | IP
31558378-b9a0-51b9-a51b-8de595c9ab61 | note | RESPONSIBILITY: Site Engineer
7801d4f1-4e1e-52d5-816c-f124f44a27f5 | textbox | Date Completed:
999b0940-a0ef-4e93-ae10-fa31dc52e22d | checkpoint | 2.4 Layer Thickness
a36b17ab-d293-502d-9b16-a4b907042f1d | note | FREQUENCY: During Excavation
28a04f86-c87e-5846-90f3-cf0a4dee280a | note | ACCEPTANCE CRITERIA: Layers placed and spread in uniform compacted layers not thicker than 200mm.
cf75caec-579a-599f-90b2-f543b4bcea31 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(iii)
d0593dce-47f6-5d50-ac74-30097e74f9f8 | note | INSPECTION/TEST METHOD: Visual Inspection
09428ce9-d416-5923-81e6-91cbca7e257c | note | RECORD OF CONFORMITY: This ITP Signed Off
a167f6e6-df35-5abc-9d9a-0737cbf37789 | note | IP
2d15ef98-e778-550a-aca8-d2082e6ecf65 | note | RESPONSIBILITY: Site Engineer
3c078be5-3bde-5e72-9929-2fed238aa30b | textbox | Date Completed:
db2d411c-517b-4493-90e9-f18be68819a7 | checkpoint | 2.5 Maximum Lot Size
b4ce5ff9-a2b1-5a6e-b001-13b0d2d94a7f | note | FREQUENCY: During Excavation
ecca13c0-c32c-5db6-b23c-253121fa87e5 | note | ACCEPTANCE CRITERIA: Lot size for testing is to be one day's production or 10,000m2, whichever is lesser.
7f3d1789-9478-5267-a226-4d7dea26c5f8 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.142
7c632949-0fc6-546e-844f-2dff19f3e0fe | note | INSPECTION/TEST METHOD: Visual Inspection
d3ed5797-a7ae-5ba2-99db-4ea6af9d02a9 | note | RECORD OF CONFORMITY: This ITP Signed Off
38ae933e-9d22-539d-b2b1-cc494d812710 | note | IP
74dc5421-f77b-521e-aba0-952fc5003291 | note | RESPONSIBILITY: Site Engineer
c5e778c9-aae2-56da-9ba0-97102a3f7d18 | textbox | Date Completed:
554f7ccc-8f6e-441a-8ba2-8405e7dfa092 | checkpoint | 2.6 Type B Placement
b2ff81d1-7c83-5c69-90d2-d3cd800dcb2d | note | FREQUENCY: Prior to Placement/ Each Lot
6308c50b-9f66-54e3-b012-c435a9d2a93d | note | ACCEPTANCE CRITERIA: Type B material shall be placed in locations shown on the drawings, or if surplus Type B material is available, it may be used in locations specified for Type C material. The highest quality Type B materials available shall be reserved for placement in the higher levels of Type B fills being constructed. Type B material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
32dc6a73-747a-56ee-ad95-ee8667320876 | note | REFERENCE DOCUMENTS: 204.10 (d) (iii).
68742937-4143-5cf9-98fe-b8bd5336c51b | note | INSPECTION/TEST METHOD: Visual Inspection
cfcca354-1709-5896-9a9d-a6437885849d | note | RECORD OF CONFORMITY: This ITP Signed Off
8b684831-aff5-56db-b7a5-b8cc8b49831d | note | IP
c4c92a34-6666-52a2-b6a8-e497192b455a | note | RESPONSIBILITY: Site Engineer / Site Foreman
2d1f6bca-19dc-5ade-8b3f-d92de04a14cc | textbox | Date Completed:
6dbc15f1-aa71-44f7-bb40-d58ae60e0738 | checkpoint | 2.7 Proof Roll
cc388c4e-e4a8-57dc-96f3-9732f5d0bc06 | note | FREQUENCY: Each lot
3cecbf47-8741-5d56-8551-0034b27245e2 | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
86fdf175-22b3-563e-b1eb-bd125ce22a95 | note | REFERENCE DOCUMENTS: 173.03, 204.12), 204.10 (b)
0cf15e7a-08d2-58ec-bed2-be2f2b9d0faf | note | INSPECTION/TEST METHOD: Visual Inspection
34fe58d1-dfa6-5045-97e6-9aa8ffdfa070 | note | RECORD OF CONFORMITY: This ITP Signed Off
64229ffe-a54e-5fa4-be66-381ae49a0280 | note | HP
f0160ec5-8365-5405-b047-1050cf2964a7 | note | RESPONSIBILITY: Site Foreman/ Superintendent
97897c2e-b08a-51b0-b92e-ce9aaffc403c | textbox | Date Completed:
c5a86971-9dab-4756-a80c-b8ef04278333 | signoff | AUTHORITY HOLDPOINT
ff1cb0d3-a9ab-4444-a3ad-b1984527baf4 | section | Testing
c21985ed-cf37-47ad-b4f4-adccc8cdbadd | checkpoint | 3.1 Reduced Test Frequency
543f5559-c66b-5033-a6d2-f4375f88faa2 | note | FREQUENCY: Each lot
8a1f4fcd-f90f-5292-985a-290a527c72ae | note | ACCEPTANCE CRITERIA: Initial Testing requirements shall satisfy the full requirements as detailed in the specification. Once three consecutive lots have achieved specified requirement, Superintendent can agree to reduce frequency of testing of subsequent lots to the reduced testing frequency specified in Table 204.141. Reduced frequency resets if one lot fails.
e0e81f51-8eee-520c-aa07-6f295ab733e8 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.131
fe2177d0-173c-51ed-ab48-08cafca56f79 | note | INSPECTION/TEST METHOD: Test Record
911df6dc-b70c-5588-9591-123863f8eb9f | note | RECORD OF CONFORMITY: Test Records
1695e86b-e996-5ca1-98b6-9b82b5c71303 | note | AP
2f9865ee-50c5-5050-8aeb-632a7cab0132 | note | RESPONSIBILITY: Project Engineer/Superintendent
54d9ccd8-7f4e-57df-8909-7c8971856b41 | textbox | Date Completed:
41945066-70f8-4013-9936-603890bf6e2c | checkpoint | 3.2 Compaction Testing
7a53cc69-c574-51a9-bc49-dadbe0288eb1 | note | FREQUENCY: First lot then every Second thereafter
acbaa813-9555-5260-ad61-94619ef1920f | note | ACCEPTANCE CRITERIA: Type B compaction required for Scale B is 98% Characteristic Value of Density Ratio
2c08b3ec-d183-5d4e-91c4-db45659dedde | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.131
923fbd77-5d73-59ba-9057-1238d3262a9f | note | INSPECTION/TEST METHOD: Verify
fe5f5a08-5ef2-590e-81ef-dce6624e86d8 | note | RECORD OF CONFORMITY: Compaction Test Records
b48b021e-4154-500c-a7d4-5b91c9654d7e | note | TP
3b73892f-812c-55a0-9c4d-cc148597703f | note | RESPONSIBILITY: Site Engineer
3432ac28-d3f6-5ca6-bdf1-05b983dfceff | textbox | Date Completed:
c2539961-9e8b-4822-beb8-e061ac0b2f92 | checkpoint | 3.3 CBR/Swell
b86ebd99-6106-5961-9aa6-e4478fea7f95 | note | FREQUENCY: 1 lot test to determine assigned CBR and Swell
42b01705-ae19-52e8-8d82-a7f5a28c8ccf | note | ACCEPTANCE CRITERIA: CBR: ≥ 1.5%, Swell: ≤ 2.5%
619bfd68-71fd-5421-8608-4b890e701b71 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14(a)(i) Table 204.141, Table 204.041
994eb231-3e6b-526a-ba4b-75a4670cf796 | note | INSPECTION/TEST METHOD: Verify
26771ba1-d38e-5cfd-8231-b9813c042596 | note | RECORD OF CONFORMITY: CBR/Swell Test Records
6cb8a7b1-d413-52b2-b681-84e9109ceae2 | note | TP
dbebdba6-0fbe-58b8-8187-b593cce6d058 | note | RESPONSIBILITY: Site Engineer
233f3abd-dea7-5200-a689-e0124f4492aa | textbox | Date Completed:
6102ad20-b65c-4c2b-8d57-7469a782d0ac | checkpoint | 3.4 Survey Conformance (at Subgrade Level)
b1168a35-4e88-56dc-8682-7c01e6295c25 | note | FREQUENCY: Each lot
8a82aa9c-9ef1-5b34-b7cb-f125156f317e | note | ACCEPTANCE CRITERIA: The number of measurements and the tolerances of the mean and standard deviation from the theoretical surface level must comply with Table 204.031
f75513b7-5e00-5238-b245-910eaba23ea5 | note | ○ Scale B:
ba4d57b2-01fd-5010-9e02-e5d462770bdf | note | — Range x = +5,-25
29b04918-c354-5777-b5c5-a5bb12fb021b | note | — Max S = 15mm
98671fee-025a-5236-a419-dff60dfa15dd | note | — 40 measurements per lot
f9bd7317-f997-55eb-b29d-ba014fd14c08 | note | REFERENCE DOCUMENTS: 204.03
42845ff0-0baf-515b-a0a0-cf8acb7db368 | note | INSPECTION/TEST METHOD: Survey conformance point
7a14a5c6-07e5-54f3-b870-26993db7a843 | note | RECORD OF CONFORMITY: Survey report, Lot Register
f6a9bb5a-0d3e-5970-a736-cc20131bc6c1 | note | WP SCP
446a9c03-d9fe-5ef5-b1a7-82c6164a0e94 | note | RESPONSIBILITY: Site Engineer & Surveyor
d4710453-43e9-52d0-ae54-ca665ac5da83 | textbox | Date Completed:
51e548a6-22c1-4fa7-ad0f-c36ba6d99e9d | checkpoint | Final Inspection
19c86849-df43-5545-9550-d25f5d279f7e | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
0aeff297-bd44-5704-a790-0a63d3d464d8 | textbox | Print Name:
3fda8588-0c51-51bd-99cc-46e63741af39 | textbox | Position:
c646e70f-912d-5039-a00a-5d5bccff0c33 | textbox | Date:
778ce653-bde9-4b4e-b9be-b8c028a57db5 | checklist | FHC-ITP-023 - Conduit, Pit & OCS Installation Rev2 | itp | FHC-ITP-023 - Conduit, Pit & OCS Installation
faa5a491-dae0-4787-a7ed-d5d81758d4cf | section | Preliminary Works
2fffc896-2aa0-4003-9397-c5eca67da8cb | checkpoint | 1.1 Check for correct documentation
c69bf14a-8945-58a0-a565-81c405a05689 | note | FREQUENCY: Prior to commencing any activity
f1dedddf-756a-5579-8939-e6b006ae03bf | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
f975dd40-34aa-5a06-af3e-2fe3f20cb03b | note | — using the correct and complete set of drawings
b1922ffa-f002-5875-8899-e1d828593f8d | note | — all drawings are the latest revision
08abac02-89fe-5ae3-baea-d496c048c484 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
413971b6-6889-565a-a089-4acd6596331f | note | INSPECTION/TEST METHOD: Visual inspection
576a65d4-e2c5-5dbe-bbf3-d45625b00174 | note | RECORD OF CONFORMITY: This ITP signed off
889f753a-f332-5055-81cb-d14910ddaffe | note | HP*
f316d615-54c1-5d6d-8c76-f26978064c8d | note | RESPONSIBILITY: Fulton Hogan Engineer
0034f31c-8804-54ad-bbbe-f7d2924f0c53 | textbox | Date Completed:
93033ec6-e891-4384-abb7-6b89578c65e9 | checkpoint | 1.2 Implementation of all measures and controls
5ff44d07-4a0f-5d21-b1c7-6e02b740b4e5 | note | FREQUENCY: Prior to commencing any activity
ca9c43aa-91b9-586a-8bf5-6b1385c8ad6a | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
7b79d4d8-49bb-54ac-a396-e48290dc8c51 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
8c70cf67-a7b2-5fa3-9a44-46997c96b5fc | note | INSPECTION/TEST METHOD: Visual Inspection
d65fa72b-632c-5f9f-8cff-21c3abcafd3e | note | RECORD OF CONFORMITY: This ITP signed off
890ee631-0e93-5c5a-b9ac-1fd148596235 | note | HP*
be0d860e-23c4-5cc1-a836-31bfb2f69e2b | note | RESPONSIBILITY: Fulton Hogan Engineer
341b3c2d-0154-5552-bd59-5e72053bc1bd | textbox | Date Completed:
101d1077-33b1-44a8-9642-190e2f928206 | checkpoint | 1.3 Materials
6fb0a1bb-9045-5999-b883-c980c0f8f31c | note | FREQUENCY: Per Batch
a1df23e7-ca26-551a-83fc-fd1840370f5d | note | ACCEPTANCE CRITERIA: Carpark Lighting A pit is to be installed adjacent to each lighting pole with 1 x 80mm HD conduit installed between pit and the pole mounting base.
c2ebd0d1-3767-55c6-8c63-2f8164b3f95d | note | ○ Electrical supply conduit all conduits for underground mains shall be heavy duty 'Orange' underground category PVC pipe complying with the most recent issue of AS/NZS 3000 Australia/New Zealand Wiring Rules.
82574d17-8e1f-5537-8dfb-c11619d803de | note | ○ Communications conduit to be white 50 HD PVC conduits and 100 HD PVC conduits
b9ab5b0f-2ba3-512a-ae2b-ed51f76ee643 | note | ○ Camera mounting poles and structures shall meet AS47806.2 (2006) Section 5.4.1 (k)
a34368ef-6f49-5a05-8548-f8c5f8882ea0 | note | ○ Cable pit lids shall be VicRoads type approved, impressed with 'VicRoads' and 'Electrical', 'Communication', 'Traffic signals" as appropriate as per VicRoads Standard Drawing TC-1220
d058eb13-1c25-54ef-8d6e-2fc779f06cdd | note | ○ All equipment labelling to comply with requirements of NIST-013.4
e1437254-72c9-5554-9976-a231b890ecef | note | ○ Cable pits shall be 435mm dia x 550mm deep, Type 43 plastic HDPE – Aco Cablemate cable pit with concrete lid or equivalent
2b29a4fb-25d1-5ea6-863a-8993cbbd75ee | note | REFERENCE DOCUMENTS: IFC Drawings
400f873d-a0a2-51d2-bd18-98cb9dabc665 | note | INSPECTION/TEST METHOD: Verify
885acb78-8c3c-5d87-a20b-a2a5bed3f7d7 | note | RECORD OF CONFORMITY: This ITP signed
6d230078-38a3-5f1c-a751-03e7773f7103 | note | HP*
f1c7fc9d-c737-5c5c-9ee2-8c6b2ce02dc3 | note | RESPONSIBILITY: Fulton Hogan Engineer, Electrical Subcontractor
d3cb8195-1724-5d91-a513-142b9147d9b4 | textbox | Date Completed:
0dac8b36-dff8-4591-906c-66954cff45dd | section | Construction Works
d301cca0-ba34-419d-b429-6625b2acffa1 | checkpoint | 2.1 Survey set-out
abb62318-03f4-5d7b-80c1-86107094ae66 | note | FREQUENCY: As required
f345ce4c-fd51-501b-a0d6-e248d0faa6e2 | note | ACCEPTANCE CRITERIA: Work is set out in accordance with drawings.
c38e31a4-684a-51a3-9195-00b2ac4c1d88 | note | REFERENCE DOCUMENTS: Work procedure, Drawings
60c13ae3-994d-561c-b64a-8a22a58cfb7b | note | INSPECTION/TEST METHOD: Verify
4dce2976-4952-5f1b-a218-ae4bff928c4b | note | RECORD OF CONFORMITY: This ITP signed
dad039ca-1806-5cbe-a1c2-1ef5f5379def | note | HP*
d6ec094a-d334-523e-95e5-629f1cca87f9 | note | RESPONSIBILITY: Fulton Hogan Engineer
51548bb4-9ef3-5337-a125-2b660966a49e | textbox | Date Completed:
7f4d3b86-a77e-4e57-ad69-4f061241e439 | checkpoint | 2.2 Excavation/Boring & Trenching
9b3b919c-0c62-5e68-94fe-de04cfddabda | note | FREQUENCY: Prior to Backfill
6970ef50-6957-5c64-943e-9438cdcffecf | note | ACCEPTANCE CRITERIA: Trenches shall be excavated to a depth required to achieve the specified depth of cover and drainage slope, plus an over-excavation of approximately 50 mm to allow for bedding sand. The width of trenches shall be as required to fit all the conduits and pipes for services sharing the trench with specified separations, plus a further 50 mm minimum clearance from the outermost pipes or conduits.
d113d568-e6d4-570f-9716-07ea4c5e268a | note | ○ Where trenches are excavated across roadways, car parks or paved areas, the trench shall be backfilled with Class 2 crushed rock. The crushed rock shall be placed in layers not exceeding 150mm finished depth and compacted to a minimum of 98% of modified density.
b57648c3-344c-5d94-8783-ecab3a3918ce | note | REFERENCE DOCUMENTS: L1-CHE-STD-077 Sect 6.10.6
ab00345f-b31c-5b76-a62d-6f3a19343858 | note | INSPECTION/TEST METHOD: Verify
61235fa1-8c67-52cc-9659-8a96a38d89fa | note | RECORD OF CONFORMITY: This ITP signed
1e0b7314-5f04-5846-b984-69286799cc55 | note | HP
ebe765a7-951c-5c9d-937f-ea3c1301b005 | note | RESPONSIBILITY: Fulton Hogan Engineer
043d9598-e745-55e0-a78b-035854457fa7 | textbox | Date Completed:
76586c75-6eca-44b2-8192-0ca8c135825b | signoff | AUTHORITY HOLDPOINT
e1889576-df6a-4efc-90f6-47b6d177a17a | checkpoint | 2.3 Installation of Pit and Conduits
4ab96606-5865-5881-bb9a-8c6372bad491 | note | FREQUENCY: Each Lot
95b44dbd-d5f4-5a50-99a7-d988a79c5096 | note | ACCEPTANCE CRITERIA: Underground conduits shall have a minimum of 750mm cover for single and dual-conduit trenches, and 650mm for tri or quad-conduit trenches.
c015214e-5f30-5189-a9a8-9488dd9daae6 | note | ○ Multiple conduit entry penetration holes on a pit wall shall be spaced at least 50 mm apart in horizontal and vertical planes
61ab7190-d7e1-5fe2-b42e-493de67b11b0 | note | REFERENCE DOCUMENTS: L1-CHE-STD-077 Sect 6.9 IFC Drawings
0a9b1fd8-94a9-5b37-829e-26e75ca39584 | note | INSPECTION/TEST METHOD: Verify
b6a7f54d-a535-528c-93d8-79533203c705 | note | RECORD OF CONFORMITY: This ITP signed WP
6ac95ce7-568a-5475-af0e-07f8934e4dd5 | note | IP
387ff1dc-3921-54bc-95f2-02b825937858 | note | RESPONSIBILITY: Fulton Hogan Engineer
f204b50f-6747-5afa-bf5d-a791468d930e | textbox | Date Completed:
7e059617-443c-481e-bf53-9e0b1e49a8f8 | checkpoint | 2.4 Back Fill of Trenches (Trafficable)
cc0ec876-72b9-56ab-b0a2-bfc132d3e3f7 | note | FREQUENCY: Each Lot
06f27727-85dc-586b-afa5-0e4e8de5c345 | note | ACCEPTANCE CRITERIA: Bedding: 5mm dust as per MA-FLH-MA-000374
edcd023d-e5a0-5e94-bf9f-091d7cf835dd | note | ○ Backfill: VicRoads 20mm class two crushed concrete base compacted to 98% of modified density in 150mm thick layers
bade0338-8b5d-5c1c-97ee-9dd0ffb093c6 | note | REFERENCE DOCUMENTS: L1-CHE-SPE-313 IFC Drawings
adde51c0-de7d-5205-8f2d-4180afd03590 | note | INSPECTION/TEST METHOD: Verify
3ca1e429-62ac-5b4d-bb4c-ca4838362fb0 | note | RECORD OF CONFORMITY: This ITP signed
24d6e86b-88d3-562a-b1e8-d8e53b049090 | note | WP/ IP
8b2bc2e8-1c0a-5445-9d6e-d46ac6f7a2e8 | note | RESPONSIBILITY: Fulton Hogan Engineer
e696bc5c-d3f9-597a-8023-a0cd3f0aa03a | textbox | Date Completed:
0a219681-1625-4b83-9d6d-e9e28ce68a34 | checkpoint | 2.5 Back Fill of Trenches (Non Trafficable)
d1747b8e-6226-5bd4-97a5-2056651d79b4 | note | FREQUENCY: Each Lot
19b5abe4-1944-5582-9cb0-9352d4ea9eec | note | ACCEPTANCE CRITERIA: Bedding: 5mm dust as per MA-FLH-MA-000374
222673f6-84ed-5870-b8e1-e9809f9dfbe4 | note | ○ Back Filling: Site or imported material containing no more than 20% mass of rock fragments with size between 75-150mm with no rock or clay fragments greater than 150mm.
65db35a6-5f49-5811-b22e-d2aa9f164512 | note | REFERENCE DOCUMENTS: L1-CHE-SPE-313 IFC Drawings
982fa5ff-7dc1-51ac-8a41-f8bed5060fd5 | note | INSPECTION/TEST METHOD: Verify
8d362578-d326-5e75-98af-aa515cc69786 | note | RECORD OF CONFORMITY: This ITP signed
b052eb66-3a12-59be-9b21-784dd5a315ca | note | WP/IP
31a2e01a-ee67-5844-89ec-18657cee4b4e | note | RESPONSIBILITY: Fulton Hogan Engineer
a1c5a0c6-ed31-5862-a9f3-2c33b9b16556 | textbox | Date Completed:
0ee5a7f7-3451-4b4f-8611-828e064c3701 | checkpoint | 2.6 Installation of Draw Cords
5b462a0d-20b4-5222-8423-6471761782ec | note | FREQUENCY: Each Lot
25d0d032-1fe6-5902-8aea-20f34081162f | note | ACCEPTANCE CRITERIA: A draw wire of 6mm polypropylene blue/yellow rope shall be placed in each pipe and suitably anchored at each end. Pipe ends shall be sealed using pipe end caps or an approved equivalent to prevent the ingress of dirt or sludge into the pipes.
85226155-5b74-51ce-8111-18faae17f82f | note | REFERENCE DOCUMENTS: NIST-012 Sect 7.12(d)
61f63d23-539d-525d-b211-a365281b0c98 | note | INSPECTION/TEST METHOD: Verify
f5f9424f-abe2-5324-b630-ebfeec978ba6 | note | RECORD OF CONFORMITY: This ITP signed
bee26026-0f92-5d37-8c10-3d80b1028bba | note | IP
f874cc2b-b8fc-58b7-b4c5-bc6ecc062b1a | note | RESPONSIBILITY: Fulton Hogan Engineer
db7310e1-b34f-5b20-8e54-4e32ef944035 | textbox | Date Completed:
f1ca29bc-69a4-43e3-b8ea-df29bdae56f5 | checkpoint | 2.7 Installation of Marker Tape
4f589cb7-5a8a-5b89-9200-a52843952c4c | note | FREQUENCY: Each Lot
1d16f325-6cd0-5fb6-9cdc-e2749ab63f66 | note | ACCEPTANCE CRITERIA: A 75 mm wide orange coloured PVC marker tape with the words “WARNING BURIED ELECTRICAL CABLES” shall be installed in all trenches at 200-250 mm above conduits.
299b956c-bfc0-5c2c-95b8-f9d3fc8764f4 | note | REFERENCE DOCUMENTS: IFC Drawings
a96fb476-8172-51ad-bd9d-06fe0767a26e | note | INSPECTION/TEST METHOD: Verify
a78a8a04-5a46-59fc-bbbc-5936b0d31efe | note | RECORD OF CONFORMITY: This ITP signed
7cc71ac7-ca0e-5399-a311-ab68effac8f3 | note | IP
de7de31f-7e57-51fd-aabc-e6ebdafa119a | note | RESPONSIBILITY: Fulton Hogan Engineer
7514e198-e96b-5358-b779-fa5d9d14fc1a | textbox | Date Completed:
ec33c62b-1d77-4a6f-adee-e4703265d3b7 | checkpoint | 2.8 Cable Pits & Pit Lids
a9ad8639-99ba-509c-b4a7-9663832e8e3c | note | FREQUENCY: Each Lot
31710eb4-b677-5ea6-915a-5e11743a0ca5 | note | ACCEPTANCE CRITERIA: Cable pits constructed and installed as per drawings
36ece984-fde8-5b52-bc36-8dbc17bb3f86 | note | ○ Pits shall be placed at each horizontal change in direction or at spacing no greater than 100m
99b0c831-832a-5e25-9cdc-f86896f640d9 | note | ○ Seperate pits shall be used for power conduits (orange) and communications (white).
e126eac9-bce7-5279-b642-2bc399f6e45a | note | REFERENCE DOCUMENTS: Lighting and OCS Pit Schedules
07e1708a-6142-5d26-ad41-dc12ba8c6fcf | note | INSPECTION/TEST METHOD: Verify
34e9165d-937d-5b7c-acb1-1679ca4e30e7 | note | RECORD OF CONFORMITY: This ITP signed
86a545c7-31c8-59c9-b945-6782ca2bdbfa | note | IP
ece283d6-529b-5a15-8044-d08933ce021c | note | RESPONSIBILITY: Fulton Hogan Engineer
a604fbee-1bec-560d-8a5f-51e8f13d601e | textbox | Date Completed:
6837bb4b-ac4e-4068-b848-9abffaf7bd36 | section | Completion
18709e01-3c9c-4deb-99d4-8b759bbcc203 | checkpoint | 3.1 Cleaning of Site
b1ecffae-ef35-5eaf-81ed-537a8d8af601 | note | FREQUENCY: Each Lot
de75fc24-2748-5b22-8d51-49ebaa84bd63 | note | ACCEPTANCE CRITERIA: All obselete cabling to be removed during installation and disposed of appropriately.
61929b47-3ccf-5f22-88eb-7dd79c6090b1 | note | ○ Upon removal of all redundant signalling equipment; the site shall be cleared of all project scrap and associated rubbish.
a0987625-60ea-5581-9704-d315c3fc37e5 | note | REFERENCE DOCUMENTS:
a6699386-75ab-5ad9-a7fa-644cc6de53c6 | note | INSPECTION/TEST METHOD: Visual inspection
381d62ad-e8bc-5c78-9eea-694f725f6abc | note | RECORD OF CONFORMITY: This ITP signed
f694f456-e997-54ea-87c2-0cd530860954 | note | IP
effcb823-f4ff-5bc8-9883-551efddda881 | note | RESPONSIBILITY: Fulton Hogan Engineer
db898353-833b-5411-ab32-7d9abd5b4e00 | textbox | Date Completed:
e1d7ec65-26d0-44ff-9266-6e32c15183fd | checkpoint | 3.2 Recording/As Built
6fa50d4b-31e1-5ec5-97c9-ba25a1265d45 | note | FREQUENCY: Each Lot
c5390f95-1967-5181-ad79-b7258a6f4d79 | note | ACCEPTANCE CRITERIA: As-built drawings will be completed by the Contractor based upon the installed system by a process of editing the approved ‘for construction’ drawings, as well as survey records.
12f33ee1-01f9-56d0-8efb-e012ed35e2c0 | note | REFERENCE DOCUMENTS:
d1dac777-5602-543f-91d3-2d7782119d0f | note | INSPECTION/TEST METHOD: Verify
35f21057-1892-56ba-a2ef-b05795c22249 | note | RECORD OF CONFORMITY: This ITP signed, As Built Drawing, Red Pen Markup
798682da-f7bc-55e0-b7fa-f7915db2b7e9 | note | IP
d987e634-35f1-5599-88e1-60885f3f4b07 | note | RESPONSIBILITY: Fulton Hogan Engineer
fb9d6e6e-a5e8-56f4-bebc-72997da2c21f | textbox | Date Completed:
a6271141-af94-4aab-927f-104d419143df | checkpoint | Final Inspection
c7236403-bcce-5031-9648-9c4938557daa | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
031f45a5-a7b0-5813-927c-70b69165ec50 | textbox | Print Name:
6acdbab0-5dab-5ddd-af4d-27e3c189e9ea | textbox | Position:
be104133-a36b-569e-9922-4f444ff003ab | textbox | Date:
2062350c-4dec-42fb-9086-81bccd9e8a7f | checklist | FHC-ITP-025 - Structural Concrete Construction Rev2 | itp | FHC-ITP-025 - Structural Concrete Construction
59d7df6f-4789-4588-bc12-8b591a7fb433 | section | Design and Submissions
8c3aae18-a884-4ab0-80ad-b8647e69bab8 | checkpoint | 1.1 Check for correct documentation
ebc98911-374f-525d-87d2-7ecc4b02a171 | note | FREQUENCY: Prior to commencing any activity
bdf129df-8f1d-552a-a54c-84b453a392b5 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
e647118e-6b69-56fc-bd44-7b50064cd0f1 | note | — using the correct and complete set of drawings
1f3e6ede-db1d-5a2d-902b-87e081a598fa | note | — All drawings are the latest revision
c843d3e2-7881-5838-a594-abca01ccbbbb | note | REFERENCE DOCUMENTS: Drawings and drawing registers
1433c0ce-dd43-5a32-94a8-a18097450b8c | note | INSPECTION/TEST METHOD: Visual inspection
914dcd01-f76f-564a-b0e9-766a9623647c | note | RECORD OF CONFORMITY: This ITP signed
f700c2ab-8084-5251-a2fd-01583dec859e | note | HP*
7eca4387-4e43-51f9-96a5-a932ea829382 | note | RESPONSIBILITY: Fulton Hogan Engineer
42c359a7-7922-53f4-931a-d87bac6b648e | textbox | Date Completed:
8d9467ac-1f0a-4848-b895-c94c82221a78 | checkpoint | 1.2 Implementation of all measures and controls
31853f2f-bb9b-5fd5-9622-28b1ceb5e940 | note | FREQUENCY: Prior to commencing any activity
1391e33f-40da-518d-bc59-27cb5489aebf | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
36256b5b-a8ee-51dc-a8b2-ded38415bec8 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
f8f6857e-1f35-5229-9952-fb021c7099aa | note | INSPECTION/TEST METHOD: Visual Inspection
bddf49ca-7a00-5ef2-a2b0-86b8018c0c59 | note | RECORD OF CONFORMITY: This ITP signed
c6ddcd55-bd16-544a-9a58-cbd486123645 | note | HP*
f7cc9d02-681a-5310-820f-9ac729079208 | note | RESPONSIBILITY: Fulton Hogan Engineer
07cc68a6-0171-5d39-a546-9ce476de6518 | textbox | Date Completed:
08297c82-0847-4c6e-ae39-eda5901a5b05 | checkpoint | 1.3 Approval of mix design
9b66febf-8633-579e-9030-1c6ad6b5c1cd | note | FREQUENCY: Prior to the first concrete pour
45e19c72-d13e-528a-954d-209508c714c1 | note | ACCEPTANCE CRITERIA: Structural Concrete Design & Submission ITP completed and signed
e6c03c48-760b-54fb-814d-0dc3460b17a0 | note | REFERENCE DOCUMENTS: 610.07
bd009b7f-0eb3-5b13-bee6-da5da5741b86 | note | INSPECTION/TEST METHOD: Verify
3410a37a-18f7-59cf-ba04-b7a4b14c50ff | note | RECORD OF CONFORMITY: This ITP signed, Teambinder records
17bc3469-0640-5a1e-9472-94ca28190621 | note | IP
e692e9b4-9e97-55d2-acef-793bc30ecde9 | note | RESPONSIBILITY: Fulton Hogan Engineer
cc8b21b9-9e77-5989-8f74-081f3ccef967 | textbox | Date Completed:
b986debb-841d-4dd1-967a-7531739740bf | checkpoint | 1.4 Reinforcement schedule
f0fd72c6-e0dd-54ee-bd14-48f249986438 | note | FREQUENCY: Prior to concrete pour
8ec4b9e2-96d4-5192-98e6-0129f67639a6 | note | ACCEPTANCE CRITERIA: Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
386323f9-b7b0-51db-bb01-e4b024d92b3f | note | REFERENCE DOCUMENTS: 611.04
81697bbb-1bd3-5d33-81ce-1ad4700607e7 | note | INSPECTION/TEST METHOD: Verify
10395166-f01a-53e7-a0d9-99ba0cdfb87a | note | RECORD OF CONFORMITY: This ITP signed, Delivery dockets
55d44233-f25b-56fb-8f41-534b4a67f5b6 | note | IP
62b7cecc-33b8-542d-b4c8-96e46ae0ef4b | note | RESPONSIBILITY: Fulton Hogan Engineer
14d48c20-558d-553b-af02-d28cf510ef5d | textbox | Date Completed:
daafcc46-bec8-4deb-80b4-02e88f58d4af | section | Construction/Erection of Formwork
2c001b02-5e0a-4eb5-a651-37bb62ee4f84 | checkpoint | 2.1 Excavation
b3db0605-d41c-5563-b275-a47890613908 | note | FREQUENCY: Prior to concrete pour
7933a7a5-fb9b-57ee-94da-85a276feca64 | note | ACCEPTANCE CRITERIA: Excavations shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation
0fe311a1-cae5-5ff4-b868-65d2b0323b17 | note | REFERENCE DOCUMENTS: Contract Drawings
c40a21c0-5b9e-5b52-857c-75dd22fa8f23 | note | INSPECTION/TEST METHOD: Inspect
54c12771-a959-5873-9706-8813530083ba | note | RECORD OF CONFORMITY: This ITP signed
d28ce50a-f81b-522f-9647-4ca5b7f3378c | note | IP
ba3983fc-0896-53af-9196-3aee40f6d0c2 | note | RESPONSIBILITY: Fulton Hogan Engineer
2cd9aeed-a248-5f6b-9b85-64baf8b821c8 | textbox | Date Completed:
abbd112f-af5c-4d0b-98e8-16e159db739b | checkpoint | 2.2 Construction Methodology
c599817c-a897-5bf1-8dab-b167728363cd | note | FREQUENCY: Prior to erection
8cc4d9eb-7f24-56e3-ba82-9ca4409ebf05 | note | ACCEPTANCE CRITERIA: Constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
00c97c74-c4b9-53ce-9270-2da0a811f135 | note | REFERENCE DOCUMENTS: 614.04, 614.06
da4c83d1-de8a-5843-bf44-c13f31df3ee2 | note | INSPECTION/TEST METHOD: Verify
e923406e-9675-53cb-bb1f-0830f38b32eb | note | RECORD OF CONFORMITY: This ITP signed
2fd70689-ac6a-5beb-b1b9-68f2783bd386 | note | IP
74e8e122-da93-5253-8da6-1d83f12b50fc | note | RESPONSIBILITY: Fulton Hogan Engineer
d285861e-e46c-5382-b669-65681b651857 | textbox | Date Completed:
4b9a160e-2d96-42ec-8207-2901c2b5645e | section | Pre-Pour Planning and Inspection
297dcc1a-18c5-42ca-a316-5300c6994479 | checkpoint | 3.1 Excavation/Foundation – Blinding, sealing or foundation concrete
2d5030d0-9998-55b2-83c4-8482c4ae4a5c | note | FREQUENCY: Prior to concrete pour
d21eb2b4-30dc-501e-b058-1bfad119e688 | note | ACCEPTANCE CRITERIA: Blinding, sealing or foundation concrete shall not be placed until the bottom of the excavation has been reviewed by the Superintendent. Inspected and approved by the Superintendent.
f578d604-97a0-5a31-90c7-df5b94c1a61f | note | ○ Hold Point released by the Superintendent.
e180a787-eaa2-5101-8d8f-2db03a0937fd | note | REFERENCE DOCUMENTS: 602.03
172d630b-bc65-569a-bb79-6e2655c980c0 | note | INSPECTION/TEST METHOD: Verify
2f85a2e0-899c-5e8f-bd58-778e5587e0ab | note | RECORD OF CONFORMITY: This ITP signed, Delivery dockets
762b296d-3d22-52a1-9989-5e92e95044b1 | note | HP
c9673577-425f-5d20-bcc9-04fd1e83bd09 | note | RESPONSIBILITY: Fulton Hogan / VicRoads
3dc3f7b5-443e-580b-9340-5d0d98c27541 | textbox | Date Completed:
37b899e5-1b89-459a-80f8-188a9c5d4a0e | signoff | AUTHORITY HOLDPOINT
cac94b25-5f62-4882-b260-bd1fa5ba2e40 | checkpoint | 3.2 Formwork levels and position
5fdcea25-a141-58ea-a84f-c21686bad84c | note | FREQUENCY: Prior to concrete pour
6f6f81a9-a987-5011-b8ea-b6689f908456 | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out to confirm erected formwork within the tolerance. Any errors in the level or positioning of formwork is to be corrected prior to placing concrete
e32e89d9-fcf5-55b2-83f0-ef6546e2caf5 | note | REFERENCE DOCUMENTS: 614.06
44ed50ef-e736-5e17-80d1-696beece497e | note | INSPECTION/TEST METHOD: Verify
14b7780f-b810-549f-9c32-251bd952d751 | note | RECORD OF CONFORMITY: This ITP signed
39ef289f-767a-5ad3-aad9-2e5e979a0ed6 | note | SCP
78e8a9f2-89d7-5124-a0ca-65d30e86da5f | note | HP*
1dce22e7-9b19-56bc-92bd-7fef33861832 | note | RESPONSIBILITY: Fulton Hogan Engineer
253846b1-123f-550f-a148-07072964bd69 | textbox | Date Completed:
12c9f3db-bb62-46d1-900e-f614259ffbf7 | checkpoint | 3.3 Location of splices
9658e072-fb28-5c44-8643-a7f2a826ebc8 | note | FREQUENCY: Schedule Review
75e2960a-4408-5e6b-8b36-c40022439472 | note | ACCEPTANCE CRITERIA: In lapped splices, the bars shall be placed in contact and the specified cover shall be maintained.
ba97d32a-d24d-5e54-8e1f-da5c587f243e | note | REFERENCE DOCUMENTS: 611.11
80e114db-7ca9-505d-af87-a212e6bd5208 | note | INSPECTION/TEST METHOD: Inspect
782038cc-ef6c-5317-abf5-e7e96529e19a | note | RECORD OF CONFORMITY: This ITP signed
0a58318f-7a54-5326-8f67-6fcd60393721 | note | IP
af294e18-e345-5963-afc5-905b9403b73a | note | RESPONSIBILITY: Fulton Hogan
fea56e5c-6356-5839-a4b0-449b68154e79 | textbox | Date Completed:
0a07dfd4-be2e-47b1-94a9-05a98ff4d5d7 | checkpoint | 3.4 Cleaning formwork
61a40ba1-48f6-5a91-bb73-10e3a22f918d | note | FREQUENCY: Each concrete pour
b740db22-fb64-5a2b-8a83-d4371eebe783 | note | ACCEPTANCE CRITERIA: Concrete shall not be placed until all foreign material has been completely removed from the forms
e485206c-79f7-5e8f-b4a6-c40a8ae2e205 | note | REFERENCE DOCUMENTS: 610.18 (a) (iii)
9f33c4c4-45b6-57e2-a2bb-3f653f92af60 | note | INSPECTION/TEST METHOD: Verify
939c6cb5-fb2c-51f1-9e21-c7216e45413b | note | RECORD OF CONFORMITY: This ITP signed
fe14348f-82ca-54e0-8ce0-28e1baad5fe7 | note | IP
010417bb-c6a8-54ee-9783-b71b7b710427 | note | RESPONSIBILITY: Fulton Hogan
4b263eb8-4343-5a20-a234-290c8f944431 | textbox | Date Completed:
9bada39a-9a77-4f93-8e9a-140f950d020e | checkpoint | 3.5 Correct forms, reinforcements, rag bolt assembly and embedments
dc3b7ef2-abea-503a-a65f-4c2c7a21e601 | note | FREQUENCY: Prior to concrete pour
7911b575-246b-5509-aa34-faadf3a80cf8 | note | ACCEPTANCE CRITERIA: Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications.
41c9be4c-fc5e-5cab-9884-4faaf518be8c | note | ○ Pre-pour checklist completed and signed.
e38a4928-56ae-50ae-b36e-906fa4ec1e75 | note | REFERENCE DOCUMENTS: 610.18 (a)
47384982-5e98-5721-b716-fd4ca916a8e9 | note | INSPECTION/TEST METHOD: Verify
2be30cfd-2608-58f9-904e-2d3b76579be0 | note | RECORD OF CONFORMITY: This ITP signed & Pre-Pour checklist completed
e4ab299f-c8fb-533e-8a31-202f10f0aba7 | note | HP
40de0f52-4c50-5fbe-b377-876ffd9d8dba | note | RESPONSIBILITY: Fulton Hogan / VicRoads
934757c8-bcd9-51d7-8270-9b711ea5ede3 | textbox | Date Completed:
e1666a90-9418-4c67-91d4-e0a95912329c | signoff | AUTHORITY HOLDPOINT
b849afc7-9d6c-4106-ac9a-ad69dbc7f887 | checkpoint | 3.6 Reinforcement assembly of piles
67a900e3-d671-513d-bf62-f8ca9bc0f8db | note | FREQUENCY: Prior to concrete pour
98018446-7f94-53e4-864e-f2cf40dff9f1 | note | ACCEPTANCE CRITERIA: Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent.
881bce5b-aaaa-5525-8363-9ddd529e465c | note | REFERENCE DOCUMENTS: 610.17 (b),( c), (d)
f8ff28a8-ec19-5dda-818f-ee9f4eb68c45 | note | INSPECTION/TEST METHOD: Verify
3b7c3e48-822b-53ab-86a1-0707bb6e726c | note | RECORD OF CONFORMITY: This ITP signed
bfb4c651-da1e-5b27-adb2-e33b37f59470 | note | HP
3c64f2dc-a698-5ad0-9211-673b169f5125 | note | RESPONSIBILITY: Fulton Hogan
3d5874fe-dd17-587c-be14-207164e65287 | textbox | Date Completed:
2b5d8da5-ee81-4635-ae3c-83aab1e6019f | signoff | AUTHORITY HOLDPOINT
9e2d3aad-07c6-491b-b57b-9df47a56b1d8 | checkpoint | 3.7 Monitoring weather
16e31531-43b9-5625-b9b7-cc706061e86b | note | FREQUENCY: Prior to concrete pour
4f54fc8f-008a-5d11-ad2a-ed7b7e7af51e | note | ACCEPTANCE CRITERIA: Concrete shall not be place when temperature is <5°C or > 35°C
f71f110e-5059-56e0-9e17-73ee984e627d | note | ○ All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
2c1f6f35-5b11-5339-8cd2-716d0888c8a1 | note | REFERENCE DOCUMENTS: 610.17 (b),( c), (d)
bd6122cf-42f6-5904-b0fd-1bdb44df6119 | note | INSPECTION/TEST METHOD: Verify
87fc4c2e-c56f-5856-a211-5408e05cd8d2 | note | RECORD OF CONFORMITY: This ITP signed
a0ec5221-384b-55c9-83a6-ee79f0b27804 | note | IP
380e9f75-ebfb-5b16-bb3e-57f81cf368b7 | note | RESPONSIBILITY: Fulton Hogan
f4ad8095-2437-58d5-8608-600e8b480ec1 | textbox | Date Completed:
39fc48b5-5562-49ed-8888-7184ce36e14f | section | Placing and Finishing Concrete
8ec8523b-8ee4-4d3a-a1cf-b9bfebccff16 | checkpoint | 4.1 Carry out sampling of concrete
a4765db7-7830-59f0-a2d9-2acc85027071 | note | FREQUENCY: Each concrete pour
75c69c57-f9b9-59ec-9403-7a4c41d05d81 | note | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16
a11ccc51-164a-5634-8907-6ef26be70137 | note | REFERENCE DOCUMENTS: 610.16
22adde39-47a0-59a8-8495-cf5bc25bf2fc | note | INSPECTION/TEST METHOD: Checklist
0a96426e-56d4-5fe6-8fe1-a774e3c546dd | note | RECORD OF CONFORMITY: This ITP signed
fd2df658-61af-5fd1-a6f6-38fe694f4cdd | note | IP
febb0152-b825-5b0b-a791-094a9b865d8d | note | RESPONSIBILITY: Fulton Hogan
073b50d3-0f13-5fcd-9ed8-b962ab1aee47 | textbox | Date Completed:
8107f361-69b7-479f-8f92-d60877b0ff23 | checkpoint | 4.2 Discharge time
78776b7a-e610-5d20-8e26-db14dd985dd5 | note | FREQUENCY: Each concrete pour
91dd9dc1-364d-5861-9238-5d89414c4530 | note | ACCEPTANCE CRITERIA: Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise.
2e609990-4ed2-575f-bf44-e859fe6eb9e2 | note | REFERENCE DOCUMENTS:
823a82a9-8049-511b-92e4-ccb5e0817e96 | note | INSPECTION/TEST METHOD: Verify
cd19526e-4762-58fc-81d6-7767af3553ac | note | RECORD OF CONFORMITY: This ITP signed. Accurate Site Notes & Load Mapping
00411d86-a71d-5b5a-a8e1-1ac5711f5952 | note | IP
f3af7c62-da43-5114-87bd-378df6b35e18 | note | RESPONSIBILITY: Fulton Hogan
3607f899-0b13-5673-b94a-53c3096672a0 | textbox | Date Completed:
bd0116c1-bc78-4342-a2c1-0bc863c8fb0a | checkpoint | 4.3 Methodology of placement (structural)
4d491472-5fae-53cf-ae3f-724dd733f95a | note | FREQUENCY: Each concrete pour
701d230d-382b-5d86-9a92-07281a7b6ecd | note | ACCEPTANCE CRITERIA: Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials
69625c11-e73a-5731-80cd-45cac8928813 | note | ○ Concrete shall not be moved horizontally by vibrators
ea714ddc-0062-563c-b121-583f9471e4df | note | ○ In continuous pours the max. time lag between truckloads on site is 25 minutes
e4942274-f68d-5d16-8f1f-9a8f3f1ecb47 | note | REFERENCE DOCUMENTS: 610.18
ab7acb2c-3672-5164-9d52-f969540fe9d7 | note | INSPECTION/TEST METHOD: Verify
aad56c59-7b54-5e23-8756-0b94b2216fc5 | note | RECORD OF CONFORMITY: This ITP signed
83be5391-e3a6-5ed4-83e5-48ba0c7899c9 | note | IP
524ce748-fe00-5d6b-8b0c-ef7f0a8b4618 | note | RESPONSIBILITY: Fulton Hogan
32333ad6-a6dd-582f-922e-03c65303e4fb | textbox | Date Completed:
817ec2c4-525f-45a6-a670-8bdc30868e16 | section | Post-Pour Details and Inspection
1d1feb0e-3edc-4975-968c-22c7c347e374 | checkpoint | 5.1 Curing
1a8e0487-ac71-53c0-95dc-d387155570ea | note | FREQUENCY: Each concrete pour
a45eafce-9a09-5ee0-bcc2-ea45e1ba025b | note | ACCEPTANCE CRITERIA: Sufficient time shall be given for the concrete to cure prior to loading.
28a97fe9-df98-5881-a975-f0f776589a3f | note | REFERENCE DOCUMENTS: 610.23
5f202e94-d8ae-5947-9725-9ba98e451655 | note | INSPECTION/TEST METHOD: Verify
eb62b76f-6d6b-556a-8153-7aa2140e32d6 | note | RECORD OF CONFORMITY: This ITP signed
3c371000-6973-591f-b0da-58285ffdeee5 | note | IP
e0dfffa1-77da-5973-bfd5-53584a077a18 | note | RESPONSIBILITY: Fulton Hogan
28ab663c-745f-5153-9ec6-dacac7b9f8d2 | textbox | Date Completed:
0dfe9069-dcee-4d03-89a8-049c79337953 | checkpoint | 5.2 Formwork removal
ca18e72f-99ed-5149-8af1-d2aa94ddfb0c | note | FREQUENCY: Each concrete pour
d18556f4-3d46-5878-8465-7e2db174c940 | note | ACCEPTANCE CRITERIA: Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
9cbbca4d-fd03-5e4b-afba-745ebf21021e | note | REFERENCE DOCUMENTS: 610.25
5f4e0b05-193e-5d34-9e7c-5bfc7529e56b | note | INSPECTION/TEST METHOD: Verify
54e8a51e-f35a-5f74-9fdd-28470f0b9da6 | note | RECORD OF CONFORMITY: This ITP signed
3a574857-091a-529e-a9d1-1ceebc87784a | note | IP
9b2fa5b8-7bd4-5069-85f4-baed72d9c58b | note | RESPONSIBILITY: Fulton Hogan
3d63be09-dd12-5fb9-8611-89ca8269b654 | textbox | Date Completed:
1c99dcf6-4bc1-4279-bd72-6305f4b75125 | checkpoint | 5.3 Positional tolerance and dimensions of concrete members and piles
c8603f45-801c-56f9-9918-71dce2e1e110 | note | FREQUENCY: Each concrete pour
02b504c6-0c8b-5c1e-aee5-2629bf65529f | note | ACCEPTANCE CRITERIA: Dimensions within the tolerances given in Cl 17.5 of AS3600 (-10,+40)
241fe64a-bf06-5453-9af4-2e5c01d019d2 | note | REFERENCE DOCUMENTS: AS3600 Cl 17.5, 607.06
aea9f72a-18a8-52c0-89d7-4aa6196c6027 | note | INSPECTION/TEST METHOD: Verify
a83223b4-7150-5856-848c-9cbbabe58b79 | note | RECORD OF CONFORMITY: This ITP signed, Post Pour Checklist completed
759345b5-44a3-52ef-bc30-200d20283736 | note | IP
405ca2e6-700f-57de-88c6-8dd2bf06bcd5 | note | RESPONSIBILITY: Fulton Hogan
8ad11e8a-6c9d-52ec-bcc6-8afc4b82323e | textbox | Date Completed:
ecab18b1-a379-4b1a-aa94-24684c467c17 | checkpoint | 5.4 Concrete Sampling and Testing
ccdd34af-3cf4-54fa-8303-99d74a6b50b2 | note | FREQUENCY: Prior to lot closure
e6a0c6b2-831f-53c6-bb55-5031d21e5880 | note | ACCEPTANCE CRITERIA: Concrete sampled and tested for Compressive Strength, and Slump.
d7f512be-aeaf-507c-ac53-831e206b06b9 | note | REFERENCE DOCUMENTS: 610.16
704e9b22-ec4e-500b-ae2d-dae905c2e36f | note | INSPECTION/TEST METHOD: Verify
c7f87942-345e-53e7-9c42-4bd6319f4d26 | note | RECORD OF CONFORMITY: This ITP signed
644513d9-639a-50a7-bd9b-32e5ce4922e9 | note | TP
07d3b51d-f5df-5f7e-a75c-6343bf08aa7b | note | RESPONSIBILITY: Fulton Hogan
6a6e5694-06dc-5329-88d3-9cc26a9ba987 | textbox | Date Completed:
45cecd56-56ea-4a71-9716-d146b74954e0 | checkpoint | 5.5 As Built Drawings
f615a554-29f2-5c20-b2d3-c176e3b9c2b0 | note | FREQUENCY: Prior to lot closure
b9c2cff9-f933-5004-b6aa-35b1582eee95 | note | ACCEPTANCE CRITERIA: Recorded of as-built drawings
ea371f28-4b73-52f5-9afe-f0a00d8a1951 | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
17b2228c-2a12-578d-9791-efc285273eb9 | note | INSPECTION/TEST METHOD: Verify
34c9eb71-e559-5196-9d4b-f4a202e49428 | note | RECORD OF CONFORMITY: This ITP signed, Lot Maps
198e41b2-37bf-577a-ae72-eb562c779d7b | note | IP
73f1a5f7-8ffd-50ac-ae8b-c4e8cd09c07c | note | RESPONSIBILITY: Fulton Hogan
4d31562e-cb8a-5ffd-ac67-2269f0a14bb4 | textbox | Date Completed:
718e2a5a-98f7-483d-b854-f3d2a09b751f | checkpoint | Final Inspection
de3e540d-42a1-563b-9991-594a764260b2 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
f7951fa8-0c93-54fe-ad2c-9ce5f50658fb | textbox | Print Name:
72c85103-08be-544a-a831-894b69ee9e7a | textbox | Position:
6b864fa4-949e-52c8-9c6e-0c9804804801 | textbox | Date:
ac382384-4db7-42bf-9ce5-2f2fd45dff2c | checklist | FHC-ITP-027 - Pile Footing Construction Rev2 | itp | FHC-ITP-027 - Pile Footing Construction
31c80701-2509-4a6d-99cf-f319780ab91f | section | Design and Submissions
13d00771-5ae3-4099-a1cd-b81116e0243f | checkpoint | 1.1 Check for correct documentation
ddb852d9-b1b7-5eeb-839d-6439fe496b11 | note | FREQUENCY: Prior to commencing any activity
19f4a5f0-ca25-50f8-8d69-a30f381a4ccc | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
c579991f-1609-5ac4-88d9-da4510ea73b6 | note | — using the correct and complete set of drawings
1dd1bfcd-0543-5518-964e-d4cd94b3c552 | note | — All drawings are the latest revision
d3e87935-f838-5e30-aad8-ebfe3fa5e77e | note | REFERENCE DOCUMENTS: Drawings and drawing registers
6e485b48-f661-5eb1-8a9e-73a14ed0685f | note | INSPECTION/TEST METHOD: Visual inspection
4265f648-4b01-514f-9cb5-0897e522096e | note | RECORD OF CONFORMITY: This ITP signed
b2ebdab0-2e7d-5d5d-b12f-713498911a47 | note | HP*
1583973d-5b35-5a2a-b724-d071ee6d75cf | note | RESPONSIBILITY: Fulton Hogan Engineer
14985bc9-695b-53ff-bf49-62387a590441 | textbox | Date Completed:
baeff06b-fdda-4440-93ff-2c3fe9d8fc09 | checkpoint | 1.2 Implementation of all measures and controls
a1978a38-4377-51ca-ae7d-7e1b73ba8799 | note | FREQUENCY: Prior to commencing any activity
4f4ffd45-7073-5335-9c27-d4f49dc189fb | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
837ad5f1-2a5e-5ff8-a95d-58b756354094 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
a32deee7-28ad-501b-9eb6-678239866572 | note | INSPECTION/TEST METHOD: Visual Inspection
92d1eb27-72b8-5aba-bfaf-269c4e9a31d0 | note | RECORD OF CONFORMITY: This ITP signed
4e48067f-6071-568d-88a8-6ed6f39841d4 | note | HP*
82df174c-5ad5-56cd-a20b-77252fdff786 | note | RESPONSIBILITY: Fulton Hogan Engineer
b9097203-21ee-51cd-a199-1423c52e4b95 | textbox | Date Completed:
3ac2142f-2c22-491e-9960-9fa96410dd58 | checkpoint | 1.3 Approval of mix design
aac71114-e533-5feb-8b90-df4bb38e65ea | note | FREQUENCY: Prior to the first concrete pour
7486fd7e-123a-511b-b10d-db2007f41353 | note | ACCEPTANCE CRITERIA: Structural Concrete Design & Submission ITP completed and signed.
a51b28ef-26e5-5faf-a704-e59c9120e274 | note | REFERENCE DOCUMENTS: 610.07
018a29a5-5056-5937-8625-975a2ce85ea3 | note | INSPECTION/TEST METHOD: Verify
ac617669-1e85-52f8-bbd0-b5aa722fc627 | note | RECORD OF CONFORMITY: This ITP signed, Teambinder records
96f178c9-2dad-5a55-a8c9-a0b586b9601e | note | IP
87b75797-33aa-587a-8158-6bac720153b8 | note | RESPONSIBILITY: Fulton Hogan Engineer
1c1ea2a8-deda-5a23-8c4c-493bb9ae9a8b | textbox | Date Completed:
f67c34fa-5516-4c2c-9716-bd4a39285a86 | checkpoint | 1.4 Reinforcement schedule
a298d376-5cf9-5bdd-9c1b-db56bd2fdd6d | note | FREQUENCY: Prior to concrete pour
89c5baa4-a347-512b-b155-63df055a792d | note | ACCEPTANCE CRITERIA: Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
e2ec60e8-5b37-5158-85d4-766bd9c22dc0 | note | REFERENCE DOCUMENTS: 611.04
30e1b97d-aaa0-57de-8d5b-050e0a609c21 | note | INSPECTION/TEST METHOD: Verify
4d5c273c-96c5-55fc-8a47-4bc4788bafab | note | RECORD OF CONFORMITY: This ITP signed
6cacad31-6ce5-5b65-9793-a72dc25b949b | note | IP
a22c80a8-5993-5c79-b27c-5d7f7b39c84f | note | RESPONSIBILITY: Fulton Hogan Engineer
3cd912c2-6caf-5a49-95dc-4bdc487f3b80 | textbox | Date Completed:
8990876c-5b4f-45b5-9712-b4d683c8c7c9 | section | Construction/Erection of Formwork
ed4bc786-0dea-4c68-90df-f4f3f5643e73 | checkpoint | 2.1 Excavation (Pile)
550f1874-b092-52a5-acc0-094454401ef8 | note | FREQUENCY: Prior to concrete pour
97df59f6-99dd-5d23-a245-0ade89096786 | note | ACCEPTANCE CRITERIA: The Contractor shall notify the Superintendent for inspection of the pile excavation by the Superintendent. Prior to inspection, the pile excavation shall be de‑watered and the walls and base of the pile cleaned out, including the internal surface of the casing, to remove all mud, loose or foreign material.
294bb00a-7f99-5cc8-af82-a861285c2aaf | note | REFERENCE DOCUMENTS: 606.05
0cb4c968-7231-50dd-a9cd-7a3cd62c85a1 | note | INSPECTION/TEST METHOD: Inspect
8f46a598-d809-5d6e-8727-568af9c65993 | note | RECORD OF CONFORMITY: This ITP signed
8ea98c67-6e69-51dd-8209-b7a8b6ca6832 | note | HP
0629ef07-bcee-5e1d-a64b-a330d7e20ecd | note | RESPONSIBILITY: Fulton Hogan Engineer / Suprintendant
d94a393a-809c-582e-bf16-4ac2732f651b | textbox | Date Completed:
1492b88d-93f8-4a4b-9210-0ace7718195f | signoff | AUTHORITY HOLDPOINT
d7f675dd-d33b-4997-8cff-05edfe31a566 | checkpoint | 2.2 Construction Methodology
1a8398a4-bde7-5459-b48c-d13a9dac0ad2 | note | FREQUENCY: Prior to erection
4d279ccc-248c-5dd5-84e6-360cbda23fad | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
15d9a067-c7fd-51ca-a9a8-6d183297edd2 | note | REFERENCE DOCUMENTS: 614.04, 614.06
74751895-707a-5202-a366-c15231ac1237 | note | INSPECTION/TEST METHOD: Verify
a277306a-cece-5a7f-ba62-057c5a6ed428 | note | RECORD OF CONFORMITY: This ITP signed
db2bc21a-6867-5d16-b540-5bf606636260 | note | IP
fe09b27e-c59b-5deb-8580-38b29723f2aa | note | RESPONSIBILITY: Fulton Hogan Engineer
1f116f6f-894b-574b-a584-28ae76e117df | textbox | Date Completed:
3482e335-a5df-45cc-a505-ffa510d11134 | checkpoint | 2.3 Construction Methodology (Pile)
98a0b557-7bc2-57bd-abd9-235063d2886d | note | FREQUENCY: Prior to construction
62d14092-9efe-5e90-8abb-0a301e4876b2 | note | ACCEPTANCE CRITERIA: Further to the requirements of clause 611.10 spacers and supports for bored pile steel reinforcement shall be placed at intervals of no more than 2 m along the full length of the steel reinforcement cage to ensure that the specified concrete cover to the steel reinforcement is maintained.
9283e3de-2a33-57d3-931a-e96cc570ce6c | note | ○ Concrete shall be placed through a tremie tube and shall not be dropped from a height greater than 2 m through air.
22f3ea40-ff6d-5ea4-8112-9983d624c53e | note | REFERENCE DOCUMENTS: 611.10, 606.06
b051e861-1829-598c-87e0-f109d5571d8a | note | INSPECTION/TEST METHOD: Verify
3bc1b3f5-4fba-5005-b5ef-1eaa57d2474a | note | RECORD OF CONFORMITY: This ITP signed
6c62c9ac-ccd3-50ae-98d8-643ae296043d | note | IP
45b93a0b-dba5-58a7-b58d-319166a2b3bc | note | RESPONSIBILITY: Fulton Hogan Engineer
fa9e1a1a-7d16-5f0f-99db-e6820d634e19 | textbox | Date Completed:
6b144c0d-1661-4657-adb9-116174bee011 | section | Pre-Pour Planning and Inspection
4680a1b0-15de-4729-868b-95237e24703e | checkpoint | 3.1 Cleaning formwork
634c33b6-6a68-53d9-9514-f777acefc4c2 | note | FREQUENCY: Each concrete pour
8466a556-2cc1-5a6e-a7ea-c071cbda7f0a | note | ACCEPTANCE CRITERIA: Concrete shall not be placed until all foreign material has been completely removed from the forms
1014be91-3c36-5e5c-a0f2-71ca2b665826 | note | REFERENCE DOCUMENTS: 610.18 (a) (iii)
aa3ab114-5a58-5412-8ec8-05ac0f0f77f7 | note | INSPECTION/TEST METHOD: Verify
1db046ce-a4d1-5a1f-bcbd-57080f72b0fb | note | RECORD OF CONFORMITY: This ITP signed
b0098a3c-258e-5b8b-80c2-6f75e9da0640 | note | IP
7b99e833-a527-5804-98ad-6eff4735ecc9 | note | RESPONSIBILITY: Fulton Hogan
bada9055-bdcb-581a-8d52-303bfb3e8060 | textbox | Date Completed:
912acbb4-d930-4c23-a24f-cc62619de4b5 | checkpoint | 3.2 Correct forms, reinforcements, rag bolt assembly and embedments
cd84619d-7edc-5030-b572-991ae21cf0f3 | note | FREQUENCY: Prior to concrete pour
3e8fac7e-1c5e-5a1d-b0aa-2ba63489ce2c | note | ACCEPTANCE CRITERIA: Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications.
9eaeb534-76af-506c-a6bb-78719e39de22 | note | ○ Pre-pour checklist completed and signed.
f3c6ba9e-c4ef-5242-915b-85d42f0cbd85 | note | REFERENCE DOCUMENTS: 610.18 (a)
c319c714-3b14-5d7c-949c-d2c8e3362cbe | note | INSPECTION/TEST METHOD: Verify
ee0c7750-0cf0-5c1c-82da-941e68c7d17f | note | RECORD OF CONFORMITY: This ITP signed & Pre-Pour checklist completed
388b80c4-bda3-5870-bbe4-940cd190d921 | note | HP
e14d7c9d-3840-5684-a52e-333c80b91e65 | note | RESPONSIBILITY: Fulton Hogan / Superintendent
4961b4b9-b0a1-577a-9bb6-cd634cb7b130 | textbox | Date Completed:
366d2df1-61cc-4576-8570-46ca871521ed | signoff | AUTHORITY HOLDPOINT
0bad5fb0-40d4-4995-9d29-0e8d3249b5dd | checkpoint | 3.3 Reinforcement assembly of piles
397ec441-b330-599c-ad0c-a8f9eda7a0e0 | note | FREQUENCY: Prior to concrete pour
3075bdda-24da-587c-9193-512ef587ce94 | note | ACCEPTANCE CRITERIA: Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent.
c53a7a54-a670-5712-aeb5-c5c842d2ed13 | note | REFERENCE DOCUMENTS: 610.17 (b),( c), (d)
05410300-3805-585b-b772-14a6d3447774 | note | INSPECTION/TEST METHOD: Verify
d25e6d3c-f8ac-5ba6-8ad9-0c91c98c488b | note | RECORD OF CONFORMITY: This ITP signed
c43a5016-af3d-5e78-a761-b520509d332d | note | HP
0706b226-e64c-5a46-bb32-ac2182b2a489 | note | RESPONSIBILITY: Fulton Hogan
3c32c4c3-61cd-5c1d-9f86-b0e84ac93a53 | textbox | Date Completed:
511c1cdd-7aa3-4922-a205-0529c3f84ffc | signoff | AUTHORITY HOLDPOINT
0959ba8a-867f-44f4-a3bd-a7c202f5d448 | checkpoint | 3.4 Monitoring weather
ec661749-c60a-55a9-9fe5-427d9e05f57b | note | FREQUENCY: Prior to concrete pour
43ebb670-65c1-5cf8-ac62-0e6b203bfa5d | note | ACCEPTANCE CRITERIA: Concrete shall not be place when temperature is <5°C or > 35°C
1b8af373-c5ad-56cb-84e2-b79be5099cf9 | note | ○ All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
6f7ae444-b8eb-5152-b559-9b53f4d0e581 | note | REFERENCE DOCUMENTS: 610.17 (b),( c), (d)
9e8a8f2f-4562-57e9-90e7-b668fb75b13e | note | INSPECTION/TEST METHOD: Verify
c221a2e2-0345-5f64-9c3c-0f8153d9d419 | note | RECORD OF CONFORMITY: This ITP signed
849cd80f-c986-51c6-a4e1-31933d48e3ea | note | IP
88b2bb7d-f0ff-55af-9527-39c0eb9f3f38 | note | RESPONSIBILITY: Fulton Hogan
5af33e9d-a6f9-59a9-a1e3-b9a69611bbd2 | textbox | Date Completed:
1736b601-1160-4fd9-8495-ea6e842b9d6e | section | Placing and Finishing Concrete
1d3c3eb6-b5eb-4648-aa5d-24bef1dcb7f2 | checkpoint | 4.1 Carry out sampling of concrete
08295df5-4777-5bce-8267-3c7267a6a219 | note | FREQUENCY: Each concrete pour
f24e5ad9-0133-5bcf-9e39-e8fa54b1d427 | note | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16
8e45ab67-a971-5ae3-a551-8ec529f57da0 | note | REFERENCE DOCUMENTS: 610.16
36956b35-6a86-54fc-83b3-d58a04a94caa | note | INSPECTION/TEST METHOD: Checklist
2632d257-04c0-5726-b4b2-573229505912 | note | RECORD OF CONFORMITY: This ITP signed, Delivery dockets
f094b9e4-ff7b-52f2-878b-d7db1fa1b04e | note | IP
2b3ad5cf-d547-5125-b0a1-da856b87f2ab | note | RESPONSIBILITY: Fulton Hogan
87dc8d85-e01b-558a-a8ed-9e438d0969b8 | textbox | Date Completed:
4f05a800-8272-4aa5-b8ce-a55dc23abcd9 | checkpoint | 4.2 Discharge time
5fa0fb48-f1fa-5c72-b661-f62ca8a5bd6b | note | FREQUENCY: Each concrete pour
14e5d58c-b0e5-5e8c-8af5-3f6f5c5a6e79 | note | ACCEPTANCE CRITERIA: Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise. Batch to be used has a discharge time of 180 minutes.
b897b4bc-3c04-501a-9ae8-1f97b261aeea | note | REFERENCE DOCUMENTS: 610.13
b3858390-0b7e-5767-91a3-bb0da8d38b2b | note | INSPECTION/TEST METHOD: Verify
f2d76acc-4bcf-5c52-a3e4-5e45e434026f | note | RECORD OF CONFORMITY: This ITP signed. Accurate Site Notes & Load Mapping if req.
0a291c95-e445-5118-bdb8-1a2c61ddd212 | note | IP
2f9fffd6-fc11-5911-8f38-403ac91be7e4 | note | RESPONSIBILITY: Fulton Hogan
21a9e6fe-7b20-5d5e-83e2-82ce70847031 | textbox | Date Completed:
cdc21501-7369-4688-a920-4b40272cebef | checkpoint | 4.3 Methodology of placement (structural)
ac74bc65-34c9-53e4-a850-20fcfac6b2e4 | note | FREQUENCY: Each concrete pour
9f84f509-df61-57c8-bd08-538cbbb662ae | note | ACCEPTANCE CRITERIA: Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials
b6057430-e93f-5670-a76f-906a9a8a7e12 | note | ○ In continuous pours the max. time lag between truckloads on site is 25 minutes
f5d07a01-cd74-584a-90cc-86e3dc44227b | note | REFERENCE DOCUMENTS: 610.18
353e83ba-dadb-53c7-be61-a3edcab038bf | note | INSPECTION/TEST METHOD: Verify
0f9e21f9-b60f-575f-99ca-84c8abca6370 | note | RECORD OF CONFORMITY: This ITP signed
855f4e3b-fb5d-5649-b7fa-8b58fbe9f199 | note | IP
4034c85d-df4a-5636-864f-5169d8af528f | note | RESPONSIBILITY: Fulton Hogan
0e7c9be7-af96-56d3-ae63-5365e5fce8c9 | textbox | Date Completed:
eae0d2cd-5d36-4803-8b6b-10522c906609 | checkpoint | 4.4 Methodology of placement (piles)
a30a1c60-1214-5930-ad26-800fae90ca61 | note | FREQUENCY: Each concrete pour
0913a923-925c-5c6b-a9b5-b5567506f3e2 | note | ACCEPTANCE CRITERIA: Unless otherwise approved by the Superintendent, temporary casing shall be used to prevent collapse of holes during the excavation operation.
cc89268d-00c2-54cf-956a-eedab427bd63 | note | ○ Care shall be taken to prevent soil and rock dislodging from the side of the hole and contaminating the concrete forming the minimum cover to the reinforcement.
36d0fc97-9fb6-53b7-9aba-b4cdb1f82e96 | note | REFERENCE DOCUMENTS: 606.03(b), 606.05
1ae4707e-2b81-5509-bdde-e92bbfa56b09 | note | INSPECTION/TEST METHOD: Verify
7d8b6aca-a6a6-57d3-9c80-7ccf11e2b495 | note | RECORD OF CONFORMITY: This ITP signed
7464a664-8526-5c0f-aa46-027e962c4158 | note | IP
00abbdcf-d1bf-5d53-ad21-9bd111ecdc8c | note | RESPONSIBILITY: Fulton Hogan
88e067cf-f373-5710-97ca-1312dfa43bf8 | textbox | Date Completed:
16c469b0-d79c-4569-95e4-127451a5cf5d | section | Post-Pour Details and Inspection
c95ceccf-a682-4ae7-abeb-aea33496f0d8 | checkpoint | 5.1 Curing
595a862f-2b42-54a3-b868-fdb129a16322 | note | FREQUENCY: Each concrete pour
05561274-3ab1-5740-bc41-a3b7d623e5ec | note | ACCEPTANCE CRITERIA: Sufficient time shall be given for the concrete to cure prior to loading.
82060fdb-44b9-57e7-9fdf-067f8397e383 | note | REFERENCE DOCUMENTS: 610.23
863978d1-16e6-5a69-9fed-59ae098a211f | note | INSPECTION/TEST METHOD: Verify
0bd9a977-2301-59da-8680-2762853ef4af | note | RECORD OF CONFORMITY: This ITP signed
f083e6ed-9dff-5ee2-8ddd-c38a2a645de8 | note | IP
368fc6cc-1259-5be0-a5ff-2ce4cf6a11c6 | note | RESPONSIBILITY: Fulton Hogan
426f4006-38a1-513a-9e47-b3dd75a36407 | textbox | Date Completed:
db4a49a5-31c0-4f22-b3cb-764ca8bd81fc | checkpoint | 5.2 Formwork removal
f5f038bc-1d08-561c-a397-4d512387f862 | note | FREQUENCY: Each concrete pour
ebbce7f9-c464-5b20-9249-e2c543645e92 | note | ACCEPTANCE CRITERIA: Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
852cef7f-dee2-5e13-9d77-5159ecf5caed | note | REFERENCE DOCUMENTS: 610.25
7964b348-14c1-59e4-a49a-0b2e58fd1d90 | note | INSPECTION/TEST METHOD: Verify
ec9e21d7-0c40-5892-bc27-e656a61a2855 | note | RECORD OF CONFORMITY: This ITP signed
952402d4-38db-5bbd-be9c-57f7d469bf0f | note | IP
1c713f05-d89c-514d-864f-7869bac2bb71 | note | RESPONSIBILITY: Fulton Hogan
3491ad30-d8ef-59ed-af24-311231467321 | textbox | Date Completed:
70df99ee-8332-490b-97ff-e84f616c431c | checkpoint | 5.3 Positional tolerance and dimensions of concrete members and piles
f5da4843-d3e0-550f-a9fc-c71f827e3484 | note | FREQUENCY: Each concrete pour
bc9d51eb-78be-53e7-8e6e-8f5bc270b8d6 | note | ACCEPTANCE CRITERIA: The centre of the pile head shall be in the specified plan position ±75 mm;
703078ec-e139-5a43-b096-771f558107d9 | note | REFERENCE DOCUMENTS: 607.06
dae4d1f4-9cfb-50d4-9341-30e70e9a8416 | note | INSPECTION/TEST METHOD: Verify
9acca444-f4e8-51cb-84ba-9ed383df1ac5 | note | RECORD OF CONFORMITY: This ITP signed, Post Pour Checklist completed
3e644deb-8f50-5493-a9b8-cafd1af17b36 | note | IP
939fab39-7803-55fa-8228-d97fd7c2e8bb | note | RESPONSIBILITY: Fulton Hogan
869f16ca-251d-563a-9f0f-ff2e750aa750 | textbox | Date Completed:
e568c4dc-cf87-41c4-a929-e7f24739f23e | checkpoint | 5.4 Concrete Sampling and Testing
1500d26f-6d18-5289-b901-074318c449e2 | note | FREQUENCY: Prior to lot closure
eb4a0ee3-02ad-5d4e-b5b7-4cac056fd278 | note | ACCEPTANCE CRITERIA: Concrete sampled and tested for Compressive Strength:
477be3df-ec04-58f7-a31c-63ced06df4a5 | note | — 2 cylinders @ 28 days for VPV=13% & Compressive Strength=40MPa
c655898f-5293-585d-a1ab-1798b8b95259 | note | — 1 cylinders @ 7 days for Compressive Strength=26MPa
c0d35631-9636-5dd3-8016-1cdd60e3a339 | note | ○ Slump flow of 550 - 800mm spread
e499884a-1562-53f1-96fd-78e342a8df05 | note | ○ T500 of 1 to 5 seconds
f347285a-1b43-5c80-bd34-0fed03e807b7 | note | ○ Passing Ability of less than or equal to 10mm
a0f0c831-4b1c-537f-84aa-7bd2b829c759 | note | REFERENCE DOCUMENTS: 610.05, 610.06, 610.13, 610.16
1457f1fa-570a-508a-9f41-ecb409d3a424 | note | INSPECTION/TEST METHOD: Verify
408433de-e1f9-5b2f-aa03-51369de9c244 | note | RECORD OF CONFORMITY: This ITP signed, Test reports
cbfe31b1-41a5-5aea-99bc-8ecb5f573201 | note | TP
be45fb1d-77ee-5b8a-b41c-37a35d5db41d | note | RESPONSIBILITY: Fulton Hogan
4bd91649-3a5b-5662-a94e-33f19933fa20 | textbox | Date Completed:
4324a5cf-0e0e-404e-9f21-e30efb60531e | checkpoint | 5.5 Protection of Adjacent Piles
fe9831f0-c143-5f82-81c8-9e8c6f77f3e3 | note | FREQUENCY: Prior to commencing any piling
684c49d0-bd5e-55ea-a582-e78d5a77064b | note | ACCEPTANCE CRITERIA: No pile construction shall be commenced within 2.5m clear distance of a newly cast pile until the concrete in the pile has attained a strength of 15 MPa.
87574a19-89fc-5478-8d97-023df53e2e04 | note | ○ Installation of piles by methods which involve driven temporary casing or result in significant vibration shall not be carried out within the distance 2.5 m to 9.0 m until the concrete in the pile has attained a strength of 15 MPa and set for a minimum of 24 hours.
02c8b694-660f-55ee-b52b-f3d4bca7fea9 | note | REFERENCE DOCUMENTS: 606.04(a), 606.04(c)
a76cfa24-0528-56d3-a3dd-b2f11c791394 | note | INSPECTION/TEST METHOD: Verify
3c1f9275-22c7-56a4-a8ff-a05cba64ba0b | note | RECORD OF CONFORMITY: This ITP signed
07f645ac-c041-591e-9767-194df9a2b5da | note | HP*
feb18b41-3855-5636-beb6-e7665e0dbb6d | note | RESPONSIBILITY: Fulton Hogan
5508d589-6741-5c21-ae61-36cc303e7dbd | textbox | Date Completed:
c2359383-266f-4a56-9f4a-d9f200d20d20 | checkpoint | 5.6 Testing Post-Pour
e1834dc0-1d13-5d5c-860d-504363cd7aac | note | FREQUENCY: Prior to lot closure
01788c0a-6705-50c4-99e5-d511e3d4f62d | note | ACCEPTANCE CRITERIA: Where necessary, piles shall be tested in accordance with 606.07; integrity testing, static load testing & dynamic testing
07a121a1-1645-5a8b-a884-a78e3de539b5 | note | REFERENCE DOCUMENTS: 606.07
1ce2880a-c534-54e9-a401-6f84750858f2 | note | INSPECTION/TEST METHOD: Verify
4fb39d29-abce-5df3-b8bc-804fce37db77 | note | RECORD OF CONFORMITY: This ITP signed
0ac03301-9961-584e-ba19-9994d6873509 | note | TP
eec6f7eb-bf81-571e-ab3f-ff407ab5a29f | note | RESPONSIBILITY: Fulton Hogan
d4e085d6-6d53-59ce-8ec4-ff3f71c14a77 | textbox | Date Completed:
b05e1af4-6303-4ccb-8880-7cabfa2901e7 | checkpoint | 5.7 As Built Drawings
44084ff4-5468-575b-8349-cca444623ff0 | note | FREQUENCY: Prior to lot closure
0fa9332e-da76-574b-a5a5-bfe8b7630f78 | note | ACCEPTANCE CRITERIA: Recorded of as-built drawings
df087582-b1a1-5cbc-8983-8ff144d02cec | note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
aadc1add-0ab6-58f9-9349-3fc283362a94 | note | INSPECTION/TEST METHOD: Verify
74c059d0-b376-5e21-85b9-ed670943ed6f | note | RECORD OF CONFORMITY: This ITP signed, Lot maps
3505f694-3abd-5c76-b62f-89a1318c894a | note | IP
ef21bca3-a8ce-53ba-be3a-1095c9624448 | note | RESPONSIBILITY: Fulton Hogan
b3261c70-4948-52ee-928f-c05c0bb4c866 | textbox | Date Completed:
c6f9c795-24f3-4c3d-8541-1cdd33503628 | checkpoint | Final Inspection
013c195c-1bd4-5c26-af5b-6ce5e5d7c5cb | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
f1e72a2f-1383-5bd9-ab5d-a59b0b142f2d | textbox | Print Name:
5d04d39c-e12b-5c77-ac90-d2ecfac36833 | textbox | Position:
e818f671-3fe6-5d63-a48c-5c3b99eb9903 | textbox | Date:
c289d51c-d64b-4f59-b211-0cb9e904b78e | checklist | FHC-ITP-036 - Type 1 Beaching Works Rev1 | itp | FHC-ITP-036 - Type 1 Beaching Works
31e49840-3fa8-45a2-a655-0cd54efbb5aa | section | Preliminary Works
4a974b9e-ace7-4dde-a776-6a88243850fd | checkpoint | 1.1 Check for correct documentation
831ddbc1-8f84-5271-85c0-10db37d095a1 | note | FREQUENCY: Prior to commencing any activity
1b2f3046-7c9f-570b-bb38-63d3271307bb | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
2772a4d0-e4ac-5169-8829-e02b42998330 | note | — using the correct and complete set of drawings
b0e4f3be-8893-558e-947e-d3d1b033c719 | note | — all drawings are the latest revision
170a6df9-43a2-571a-8f8f-00fed1978b86 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
95163b69-e2f1-5210-8103-e96f513ecac0 | note | INSPECTION/TEST METHOD: Visual inspection
33790979-a76a-51a4-8c3c-1744fa596933 | note | RECORD OF CONFORMITY: This ITP signed off
63bc2555-dd39-5ddc-98cb-0fb78ce24197 | note | HP*
45008c84-9f23-56ea-b6dc-be9374ca666f | note | RESPONSIBILITY: Site Engineer / Site Foreman
2f22549b-1f42-558f-87a6-f1ad3e5fb164 | textbox | Date Completed:
312ec7ac-6306-4358-ade8-0a5ca40108fa | checkpoint | 1.2 Implementation of all measures and controls
e6bd9d44-a80c-5d41-9ce4-6721c73d4181 | note | FREQUENCY: Prior to commencing any activity
40e543ba-e877-5e14-abdf-c1b8b38b9781 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
0c6c72ed-2387-58fa-b86a-e28c4350734e | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
1eea7e91-6401-5621-a38f-e8d424b9ca08 | note | INSPECTION/TEST METHOD: Visual Inspection
ee68f077-1a1a-57e6-9968-7c436cc8bd8b | note | RECORD OF CONFORMITY: This ITP signed off
d12ac4ba-43b4-5144-8e34-7af6f4a3a26e | note | HP*
bb1c6a68-fa67-56d8-a044-269afb66a996 | note | RESPONSIBILITY: Site Engineer / Site Foreman
579d5a40-7d04-5771-a563-b8991445bc9a | textbox | Date Completed:
197fd5ad-da6f-4d3c-b834-6ebdf4b5ba3f | checkpoint | 1.3 Material Approval
a5fc124c-6e3b-5318-8a04-02ccd249183a | note | FREQUENCY: Prior to Placement
aab4bda2-45ed-5ed0-a169-aac9df6b90fd | note | ACCEPTANCE CRITERIA: Material intended for use is to be submitted to the client prior to placement to verify it conforms to required specifications.
d9523dfa-cb8d-577c-b777-58f0936dfcfe | note | ○ Materials used for rock beaching shall be resistant to weathering action of air, wind and water and shall be free from staining, laminations, cracks and other structural defects which may reduce its mechanical strength.
05cec311-4b1c-5686-9a7a-468db451788b | note | REFERENCE DOCUMENTS: Material specification sheets
6b482aa7-3e90-52b5-967b-4f705d4691e0 | note | INSPECTION/TEST METHOD: Verfiy
86bc3d72-ba92-5f9f-8cee-f38886892f34 | note | RECORD OF CONFORMITY: Teambinder Acceptance
2ecf5ff1-ede7-58c4-b933-e11b78c71aee | note | HP
fc637f2f-e133-5a31-b8ec-c49c94712fe7 | note | RESPONSIBILITY: Site Engineer/ Superintendent
cfc69d0d-23b4-5399-8f73-151b002dc7fa | textbox | Date Completed:
e01c33d6-e74f-40e8-a393-8888b79d2736 | signoff | AUTHORITY HOLDPOINT
f5811d99-4448-4210-99d4-38404d2dda70 | section | Construction Works
c0e99b7a-c832-461b-b713-80a764ba921b | checkpoint | 2.1 Excavation Permit
68c48309-0057-52b3-9798-c25d6281403a | note | FREQUENCY: Each lot
b51eac6b-ac40-5849-a3ed-7a72724dae2a | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
66ec0b73-d182-5727-b1a5-0b90be3e000d | note | ○ Plant and equipment shall be appropriate for the task.
3b46237a-cdc9-5442-a7db-dee31e565da0 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
00187334-3833-5367-93cf-a8d9bc6c41b3 | note | REFERENCE DOCUMENTS: Excavation permit
cb164ec3-dceb-5099-93ba-3812617465d7 | note | INSPECTION/TEST METHOD: Verify
ef8db7b2-89c9-5f8d-a560-532379297792 | note | RECORD OF CONFORMITY: This ITP Signed Off
6724025d-8f86-51c0-9257-3c28671b187c | note | HP*
0d539f7d-c6c4-53c3-b091-0352ef1774b4 | note | RESPONSIBILITY: Site Engineer
ece9c34f-cdb2-5713-b967-21496c72e4d2 | textbox | Date Completed:
cdb76eb0-4207-4e4f-a8b1-9f1d82af1d2a | checkpoint | 2.2 Set out beaching extents
ea4131d4-caa0-5733-a64c-b8be53524e50 | note | FREQUENCY: Prior to backfilling
47e71ee9-ef65-56f9-b41d-167866c9567c | note | ACCEPTANCE CRITERIA: The position of all beaching locations are to be confirmed with the superintendent
35648193-e713-55c5-8cde-2f595c8965dd | note | REFERENCE DOCUMENTS: IFC Drawings
b016df75-d9ac-5641-a1eb-07ebd0b2f70b | note | INSPECTION/TEST METHOD: Visual Inspection
90dfc633-cefe-5dbb-8c28-44ec9a8e5c74 | note | RECORD OF CONFORMITY: ITP Signed
ee1d5e59-643e-5238-adec-3663ab1843d3 | note | HP*
a151e0c0-b350-54c6-8f78-42d3d96b4623 | note | RESPONSIBILITY: Site Engineer
54b8d5c4-457f-55de-a97d-75f8d266b931 | textbox | Date Completed:
9d6fee22-1502-40a3-83c4-69c209ee5c15 | checkpoint | 2.3 Preparation of surface
7cd9dc6c-5670-5b64-98fe-2cba8582ce85 | note | FREQUENCY: Each Lot
e3c169c6-7984-58f9-8ad3-f1e096c6e2b2 | note | ACCEPTANCE CRITERIA: Areas on which beaching is to be placed shall be compacted and trimmed as required to provide a finished surface level of beaching in accordance with the drawings.
dc263bd0-ab1f-59fc-96ea-9e5a19341ebf | note | ○ Any scours or hollows in the surface shall be filled with compacted Class 4 crushed rock.
2f4cde35-156f-5f4b-ba9b-b3054068713f | note | REFERENCE DOCUMENTS: 713.04
6b398842-2ebe-5bd5-8394-0d18b56f804c | note | INSPECTION/TEST METHOD: Visual Inspection
4a6a169a-6634-5294-aabc-4c88d805e472 | note | RECORD OF CONFORMITY: This ITP signed off
9ef1ad4c-310f-5148-9335-808f7ce213e4 | note | IP
0b0c09ab-934d-58be-b01a-998e41434d14 | note | RESPONSIBILITY: Site Engineer / Site Foreman
c7ec911e-b539-5402-a050-86efb7ddeda5 | textbox | Date Completed:
b8c56f14-a47f-4123-8f32-402b4c119aff | checkpoint | 2.4 Placement of bedding / geotextile
7c4e4e39-dc16-5f10-8f46-0ae10dc958a1 | note | FREQUENCY: Each Lot
2ea3c937-0a32-52ef-9227-0f1aad17ceb3 | note | ACCEPTANCE CRITERIA: Type 1 beaching shall not routinely require a granular bedding, however a very robust needle-punched non woven geotextile (mass >250 g/m2) shall be laid over the trimmed surface where rock beaching is to be placed.
58f0526e-47ac-5ffb-88bf-f606f6e764fd | note | ○ The geotextile shall be laid evenly with no kinks or folds, and joints shall be formed by overlapping the geotextile by not less than 300 mm and not more than 500 mm.
e22ae4a0-1589-57c5-ac73-3c88b95b425f | note | REFERENCE DOCUMENTS: 713.03(b)
8beea9f0-7e80-5cb1-9f3b-8104c03172db | note | INSPECTION/TEST METHOD: Visual Inspection
1a5bc099-9d0d-53d9-a9e8-b9a0065160ce | note | RECORD OF CONFORMITY: This ITP signed off
db917e7f-139c-5aa4-bb97-03f434b18a7f | note | IP
bbe05a82-06fb-5ce9-b29b-666ca8f45fa6 | note | RESPONSIBILITY: Site Engineer / Site Foreman
5270d47e-3df1-5100-be3e-f04839cada95 | textbox | Date Completed:
f34bf500-3688-49cf-b68a-ef6a44d813cc | checkpoint | 2.5 Excavation of anchor trench
6846ef69-2f75-5c88-a333-1f8eaf42a298 | note | FREQUENCY: Each Lot
f127e91b-6ef3-5b6d-8114-856b41d17f80 | note | ACCEPTANCE CRITERIA: Geotextiles used shall comply with and be placed in accordance with Section 210. The geotextile shall be buried to a depth of 300 mm at the edges of beaching and placed under and around the excavation for the toe wall and for any other perimeter walls provided.
c29c8767-06cd-59e2-aa80-e6a556694ec2 | note | REFERENCE DOCUMENTS: 713.03(b)
1ca2574b-ac06-5757-8137-dcffc058b2dc | note | INSPECTION/TEST METHOD: Visual Inspection
78084cbb-c450-5147-aa7a-4add2ec329b7 | note | RECORD OF CONFORMITY: This ITP signed off
58f010ea-10ab-5942-9310-b30281c033b8 | note | IP
aa7dd2ce-1411-5dfc-95d9-09a66c4801c4 | note | RESPONSIBILITY: Site Engineer / Site Foreman
3bf370fd-fe10-5a47-9ae4-5803dcf31e0c | textbox | Date Completed:
d22edfbe-e846-4d1e-bf1c-dbee495538cb | checkpoint | 2.6 Placement of beaching
c875faf3-829d-536e-b2f9-83182d773f50 | note | FREQUENCY: Each Lot
136f1b04-9f3b-5336-92a6-2b21375f85c3 | note | ACCEPTANCE CRITERIA: Rock for Type 1 beaching shall consist of field or quarry rock.
8d0302cc-add9-5004-a198-238a0c2218de | note | ○ All rocks shall have a mass of between 20 and 70 kg and at least 60% by number shall be over 40 kg. Rocks shall be of such size that the layer of beaching is not less than 225 mm thick
f1041bc4-915a-59b1-8f02-d572a52b9f64 | note | REFERENCE DOCUMENTS: 713.03(a)
18c33c9c-8893-5f40-a41b-d473fe9519b4 | note | INSPECTION/TEST METHOD: Visual Inspection
12739d3d-8838-58d2-b34a-971339a351ee | note | RECORD OF CONFORMITY: This ITP signed off
a46f2077-deb4-506c-9094-0ce4491c6905 | note | IP
08cc8380-2a09-5fc4-ae24-3e2a968168d3 | note | RESPONSIBILITY: Site Engineer / Site Foreman
6acc6a1f-f5ca-58f0-a165-3c34593ca99e | textbox | Date Completed:
e1e2aef9-ba9c-43e1-8fd6-3b79aa465a47 | checkpoint | 2.7 Interlocking of beaching
d0a12106-cbf3-597d-80fb-4918a0f977c7 | note | FREQUENCY: Each Lot
fb99f64a-08cf-549b-983e-918fa661a593 | note | ACCEPTANCE CRITERIA: Beaching materials shall be firmly bedded on the prepared embankment and/or bedding if required and laid in courses commencing from the bottom of any slope.
f5336d05-bab4-5188-8352-b759171ad72b | note | ○ Un-grouted beaching and armour stone when placed shall form a tight ‘interlocking grid’, which shall prevent the removal of individual rocks.
56a09450-5bec-563b-87f2-33b9e78b2ef7 | note | REFERENCE DOCUMENTS: 713.05 (a)
878e7665-66ac-5158-8364-7099b78d6e10 | note | INSPECTION/TEST METHOD: Visual Inspection
2b7a76e4-fa73-5827-852f-7d1dd63a6ab3 | note | RECORD OF CONFORMITY: This ITP signed off
0e25d578-bf07-5357-8490-1b0fe669660c | note | IP
1d0e1fbb-447e-503e-9141-1405bb79feda | note | RESPONSIBILITY: Site Engineer / Site Foreman
44a0ac0d-91c0-5606-b4f5-05d64f270901 | textbox | Date Completed:
19945211-b2ed-4616-9cad-585d154a288b | section | Finishing Works
76ee54c4-7fbc-4837-be70-47b32389f7ae | checkpoint | 3.1 Finishing of beaching
2fb60783-cfd7-5754-9168-bcfce1d5fd3a | note | FREQUENCY: Each lot
64f5fa4d-ff5a-5686-8a41-b80c052ce3fa | note | ACCEPTANCE CRITERIA: Finished surface levels of rock beaching placed in open drains shall be flush with adjacent soil levels to allow mowing and maintenance.
a12d53d6-c1e1-5cd5-b775-7d027562100b | note | ○ Rock beaching shall not protrude more than 50 mm above the surrounding ground levels.
75e78947-20e3-58be-8a2d-f81019d9f3d4 | note | REFERENCE DOCUMENTS: 713.05(a)
f33f1976-c8e9-51af-8b82-0e295a7dd859 | note | INSPECTION/TEST METHOD: Visual Inspection
7f9c987f-a804-5828-b79f-c782a03b43cb | note | RECORD OF CONFORMITY: This ITP signed off
c2b37945-14f9-5b70-9042-dc1dbdd3a875 | note | IP
4dd1f808-fc4f-5846-a033-53b9a347cc12 | note | RESPONSIBILITY: Site Engineer / Site Foreman
72237630-1e0e-5b69-8fba-628606b671f0 | textbox | Date Completed:
325aa963-702a-4864-95eb-5305bcdd856c | checkpoint | 3.2 Conformity with drawings
4e68b6d3-56d3-5b62-b585-ace1a992519c | note | FREQUENCY: Each Lot
9e5fb7c3-9cf8-5c92-bc36-81d4fc01c293 | note | ACCEPTANCE CRITERIA: The finished surface of the beaching shall conform to the levels, lines and grades as shown on the drawings or as specified.
ca357008-8590-59e8-8ad8-8bd7ff798018 | note | REFERENCE DOCUMENTS: 713.02
02b4deac-05eb-5d6a-aced-35e6c47c8d9a | note | INSPECTION/TEST METHOD: Visual Inspection
88010f56-4523-5837-a2c6-496d5fedab11 | note | RECORD OF CONFORMITY: This ITP signed off
281a8f28-f2b7-53f1-899d-bbddc8a2ddfc | note | IP
5755e363-bc40-513e-8293-1af856c89175 | note | RESPONSIBILITY: Site Engineer / Site Foreman
1d5c88b8-94c7-5bfc-a6ea-ab22361cb9a2 | textbox | Date Completed:
a2d23407-4b96-4821-8024-528e142d6ebb | checkpoint | Final Inspection
db31fa49-555f-5479-a239-0bcc64724358 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
e01f632c-1a5e-5d8c-b341-e262dc515863 | textbox | Print Name:
b594280d-9f8f-503f-85aa-18dc2c2245cd | textbox | Position:
0cd2b664-bddd-533d-9cdc-205b487f6998 | textbox | Date: