## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Floor Preparation
section | Details
checkpoint | Check Area clear of all other trades and their materials
checkpoint | Grind Floor
checkpoint | Surface is clean, dry, and free from dust, debris or contaminants
checkpoint | Apply Moisture Fix if required for job
checkpoint | Disc purged material
checkpoint | Are there any cracks that require remediation?
checkpoint | Remediate cracks
checkpoint | Apply prep compound
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Carpet Installation
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor if prep is required
section | Installation
checkpoint | Install carpet including smoothedge and underlay as applicable
checkpoint | Check carpet direction
checkpoint | Install trims as applicable
checkpoint | Smoothedge nails not protruding through carpet
checkpoint | All temporary nails removed
checkpoint | All areas are carpeted: bedrooms, wardrobes, living, stairs, hall etc
checkpoint | All strands cut off
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Timber Installation
section | Preparation
checkpoint | Check installation type: floating, glue down
checkpoint | Check subfloor - level, stable and clean
section | Installation
checkpoint | Check floor for U3 (3mm variance over 3m)
checkpoint | Install Underlay/glue if required
checkpoint | Install Timber
checkpoint | Apply sealant if required
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL