## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
f36d73c8-947f-4e7e-a637-e9015822796d | checklist | Balcony Build |  | Balcony Build
4ff9886c-125c-4c62-8db7-673ae845b318 | section | Cassette Assembly
48f82a21-4fd2-4a45-83d9-7f59df9dff53 | checkpoint | All parts free from defects and damage
d371f27c-ee3a-4f77-9421-db7ef68a54e8 | checkpoint | Frame squareness
dc09f876-58e8-58c0-937c-db4648baf813 | note | Measure Diagonals and compare
edfddac7-470d-5963-9430-74b9cd64617a | note | Diagonals to match +/- 2mm
22d7dfe7-2c4b-4e5a-84ce-415eedafa181 | checkpoint | Verify all parts and fixings have been fitted as per drawings and schedules
dbacb0d5-a1a5-504b-8744-d5957767b673 | note | Note: cut / drill clearance holes in Joist and Soffit around lifting eyelet
f468334d-43f1-41fa-8173-64f094b1a0bb | checkpoint | Bolt Tightness
07e48c82-47d0-5859-9b84-051fddad5cf0 | note | Frequency: Every Bolt Nut Washer
4f76b325-68bb-5590-95e3-b1d6e32c7a12 | note | Torque Wrench: M8 Bolts to 22Nm (yellow marker)
2834aec8-1e80-5e96-aa00-7522ff6c261d | note | M10 to 44Nm (blue Marker) M12 to 77Nm (green marker)
56402acf-b464-425f-a867-91a5c253deb8 | section | Soffit Check
d0f7514a-e925-4ec7-9737-38680ab248a5 | checkpoint | Soffits Level - rear angle support added
e4bae5ce-2a65-421d-ba57-d3dfe0793de6 | checkpoint | Rivets / Screws: Correct Sizes and Integrity
2362af13-e550-5960-bc11-b2761a5cec89 | note | Visual Check: all mounting points
1dfec96d-925a-51d8-b648-544bfaaf30fa | note | Frequency: Every Rivet / Screw
2f5d427c-041c-4f27-968b-9d312f845e42 | checkpoint | Joints Tight
28a77171-f7f5-56f9-8f96-5a471d605d20 | note | All soffit panels pulled tight to each other
36bf1ec6-2765-4d33-9e1c-c730db0b072d | checkpoint | Gutter Section Assembled
c5d24149-83b5-48b6-a7f8-b3b57ee785f2 | checkpoint | Surface Finish
45cfcb35-cf8f-5dc0-8282-7b07271b134c | note | No imperfections visible beyond 3m
316a5720-528b-529b-a4d7-69ce6274e141 | note | Frequency: Every Soffit Panel
93607e83-e2cf-4f37-aafb-707184b08f92 | section | Balustrade Check
7703ff3f-ef0c-4a40-9f19-9316b29e8960 | checkpoint | Balustrade Kit Prepared
536228ee-02ad-569b-800e-ebcb5ae9e735 | note | All Parts included
6417515e-3220-5bee-ba74-b5fdd8022434 | note | Correct for Lower or Upper Type
f1349ca0-cffd-4beb-a113-e3fd54e20153 | section | Decking Check
874e5fa6-25a0-4c65-bc82-44011e042405 | checkpoint | Perforated sheets fitted where applicable
255c6b1f-a3ea-5422-adc5-847824590242 | note | Site fitted sheets included in pack
0abd3cee-cc78-57d8-b2f1-a4823972f5ec | note | Correct for Left or Right Side Unit
f5d01352-3cba-4ca6-9497-e7fa14a02bc3 | section | Completion Check
d725f989-4859-4654-a817-c67d043063dd | checkpoint | Site pack compiled
35ffa95d-7eb3-5cc5-86c7-afc4994ca9b0 | note | Perforated sheets, Gutter, Tile edging angle and Balustrade Kit packed
0b035445-0e06-5445-ba23-7c7859d32bf5 | note | Correct for Upper or Lower Type
9be18b35-6b4c-5a68-83b0-918bfa836ae6 | note | Correct for Left or Right Side Unit
fdaf937a-970d-41bc-b69f-1dc837e8f5d4 | checkpoint | Balcony Labeled
79b18ea3-2eb7-5786-a799-55db51ce845c | note | Attache and Sign QA label
0fb91a8f-be9b-5383-825f-2930f45f6883 | note | Label states Type, Side and Upper / Lower designation
f7f21903-d2ec-4768-9f5e-c52c55fcdf12 | checklist | Mulcahy - Frame Checks |  | Frame Checks
5a522059-a6c9-4534-9bdb-733bedce1215 | checkpoint | Verify barcode label has been stuck in place
64ce4464-44f9-56f8-adcb-d963aaf6e7de | note | Well adhered with no wrinkles or bubbles
729b2a55-c94c-4b7d-9b81-084639e6660f | checkpoint | Frame squareness
f8f1f214-0a4e-5a44-9878-c61f0a3b7386 | note | Measure Diagonals and compare
14220fd1-0d9f-5727-94f4-440af5755106 | note | Diagonals to match +/- 2mm
11396b5b-46e7-4e1a-89dd-fe2547737509 | checkpoint | Verify all parts have been fitted as drawings and schedules
c3f9fdb3-8717-4d63-8042-dfe397dc9529 | checkpoint | Bolt tightness
bc87ce34-fff8-5439-904d-862ca7762c6a | note | Torque Wrench: M8 Bolts to 29Nm
ea210a5f-7d53-560d-91eb-be1f70a823cf | note | Mark thread with 'torque mark' as visual indicator
59315753-8760-4fda-90d1-0057dadc4a98 | checklist | QA - Belcanto - Installation Checklist |  | Balcony Installation
42c34599-b4ef-4c31-af04-c401442116f5 | checkpoint | Packers in place
cae8ff03-457f-487b-9923-d9a087a4b864 | checkpoint | Balcony Level
ee9c578e-559e-496b-8e94-eb432b88417e | checkpoint | Clamps Tighetened
3abbf6b0-587b-4195-b7a9-3c68f9c6314e | checkpoint | Anti Slip Bracket Installed
1efd2325-7f60-4b3e-9d38-3351e972ac68 | checkpoint | Remainder of Decking Installed
fb3ed987-0ffc-49a5-97d8-b0ae3591cc21 | checkpoint | Any PC defects touched up
a467b5ec-333d-49a2-b5d3-f0665d97e305 | checklist | QA - Belcanto - Manufacturing Checklist |  | Manufacturing
50a4f318-59b7-4f7a-94ea-c6583ca1d948 | section | Soffit Check
67588c98-776b-4272-8482-09ade130c2fc | checkpoint | Rivet sizes
03e64f15-4e45-5608-b824-aa743a8d4c6b | note | As per assembly diagram
a56beb1d-29fc-5bb4-82fc-ee0234fb339d | note | Visual Check
48281ded-ff28-5aa6-9a31-514b14c8a554 | note | Frequency: Every Rivet
76c6899f-19c9-4f47-af4c-3e564dd5b502 | checkpoint | Rivet integrity
a7ceda68-ffd1-55d2-803f-c440b82ef0ee | note | Ensure rivets are pulled up tight
cf0f2c4c-873f-5578-aec3-30e738de4a74 | note | Visual Check
e305eccd-5f06-5431-83d0-6f0f386035d1 | note | Frequency: Every Rivet
0ce40530-5af7-4f0a-92bb-6e88d3b2d687 | checkpoint | Joints tight
a3668278-80b9-5b2e-b76a-91d6f7828305 | note | All soffit panels pulled tight to each other with siliconed joints
2a11e632-074f-504b-a049-1a1b2af1c0d1 | note | Visual Check
7f70c2ce-d460-58a4-b97f-70bb6245b902 | note | Frequency: Every Soffit Panel
e6a6f480-9b92-4672-8175-14b217ec8f69 | checkpoint | Z Brackets
ff61d759-ce6b-58e2-b8ba-ff51e1b124e7 | note | Ensure Z Brackets Installed corectly
9062bc58-b7b4-575d-8422-2abd5541d666 | note | Visual Check
e75cd7e2-39f6-5611-a05c-5974247f250a | note | Frequency: Every Z Bracket
c3d7bbfe-5e49-480e-a068-219afdc072ea | checkpoint | Promate Board
ff3bf088-e7d2-52da-9543-6f0f4709f986 | note | Ensure PromateBoard Installed Correctly
4994f7b9-1b73-536f-aa93-30b2a9a5f0b0 | note | Visual Check
c220bb68-b6c8-5218-a80a-e0a225cd9583 | note | Frequency: Every Promate Board
ebc21123-ba77-4e5a-b45d-aeb7a278b874 | checkpoint | Surface finish
637f4210-b24f-5ff1-bcd7-6e0aefa5bbfd | note | No imperfections visible beyond 3m
129cd1df-80bd-591c-b881-9c36f5300177 | note | Visual Check
c27f614d-03f6-5ccf-bd8c-f49fca56c127 | note | Frequency: Every Soffit Panel
37fbec39-15a0-4227-b630-78bb3923e3e5 | section | Balustrade (including Fascia) Check
44ea1858-3a11-4d28-bf47-0bb7d86eaa47 | checkpoint | All parts fitted
94512a29-4199-5b43-b9e0-73530388c626 | note | As per drawings and schedules
84e8b4fd-f71b-5672-ae39-2b6f4e26a24a | note | Visual Check
0f0369dd-5d50-5487-99ff-3477aed1156a | note | Frequency: Every Balustrade
902042e6-6f2a-422b-a7c6-33e52e64ad85 | checkpoint | Surface finish
da33f926-476e-51ba-9bee-e2fa1153ac93 | note | No imperfections visible beyond 2m
22035a55-26bd-516d-baa9-7059a8236c14 | note | Visual Check
53d7418b-ebc4-5545-9d2f-22badd94f52f | note | Frequency: Every Balustrade
3c51ae9a-f8e0-4869-9435-ca1c535dcef3 | checkpoint | Supports added
adb3b346-6b2d-5275-9e2d-7a68986ce3f7 | note | Supports fitted to side balustrades
c6e0956d-7cf2-5177-915a-b05946295b86 | note | Visual Check
c66531a1-da7e-5a5c-a746-8cc1ec7b2ee8 | note | Frequency: Side Balustrades
3435141e-3702-480e-9628-884b51ad2711 | checkpoint | Bolt tightness
5f2a1049-0657-5d1e-ad61-8efbadf9f97b | note | Torque Wrench: M8 Bolts to 29Nm
eecd7859-a668-58d6-8d0f-bc9d79b01a99 | note | Mark thread with 'torque mark' as visual indicator
1404e791-9089-5196-b77b-88cb43437f41 | note | Frequency: Every Bolt
2aca6b06-a2d2-411a-b846-2223c12bc3dc | checkpoint | Fascia secure
bda91a85-c1ea-5c2f-ba9d-94ad9aa11ca4 | note | All fixings present and well secured
f46a6119-7ac0-5adf-ade8-36efb175c56f | note | Visual Check
46faaa01-9017-5111-8126-745783d4d95f | note | Frequency: Every Fascia
84942778-c0b6-453e-9308-8e792b1b224c | checkpoint | Handrail secure
c7868821-9547-5ebe-b55f-3afd75de9430 | note | All fixings present and well secured
441c3940-0694-5a13-8b8c-9cac2364e32b | note | Visual Check
479b2cd9-45fb-5f6f-9a14-4c77327f802e | note | Frequency: Every Handrail
351e372f-8a6f-4751-9ab3-50d7248996a8 | section | Flooring Check
734fe40e-f796-444b-8579-3fc693838037 | checkpoint | Connection points accessible
96e0576c-4a69-5438-984e-5fc941eba791 | note | All connection points (clamps, sprinkler, vents, etc.) accessible via access panels
2cc10c96-eceb-5824-ab98-7810908f891f | note | Visual Check
576202e9-7dd9-510c-955a-39284082ae87 | note | Frequency: Every Balcony
2836f3d6-62d3-4dc8-b037-e5d21592a4d7 | checkpoint | Decking Screws Teightened
1fd4c8ec-478b-5327-bfae-b625c0d84a32 | note | All decking screws tightened properly
8054bc86-86cf-5ea3-acbf-10e85c718267 | note | Phycial Check
72a69444-7f19-54bb-bae2-a5acf7123de5 | note | Frequency: Every Screw
b2e819b4-d75d-4396-952b-cfa75e7adee3 | checkpoint | Decking Defects
710ccd5e-d029-50d0-9b47-b765a72faba2 | note | No Defects in the Stabiwood
6475011f-b04f-5251-ad8b-253ea7e55e90 | note | Visual Check
6923cc9d-7674-5d24-acb5-4352f94d1e96 | note | Frequency: Every Board
10d8b2c8-ed3a-4424-aed6-42330880431d | section | Completion Check
00cd59de-801a-4e03-a586-bacca9ac6ffa | checkpoint | Fascia protection applied
2bfc973b-2b76-551d-8c59-9d5cd28c3451 | note | All fasciae are protected by stretchwrap
6823fc3a-0b58-5e3b-ba0c-950930b59400 | note | Visual Check
b8474bca-1bb6-5219-9cba-fbd74ffdbf40 | note | Frequency: Every Balcony
728e832e-d510-4f52-947f-07e0d2dd82a4 | checkpoint | Handrail/capping protection applied
349ebd4e-ad4e-5824-857d-030afd80b4ac | note | All handrail/capping protected by low-tack tape
deabe019-66f5-5ef3-9459-4f27f33f5d44 | note | Visual Check
c31f21b7-ea78-5a52-909b-c6c327d7f25f | note | Frequency: Every Balcony
159a6d7d-7209-49db-9218-c679b2151292 | checkpoint | Paving restraint
ff840877-fcbd-5e58-a52a-52ffb0e2b110 | note | Pavers restrained from transport movement by strapping plywood over top
6a316001-e2f4-5a99-b6b1-dbe8f9956859 | note | Visual Check
05a7d354-8ff7-5c24-b251-a55d55fba722 | note | Frequency: Every Balcony
ad993aa5-1b68-444a-8ec2-be59f0d0962b | checkpoint | Lifting slings inserted correctly
ad9b173d-03c6-565e-8fe3-33fa08fd000a | note | In accordance with slinger training
7f2c05c5-7fa5-5d63-8ded-9b8fcd4ad3e3 | note | Visual Check
071b5048-a5d8-59e6-b810-e8ec6b9546b6 | note | Frequency: Every Balcony
cead4df8-1186-4fb1-9ec3-cfd54f397928 | checkpoint | Site pack compiled
15d82f4f-cfd7-548e-9be0-3a8cd75d2683 | note | Site pack includes fixings, cut slabs, side fasciae, post cladding and any other site required parts
77be4b51-1197-5842-b7b0-60298e46caaf | note | Visual Check
9487a013-cdce-5225-bde0-46a538921ee2 | note | Frequency: Every Balcony
c82b00be-9558-4cc6-98e5-7764a076d2d1 | checklist | Site Install Checklist |  | Site Install Checklist
5a450c7c-b9c1-4280-acd5-2af9e9aa7f1c | section | Structure
aec77128-1518-41c7-a5df-5b9571815f36 | checkpoint | Steel arms level and correct alignment
615032d6-ff79-4bda-8dc2-643a706f230f | checkpoint | Packing inplace and equal height
50a7c8d3-5372-4def-8e9c-19fa2bfd596c | section | Cassette
8be3ff88-669a-4794-a286-6e454bbbdce6 | checkpoint | Cassette set to correct height to FFL
389d7db7-99f9-4119-942a-8fa843f079cf | checkpoint | Cassette placement correct and aligned
baa82437-9c03-4ee9-83b3-159874e8fdb1 | checkpoint | Connection Bolts installed and tight
b2284850-6597-4a93-901b-0d04e6cbe12f | checkpoint | Perf Sheet fastened
c438d660-0dd6-4d10-9b96-32bfdbadb010 | checkpoint | Door Angle installed
8a3ec020-fbcd-492c-a829-76608c3c24b3 | checkpoint | Facia brackets installed
121d655a-a798-4039-8134-c94eb5420af3 | checkpoint | Gutter installed
60c59aae-b253-4376-8740-91e870ca590d | section | Cladding
8fb50998-6ad7-4f7c-ba5d-f728732798d9 | checkpoint | Cladding fixed and aligned
b92f4e8d-b528-4cfb-a53a-67cc04cf8689 | checkpoint | Sealant applied and even
5c259924-1e16-491e-a45f-7549f40ebf19 | section | Balustrade
f6d2674a-82bc-4aff-a472-78b4dfd6bb98 | checkpoint | Balustrade posts bolted and tourqed
d179ee98-832d-48a2-aaea-4eae1501b135 | checkpoint | Glass installed correct, wedges inplace
f14e129e-bff5-4149-a122-d8535ab302a6 | checkpoint | Capping rail, scratch, dent free
3638e14e-8f54-4212-b0ed-1d018212158a | checkpoint | Balustrade level
7126417e-08a2-461e-a4ff-f46b2276b179 | section | Flooring
ad899432-ea5b-4105-974f-1abc7d14bfc8 | checkpoint | Tiles alinged and spaced correctly
869a2dc2-39cd-441a-bd10-2017ead68332 | checkpoint | 12mm gap min against façade
1e89ef89-f32a-465a-8ad7-c13a77e90b29 | section | IT Screens
b4da694e-0d43-44fe-acbd-da23b375711d | checkpoint | Screen fixed and secure
2515484c-649e-432f-b641-87c6c8362022 | checkpoint | Scratches touched up
e801031c-2fe3-45ea-94df-d8110f4d9bb9 | checkpoint | Screen leveled
b8f04d25-f32f-42ad-ab45-4ec8fbe79661 | section | Dummy Posts
fff2524a-d287-4bfc-825a-bd4a0923920a | checkpoint | Posts secured and level
a0f2261c-902f-4be3-95c6-e457d87edd1a | checkpoint | Balcony defects complete
3d4f9114-99b2-423d-8ebe-683ca36d7c4d | checklist | SYS - Balcony Build (old version) |  | Balcony Build
efd3374d-586a-4e2d-ba28-f1924e4d28de | section | Cassette Assembly
b516338a-94d4-48e9-8c7f-bd0cdb46ca01 | checkpoint | All parts free from defects and damage
c3df5074-96b8-51f5-889f-ce7b0ff39f41 | textbox | Add Comment
dc6c05cb-d497-4d7e-8d6a-e6bb5165d020 | checkpoint | Frame squareness
5f4ff599-feed-50bd-a982-8747b8624076 | note | Measure Diagonals and compare
a1ed409e-a045-5be8-add8-93e8d4b8c4c3 | note | Diagonals to match +/- 2mm
14efe903-9c98-5042-b937-5ff5be88787d | textbox | Add Comment
fd0bd0d2-3c0a-489c-905d-c00b149a0deb | checkpoint | Verify all parts and fixings have been fitted as per drawings and schedules
f5bfb725-68d6-50c6-bc43-00d75a08c56c | note | Note: cut / drill clearance holes in Joist and Soffit around lifting eyelet
9e01f9b1-5f0d-54ee-8dde-1cf18a392571 | textbox | Add Comment
a041c3fe-f7a2-48e5-ac85-9e1a0f825869 | checkpoint | Bolt Tightness
24ae74e5-fad6-59a3-abd0-abc38db674fc | note | Frequency: Every Bolt Nut Washer
1a4b2c39-a63b-50b6-812b-24503da2a42f | note | Torque Wrench: M8 Bolts to 22Nm (yellow marker)
a31653b0-de99-5325-bf91-2c33d5695959 | note | M10 to 44Nm (blue Marker) M12 to 77Nm (green marker)
50e03cbe-ee88-54e1-adcb-2c8432231cea | textbox | Add Comment
afdf3d47-f331-410b-8fe7-66e1d27f8bdc | section | Soffit Check
e8fcae23-0285-4572-8103-dda18bd28fc8 | checkpoint | Soffits Level - rear angle support added
94d55137-f09b-5a6e-ae49-65eaf18bf7b7 | textbox | Add Comment
066ccb94-b23e-4db3-9d6e-b20f28d93057 | checkpoint | Rivets / Screws: Correct Sizes and Integity
a83beea0-4b28-55e6-81a4-d2b6d453f4b2 | note | Visual Check: all mounting points
ac783846-9402-50b1-a9bb-e1ffbc7be22a | note | Frequency: Every Rivet / Screw
2773bd6f-de51-5638-80e0-f9071dc03f1f | textbox | Add Comment
fa383474-0176-41ee-91f7-b15db9aaf328 | checkpoint | Joints Tight
aa7b1b38-30af-5f9b-a17d-5c2825b2ca1c | note | All soffit panels pulled tight to each other
f63ef482-8469-4707-a63c-fbcb1910ce07 | checkpoint | Gutter Section Assembled
d7b36cf5-73f9-519e-88df-ee7d579cba12 | textbox | Add Comment
adbdd823-cd35-40dc-b3b6-57a4d1516405 | checkpoint | Surface Finish
100598cb-0eb7-5bd3-8b6d-f89014fd5b9d | note | No imperfections visible beyond 3m
76fdd2dd-a2b5-5783-94cf-17c0cd32025e | note | Frequency: Every Soffit Panel
5a50463f-d415-5ce9-b252-eefe0e485dfa | textbox | Add Comment
caa36bc2-2858-464b-b175-94ca95682679 | section | Balustrade Check
ae54355a-acc0-4595-b907-52ae5472fff9 | checkpoint | Balustrade Kit Prepared
057f56e8-a1ea-529e-b92e-3f73aee9bcd9 | note | All Parts included
2de10903-45b7-5b92-9b25-4f7f2bb60ed9 | note | Correct for Lower or Upper Type
6bdaa55a-b4b9-5248-8a72-fc48d4648907 | textbox | Add Comment
ae3a6353-2d8c-4cfb-a7fd-1a42c7745941 | section | Decking Check
39d27108-c360-4e1a-8c53-fcfacf6b042e | checkpoint | Preforated sheets fitted where applicable
1a73bcb7-9b0d-5c60-bcb5-8d0eaf711b18 | note | Site fitted sheets included in pack
903b709d-feb9-53a9-a70b-b334d5d712de | note | Correct for Left or Right Side Unit
7bb70909-2bbd-5efc-b2f2-ba4dadd6efd2 | textbox | Add Comment
0e76ae92-ac96-4667-86ab-f110f86a0698 | section | Completion Check
5a5dd0d3-6ba1-4e42-91d4-d0560fe2a0a2 | checkpoint | Site pack compiled
70b42c19-6d6a-5774-b7e5-900ec72fd6a6 | note | Preforated sheets, Gutter, Tile edging angle and Balustrade Kit packed
f579643b-7f07-5b03-8fa2-bbe5f2ff5bff | note | Correct for Upper or Lower Type
42b0473a-4c29-55a8-92ab-67b17ce340da | note | Correct for Left or Right Side Unit
826be2f8-1fb9-597d-9cf9-0b75a2220119 | textbox | Add Comment
b8928b54-c882-4088-b2d4-19381b479f3d | checkpoint | Balcony Labeled
b7b77698-841c-54e5-b8a1-4c5e57ba7933 | note | Attache and Sign QA label
a0b9f6af-d50f-50ee-bd40-42a9cbdced68 | note | Label states Type, Side and Upper / Lower designation
ebc4b941-5d78-5eed-a81a-48ec8c3c3d9a | textbox | Add Comment