## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Geotextiles for paving applications | itp
section | Geotextiles for paving applications
checkpoint | Geotextile Filtration & Strength Class
label | Acceptance Criteria and Frequency - Geotextile to be used as specified in approved drawings
label | Reference - Drawing Notes
label | Item Check - Check and Verify
checkpoint | Storage, packaging and identification on site
label | Acceptance Criteria and Frequency - Geotextiles shall be stored under protective cover or wrapped with a waterproof, opaque UV protective sheeting to avoid any damage prior to installation.
label | ○ Geotextiles shall not be stored directly on the ground or in any manner in which they may be affected by heat. The method of storage shall be in accordance with any other recommendations set by the manufacturer.
label | ○ The protected geotextile rolls shall be clearly labelled showing manufacturer, type of geotextile and batch number identification number
label | Reference - MRTS27 Clause 7
label | Item Check - Check and Verify
checkpoint | Geotextile Construction Procedure
label | Acceptance Criteria and Frequency - A construction procedure detailing all work described in this Technical Specification shall be prepared. The construction procedure shall be consistent with the guidelines set out in the Transport and Main Road’s Pavement Rehabilitation Manual April 2012, Sections 4.4.6 to 4.4.6.8.
label | ○ The proposed construction procedure shall be submitted to the Administrator at least 14 days prior to the commencement of any works related to the placement of paving geotextile(s)
label | Reference - MRTS57 Clause 5.2
label | Item Check - Milestone
checkpoint | Approval of construction Procedure
label | Acceptance Criteria and Frequency - No works related to the placement of paving geotextile(s) shall commence until the construction procedures have been approved by the Administrator and the Administrator has given the Contractor permission to proceed.
label | Reference - MRTS57 Clause 5.2
label | Item Check - Hold Point 1
holdpoint | HOLD POINT
checkpoint | Ordering - Technical Data
label | Acceptance Criteria and Frequency - At least 14 days prior to the proposed ordering date of any geotextile, the Contractor shall submit to the Administrator a copy of the proposed manufacturer’s technical data sheet and a sample of the proposed geotextile from the manufacturer demonstrating compliance with this Technical Specification
label | Reference - MRTS57 Cl 8.2
label | Item Check - Milestone
checkpoint | Ordering
label | Acceptance Criteria and Frequency - The Contractor shall not order any geotextile prior to the acceptance of that geotextile by the Administrator.
label | Reference - MRTS57 Cl 8.2
label | Item Check - Hold Point 2
holdpoint | HOLD POINT
checkpoint | Delivery
label | Acceptance Criteria and Frequency - With each batch of geotextile incorporated in the Works, a certificate of compliance stating that the geotextile complies with all the requirements of this Technical Specification as appropriate to the application, together with test results reported on NATA endorsed test documents, shall be included in the Quality Records
label | Reference - MRTS57 Cl 8.4
label | Item Check - Check and Verify
checkpoint | Surface Temperature
label | Acceptance Criteria and Frequency - Spraying of bitumen or placement of geotextile shall not commence until the temperature of the surface of the pavement is above the temperature specified in MRTS11 Sprayed Bituminous Surfacing
label | Reference - MRTS57 Cl 9.3
label | Item Check - Check and Verify
checkpoint | Final Sign off and Approval - Conformance with the Specification
textbox | Name of Cient's Representative
date | Date
textbox | Name of Contractor's Representative
date | Date
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | ITP - Clearing and Grubbing | itp
section | Clearing and Grubbing
checkpoint | Clearing Requirements
label | Acceptance Criteria and Frequency - Where an area of the premises are required to be cleared, the clearing includes the removal of all artificial obstructions including fences, rubbish unnecessary structures, building foundations, obsolete pipelines and the like plants (including stumps and boulders) other than the plants required to be retained as shown on the approved drawings;
label | Reference - LCC SS 1 Part 2.1
label | Item Check - Check and Verify
checkpoint | Extent of clearing and grubbing
label | Acceptance Criteria and Frequency - The extent of the cleared area is limited to the minimum area of the premises to be occupied by the completed earthworks or 1 metre on each side of the completed earthworks or the minimum area of the premises required to safely install a service.
label | ○ Grubbing, being the removal from the ground of trees, roots and stumps to a depth of 300mm below the surface of the ground, is carried out across the entire cleared area, any area which is identified as an area not to be disturbed, is to be fenced off.
label | Reference - LCC SS 1 Part 2.2 & 3.1
label | Item Check - Check and Verify
checkpoint | Removal of material from the premises
label | Acceptance Criteria and Frequency - Cleared plants are disposed of by mulching and reusing the mulch on the premises as far as possible.
label | ○ All material, other than plant material that is mulched and reused on the premises, is removed from the premises to a place approved by the local government, no material is to be burnt on site
label | Reference - LCC SS 1 Part 2.4
label | Item Check - Check and Verify
checkpoint | Fauna Habitat Logs
label | Acceptance Criteria and Frequency - Hollow timber which is identified as being suitable for fauna habitat logs shall be relocated to areas clear of construction activities as follows:
label | a) behind batters
label | b) behind proposed safety barriers but not within any hazard free zone, and
label | c) areas at least 9 m clear of carriageways.
label | ○ Fauna habitat log density shall not exceed 20 m length per 100 m² area. Logs shall not be placed in waterways or in any area where they are likely to be struck by errant vehicles.
label | Reference - MRTS04 Clause 7.2.5
label | Item Check - Check and Verify
checkpoint | Additional Requirements:
label | Acceptance Criteria and Frequency - Within the limits of the clearing and grubbing, but clear of earthworks operations, any existing local irregularities of the natural surface are trimmed so as not to cause a hazard to errant vehicles. The surface is lightly compacted when necessary to provide a surface consistent with that existing prior to the Works
label | Reference - MRTS04 Clause 7.2.8
label | Item Check - Check and Verify
checkpoint | Final Sign off and Approval - Conformance with the Specification
textbox | Name of Cient's Representative
date | Date
textbox | Name of Contractor's Representative
date | Date
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | ITP - Traffic Management on Site | itp
section | Traffic Management on Site
checkpoint | Nominated traffic officer training/experience requirements
label | Acceptance Criteria and Frequency - The Contractor's Nominated Traffic Officer submitted to the Administrator and meets the requirements as specified
label | Reference - MRTS02 Cl 5.2.
label | Item Check - Check and Verify
checkpoint | Traffic management plan submission and approval
label | Acceptance Criteria and Frequency - A traffic management plan for the works is provided to the local governement and approved prior to the commencement of work and complies with the MUTCD, any changes to the TMP will be provided
label | Reference - LCC SS 10 Part 2.1.1
label | Item Check - Hold Point
holdpoint | HOLD POINT
checkpoint | Traffic guidance scheme submission and consideration
label | Acceptance Criteria and Frequency - All TGS's prepared by a suitably qualified person and submitted and approved by the Administrator
label | Reference - MRTS02 Cl 6.2
label | Item Check - Hold Point 2
holdpoint | HOLD POINT
checkpoint | Traffic Management Plan Alterations
label | Acceptance Criteria and Frequency - Any variation to the traffic management plan made during the work, is provided to the Administrator
label | Reference - LCC SS 10 Part 2.1.3
label | Item Check - Milestone
checkpoint | Dust Suppression
label | Acceptance Criteria and Frequency - Adequate precautions are taken to minimise dust or dust-related conditions during any activity which may affect the safety and general comfort of any person. Regular applications of water are applied to any roads or structures whilst completing earthworks
label | Reference - LCC SS 10 Part 2.5
label | Item Check - Check and Verify
checkpoint | Temporary road safety barriers
label | Acceptance Criteria and Frequency - Temporary Road Safety Barriers (TRSB) shall be used to contain and redirect errant vehicles so as to reduce the likelihood of them entering the work site
label | ○ Provision shall be made for TRSB At locations where work is to be close to traffic, and in accordance with Worker safety requirements in MUTCD Part 3;
label | ○ Only those TRSB which are included in the Transport and Main Roads – Road Safety Barrier Systems, End Treatments and other related Road Safety Devices shall be used
label | ○ All TRSB and end treatments shall be installed in accordance with the department's Standard Drawings and/or the manufacturer's specifications
label | Reference - MRTS02 Cl 6.5.11 & Annexure 2.1
label | Item Check - Check and Verify
checkpoint | Temporary line marking
label | Acceptance Criteria and Frequency - Details of proposed temporary pavement markings are submitted to the local government for approval at least two working days prior to the proposed installation of the temporary pavement.
label | Reference - LCC SS 10 Part 2.8.4
label | Item Check - Check and Verify
checkpoint | Traffic Mmanement inspection reporting
label | Acceptance Criteria and Frequency - The officer undertaking the Traffic Management Inspection shall provide a report to the Contractor for its action. The Contractor shall forward to the Administrator, within one week of the receipt of the report, the reports and findings, together with documentation of any actions taken in regard to the findings.
label | Reference - MRTS02 Cl 7.5
label | Item Check - Milestone
checkpoint | Final Sign off and Approval - Conformance with the Specification
textbox | Name of Cient's Representative
date | Date
textbox | Name of Contractor's Representative
date | Date
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | ITP - Environmental Management Systems | itp
section | Environmental Management Systems
checkpoint | Environmental Inspection
label | Acceptance Criteria and Frequency - Enviromental site inspections to be conducted daily against all licences, permits, approvals and other environmental performance requirements all Inspection to be documented in donesafe. The Contractor’s Environmental Representative shall undertake and document Weekly Site Inspections.
label | Reference - Internal
label | Item Check - Check and Verify
checkpoint | Management Plan
label | Acceptance Criteria and Frequency - Environmental Management Plan (Construction) submitted in accordance with Conditions of Contract.
label | Reference - MRTS51 Cl 6.3
label | Item Check - Hold Point 1
holdpoint | HOLD POINT
checkpoint | Approval Environmental Management Plan
label | Acceptance Criteria and Frequency - Works shall not commence until the Environmental Management Plan (Construction) has been assessed for suitability by the Administrator and approved.
label | Reference - MRTS51 Cl 6.3
label | Item Check - Check and Verify
checkpoint | Amendments
label | Acceptance Criteria and Frequency - Amendments to the Environmental Management Plan (Construction) to be submitted on a monthly bases for assessment of suitability by the Administrator.
label | Reference - MRTS51 Cl 6.4
label | Item Check - Hold Point 2
holdpoint | HOLD POINT
checkpoint | Noise Monitoring
label | Acceptance Criteria and Frequency - Noise monitoring shall be undertaken as per the contract specifications
label | Reference - Internal
label | Item Check - Check and Verify
checkpoint | Water quality
label | Acceptance Criteria and Frequency - Water quality monitoring undertaken as per requirements in MRTS52 and otherwise specified in contract
label | Reference - MRTS51 Cl 8.2
label | Item Check - Check and Verify
checkpoint | Erosion and Sediment Control
label | Acceptance Criteria and Frequency - Requirements relating to Erosion and Sediment Control are contained within MRTS52
label | Reference - MRTS51 Cl 8.3
label | Item Check - Check and Verify
checkpoint | Areas of cultural significance
label | Acceptance Criteria and Frequency - Areas of cultural significance have been identified and are managed as per Clause 3 of Annexure MRTS51.1.
label | Reference - MRTS51.1 Cl 2.2
label | Item Check - Check and Verify
checkpoint | Dilapidation Report
label | Acceptance Criteria and Frequency - A copy of the condition/dilapidation survey for vibration has been given to the Administrator before any works that cause vibration start (5 days) - Condition surveys to be undertaken at the Locations listed in Cl 5.5 of the annexure
label | Reference - MRTS51 Cl Clause 8.6.2.3
label | Item Check - Check and Verify
checkpoint | Air Quality
label | Acceptance Criteria and Frequency - Construction activities have not resulted in air quality impacts that cause environmental nuisance or harm. Burning material not permitted on site
label | Reference - MRTS51 Cl Clause 8.7.3
label | Item Check - Check and Verify
checkpoint | Acid Sulphate Soil
label | Acceptance Criteria and Frequency - Acid Sulphate Soils have been managed as per the requirements of MRTS04
label | Reference - MRTS51 Cl 8.8
label | Item Check - Check and Verify
checkpoint | Contaminated sites
label | Acceptance Criteria and Frequency - Contaminated sites (contaminated soils, waste dumps, unexploded ordinances ) within the worksite have been addressed as per requirements of MRTS04.
label | Reference - MRTS51 Cl 8.9.5
label | Item Check - Check and Verify
checkpoint | Fauna
label | Acceptance Criteria and Frequency - No harm caused to native fauna. Areas of significance and related management requirements are stated in contract. Contact details for emergency wildlife care shall be included on project emergency contact list.
label | Reference - MRTS51 Cl 8.10.1
label | Item Check - Check and Verify
checkpoint | Vegitation
label | Acceptance Criteria and Frequency - Management of vegetation within the worksite. The daily site inspections shall include visual assessments of vegetation management measures.
label | Reference - MRTS51 Cl 8.11.1
label | Item Check - Check and Verify
checkpoint | Pest Management
label | Acceptance Criteria and Frequency - All declared pest known to occur within the worksite and any associated management requirements are stated in the contract have been managed and prevented from spreading on and off site
label | Reference - MRTS51 Cl8.12.2
label | Item Check - Check and Verify
checkpoint | Chemicals & Fulels
label | Acceptance Criteria and Frequency - All chemicals and fuels within the worksite are contained so as not to cause environmental nuisance or harm.
label | ○ Spill kits response equipment are available on site for use in emergency
label | Reference - MRTS51 8.14.3
label | Item Check - Check and Verify
checkpoint | Final Sign off and Approval - Conformance with the Specification
textbox | Name of Cient's Representative
date | Date
textbox | Name of Contractor's Representative
date | Date
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | ITP - Unbound Pavement | itp
section | Unbound Pavement
checkpoint | Acceptance of Construction Procedures for unbound pavement Works
label | Acceptance Criteria and Frequency - No unbound pavement Works shall commence until all relevant construction procedures have been accepted by the Administrator
label | Reference - MRTS05 Cl 5.2.1
label | Item Check - Hold Point 1
holdpoint | HOLD POINT
checkpoint | Submit Construction Procedure for aggregate production
label | Acceptance Criteria and Frequency - The Material Production Procedures shall be submitted to the Administrator at least seven days prior to the commencement of material production for the Works
label | Reference - MRTS05 Cl 5.2.2
label | Item Check - Milestone
checkpoint | Unbound Pavement construction procedure
label | Acceptance Criteria and Frequency - The Unbound Pavement Construction Procedure shall be submitted to the Administrator at least 14 days prior to the commencement of unbound pavement Works.
label | Reference - MRTS05 Cl 5.2.3
label | Item Check - Milestone
checkpoint | Supplier Registration and source Material assessment
label | Acceptance Criteria and Frequency - The written permission of the Administrator is required prior to material being supplied to or used in the Works from any source nad the current TMR registration certificate for all sources to be used in the works shall be submitted to the administror 7 days prior to works beginning
label | Reference - MRTS05 Cl 6.1
label | Item Check - Hold Point 2
holdpoint | HOLD POINT
checkpoint | Compaction
label | Acceptance Criteria and Frequency - Type 2.1 material shall be compacted to 100% modified compaction
label | Reference - MRTS05 CL 8.4.3(a)
label | Item Check - Check and Verify
checkpoint | Alignment, Grade and Crossfall Tolerance for base course
label | Acceptance Criteria and Frequency - Tolerances for base cousre pavement are as follows:
label | ○ Design Level: +15mm -10mm
label | ○ Thickness tolerance: +15mm -15mm
label | ○ Shape Tolerance: 15mm in 3 meters maximum
label | Reference - LCC SS 6 Part 5.1.1
label | Item Check - Check and Verify
checkpoint | Proof Rolling
label | Acceptance Criteria and Frequency - Each unbound pavement layer shall be tested for perceptible surface deformation by ‘proof rolling’ the pavement, in the presence of the Administrator. All areas of unbound pavements shall be ‘proof rolled’, including all trafficked lanes, shoulders and other areas
label | Reference - MRTS05 Cl 9.4.7
label | Item Check - Witness Point 2
checkpoint | Lot Acceptance
label | Acceptance Criteria and Frequency - Unless otherwise approved by the Administrator, no unbound pavement layer shall be covered by a subsequent layer of pavement or by a surfacing until:
label | a) all testing has been completed
label | b) the surface finish of the layer complies with the requirements of Clause 8.3.5
label | c) all test results comply with the requirements of this Technical Specification, or any nonconformances have been submitted, with corrective actions proposed by the Contractor, and accepted by the Administrator
label | d) the layer has been presented to the Administrator for inspection, and
label | Reference - MRTS05 Cl 9.5.1 & LCC SS 6 4.2.1
label | Item Check - Hold Point 6
holdpoint | HOLD POINT
checkpoint | Final Sign off and Approval - Conformance with the Specification
textbox | Name of Cient's Representative
date | Date
textbox | Name of Contractor's Representative
date | Date
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | ITP - Reinforced Concrete Pipe | itp
section | Reinforced Concrete Pipe Works
checkpoint | General
label | Acceptance Criteria and Frequency - All reinforced concrete pipes and pit shall be as per drawings unless an alternitive is approved, all pipes shall be laid in location and to levels specified in drawings.
label | ○ Drawings specify
label | Reference - General
label | Item Check - Check and Verify
checkpoint | Material Conformance
label | Acceptance Criteria and Frequency - Unless otherwise noted on the approved drawings all pipes are Class 2 and comply with the requirements of AS 4058–2007 and all matrial conformnace data shall be included in the lot submission to the administrator.
label | Reference - LCC SS No.3 Part 2.1
label | Item Check - Check and Verify
checkpoint | Construction
label | Acceptance Criteria and Frequency - All RCP will be constructed as per IPWEA-STD-DS-030 which covers excavation, bedding material and backfilling
label | ○ Bottom of excavation shall be compacted to a 95% standard compaction unless insitu material is rock for all excavations.
label | ○ Backfill material shall be either 5 or 10mm aggregate.
label | Reference - LCC SS No.3 Part 6.3
label | Item Check - Check and Verify
checkpoint | Pipe Laying
label | Acceptance Criteria and Frequency - Pipes are laid true to line and grade, and are free draining and firmly bedded and are laid from the discharge end upstream to the following tolerances:
label | – invert levels - ±50mm;
label | – gully locations - within 300mm of design.
label | ○ For pipes up to and including 600mm diameter, the socketed end of the pipe is laid upstream and a shallow excavation is made under the socket of each pipe so that the pipe fully rests for its full length of barrel upon the bedding material in the trench.
label | Reference - LCC SS No.3 Part 4.2
label | Item Check - Check and Verify
checkpoint | Construction - Backfilling
label | Acceptance Criteria and Frequency - Pipe is not to be backfilled without being inspected and approved by administrator.
label | Reference - LCC SS No.3 Part 5.1
label | Item Check - Hold Point
holdpoint | HOLD POINT
checkpoint | Backfilling Material
label | Acceptance Criteria and Frequency - Prior to incorporating any Backfill material into the Works, the Contractor shall submit stockpile or source tests results as specified in part 4 of Standard specification 3 and conforms with table 4.1.1 Bedding Material
label | Reference - LCC SS No.3 Part 4.1
label | Item Check - Hold Point/ Witness Point
holdpoint | HOLD POINT
checkpoint | Backfilling Under Proposed Pavements
label | Acceptance Criteria and Frequency - backfilled with approved material of minimum 4 day soaked California bearing ratio of 15 and compacted to 100 percent standard compaction.
label | Reference - LCC No.3 Part 5.2.1.(a)
label | Item Check - Check and Verify
checkpoint | Pipe Laying Compliance Testing
label | Acceptance Criteria and Frequency - All pipes lines are subject to internal inspection and approval, the inspection of all pipes is carried out using a remote controlled video camera and is submitted to the local government before being accepted on-maintenance. A report on the findings of a remote controlled video camera inspection is to be submitted to the local government in an electronic format suitable for utilisation in “Sewer Rat” compatible applications. Pipes must not show clearly visible cracks of more than one millimetre for a length of 300mm or more on the inside.
label | Reference - LCC SS No.3 Part 4.4
label | Item Check - Hold Point
holdpoint | HOLD POINT
section | Insitu Gully Pit Works
checkpoint | General
label | Acceptance Criteria and Frequency - A drainage structure includes all work and materials necessary for the construction of gullies, inlet pits and manholes, including excavation, concrete rendering and all necessary frames, curves, gratings, precast units and surrounds, precast troughs, chambers, lintels and shafts for side entry gullies, as specified in the approved drawings and standard drawings.
label | ○ IPWEA-STD-DS-60
label | Reference - LCC SS No.3 Part 6.1
label | Item Check - Check and Verify
checkpoint | Materials - Gully Pit
label | Acceptance Criteria and Frequency - All materials used in insitu drainage structure will ne N32 class concrete or otherewise specified.
textbox | Concrete mix used -
label | Reference - LCC SS No.3 Part 6.2
label | Item Check - Check and Verify
checkpoint | Formwork Approval
label | Acceptance Criteria and Frequency - All concrete is placed in dry conditions and no concrete is placed until the formwork, falsework, and reinforcing materials have been inspected and approved by the local government.
label | Reference - LCC SS No.7 Part 4.1.1
label | Item Check - Hold Point
holdpoint | HOLD POINT
checkpoint | Construction of Gully Pit
label | Acceptance Criteria and Frequency - Where the sides of the excavation are deemed to be in solid ground shafts may be constructed without the use of backforms, where concrete is placed without backforms the specified wall thickness is increased by 50mm minimum and not greater than 300mm of the design thickness. The finished concrete surface shall have smooth even and neat edges and will be shaped per the design intent.
label | Reference - LCC SS No.3 Part 6.3
label | Item Check - Check and Verify
checkpoint | Final Sign off and Approval - Conformance with the Specification
textbox | Name of Cient's Representative
date | Date
textbox | Name of Contractor's Representative
date | Date
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | ITP - Contractor's Site Facilites | itp
section | Contractor's Site Facilites
checkpoint | General
label | Acceptance Criteria and Frequency - The Contractor shall provide properly constructed toilets, drinking water, eating and washing facilities at the Contractor’s site facilities for the use of personnel and connect to town sewer where possible and shall comply with AS 1547 On-site domestic wastewater management.
label | Reference - MRTS 28 Clause 4.3 & MRTS 28 Clause 3, Clause 8
label | Item Check - Check and Verify
checkpoint | Site Security
label | Acceptance Criteria and Frequency - The Contractor shall be responsible for the security of the buildings, construction plant and machinery.
label | ○ The Contractor shall also take all necessary precautions to make the area safe to the public, including provision of signs outlining relevant project contact details, safety requirements and any other relevant details on the main entry gate.
label | Reference - MRTS 28 Clause 4.3
label | Item Check - Check and Verify
checkpoint | Visibility to the public
label | Acceptance Criteria and Frequency - External lights on the facilities and camps should be positioned or shielded to minimise light overflow onto neighbouring properties.
label | Reference - MRTS 28 Clause 4.5.2
label | Item Check - Check and Verify
checkpoint | Noise
label | Acceptance Criteria and Frequency - Noise generated from the site facilities shall be kept to a minimum and the Contractor shall construct noise amelioration devices around the site facilities to bring the noise levels within specified criteria.
label | Reference - MRTS 28 Clause 4.5.3
label | Item Check - Check and Verify
checkpoint | Dust Suppression
label | Acceptance Criteria and Frequency - Adequate precautions are taken to minimise dust or dust-related conditions during any activity which may affect the safety and general comfort of any person. Regular applications of water are applied to any roads or structures whilst completing earthworks
label | Reference - MRTS 28 Clause 4.5.4
label | Item Check - Check and Verify
checkpoint | Temporary road safety barriers
label | Acceptance Criteria and Frequency - Temporary Road Safety Barriers (TRSB) shall be used to contain and redirect errant vehicles so as to reduce the likelihood of them entering the work site
label | ○ Provision shall be made for TRSB At locations where work is to be close to traffic, and in accordance with Worker safety requirements in MUTCD Part 3;
label | ○ Only those TRSB which are included in the Transport and Main Roads – Road Safety Barrier Systems, End Treatments and other related Road Safety Devices shall be used
label | ○ All TRSB and end treatments shall be installed in accordance with the department's Standard Drawings and/or the manufacturer's specifications
label | Reference - MRTS02 Cl 6.5.11 & Annexure 2.1
label | Item Check - Check and Verify
checkpoint | Temporary line marking
label | Acceptance Criteria and Frequency - Details of proposed temporary pavement markings are submitted to the local government for approval at least two working days prior to the proposed installation of the temporary pavement.
label | Reference - LCC SS 10 Part 2.8.4
label | Item Check - Check and Verify
checkpoint | Access
label | Acceptance Criteria and Frequency - The Contractor’s site facilities shall be located to provide safe ingress and egress of traffic to the Site and public roads and shall not deteriorate the existing traffic operation.
label | Reference - MRTS 28 Clause 4.5.6
label | Item Check - Check and Verify
checkpoint | Final Sign off and Approval - Conformance with the Specification
textbox | Name of Cient's Representative
date | Date
textbox | Name of Contractor's Representative
date | Date
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | ITP - Dense Grade Asphalt | itp
section | Dense Grade Asphalt
checkpoint | Submission of Asphalt Quality Plan
label | Acceptance Criteria and Frequency - The Contractor must develop an Asphalt Quality Plan (AQP) for the asphalt work to the Administrator for consideration at least seven days prior to work commencing and must be implemented.
label | Reference - MRTS30 Cl 5.2
label | Item Check - Milestone
checkpoint | Nomination of registered mix designs
label | Acceptance Criteria and Frequency - At least seven days before asphalt is to be incorporated into the Works, the Contractor shall submit to the Administrator a copy of the mix design certificate(s) for each nominal size and type of asphalt mix to be incorporated into the Works.
label | Reference - MRTS30 Cl 7.3.3
label | Item Check - Milestone
checkpoint | Asphalt Mix Properties
label | Acceptance Criteria and Frequency - The properties of asphalt mix must comply with Table 2.6.1 - Asphalt mix properties of LCC spec No. 13 Part 2.6.1 when tested in accordance with column 3, asphalt shall aslo comply with MRTS 30.
label | Reference - LCC SS 13 Part 2.6 & MRTS 30
label | Item Check - Check and Verify
checkpoint | General
label | Acceptance Criteria and Frequency - All asphalt shall be placed in accordance with design drawings and as per drawings GW001 & LS001
label | Reference - General
label | Item Check - Ckeck and Verify
checkpoint | Production of Asphalt
label | Acceptance Criteria and Frequency - Asphalt shall be produced by a registered asphalt manufacturer from the nominated asphalt plant in accordance with the nominated mix design for the Works. Asphalt shall not be incorporated into the Works until the Contractor has demonstrated to the Administrator that the underlying lots conform to the specified requirements
label | Reference - MRTS30 Cl 7.4.1
label | Item Check - Hold Point 2
holdpoint | HOLD POINT
checkpoint | Production of Asphalt
label | Acceptance Criteria and Frequency - For asphalt placed over pavement constructed by others, the surface on which asphalt will be placed shall be tested for perceptible surface deformation by ‘proof rolling’ in the presence of the Administrator.
label | Reference - MRTS30 Cl 8.2.2
label | Item Check - Witness Point 1
checkpoint | Preparation
label | Acceptance Criteria and Frequency - Unless otherwise approved by the Administrator, asphalt shall not be placed over pavement exhibiting significant perceptible surface deformation.
label | Reference - MRTS30 Cl 8.2.2
label | Item Check - Hold Point 4
holdpoint | HOLD POINT
checkpoint | Preparation of pavement
label | Acceptance Criteria and Frequency - Existing substrate shall not be wet and shall be swept thouroughly to remove and loose or deleterious material
label | Reference - MRTS30 Cl 8.2.2
label | Item Check - Check and Verify
checkpoint | Application of Asphalt - Temperature
label | Acceptance Criteria and Frequency - The asphalt mix temperature is controlled so that it is between 135C and 175C when loaded into the delivery truck, the mix temperature is between 110C and 165C immediately behind the paver with compaction commencing before the temperature of the mix falls below a minimum of 95C.
label | Reference - LCC SS 13 Part 3.1.1&2
label | Item Check - Check and Verify
checkpoint | Asphalt Compaction
label | Acceptance Criteria and Frequency - Compaction is commenced as soon as possible after spreading, and is completed in the shortest possible time except in the event of significant deformation or an irregularity occurring under the action of the roller in which case, rolling is delayed
label | ○ For compaction testing, a lot is the same as for a production lot and compaction testing is undertaken in accordance with Q302A, Q302B, Q306B and Q314.
label | ○ After completion of each job, core samples are taken from the compacted asphalt at the rate of one core per 1000m2 of asphalt laid, but with a minimum of three cores per job, asphalt compaction shall be greater than 95%
label | Reference - LCC SS 13 Part 3.4 & 3.5
label | Item Check - Hold Point
holdpoint | HOLD POINT
checkpoint | Final Sign off and Approval - Conformance with the Specification
textbox | Name of Cient's Representative
date | Date
textbox | Name of Contractor's Representative
date | Date
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | ITP - Precast Concrete Channel Drain | itp
section | Precast Concrete Channel Drain
checkpoint | General
label | Acceptance Criteria and Frequency - Precast and/or preformed trough components shall be installed in the locations and in accordance with the details specified in the drawings and excavations shall be carried out in accordance with Clause 13 of MRTS04 General Earthworks.
label | Reference - General
label | Item Check - Check and Verify
checkpoint | Bedding of drainage trough components
label | Acceptance Criteria and Frequency - Foundation bedding materials shall be placed in accordance with Clause 19 of MRTS04 General Earthworks. The foundation bedding shall provide continuous, even support to the drainage trough components
label | Reference - MRTS 03 Cl 12.3.2
label | Item Check - Check and Verify
checkpoint | Precast concrete drain assembly
label | Acceptance Criteria and Frequency - Drainage trough components shall be assembled in accordance with the manufacturer’s drawings and recommendations.
label | Reference - MRTS 03 Cl 12.3.3
label | Item Check - Check and Verify
checkpoint | Laying drainage trough components
label | Acceptance Criteria and Frequency - Drainage trough components shall be laid with the tops flush with the finished batter the laying of drainage trough components shall commence at the outlet end of the trough and progress to the inlet end.
label | ○ Where necessary, components shall be selected and arranged to give satisfactory fit the ends of components shall be free of any foreign matter at the time of jointing, when butt and flush joints are specified, the drainage trough components shall abut one another.
label | Reference - MRTS 03 Cl 12.3.4
label | Item Check - Check and Verify
checkpoint | Drainage trough bandages
label | Acceptance Criteria and Frequency - Bandage covers shall be applied to the outer surfaces of butt and flush joints. Bandage covers shall consist of:
label | a) one layer of non-woven fabric, or
label | b) three layers of woven fabric.
label | ○ Fabric covers shall have a width sufficient to overlap adjacent components by not less than 45 mm and shall not be applied until the ambient temperature exceeds 15°C. Fabric covers shall not be wrinkled and shall adhere to the outer surfaces of the adjacent components. The ends of the fabric in the covers shall be secured in accordance with the manufacturer’s recommendations.
label | Reference - MRTS 03 Cl 12.3.4
label | Item Check - Check and Verify
checkpoint | Cutting Draianage trough components
label | Acceptance Criteria and Frequency - Where the cutting of precast drainaage components is required the following actions shall be taken:
label | ○ Cutting operations shall provide neat end surfaces, the cut surfaces of concrete drainage trough components shall be given two coats of a surface tolerant epoxy.
label | ○ The cut surfaces of corrugated steel drainage trough components shall be given two coats of zinc-rich organic priming paint as specified in AS 3750.9. The coats shall have a combined thickness at least equivalent to the galvanised coating thickness. Each coat shall overlap adjacent uncut surfaces by not less than 25 mm.
label | Reference - MRTS 03 Cl 12.3.5
label | Item Check - Check and Verify
checkpoint | Installing holding down anchors
label | Acceptance Criteria and Frequency - Holding down anchors shall be installed in accordance with the requirements specified in the Standard Drawings and the manufacturer’s recommendations as relevant
label | Reference - MRTS 03 Cl 12.3.6
label | Item Check - Check and Verify
checkpoint | Water Test
label | Acceptance Criteria and Frequency - Where the longitudinal grade of channels is less than 1%, a test shall be carried out by discharging water into the channel to check uniformity of flow along the channel. After the flow has ceased, water shall not pond to a depth of more than 5 mm in any section of the channel. The test shall be carried out as soon as possible after the concrete in the channel has hardened.
label | Reference - MRTS 03 Cl 18.5
label | Item Check - Witness Point 1
checkpoint | Final Sign off and Approval - Conformance with the Specification
textbox | Name of Cient's Representative
date | Date
textbox | Name of Contractor's Representative
date | Date
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | ITP - Sprayed Bitumen Surfacing | itp
section | Sprayed Bitumen Surfacing
checkpoint | Construction Procedure
label | Acceptance Criteria and Frequency - Procedures shall be submitted to the Administrator not less than seven days prior to their use, and procedures shall not be implemented until permission to use has been granted by the Administrator.
label | Reference - MRTS12 Cl 5.2
label | Item Check - Hold Point 1
holdpoint | HOLD POINT
checkpoint | Plant Required
label | Acceptance Criteria and Frequency - The Contractor shall have on the Site and in use as required the plant necessary for the performance of the particular operation. The respective minimum requirements for the plant listed in Table 9 shall apply. Not less than seven days prior to sealing operations, the Contractor shall submit details of all plant to be used in the operations.
label | Reference - MRTS12 Cl 9
label | Item Check - Hold Point 4
holdpoint | HOLD POINT
checkpoint | Surface Preparation
label | Acceptance Criteria and Frequency - Any surface that is to be sprayed shall be prepared in a manner that all foreign and loose material, including lenses of pavement material, are removed from the surface, the surface is swept with a road broom until the larger particles in the surface of the pavement are slightly exposed without dislodgement and excessive erosion of the surrounding finer material, a light watering is carried out just prior to spraying; or all foreign and loose material is removed from the surface; the surface is swept with a road broom;
label | Reference - LCC SS 14 Part 4.1.3
label | Item Check - Check & Verify
checkpoint | Pavement Surface Temperature
label | Acceptance Criteria and Frequency - Spraying shall not commence until the temperature on the surface of the pavement is above the temperature given in Clause 4.2 of the Annexure MRTS12.1 or, if not so given, above 20ºC for at least one hour before spraying commences.
label | Reference - LCC SS 14 Part 6.1.1
label | Item Check - Check & Verify
checkpoint | Spraying Temperature
label | Acceptance Criteria and Frequency - Bituminous emulsion shall be sprayed at a temperature consistent with the requirements detailed in Table 12.5
label | – – – – – – – – – – – – – – – – –
label | Table 12.5 - Spraying temperature range
label | Material ¦¦ Spraying Temperature Range
label | – – – – – – – – – – – – – – – – –
label | Bituminous emulsion - 60% bitumen content ¦¦ Ambient
label | Bituminous emulsion - 67% bitumen content ¦¦ Minimum - 30°C, Maximum - 80°C
label | Modified Bituminous emulsion ¦¦ As shown in Clause 1.2 of Annexure MRTS12.1
label | – – – – – – – – – – – – – – – – –
label | Reference - MRTS 12 Cl 12.5
label | Item Check - Witness Point 2
checkpoint | General Standards
label | Acceptance Criteria and Frequency - Emulsion primers only to be used where approved by administrator and shall be used according to the manufacturers specifications.
label | Reference - LCC SS 14 Part 4.1.3
label | Item Check - Check & Verify
checkpoint | Details of spraying operations
label | Acceptance Criteria and Frequency - After each spray run, all details of the sealing operations are recorded on a bituminous materials spraying record sheet. The bituminous materials spraying record sheet is signed by the local government and a copy of the completed bituminous materials spraying record sheet is provided to the local government at the end of each day's operation.
label | Reference - LCC SS 14 Part 10.1.1
label | Item Check - Witness Point
checkpoint | Final Sign off and Approval - Conformance with the Specification
textbox | Name of Cient's Representative
date | Date
textbox | Name of Contractor's Representative
date | Date
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | ITP - Hand Placed Concrete | itp
section | Hand Placed Concrete
checkpoint | Design location
label | Acceptance Criteria and Frequency - All concrete works are to be intalled in location and noted on a lot map attached to this document and accordance with the specified drawings:
textbox | Specified Drawing:
label | Reference - IFC Design Drawings
label | Item Check - Check and Verify
checkpoint | Concrete Mix Design Submission
label | Acceptance Criteria and Frequency - All mix designs shall be submitted to the administrator prior to works beginning if insufficient testing history is available for the specified mix from an approved supplier, preliminary mixes for all grades of concrete are designed, made and tested.
label | Reference - LCC SS No. 7 Part 2.3
label | Item Check - Milestone
checkpoint | Concrete Mix Design Approval
label | Acceptance Criteria and Frequency - Concrete Mix designs are approved prior to the usage in any works.
label | Reference - LCC SS No. 7 Part 2
label | Item Check - Hold Point
holdpoint | HOLD POINT
checkpoint | Formwork Approval
label | Acceptance Criteria and Frequency - All steel reinforcement that will be used in concrete works shall be inspected and approved by the local government prior to the placement of concrete, all formwork shall be inspected and checked against formwork checklist. When forms appear to be unsatisfactory in any way, either before or during the placing of concrete, the work does not proceed until the defects have been corrected to the approval of the local government.
label | Reference - LCC SS No. 7 Part 5.3.11
label | Item Check - Hold Point
holdpoint | HOLD POINT
checkpoint | Footpath Contraction Joint
label | Acceptance Criteria and Frequency - Contraction joints:
label | (a) are provided at centres matching the width of the footpath and not more than 3.0 metres;
label | (b) are formed by a jointing tool;
label | (c) do not exceed 35mm in depth or 6mm in width;
label | (d) are at right angles to the edge of the path.
label | Reference - LCC SS No. 8 Part 3.1.4
label | Item Check - Check and Verify
checkpoint | Footpath Expansion Joint
label | Acceptance Criteria and Frequency - Expansion joints:
label | (a) are placed at 15 metre centres except for 2.0m footpath which can be 16m to match dimension multiplier;
label | (b) are at right angles to the edge of the path;
label | (c) extend for the full depth of the concrete path and are 10mm in width.
label | ○ All expansion joints shall be as per LCC specifcations or where specified in standard darwings.
label | Reference - LCC SS No. 8 Part 3.1.5
label | Item Check - Check and Verify
checkpoint | Slump & Testing
label | Acceptance Criteria and Frequency - All concrete poured on site shall be slump tested by a NATA certified testing contractor, all slump testing values shall be recorded by a pour record sheet and provided to the administrator with the submission of the lot. All slump values shall comply with table 2.4.1 under Standard Specification 7. All concrete shall be tested for strength, concrete is sampled and tested in accordance with AS 1012.1-1993 Methods of testing concrete - Sampling of fresh concrete, by an approved NATA registered laboratory and the results are provided to the local government.
label | Reference - LCC SS No. 7 Part 2.4
label | Item Check - Check and Verify
checkpoint | Temperature and Timing
label | Acceptance Criteria and Frequency - Where the ambient temperature is likely to exceed 30°C, all practical precautions are taken to maintain the concrete at a temperature not exceeding 30°C at the time of placing to prevent shrinkage, settlement and presetting cracks. No concrete with a temperature higher than 30°C is placed unless otherwise approved by the local government.
label | ○ Ready mixed concrete is placed and compacted within 1 hour 15 minutes of charging the mixer for concrete temperatures up to 30°C and within 30 minutes of charging the mixer.
label | Reference - LCC SS No. 7 Part 4.2&4.3
label | Item Check - Check and Verify
checkpoint | Finishing
label | Acceptance Criteria and Frequency - All surfaces of concrete that are exposed to view in the completed structure are finished such that:
label | (a) Immediately after the removal of forms, all fins and other projections are ground off, all pockets and honeycombs are cleaned and filled with a stiff cement mortar having the same proportion of cement and sand as the original concrete, and the surface of the patch is ground flush;
label | (b) Decks are roughened slightly by brooming or other approved method before initial set;
label | (c) Kerb and channel, invert crossings, vehicle crossings and industrial crossings are finished with an approved steel finishing tool;
label | (d) Footpaths and pram ramps are finished with a wooden float and broomed.
label | Reference - LCC SS No. 7 Part 6.1.2
label | Item Check - Check and Verify
checkpoint | Curing
label | Acceptance Criteria and Frequency - Concrete surfaces are kept moist by spraying with an approved curing compound, or water sprays or wet sand in which case the surfaces are kept moist 24 hours a day for the full period specified without any breaks at weekends or holidays. Curing is commenced immediately on completion of the finishing of exposed surfaces or within 30 minutes of removal of the forms from other surfaces.
label | Reference - LCC SS No. 7 Part 6.3
label | Item Check - Check and Verify
checkpoint | Dimension Tolerances
label | Acceptance Criteria and Frequency - Where tolerances are not stated in the approved drawings for any individual structure or feature thereof, deviations from established lines, grades and dimensions are not greater than the tolerances listed in Table 6.4.1–Tolerances of this standard specification and are applied to the completed work.
label | ○ Size of member or thickness of slab: +7mm, -0
label | ○ Cover of Concrete Over Reinforcement: +7mm, -3mm
label | ○ Contract dimensions:
label | – 0-20meters: +7mm
label | – Over 20meters: +13mm
label | Reference - LCC SS No. 7 Part 6.4
label | Item Check - Check and Verify
checkpoint | Final Sign off and Approval - Conformance with the Specification
textbox | Name of Cient's Representative
date | Date
textbox | Name of Contractor's Representative
date | Date
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | ITP - Landscaping | itp
section | Topsoil & Turf
checkpoint | Soil Type
label | Acceptance Criteria and Frequency - Alll topsoil imported to site shall comply wiht the following below
label | (a) is a fine soil type in accordance with Table 6.2.1–Soil type by texture of this standard specification;
label | (b) is friable;
label | (c) is moderately free draining;
label | (d) complies with AS 4419–2003 Soils for landscaping and garden use;
label | (e) is free of fire ants;
label | (f) is free from Nut Grass (Cyperus rotundus);
label | Reference - LCC SS No. 2 Part 6.2.2
label | Item Check - Check and Verify
checkpoint | Topsoil Provider
label | Acceptance Criteria and Frequency - Soil is imported from a source approved by the local government or is provided from material upon the premises where approved by the local government.
label | ○ Soil from the premises which is improved to comply with Table 6.2.1–Soil type by texture of this standard specification by the use of additives such as Gypsum, may be used as topsoil where approved by the local government.
label | Reference - LCC SS No. 2 Part 6.2.3
label | Item Check - Hold Point
holdpoint | HOLD POINT
checkpoint | Spreading Topsoil
label | Acceptance Criteria and Frequency - Soil is spread such that:
label | (a) the finished surface of the soil is smooth, free of lumps and free draining;
label | (b) the finished surface levels allows for the settling and spreading of mulch;
label | (c) the soil is lightly compacted over the prepared sub-grade;
label | (d) in a grassed area the edge of the soil is feathered into undisturbed ground.
label | Reference - LCC SS No. 2 Part 6.2.5
label | Item Check - Check and Verify
checkpoint | Topsoil Finish
label | Acceptance Criteria and Frequency - Where soil is next to a kerb, a path, a mowing strip or other hard paved surface:
label | (a) the soil is finished flush for a seeded grass area and bevelled below the abutting finished grade to allow for turf or mulch;
label | (b) the finished grade of the mulch is approximately 10mm below the abutting finished surface level;
label | (c) the finished surface level of the turf is flush with the abutting finished surface level;
label | (d) the finished surface level of a grass area, turf and a garden bed adjacent to a building or other structure is 125mm below the weepholes in the building or the structure.
label | Reference - LCC SS No. 2 Part 6.2.6
label | Item Check - Check and Verify
checkpoint | Topsoil Depth
label | Acceptance Criteria and Frequency - Topsoil depth is 75mm as per contract drawing GW001
label | Reference - Contract Drawings
label | Item Check - Check and Verify
checkpoint | Fertiliser
label | Acceptance Criteria and Frequency - Fertiliser is to be applied as per manufacturer's specification to ensure healthy long term growth.
label | Reference - LCC SS No. 2 Part 6.4.1
label | Item Check - Check and Verify
checkpoint | Turfed Area
label | Acceptance Criteria and Frequency - A turf roll has a minimum soil thickness of 20mm.
label | (2) The turf is delivered to the premises within 24 hours of being cut.
label | (3) The turf is laid within 36 hours of being cut.
label | (4) Where the laying of the turf is delayed, the turf is:
label | (a) protected and watered to maintain its condition;
label | (b) not allowed to dry out at any stage from cutting to laying.
label | Reference - LCC SS No. 2 Part 6.4.3
label | Item Check - Check and Verify
section | Maintenance
checkpoint | General Maintenance
label | Acceptance Criteria and Frequency - The premises is to be kept free of weeds and rubbish and any damaged, defective or stolen landscaping item is to be repaired or replaced.
label | Reference - LCC SS No.3 Part 7.1
label | Item Check - Check and Verify
checkpoint | Maintenance Period
label | Acceptance Criteria and Frequency - All turfef areas are maintained through the maintenance period such that at the end of the establishment period a turfed area has 100 percent of turf coverage, the plant estabblishment period is a minimum period of 12 weeks from the date that PC is approved.
label | Reference - LCC SS No.3 Part 7.3
label | Item Check - Check and Verify
checkpoint | Maintenance of Turf
label | Acceptance Criteria and Frequency - A grassed area is maintained during the maintenance period by:
label | (a) mowing grass to 50mm height when grass has grown no higher than 75mm and removing grass clippings from the landscape area or as otherwise approved by the local government;
label | (b) applying water at regular intervals to ensure ongoing healthy growth
label | Reference - LCC SS No.3 Part 7.4.2
label | Item Check - Check and Verify
checkpoint | Maintenance Program
label | Acceptance Criteria and Frequency - The Maintenance Program is to be prepared by the Contractor and submitted to the Superintendent for approval prior to commencement of work under the Contract and is to contian details about the frequency which the contractor proposes to carry out its obligation under section 7.4 SS 2
label | Reference - LCC SS No.7 Part 8.3.4
label | Item Check - Milestone/ Hold Point
holdpoint | HOLD POINT
checkpoint | Final Sign off and Approval - Conformance with the Specification
textbox | Name of Cient's Representative
date | Date
textbox | Name of Contractor's Representative
date | Date
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | ITP - Conduits and Pits | itp
section | Conduits and Pits
checkpoint | General
label | Acceptance Criteria and Frequency - A construction procedure for the installation of all conduits and pits shall be submitted to the Administrator at least 14 days prior to the commencement of installation. No excavation activity associated with the installation of conduits and pits shall commence until the expiration of the 14-day period.
label | Reference - MRTS 91 Clause 5.3
label | Item Check - Witness Point & Hold Point
holdpoint | HOLD POINT
checkpoint | Asbestos Assessment
label | Acceptance Criteria and Frequency - Asbestos is suspected or found in existing installation, work at this site must be stopped immediately, and the finding must be reported to the principal immediately for their decision and instruction on the work to be carried out at the site.
label | Reference - MRTS 91 Clause 6.1
label | Item Check - Hold Point
holdpoint | HOLD POINT
checkpoint | Material Certification
label | Acceptance Criteria and Frequency - All materials must comply strictly with the requirements of this Technical Specification. For all materials, a certificate of such compliance shall be provided to the Administrator before the materials are incorporated into the works
label | Reference - MRTS 91 Clause 7.1
label | Item Check - Hold Point
holdpoint | HOLD POINT
checkpoint | Excavation for underground conduits and pits
label | Acceptance Criteria and Frequency - Conduit runs and pit locations shall be set out and notice of such set out shall be provided to the principal at least 48 hours prior to the commencement of excavation. Construction shall not commence before the expirations of the period of notice.
label | Reference - MRTS 91 Claus 8.1
label | Item Check - Witness Point & Hold Point
holdpoint | HOLD POINT
checkpoint | Bottom of trench
label | Acceptance Criteria and Frequency - The bottom of the trench shall be compacted as per Standard Drawing 1149 to form a firm uniform surface free from loose material.
label | Reference - MRTS 91 Clause 8.4
label | Item Check - Witness Point
checkpoint | Boring and Jacking
label | Acceptance Criteria and Frequency - Work shall not commence until it has been demonstrated to the Administrator that the proposed equipment can accurately install the conduit in accordance with MRTS140 Horizontal Directional Drilling (HDD) and Standard Drawing 1149 Installation of Underground Electrical and Communication.
label | Reference - MRTS 91 Clause 8.7
label | Item Check - Hold Point
holdpoint | HOLD POINT
checkpoint | Installation of conduits
label | Acceptance Criteria and Frequency - The installation of conduits shall conform to the requirements of Standard Drawing 1149. The installation of communications conduits shall also comply with the requirements of AS/CA S009. Prior to installation, the Contractor shall inspect all conduit and conduit fittings to ensure that they are free of any defects that could damage the cables during installation. Conduits to be installed without dips/low points to ensure that drainage at pits operates as intended.
label | ○ The conduits are not to be lower than the pit it connects to unless approved by the Principal. Road crossing installed by ‘boring’ conduit to be installed level to facilitate correct drainage of conduit.
label | Reference - MRTS 91 Clause 9.1
label | Item Check - Hold Point
holdpoint | HOLD POINT
checkpoint | Mandrel
label | Acceptance Criteria and Frequency - After installation and backfilling, the conduit and conduit fittings shall be proved by drawing a mandrel having a diameter of at least 95% of the internal diameter of the conduit. The mandrel shall have a length sufficient to allow it to pass around any bends in the conduit, but not shorter than 95% of the diameter of the conduit being tested
label | Reference - MRTS 91 Clause 9.1
label | Item Check - Hold Point
holdpoint | HOLD POINT
checkpoint | Draw rope
label | Acceptance Criteria and Frequency - Any joints made in the draw rope shall be capable of resisting the same tensile load as the draw rope without such a joint. The joint shall not appreciably increase the diameter of the rope.
label | Reference - MRTS 91 Clause 9.13
label | Item Check - Witness point
checkpoint | Vermin proofing of conduits
label | Acceptance Criteria and Frequency - Any alternative proposed conduit sealing system shall be fit for purpose, and a proprietary system, and shall be submitted to the Administrator for consideration and approval prior to commencement of the installation of any cabling.
label | Reference - MRTS 91 Clause 10.9
label | Item Check - Hold Point
holdpoint | HOLD POINT
checkpoint | Bedding of pit
label | Acceptance Criteria and Frequency - The bottom of an excavation for a pit shall be compacted to at least 95% relative compaction.
label | Reference - MRTS 91 Clause 10.4
label | Item Check - Hold Point
holdpoint | HOLD POINT
checkpoint | Compact bedding material
label | Acceptance Criteria and Frequency - Compact bedding material to density index 60.
label | Reference - MRTS 91 Clause 10.4
label | Item Check - Check & Verify
checkpoint | Drainage Holes
label | Acceptance Criteria and Frequency - The lowest open end of conduits installed in poles and other field equipment enclosures shall be at least 50 mm higher than the surrounding finished surface level.
label | Reference - MRTS 91 Clause 10.11
label | Item Check - Witness Point
checkpoint | Backfilling
label | Acceptance Criteria and Frequency - Backfilling of trenches for conduits shall not commence until the conduit system has been inspected by the Administrator
label | Reference - MRTS 91 Clause 13.1
label | Item Check - Hold Point
holdpoint | HOLD POINT
checkpoint | Final Sign off and Approval - Conformance with the Specification
textbox | Name of Cient's Representative
date | Date
textbox | Name of Contractor's Representative
date | Date
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | ITP - Linemarking | itp
section | Linemarking
checkpoint | General
label | Acceptance Criteria and Frequency - The Contractor shall provide properly constructed toilets, drinking water, eating and washing facilities at the Contractor’s site facilities for the use of personnel and connect to town sewer where possible and shall comply with AS 1547 On-site domestic wastewater management.
label | Item Check - Check and Verify
checkpoint | Site Security
label | Acceptance Criteria and Frequency - The Contractor shall be responsible for the security of the buildings, construction plant and machinery.
label | ○ The Contractor shall also take all necessary precautions to make the area safe to the public, including provision of signs outlining relevant project contact details, safety requirements and any other relevant details on the main entry gate.
label | Item Check - Check and Verify
checkpoint | Visibility to the public
label | Acceptance Criteria and Frequency - External lights on the facilities and camps should be positioned or shielded to minimise light overflow onto neighbouring properties.
label | Item Check - Check and Verify
checkpoint | Noise
label | Acceptance Criteria and Frequency - Noise generated from the site facilities shall be kept to a minimum and the Contractor shall construct noise amelioration devices around the site facilities to bring the noise levels within specified criteria.
label | Item Check - Check and Verify
checkpoint | Dust Suppression
label | Acceptance Criteria and Frequency - Adequate precautions are taken to minimise dust or dust-related conditions during any activity which may affect the safety and general comfort of any person. Regular applications of water are applied to any roads or structures whilst completing earthworks
label | Item Check - Check and Verify
checkpoint | Temporary road safety barriers
label | Acceptance Criteria and Frequency - Temporary Road Safety Barriers (TRSB) shall be used to contain and redirect errant vehicles so as to reduce the likelihood of them entering the work site
label | ○ Provision shall be made for TRSB At locations where work is to be close to traffic, and in accordance with Worker safety requirements in MUTCD Part 3;
label | ○ Only those TRSB which are included in the Transport and Main Roads – Road Safety Barrier Systems, End Treatments and other related Road Safety Devices shall be used
label | ○ All TRSB and end treatments shall be installed in accordance with the department's Standard Drawings and/or the manufacturer's specifications
label | Item Check - Check and Verify
checkpoint | Temporary line marking
label | Acceptance Criteria and Frequency - Details of proposed temporary pavement markings are submitted to the local government for approval at least two working days prior to the proposed installation of the temporary pavement.
label | Item Check - Check and Verify
checkpoint | Access
label | Acceptance Criteria and Frequency - The Contractor’s site facilities shall be located to provide safe ingress and egress of traffic to the Site and public roads and shall not deteriorate the existing traffic operation.
label | Item Check - Check and Verify
checkpoint | Final Sign off and Approval - Conformance with the Specification
textbox | Name of Cient's Representative
date | Date
textbox | Name of Contractor's Representative
date | Date
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | ITP - Subsoil Drains | itp
section | Subsoil Drains
checkpoint | Material Requirements - Standard subsoil drains
label | Acceptance Criteria and Frequency - A sub-soil drainage pipe is a class 400 perforated corrugated PVC pipe Type 1 in accordance with AS 2439.1-2007 Perforated plastics drainage and effluent pipe and fittings - Perforated drainage pipe and associated fittings.
label | ○ The diameter of a sub-soil drainage pipe is a minimum of 100mm and the perforations do not exceed 1.1mm in width and 7.4mm in length.
label | Reference - LCC SS 12 Part 2.5
label | Item Check - Check and Verify
checkpoint | Longitudinal subsoil drain in pavement
label | Acceptance Criteria and Frequency - Where a kerb and channel is constructed a sub-soil drainage pipe is constructed:Standard specification No. 12 (Sub-soil drainage) Ss12-2
label | (a) immediately below the back of the kerb in accordance with standard drawing IPWEAQ R-0140,
label | (b) at least 150mm below the finished sub-grade level
label | Reference - LCC SS 12 Part 2.2
label | Item Check - Check and Verify
checkpoint | Subsoil Drain Excavation
label | Acceptance Criteria and Frequency - A trench for a sub-soil drainage pipe is excavated to 50mm below the invert level of the sub-soil drainage pipe and have a gradient which is specified in the approved drawings or which is a minimum of 0.5 percent. the excavated trench is to be a minimum of 100mm wider than the outside diameter of the sub-soil drainage pipe.
label | Reference - LCC SS 12 Part 2.4
label | Item Check - Check and Verify
checkpoint | Filter Material
label | Acceptance Criteria and Frequency - Fileter material shall be either 5mm or 10mm drainage aggregate as per standard drawing IPWEA - RS - 140
label | Reference - IPWEA-RS-140
label | Item Check - Check and Verify
checkpoint | Subsoil drain outlet
label | Acceptance Criteria and Frequency - A sub-soil drainage pipe: shall be connected to a gully pit, as specified in standard drawing IPWEAQ R-0140; or discharges to a culvert head wall or an open channel below the edge of the road shoulder or at the edge of an embankment.
label | (a) If a sub-soil drainage pipe is not connected into a gully pit or a culvert headwall, a concrete headwall is provided to the sub-soil drainage pipe.
label | (b) The headwall is at least 100mm thick and extends for a minimum of 150mm on all sides of the pipe.
label | (c) Where the outlet is through a batter, the surface of the headwall conforms to the batter slope.
label | Reference - LCC SS 12 Part 4.3
label | Item Check - Check and Verify
checkpoint | Final Sign off and Approval - Conformance with the Specification
textbox | Name of Cient's Representative
date | Date
textbox | Name of Contractor's Representative
date | Date
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | ITP - General Excavation | itp
section | General Excavation
checkpoint | Lot Boundries
label | Acceptance Criteria and Frequency - Lot Number established with the Lot boundaries of the works clearly defined for traceability within the works
label | Reference - MRTS 04 Cl 5.6
label | Item Check - Check and Verify
checkpoint | Services:
label | Acceptance Criteria and Frequency - All services identified – shall be marked, potholed and/or protected as required
label | ○ Permit to excavate issued by Project Engineer
label | Reference - DBYD
label | Item Check - Check and Verify
checkpoint | Erosion Sediment Control
label | Acceptance Criteria and Frequency - Erosion and sediment controls in place
label | ○ Due care taken to ensure native fauna is not harmed
label | ○ Vibration and Air quality to be monitored as a direct result of construction activities
label | Reference - MRTS51 Cl 10.3
label | Item Check - Check and Verify
checkpoint | Excavation Cutting
label | Acceptance Criteria and Frequency - The bottom of excavations shall be trimmed to the tolerances specified in Clause 6 and any loose material removed from the surface.
label | ○ The existing soil is compacted to 95 percent relative dry density standard compaction, for a depth of 300mm below the sub-grade and care is taken to ensure that the topsoil and organic material is removed and replaced with approved selected material for a depth of 500mm and compacted to 95 percent relative dry density standard compaction where the sub-grade passes through the natural surfaceat the ends of the excavation or anywhere in cross-section.
label | Reference - LCC SS No.1 Part 9.1
label | Item Check - Check and Verify
checkpoint | Unsuitable Material in Excavtion
label | Acceptance Criteria and Frequency - Unsuitable material below the level of the sub-grade in an excavation is:
label | (a) removed and run to spoil in accordance with section 12.1 of Specification 1,or replaced with select backfill in accordance with section 8.3–Selected gravel fill or selected backfill of this standard specification;
label | (b) compacted to 95 percent relative dry density standard compaction
label | Reference - LCC SS No.1 Part 9.3
label | Item Check - Check and Verify
checkpoint | Unsuitable Material Below Lines of Cuttings
label | Acceptance Criteria and Frequency - Material below the finished lines and levels of cuttings, which is Unsuitable Material in accordance with the provisions of Clause 9.2, shall be removed and disposed of in accordance with the provisions of Clause 9.4.
label | ○ Where Unsuitable Material has been removed, the excavation shall be backfilled to the finished surface level with appropriate fill material as specified on the drawings or in accordance with Clause 18 and 19.
label | Reference - MRTS04 Clause 13.3.2.2
label | Item Check - Check and Verify
checkpoint | Finished Cut Surface Survey
label | Acceptance Criteria and Frequency - Once Works are completed to Subgrade Level (including all Subgrade treatments), an As Constructed Survey of the bottom of the excavated area shall be undertaken as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator.
label | Reference - MRTS04 Clause 13.3.2.1
label | Item Check - Check and Verify
checkpoint | Lot Acceptance
label | Acceptance Criteria and Frequency - Lot closure requires all relevant information to be attached to the Conformance Report this includes a Lot Plan, Survey Report, Hold Points/Approvals & any supporting documentation
label | Item Check - Check and Verify
checkpoint | Final Sign off and Approval - Conformance with the Specification
textbox | Name of Cient's Representative
date | Date
textbox | Name of Contractor's Representative
date | Date
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | ITP - Subgrade Treatment | itp
section | Subgrade Treatment
checkpoint | Lot Boundries
label | Acceptance Criteria and Frequency - Lot Number established with the Lot boundaries of the works clearly defined for traceability within the works
label | Reference - MRTS 04 Cl 5.6
label | Item Check - Check and Verify
checkpoint | Proof Roll
label | Acceptance Criteria and Frequency - At the completion of earthworks to Subgrade Level, the Contractor shall test for perceptible surface deformation by undertaking proof rolling, Work on the pavement does not commence until the subgrade has been inspected and approved by the local government
label | Reference - LCC SS No.6 Part 4.1
label | Item Check - Hold Point
holdpoint | HOLD POINT
checkpoint | Testing - Compaction
label | Acceptance Criteria and Frequency - Subgrade shall be compacted and tested for a standard conpaction of 95% as per table 6.1.1
label | Reference - LCC SS No. 6 Part 6.1
label | Item Check - Test Reports
label | ○ 1 per 500m2
label | ○ 4 per Lot
checkpoint | Geometrics - Survey
label | Acceptance Criteria and Frequency - The heights of earthworks measured anywhere on a layer surface shall not vary from those shown on the drawings,by more than the tolerance stated in Table 5.1.1 unless specified otherwise.
label | ○ Subgrade Level tolerances as per table 5.1.1:- 30mm and +10mm
label | Reference - LCC SS No. 6 Part 5.1
label | Item Check - Survey, 20m intervals
checkpoint | Final Sign off and Approval - Conformance with the Specification
textbox | Name of Cient's Representative
date | Date
textbox | Name of Contractor's Representative
date | Date
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | ITP - Installation of Kerb, Channel & Kerb and Channel | itp
section | Installation of Kerb, Channel & Kerb and Channel
checkpoint | Kerb type
label | Acceptance Criteria and Frequency - Kerb and channel complies with standard drawing number R-0080 and is one of the following profiles: B1, B2, SM5, M3, Median and Invert, and must be wet mix unless otherwise approvd by local government
label | Reference - LCC SS No.8 Part 2.1
label | Item Check - Check and Verify
checkpoint | Design and Set-Out Locations
label | Acceptance Criteria and Frequency - Concrete for kerb and kerb and channel is 32 MPa strength grade complying with the requirements of AS 1379-2007:
label | ○ The slump values of the concrete are machine finished (wet kerb)—12mm minimum—40mm maximum.
label | Reference - LCC SS No.8 Part 2.3
label | Item Check - Check and Verify
checkpoint | Compaction of Materials
label | Acceptance Criteria and Frequency - Where pavement thickness exceeds 175mm in depth, the pavement extends under the kerb where the pavement thickness does not exceed 175mm in depth, the kerb and channel is firmly bedded on 100mm road base aggregate compacted to 95 percent modified dry density as required under AS 1289.0-2000 Methods of testing soils for engineering purposes - General requirements and list of methods.
label | ○ No concrete is placed until the foundations have been approved by the local government.
label | Reference - LCC SS No.8 Part 2.2
label | Item Check - Hold Point
holdpoint | HOLD POINT
checkpoint | Joining existing Kerb
label | Acceptance Criteria and Frequency - The concrete kerb or kerb and channel joins neatly with the existing kerb or kerb and channel over a minimal transitional length of 2 metres
label | Reference - LCC SS No.8 Part 2.5
label | Item Check - Check and Verify
checkpoint | Expansion Joints
label | Acceptance Criteria and Frequency - In the case of kerb, a joint is cut and cork jointing is inserted every 20 metres with a cut joint midway between cork joints and jointing is placed in such a manner as to dissect the kerb for its full thickness.
label | Reference - LCC SS No.8 Part 2.4
label | Item Check - Check and Verify
checkpoint | Contraction Joints
label | Acceptance Criteria and Frequency - A contraction joint is provided at 4 metre centres which is finished square and at right angles to the section of kerb or kerb and channel. The kerb or kerb and channel at a contraction joint is guillotined to the full depth of the concrete and re-finished with a jointing tool to form neat joint lines not exceeding 3mm in width and 6mm in depth
label | Reference - LCC SS No.8 Part 2.4
label | Item Check - Check and Verify
checkpoint | Tolerances
label | Acceptance Criteria and Frequency - The horizontal and vertical alignments of kerb, channel and/or kerb and channel shall not vary from those specified by more than ± 10 mm provided that the difference between the deviations from the correct levels at any two points 30 metres apart does not exceed 30mm.
label | ○ Crossfall is maintained within +/- 0.50 percent of the design
label | Reference - LCC SS No.8 Part 2.4
label | Item Check - Check and Verify
checkpoint | Water Test
label | Acceptance Criteria and Frequency - Notwithstanding the allowable tolerances, the invert of the channel is finished true to grade and alignment and channelling in which water is found to pond is not accepted and is removed immediately
label | Reference - LCC SS No.8 Part 2.4.10
label | Item Check - WITNESS POINT
checkpoint | Final Sign off and Approval - Conformance with the Specification
textbox | Name of Cient's Representative
date | Date
textbox | Name of Contractor's Representative
date | Date
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off