## General
SECTION 1 – GENERAL DETAILS
Project Name: | SP1 NZTA Ohakea Weigh Right | [5 empty] | Inspection Key |  | Responsibilities
Project Number: | 558020 | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Waka Kotahi | [5 empty] | B | Report by Breach | CM | Construction Manager | Christopher Colman | CC
Contract Number: | 7456 | [5 empty] | C | Check | CR | Cust. Representative (WSP Engineers) | Mark Frampton & Alex Brown | MF / AB
Area/ Sub-System: | CVSC - Pavement |  |  | Lot ID Number: |  |  | D | Dimension Inspection | IP | Inspection Personnel | N/A
[7 empty] | E | Examine | MC | Material Controller | N/A
ITP Number: | 558020-DOW-ITP-PC-0027 |  |  | Version: | 3 |  | H | Hold Point | OP | Operations Manager | N/A
ITP Description: | This ITP comprehensively encompasses the critical aspects related to incoming materials and processes associated with pavement. | [5 empty] | I | Inspection | PM | Project Manager | Krishna Marangat | KM
Discipline: | Pavement | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor | Gavin Hosnell | GH
Specification: | TNZ B/2, TNZ M/1, TNZ M/3, TNZ M/4, TNZ M/6, NZTA Q/5, NZS 3112, NZS 4402:1986, NZS 4407:2015 | [5 empty] | O | Operation | QM | QA Manager | Steve Darby | SD
[7 empty] | R | Review | SE | Site Engineer | Ribin Jose | RJ
Drawings: | Waka Kotahi NZ Transport Agency SH3 & Pukenui Rd Intersection, Ohakea Weigh Right Programme. Civil - For Construction | [5 empty] | S | Subcontractor | SP | Supervisor | Gavin Hosnell (Civil) & Gareth Mclellan (Drainage) | GH / GM
[7 empty] | V | Visual Verification | ST | Superintendent | N/A
Prepared By: | Ribin Jose |  |  | Date: | 2023-11-16 |  | W | Witness Point | SV | Surveyor | Stefan Killian | SK
Quality Specified: | [8 empty] | WS | Welding Supervisor | N/A
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: | Ribin Jose |  |  | Signature: |  |  |  |  | Date: | 2024-04-15
Downer Approval |  | Name: | Krishna Marangat |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:

## Receiving Inspection
SECTION 3 – RECEIVING INSPECTIONS
Item No. | Activity/ Task Description | Standards/Specification | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Signature | Date
[7 empty] | Key | By (Role Key)
3.1 | General Preliminary
3.1.1 | Survey Setout | Downer Standard | Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed. | Survey Records | Prior to Works | Document review | H | SV
3.1.2 | Service Location | Downer Standard | Complete the on site check to identify, locate and protect all services. | Service location documents | Prior to Works | Document review | R | SE
3.1.3 | Internal Permits | Downer Standard | Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. | Internal Permits | Prior to Excavation | Document review | R | SE
3.1.4 | External Permits | Downer Standard | Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc. | External Permits | Prior to Excavation | Document review | R | SE
3.1.5 | ESCP | As per contracts | Prior to starting works, Ensure that ESCP plan an approved ESCP by counsil is in place and valid | Approved ESCP plan | Prior to Works | Document review | R | SE
3.1.6 | Approved Construction Drawings | Downer Standard | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | IFC Drawings | Prior to works start | Document review | R | SE
3.2 | Pavement Materials
3.2.1 | AP65 - Source Property Tests and Sampling | TNZ M/3 Notes : 1986 TNZ M/4: 2006 NZS 4407 : 1991 NZS 4402 : 1986 | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio. | IANZ Lab Reports | 1 per source | Document review | H | CR
3.2.2 | AP65 - Production Property Tests and Sampling | TNZ M/3 Notes : 1986 TNZ M/4: 2006 NZS 4407 : 1991 | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fines, Permeability, and Particle Size Distribution. | IANZ Lab Reports | 3 per source initially, then 1/1000m³ (stockpile sample) | Document review | H | CR
3.2.3 | AP65 - Testing for Layer Compaction - MDD | TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3 | The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). | IANZ Lab Reports | 1 per material source (stockpile sample) | Document review | H | CR
3.2.4 | AP40 - Source Property Tests and Sampling | TNZ M/4: 2006 - 3 NZS 4407 : 1991 NZS 4402 : 1986 | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio. | IANZ Lab Reports | 1 per source initially, then 1/1000m³ (stockpile sample) | Document review | H | CR
3.2.5 | AP40 - Production Property Tests and Sampling | TNZ M/4: 2006 - 4 NZS 4407 : 1991 | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine as per M/4 Figure 1, Broken Face Content, and WET Particle Size Distribution Limits and Shape Control. | IANZ Lab Reports | 3 per source initially, then 1/1000m³ (stockpile sample) | Document review | H | CR
3.2.6 | AP40 - Testing for Layer Compaction - MDD | TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3 | The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). | IANZ Lab Reports | 5,000m2 | Document review | H | CR
3.2.7 | Sealing Chip - Source Property Tests and Sampling | TNZ M/6: 2019 - 4 | The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Resistance, Weak Particles Test, Skid Resistance, and PSV | IANZ Lab Reports | Before Supply and Every 10,000m3 Thereafter | Document review | H | CR
3.2.8 | Sealing Chip - Production Property Test Sampling | TNZ M/6: 2019 - 5 | The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Cleanness, Size and Shape, and PSD for G5 / G6 | IANZ Lab Reports | Every 500m3 | Document review | H | CR
3.2.9 | Bitumen - Quality Testing | NZTA M01: 2022 - 6 | The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01. | IANZ Lab Reports | One test per grade supplied | Document review | H | CR
3.2.10 | Bitumen - Supply Testing | NZTA Q05: 2022 - 6.2 | The binder shall have benchmark parameter testing completed complying with the requirements of NZTA Q05. | IANZ Lab Reports | Every 200 tonnes supplied. | Document review | H | CR
3.3 | Cement Treated Basecourse
3.3.1 | Cement | NZS3112 | General purpose Portland cement, type GP, shall be used unless otherwise specified in the Contract documents. | Datasheet | Prior to use | Document review | H | CR
3.4 | Asphalt
3.4.1 | AC14 | Pre-construction | As per NZTA M/10 specification | Mix Design, Production Test report or Volumetric properties | Per Mix | Document review | H | CR
3.5 | Geotextile and Geogrid
3.5.1 | Geotextile | Class C as per design spec | The Contractor shall submit to the Engineer for approval the details of the filter fabric they propose to use at least two weeks prior to commencement of works, including compliance certificates. | Datasheet | Prior to use | Document review | R | SE
3.5.2 | Geogrid | TENSAR TRIAX TX160 as per desig spec | The geogrid shall be manufactured in accordance with a management system that complies with BS EN ISO 9001 and BS 14001. | Datasheet | Prior to use | Document review | R | SE

## In Process Inspections
SECTION 4 – IN-PROCESS INSPECTIONS
Item No. | Activity/ Task Description | Spectification | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Signature | Date
[7 empty] | Key | By (Role Key)
4.1 | Unbound Pavement Construction
4.1.1 | Top Subgrade CBR | Project Specification CVSC Pvmt Type C Detail on Bartley Dwg TD002 | Minimum CBR 3.5% to be achieved failed to achieve the above need to carry with the contingency details as per Project Specification CVSC Pvmt Type C Detail on Bartley Dwg TD002 | Test Report | Before starting Subbase layer, whole lot in 20x20 centers | Check | H | SE,CR
4.1.2 | Geotextile | NZTA F/7 | All geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets. | Photos | Each roll out and overlaps | Check | C | SP
4.1.3 | Geogrid | Project Specification CVSC Pvmt Type C Detail on Bartley Dwg TD002 | Prior to placement of the geogrid, verification of the grade, length, orientation and layout is required against the drawings. A minimum overlap of 500mm is required between sheets. | Photos | Each roll out and overlaps | Check | C | SP
4.1.4 | Material Placement | Downer Standard | The uniformity, contamination and segregation shall be Continuous monitored thoughout | Photos | Continuous monitoring. | Check | C | PS
4.1.5 | Plateau Density Tests (Sub-basecourse) | TNZ B/02: 2005 - 7.5 | The plateau density tests shall be undertaken on 100m test strips using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC. | Plateau test results confirmance | Continuous monitoring. | Check | C | SE
4.1.6 | Sub-basecourse Pavement Layer Compaction (NDM) | TNZ B/02: 2005 - 7.6 | Mean Value ≥ 95 % of MDD Minimum Value ≥ 92 of MDD | NDM Report | 1/10m each layer not exceeding 200mm If no clear lanes then 1 test per 50m2 | Check | H | SE
4.1.7 | Sub-basecourse Layer thickness | TNZ B/02: 2005 - 5.1 | The Sub-basecourse shall be monitured for Layer thickness. –25 mm +5 mm | Survey / Level Checks | 1/20m Full width | Dimensional Inspection | D | SV or SE
4.1.8 | Benkelman Beaming on Subbase | Contract Specification, Section 3.5.5 & Appendix F | • 90th percentile deflection ≤ 1.3mm. • No single deflection > 1.4mm. | Test report, delivered weekly | 1 per 10m each traffic lane (alternating wheel paths) or 1 test /50m2 if no clear lane | Dimensional Inspection | C | SE
4.1.9 | Plateau Density Tests (Pre stabilise Basecourse) | TNZ B/02: 2005 - 7.5 | The plateau density tests shall be undertaken on 100m test strips using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC. | Plateau test results confirmance | Continuous monitoring. | Check | C | SE
4.1.10 | Basecourse Pavement Layer Compaction (Pre stabilise Basecourse) | TNZ B/02: 2005 - 7.6 | Mean Value ≥ 98 % of MDD Minimum Value ≥ 95 of MDD | NDM Report | 1/10m each layer not exceeding 200mm If no clear lanes then 1 test per 50m2 | Check | H | SE
4.1.11 | Basecourse Layer thickness. (Pre stabilise Basecourse) | TNZ B/02: 2005 - 5.1 | The Sub-basecourse shall be monitured for Layer thickness. –5 mm +15 mm | Survey / Level Checks | 1/20m Full width | Dimensional Inspection | D | SV or SE
4.2 | CTB (Cement Treated Basecourse)
4.2.1 | Pre-Stab check | Downer Standard | Check the temperature(between 5 °C or and 30 ºC), Wind (not exceeds 25km/hr), Rain, Time limitations(Primary compaction within 2 hr and the final trimming compaction within 4 hrs) | Checklsit | Befoore the stabilisation | Check | C | SE
4.2.2 | Mat testing | NZTA B/5: 2008 - 7.3 | Every 400 m2 complete a Mat test using a 1m2 cancas. The ammount of Stabilising Agent on the canvas shall be within ±0.5 kg/m2 of the specified rate. | Test Results/Photos | Every 400 m2 | Dimensional Inspection | D | SE
4.2.3 | Average usage test | NZTA B/5: 2008 - 7.3 | Upon emptying the spreader and bulk tanker, Compare tonnes of Stabilising Agent used (from delivery docket) with measured area. Usagese shall be within ±2.5 % of the specified rate | Calculation with Dockets and Weights | Upon emptying the spreader and bulk tanker | Dimensional Inspection | D | SE
4.2.4 | Water content during compaction | NZTA B/5: 2008 - 7.5 | The water content during compaction shall be in the range of 90% to 100% of the material’s optimum water content. The water content tests taken prior to stabilising and the water consumed per cut shall be recorded in the production plan records. | NDM Results, delivered weekly | 5 tests per 1000m2 | Check | C | SE
4.2.5 | Control of cut depth | NZTA B/5: 2008 - 7.6.1 | The actual depth of the cut shall be physically measured at both ends of the stabilising drum at least once every 200 m along the cut length. Maximum variation from the specified depth of cut is –0 mm and +20 mm. Unless specifically allowed in the project specification, the depth of cut shall not intrude into a subgrade layer. | Site Records/Photos | Each Cut | Check | C | SE
4.2.6 | Overlap on longitudinal joints | NZTA B/5: 2008 - 7.6.2 | To ensure complete stabilisation across the full width of the road, longitudinal joints between successive cuts shall overlap by minimum of 200 mm or half the layer thickness, whichever is the greater. | Site Records/Photos | Each Cut | Check | C | SE
4.2.7 | Continuity of stabilised layer | NZTA B/5: 2008 - 7.6.3 | The exact location of the end of the cut shall be carefully marked. This mark shall coincide with the position of the centre of the mixing drum at the point at which the supply of the stabilising agent ceased. To ensure continuity of the stabilised layer, the next successive cut shall be started 1 m behind this mark. | Site Records/Photos | Each Cut | Check | C | SE
4.2.8 | Plateau Density tests | NZTA B/5: 2008 - 7.7 | At the outset of compaction the contractor shall undertake plateau density tests for the purpose of determining the practicality of both the OWC and the MDD mix design targets, the minimum, and possibly the maximum, number and type of roller passes required to achieve the MDD for the proposed compaction plant and stiffness of lower pavement ‘anvil’ beneath the layer to be compacted. | Plateau Density test | Continuous monitoring. | Inspection | I | SE
4.2.9 | Compaction testing | NZTA B/5: 2008 - 7.7.1 | The Degree of Compaction for Cement Treated Subbase shall have a Mean Dry Density of ≥ 98 % and a Minimum Dry Density of ≥ 95%. Compaction testing during construction of the stabilised pavement layers shall be carried out in lots.The area of a lot shall not exceed 1000 m2 | NDM Results | 5 tests per Lot | Check | C | SE
4.2.10 | ITS Testing | NZTA T/19, Contract Specification, Section 3.6.5, Appendix F | ITS testing shall be carried out in accordance with NZTA T/19. The maximum time between mixing and compaction shall be 2 hours. The ITS test ranges shall be as follows: - Dry: 150kPa - 350 kPa - Soaked: 100kPa - 300kPa The Tensile Strength Retained (TSR) shall be no less than 75% If results are below the target strengths then notify the Engineer immediately. | Test Results, delivered weekly | 2 ITS (dry) and 2 ITS (soaked) for behind the hoe sampled each day of stabilisation. Samples are to be taken from seperate locations. | Check | C | SE
4.2.11 | Benkelman Beaming on Basecourse (cement modified) | Contract Specification, Section 3.5.5 & Appendix F | • 90th percentile deflection ≤ 1.0mm. • No single deflection > 1.1mm. | Test report, delivered weekly | 1 per 10m each traffic lane (alternating wheel paths) or 1 test /50m2 if no clear lane | Dimensional Inspection | C | SE
4.2.12 | Construction Tolerances | TNZ B/5: 2008 - 7.8 | Basecourse where asphalt surfacing with concrete channel (i) at or close to the lip of channel –5 +5 mm (ii) at other locations on pavement –15 +5 mm (iii) at other locations on pavement –5 +15 mm | Survey Records | On final layer | Dimensional Inspection | C | SV
4.2.13 | Surface Finish post sweeping | TNZ B/02: 2005 - 7.8 | The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept. | Photos | Prior to sealing | Visual Inspection | V | SE
4.3 | Grade 3/5 Chip Sealing
4.3.1 | Presealing Requirements | TNZ B/02: 2005 - 12, Contract Specification, Section 3.6.7 | The seal coat shall not be applied unless the water content at each test point of the basecourse layer is such that the degree of saturation (DOS) is less than 70%. | NDM Report | 1/10m | Check | C | SE
4.3.2 | Benkelman Beaming on Basecouse (on AP40 CTB) | Contract Specification, Section 3.5.5 & Appendix F | • 90th percentile deflection ≤ 1.0mm. • No single deflection > 1.1mm. | Test report, delivered weekly | 1 per 10m each traffic lane (alternating wheel paths) or 1 test /50m2 if no clear lane | Inspection | I | SE
4.3.3 | Preseal inspection/ Subbase/Basecourse check | TNZ P3 TNZ B02 | The road shall be reasonably dry before the binder is applied, and no spraying with asphaltic binder shall be carried out when the air temperature measured within the confines of the sealing course is below 10oC in the shade. Visual inspection by engineer's representative | Hold point Release, ITP Sign off | Prior to sealing | Check | I | SE
4.3.4 | Spray Temperature | TNZ P3 | The emulsified asphalt may be sprayed at the temperature at which it is received from the manufacturing plant except that no emulsified asphalt shall be sprayed at a temperature in excess of 90oC or below 20oC. | Sealing statement | Prior to sealing | Check | I | SE
4.3.5 | Chip Application | TNZ P3 | All binder sprayed shall be covered with chips across the full sprayed width, apart from necessary longitudinal laps, within five minutes of spraying. | Sealing statement | For every spray run | Check | I | SE
4.3.6 | Post Seal Inspections | TNZ P3 | The Engineer will inspect the sealcoat immediately prior to the removal of the temporary speed restriction and after final surplus chip removal is completed. | Engineers Acceptance | After Final Sweeping | Visual Inspection | H | SE,CR
4.3.7 | Chipseal Repairs | TNZ P3 | The Contractor shall make no repairs without the prior approval of the Engineer for the methods to be used. | Approved Repair Methodology | Prior to Repairs | Review | A | SE
4.4 | Asphaltic Concrete (AC14)
4.4.1 | Preparation of Area to be Paved | NZTA M27:2020 - 9 | The surface on which the paving is to be laid shall be free from standing water, and any loose material, dust, clay or foreign matter shall be removed by sweeping. All fatty and unsuitable patches shall be removed. Depressions and other irregularities shall be patched or corrected. | Site Notes/Photos | Pre Seal | Visual Inspection | V | PS
4.4.2 | Ambient Conditions for Placing | NZTA M27:2020 - 9 | Wearing course asphalt shall not be placed when the pavement surface temperature is less than 10°C, | Site Notes/ Weather report | Pre Seal | Check | R | PS
4.4.3 | Seal surface check prior to asphalt | as per project specification 3.7.7 | Visual inspection by engineer's representative | ITP Sign off | All | Visual | H | CR
4.4.4 | Tack coat emulsion | Minimum Residual Bitumen of 0.3 L/m2 As per project based pavement specification | Tack coat shall be applied to the cleaned surface prior to placing asphalt. Tack coats shall be applied using a distributor. The use of a hand lance shall be minimised to ensure an even application of the tack coat. | Run sheet, QA from Sub | Entire length of pavement | Visual Inspection | V | SE
4.4.5 | Asphaltic Concrete - Surfacing | NZTA M10 & M27, Contract Specification 3.7.15, Appendix F, Section 10.15 | 55mm of AC14 Asphalt layers less than or equal to 55mm shall be +/- 5mm from the specified design thickness. The combined thickness of all asphalt layers should not be less than the specified total asphalt depth. | Run sheet, QA from Sub | Entire length of pavement | Dimensional Inspection | D | SE
4.4.6 | Thickness | Contract Specification, Section 3.7.15 | Thickness as per design lift with +/-10mm (AC14) | ITP Sign off | Continuos | Visual | C | SE
4.4.7 | Finished surface at joints | Contract Specification, Section 3.7.16 | No more than 5 mm variation under a 3 m stright edge | ITP Sign off | Continuos | Visual | C | SE
4.4.8 | Air Voids | NZTA M/10 | The maximum and minimum air voids for each core shall be +3%/-2% from the mix design air voids. | Test results, delivered weekly | Continuos | Review | C | SE
4.4.9 | Level checks | Survey | Thickness as per design lift with +/-10mm (AC14) | As-built drawing | 1/20m full width | As-built | D | SV
4.4.10 | Line marking | Set out | As per NZTA standard/ design drawings | ITP sign off/ Photos | All | Visual Inspection | V | SE

## Final Inspection and Handover
SECTION 5 – FINAL INSPECTION AND HANDOVER
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type | Inspection |  | Inspection Point/Signature & Date
[7 empty] | Key | By | Downer Signature | Date | Customer Requirements Verification Records/Location
5.1 | Construction Record Compilation | Upon completion of works | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Closed-out NCR/Defects | Post construction | Review | R | SE
5.2 | As-built Survey | Upon completion of works | Ensure all items have been surveyed and records are assembled for asbuilting | As built survey record completed | Post construction | Review | R | SV
5.3 | Red-line As-built Drawings | Upon completion of works | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar | Signed As-built Drawings | Post construction | Review | R | SE,SV
5.4 | Defect, Snag and Punch List | Upon completion of works | Update the project Defect, Snag and Punch List Register | Register | Post construction | Review | R | PE
5.5 | All QA documentation collated & signed-off | Upon completion of works | All signed and closed out | Signed off Documents | Post construction | Review | R | QM