## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | 558020-DOW-ITP-PC-0027_v3 (Pavement - CVSC) | itp | 558020-DOW-ITP-PC-0027_v3 (Pavement - CVSC) |  | 5b39dd18-42f0-4f6d-858b-a020a6cd46ec
| section | 3.1 General Preliminary
| checkpoint | 3.1.1 - Survey Setout
847d6c63-150e-5d03-b4c8-572eaa9c1c00 | note | Standard/Specification - Downer Standard
51547b4b-05d0-54f5-ad71-41c99c6c58d5 | note | Acceptance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
e10acbde-1af1-5d68-86f6-112f57296566 | note | Verifying Document - Survey Records
11ef350a-33e2-547a-a3b0-5c9adaf9493a | note | Frequency - Prior to Works
52dc4ddc-85de-549f-bf65-5490bd367253 | note | Inspection Type (Visual, other) - Document review
a2d1eebd-07f2-57e4-83cf-ff31eefbbfa5 | note | Inspection: Key - H
c9c97a5e-55e7-56da-a495-f79babdd4d85 | note | Inspection: By - SV
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1.2 - Service Location
0bc4e475-dc98-54b0-bcdb-80c7dc33ae29 | note | Standard/Specification - Downer Standard
b1c0ce26-ac85-5574-afc9-ff9c58e3f4ef | note | Acceptance Criteria - Complete the on site check to identify, locate and protect all services.
4532d5be-13bb-5093-bb9b-b6e5c046fbe9 | note | Verifying Document - Service location documents
c0de4a0a-e9a7-58a5-8db6-b4faba192ec6 | note | Frequency - Prior to Works
8e5a4fd3-4054-5dfb-8bd2-fab2b30f8af8 | note | Inspection Type (Visual, other) - Document review
7bad0b22-4f5d-5deb-bed4-34724344a3ca | note | Inspection: Key - R
fcfa1ffa-43da-5836-b5de-784c30a37fd6 | note | Inspection: By - SE
| checkpoint | 3.1.3 - Internal Permits
14e8d99c-d3f9-5ce9-af98-2ac2f3ae69c8 | note | Standard/Specification - Downer Standard
11d6d146-3fa6-5f41-8263-1e6d98bd25fe | note | Acceptance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
c823e88b-5484-5d5f-b5a7-a0c1acc19b3d | note | Verifying Document - Internal Permits
02bff64a-a626-531a-9080-2e9f2a2be348 | note | Frequency - Prior to Excavation
244db40d-5f54-542f-ba5e-7021bf34ce72 | note | Inspection Type (Visual, other) - Document review
db6d655c-aa25-5d2d-8dc4-8de9f923b4f4 | note | Inspection: Key - R
f6cc6885-0103-5eae-a2d5-5473f2be496c | note | Inspection: By - SE
| checkpoint | 3.1.4 - External Permits
42456ecb-0e2a-5f22-ad51-aac552887127 | note | Standard/Specification - Downer Standard
6b216733-50ad-5ca3-ac72-c23dca4d2717 | note | Acceptance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
14651cb1-fb48-5fee-98db-5925619faab9 | note | Verifying Document - External Permits
31dfc0f2-62f9-5f4f-876a-4eb683e30b2c | note | Frequency - Prior to Excavation
40cb714b-177b-5f44-9755-fc3fa8ec9802 | note | Inspection Type (Visual, other) - Document review
d7fc50c4-5ee3-5461-9d43-f05413f460e1 | note | Inspection: Key - R
41102a4f-b4aa-5351-b54b-2b10493cf8a5 | note | Inspection: By - SE
| checkpoint | 3.1.5 - ESCP
35bdff83-20c5-5855-a49b-8f06c1603704 | note | Standard/Specification - As per contracts
61e227a6-565a-57a1-9bcf-44b135572481 | note | Acceptance Criteria - Prior to starting works, Ensure that ESCP plan an approved ESCP by counsil is in place and valid
109b32af-0ff8-5ec5-9e2d-339a575e2ef9 | note | Verifying Document - Approved ESCP plan
b6392720-3a3c-58d6-a07f-f6d91116ced7 | note | Frequency - Prior to Works
dc86d3c9-08bc-5f20-8ca3-49d72dabd834 | note | Inspection Type (Visual, other) - Document review
b30b58a7-b818-514e-955d-bdd26ef4bc8e | note | Inspection: Key - R
aee0ae00-3b42-5b1b-89c5-f5f528f244ed | note | Inspection: By - SE
| checkpoint | 3.1.6 - Approved Construction Drawings
269e2b77-aae3-5868-ad5b-8ca0e59fd187 | note | Standard/Specification - Downer Standard
c4a09cf8-c6d2-5abb-b70f-16ea2274c86f | note | Acceptance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
13987449-65cc-54a2-b233-8da961001b84 | note | Verifying Document - IFC Drawings
184d7c95-d855-580b-a1fe-6371a3466339 | note | Frequency - Prior to works start
d1058bc4-6a28-5cae-99e3-e4d1db34756c | note | Inspection Type (Visual, other) - Document review
1b3d5950-19ba-5d4d-b4b9-83742f191482 | note | Inspection: Key - R
6aee0706-6471-52c3-9461-c5841f1f745e | note | Inspection: By - SE
| section | 3.2 Pavement Materials
| checkpoint | 3.2.1 - AP65 - Source Property Tests and Sampling
025eb54b-75e5-5455-b5ae-4c8be92ad733 | note | Standard/Specification - TNZ M/3 Notes : 1986 TNZ M/4: 2006, NZS 4407 : 1991, NZS 4402 : 1986
76d9e947-ed83-58ac-8e50-02215aeb145e | note | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio.
8c69b5c0-1d01-5ec9-b682-fbd7f6f4b9b7 | note | Verifying Document - IANZ Lab Reports
3e91cc9d-3251-5cab-98fe-59b92b08823a | note | Frequency - 1 per source
f347a7df-9d4a-5bc0-b465-65336b90fd67 | note | Inspection Type (Visual, other) - Document review
13bcfb4e-eadc-5914-b34c-050df92f25ea | note | Inspection: Key - H
fb9f5ae7-e234-5d99-9838-2541c9681cad | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.2 - AP65 - Production Property Tests and Sampling
93eccdd3-5ad9-57aa-ad62-765be2a11acb | note | Standard/Specification - TNZ M/3 Notes : 1986 TNZ M/4: 2006, NZS 4407 : 1991
839306f5-3f07-5f38-8e79-c70dd58a10e0 | note | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fines, Permeability, and Particle Size Distribution.
07725c69-f608-5a09-abfc-0a481b1673b4 | note | Verifying Document - IANZ Lab Reports
9928738c-73bc-54c4-8576-0e5834aab9fc | note | Frequency - 3 per source initially, then 1/1000m³ (stockpile sample)
dd4ab942-e24c-5ea1-a39c-64a872008b97 | note | Inspection Type (Visual, other) - Document review
ddcd7515-6974-54b9-b5fe-2f0fc3e0828e | note | Inspection: Key - H
fa440b39-c232-5d4b-ab28-c87bf8e0c23a | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.3 - AP65 - Testing for Layer Compaction - MDD
2e8614f5-d225-516d-8fe5-a4b2b291f80d | note | Standard/Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
12b331b1-9ffc-5c88-842c-ef235f5e9cb4 | note | Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
24bbfb73-dfee-5e7d-8f10-5575c44ef0e0 | note | Verifying Document - IANZ Lab Reports
16fc6ebc-6078-5449-b275-282807911f20 | note | Frequency - 1 per material source (stockpile sample)
c0161c16-61b5-50f9-9ff8-dcfd016b6c28 | note | Inspection Type (Visual, other) - Document review
64af2501-0b87-5d34-bcae-4ce1b1ba534f | note | Inspection: Key - H
edf496ed-068e-557c-8df5-be1c6cc0a901 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.4 - AP40 - Source Property Tests and Sampling
462ebc7f-2a48-523a-900a-4eb982f94e14 | note | Standard/Specification - TNZ M/4: 2006 - 3 NZS 4407 : 1991 NZS 4402 : 1986
3b23ea13-8e6a-5c59-b03e-54919b727d9e | note | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio.
76ecc44b-fa67-5391-bcb6-baa5cb70c0b1 | note | Verifying Document - IANZ Lab Reports
2ed6e7d5-c46c-542d-b0d7-74decd39e7bf | note | Frequency - 1 per source initially, then 1/1000m³ (stockpile sample)
cfcc56ee-3a01-56e7-919c-775fe3cf0dbc | note | Inspection Type (Visual, other) - Document review
5b5bea69-1b25-555a-9429-e3f465544653 | note | Inspection: Key - H
cd36a09d-8175-5998-8abc-a099c260a8d3 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.5 - AP40 - Production Property Tests and Sampling
25270210-6672-5907-bf26-856532744f6f | note | Standard/Specification - TNZ M/4: 2006 - 4 NZS 4407 : 1991
2485bf5e-7d53-58e0-bbbc-02d94c63ec74 | note | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine as per M/4 Figure 1, Broken Face Content, and WET Particle Size Distribution Limits and Shape Control.
c1f653f4-a400-5ab6-b396-d659d0e86023 | note | Verifying Document - IANZ Lab Reports
68ee175b-ff47-52cf-bc06-57660bd6e464 | note | Frequency - 3 per source initially, then 1/1000m³ (stockpile sample)
d66334d2-ced0-5f79-ba1d-996010f04c33 | note | Inspection Type (Visual, other) - Document review
13f942d4-94f9-5c3d-9162-a6de0df0a791 | note | Inspection: Key - H
4194cd99-5062-5326-904b-dca499d04ba4 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.6 - AP40 - Testing for Layer Compaction - MDD
20277a0e-40ab-56e5-b2cc-2fc3b3aa6ed6 | note | Standard/Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
68aeed14-d535-5606-91df-d76b16409ea2 | note | Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
e5e5717d-e637-5254-9f8e-353b8bcad44c | note | Verifying Document - IANZ Lab Reports
81b5017e-4ef5-5867-8dac-1cf7a9dbceaa | note | Frequency - 5,000m2
c497769f-8831-5084-8927-732ee5c2864e | note | Inspection Type (Visual, other) - Document review
74fbd330-10aa-57ee-9db9-49d92c65f56b | note | Inspection: Key - H
6e90f090-fc99-5d32-af04-081efc8be709 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.7 - Sealing Chip - Source Property Tests and Sampling
cd9b86e7-dec0-5c02-a35e-393d80f8b4fd | note | Standard/Specification - TNZ M/6: 2019 - 4
f1334ba4-95d9-59cf-bdb4-ae9f78e0dff7 | note | Acceptance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Resistance, Weak Particles Test, Skid Resistance, and PSV
df6adaab-1aeb-55ae-bcb2-a8bae58440d5 | note | Verifying Document - IANZ Lab Reports
0a9630a5-950f-51e4-98ee-e9ba20ab8c5b | note | Frequency - Before Supply and Every 10,000m3 Thereafter
2c08ccf9-01b8-532e-8874-9b5006366c50 | note | Inspection Type (Visual, other) - Document review
d0e4ef01-e508-5d49-b0b5-2e3388fdf949 | note | Inspection: Key - H
4fd2731c-3475-58c7-a90f-1f4770ebc0eb | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.8 - Sealing Chip - Production Property Test Sampling
ab6cb2a3-5e88-5bce-ac12-db6edcbce305 | note | Standard/Specification - TNZ M/6: 2019 - 5
06ba3dd1-a062-5a53-bee9-d0dedacd9452 | note | Acceptance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Cleanness, Size and Shape, and PSD for G5 / G6
80940501-b482-5f7e-a04a-2c5aaebd11c1 | note | Verifying Document - IANZ Lab Reports
9600bd9c-d66f-5afa-9dbe-f6f8d5f8cc0a | note | Frequency - Every 500m3
994ceecc-6a9b-530a-9808-5f897d9acc62 | note | Inspection Type (Visual, other) - Document review
a7c3e921-da14-5d9a-b278-84d75a3ed410 | note | Inspection: Key - H
692dfdbc-cf37-5335-aed3-77e35c7c2d2d | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.9 - Bitumen - Quality Testing
5336e6cf-cb52-54a8-a887-cfa3b9d6fad4 | note | Standard/Specification - NZTA M01: 2022 - 6
de21d394-2f36-5454-93fd-f3c7f6876ce5 | note | Acceptance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01.
1f83164f-d4c2-566b-ae2a-31a824a921db | note | Verifying Document - IANZ Lab Reports
0426be1e-bef8-557f-896e-a224aa5859d1 | note | Frequency - One test per grade supplied
1b040053-af9b-5fb8-ab87-4f6f89897872 | note | Inspection Type (Visual, other) - Document review
7496179d-3c18-52ab-9a56-dc911bda82e9 | note | Inspection: Key - H
6aa2cb72-192c-5bf4-8efd-28d7bc189775 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.10 - Bitumen - Supply Testing
983377e9-b640-5f14-8123-8b717540c625 | note | Standard/Specification - NZTA Q05: 2022 - 6.2
921baa72-6979-53df-9cca-d4d7225acaaf | note | Acceptance Criteria - The binder shall have benchmark parameter testing completed complying with the requirements of NZTA Q05.
3008cbbe-83b8-51c0-8829-2820d70f5b8a | note | Verifying Document - IANZ Lab Reports
d27ba970-52ce-5658-8171-aa2e436e158a | note | Frequency - Every 200 tonnes supplied.
cec30357-b157-57d4-9ed6-85fa4b04b211 | note | Inspection Type (Visual, other) - Document review
16ac327b-3792-5cd8-bf17-9a4a341bc182 | note | Inspection: Key - H
52404e03-3df9-5885-881a-93b58a7fe70a | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| section | 3.3 Cement Treated Basecourse
| checkpoint | 3.3.1 - Cement
5d02a1df-ba37-5196-962a-6765e40d7244 | note | Standard/Specification - NZS3112
60c5f12e-e96c-5515-846f-d4a1dc34e291 | note | Acceptance Criteria - General purpose Portland cement, type GP, shall be used unless otherwise specified in the Contract documents.
3f4de7f1-65c5-52a9-b46c-e439e219847c | note | Verifying Document - Datasheet
2342d9cb-619e-5fa6-8e0e-256e231bb9ac | note | Frequency - Prior to use
1c1991c1-7ef2-5313-889e-e31206622f1f | note | Inspection Type (Visual, other) - Document review
0a4bf14e-922e-5a08-b363-20594f23c4d0 | note | Inspection: Key - H
fdcf682b-e586-5b92-b5a1-7b8255f00cee | note | Inspection: By (Role Key) - CR
| signoff | AUTHORITY HOLDPOINT
| section | 3.4 Asphalt
| checkpoint | 3.4.1 - AC14
085959e3-473f-5492-898d-c979db790582 | note | Standard/Specification - Pre-construction
1e3fb505-ce28-58b8-ac26-adffdb56f529 | note | Acceptance Criteria - As per NZTA M/10 specification
69785efa-5fb3-5b73-abba-67e76cd183a2 | note | Verifying Document - Mix Design, Production Test report or Volumetric properties
d75b140a-7f69-51e5-9719-c41db3c29d86 | note | Frequency - Per Mix
fb8a6e52-11e0-51f6-b035-e4283ef19cec | note | Inspection Type (Visual, other) - Document review
b371a82b-3d93-5e23-94cf-e3a5f975cd9a | note | Inspection: Key - H
322fbc31-1b06-5ddb-8c67-dfc03eecbd70 | note | Inspection: By (Role Key) - CR
| signoff | AUTHORITY HOLDPOINT
| section | 3.5 Geotextile and Geogrid
| checkpoint | 3.5.1 - Geotextile
f4b80b72-7f7e-593a-8cc0-e70257667aee | note | Standard/Specification - Class C as per design spec
3591d190-8c68-5f58-9d4f-15d8b42f6fa1 | note | Acceptance Criteria - The Contractor shall submit to the Engineer for approval the details of the filter fabric they propose to use at least two weeks prior to commencement of works, including compliance certificates.
54366453-7a09-5ad3-b37d-30b45197b11c | note | Verifying Document - Datasheet
d1c69967-27ff-5995-b9e5-d06a92883690 | note | Frequency - Prior to use
74357906-3520-5e9e-bb6c-e24f10daa5ad | note | Inspection Type (Visual, other) - Document review
ce00c77c-76be-5b98-b78a-2ea5cba254fa | note | Inspection: Key - R
6586a027-ed2c-5c81-acc3-2386685d97ce | note | Inspection: By (Role Key) - SE
| checkpoint | 3.5.2 - Geogrid
9724947a-f3fc-5bb8-aff5-0f1077ffdbd3 | note | Standard/Specification - TENSAR TRIAX TX160 as per desig spec
d197e62e-5452-5a96-9a4f-ac56497689ae | note | Acceptance Criteria - The geogrid shall be manufactured in accordance with a management system that complies with BS EN ISO 9001 and BS 14001.
c76b9ade-47ac-5e04-b5f2-057bf5f56739 | note | Verifying Document - Datasheet
5b55d26b-51e9-5a6a-9557-d1f7ec92a449 | note | Frequency - Prior to use
477a408d-62f9-5267-a31f-fe8222604904 | note | Inspection Type (Visual, other) - Document review
54348746-9c79-5e47-bb6f-d8a1f99e9c7b | note | Inspection: Key - R
f7bf5415-7b52-56fa-bde5-8de064306b3e | note | Inspection: By (Role Key) - SE
| section | 4.1 Unbound Pavement Construction
| checkpoint | 4.1.1 - Top Subgrade CBR
4fe7f51e-cd23-5e93-a34c-b4f73e92fa6d | note | Standard/Specification - Project Specification CVSC Pvmt Type C Detail on Bartley Dwg TD002
fe7a0bbc-445c-51fe-a7f1-c76b0d0d169a | note | Acceptance Criteria - Minimum CBR 3.5% to be achieved failed to achieve the above need to carry with the contingency details as per Project Specification CVSC Pvmt Type C Detail on Bartley Dwg TD002
121e28f3-f471-579a-8385-c6d474982cc4 | note | Verifying Document - Test Report
65e3cbb6-3d98-579e-8de3-2a48d976cad0 | note | Frequency - Before starting Subbase layer, whole lot in 20x20 centers
393bb36d-eb04-53b9-996c-cd1b70181b03 | note | Inspection Type (Visual, other) - Check
3d03200b-82f0-524e-ad91-cb63f869994f | note | Inspection: Key - H
d7cc96e6-dd64-5b1d-9284-bbf0492e358d | note | Inspection: By - SE, CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.2 - Geotextile
d4280938-d187-554d-9391-285439766aa5 | note | Standard/Specification - NZTA F/7
e8a9f971-55f7-5857-9aec-8c5c72204ff9 | note | Acceptance Criteria - All geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets.
acde397f-2e38-5dc9-9973-add86530d092 | note | Verifying Document - Photos
c9367394-24b0-572c-a7ad-aef5c5223ef3 | note | Frequency - Each roll out and overlaps
290bf472-3f0a-5b45-bea1-761d55905c81 | note | Inspection Type (Visual, other) - Check
1214d1d7-3585-5a64-a30c-be964ebae246 | note | Inspection: Key - C
5a6510ad-abf2-5af8-a572-ff70e77fb79d | note | Inspection: By - SP
| checkpoint | 4.1.3 - Geogrid
da6273fa-3b3c-53b1-8b95-c5b4638ff1a9 | note | Standard/Specification - Project Specification CVSC Pvmt Type C Detail on Bartley Dwg TD002
d735b33e-8e3d-5305-98a3-50970b465a40 | note | Acceptance Criteria - Prior to placement of the geogrid, verification of the grade, length, orientation and layout is required against the drawings.
adc09031-f655-5199-8a31-c8a805107a71 | note | ○ A minimum overlap of 500mm is required between sheets.
53f09362-bc19-5496-a161-d395471a42fc | note | Verifying Document - Photos
a4a3b83b-78ce-5e78-9b6a-03ee40edfeb7 | note | Frequency - Each roll out and overlaps
8b93c68a-be27-5d60-b662-f4d4e948bf30 | note | Inspection Type (Visual, other) - Check
43dc1c06-fcc8-51af-8345-0b8b162e3ca3 | note | Inspection: Key - C
8a99809b-8cab-55f5-961a-f2e7218340b8 | note | Inspection: By - SP
| checkpoint | 4.1.4 - Material Placement
1a4350b4-776f-5696-b146-69c7defcde88 | note | Standard/Specification - Downer Standard
626f7f68-5e8c-57b3-924b-14ad47cf805d | note | Acceptance Criteria - The uniformity, contamination and segregation shall be Continuous monitored thoughout
139f4ff0-39bc-5893-8dd0-cf9958a63ce2 | note | Verifying Document - Photos
902d769d-9815-540f-9a68-60a99c12f9e4 | note | Frequency - Continuous monitoring.
7fd7a35b-d3f0-58bc-b430-1026234e914b | note | Inspection Type (Visual, other) - Check
77b46f8d-bf09-5f55-abe6-c96a744e771a | note | Inspection: Key - C
6a4c4865-858d-59ad-b2ef-3721997ba2f9 | note | Inspection: By - PS
| checkpoint | 4.1.5 - Plateau Density Tests (Sub-basecourse)
f022dfb3-02a9-54d0-a60a-c17266fd33ec | note | Standard/Specification - TNZ B/02: 2005 - 7.5
5b641802-8f10-5e0c-84d6-ff290c839f88 | note | Acceptance Criteria - The plateau density tests shall be undertaken on 100m test strips using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC.
4b47ce51-ff0b-547d-b1ab-9e19f94e6f64 | note | Verifying Document - Plateau test results confirmance
94c362d3-4ca8-57e5-953d-28f206f8354d | note | Frequency - Continuous monitoring.
68877cbe-0e10-5521-8896-51df2bbd7397 | note | Inspection Type (Visual, other) - Check
237483d6-6430-5a77-afc3-0e6d4f9f7378 | note | Inspection: Key - C
89b7d323-726c-5597-af45-97fcb1f6bde6 | note | Inspection: By - SE
| checkpoint | 4.1.6 - Sub-basecourse Pavement Layer Compaction (NDM)
0b317ecc-f599-557e-a9fc-d52b262b6ea9 | note | Standard/Specification - TNZ B/02: 2005 - 7.6
e45e31fd-44f2-595f-9f6c-27535b97a2cd | note | Acceptance Criteria - Mean Value ≥ 95 % of MDD Minimum Value ≥ 92 of MDD
ba2e9f35-1846-5c57-9fdc-6e65e46052f9 | note | Verifying Document - NDM Report
3bb5b311-8fa4-5cea-a040-8a68c36aad38 | note | Frequency - 1/10m each layer not exceeding 200mm. If no clear lanes then 1 test per 50m2.
9ad5e5fc-7238-5337-a7b0-2a12291674c8 | note | Inspection Type (Visual, other) - Check
31d91026-8d89-50a9-8ff8-43422c480db2 | note | Inspection: Key - H
a0976e49-e937-5262-ae01-f513f717beed | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.7 - Sub-basecourse Layer thickness
cf82c409-73b6-51cf-a395-d616f1a2e90a | note | Standard/Specification - TNZ B/02: 2005 - 5.1
2bd77f62-23af-56ed-ba63-a1b8882a791a | note | Acceptance Criteria - The Sub-basecourse shall be monitured for Layer thickness. –25 mm +5 mm
a45c92cf-9185-5fa3-a631-b4e114db4fd3 | note | Verifying Document - Survey / Level Checks
b54c2100-c4d0-55d2-a0cf-240431b6cfef | note | Frequency - 1/20m Full width
7b6fe019-8954-5450-a62b-f6f82cc8c522 | note | Inspection Type (Visual, other) - Dimensional Inspection
320dc52f-fc06-50f7-bc50-5deceb0bcfb8 | note | Inspection: Key - D
7023e306-7b67-5d21-96bc-3db133ef867f | note | Inspection: By - SV or SE
| checkpoint | 4.1.8 - Benkelman Beaming on Subbase
31676058-177e-5367-93e1-4b95f17904d4 | note | Standard/Specification - Contract Specification, Section 3.5.5 & Appendix F
0afb38bc-a49a-50d6-9b57-9509acf89c7a | note | Acceptance Criteria - 90th percentile deflection ≤ 1.3mm.
a7c4464f-3fe4-5cbc-a15f-738fd795c723 | note | ○ No single deflection > 1.4mm.
88e475d4-930a-5782-bcc9-6e8e8304d741 | note | Verifying Document - Test report, delivered weekly
5db4fc73-fb40-51eb-820e-e2b6c3bd7237 | note | Frequency - 1 per 10m each traffic lane (alternating wheel paths) or 1 test /50m2 if no clear lane
a1f6c029-e61c-5520-bd71-2bf1ec6b0bb1 | note | Inspection Type (Visual, other) - Dimensional Inspection
efdaf6a5-054e-5aae-a941-8d121578972b | note | Inspection: Key - C
ef72d68b-643f-5733-b528-444878b04a1c | note | Inspection: By - SE
| checkpoint | 4.1.9 - Plateau Density Tests (Pre stabilise Basecourse)
2f537b3e-213c-5c32-9698-dea246a9484e | note | Standard/Specification - TNZ B/02: 2005 - 7.5
3848e550-0918-5b21-97bd-b2a70354dd19 | note | Acceptance Criteria - The plateau density tests shall be undertaken on 100m test strips using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC.
6d69fb1c-2b62-5989-8d7e-2d476fbf3b55 | note | Verifying Document - Plateau test results confirmance
8f3b895a-22ef-5724-a7c3-4f25e6694d51 | note | Frequency - Continuous monitoring.
8d59f6e3-c214-5392-a6e7-a57a8894cfc4 | note | Inspection Type (Visual, other) - Check
fd14b396-5b34-52de-a639-b1b7559d47f4 | note | Inspection: Key - C
10375e7b-42c5-525d-97d9-6926ad1ce04b | note | Inspection: By - SE
| checkpoint | 4.1.10 - Basecourse Pavement Layer Compaction (Pre stabilise Basecourse)
e0f3aae0-6af8-5b11-ab3b-2832a9e6fd59 | note | Standard/Specification - TNZ B/02: 2005 - 7.6
326aecfe-2614-573d-b9b3-e3bafc59f011 | note | Acceptance Criteria - Mean Value ≥ 98 % of MDD Minimum Value ≥ 95 of MDD
f9764152-741e-5d47-a18b-bf6d91f2ad80 | note | Verifying Document - NDM Report
491de88f-e6c8-5ae9-9d9a-fa62b2d9e4b5 | note | Frequency - 1/10m each layer not exceeding 200mm. If no clear lanes then 1 test per 50m2.
a46533b7-dea0-52ce-9bc3-321100c8b83c | note | Inspection Type (Visual, other) - Check
598f44bd-3903-5017-8c40-b5f100449c22 | note | Inspection: Key - H
d5414d93-8f3e-5066-b08b-d85f9e918f41 | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.11 - Basecourse Layer thickness. (Pre stabilise Basecourse)
05000847-8f1a-54b3-b329-07f0d7e3bdcb | note | Standard/Specification - TNZ B/02: 2005 - 5.1
41e97ab2-6a1e-50b8-9fb9-204cbb73a124 | note | Acceptance Criteria - The Sub-basecourse shall be monitured for Layer thickness. –5 mm +15 mm
d1224440-2053-5ccc-aa77-8e1b0a16bc91 | note | Verifying Document - Survey / Level Checks
69481786-4491-5d91-b755-f9d7eb497a57 | note | Frequency - 1/20m Full width
57f1aa10-14ed-5721-9795-1bf4512e51b0 | note | Inspection Type (Visual, other) - Dimensional Inspection
b359a309-d84e-5d1f-8ca6-709699d86d06 | note | Inspection: Key - D
dbeced11-ee46-52de-b986-4fc17714b892 | note | Inspection: By - SV or SE
| section | 4.2 CTB (Cement Treated Basecourse)
| checkpoint | 4.2.1 - Pre-Stab check
5195348e-f429-5959-a38d-d79ac57c3a7c | note | Standard/Specification - Downer Standard
34c626f4-2d7e-5133-8142-48c484d86589 | note | Acceptance Criteria - Check the temperature (between 5 °C or and 30 ºC), Wind (not exceeds 25km/hr), Rain, Time limitations(Primary compaction within 2 hr and the final trimming compaction within 4 hrs)
c4ff8757-c2d5-5ed5-8708-2f7c07d1cbad | note | Verifying Document - Checklsit
d33b04e3-297e-596a-aee6-b22f63f6d490 | note | Frequency - Befoore the stabilisation
a54d4c6c-866c-553f-bb60-ae362e7b4c54 | note | Inspection Type (Visual, other) - Check
7de51829-eec2-5e35-af0e-d7c8cfa67517 | note | Inspection: Key - C
550cfcd2-2203-5be6-afbd-3e517fbd3eb5 | note | Inspection: By - SE
| checkpoint | 4.2.2 - Mat testing
b1ac9697-e45b-5b33-973e-4b1834094c98 | note | Standard/Specification - NZTA B/5: 2008 - 7.3
708784e8-45d8-5dc0-b55c-ed8da7dd449b | note | Acceptance Criteria - Every 400 m2 complete a Mat test using a 1m2 cancas. The ammount of Stabilising Agent on the canvas shall be within ±0.5 kg/m2 of the specified rate.
f8c7f5f9-2077-5ff0-8abb-fec1176d53b0 | note | Verifying Document - Test Results/Photos
6b02d068-2d94-5800-a42c-38fbb216db92 | note | Frequency - Every 400 m2
49cf340a-c862-5d0d-bbf4-743ede17a0b2 | note | Inspection Type (Visual, other) - Dimensional Inspection
4cee6249-470f-5ad5-8702-53ccba59eabb | note | Inspection: Key - D
de7a40fd-0e68-5876-897d-7e585b4d4c6a | note | Inspection: By - SE
| checkpoint | 4.2.3 - Average usage test
69db5051-878d-5577-8ee2-1ab3615b4d36 | note | Standard/Specification - NZTA B/5: 2008 - 7.3
a67a06a8-5077-51a2-943c-bba07a34cf2a | note | Acceptance Criteria - Upon emptying the spreader and bulk tanker, Compare tonnes of Stabilising Agent used (from delivery docket) with measured area. Usagese shall be within ±2.5 % of the specified rate
12c3edac-159d-5c12-98f2-a583283ca55b | note | Verifying Document - Calculation with Dockets and Weights
b845eff4-4ac8-590b-9961-0e3c159de34d | note | Frequency - Upon emptying the spreader and bulk tanker
09a138af-4d58-5094-9cf2-9400023f0366 | note | Inspection Type (Visual, other) - Dimensional Inspection
89d2c230-3a3e-50a2-ac1e-de1105d38751 | note | Inspection: Key - D
4ebf7371-f59e-5d51-ac17-ae07617c0af4 | note | Inspection: By - SE
| checkpoint | 4.2.4 - Water content during compaction
22fc1983-2698-5f62-9df2-d09ec62d3c72 | note | Standard/Specification - NZTA B/5: 2008 - 7.5
07f74200-c973-5203-a0c8-e07b977afd65 | note | Acceptance Criteria - The water content during compaction shall be in the range of 90% to 100% of the material’s optimum water content. The water content tests taken prior to stabilising and the water consumed per cut shall be recorded in the production plan records.
78145596-e2a9-5be2-8236-b8d3c561a78b | note | Verifying Document - NDM Results, delivered weekly
2d7fcdf1-7794-5e98-aaf6-9212f8bcb683 | note | Frequency - 5 tests per 1000m2
e21d4a40-e079-507e-a5b6-55c6f16ef766 | note | Inspection Type (Visual, other) - Check
88753d38-4e80-5169-8077-b36209f6b784 | note | Inspection: Key - C
f6f19f7c-b370-5806-b10b-93190d640459 | note | Inspection: By - SE
| checkpoint | 4.2.5 - Control of cut depth
7be3ea67-180c-5313-8fe3-c5bcc4a833f7 | note | Standard/Specification - NZTA B/5: 2008 - 7.6.1
5cf8ec65-9b6a-5b07-ba03-ddb6bcadbb2c | note | Acceptance Criteria - The actual depth of the cut shall be physically measured at both ends of the stabilising drum at least once every 200 m along the cut length. Maximum variation from the specified depth of cut is –0 mm and +20 mm. Unless specifically allowed in the project specification, the depth of cut shall not intrude into a subgrade layer.
22cfa1b7-74d8-5046-a2d9-b031dfcbbffe | note | Verifying Document - Site Records/Photos
3510c2e5-4ed1-54cb-8296-616f7f6145e6 | note | Frequency - Each Cut
95445630-eeee-5814-b7bb-eb0496b5264a | note | Inspection Type (Visual, other) - Check
83f59a6c-7f7c-53d3-83dd-21a652f2af96 | note | Inspection: Key - C
b3053f1a-a754-5b67-98bc-fbe16bf47d9e | note | Inspection: By - SE
| checkpoint | 4.2.6 - Overlap on longitudinal joints
fedefdc5-6f28-5c70-ad50-419d675eb324 | note | Standard/Specification - NZTA B/5: 2008 - 7.6.2
f7c5051b-8114-5cb5-a3b9-17855536cb59 | note | Acceptance Criteria - To ensure complete stabilisation across the full width of the road, longitudinal joints between successive cuts shall overlap by minimum of 200 mm or half the layer thickness, whichever is the greater.
878e400a-0aa4-51a3-8c7c-b5845bc37a94 | note | Verifying Document - Site Records/Photos
80f0e09a-bbef-589f-8486-f53a96f5c983 | note | Frequency - Each Cut
6f53401b-533b-5360-bee9-a55f30cd9bd4 | note | Inspection Type (Visual, other) - Check
741f4c81-77f5-5478-bf65-01c20113a4d1 | note | Inspection: Key - C
16e03a93-a570-5843-99f0-0f8d28284966 | note | Inspection: By - SE
| checkpoint | 4.2.7 - Continuity of stabilised layer
afffdc2a-bdf9-5244-b6c1-e3e875efdfcc | note | Standard/Specification - NZTA B/5: 2008 - 7.6.3
384de8c8-2324-5713-8579-2d126dff1f93 | note | Acceptance Criteria - The exact location of the end of the cut shall be carefully marked. This mark shall coincide with the position of the centre of the mixing drum at the point at which the supply of the stabilising agent ceased. To ensure continuity of the stabilised layer, the next successive cut shall be started 1 m behind this mark.
b7beef9a-3268-5f6d-95a1-cadecbffc524 | note | Verifying Document - Site Records/Photos
0b08f505-1f06-55f2-8ec3-93d2209a524a | note | Frequency - Each Cut
f3b91639-3eb5-546f-bd1f-0af84d527a80 | note | Inspection Type (Visual, other) - Check
e99c7cb7-a0fa-5e66-a981-f45641e84931 | note | Inspection: Key - C
1243b47c-b79a-50d7-9e9a-08f98cfe0cd6 | note | Inspection: By - SE
| checkpoint | 4.2.8 - Plateau Density tests
9c2986e5-9f59-5de6-9183-07ab9ec960a0 | note | Standard/Specification - NZTA B/5: 2008 - 7.7
5894f7ec-b942-54ec-8548-7557c5e07603 | note | Acceptance Criteria - At the outset of compaction the contractor shall undertake plateau density tests for the purpose of determining the practicality of both the OWC and the MDD mix design targets, the minimum, and possibly the maximum, number and type of roller passes required to achieve the MDD for the proposed compaction plant and stiffness of lower pavement ‘anvil’ beneath the layer to be compacted.
0806a46b-8158-587b-899e-a9a957ad1a76 | note | Verifying Document - Plateau Density test
ec246258-a89e-50d0-bfa6-8a0d4194fc45 | note | Frequency - Continuous monitoring.
511fb46a-a29e-55b8-b219-f16ede65111c | note | Inspection Type (Visual, other) - Inspection
4ccc6739-0509-5b52-97cd-d87989858da9 | note | Inspection: Key - I
1be8d6fb-ef20-5da7-9a9c-3d8d0da4b227 | note | Inspection: By - SE
| checkpoint | 4.2.9 - Compaction testing
d5709ae7-458a-5298-8236-0cafbc0fc2cc | note | Standard/Specification - NZTA B/5: 2008 - 7.7.1
a8efca4c-808c-5871-a550-caf6551d7bd7 | note | Acceptance Criteria - The Degree of Compaction for Cement Treated Subbase shall have a Mean Dry Density of ≥ 98 % and a Minimum Dry Density of ≥ 95%. Compaction testing during construction of the stabilised pavement layers shall be carried out in lots.The area of a lot shall not exceed 1000 m2
89dfc105-9dbf-531d-a1b4-7f8c169bf884 | note | Verifying Document - NDM Results
cabbbf80-6dc6-5085-a11a-ee1a3bca2343 | note | Frequency - 5 tests per Lot
efed4098-94e6-556d-a9e6-13263c043992 | note | Inspection Type (Visual, other) - Check
7403241b-4bf6-5611-a069-92ed61354cb4 | note | Inspection: Key - C
ae754a14-12b4-5b10-88b2-9ede924c7104 | note | Inspection: By - SE
| checkpoint | 4.2.10 - ITS Testing
e79f2903-cc64-51ab-98e4-7484ef86faa8 | note | Standard/Specification - NZTA T/19, Contract Specification, Section 3.6.5, Appendix F
ffccd810-7b2b-5110-899c-642e1ccea1f5 | note | Acceptance Criteria - ITS testing shall be carried out in accordance with NZTA T/19. The maximum time between mixing and compaction shall be 2 hours. The ITS test ranges shall be as follows:
7ca30abc-880d-59ab-9e85-8aea916fcc05 | note | ○ Dry: 150kPa - 350 kPa
1cef5fa9-4a43-5a34-81eb-776117c8949c | note | ○ Soaked: 100kPa - 300kPa
2948cf31-f97f-5b95-94b5-b00f01c65801 | note | – The Tensile Strength Retained (TSR) shall be no less than 75%
9ec95b0c-ab9f-5cd9-ae31-5c21bc5bbc64 | note | – If results are below the target strengths then notify the Engineer immediately.
8c6715d4-f3a1-50b1-944e-9a11fe983855 | note | Verifying Document - Test Results, delivered weekly
76fe2990-37f2-56e1-9c98-30e49db41785 | note | Frequency - 2 ITS (dry) and 2 ITS (soaked) for behind the hoe sampled each day of stabilisation. Samples are to be taken from seperate locations.
2a204e19-3dc6-5a7a-a5e8-810bf447c3bb | note | Inspection Type (Visual, other) - Check
c85720f8-818c-50c1-92b4-844a978adfe6 | note | Inspection: Key - C
f5c7411b-8ab7-5c66-9927-2f377f984f24 | note | Inspection: By - SE
| checkpoint | 4.2.11 - Benkelman Beaming on Basecourse (cement modified)
0171acd1-0883-5933-930b-d1e308eaf506 | note | Standard/Specification - Contract Specification, Section 3.5.5 & Appendix F
7668d6ce-6b2b-5d7d-ac09-80a6c4114479 | note | Acceptance Criteria - 90th percentile deflection ≤ 1.0mm.
4644cc20-be73-5193-8880-d23ef17ed570 | note | ○ No single deflection > 1.1mm.
097e6e99-b632-5331-bd7c-8bbf7e738d6c | note | Verifying Document - Test report, delivered weekly
b20fe515-d609-5f84-98ef-91fbc8ea5f10 | note | Frequency - 1 per 10m each traffic lane (alternating wheel paths) or 1 test /50m2 if no clear lane
7b602984-bcd1-5fb1-9858-018265e59fae | note | Inspection Type (Visual, other) - Dimensional Inspection
2f745f6d-8d3d-5632-81ff-817cd8c4ca4d | note | Inspection: Key - C
193b6086-6afe-57b1-a9dc-3268b080a0d2 | note | Inspection: By - SE
| checkpoint | 4.2.12 - Construction Tolerances
a0f43756-5a3a-5658-a7d9-e1ab844e7804 | note | Standard/Specification - TNZ B/5: 2008 - 7.8
4e594773-20a4-5f31-a707-fe128c64addf | note | Acceptance Criteria - Basecourse where asphalt surfacing with concrete channel
3cdcefd6-9d2f-5139-8f8a-80eafe75644f | note | (i) at or close to the lip of channel –5 +5 mm
8c214878-f448-54b0-afee-d712bf8d8f46 | note | (ii) at other locations on pavement –15 +5 mm
ce03b0e4-a2c5-55db-82fc-4633a85753a7 | note | (iii) at other locations on pavement –5 +15 mm
4424ef15-913f-590a-8c0c-92eb9b7d4193 | note | Verifying Document - Survey Records
c667262c-9d04-5082-80f2-9ab2f7ee4597 | note | Frequency - On final layer
52046d0e-ad7b-58c4-b8b5-ce6fd83dcb18 | note | Inspection Type (Visual, other) - Dimensional Inspection
e9293513-53aa-5d48-a9ed-cc1cc4ccdbb2 | note | Inspection: Key - C
5953f9e7-f075-59be-ba0e-d4e3d95c3701 | note | Inspection: By - SV
| checkpoint | 4.2.13 - Surface Finish post sweeping
fe80ecf6-f991-52c9-b44d-11694ef9451e | note | Standard/Specification - TNZ B/02: 2005 - 7.8
f1ae74c0-2813-567f-8fe0-299f33d7acb0 | note | Acceptance Criteria - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept.
bd032a49-6016-5ec7-90fc-c9de2b3c6c09 | note | Verifying Document - Photos
7a62b4ab-7cec-5f97-8a7b-e66bf98f78ee | note | Frequency - Prior to sealing
d48b8225-3a4b-5f06-b1a8-a7abe758daa7 | note | Inspection Type (Visual, other) - Visual Inspection
4324aff6-df12-5ae2-98d0-d4d1147e83c9 | note | Inspection: Key - V
dc137125-de92-5b6e-bc2e-508a86d8841b | note | Inspection: By - SE
| section | 4.3 Grade 3/5 Chip Sealing
| checkpoint | 4.3.1 - Presealing Requirements
41393b5c-8e84-5b6d-9530-8cec2e1cfb61 | note | Standard/Specification - TNZ B/02: 2005 - 12, Contract Specification, Section 3.6.7
18bd21a3-db49-5431-add5-8d9b58e80448 | note | Acceptance Criteria - The seal coat shall not be applied unless the water content at each test point of the basecourse layer is such that the degree of saturation (DOS) is less than 70%.
56cbf788-3ebf-5b17-9194-d0b987ad72d4 | note | Verifying Document - NDM Report
a2c743c6-d41c-5ed1-9502-2b3767223f48 | note | Frequency - 1/10m
d0d1b3e4-0905-5246-aa7f-a733c88977bb | note | Inspection Type (Visual, other) - Check
5838e3b6-1f01-56a9-93ae-203396b128f1 | note | Inspection: Key - C
ecd6cd24-c3a1-547f-bfcc-df19bac36b15 | note | Inspection: By - SE
| checkpoint | 4.3.2 - Benkelman Beaming on Basecouse (on AP40 CTB)
eb0fd6d7-206f-59a6-9451-049fc5bacf0a | note | Standard/Specification - Contract Specification, Section 3.5.5 & Appendix F
c2f542ef-1cb4-5fa7-8c30-f18440e993ba | note | Acceptance Criteria - 90th percentile deflection ≤ 1.0mm.
c2f7795a-ee6b-5eb0-8b6b-4e5f3eebd673 | note | ○ No single deflection > 1.1mm.
75e8975a-4131-54a8-8167-88c9eb29d703 | note | Verifying Document - Test report, delivered weekly
a41540db-f185-5400-8c94-83278ff5d6c8 | note | Frequency - 1 per 10m each traffic lane (alternating wheel paths) or 1 test /50m2 if no clear lane
c42414e5-7507-5f95-987d-f26d4302ddda | note | Inspection Type (Visual, other) - Inspection
c3fff91d-592e-5a7e-abc7-2c55b291127f | note | Inspection: Key - I
ed7850a2-7b93-5a21-a943-f6059b8218ea | note | Inspection: By - SE
| checkpoint | 4.3.3 - Preseal inspection/ Subbase/Basecourse check
165fb6df-bd43-5614-a694-35f255e77a06 | note | Standard/Specification - TNZ P3 TNZ B02
8b734e14-a67f-5d30-bfe2-5e76d6897e40 | note | Acceptance Criteria - The road shall be reasonably dry before the binder is applied, and no spraying with asphaltic binder shall be carried out when the air temperature measured within the confines of the sealing course is below 10oC in the shade.
140c78de-2e3c-59f1-9777-084d50134b4f | note | ○ Visual inspection by engineer's representative
460dfc1b-87b4-5176-a8db-d5c696fb09fe | note | Verifying Document - Hold point Release, ITP Sign off
9541677e-1179-552a-a833-9c55395057f0 | note | Frequency - Prior to sealing
b031aabc-21b0-5c78-ae01-20cd30fa4514 | note | Inspection Type (Visual, other) - Check
f162c79b-e62b-5a74-a32f-f5f1e6abf9df | note | Inspection: Key - I
ba4da028-98f3-5df9-a52c-0fc85840e664 | note | Inspection: By - SE
| checkpoint | 4.3.4 - Spray Temperature
2d6ed30a-76ef-5cc5-9018-463d3e7243fe | note | Standard/Specification - TNZ P3
eead3e59-04bc-541d-bb85-8f1c7d469f70 | note | Acceptance Criteria - The emulsified asphalt may be sprayed at the temperature at which it is received from the manufacturing plant except that no emulsified asphalt shall be sprayed at a temperature in excess of 90oC or below 20oC.
86d560be-5cbf-5bcd-a8a3-376c5be05cb4 | note | Verifying Document - Sealing statement
a6c1711f-86cc-56f8-af70-73cf05c3b9d0 | note | Frequency - Prior to sealing
3ae4d9d5-a344-533e-a115-8f0a96a6c44d | note | Inspection Type (Visual, other) - Check
dfdfffee-41c7-5203-8366-359567559186 | note | Inspection: Key - I
cef81091-b8dc-53b0-bb11-3fd9b9dd4522 | note | Inspection: By - SE
| checkpoint | 4.3.5 - Chip Application
536dc5d3-6aa8-5d9f-8c4b-51a2a8d4adf4 | note | Standard/Specification - TNZ P3
639d64d7-303d-5408-8112-be9f3b325181 | note | Acceptance Criteria - All binder sprayed shall be covered with chips across the full sprayed width, apart from necessary longitudinal laps, within five minutes of spraying.
0bab0fab-49a6-5f45-941b-0c7dcb993cc7 | note | Verifying Document - Sealing statement
fd9c69d8-7a59-55ac-90e8-50dbbaa34749 | note | Frequency - For every spray run
1a0beb19-9e6f-5869-9368-e39ec3ac2777 | note | Inspection Type (Visual, other) - Check
227a1f69-99e9-5394-ae82-5b70577094f3 | note | Inspection: Key - I
4078f6fb-0e7b-5e85-bf9a-82956cfe9a3a | note | Inspection: By - SE
| checkpoint | 4.3.6 - Post Seal Inspections
3ad10fb2-a25b-59b0-9a6e-c2dc68479575 | note | Standard/Specification - TNZ P3
6b3612c1-03ff-5750-9abb-db2d83ef77d7 | note | Acceptance Criteria - The Engineer will inspect the sealcoat immediately prior to the removal of the temporary speed restriction and after final surplus chip removal is completed.
3f656ee5-a725-5ae7-a7ed-3c735d83ad98 | note | Verifying Document - Engineers Acceptance
7a11de81-0bc2-5ffe-aca7-a197002ca3da | note | Frequency - After Final Sweeping
e6461434-142d-5d88-8be8-b4f3b945182b | note | Inspection Type (Visual, other) - Visual Inspection
82dc6453-4e7b-5010-bf4c-dbdbb407c0a2 | note | Inspection: Key - H
f0755141-c96d-5bce-9916-3f36876cf1b7 | note | Inspection: By - SE, CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3.7 - Chipseal Repairs
a5a948b1-5409-5dc3-9312-f6ca53e4326e | note | Standard/Specification - TNZ P3
3162bf64-cdd6-5d6a-86df-16700739846a | note | Acceptance Criteria - The Contractor shall make no repairs without the prior approval of the Engineer for the methods to be used.
992ce976-cf4e-5c82-8e12-6f5cf2cace40 | note | Verifying Document - Approved Repair Methodology
d5a38a4e-a755-5b7a-a5dc-96276eecfb1f | note | Frequency - Prior to Repairs
232f7ebd-711f-5317-85bc-d63af1d1c878 | note | Inspection Type (Visual, other) - Review
83298693-fe30-501e-986c-d124136dd013 | note | Inspection: Key - A
b530ce4d-af38-5b86-899e-285901a41227 | note | Inspection: By - SE
| section | 4.4 Asphaltic Concrete (AC14)
| checkpoint | 4.4.1 - Preparation of Area to be Paved
bd85a623-191b-5286-8082-72c766078535 | note | Standard/Specification - NZTA M27:2020 - 9
ef53f705-d1d6-5ecf-833b-76d18bf402a4 | note | Acceptance Criteria - The surface on which the paving is to be laid shall be free from standing water, and any loose material, dust, clay or foreign matter shall be removed by sweeping. All fatty and unsuitable patches shall be removed. Depressions and other irregularities shall be patched or corrected.
26ecfa1d-3534-5a5d-817e-428985ebb7ed | note | Verifying Document - Site Notes/Photos
6c1c75ed-645e-58e0-84db-c4e3489014dd | note | Frequency - Pre Seal
cbabbb51-b5c1-5b80-b2d6-97f59805cd1b | note | Inspection Type (Visual, other) - Visual Inspection
b148d054-b7a8-54cb-aaa3-b4e177a8e9f8 | note | Inspection: Key - V
4d2a6ad2-3d52-511b-b0e0-0ef0a0df0740 | note | Inspection: By - PS
| checkpoint | 4.4.2 - Ambient Conditions for Placing
a0c15321-b6b9-5a04-a8ad-88b9447b4e33 | note | Standard/Specification - NZTA M27:2020 - 9
812e851a-fd8c-5e0a-a867-641d1dc5c719 | note | Acceptance Criteria - Wearing course asphalt shall not be placed when the pavement surface temperature is less than 10°C,
11cb05d8-8e4f-53fc-9b94-9668458b09bd | note | Verifying Document - Site Notes/ Weather report
ff35a444-34ed-5278-b521-2c0d8837c9d2 | note | Frequency - Pre Seal
23a1774e-469d-519a-9d3f-e44502b0fb52 | note | Inspection Type (Visual, other) - Check
c6a645e6-b560-558c-a598-8969a49b447c | note | Inspection: Key - R
9296ff61-23d8-54df-a5ad-7827747c4af7 | note | Inspection: By - PS
| checkpoint | 4.4.3 - Seal surface check prior to asphalt
60fc2819-8492-5ea1-896c-715671d47878 | note | Standard/Specification - as per project specification 3.7.7
0f1565e4-ae16-52a4-963d-993066882831 | note | Acceptance Criteria - Visual inspection by engineer's representative
88b646d8-4a94-5440-ac0d-fe9962edac3c | note | Verifying Document - ITP Sign off
41c52791-4f88-555d-8cff-ecb0e247566b | note | Frequency - All
89d074ee-21ce-5e2f-9121-082d95fc28ef | note | Inspection Type (Visual, other) - Visual
29450f86-5962-5a6d-8e60-ac0fc2975473 | note | Inspection: Key - H
41057b54-95a2-53d9-a902-8465174edb2d | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.4.4 - Tack coat emulsion
27c0e5f2-8df3-5ca9-8aa7-0a730571ad78 | note | Standard/Specification - Minimum Residual Bitumen of 1.2 L/m2 As per project based pavement specification
a7411259-f31c-5910-80c9-cef0f4cc2c23 | note | Acceptance Criteria - Tack coat shall be applied to the cleaned surface prior to placing asphalt. Tack coats shall be applied using a distributor. The use of a hand lance shall be minimised to ensure an even application of the tack coat.
a5d68dc2-1f10-5058-8096-9a15c64fd700 | note | Verifying Document - Run sheet, QA from Sub
378407c3-7dd1-5345-a4f3-e6118d5f9525 | note | Frequency - Entire length of pavement
77f1fa6e-16df-5cba-91a6-099f979f08bf | note | Inspection Type (Visual, other) - Visual Inspection
703f92f9-a510-503c-9e3d-1e326df5b911 | note | Inspection: Key - V
707b6084-65b0-509a-a393-b378500e404f | note | Inspection: By - SE
| checkpoint | 4.4.5 - Asphaltic Concrete - Surfacing
5cb75794-47bf-5e2d-9e02-40bce7dbd5df | note | Standard/Specification - NZTA M10 & M27, Contract Specification 3.7.15, Appendix F, Section 10.15
05210fb0-3576-538f-a551-b9aeb268bf90 | note | Acceptance Criteria - 55mm of AC14
10d3ac04-75a5-5149-bff1-67f2e8dfe4bf | note | ○ Asphalt layers less than or equal to 55mm shall be +/- 5mm from the specified design thickness.
125ec925-05cb-5ae9-817c-a06ab5290f2b | note | ○ The combined thickness of all asphalt layers should not be less than the specified total asphalt depth.
ee33e08b-5626-5c4b-b6d6-48c1f4b882ab | note | Verifying Document - Run sheet, QA from Sub
b61fc35e-4e57-5f87-966c-1579a62ddede | note | Frequency - Entire length of pavement
66b99dc4-a56b-5919-be51-565b391db8b5 | note | Inspection Type (Visual, other) - Dimensional Inspection
0b9aecbb-8cde-5828-a41b-7112b9c00caf | note | Inspection: Key - D
805208dc-9ee0-55fd-919e-c9939b8e8894 | note | Inspection: By - SE
| checkpoint | 4.4.6 - Thickness
ddd725b5-c542-551c-b774-43144033ac67 | note | Standard/Specification - Contract Specification, Section 3.7.15
ee475d01-30bb-5663-bcf0-4e9b1a6967a3 | note | Acceptance Criteria - Thickness as per design lift with +/-10mm (AC14)
788643ea-c697-59c4-8909-97b92847513f | note | Verifying Document - ITP Sign off
31e85044-96bc-5aa4-82b0-8de0e26017b7 | note | Frequency - Continuos
1fb35878-f5d9-547d-8b27-d6e82e5eecc6 | note | Inspection Type (Visual, other) - Visual
a15a7046-04bf-58e3-b3e9-827f96613996 | note | Inspection: Key - C
b29b0107-bd13-528c-96f1-dde98392d3e1 | note | Inspection: By - SE
| checkpoint | 4.4.7 - Finished surface at joints
d453e75a-95bf-5e45-a238-d1a4771a4eb3 | note | Standard/Specification - Contract Specification, Section 3.7.16
f511aa99-7200-5f61-8864-73b040cab660 | note | Acceptance Criteria - No more than 5 mm variation under a 3 m stright edge
2db45deb-0a22-5aa0-b62f-ecd68e08c623 | note | Verifying Document - ITP Sign off
66b6a6c6-760a-59ca-a596-27d5c1282422 | note | Frequency - Continuos
43ac59c2-5de5-5a63-8bc7-01b2ca70047b | note | Inspection Type (Visual, other) - Visual
68cbc332-50d0-5e33-9688-00b669123ac3 | note | Inspection: Key - C
e1304afc-2977-5925-8315-8532c633a44d | note | Inspection: By - SE
| checkpoint | 4.4.8 - Air Voids
1d0e2e9c-daaf-56be-aa09-6ad251ad41bf | note | Standard/Specification - NZTA M/10
e98c2842-35bf-58f5-bc90-3827b5267557 | note | Acceptance Criteria - The maximum and minimum air voids for each core shall be +3%/-2% from the mix design air voids.
0834a204-91a9-5ead-8d40-99ac274444c0 | note | Verifying Document - Test results, delivered weekly
0743d953-a02a-54bb-b6e9-fb5da08cb56b | note | Frequency - Continuos
260ea949-84a1-5736-a051-c86822ef1b0a | note | Inspection Type (Visual, other) - Review
0fd2a7cb-2f23-587a-8112-191f084c7b8d | note | Inspection: Key - C
bda919a9-5d68-574b-bc30-0952353bbc82 | note | Inspection: By - SE
| checkpoint | 4.4.9 - Level checks
5115460c-52fb-51b0-a1a7-f6fd3f4b0c0c | note | Standard/Specification - Survey
d1b64206-e67f-579a-a405-efcdd1c8c8fe | note | Acceptance Criteria - Thickness as per design lift with +/-10mm (AC14)
3b63ed51-b1ad-5803-b03e-545a48411907 | note | Verifying Document - As-built drawing
1f49f846-5296-598b-87fc-bc2ae70fe4f1 | note | Frequency - 1/20m full width
02bc9bf4-0327-56dd-bb82-8ce66c3a41fb | note | Inspection Type (Visual, other) - As-built
255a7dbe-c330-5647-8cb6-181702556665 | note | Inspection: Key - D
5802c83c-35d9-5b7e-9753-9a492de02e24 | note | Inspection: By - SV
| checkpoint | 4.4.10 - Line marking
dff29e4d-e2be-57ef-b547-e77e1a494837 | note | Standard/Specification - Set out
62e647d5-d497-5a32-bf09-672faeb1f142 | note | Acceptance Criteria - As per NZTA standard/ design drawings
b318c8b4-1861-57ef-a8c9-ca8ca02a27a1 | note | Verifying Document - ITP sign off/ Photos
f601fac7-0315-5e57-97ca-7fa6be42d8a7 | note | Frequency - All
f915a790-17e5-5666-b31d-3a7a9559ed85 | note | Inspection Type (Visual, other) - Visual Inspection
f834ad60-a09a-5870-8c5d-304ca401ad27 | note | Inspection: Key - V
2eee8f9d-8fdc-5207-ae35-75d0c7e6af6f | note | Inspection: By - SE
| section | FINAL INSPECTION AND HANDOVER
| checkpoint | 5.1 - Construction Record Compilation
224eba33-b1f3-5285-b628-1d137463422a | note | Inspection Point: Quality Control Activity - Upon completion of works
9ca1824c-2aca-558e-9a32-01afe6c80d1d | note | Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
d65b9a14-165f-5cf1-a859-f080c2df6bbc | note | Verifying Document - Closed-out NCR/Defects
fd687f3f-ece4-59df-8487-21dc4a271855 | note | Frequency - Post construction
de8e509a-a214-5d4d-8d69-3139605f6734 | note | Inspection Type - Review
11edbc9b-5de1-5dd4-81e6-7a010c4eb159 | note | Inspection: Key - R
e17e76b4-ac41-5a28-ba14-352f2fd70ba4 | note | Inspection: By - SE
| checkpoint | 5.2 - As-built Survey
8c97c4d4-a052-5433-a72e-e6bd88283243 | note | Inspection Point: Quality Control Activity - Upon completion of works
15be9ba7-4cc8-5c96-960d-a02c6ae69863 | note | Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
83b43b10-2063-5c01-a802-c5eda9565a44 | note | Verifying Document - As built survey record completed
af4b6f82-ba4b-50d6-a6dc-bd16367b4b69 | note | Frequency - Post construction
298793b0-2564-579e-b771-dea14e06f749 | note | Inspection Type - Review
bbcd52f1-b5e7-5b96-a7ac-0a32aa389e58 | note | Inspection: Key - R
9b438564-b468-5fc2-b057-7b02dc31ce61 | note | Inspection: By - SV
| checkpoint | 5.3 - Red-line As-built Drawings
5ff6838a-4bba-514d-bfe5-d03a3908c90e | note | Inspection Point: Quality Control Activity - Upon completion of works
1758cdce-a015-58ae-ac1a-cac1696b42c5 | note | Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar
b4d92f1d-36cb-59a4-a46d-8f5d99a450cc | note | Verifying Document - Signed As-built Drawings
53cf08c3-d86f-5437-b305-ba2c1e3b0d04 | note | Frequency - Post construction
ae43a2b5-4816-5b6d-8646-6cdde6ec9867 | note | Inspection Type - Review
7f97fd26-f6f7-5516-bbe7-284c2bb94604 | note | Inspection: Key - R
41e9a5a2-55ff-5d9f-bf3b-55da1b0d0968 | note | Inspection: By - SE, SV
| checkpoint | 5.4 - Defect, Snag and Punch List
7e80c029-ad45-51ba-a590-1686ada750fb | note | Inspection Point: Quality Control Activity - Defect, Snag and Punch List
d94b5425-1d07-537d-8e4c-b874deeb553e | note | Acceptance Criteria - Update the project Defect, Snag and Punch List Register
26d488e2-0b4f-5429-a3a3-fc78d619c13e | note | Verifying Document - Register
9c441c04-b3c2-558a-a2a7-c39eff27ba4f | note | Frequency - Post construction
023c92ad-32ee-5623-942c-3e484ad6f8d8 | note | Inspection Type - Review
110dc694-7086-526a-8208-3697b1ee3784 | note | Inspection: Key - R
4c1974b8-429e-5437-9fc9-79e615fe6f3c | note | Inspection: By - PE
| checkpoint | 5.5 - All QA documentation collated & signed-off
89ee3c80-65b5-5152-bd31-a809a665eb38 | note | Inspection Point: Quality Control Activity - Upon completion of works
bf1fa2b2-88a8-5555-94f5-ee905f814d5c | note | Acceptance Criteria - All signed and closed out
a8c58e2e-9149-56cb-9795-bb16edefd768 | note | Verifying Document - Signed off Documents
6c31713d-5163-511f-95fd-bf1e77066d63 | note | Frequency - Post construction
50027f20-f28c-5ad4-8da5-7cf4b3739301 | note | Inspection Type - Review
40047498-83cd-537d-800e-29b0c2ff1296 | note | Inspection: Key - R
b062bedd-1c09-5c92-9d04-0fb074b1ea14 | note | Inspection: By - QM