## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [6 empty] | Document # ITP-015
Revision : 1
Client: |  | Wyndham City Council |  | Construction Process: | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | K Rd |  | Kerb and Channel | Name: | Jarvis Gleeson | Name: |  |  | Name:
Contract No: |  | N400378 |  | Specifications: VicRoads Standard Specification – Section 703
|  |  |  | Structure / Component: Drainage | Signed : | J.GLEESON | Signed : |  |  | Signed :
|  |  |  | Location: | Date : | 2024-06-13 | Date : |  |  | Date :
Lot No: |  |  | Lot Details: |  |  |  |  | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | Date
1.1 | Pre-Construction Site Preperation |  | Prior to Construction | Site cleared and graded as per design; kerb line marked, and utilities identified to avoid conflicts. | Confrim site setup and markings before formwork installation | Signed ITP | IP | Site Engineer | N/A
1.2 | Formwork Installation |  | During Construction | Formwork set to specified alignment and profile, with correct height and level, secure and free of movement | Inspect formwork for stability and alignment before reinforcement. | Signed ITP | IP | Site Engineer | N/A
1.3 | Reinforcement Placement |  | During Construction | Reinforcement placed as per design, with correct cover, spacing, and securely fixed in position. | Verify reinforcement placement before concrete pour. | Signed ITP | IP | Site Engineer | N/A
1.4 | Concrete Mixing and Delivery |  | During Construction | Concrete mix complies with design specifications (e.g., strength, slump, and mix ratio); verify batching records. | Check concrete mix quality upon delivery. | Signed ITP | IP | Site Engineer | N/A
1.5 | Concrete Pouring and Compaction |  | During Construction | Concrete poured continuously and compacted to avoid air pockets; proper finish achieved on kerb face. | Inspect pour for consistent compaction and surface finish. | Signed ITP | IP | Site Engineer | N/A
1.6 | Surface Finishing |  | During Construction | Kerb surface finished to specified texture and profile; edges clean and sharp as per design. | Verify surface finish before initial curing. | Signed ITP | IP | Site Engineer | N/A
1.7 | Curing Application |  | During Construction | Apply curing compound or cover with moist material; ensure curing process follows project specifications. | Inspect curing method and ensure it is maintained for the specified period. | Signed ITP | IP | Site Engineer | N/A
1.8 | Expansion and Control Joints |  | During Construction | Expansion and control joints installed at specified intervals and filled as per design. | Check joint placement and filling before final inspection. | Signed ITP | IP | Site Engineer | N/A
1.9 | Final inspection and Tolerance Check |  | During Construction | Verify kerb alignment, elevation, and surface finish against design tolerances; no visible cracks or defects. | Final inspection before project sign off. | Signed ITP | IP | Site Engineer | N/A
COMMENTS |  | _______________________________________________________________________________________________________________________________________________________________________________________________ _______________________________________________________________________________________________________________________________________________________________________________________________
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: | [5 empty] | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent