## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [6 empty] | Document # ITP-022
Revision : 1
Client: |  | Wyndham City Council |  | Construction Process: | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | K Rd |  | General Concrete Paving | Name: | Jarvis Gleeson | Name: |  |  | Name:
Contract No: |  | N400378 |  | Specifications:
|  |  |  | Structure / Component: | Signed : | J.GLEESON | Signed : |  |  | Signed :
|  |  |  | Location: | Date : | 2024-11-08 | Date : |  |  | Date :
Lot No: |  |  | Lot Details: |  |  |  |  | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | Date
1 | Construction Works
| Pre-Construction Site Preparation |  | Prior to Construction | Site cleared, graded, and free from debris; utilities marked to avoid conflicts; area prepared as per design. | Confirm site setup and grading complete before formwork installation. | Signed ITP | HP | Site Engineer | N/A
| Formwork Installation |  | During Construction | Formwork set to correct alignment and elevation, secured, and checked for stability. | Inspect formwork for stability and dimension before reinforcement. | Signed ITP | HP | Site Engineer | N/A
| Reinforcement Placement |  | During Construction | Reinforcement placed per design specifications, with correct cover, spacing, and securely fixed in place. | Verify reinforcement placement before concrete pour. | Signed ITP | HP | Site Engineer | N/A
| Concrete Mix Verification |  | During Construction | Concrete mix complies with design specifications for strenght, slump, and mix ratio. Batch records verified. | Inspect concrete mix and batch record upon delivery. | Signed ITP | HP | Site Engineer | N/A
| Concrete Pouring and Compaction |  | During Construction | Concrete poured in sections and compacted to avoid air pockets and achieve uniform density. | Check compaction and placement during pour. | Signed ITP | HP | Site Engineer | N/A
| Surface finishing |  | During Construction | Finish applied as specified (e.g., broomed or troweled); edges cleaned and straight. | Inspect surface finish before curing. | Signed ITP | HP | Site Engineer | N/A
| Curing Application |  | During Construction | Curing applied (e.g., curing compound or covering) per specification, and maintained for the required period. | Check curing application and maintenance for specified period. | Signed ITP | HP | Site Engineer | N/A
| Joint Placement and Sealing |  | During Construction | Expansion and control joints placed at specified intervals; joints cleaned and sealed per design. | Verify joint placement and sealing before final inspection. | Signed ITP | HP | Site Engineer | N/A
| Final Inspection and Tolerance Check |  | Post Construction | Confirm alignment, elevation, surface smoothness, and joint placement within design tolerances; no visible cracks or defects. | Conduct final inspection before project sign-off. | Signed ITP | HP | Site Engineer | N/A
COMMENTS |  | ____________________________________________________________________________________________________________________________________________________________________________________ ____________________________________________________________________________________________________________________________________________________________________________________
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: | [5 empty] | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent