## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [6 empty] | Document # ITP-026
Revision : 1
Client: |  | Wyndham City Council |  | Construction Process: | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | K Rd |  | Decking Installation | Name: | Jarvis Gleeson | Name: |  |  | Name:
Contract No: |  | N400378 |  | Specifications:
|  |  |  | Structure / Component: | Signed : | J.GLEESON | Signed : |  |  | Signed :
|  |  |  | Location: | Date : | 2024-07-30 | Date : |  |  | Date :
Lot No: |  |  | Lot Details: |  |  |  |  | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent | Fulton Hogan | Date
1.1 | Pre-Construction Site Preperation |  | Prior To Construction | Site is cleared, pile locations are marked, and access for materials and equipmet is confirmed. | Confirm all setup tasks are completed before pile installation. | Signed ITP | IP | Site Engineer | N/A
1.2 | Pile Installation |  | During Construction | Proprietary piles installed to specific depths and load ratings. | Inspect piles for correct installation depth and load bearing capacity. | Signed ITP | IP | Building Surveyor
1.3 | Verification of Pile Load Capacity |  | During Construction | Piles meet load capacities of 100 kN or 200 kN as specified. | Testing required before further assembly | Signed ITP | IP | Site Engineer | N/A
1.4 | Beam and Frame Placement |  | During Construction | Position beam and frames according to layout in S010 and S011; confirm alignment and level. | Verify alignment and secure placement of primary beams before fising | Signed ITP | IP | Site Engineer | N/A
1.5 | Sub Floor Inspection |  | During Construction | Sub floor area is free of debris, properly leveled and complies with with design tolerances and specifications. | Confirm sub floor condition before continueing with flooring | Signed ITP | IP | Building Surveyor
1.6 | Connection Assembly |  | During Construction | Connections use specified bolts and welds (e.g., 6CFW); Alignment meets drawings on S020 and S021. | Inspect each connection for compliance with spacing and alignment. | Signed ITP | IP | Site Engineer | N/A
1.7 | Decking Installation |  | During Construction | Install decking panels securely with no gaps or misalignment; confirm all dimentions per design. | Final check of decking placement before apllying finishes. | Signed ITP | IP | Site Engineer | N/A
1.8 | Balustrate and Handrail Installation. |  | During Construction | Balustrate and handrails installed per design specifications; stanchion spacing does not exceed 2500mm. | Verify spacing and stability of balustrate and handrails. | Signed ITP | IP | Site Engineer | N/A
1.9 | Welding and Structural Integrity Check |  | During Construction | Welds inspected per design and safety standards; no signs of defects (e.g cracks, undercuts). | Welding inspection required before load application. | Signed ITP | IP | Site Engineer | N/A
1.1 | Finishing and Surface Protection |  | During Construction | Apply protective coatings and finishes; ensure decking and handrails are sealed as per specifications. | Check final finished before handover. | Signed ITP | IP | Site Engineer | N/A
1.11 | Final Inspection and Load Testing |  | Post Construction | Complete a final inspection and load testing to confirm structural integrity and design compliance. | Final load test and safety checks required before comissioning. | Signed ITP | IP | Building Surveyor
COMMENTS |  | _______________________________________________________________________________________________________________________________________________________________________________________ _______________________________________________________________________________________________________________________________________________________________________________________
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: | [5 empty] | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent